{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Work_plan_3gpp_250306"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Work_plan_3gpp_250306","index":0,"n_rows":9217,"n_cols":22,"rows_kept":4500,"cut":true,"hidden":false,"merged":[],"bounds":{"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0}}
["ID","Unique_ID","Name","Acronym","OutlineLevel","Release","ResourceNames","Start","Finish","%Complete","Hyperlink","Status Report","WI rapporteur name","WI rapporteur e-mail","Notes","Impacted TSs and TRs","TSG approved","PCG approved","TSG stopped","PCG stopped","Created","last modif"]
[1,0,"Work Plan 3GPP version June 6th 2025",null,1,"Rel-20",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-01-15","2015-03-05"]
[2,0,"Pre TSG#108 version",null,1,"Rel-20",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2018-03-15","NA"]
[3,0,"Next main milestones: Rel-19 St.3: Sept.25",null,1,"Rel-20",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-08-12","NA"]
[4,0,null,null,1,"Rel-20",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2017-03-03","NA"]
[5,0,"--- RELEASE 20 ---","-",1,"Rel-20",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[6,0,"Rel-20 6G Studies","-",1,"Rel-20",null,"Tue 02/04/24","Thu 11/06/26",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[7,1050110,"Study on 6G Use Cases and Service Requirements ","FS_6G_REQ",1,"Rel-20","S1","Wed 04/09/24","Tue 03/03/26",0.66,"SP-241391",null,"Xiaonan Shi, China Mobile","shixiaonan@chinamobile.com","6/3/25: 0%->25; 5/6/25: 25%->66",null,105,53,null,null,"Wed 04/09/24","Thu 05/06/25"]
[8,1060079,"Study on 6G Scenarios and Requirements ","FS_6G_RAN_Scen_Req",1,"Rel-20","RP","Sun 08/12/24","Fri 05/06/26",0.1,"RP-250810","RP-251396","CMCC ",null,"6/3/25: FCD:01/03/2026->05/06/2026; Compl:0%->5%; Stat Rep: ->RP-250266; ; 26/3/25: 38.914 added;; 3/4/25: WID:RP-243327->RP-250810; 6/6/25: Compl:5%->10%; Stat Rep: RP-250266->RP-251396; List of Impacted TS & TR updated; ",38.914000000000001,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[9,1080057,"Study on Architecture for 6G System ","FS_6G_ARC",1,"Rel-20","S2","Thu 05/06/25","Sat 06/06/26",0,"SP-250488",null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[10,0,"Rel-20 Topics involving several WG/TSGs","-",1,"Rel-20",null,"Tue 02/04/24","Thu 11/06/26",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[11,1080054,"Satellite access - Phase 4",null,1,"Rel-20",null,"Tue 02/04/24","Fri 06/06/25",1,null,null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[12,1030042,"   Study on satellite access - Phase 4 ","FS_5GSAT_Ph4",2,"Rel-20","S1","Tue 02/04/24","Thu 12/12/24",1,"SP-241824",null,"Thierry Bérisot, Novamint ","tberisot@novamint.com ","13/6/24: 0%->30; 4/9/24: 30%->60; 8/1/25: WID:SP-240495->SP-241824; 6/3/25: 60%->85; 5/6/25: 85%->100","22.887",103,52,null,null,"Wed 13/03/24","Thu 05/06/25"]
[13,1060071,"   Stage 1 for Satellite access - Phase 4","5GSAT_Ph4-REQ",2,"Rel-20","S1","Thu 05/12/24","Fri 06/06/25",1,"SP-250386",null,"Thierry Bérisot, Novamint, ","tberisot@novamint.com ","; 6/3/25: 0%->60; 26/3/25: WID:SP-241822->SP-250386; 26/3/25: FCD:03/02/2025->/25; 5/6/25: 60%->100","22.261 ",106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[14,1070011,"Study on Integration of satellite components in the 5G architecture Phase 4 ","FS_5GSAT_Ph4_ARC",1,"Rel-20","S2","Wed 26/03/25","Fri 12/12/25",0,"SP-250400",null,"Hucheng Wang (CATT) ","wanghucheng@catt.cn ",null,null,107,54,null,null,"Wed 05/03/25","NA"]
[15,1050105,"Indirect Network Sharing on Satellite Access Network ","INS_SAT",1,"Rel-20","S1","Wed 04/09/24","Mon 09/09/24",1,"SP-241393",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,"22.261 ",105,53,null,null,"Wed 04/09/24","NA"]
[16,1060072,"MPS support in 3GPP system with satellite ","MPS_Sat",1,"Rel-20","S1","Thu 05/12/24","Thu 12/12/24",1,"SP-241823",null,"Singh, Ray, Peraton Labs, ","rsingh@peratonlabs.com ","; 5/12/24: 0%->100","22.153 ",106,54,null,null,"Thu 05/12/24","Thu 05/12/24"]
[17,1080027,"Study on enhancements to application enablement for satellite access enabled 5G services ","FS_5GSAT_Ph4_APP",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250586",null,"Zhou Zhe, China Telecom, ","zhouz11@chinatelecom.cn ",null,null,null,null,null,null,"Thu 05/06/25","NA"]
[18,1080053,"Energy Efficiency as Service Criteria Phase 2 ",null,1,"Rel-20",null,"Tue 02/04/24","Fri 06/06/25",0.71,null,null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[19,1030044,"   Study on Energy Efficiency as Service Criteria Phase 2 ","FS_EnergyServ_Ph2",2,"Rel-20","S1","Tue 02/04/24","Mon 03/03/25",1,"SP-240494",null,"Laurent-WalterGoix, Nokia ","laurent-walter.goix@NOKIA.COM ","13/6/24: 0%->25; 4/9/24: 25%->55; 6/3/25: 55%->100","22.883",103,52,null,null,"Wed 13/03/24","Thu 06/03/25"]
[20,1070051,"   Stage 1 for Energy Efficiency as Service Criteria Phase 2 ","EnergyServ_Ph2-REQ",2,"Rel-20","S1","Thu 06/03/25","Fri 06/06/25",0,"SP-250385",null,"Laurent-Walter Goix, Nokia ","laurent-walter.goix@nokia.com ","; 26/3/25: WID:SP-250271->SP-250385","22.261 ",107,54,null,null,"Wed 05/03/25","Wed 26/03/25"]
[21,1070058,"Study on Energy Efficiency and Energy Saving Phase2","FS_EnergySys_Ph2",1,"Rel-20","S2","Wed 26/03/25","Fri 12/12/25",0,"SP-250417",null,"Konstantinos Samdanis (Lenovo)","ksamdanis@lenovo.com",null,null,107,54,null,null,"Wed 26/03/25","NA"]
[22,1080024,"Study on Application Enablement to support Energy Saving [Phase 2?]","FS_EnergySys_APP",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250583",null,"Yue, Jing, Ericsson ","jing.yue@ericsson.com ",null,null,null,null,null,null,"Thu 05/06/25","NA"]
[23,1080005,"Study on energy efficiency and energy saving aspects of 5G Advanced ","FS_Energy-OAM_Ph4",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250495",null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[24,1080050,"Study on Media energy consumption exposure and evaluation framework Phase 2 ","FS_Energy_Ph2_MED",1,"Rel-20","S4","Thu 05/06/25","Tue 03/03/26",0,"SP-250636",null,"Julien Lemotheux, Orange ","<julien.lemotheux@orange.com> ",null,"26.942 ",null,null,null,null,"Thu 05/06/25","NA"]
[25,1080052,"Indirect Network Sharing Phase 2 ","NetShare_Ph2",1,"Rel-20","S1","Thu 08/02/24","Wed 09/09/26",0.32,"SP-241147",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,"22.261 ",105,53,null,null,"Wed 04/09/24","NA"]
[26,1050106,"   Stage 1 for Indirect Network Sharing Phase 2 ","NetShare_Ph2-REQ",2,"Rel-20","S1","Thu 08/02/24","Mon 09/09/24",1,"SP-241147",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,null,null,null,null,null,"Thu 05/06/25","NA"]
[27,1080059,"   Stage 2 for Indirect Network Sharing Phase2 ","NetShare_Ph2-ARC",2,"Rel-20","S2","Thu 05/06/25","Wed 09/09/26",0,"SP-250482",null,null,null,null,"23.501; 23.502; 23.503 ",null,null,null,null,"Thu 05/06/25","NA"]
[28,1080055,"FRMCS Phase 6 ",null,1,"Rel-20",null,"Wed 13/03/24","Sat 06/06/26",0.51,null,null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[29,1030043,"   Study on FRMCS Phase 6 ","FS_FRMCS_Ph6",2,"Rel-20","S1","Wed 13/03/24","Mon 03/03/25",1,"SP-241392",null,"Nikolopoulou, Vassiliki, UIC, ","nikolopoulou@uic.org ","; 13/6/24: 0%->20; 4/9/24: 20%->40; 26/9/24: WID:SP-240199->SP-241392; 26/9/24: FCD:09/09/2024->/25; 6/3/25: 40%->100","22.989 ",103,52,null,null,"Wed 13/03/24","Thu 06/03/25"]
[30,1070054,"   Stage 1 for FRMCS Phase 6 ","FRMCS_Ph6-REQ",2,"Rel-20","S1","Thu 06/03/25","Fri 06/06/25",0,"SP-250277",null,"Nikolopoulou, Vassiliki, UIC ","nikolopoulou@uic.org ",null,"22.280; 22.179; 22.281 ",107,54,null,null,"Wed 05/03/25","NA"]
[31,1070031,"   Stage 2 for FRMCS Phase 6 ","FRMCS_Ph6-MC",2,"Rel-20","S6","Wed 26/03/25","Sat 06/06/26",0.35,"SP-250390",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 6/6/25: 0%->35","23.280; 23.281; 23.282; 23.379; 23.283; 23.289 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[32,1080056,"Short Message Service to Emergency Response Centre Phaase 2",null,1,"Rel-20",null,"Sun 02/02/25","Fri 12/12/25",0.14000000000000001,null,null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[33,1070052,"   Stage 1 of Phase 2 of SMS to Emergency Centre","SMS2EC_Ph2-REQ",2,"Rel-20","S1","Sun 02/02/25","Mon 03/03/25",1,"SP-250387",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ",null,"22.201 ",107,54,null,null,"Wed 05/03/25","NA"]
[34,1080062,"   Study on [phase 2 of] Short Message Service to Emergency Response Centre ","FS_SMS2EC_Ph2_ARC",2,"Rel-20","S2","Thu 05/06/25","Fri 12/12/25",0,"SP-250484",null,"TBD ",null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[35,1070025,"Study on Logging and recording of mission critical services, Phase 2 ","FS_MCLOG_Ph2",1,"Rel-20","S6","Wed 26/03/25","Tue 03/03/26",0.1,"SP-250380",null,"Vialen, Jukka, Airbus ","jukka.vialen@airbus.com ","3/4/25: 23.700-39 added;; 6/6/25: 0%->10","23.700-39",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[36,1070024,"Study on Discreet listening and monitoring of mission critical services, Phase 2 ","FS_MCDISC_Ph2",1,"Rel-20","S6","Wed 26/03/25","Tue 03/03/26",0.1,"SP-250379",null,"Vialen, Jukka, Airbus ","jukka.vialen@airbus.com ","3/4/25: 23.700-37 added;; 6/6/25: 0%->10","23.700-37",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[37,1080044,"Mission critical security for Rel-20 ","MCX20-SEC",1,"Rel-20","S3","Thu 05/06/25","Sat 06/06/26",0,"SP-250653",null,"Woodward, Tim, Motorola Solutions, Inc., ","tim.woodward@motorolasolutions.com ",null,"33.180 ",null,null,null,null,"Thu 05/06/25","NA"]
[38,1070029,"Study on Stage 2 for AI/ML service Phase 2 ","FS_AIML_App_Ph2",1,"Rel-20","S6","Wed 26/03/25","Fri 12/12/25",0.4,"SP-250384",null,"Pateromichelakis, Emmanouil (Manos), Lenovo ","epateromiche@lenovo.com ","3/4/25: 23.700-83 added;; 6/6/25: 0%->40","23.700-83",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[39,1080049,"Media aspects for AI/ML in IMS services ","AI_IMS-MED",1,"Rel-20","S4","Fri 06/06/25","Tue 03/03/26",0,"SP-250634",null,"Yip, Eric, Samsung Electronics Co., Ltd, ","eric dot yip AT samsung dot com ",null,"26.114; 26.264 ",null,null,null,null,"Thu 05/06/25","NA"]
[40,0,"Rel-20 Other topics","-",1,"Rel-20",null,"Tue 02/04/24","Thu 11/06/26",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[41,1060070,"Vehicle-Mounted Relays Phase3 ","VMR_Ph3",1,"Rel-20","S1","Thu 05/12/24","Thu 12/12/24",1,"SP-241821",null,"Qing Wan, CATT, ","wanqing1@cictmobile.com ","; 5/12/24: 0%->100","22.261 ",106,54,null,null,"Thu 05/12/24","Thu 05/12/24"]
[42,1050107,"Resident Phase 2 ","Resident_Ph2",1,"Rel-20","S1","Wed 04/09/24","Mon 09/09/24",1,"SP-241149",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,"22.261 ",105,53,null,null,"Wed 04/09/24","NA"]
[43,1080058,"5G ProSe Phase 4 ","ProSe_Ph4-ARC",1,"Rel-20","S2","Thu 05/06/25","Wed 09/09/26",0,"SP-250483",null,"TBD ",null,null,"23.304 ",null,null,null,null,"Thu 05/06/25","NA"]
[44,1080045,"Study on Transitioning to Post Quantum Cryptography in 3GPP ","FS_CryptoPQC",1,"Rel-20","S3","Thu 05/06/25","Sat 06/06/26",0,"SP-250654",null,"TBD ",null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[45,1080047,"CPAS specific requirement ","CPAS-REQ",1,"Rel-20","S1","Thu 05/06/25","Fri 06/06/25",1,"SP-250627",null,"Pengtai Qin ","qinpengtai@chinamobile.com ","; 5/6/25: 0%->100","23.304 ",null,null,null,null,"Thu 05/06/25","Thu 05/06/25"]
[46,1080042,"Security Assurance Specification for 5G-Advanced ","SCAS_5GA",1,"Rel-20","S3","Thu 05/06/25","Wed 09/09/26",0,"SP-250650",null,"TBA ",null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[47,1080041,"Security related Events Handling ","SECHAND",1,"Rel-20","S3","Thu 05/06/25","Fri 12/12/25",0,"SP-250648",null,"TBA ",null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[48,1080029,"Guidelines for 3GPP Application Enablement usage ","AppEnable_EXT",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250588",null,"David Artuñedo, Telefónica ","david.artunedoguillen@telefonica.com ",null,null,null,null,null,null,"Thu 05/06/25","NA"]
[49,1080026,"Study of CAPIF Phase 4 ","FS_CAPIF_Ph4",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250585",null,"Niranth Amogh, Nokia, ","niranth.amogh@nokia.com ",null,null,null,null,null,null,"Thu 05/06/25","NA"]
[50,1080025,"Study on Application user consent ","FS_APCOT",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250584",null,"Cristina Badulescu ","cristina.badulescu@ericsson.com ",null,null,null,null,null,null,"Thu 05/06/25","NA"]
[51,1080060,"Study on system architecture for Phae 3 of NG RTC","FS_NG_RTC_Ph3_ARC",1,"Rel-20","S2","Thu 05/06/25","Tue 03/03/26",0,"SP-250485",null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[52,1080061,"Study on MPS Enhancements for IoT ","FS_MPS_IOT_ARC",1,"Rel-20","S2","Thu 05/06/25","Fri 12/12/25",0,"SP-250486",null,"TBD @ SA ",null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[53,1080063,"Study on Architecture support of Ambient power-enabled Internet of Things - Phase 2 ","FS_AmbientIoT_Ph2_ARC",1,"Rel-20","S2","Thu 05/06/25","Tue 03/03/26",0,"SP-250487",null,"To be added. ",null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[54,1080023,"Study on application enablement for Ambient IoT [Phase 2? ] services ","FS_AmbientIoT_APP",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250582",null,"Liping Wu, CATT ","wuliping@cictmobile.com ",null,null,null,null,null,null,"Thu 05/06/25","NA"]
[55,1050034,"Study on Service Enabler Architecture Layer (SEAL) Phase 4","FS_SEAL_Ph4",1,"Rel-20","S6","Wed 04/09/24","Fri 12/12/25",0.75,"SP-250374",null,"Yang, Yanmei, Huawei Technologies Co.,Ltd. ","yangyanmei@huawei.com","5/12/24: 0%->20; 6/3/25: 20%->40. Moved from Rel-19; 26/3/25: WID:SP-241375->SP-250374; 26/3/25: FCD:12/12/2024->12/25; 6/6/25: 40%->75",null,105,53,null,null,"Wed 04/09/24","Fri 06/06/25"]
[56,1070053,"Stage 1 for Ambient listening enhancements including pause and resume in MCS ","ALPR-REQ",1,"Rel-20","S1","Tue 11/02/25","Mon 03/03/25",1,"SP-250275",null,"S. (Ram) Ramanan ","Sivasubramaniam.ramanan@homeoffice.gov.uk ","; 26/3/25: 0%->100","22.179; 22.280 ",107,54,null,null,"Wed 05/03/25","Wed 26/03/25"]
[57,1070026,"Study on Application enabler for XR Services Phase 3 ","FS_XRM_Ph3_APP",1,"Rel-20","S6","Wed 26/03/25","Fri 12/12/25",0.35,"SP-250381",null,"Zheng, Shaowen, China Mobile ","zhengshaowen@chinamobile.com ","3/4/25: 23.700-51 added;; 6/6/25: 0%->35","23.700-51",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[58,1070027,"Study on SEAL data delivery Phase 3 ","FS_SEALDD_Ph3",1,"Rel-20","S6","Wed 26/03/25","Fri 12/12/25",0.3,"SP-250382",null,"Ge, Cuili, Huawei ","gecuili@huawei.com ","3/4/25: 23.700-52 added;; 6/6/25: 0%->30","23.700-52",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[59,1070028,"Study on Stage 2 for MMTel Phase 2 ","FS_MMTel_Ph2_APP",1,"Rel-20","S6","Wed 26/03/25","Tue 03/03/26",0.3,"SP-250383",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","3/4/25: 23.700-57 added;; 6/6/25: 0%->30","23.700-57",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[60,1070030,"Stage 2 for Mission Critical Services for UE-to-UE and UE-to-Network over multi-hop relay ","MultiHop-MC",1,"Rel-20","S6","Wed 26/03/25","Tue 03/03/26",0,"SP-250389",null,"Lipford, Mark, FirstNet Authority ","mark.lipford@firstnet.gov ","; 6/6/25: 0%->75","23.289 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[61,1070032,"Stage 2 for Enhanced Mission Critical Services Architecture Phase 2 ","enhMC_Ph2-MC",1,"Rel-20","S6","Wed 26/03/25","Sat 06/06/26",0.15,"SP-250391",null,"Negalaguli, Harish, Motorola Solutions ","harish.negalaguli@motorolasolutions.com ","; 6/6/25: 0%->15","23.280; 23.379; 23.281; 23.282; 23.283; 23.289 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[62,1070033,"Stage 2 for mobile metaverse services Phase 2 ","Metaverse_Ph2-APP",1,"Rel-20","S6","Wed 26/03/25","Fri 12/12/25",0.45,"SP-250392",null,"Ramamoorthy, Arunprasath (Arun), Samsung, ","arun.prasath@samsung.com ","; 6/6/25: 0%->45","23.437; 23.438 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[63,1070055,"Study on Ultra Low Bitrate Speech Codec ","FS_ULBC",1,"Rel-20","S4","Wed 26/03/25","Sat 06/06/26",0.1,"SP-250378",null,"Xu Jiayi, China Mobile ","xujiayi@chinamobile.com ","3/4/25: 26.940 added;; 5/6/25: 0%->10","26.940",107,54,null,null,"Wed 05/03/25","Thu 05/06/25"]
[64,1070013,"Study on Core Network Enhanced Support for Artificial Intelligence (AI) / Machine Learning (ML) Phase 2 ","FS_AIML_CN_Ph2",1,"Rel-20","S2","Wed 26/03/25","Fri 12/12/25",0,"SP-250413",null,"Xiaobo Wu, vivo ","xiaobo.wu@vivo.com ",null,null,107,54,null,null,"Wed 05/03/25","NA"]
[65,1070012,"Study on Stage 2 for Integrated Sensing and Communication ","FS_Sensing_ARC",1,"Rel-20","S2","Wed 26/03/25","Fri 12/12/25",0,"SP-250401",null,"Jianning LIU, Xiaomi ","liujianning@xiaomi.com ",null,null,107,54,null,null,"Wed 05/03/25","NA"]
[66,1080028,"Study on use of Sensing results for Vertical Applications ","FS_Sensing_APP",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250587",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,null,null,null,null,null,"Thu 05/06/25","NA"]
[67,1050108,"Combined QoS configuration and monitoring ","CombQoS",1,"Rel-20","S1","Wed 04/09/24","Mon 09/09/24",1,"SP-241150",null,"Yansheng Liu, ZTE ","liu.yansheng@zte.com.cn ",null,"22.261 ",105,53,null,null,"Wed 04/09/24","NA"]
[68,1050109,"Legacy Residential Gateway Supporting 5G LAN-type Service ","LegacyRG_5GLAN",1,"Rel-20","S1","Wed 04/09/24","Mon 09/09/24",1,"SP-241151",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ",null,"22.261 ",105,53,null,null,"Wed 04/09/24","NA"]
[69,1050111,"Exposure for Virtual Network information and capability ","VNExposure",1,"Rel-20","S1","Wed 04/09/24","Mon 09/09/24",1,"SP-241153",null,"Pengtai Qin, China Mobile ","qinpengtai@chinamobile.com ",null,"22.261 ",105,53,null,null,"Wed 04/09/24","NA"]
[70,1040011,"Lawful Interception Rel-20 ","LI20",1,"Rel-20","S3LI","Thu 06/03/25","Wed 03/03/27",0,"SP-250388",null,"Koen Jaspers, PIDS, ","k.b.jaspers@minjenv.nl ","; 26/3/25: WID:SP-241012->SP-250388","33.107; 33.108; 33.126; 33.127; 33.128; 33.928 ",104,53,null,null,"Wed 12/06/24","Wed 26/03/25"]
[71,0,"Rel-20 Miscellaneous OAM&Charging",null,1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,null,null,null,null,null,null,null,null,null,null,"Thu 07/12/23","NA"]
[72,1080006,"Study on intent driven management services for mobile network phase 4 ","FS_IDMS_MN_Ph4",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250496",null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[73,1080007,"Study on Management Data Analytics (MDA) phase 4 ","FS_eMDAS_Ph4",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250497",null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[74,1080008,"Study on Service Based Management Architecture enhancement phase 4 ","FS_SBMA_Ph4",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250498",null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[75,1080009,"Study on Enhanced exposure of management services ","FS_EnExpo",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250499",null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[76,1080010,"Study for Data management phase 3 ","FS_MADCOL_Ph3",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250500",null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[77,1080011,"Study on management aspects of Network Digital Twins phase 2 ","FS_NDT_Ph2",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250501",null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[78,1080012,"Study on AI/ML management phase 3 ","FS_AIML_MGT_Ph3",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250502",null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[79,1080013,"Study on Closed Control Loop Management phase 2 ","FS_CCLM_Ph2",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250503",null,null,null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[80,1080015,"5G performance measurements/KPIs and Trace/MDT/QoE ","PM_KPI_Trace_MDT_QoE-OAM",1,"Rel-20","S5","Thu 05/06/25","Wed 09/09/26",0,"SP-250505",null,null,null,null,"28.552; 28.554; 28.532; 28.558; 32.404; 32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.622; 28.623; 28.541 ",null,null,null,null,"Thu 05/06/25","NA"]
[81,1080017,"Management Aspects related to NWDAF phase 3 ","NWDAF-OAM_Ph3",1,"Rel-20","S5","Thu 05/06/25","Sat 06/06/26",0,"SP-250507",null,null,null,null,"28.541; 28.552; 28.554 ",null,null,null,null,"Thu 05/06/25","NA"]
[82,1080018,"5G Advanced NRM features phase 4 ","AdNRM_Ph4",1,"Rel-20","S5","Thu 05/06/25","Sat 12/12/26",0,"SP-250508",null,null,null,null,"28.540; 28.541; 28.622; 28.623; 32.160 ",null,null,null,null,"Thu 05/06/25","NA"]
[83,1089999,"(Small) Technical Enhancements and Improvements for Rel-20","TEI20",1,"Rel-20",null,"Thu 05/06/25","Sat 12/12/26",0,null,null,null,null,null,null,92,47,null,null,"Mon 15/06/15","Mon 15/06/15"]
[84,0,"--- RELEASE 19 ---","-",1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[85,0,"Rel-19 Energy Efficiency, Energy Saving","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[86,1020060,"Energy Efficiency as Service Criteria ","EnergyServ",1,"Rel-19",null,"Thu 02/06/22","Tue 09/09/25",0.88,"SP-230520",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 6/9/23: 0%->75; 8/12/23: 75%->100","22.261 ",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[87,960019,"   Study on Energy Efficiency as service criteria ","FS_EnergyServ",2,"Rel-19","S1","Thu 02/06/22","Sat 09/09/23",1,"SP-230235",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","13/7/22: 22.882 added;; 9/9/22: 0%->10; 10/12/22: FCD:10/03/2023->06/23; 10/12/22: 10%->40; 16/3/23: WID:SP-220446->SP-230235; 17/3/23: 40%->70; 8/6/23: 70%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95; 8/12/23: 95%->100","22.882",96,49,null,null,"Thu 02/06/22","Fri 08/12/23"]
[88,1000033,"   Stage 1 of Energy Efficiency as Service Criteria ","EnergyServ",2,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230520",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 6/9/23: 0%->75; 8/12/23: 75%->100","22.261 ",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[89,1040018,"   Charging Aspects for Energy Efficiency of Network Slice","EnergySys_CH",2,"Rel-19","S5","Wed 12/06/24","Fri 06/06/25",1,"SP-250124",null,"YiMeng, DENG, Huawei, ","dengyimeng@huawei.com ","; 4/9/24: 0%->45; 6/3/25: 45%->100; 26/3/25: WID:SP-241003->SP-250124; 26/3/25: FCD:12/12/2024->6/6/25. Name changed from \"Charging Aspects for Energy Efficiency of 5G\"","32.240; 28.201; 28.202; 32.291; 32.298 ",104,53,null,null,"Wed 12/06/24","Wed 26/03/25"]
[90,1010029,"   Study on Energy Efficiency and Energy Saving","FS_EnergySys",2,"Rel-19","S2","Sat 09/09/23","Thu 06/06/24",1,"SP-231391",null,"Jungshin Park (Samsung)","shin02.park@samsung.com","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-66 added;; 8/12/23: 0%->15; 4/1/24: 28.880 added;; 14/3/24: 15%->55; 13/6/24: 55%->100; 4/9/24: 99%->100","SP-231192; 23.700-66; 28.880",101,51,null,null,"Wed 20/09/23","Wed 04/09/24"]
[91,1050112,"   Energy Efficiency and Energy Saving ","EnergySys",2,"Rel-19","S2","Wed 04/09/24","Thu 12/12/24",1,"SP-250069",null,"Primary Rapporteur: Jungshin Park (Samsung) ","shin02.park@samsung.com ","; 5/12/24: 0%->70; 6/3/25: 70%->100; 26/3/25: WID:SP-241388->SP-250069","23.501; 23.502; 23.503 ",105,53,null,null,"Wed 04/09/24","Wed 26/03/25"]
[92,1070002,"   CT aspects of energy efficiency and energy saving","EnergySys",2,"Rel-19","C3","Mon 03/03/25","Tue 09/09/25",0.52,"CP-250247",null,"Suh, Kyungjoo(Grace), Samsung","joo.suh@samsung.com",null,"29.508,29.513,29.522,29.122,29.519,29.510,29.503,29.504,29.518",105,53,null,null,"Wed 04/09/24","Thu 05/12/24"]
[93,1070034,"      CT3 aspects of energy efficiency and energy saving","EnergySys",3,"Rel-19","C3","Mon 03/03/25","Tue 09/09/25",0.75,"CP-250247",null,"Suh, Kyungjoo(Grace), Samsung","joo.suh@samsung.com",null,"29.508,29.513,29.522,29.122,29.519,29.510,29.503,29.504,29.518",105,53,null,null,"Wed 04/09/24","Thu 05/12/24"]
[94,1070035,"      CT4 aspects of energy efficiency and energy saving","EnergySys",3,"Rel-19","C4","Mon 03/03/25","Tue 09/09/25",0.75,"CP-250247",null,"Suh, Kyungjoo(Grace), Samsung","joo.suh@samsung.com",null,"29.508,29.513,29.522,29.122,29.519,29.510,29.503,29.504,29.518",105,53,null,null,"Wed 04/09/24","Thu 05/12/24"]
[95,1020021,"   Study on energy efficiency and energy saving aspects of 5G networks and services ","FS_Energy_OAM_Ph3",2,"Rel-19","S5","Fri 08/12/23","Thu 12/12/24",1,"SP-241568",null,"Jean-Michel Cornily (Huawei)","jean.michel.cornily@huawei.com","4/1/24: 28.866 added;; 14/3/24: 0%->10; 13/6/24: 10%->25; 4/9/24: 25%->60; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 60%->100; 8/1/25: WID:SP-231723->SP-241568","28.866",102,52,null,null,"Thu 07/12/23","Wed 08/01/25"]
[96,1030038,"   Study on security aspects of energy saving in 5G ","FS_Energy_Sec",2,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240512",null,"Bo Bjerrum ","bo.bjerrum@nokia.com ","3/4/24: 33.766 added;; 13/6/24: 0%->30; 5/9/24: 30%->70; 5/12/24: 70%->90; 6/3/25: 90%->100; 5/6/25: 100%->100","33.766",103,52,null,null,"Thu 14/03/24","Thu 05/06/25"]
[97,1060007,"   Energy efficiency and energy saving aspects of 5G networks and services ","Energy_OAM_Ph3",2,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.7,"SP-241940",null,"Jean-Michel Cornily (Huawei)","jean.michel.cornily@huawei.com ","; 6/3/25: 0%->20; 6/6/25: 20%->70","28.310; 28.622; 28.623; 28.541; 28.554; 28.104 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[98,1020095,"Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.52,"RP-250343",null,"Ericsson ",null,"2/4/24: WID:RP-234065->RP-240170; 23/7/24: WID:RP-240170->RP-241650; 26/9/24: WID:RP-241650->RP-242354; 3/4/25: WID:RP-242354->RP-250343",null,102,52,null,null,"Tue 02/01/24","Thu 03/04/25"]
[99,1021095,"   Core part: Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh-Core",2,"Rel-19","R1","Wed 13/12/23","Tue 09/09/25",0.9,"RP-250343","RP-251677","Ajit Nimbalker, Ericsson","Ajit.Nimbalker@ericsson.com","14/3/24: Compl:0%->5%; Stat Rep: ->RP-240169; Rapporteur: Ericsson->Ajit Nimbalker, Ericsson; Rap eMail: ->Ajit.Nimbalker@ericsson.com; ; 13/6/24: Compl:5%->25%; Stat Rep: RP-240169->RP-241182; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:25%->35%; Stat Re",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[100,1022095,"   Perf. part: Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0.1,"RP-250343","RP-251677","Ajit Nimbalker, Ericsson","Ajit.Nimbalker@ericsson.com","14/3/24: Stat Rep: ->RP-240169; Rapporteur: Ericsson->Ajit Nimbalker, Ericsson; Rap eMail: ->Ajit.Nimbalker@ericsson.com; ; 13/6/24: Stat Rep: RP-240169->RP-241182; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241182->RP-241866; ; 6/12/24: FCD:03/03",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[101,1030004,"Study on Media enerGy consumption exposuRE and EvaluatioN framework ","FS_MediaEnergyGREEN",1,"Rel-19","S4","Tue 02/04/24","Mon 03/03/25",1,"SP-240481",null,"Julien Lemotheux, Orange, ","julien.lemotheux@orange.com ","14/5/24: 26.942 added;; 13/6/24: 0%->15; 4/9/24: 15%->30; 5/12/24: 30%->60; 6/3/25: 60%->100","26.942",103,52,null,null,"Wed 13/03/24","Thu 06/03/25"]
[102,1020094,"Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.5,"RP-241824",null,"vivo ",null,"2/4/24: WID:RP-234056->RP-240801; 26/9/24: WID:RP-240801->RP-241824; 26/9/24: 38.774 added;","38.774",102,52,null,null,"Tue 02/01/24","Thu 26/09/24"]
[103,1021094,"   Core part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS-Core",2,"Rel-19","R1","Wed 13/12/23","Tue 09/09/25",0.9,"RP-241824","RP-251199","Xueming Pan, vivo","panxueming@vivo.com","14/3/24: Compl:0%->8%; Stat Rep: ->RP-240134; Rapporteur: vivo->Xueming Pan, vivo; Rap eMail: ->panxueming@vivo.com; ; 13/6/24: Compl:8%->20%; Stat Rep: RP-240134->RP-241039; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:20%->30%; Stat Rep: RP-241039->RP-24",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[104,1022094,"   Perf. part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0.05,"RP-241824","RP-251199","Xueming Pan, vivo","panxueming@vivo.com","14/3/24: Stat Rep: ->RP-240134; Rapporteur: vivo->Xueming Pan, vivo; Rap eMail: ->panxueming@vivo.com; ; 13/6/24: Stat Rep: RP-240134->RP-241039; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241039->RP-241822; ; 6/12/24: FCD:03/03/2025->03/03/2026; ",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[105,0,"Rel-19 Artificial Intelligence (AI)/Machine Learning (ML)","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[106,1060078,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface Phase 2 ","FS_NR_AIML_air_Ph2",1,"Rel-19","R1","Mon 14/10/24","Tue 09/09/25",0.9,"RP-250308","RP-251184","Qualcomm ",null,"6/3/25: FCD:07/09/2025->09/09/2025; Compl:0%->50%; Stat Rep: ->RP-250307; ; 3/4/25: WID:RP-243245->RP-250308; 6/6/25: Compl:50%->90%; Stat Rep: RP-250307->RP-251184; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[107,1040084,"Study on 3GPP AI/ML Consistency Alignment","FS_AIML_CAL",1,"Rel-19","SP","Sun 06/10/24","Fri 06/06/25",0,"SP-241368",null,"Johannes Achter, Magenta",null,"26/9/24: WID:SP-240970->SP-241368",null,104,53,null,null,"Thu 20/06/24","Thu 26/09/24"]
[108,950008,"Study on AI/ML Model Transfer Phase2 ","FS_AIML_MT_Ph2",1,"Rel-19","S1","Thu 10/03/22","Sat 09/09/23",1,"SP-220439",null,"Yang Xu, OPPO ","xuyang@oppo.com ","5/4/22: 22.875 added;; 4/6/22: 0%->15; 21/6/22: WID:SP-220083->SP-220439. FS_AIML_Ph2->FS_AIML_MT_Ph2; 13/7/22: 22.876 added;; 10/12/22: 15%->50; 10/12/22: FCD:12/12/2022->06/23; 17/3/23: 50%->75; 8/6/23: 75%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 95","22.875; 22.876",95,48,null,null,"Thu 10/03/22","Wed 06/09/23"]
[109,950011,"Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media ","FS_AI4Media",1,"Rel-19","S4","Sat 12/03/22","Fri 06/06/25",1,"SP-220328",null,"Eric Yip, Samsung ","eric.yip@samsung.com ","5/4/22: 26.927 added;; 4/6/22: 0%->10; 12/9/22: 10%->15; 12/9/22: FCD:12/03/2022->12/23; 11/12/22: 15%->20; 17/3/23: 20%->25; 8/6/23: 25%->35; 8/6/23: FCD:12/12/2023->/24; 7/9/23: 35%->40; 21/9/23: 26.847 added;; 8/12/23: 40%->50; 14/3/24: 50%->60; 14/...","26.927; 26.847",95,48,null,null,"Thu 10/03/22","Thu 05/06/25"]
[110,1000030,"AI/ML Model Transfer Phase 2 ","AIML_MT_Ph2",1,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230514",null,"Yang Xu, OPPO ","xuyang<at>oppo.com ","; 6/9/23: 0%->80; 8/12/23: 80%->100","22.261 ",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[111,1050047,"Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",1,"Rel-19",null,"Wed 12/06/24","Tue 09/09/25",0.64,"SP-240991",null,"Xiaobo Wu, vivo ","(xiaobo.wu@vivo.com) ",null,"23.288; 23.501; 23.502; 23.503; 23.273 ",105,53,null,null,"Wed 12/06/24","NA"]
[112,1040033,"   Stage 2 of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",2,"Rel-19","S2","Wed 12/06/24","Thu 17/10/24",0.99,"SP-240991",null,"Xiaobo Wu, vivo ","(xiaobo.wu@vivo.com) ","; 4/9/24: 0%->15; 5/12/24: 15%->85; 6/3/25: 85%->98; 5/6/25: 98%->99","23.288; 23.501; 23.502; 23.503; 23.273 ",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[113,1050014,"   CT aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.48,"CP-250250",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com",null,"29.508,29.513,29.517,29.520,29.522,29.552,29.574,29.575,29.576,29.591,24.080,29.503,29.510,29.518,29.572",105,53,null,null,"Wed 12/06/24","NA"]
[114,1050048,"      CT3 aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.7,"CP-250250",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[115,1050049,"      CT4 aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.7,"CP-250250",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","; 26/3/25: 29.570 added;","29.570",105,53,null,null,"Wed 12/06/24","Wed 26/03/25"]
[116,1060059,"   Security aspects of Core Network Enhanced Support for AIML ","AIML_CN_SEC",2,"Rel-19","S3","Thu 05/12/24","Fri 06/06/25",1,"SP-241957",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 6/3/25: 0%->80; 5/6/25: 80%->100","33.501 ",106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[117,1050044,"Application enablement for AI/ML services ","AIML_App",1,"Rel-19",null,"Tue 16/07/24","Tue 09/09/25",0.49,"SP-241008",null,"Pateromichelakis, Emmanouil (Manos), ","epateromiche@lenovo.com ",null,"23.436; 23.434; 23.558 ",105,53,null,null,"Wed 12/06/24","NA"]
[118,1040075,"   Stage 2 of Application enablement for AI/ML services ","AIML_App",2,"Rel-19","S6","Tue 16/07/24","Thu 12/12/24",1,"SP-241008",null,"Pateromichelakis, Emmanouil (Manos), ","epateromiche@lenovo.com ","; 4/9/24: 0%->40; 26/9/24: 23.482 added;; 5/12/24: 40%->100","23.436; 23.434; 23.558 ; 23.482",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[119,1050024,"   CT aspects of Application enablement for AI/ML services ","AIML_App",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.42,"CP-243310",null,"Atarius, Roozbeh (Lenovo)","ratarius@motorola.com",null,"24.559, 29.549, 29.558, 24.559, 29.549, 29.558",105,53,null,null,"Wed 12/06/24","NA"]
[120,1050045,"      CT1 aspects of Application enablement for AI/ML services ","AIML_App",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.6,"CP-243310",null,"Atarius, Roozbeh (Lenovo)","ratarius@motorola.com","; 26/9/24: 24.560 added;",null,105,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[121,1050046,"      CT3 aspects of Application enablement for AI/ML services ","AIML_App",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.6,"CP-243310",null,"Atarius, Roozbeh (Lenovo)","ratarius@motorola.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[122,1060011,"AI/ML Management Phase 2 ","AIML_MGT_Ph2",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.52,"SP-241944",null,"Hassan Al-Kanani (NEC)","Hassan.Alkanani@EMEA.NEC.COM","; 6/3/25: 0%->15; 6/6/25: 15%->52","28.105; 28.552; 28.554; 28.541 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[123,1020068,"Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","FS_AIML_CN",1,"Rel-19","S2","Thu 04/01/24","Thu 06/06/24",1,"SP-241936",null,"Xiaobo Wu, vivo ","xiaobo.wu@vivo.com) ","14/3/24: 0%->25; 13/6/24: 25%->100; 26/9/24: WID:SP-231800->SP-241383; 8/1/25: WID:SP-241383->SP-241936; 6/3/25: 100%->100",null,102,52,null,null,"Wed 03/01/24","Thu 06/03/25"]
[124,1030035,"Study on security aspects of Core Network Enhanced Support for AIML ","FS_AIML_CN_SEC",1,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240509",null,"Chang Liu, ","liuchangyjy@chinamobile.com ","3/4/24: 33.784 added;; 13/6/24: 0%->35; 5/9/24: 35%->60; 5/12/24: 60%->100; 6/3/25: 100%->100; 5/6/25: 100%->100","33.784",103,52,null,null,"Thu 14/03/24","Thu 05/06/25"]
[125,1020007,"Study on AI/ML management - phase 2 ","FS_AIML_MGT_Ph2",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-241567",null,"Yizhi Yao (Intel) ","yizhi.yao@intel.com ","13/6/24: 0%->19; 16/7/24: WID:SP-231780->SP-240965; 4/9/24: 19%->55; 4/9/24: FCD:09/09/2024->12/24; 26/9/24: 28.858 added;; 5/12/24: 55%->100; 8/1/25: WID:SP-240965->SP-241567; 6/6/25: 100%->100","28.858",102,52,null,null,"Thu 07/12/23","Fri 06/06/25"]
[126,1010005,"Study on application layer support for AI/ML services ","FS_AIMLAPP",1,"Rel-19","S6","Thu 07/09/23","Mon 09/09/24",1,"SP-231182",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","8/12/23: 0%->35; 4/1/24: 23.700-82 added;; 14/3/24: 35%->55; 13/6/24: 55%->95; 4/9/24: 95%->100","23.700-82",101,51,null,null,"Thu 07/09/23","Wed 04/09/24"]
[127,1020083,"Study on enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN ","FS_NR_AIML_NGRAN_enh",1,"Rel-19","R3","Wed 13/12/23","Mon 09/09/24",1,"RP-240323","RP-241791","ZTE ",null,"14/3/24: FCD:06/06/2024->/24; 2/4/24: WID:RP-234054->RP-240323; 3/4/24: 38.743 added;; 13/6/24: Compl:0%->80%; Stat Rep: ->RP-241097; ; 4/9/24: FCD:09/09/2024->24/09/2024; Compl:80%->100%; Stat Rep: RP-241097->RP-241791; ","38.743",102,52,null,null,"Tue 02/01/24","Wed 04/09/24"]
[128,1020084,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for mobility in NR ","FS_NR_AIML_Mob",1,"Rel-19","R2","Thu 07/03/19","Tue 09/09/25",0.9,"RP-242393","RP-250970","Zhongda Du, OPPO","duzhongda@oppo.com","14/3/24: FCD:28/05/2021->12/12/2024; Stat Rep: ->RP-240083; Rapporteur: Oppo->Zhongda Du, OPPO; Rap eMail: ->duzhongda@oppo.com; ; 2/4/24: WID:RP-234055->RP-240082; 3/4/24: 38.744 added;; 4/9/24: FCD:12/12/2024->25/09/2024; Compl:0%->38%; Stat Rep: RP-...",38.744,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[129,1020093,"Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.5,"RP-243244",null,"Qualcomm ",null,"2/4/24: WID:RP-234039->RP-240774; 26/9/24: WID:RP-240774->RP-242399; 24/1/25: WID:RP-242399->RP-243244",null,102,52,null,null,"Tue 02/01/24","Fri 24/01/25"]
[130,1021093,"   Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air-Core",2,"Rel-19","R1","Wed 13/12/23","Tue 09/09/25",0.85,"RP-250792","RP-251185","Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson","juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com","14/3/24: Compl:0%->5%; Stat Rep: ->RP-240499; Rapporteur: Qualcomm->Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson; Rap eMail: ->juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsso...",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[131,1022093,"   Perf. part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0.1,"RP-250792","RP-251185","Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson","juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com","14/3/24: Stat Rep: ->RP-240499; Rapporteur: Qualcomm->Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson; Rap eMail: ->juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com; ; 13/6/...",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[132,1050124,"Enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN ","NR_AIML_NGRAN_enh",1,"Rel-19","R3","Mon 09/09/24","Tue 09/09/25",0.8,"RP-250326",null,"ZTE ",null,"3/4/25: WID:RP-242385->RP-250326",null,105,53,null,null,"Thu 26/09/24","Thu 03/04/25"]
[133,1051124,"   Core part: Enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN ","NR_AIML_NGRAN_enh-Core",2,"Rel-19","R3","Mon 09/09/24","Tue 09/09/25",0.8,"RP-250326","RP-251246","ZTE ",null,"6/12/24: Compl:0%->30%; Stat Rep: ->RP-242503; ; 6/3/25: FCD:20/05/2025->09/09/2025; Compl:30%->50%; Stat Rep: RP-242503->RP-250327; ; 6/6/25: Compl:50%->80%; Stat Rep: RP-250327->RP-251246; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[134,0,"Rel-19 Ambient power-enabled Internet of Things ","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[135,1020055,"Ambient power-enabled Internet of Things ","AmbientIoT",1,"Rel-19",null,"Thu 10/03/22","Tue 09/09/25",0.95,"SP-231403",null,"Xu, Weijie, OPPO ","xuweijie@oppo.com ","; 8/12/23: 0%->95","22.261 ",102,52,null,null,"Thu 07/12/23","Fri 08/12/23"]
[136,950004,"   Study on Ambient power-enabled Internet of Things ","FS_AmbientIoT",2,"Rel-19","S1","Thu 10/03/22","Tue 12/12/23",1,"SP-220085",null,"Rapporteur:Xu, weijie, OPPO ","xuweijie@oppo.com ","5/4/22: 22.840 added;; 4/6/22: 0%->25; 9/9/22: 25%->50; 10/12/22: 50%->65; 17/3/23: 65%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->90; 8/6/23: FCD:03/03/2023->12/20; 6/9/23: 90%->95; 8/12/23: 95%->100","22.840",95,48,null,null,"Thu 10/03/22","Fri 08/12/23"]
[137,1020071,"   Study on Architecture support of Ambient power-enabled Internet of Things ","FS_AmbientIoT",2,"Rel-19","S2","Thu 04/01/24","Thu 12/12/24",1,"SP-240969",null,"Runze Zhou (Huawei) ","zhourunze@huawei.com ","14/3/24: 0%->25; 13/6/24: 25%->65; 16/7/24: WID:SP-231803->SP-240969; 4/9/24: 65%->80; 5/12/24: 80%->90; 6/3/25: 90%->100",null,102,52,null,null,"Wed 03/01/24","Thu 06/03/25"]
[138,1020030,"   Stage 1 of Ambient power-enabled Internet of Things ","AmbientIoT",2,"Rel-19","S1","Thu 07/12/23","Tue 12/12/23",1,"SP-231403",null,"Xu, Weijie, OPPO ","xuweijie@oppo.com ","; 8/12/23: 0%->95; 6/3/25: 95%->100","22.261 ",102,52,null,null,"Thu 07/12/23","Thu 06/03/25"]
[139,1070010,"   Architecture support of Ambient power-enabled Internet of Things ","AmbientIoT-ARC",2,"Rel-19","S2","Wed 26/03/25","Fri 06/06/25",0.9,"SP-250377",null,"Runze Zhou (Huawei) ","zhourunze@huawei.com ","; 5/6/25: 0%->90","23.501; 23.502 ",107,54,null,null,"Wed 05/03/25","Thu 05/06/25"]
[140,1080021,"   CT aspects of Ambient power-enabled Internet of Things","AmbientIoT-CT",2,"Rel-19","C1","Fri 06/06/25","Tue 09/09/25",0.84,"CP-251236",null,"Wass, Mikael, Huawei","mikael.wass@huawei.com",null,"29.522, 23.003, 29.518, 29.504, 29.505, 29.510, 29.571",107,54,null,null,"Wed 05/03/25","NA"]
[141,1080030,"      CT1 aspects of Ambient power-enabled Internet of Things","AmbientIoT-CT",3,"Rel-19","C1","Fri 06/06/25","Tue 09/09/25",0.3,"CP-251236",null,"Wass, Mikael, Huawei","mikael.wass@huawei.com",null,"29.522, 23.003, 29.518, 29.504, 29.505, 29.510, 29.571",107,54,null,null,"Wed 05/03/25","NA"]
[142,1080031,"      CT3 aspects of Ambient power-enabled Internet of Things","AmbientIoT-CT",3,"Rel-19","C3","Fri 06/06/25","Tue 09/09/25",0.7,"CP-251236",null,"Wass, Mikael, Huawei","mikael.wass@huawei.com",null,"29.522, 23.003, 29.518, 29.504, 29.505, 29.510, 29.571",107,54,null,null,"Wed 05/03/25","NA"]
[143,1080032,"      CT4 aspects of Ambient power-enabled Internet of Things","AmbientIoT-CT",3,"Rel-19","C4","Fri 06/06/25","Tue 09/09/25",0.6,"CP-251236",null,"Wass, Mikael, Huawei","mikael.wass@huawei.com",null,"29.522, 23.003, 29.518, 29.504, 29.505, 29.510, 29.571",107,54,null,null,"Wed 05/03/25","NA"]
[144,1020085,"Study on solutions for Ambient IoT (Internet of Things) in NR ","FS_Ambient_IoT_solutions",1,"Rel-19","R1","Wed 13/12/23","Thu 12/12/24",1,"RP-240826","RP-242965","Xiaodong Shen, CMCC","shenxiaodong@chinamobile.com","14/3/24: Compl:0%->8%; Stat Rep: ->RP-240155; Rapporteur: CMCC->Xiaodong Shen, CMCC; Rap eMail: ->shenxiaodong@chinamobile.com; ; 2/4/24: WID:RP-234058->RP-240826; 3/4/24: 38.769 added;; 13/6/24: Compl:8%->40%; Stat Rep: RP-240155->RP-241206; ; 4/9/24: FC","38.769",102,52,null,null,"Tue 02/01/24","Fri 24/01/25"]
[145,1030031,"Study on Security Aspect of Ambient IoT Services in 5G ","FS_Ambient_IoT_Sec",1,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",0.9,"SP-240506",null,"Marcus Wong, ","marcus.wong@oppo.com ","3/4/24: 33.713 added;; 13/6/24: 0%->30; 5/9/24: 30%->35; 5/12/24: 35%->55; 6/3/25: 55%->75; 6/3/25: FCD:12/12/2024->/25; 5/6/25: 75%->90","33.713",103,52,null,null,"Thu 14/03/24","Thu 05/06/25"]
[146,1070018,"Charging for Ambient power-enabled Internet of Things ","AmbientIoT-CH",1,"Rel-19","S5","Wed 26/03/25","Tue 09/09/25",1,"SP-250369",null,"YiMeng, DENG, Huawei ","dengyimeng@huawei.com ","; 6/6/25: 0%->100","32.240; 32.254; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[147,1070022,"Security Aspects of Ambient IoT Services in 5G ","AmbientIoT-SEC",1,"Rel-19","S3","Wed 26/03/25","Tue 09/09/25",0.45,"SP-250359",null,"Marcus Wong ","marcus.wong@oppo.co ","3/4/25: 33.369 added;; 5/6/25: 0%->45","33.369",107,54,null,null,"Wed 26/03/25","Thu 05/06/25"]
[148,1060084,"Solutions for Ambient IoT (Internet of Things) in NR ","Ambient_IoT_Solutions",1,"Rel-19",null,"Sun 19/05/24","Mon 02/03/26",0.36,"RP-250796",null,"CMCC ",null,"26/3/25: 38.391 added;; 26/3/25: 38.191 added;; 26/3/25: 38.194 added;; 26/3/25: 38.195 added;; 3/4/25: WID:RP-243326->RP-250796","38.391; 38.191; 38.194; 38.195",106,54,null,null,"Fri 24/01/25","Thu 03/04/25"]
[149,1061084,"   Core part: Solutions for Ambient IoT (Internet of Things) in NR ","Ambient_IoT_Solutions-Core",2,"Rel-19","R1","Mon 14/10/24","Tue 09/09/25",0.84,"RP-240796","RP-251399","CMCC ",null,"6/3/25: FCD:07/09/2025->09/09/2025; Compl:0%->27%; Stat Rep: ->RP-250267; ; 6/6/25: Compl:27%->84%; WID: RP-250796->RP-240796; Stat Rep: RP-250267->RP-251399; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[150,1062084,"   Perf. part: Solutions for Ambient IoT (Internet of Things) in NR ","Ambient_IoT_Solutions-Perf",2,"Rel-19","R4","Sun 08/12/24","Tue 03/03/26",0,"RP-240796","RP-251399","CMCC ",null,"6/3/25: FCD:01/03/2026->03/03/2026; Stat Rep: ->RP-250267; ; 6/6/25: WID: RP-250796->RP-240796; Stat Rep: RP-250267->RP-251399; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[151,0,"See also IoT_NTN_Ph3 under Satellite/NTN ","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[152,0,"Rel-19 Internet of Things, RedCap, MTC","-",1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[153,1040133,"NR power class 2 RedCap (Reduced Capability) UE in FR1 ","NR_PC2_RedCap_UE",1,"Rel-19",null,"Thu 06/06/24","Fri 06/06/25",1,"RP-243267",null,"China Telecom ",null,"26/9/24: WID:RP-241665->RP-241997; 24/1/25: WID:RP-241997->RP-243267",null,104,53,null,null,"Tue 23/07/24","Fri 24/01/25"]
[154,1041133,"   Core part: NR power class 2 RedCap (Reduced Capability) UE in FR1 ","NR_PC2_RedCap_UE-Core",2,"Rel-19","R4","Thu 06/06/24","Fri 06/06/25",1,"RP-243267","RP-251452","China Telecom ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->20%; Stat Rep: ->RP-241998; ; 6/12/24: Compl:20%->50%; Stat Rep: RP-241998->RP-242859; ; 6/3/25: FCD:14/02/2025->06/06/2025; Compl:50%->70%; Stat Rep: RP-242859->RP-250372; ; 6/6/25: Compl:70%->100%; Stat Rep",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[155,1050123,"Introduction of IoT-NTN TDD mode ","IoT_NTN_TDD",1,"Rel-19",null,"Mon 09/09/24","Tue 03/03/26",0.38,"RP-243293",null,"Iridium ",null,"24/1/25: WID:RP-242415->RP-243293",null,105,53,null,null,"Thu 26/09/24","Fri 24/01/25"]
[156,1051123,"   Core part: Introduction of IoT-NTN TDD mode ","IoT_NTN_TDD-Core",2,"Rel-19","R1","Mon 09/09/24","Tue 09/09/25",0.76,"RP-243293","RP-251175","Iridium ",null,"6/12/24: Compl:0%->20%; Stat Rep: ->RP-242652; ; 6/3/25: FCD:20/05/2025->09/09/2025; Compl:20%->30%; Stat Rep: RP-242652->RP-250045; ; 6/6/25: Compl:30%->76%; Stat Rep: RP-250045->RP-251175; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[157,1052123,"   Perf. part: Introduction of IoT-NTN TDD mode ","IoT_NTN_TDD-Perf",2,"Rel-19","R4","Sun 23/02/25","Tue 03/03/26",0,"RP-243293","RP-251175","Iridium ",null,"6/12/24: Stat Rep: ->RP-242652; ; 6/3/25: Stat Rep: RP-242652->RP-250045; ; 6/6/25: Stat Rep: RP-250045->RP-251175; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[158,1060008,"Management Aspects of RedCap features ","NR_RedCap_OAM",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.9,"SP-241941",null,"Zhen Xing (China Unicom)","xingz12@chinaunicom.cn ","; 6/3/25: 0%->50; 6/6/25: 50%->90","28.540; 28.541; 28.552; 28.554 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[159,0,"Rel-19 Satellite (5GSAT), NTN","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[160,1020058,"Satellite access Phase 3 ","5GSAT_Ph3",1,"Rel-19",null,"Thu 02/06/22","Tue 09/09/25",0.72,"SP-230516",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","; 6/9/23: 0%->95; 8/12/23: 95%->100","22.261 ",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[161,960016,"   Study on satellite access - Phase 3 ","FS_5GSAT_Ph3",2,"Rel-19","S1","Thu 02/06/22","Sat 09/09/23",1,"SP-220679",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","17/8/22: WID:SP-220443->SP-220679; 9/9/22: 0%->35; 10/12/22: 35%->55; 10/12/22: FCD:10/03/2023->06/23; 17/3/23: 55%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100",null,96,49,null,null,"Thu 02/06/22","Wed 06/09/23"]
[162,1000024,"   Stage 1 of Satellite access Phase 3 ","5GSAT_Ph3",2,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230516",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","; 6/9/23: 0%->95; 8/12/23: 95%->100","22.261 ",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[163,1010033,"   Study on Integration of satellite components in the 5G architecture Phase 3","FS_5GSAT_Ph3_ARCH",2,"Rel-19","S2","Wed 20/09/23","Thu 06/06/24",1,"SP-231199",null,"Jean-Yves Fine (Thales) ","jean-yves.fine@thalesgroup.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-29 added;; 8/12/23: 0%->15; 4/1/24: 28.874 added;; 14/3/24: 15%->55; 13/6/24: 55%->100; 4/9/24: 99%->100","23.700-29; 28.874",101,51,null,null,"Wed 20/09/23","Wed 04/09/24"]
[164,1020053,"   Study on application enablement for Satellite access enabled 5G Services ","FS_5GSAT_Ph3_App",2,"Rel-19","S6","Wed 03/01/24","Mon 09/09/24",1,"SP-240296",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","8/12/23: 0%->5; 14/3/24: 0%->25; 2/4/24: WID:SP-231738->SP-240296; 3/4/24: 23.700-01 added;; 13/6/24: 25%->60; 4/9/24: 60%->100","23.700-01",102,52,null,null,"Thu 07/12/23","Wed 04/09/24"]
[165,1040027,"   Integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3-ARC",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-241386",null,"Hucheng Wang (CATT) ","wanghucheng@catt.cn","4/9/24: 0%->15; 26/9/24: WID:SP-240986->SP-241386; 5/12/24: 15%->65; 6/3/25: 65%->100; 5/6/25: 100%->100","23.501; 23.502; 23.503; 23.682; 23.228; 23.401 ",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[166,1040077,"   Application enablement for satellite access Phase 3 ","5GSAT_Ph3_App",2,"Rel-19","S6","Tue 16/07/24","Mon 28/10/24",1,"SP-241690",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","; 4/9/24: 0%->5; 5/12/24: 5%->75; 8/1/25: WID:SP-241010->SP-241690; 6/3/25: 75%->100","23.558; 23.434; 23.289 ",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[167,1060023,"   CT aspects for application enablement for satellite access Phase 3","5GSAT_Ph3_App",2,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.36,"CP-243071",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","; 4/9/24: 0%->5",null,104,53,null,null,"Wed 12/06/24","Wed 04/09/24"]
[168,1060032,"      CT1 aspects for application enablement for satellite access Phase 3","5GSAT_Ph3_App",3,"Rel-19","C1","Mon 02/12/24","Tue 09/09/25",0.3,"CP-243071",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","; 4/9/24: 0%->5",null,104,53,null,null,"Wed 12/06/24","Wed 04/09/24"]
[169,1060033,"      CT3 aspects for application enablement for satellite access Phase 3","5GSAT_Ph3_App",3,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.75,"CP-243071",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","; 4/9/24: 0%->5",null,104,53,null,null,"Wed 12/06/24","Wed 04/09/24"]
[170,1050019,"   CT aspects of integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3_ARCH",2,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.63,"CP-250134",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com","24.301,23.040,27.007,24.229,29.122,29.214,29.508,29.512,29.513,29.514,29.272,29.128,29.336,29.502,29.571,29.230",null,105,53,null,null,"Wed 12/06/24","NA"]
[171,1050041,"      CT1 aspects of integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3_ARCH",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.9,"CP-250134",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[172,1050042,"      CT3 aspects of integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3_ARCH",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.95,"CP-250134",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[173,1050043,"      CT4 aspects of integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3_ARCH",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.9,"CP-250134",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[174,1060016,"Management Aspects of NTN Phase 2 ","NTN_OAM_Ph2",1,"Rel-19","S5","Thu 30/01/25","Fri 06/06/25",1,"SP-241949",null,"MingRui Sun (China Unicom)","sunmr19@chinaunicom.cn","; 6/3/25: 0%->25; 6/6/25: 25%->100","28.541; 28.552; 28.554; 28.658; 28.662; 28.540; 28.530 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[175,1020044,"Study on Security Aspects of 5G Satellite Access Phase 3 ","FS_5GSAT_Ph3_SEC",1,"Rel-19","S3","Thu 04/01/24","Thu 12/12/24",1,"SP-240232",null,"Zhou Wei ","zhouwei@catt.cn ","No end date in initial WID SP-231317; 4/1/24: 33.700-29 added;; 14/3/24: 0%->10; 2/4/24: WID:SP-231790->SP-240232; 13/6/24: 10%->65; 5/9/24: 65%->75; 5/12/24: 75%->85; 6/3/25: 85%->100; 5/6/25: 100%->100","33.700-29",102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[176,1060065,"Security Aspects of 5G Satellite Access Phase 3 ","5GSAT_Ph3_SEC",1,"Rel-19","S3","Thu 05/12/24","Fri 06/06/25",1,"SP-241780",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 6/3/25: 0%->35; 5/6/25: 35%->100","33.401 ",106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[177,1040014,"Study on charging aspects of satellite access Phase 3 ","FS_5GSAT_Ph3_CH",1,"Rel-19","S5","Wed 12/06/24","Wed 11/12/24",1,"SP-240980",null,"Yingying Liu, CATT, ","liuyingying@cictmobile.com ","13/6/24: 0%->10; 4/9/24: 10%->40; 26/9/24: 28.846 added;; 5/12/24: 40%->75; 5/12/24: FCD:12/12/2024->/25; 6/3/25: 75%->100","28.846",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[178,1070014,"Charging aspects of satellite access Phase 3 ","5GSAT_Ph3-CH",1,"Rel-19","S5","Wed 26/03/25","Fri 06/06/25",0.9,"SP-250365",null,"Yingying Liu, CATT ","liuyingying@cictmobile.com ","; 6/6/25: 0%->90","32.240; 32.251; 32.255; 32.257; 32.260; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[179,1020097,"Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.48,"RP-243300",null,"Thales ",null,"2/4/24: WID:RP-234078->RP-240775; 23/7/24: WID:RP-240775->RP-241667; 26/9/24: WID:RP-241667->RP-241789; 24/1/25: WID:RP-241789->RP-243300",null,102,52,null,null,"Tue 02/01/24","Fri 24/01/25"]
[180,1021097,"   Core part: Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3-Core",2,"Rel-19","R2","Wed 13/12/23","Tue 09/09/25",0.9,"RP-243300","RP-251003","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","14/3/24: Compl:0%->5%; Stat Rep: ->RP-240091; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com; ; 13/6/24: Compl:5%->25%; Stat Rep: RP-240091->RP-240923; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:25%->45%",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[181,1022097,"   Perf. part: Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0,"RP-243300","RP-251003","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","14/3/24: Stat Rep: ->RP-240091; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com; ; 13/6/24: Stat Rep: RP-240091->RP-240923; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-240923->RP-241742; ; 6/12/24: ",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[182,1020096,"Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 (for LTE)","IoT_NTN_Ph3",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.63,"RP-250472",null,"Mediatek ",null,"2/4/24: WID:RP-234077->RP-240776; 23/7/24: WID:RP-240776->RP-241624; 26/9/24: WID:RP-241624->RP-242397; 24/1/25: WID:RP-242397->RP-243278; 3/4/25: WID:RP-243278->RP-250472",null,102,52,null,null,"Tue 02/01/24","Thu 03/04/25"]
[183,1021096,"   Core part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 ","IoT_NTN_Ph3-Core",2,"Rel-19","R2","Wed 13/12/23","Tue 09/09/25",0.9,"RP-250472","RP-251289","Mediatek ",null,"13/6/24: Compl:0%->15%; Stat Rep: ->RP-241356; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:15%->30%; Stat Rep: RP-241356->RP-242050; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:30%->50%; Stat Rep: RP-242050->RP-242996; ; 6/3/25: FCD:26/02/2025->09/09/202",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[184,1032087,"   Perf. part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 ","IoT_NTN_Ph3-Perf",2,"Rel-19","R4","Sun 13/10/24","Tue 03/03/26",0.3,"RP-250472","RP-251289","Mediatek ",null,"13/6/24: FCD:03/03/2026->12/12/2025; Stat Rep: ->RP-241356; ; 4/9/24: FCD:12/12/2025->26/03/2025; Stat Rep: RP-241356->RP-242050; ; 6/12/24: Stat Rep: RP-242050->RP-242996; ; 6/3/25: WID: RP-243278->RP-242397; Stat Rep: RP-242996->RP-250470; ; 6/6/25: Com",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[185,1030076,"Inter-RAT mode mobility support from E-UTRAN TN to NR NTN ","LTE_TN_NR_NTN_mob",1,"Rel-19",null,"Sun 03/03/24","Mon 09/09/24",0.99,"RP-240924",null,"Thales ",null,"23/7/24: WID:RP-240846->RP-240924",null,103,52,null,null,"Tue 02/04/24","Tue 23/07/24"]
[186,1031076,"   Core part: Inter-RAT mode mobility support from E-UTRAN TN to NR NTN ","LTE_TN_NR_NTN_mob-Core",2,"Rel-19","R2","Sun 03/03/24","Tue 09/09/25",0.99,"RP-240846","RP-251004","Thales ",null,"13/6/24: Compl:0%->70%; Stat Rep: ->RP-240925; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:70%->95%; WID: RP-240924->RP-240846; Stat Rep: RP-240925->RP-241741; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:95%->96%; Stat Rep: RP-241741->RP-242463; ; 6/3/25",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[187,1030086,"Enhanced requirements and test methodology for NR NTN and IoT NTN ","NR_IoT_NTN_req_test_enh",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.61,"RP-242901",null,"Samsung ",null,"23/7/24: WID:RP-240857->RP-241281; 26/9/24: WID:RP-241281->RP-241985; 24/1/25: WID:RP-241985->RP-242901",null,103,52,null,null,"Tue 02/04/24","Fri 24/01/25"]
[188,1031086,"   Core part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN ","NR_IoT_NTN_req_test_enh-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.88,"RP-242901","RP-251015","Samsung ",null,"13/6/24: Stat Rep: ->RP-241280; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->16%; Stat Rep: RP-241280->RP-241984; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:16%->50%; Stat Rep: RP-241984->RP-242592; ; 6/3/25: FCD:23/03/2025->09/09/2025; Compl:50%->65",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[189,1032086,"   Perf. Part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN ","NR_IoT_NTN_req_test_enh-Perf",2,"Rel-19","R4","Sun 03/03/24","Tue 03/03/26",0.4,"RP-242901","RP-251015","Samsung ",null,"13/6/24: Stat Rep: ->RP-241280; ; 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->10%; Stat Rep: RP-241280->RP-241984; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:10%->30%; Stat Rep: RP-241984->RP-242592; ; 6/3/25: FCD:22/07/2025->03/03/2026; Compl:30%->35",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[190,1040129,"Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","NR_NTN_Sband",1,"Rel-19",null,"Thu 06/06/24","Fri 06/06/25",1,"RP-250488",null,"Qualcomm ",null,"26/9/24: WID:RP-241661->RP-241885; 3/4/25: WID:RP-241885->RP-250488",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[191,1041129,"   Core part: Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","NR_NTN_Sband-Core",2,"Rel-19","R4","Thu 06/06/24","Fri 06/06/25",1,"RP-250488","RP-251476","Qualcomm ",null,"4/9/24: FCD:03/03/2025->25/06/2025; Compl:0%->20%; Stat Rep: ->RP-241884; ; 6/12/24: FCD:06/06/2025->03/03/2025; Compl:20%->50%; Stat Rep: RP-241884->RP-242615; ; 6/3/25: FCD:09/12/2024->06/06/2025; Compl:50%->70%; Stat Rep: RP-242615->RP-250487; ; 6/6/2",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[192,1042129,"   Perf. part: Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","NR_NTN_Sband-Perf",2,"Rel-19","R4","Thu 26/09/24","Fri 06/06/25",1,"RP-250488","RP-251476","Qualcomm ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Stat Rep: ->RP-241884; ; 6/12/24: Stat Rep: RP-241884->RP-242615; ; 6/3/25: Stat Rep: RP-242615->RP-250487; ; 6/6/25: Compl:0%->100%; Stat Rep: RP-250487->RP-251476; ",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[193,1040130,"Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","IoT_NTN_FDD_S_band",1,"Rel-19",null,"Thu 06/06/24","Fri 06/06/25",1,"RP-250474",null,"Mediatek ",null,"26/9/24: WID:RP-241662->RP-242062; 3/4/25: WID:RP-242062->RP-250474",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[194,1041130,"   Core part: Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","IoT_NTN_FDD_S_band-Core",2,"Rel-19","R4","Thu 06/06/24","Fri 06/06/25",1,"RP-250474","RP-251290","Mediatek ",null,"4/9/24: FCD:03/03/2025->25/06/2025; Compl:0%->20%; Stat Rep: ->RP-242061; ; 6/12/24: FCD:06/06/2025->03/03/2025; Compl:20%->50%; WID: RP-241662->RP-242062; Stat Rep: RP-242061->RP-242999; ; 6/3/25: FCD:09/12/2024->06/06/2025; Compl:50%->70%; Stat Rep: RP",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[195,1042130,"   Perf. part: Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","IoT_NTN_FDD_S_band-Perf",2,"Rel-19","R4","Thu 26/09/24","Fri 06/06/25",1,"RP-250474","RP-251290","Mediatek ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Stat Rep: ->RP-242061; ; 6/12/24: WID: RP-241662->RP-242062; Stat Rep: RP-242061->RP-242999; ; 6/3/25: Stat Rep: RP-242999->RP-250473; ; 6/6/25: Compl:0%->100%; Stat Rep: RP-250473->RP-251290; ",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[196,1040135,"Introduction of Ku bands for NR NTN ","NR_NTN_Ku_bands",1,"Rel-19",null,"Thu 06/06/24","Mon 03/03/25",0.33,"RP-250799",null,"Intelsat ",null,"24/1/25: WID:RP-241690->RP-243314; 3/4/25: WID:RP-243314->RP-250799",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[197,1041135,"   Core part: Introduction of Ku bands for NR NTN ","NR_NTN_Ku_bands-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.65,"RP-250799","RP-251271","Intelsat ",null,"4/9/24: FCD:09/09/2025->24/09/2024; Compl:0%->15%; Stat Rep: ->RP-241788; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->30%; Stat Rep: RP-241788->RP-242946; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:30%->50%; Stat Rep: RP-242946->RP-250466; ; 6/6/2",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[198,1042135,"   Perf. part: Introduction of Ku bands for NR NTN ","NR_NTN_Ku_bands-Perf",2,"Rel-19","R4","Fri 20/12/24","Tue 03/03/26",0,"RP-250799","RP-251271","Intelsat ",null,"4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: ->RP-241788; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-241788->RP-242946; ; 6/3/25: Stat Rep: RP-242946->RP-250466; ; 6/6/25: Compl:0%->50%; WID: RP-250799->RP-243314; Stat Rep: RP-250466->RP-251271",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[199,1040134,"New NR NTN bands to support Extended L-band and combined MSS L-band and Extended L-band ranges ","NR_NTN_combinedLband",1,"Rel-19",null,"Thu 06/06/24","Fri 06/06/25",0.9,"RP-250752",null,"Aalyria",null,"26/9/24: WID:RP-241689->RP-241856; 3/4/25: WID:RP-241856->RP-250752; rapporteur: Inmarsat=> Aalyria",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[200,1041134,"   Core part: Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) ","NR_NTN_combinedLband-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.9,"RP-250752","RP-250982","Aalyria",null,"4/9/24: FCD:03/03/2025->25/03/2025; Compl:0%->15%; Stat Rep: ->RP-241782; ; 6/12/24: Compl:15%->35%; Stat Rep: RP-241782->RP-242601; ; 6/3/25: FCD:09/12/2024->06/06/2025; Compl:35%->70%; Stat Rep: RP-242601->RP-250751; ; 6/6/25: FCD:Fri 06/06/25->Tue 09/",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[201,1042134,"   Perf. part: Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) ","NR_NTN_combinedLband-Perf",2,"Rel-19","R4","Thu 26/09/24","Tue 09/09/25",0.9,"RP-250752","RP-250982","Aalyria",null,"4/9/24: FCD:06/06/2025->25/06/2025; Stat Rep: ->RP-241782; ; 6/12/24: Stat Rep: RP-241782->RP-242601; ; 6/3/25: Stat Rep: RP-242601->RP-250751; ; 6/6/25: FCD:Fri 06/06/25->Tue 09/09/25; Compl:0%->90%; Stat Rep: RP-250751->RP-250982; ",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[202,1050127,"Introduction of additional operating NR bands for HAPS (High Altitude Platform Station) ","NR_HAPS_bands",1,"Rel-19",null,"Mon 09/09/24","Mon 03/03/25",1,"RP-242891",null,"SoftBank ",null,"24/1/25: WID:RP-242373->RP-242891",null,105,53,null,null,"Thu 26/09/24","Fri 24/01/25"]
[203,1051127,"   Core part: Introduction of additional operating NR bands for HAPS (High Altitude Platform Station) ","NR_HAPS_bands-Core",2,"Rel-19","R4","Mon 09/09/24","Mon 03/03/25",1,"RP-242891","RP-250407","SoftBank ",null,"6/12/24: FCD:12/12/2024->03/03/2025; Compl:0%->99%; Stat Rep: ->RP-242890; ; 6/3/25: FCD:08/01/2025->03/03/2025; Compl:99%->100%; Stat Rep: RP-242890->RP-250407; ",null,105,53,null,null,"Thu 26/09/24","Thu 06/03/25"]
[204,1052127,"   Stopped - Perf. part: Introduction of additional operating NR bands for HAPS (High Altitude Platform Station) ","NR_HAPS_bands-Perf",2,"Rel-19","R4","Mon 09/09/24","Thu 12/12/24",1,"RP-242891",null,"SoftBank ",null,"24/1/25: Stopped at 0%",null,105,53,null,null,"Thu 26/09/24","Fri 24/01/25"]
[205,0,"Rel-19 XR (eXtended Reality), Metaverse","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[206,1020056,"Localized Mobile Metaverse Services ","Metaverse",1,"Rel-19",null,"Thu 10/03/22","Tue 09/09/25",0.76,"SP-230509",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","; 6/9/23: 0%->80; 21/9/23: 22.156 added;; 8/12/23: 80%->100","new 22.156, 22.261 ; 22.156",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[207,950005,"   Study on Localized Mobile Metaverse Services ","FS_Metaverse",2,"Rel-19","S1","Thu 10/03/22","Sat 09/09/23",1,"SP-220353",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","5/4/22: 22.856 added;; 4/6/22: 0%->15; 9/9/22: 15%->40; 10/12/22: 40%->55; 17/3/23: 55%->75; 8/6/23: 75%->90; 8/6/23: FCD:03/03/2023->09/20; 8/12/23: 90%->100","22.856",95,48,null,null,"Thu 10/03/22","Fri 08/12/23"]
[208,1000028,"   Stage 1 of Localized Mobile Metaverse Services ","Metaverse",2,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230509",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","; 6/9/23: 0%->80; 21/9/23: 22.156 added;; 8/12/23: 80%->100","new 22.156, 22.261 ; 22.156",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[209,1040076,"   Application enablement for mobile metaverse services ","Metaverse_App",2,"Rel-19","S6","Tue 16/07/24","Mon 28/10/24",1,"SP-241390",null,"Shah, Sapan, Samsung ","<sapan.shah@samsung.com> ","; 4/9/24: 0%->25; 26/9/24: WID:SP-241009->SP-241390; 26/9/24: 23.437 added;; 5/12/24: 25%->80; 6/3/25: 80%->100; 26/3/25: 23.438 added;","23.434; 23.542; 23.558; 23.436 ; 23.437; 23.438",104,53,null,null,"Wed 12/06/24","Wed 26/03/25"]
[210,1020052,"   Study on application enablement for Localized Mobile Metaverse Services ","FS_Metaverse_App",2,"Rel-19","S6","Wed 03/01/24","Mon 09/09/24",1,"SP-231806",null,"Shah, Sapan, Samsung ","sapan.shah@samsung.com ","8/12/23: 0%->10; 14/3/24: 0%->30; 3/4/24: 23.700-21 added;; 13/6/24: 30%->70; 4/9/24: 70%->100","23.700-21",102,52,null,null,"Thu 07/12/23","Wed 04/09/24"]
[211,1030039,"   Study on security aspects of 5G Mobile Metaverse services ","FS_Metaverse_Sec",2,"Rel-19","S3","Tue 02/04/24","Fri 06/06/25",1,"SP-240508",null,"Rohini Rajendran, ","r.rohini@samsung.com ","3/4/24: 33.721 added;; 13/6/24: 0%->20; 5/9/24: 20%->50; 5/12/24: 50%->70; 6/3/25: 70%->79; 6/3/25: FCD:12/12/2024->/25; 5/6/25: 79%->100; 5/6/25: FCD:Sat 25/01/->/25","33.721",103,52,null,null,"Thu 14/03/24","Thu 05/06/25"]
[212,1050025,"   CT aspects of Application enablement for mobile metaverse services ","Metaverse_App",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.43,"CP-243309",null,"Vijay Sangameshwara, Samsung","s.vijay@samsung.com",null,"24.583, 24.545, 29.549",105,53,null,null,"Wed 12/06/24","NA"]
[213,1050060,"      CT1 aspects of Application enablement for mobile metaverse services ","Metaverse_App",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.7,"CP-243309",null,"Vijay Sangameshwara, Samsung","s.vijay@samsung.com","; 26/9/24: 24.437 added;",null,105,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[214,1050061,"      CT3 aspects of Application enablement for mobile metaverse services ","Metaverse_App",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.55000000000000004,"CP-243309",null,"Vijay Sangameshwara, Samsung","s.vijay@samsung.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[215,1060060,"   Security aspects of 5G Mobile Metaverse services ","Metaverse_Sec",2,"Rel-19","S3","Thu 02/01/25","Mon 03/03/25",0,"SP-250075",null,"Rohini Rajendran, r.rohini@samsung.com ","Lihui Xiong, xionglihui@oppo.com ","; 26/3/25: WID:SP-241775->SP-250075","33.434 ",106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[216,1060034,"Extended Reality and Media",null,1,"Rel-19",null,"Thu 16/03/23","Sat 06/06/26",0.75,null,null,null,null,null,null,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[217,990052,"   Supporting UE Mobility for XR Services ","XRMobility",2,"Rel-19","S1","Thu 16/03/23","Tue 06/06/23",1,"SP-230233",null,"Xiaonan Shi, ChinaMobile ","shixiaonan@chinamobile.com ","; 17/3/23: 0%->50; 6/9/23: 50%->100","22.261 ",99,50,null,null,"Thu 16/03/23","Wed 06/09/23"]
[218,1010032,"   Study on Extended Reality and Media service (XRM) Phase 2 ","FS_XRM_Ph2",2,"Rel-19","S2","Wed 03/01/24","Mon 09/09/24",1,"SP-231671",null,"Primary Rapporteur: Devaki Chandramouli (Nokia) ","devaki.chandramouli@nokia.com. ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-70 added;; 8/12/23: 0%->13; 14/3/24: 0%->45; 13/6/24: FCD:05/06/2024->/24; 13/6/24: 45%->90; 4/9/24: 90%->100","23.700-70",101,51,null,null,"Wed 20/09/23","Wed 04/09/24"]
[219,1040032,"   Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-241385",null,"Georgios Gkellas (Nokia), ","Georgios.Gkellas@nokia.com. ","; 4/9/24: 0%->5; 26/9/24: WID:SP-240990->SP-241322; 26/9/24: WID:SP-241322->SP-241385; 5/12/24: 5%->65; 6/3/25: 65%->100","23.501; 23.502; 23.503; 23.316 ",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[220,1060027,"   CT aspects of Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",2,"Rel-19",null,"Mon 02/12/24","Tue 09/09/25",0.91,"CP-243075",null,"Ravindran, Parthasarathi, Nokia","parthasarathi.ravindran@nokia.com",null,"24.501, 29.122, 29.508, 29.512, 29.514, 29.522, 29.513, 29.561, 29.281, 29.244, 29.502, 29.564, 29.571",104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[221,1060035,"      CT1 aspects of Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",3,"Rel-19","C1","Mon 02/12/24","Tue 09/09/25",0.98,"CP-243075",null,"Ravindran, Parthasarathi, Nokia","parthasarathi.ravindran@nokia.com",null,null,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[222,1060036,"      CT3 aspects of Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",3,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.85,"CP-243075",null,"Ravindran, Parthasarathi, Nokia","parthasarathi.ravindran@nokia.com",null,null,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[223,1060037,"      CT4 aspects of Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",3,"Rel-19","C4","Mon 02/12/24","Tue 09/09/25",0.9,"CP-243075",null,"Ravindran, Parthasarathi, Nokia","parthasarathi.ravindran@nokia.com",null,null,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[224,1020051,"   Study on Application enabler for XR Services ","FS_XRApp",2,"Rel-19","S6","Wed 03/01/24","Thu 12/12/24",1,"SP-2315739",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","8/12/23: 0%->10; 14/3/24: 0%->20; 3/4/24: 23.700-23 added;; 13/6/24: 20%->65; 4/9/24: 65%->90; 5/12/24: 90%->100; 5/12/24: FCD:09/09/2024->12/24","23.700-23",102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[225,1040074,"   Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",2,"Rel-19","S6","Tue 16/07/24","Mon 28/10/24",1,"SP-241207",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 4/9/24: 0%->15; 26/9/24: WID:SP-241007->SP-241207; 5/12/24: 15%->90; 6/3/25: 90%->100","23.433; 23.558 ",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[226,1060024,"   CT aspects of Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",2,"Rel-19",null,"Mon 02/12/24","Tue 09/09/25",0.69,"CP-243072",null,"Zhenning, Huang, China Mobile","huangzhenning@chinamobile.com",null,"24.543, 24.548, 29.548, 29.549, 29.558",104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[227,1060038,"      CT1 aspects of Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",3,"Rel-19","C1","Thu 27/02/25","Tue 09/09/25",0.4,"CP-243072",null,"Zhenning, Huang, China Mobile","huangzhenning@chinamobile.com",null,null,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[228,1060039,"      CT3 aspects of Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",3,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.9,"CP-243072",null,"Zhenning, Huang, China Mobile","huangzhenning@chinamobile.com",null,null,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[229,1070021,"   Protection of XRM Media related information ","XRM_Ph2-SEC",2,"Rel-19","S3","Tue 11/02/25","Mon 03/03/25",0,"SP-250361",null,"Daniel Cho ","daniel.cho@ericsson.com ",null,"33.501 ",107,54,null,null,"Wed 05/03/25","NA"]
[230,1080016,"   OAM support for Extended Reality and Media service (XRM) phase 2 ","XRM_Ph2-OAM",2,"Rel-20","S5","Thu 05/06/25","Sat 06/06/26",0,"SP-250506",null,null,null,null,"28.540; 28.541; 28.552; 28.554 ",null,null,null,null,"Thu 05/06/25","NA"]
[231,1020098,"XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.48,"RP-250107",null,"Nokia ",null,"2/4/24: WID:RP-234080->RP-240791; 26/9/24: WID:RP-240791->RP-241771; 24/1/25: WID:RP-241771->RP-243318; 3/4/25: WID:RP-243318->RP-250107",null,102,52,null,null,"Tue 02/01/24","Thu 03/04/25"]
[232,1021098,"   Core part: XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3-Core",2,"Rel-19","R2","Wed 13/12/23","Tue 09/09/25",0.9,"RP-250107","RP-251002","Benoist Sebire, Nokia","benoist.sebire@nokia.com","14/3/24: Compl:0%->2%; Stat Rep: ->RP-240081; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; ; 13/6/24: Compl:2%->18%; Stat Rep: RP-240081->RP-240927; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:18%->30%; Stat Rep: RP-240",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[233,1022098,"   Perf. part: XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0,"RP-250107","RP-251002","Benoist Sebire, Nokia","benoist.sebire@nokia.com","14/3/24: Stat Rep: ->RP-240081; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; ; 13/6/24: Stat Rep: RP-240081->RP-240927; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-240927->RP-241770; ; 6/12/24: FCD:03/03/2025->03",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[234,1030045,"Indirect Network Sharing ","TEI19_NetShare",1,"Rel-19",null,"Thu 10/03/22","Tue 09/09/25",1,null,null,null,null,null,null,103,52,null,null,"Wed 13/03/24","NA"]
[235,950006,"   Study on Network Sharing Aspects ","FS_NetShare",2,"Rel-19","S1","Thu 10/03/22","Sat 09/09/23",1,"SP-220087",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","5/4/22: 22.851 added;; 4/6/22: 0%->10; 9/9/22: 10%->20; 10/12/22: 20%->75; 17/3/23: 75%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->95; 8/6/23: FCD:03/03/2023->09/20; 6/9/23: 95%->100","22.851",95,48,null,null,"Thu 10/03/22","Wed 06/09/23"]
[236,1000029,"   (Stage 1 of) Indirect Network Sharing ","NetShare",2,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230511",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 6/9/23: 0%->100","22.261 ",100,51,null,null,"Thu 08/06/23","Wed 06/09/23"]
[237,1030011,"   (Stage 2 of) Indirect Network Sharing ","TEI19_NetShare",2,"Rel-19","S2","Tue 02/04/24","Thu 06/06/24",1,"SP-240488",null,"Xing, Tianqi, China Unicom, ","xingtq@chinaunicom.cn ","; 13/6/24: FCD:12/12/2024->06/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[238,1040019,"   Charging enhancement for indirect network sharing ","NetShare_CH",2,"Rel-19","S5","Wed 12/06/24","Thu 12/12/24",1,"SP-241004",null,"Robert Törnkvist, Ericsson, ","robert.tornkvist@ericsson.com ","; 5/12/24: 0%->100","32.240; 32.255; 32.256 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[239,1050004,"   CT aspects of indirect network sharing ","TEI19_NetShare",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",1,"CP-250019",null,"Xing Tianqi, China Unicom","xingtq@chinaunicom.cn",null,"24.501,29.507,29.525,29.531,29.510,29.502,29.509,29.503,29.536",105,53,null,null,"Wed 12/06/24","NA"]
[240,1050074,"      CT1 aspects of indirect network sharing ","TEI19_NetShare",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",1,"CP-250019",null,"Xing Tianqi, China Unicom","xingtq@chinaunicom.cn",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[241,1070048,"      CT3 aspects of indirect network sharing ","TEI19_NetShare",3,"Rel-19","C3","Mon 03/03/25","Tue 09/09/25",1,"CP-250019",null,"Xing Tianqi, China Unicom","xingtq@chinaunicom.cn",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[242,1050075,"      CT4 aspects of indirect network sharing ","TEI19_NetShare",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",1,"CP-250019",null,"Xing Tianqi, China Unicom","xingtq@chinaunicom.cn",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[243,1060017,"Management of Network Sharing Phase 3","NetShare_OAM_Ph3",1,"Rel-19","S5","Thu 30/01/25","Fri 06/06/25",0.95,"SP-241950",null,"ZhaoNing Wang (China Unicom)","wangzn18@chinaunicom.cn","; 6/3/25: 0%->50; 6/6/25: 50%->95","28.552; 32.130; 28.541 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[244,1030046,"Roaming Value-Added Services ","TEI19_RVAS",1,"Rel-19",null,"Thu 02/06/22","Fri 06/06/25",0.87,null,null,null,null,null,null,103,52,null,null,"Wed 13/03/24","NA"]
[245,960015,"   Study on roaming value added services ","FS_RVAS",2,"Rel-19","S1","Thu 02/06/22","Mon 12/12/22",1,"SP-220442",null,"Peter Bleckert, Ericsson ",null,"13/7/22: 22.877 added;; 9/9/22: 0%->60; 10/12/22: FCD:10/03/2023->12/22; 10/12/22: 60%->100","22.877",96,49,null,null,"Thu 02/06/22","Sat 10/12/22"]
[246,990051,"   Roaming Value-Added Services ","RVAS",2,"Rel-19","S1","Thu 02/02/23","Fri 03/03/23",1,"SP-230231",null,"Peter Bleckert, Ericsson ",null,"; 17/3/23: 0%->100","22.261 ",99,50,null,null,"Thu 16/03/23","Fri 17/03/23"]
[247,1030013,"   Architecture support of roaming value-added services ","TEI19_RVAS",2,"Rel-19","S2","Wed 13/03/24","Thu 06/06/24",1,"SP-240119",null,"Qian Chen, Ericsson, ","qian.xb.chen@ericsson.com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[248,1050002,"   CT aspects of Architecture support of roaming value-added services ","TEI19_RVAS",2,"Rel-19",null,"Mon 09/09/24","Fri 06/06/25",0.81,"CP-242022",null,"Frank Yong, Yang, Ericsson","frank.yong.yang@ericsson.com",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[249,1050087,"      CT3 aspects of Architecture support of roaming value-added services ","TEI19_RVAS",3,"Rel-19","C3","Mon 09/09/24","Fri 06/06/25",0.9,"CP-242022",null,"Frank Yong, Yang, Ericsson","frank.yong.yang@ericsson.com",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[250,1050088,"      CT4 aspects of Architecture support of roaming value-added services ","TEI19_RVAS",3,"Rel-19","C4","Mon 09/09/24","Fri 06/06/25",1,"CP-242022",null,"Frank Yong, Yang, Ericsson","frank.yong.yang@ericsson.com",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[251,0,"Rel-19 user plane","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[252,1080048,"Media Messaging Enhancements ","MeME-MED",1,"Rel-19","S4","Thu 05/06/25","Tue 09/09/25",0,"SP-250632",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ",null,"26.143 ",null,null,null,null,"Thu 05/06/25","NA"]
[253,1070056,"Avatar Communications in AR Calls ","AvCall-MED",1,"Rel-19","S4","Thu 06/03/25","Tue 09/09/25",0.15,"SP-250264",null,"Bouazizi, Imed, Qualcomm, ","bouazizi AT qti dot qualcomm dot com ","; 5/6/25: 0%->15","26.264 ",107,54,null,null,"Wed 05/03/25","Thu 05/06/25"]
[254,1050037,"Study on immersive Real-Time Communication for WebRTC, Phase 2 ","FS_iRTCW_Ph2",1,"Rel-19","S4","Mon 09/09/24","Fri 06/06/25",1,"SP-241374",null,"Hakju Ryan Lee, Samsung Electronics, CO., LTD, ","hakju00.lee@samsung.com ","5/12/24: 0%->15; 6/3/25: 15%->35; 26/3/25: 26.830 added;; 5/6/25: 35%->100; 5/6/25: FCD:Mon 03/03/->/25","26.830",105,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[255,1050113,"Terminal Audio quality performance and Test methods for Immersive Audio Services, Phase 2 ","ATIAS_Ph2",1,"Rel-19","S4","Mon 09/09/24","Tue 09/09/25",0.65,"SP-241314",null,"Jan Reimes, HEAD acoustics GmbH, ","jan.reimes@head-acoustics.com ","; 6/3/25: 0%->25; 5/6/25: 25%->65; 5/6/25: FCD:Fri 06/06/->/25","26.259; 26.260; 26.261 ",105,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[256,1060022,"Diverse audio Capturing System for UEs ","DaCAS",1,"Rel-19","S4","Thu 05/12/24","Tue 09/09/25",0.5,"SP-241962",null,"Wang Bin, Xiaomi Technology ","wangbin23@xiaomi.com ","6/3/25: 0%->5; 5/6/25: 5%->50; 5/6/25: FCD:Fri 06/06/->/25","26.533",106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[257,1040022,"Study on Spatial Computing for AR Services ","FS_ARSpatial",1,"Rel-19","S4","Thu 06/06/24","Tue 09/09/25",0.45,"SP-240927",null,"Hamza, Ahmed, InterDigital Canada ","<Ahmed.Hamza@InterDigital.com> ","4/9/24: 0%->10; 26/9/24: 26.819 added;; 5/12/24: 10%->25; 6/3/25: 25%->45; 5/6/25: 45%->45; 5/6/25: FCD:Fri 14/02/->/25","26.819",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[258,1040021,"EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 ","IVAS_Codec_Ph2",1,"Rel-19","S4","Thu 06/06/24","Tue 09/09/25",0.65,"SP-250262",null,"Su, Huan-yu, Huawei Technologies Co Ltd., ","su.huanyu@huawei.com ","; 4/9/24: 0%->5; 5/12/24: 5%->20; 5/12/24: FCD:06/06/2025->/25; 6/3/25: 20%->35; 26/3/25: WID:SP-241000->SP-250262; 26/3/25: FCD:19/04/2025->12/25; 5/6/25: 35%->65; 5/6/25: FCD:Fri 12/12/->/25","26.114; 26.117; 26.119; 26.249; 26.250; 26.252; 26.253; 26.258; 26.997 ",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[259,1040020,"Study on Haptics in 5G Media Services ","FS_HapticsMedia",1,"Rel-19","S4","Wed 12/06/24","Mon 03/03/25",1,"SP-241121",null,"Gaëlle Martin-Cocher, InterDigital ","(Gaelle.Martin-Cocher@InterDigital.com) ","4/9/24: WID:SP-240979->SP-241121; acron.: FS_HapticsMed-> FS_HapticsMedia; 4/9/24: 0%->15; 26/9/24: 26.854 added;; 5/12/24: 15%->60; 6/3/25: 60%->100","26.854",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[260,1050097,"UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",1,"Rel-19","S2","Thu 04/01/24","Tue 09/09/25",1,"SP-240995",null,"Zhu Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502; 23.503 ",105,53,null,null,"Wed 12/06/24","NA"]
[261,1020003,"   Study on UPF enhancement for Exposure And SBA Phase 2 ","FS_UPEAS_Ph2",2,"Rel-19","S2","Thu 04/01/24","Thu 06/06/24",1,"SP-231795",null,"Zhu Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","14/3/24: 0%->45; 13/6/24: 45%->100",null,102,52,null,null,"Wed 03/01/24","Thu 13/06/24"]
[262,1040035,"   Stage 2 of UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-240995",null,"Zhu Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 4/9/24: 0%->65; 5/12/24: 65%->100","23.501; 23.502; 23.503 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[263,1050001,"   CT aspects of UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",2,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",1,"CP-250018",null,"Shuang Liang, ZTE","liang.shuang3@zte.com.cn",null,"29.244,29.503,29.504,29.510,29.564,29.571,29.508,29.512,29.513,29.514,29.519,29.522",105,53,null,null,"Wed 12/06/24","NA"]
[264,1050098,"      CT3 aspects of UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",1,"CP-250018",null,"Shuang Liang, ZTE","liang.shuang3@zte.com.cn",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[265,1050099,"      CT4 aspects of UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",1,"CP-250018",null,"Shuang Liang, ZTE","liang.shuang3@zte.com.cn",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[266,1030002,"Video Operating Points - Harmonization and Stereo MV-HEVC ","VOPS",1,"Rel-19","S4","Wed 13/03/24","Fri 12/12/25",0.7,"SP-250633",null,"Waqar Zia ","waqar_zia (at) apple.com ","14/5/24: 26.265 added;; 13/6/24: 0%->15; 4/9/24: 15%->20; 4/9/24: 20%->; 5/12/24: 20%->45; 5/12/24: FCD:03/03/2025->/25; 6/3/25: 45%->70; 5/6/25: 70%->70; 5/6/25: FCD:Sat 18/01/->12/20; 5/6/25: WID:SP-240060->SP-250633","26.265",103,52,null,null,"Wed 13/03/24","Thu 05/06/25"]
[267,1030003,"Split rendering over IMS ","SR_IMS",1,"Rel-19","S4","Tue 02/04/24","Tue 09/09/25",0.95,"SP-240492",null,"He, Shane, Nokia Corporation ","shane.he@nokia.com ","; 14/5/24: 26.567 added;; 13/6/24: 0%->10; 4/9/24: 10%->25; 5/12/24: 25%->45; 5/12/24: FCD:03/03/2025->/25; 6/3/25: 45%->65; 5/6/25: 65%->95; 5/6/25: FCD:Sat 25/01/->/2025","26.264 ; 26.567",103,52,null,null,"Wed 13/03/24","Thu 05/06/25"]
[268,1030005,"Study on Media Messaging ","FS_MeMe",1,"Rel-19","S4","Tue 02/04/24","Fri 06/06/25",1,"SP-240477",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","13/6/24: 0%->10; 13/6/24: FCD:12/12/2024->/25; 4/9/24: 10%->30; 5/12/24: 30%->60; 6/3/25: 60%->65; 6/3/25: FCD:03/03/2025->/25; 5/6/25: 65%->100; 5/6/25: FCD:Sat 25/01/->/25",null,103,52,null,null,"Wed 13/03/24","Thu 05/06/25"]
[269,1030006,"Study on Advanced Media Delivery ","FS_AMD",1,"Rel-19","S4","Tue 02/04/24","Thu 12/12/24",1,"SP-241011",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","; 13/6/24: 0%->15; 16/7/24: WID:SP-240478->SP-241011; 4/9/24: 15%->30; 5/12/24: 30%->75; 6/3/25: 75%->100","26.802; 26.804 ",103,52,null,null,"Wed 13/03/24","Thu 06/03/25"]
[270,1060069,"Stage 2 for Advanced Media Delivery ","AMD-ARCH-MED",1,"Rel-19","S4","Thu 05/12/24","Mon 03/03/25",1,"SP-241963",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","; 6/3/25: 0%->100","26.501; 26.502 ",106,54,null,null,"Thu 05/12/24","Thu 06/03/25"]
[271,1070057,"Stage 3 for Advanced Media Delivery ","AMD_PRO-MED",1,"Rel-19","S4","Wed 05/03/25","Tue 09/09/25",0.4,"SP-250265",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com, for all topics except OpenAPI ","; 5/6/25: 0%->40","26.510; 26.511; 26.512; 26.517; 26.532; 26.247; 26.510; 26.512; 26.517; 26.532 ",107,54,null,null,"Wed 05/03/25","Thu 05/06/25"]
[272,1080004,"CT aspects of Advanced Media Delivery ","AMD_PRO-MED-CT",1,"Rel-19","C4","Fri 06/06/25","Tue 09/09/25",0.25,"CP-251037",null,"Hanna Lim, Qualcomm Incorporated ","hannalim@qti.qualcomm.com",null,"29.520, 29.580, 29.581",107,54,null,null,"Wed 05/03/25","NA"]
[273,1080033,"   CT3 aspects of Advanced Media Delivery ","AMD_PRO-MED-CT",2,"Rel-19","C3","Fri 06/06/25","Tue 09/09/25",0,"CP-251037",null,"Hanna Lim, Qualcomm Incorporated ","hannalim@qti.qualcomm.com",null,"29.520, 29.580, 29.581",107,54,null,null,"Wed 05/03/25","NA"]
[274,1080034,"   CT4 aspects of Advanced Media Delivery ","AMD_PRO-MED-CT",2,"Rel-19","C4","Fri 06/06/25","Tue 09/09/25",0.5,"CP-251037",null,"Hanna Lim, Qualcomm Incorporated ","hannalim@qti.qualcomm.com",null,"29.520, 29.580, 29.581",107,54,null,null,"Wed 05/03/25","NA"]
[275,1030007,"Study of 5G Real-time Transport Protocol Configurations, Phase 2 ","FS_5G_RTP_Ph2",1,"Rel-19","S4","Tue 02/04/24","Thu 12/12/24",1,"SP-240482",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","14/5/24: 26.822 added;; 13/6/24: 0%->40; 4/9/24: 40%->65; 5/12/24: 65%->100","26.822",103,52,null,null,"Wed 13/03/24","Thu 05/12/24"]
[276,1060021,"5G Real-time Transport Protocol Configurations, Phase 2 ","5G_RTP_Ph2",1,"Rel-19","S4","Thu 05/12/24","Tue 09/09/25",0.75,"SP-241961",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","; 6/3/25: 0%->35; 5/6/25: 35%->75; 5/6/25: FCD:Sun 15/06/->/25","26.522; 26.510; 26.113 ",106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[277,1030008,"Study on Beyond 2D Video ","FS_Beyond2D",1,"Rel-19","S4","Tue 02/04/24","Tue 09/09/25",0.7,"SP-240479",null,"Jiayi Xu, ","xujiayi@chinamobile.com ","14/5/24: 26.956 added;; 13/6/24: 0%->10; 4/9/24: 10%->17; 5/12/24: 17%->28; 6/3/25: 28%->50; 6/3/25: FCD:06/06/2025->/25; 5/6/25: 50%->70; 5/6/25: FCD:Fri 06/06/->/25","26.956",103,52,null,null,"Wed 13/03/24","Thu 05/06/25"]
[278,1030009,"Study on Audio Codec APIs ","FS_ACAPI",1,"Rel-19","S4","Tue 02/04/24","Fri 12/12/25",0.47,null,null,"Stefan Döhla ","(stefan DOT doehla AT iis DOT fraunhofer DOT de) ","14/5/24: 26.858 added;; 13/6/24: 0%->10; 5/12/24: 10%->20; 5/12/24: FCD:03/03/2025->/25; 6/3/25: 20%->40; 5/6/25: 40%->47; 5/6/25: FCD:Sat 25/01/->12/25","26.858",103,52,null,null,"Wed 13/03/24","Thu 05/06/25"]
[279,0,"Rel-19 Verticals and Non Public Network","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[280,1060040,"Common API Framework (CAPIF) Phase 3 ","CAPIF_Ph3",1,"Rel-19","S6","Thu 04/01/24","Tue 03/03/26",0.62,"SP-241381",null,"Niranth Amogh, Nokia ","niranth.amogh@nokia.com ",null,"23.222 ",105,53,null,null,"Wed 04/09/24","NA"]
[281,1020062,"   Study on CAPIF Phase 3 ","FS_CAPIF_Ph3",2,"Rel-19","S6","Thu 04/01/24","Thu 12/12/24",1,"SP-231741",null,"Preciado Rojas, Diego, Nokia ","diego.preciado_rojas@nokia.com ","14/3/24: 0%->20; 3/4/24: 23.700-22 added;; 13/6/24: 20%->55; 4/9/24: 55%->90; 5/12/24: 90%->100; 5/12/24: FCD:09/09/2024->12/24","23.700-22",102,52,null,null,"Wed 03/01/24","Thu 05/12/24"]
[282,1050035,"   Stage 2 of Common API Framework (CAPIF) Phase 3 ","CAPIF_Ph3",2,"Rel-19","S6","Fri 04/10/24","Thu 12/12/24",0,"SP-241694",null,"Niranth Amogh, Nokia ","niranth.amogh@nokia.com ","; 8/1/25: WID:SP-241381->SP-241694","23.222 ",105,53,null,null,"Wed 04/09/24","Wed 08/01/25"]
[283,1060026,"   CT aspects of Common API Framework (CAPIF) Phase 3","CAPIF_Ph3",2,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.42,"CP-243074",null,"Paul, Bhaskar, Nokia","bhaskar.paul@nokia.com",null,"29.222",105,53,null,null,"Wed 04/09/24","NA"]
[284,1060041,"      CT3 aspects of Common API Framework (CAPIF) Phase 3","CAPIF_Ph3",3,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.6,"CP-243074",null,"Paul, Bhaskar, Nokia","bhaskar.paul@nokia.com",null,"29.222",105,53,null,null,"Wed 04/09/24","NA"]
[285,1040025,"   Study on security aspects of CAPIF Phase 3 ","FS_CAPIF_Ph3-sec",2,"Rel-19","S3","Wed 12/06/24","Fri 06/06/25",1,"SP-240654",null,"Henry Leung ( Xiaomi) ","lianghaoran@xiaomi.com ","5/9/24: 0%->20; 26/9/24: 33.700-22 added;; 5/12/24: 20%->60; 6/3/25: 60%->60; 5/6/25: 60%->100; 5/6/25: FCD:Thu 17/10/->/25","33.700-22",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[286,1060061,"   Security aspects of CAPIF Phase3 ","CAPIF_Ph3_sec",2,"Rel-19","S3","Thu 30/01/25","Fri 06/06/25",1,"SP-250076",null,"1st rapporteur: Henry Leung (Xiaomi), ","lianghaoran@xiaomi.com ","; 26/3/25: WID:SP-241776->SP-250076; 5/6/25: 0%->100","33.122 ",106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[287,1040015,"   Study on Charging Aspects of CAPIF ","FS_CAPIF_Ph2_CH",2,"Rel-19","S5","Wed 12/06/24","Thu 17/10/24",1,"SP-240981",null,"João Rodrigues, Nokia, ","joao.a.rodrigues@nokia.com ","13/6/24: 0%->15; 4/9/24: 15%->35; 26/9/24: 28.849 added;; 5/12/24: 35%->75; 6/3/25: 75%->100","28.849",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[288,1070015,"   Charging aspects of CAPIF ","CH_CAPIF_EXT",2,"Rel-19","S5","Wed 26/03/25","Tue 09/09/25",0.7,"SP-250366",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","; 6/6/25: 0%->70","32.240; 32.254; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[289,1080014,"   Study on Charging Aspects of CAPIF phase 3 ","FS_CAPIF_Ph3-CH",2,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250504",null,"To be defined ",null,null,null,null,null,null,null,"Thu 05/06/25","NA"]
[290,1080019,"   Converged Charging aspects of CAPIF Phase 3 ","CAPIF_Ph3_con-CH",2,"Rel-19","S5","Thu 05/06/25","Tue 09/09/25",0,"SP-250509",null,null,null,null,"32.254; 32.291; 32.298 ",null,null,null,null,"Thu 05/06/25","NA"]
[291,1060009,"Enhanced OAM for management service exposure to external consumers through CAPIF ","MExpo",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.8,"SP-241942",null,"Winnie Nakimuli (Nokia) ","winnie.nakimuli@nokia.com","6/3/25: 0%->15; 6/6/25: 15%->80",null,106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[292,1000027,"Non-Public Network (NPN) security considerations ","SecNPN",1,"Rel-19","S1","Mon 22/05/23","Tue 06/06/23",1,"SP-230523",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ",null,"22.261 ",100,51,null,null,"Thu 08/06/23","NA"]
[293,1020039,"Study on security for PLMN hosting a NPN ","PLMNNPN_SEC",1,"Rel-19","S3","Wed 03/01/24","Mon 09/09/24",1,"SP-231786",null,"Jun Shen","shenjun6@chinatelecom.cn","4/1/24: 33.757 added;; 14/3/24: 0%->25; 13/6/24: 25%->70; 5/9/24: 70%->75; 5/12/24: 75%->95; 6/3/25: 95%->100; 5/6/25: 100%->100","33.757",102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[294,1060067,"Security for PLMN hosting a NPN ","PLMNNPN",1,"Rel-19","S3","Thu 05/12/24","Fri 06/06/25",1,"SP-241782",null,"Jun Shen ","shenjun6@chinatelecom.cn ","; 6/3/25: 0%->90; 5/6/25: 90%->100","33.501 ",106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[295,1050080,"ProSe support in NPN ","TEI19_ProSe_NPN",1,"Rel-19",null,"Wed 13/03/24","Tue 09/09/25",0.9,"SP-240122",null,"Walter Dees, Philips International B.V., ","walter.dees@philips.com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.304; 23.501 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[296,1030016,"   Stage 2 of ProSe support in NPN ","TEI19_ProSe_NPN",2,"Rel-19","S2","Wed 13/03/24","Thu 06/06/24",1,"SP-240122",null,"Walter Dees, Philips International B.V., ","walter.dees@philips.com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.304; 23.501 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[297,1050021,"   CT aspects of ProSe support in NPN ","TEI19_ProSe_NPN",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.9,"CP-243264",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[298,1050081,"      CT1 aspects of ProSe support in NPN ","TEI19_ProSe_NPN",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",1,"CP-243264",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[299,1060042,"      CT3 aspects of ProSe support in NPN ","TEI19_ProSe_NPN",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",1,"CP-243264",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[300,1050082,"      CT4 aspects of ProSe support in NPN ","TEI19_ProSe_NPN",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.95,"CP-243264",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[301,1050083,"      DELETED - CT6 aspects of ProSe support in NPN ","TEI19_ProSe_NPN",3,"Rel-19","C6","Mon 30/12/24","Tue 09/09/25",1,"CP-243264",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,108,null,"Wed 13/03/24","Thu 13/06/24"]
[302,1040009,"Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs","NBI19",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.62,"CP-243079",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,"24.558, 24.559, 24.549, 29.116, 29.122, 29.222, 29.255, 29.257, 29.343, 29.435, 29.486, 29.522, 29.538, 29.548, 29.549, 29.558, 29.583",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[303,1040060,"   CT1 aspects of Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs","NBI19",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-243079",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[304,1040061,"   CT3 aspects of Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs","NBI19",2,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.85,"CP-243079",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[305,0,"Rel-19 Radio: NR-only, band-related",null,1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,null,null,null,null,null,null,null,null,null,null,"Thu 07/12/23","NA"]
[306,1060083,"7MHz Channel Bandwidth for n26 and n5 ","NR_FR1_7MHz_BW",1,"Rel-19","R4","Sun 19/05/24","Mon 08/09/25",0.34,"RP-250373",null,"China Telecom",null,"3/4/25: WID:RP-243323->RP-250373; rapporteur: T-Mobile => China Telecom",null,106,54,null,null,"Fri 24/01/25","Thu 03/04/25"]
[307,1061083,"   Core part: 7MHz Channel Bandwidth for n26 and n5 ","NR_FR1_7MHz_BW-Core",2,"Rel-19","R4","Mon 14/10/24","Tue 09/09/25",0.55000000000000004,"RP-250373","RP-251454","China Telecom",null,"6/3/25: FCD:07/09/2025->09/09/2025; Compl:0%->10%; Stat Rep: ->RP-250374; ; 6/6/25: Compl:10%->55%; Stat Rep: RP-250374->RP-251454; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[308,1062083,"   Perf. Part: 7MHz Channel Bandwidth for n26 and n5 ","NR_FR1_7MHz_BW-Perf",2,"Rel-19","R4","Mon 14/10/24","Tue 03/03/26",0.2,"RP-250373","RP-251454","China Telecom",null,"6/3/25: FCD:07/09/2025->03/03/2026; Stat Rep: ->RP-250374; ; 6/6/25: Compl:0%->20%; Stat Rep: RP-250374->RP-251454; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[309,1040127,"Introduction of the NR FDD 1.4 GHz band ","NR_FDD_1400MHz",1,"Rel-19","R4","Thu 06/06/24","Thu 12/12/24",1,"RP-250760",null,"MidWave Wireless ",null,"26/9/24: WID:RP-241648->RP-242120; 3/4/25: WID:RP-242120->RP-250760",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[310,1041127,"   Core part: Introduction of the NR FDD 1.4 GHz band ","NR_FDD_1400MHz-Core",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-250760","RP-250403","MidWave Wireless ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->40%; Stat Rep: ->RP-242117; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:40%->99%; WID: RP-242120->RP-241648; Stat Rep: RP-242117->RP-242494; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:99%->100%; Stat Rep: R",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[311,1042127,"   Perf. part: Introduction of the NR FDD 1.4 GHz band ","NR_FDD_1400MHz-Perf",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-250760","RP-250403","MidWave Wireless ",null,"4/9/24: FCD:03/03/2025->24/12/2024; Compl:0%->40%; Stat Rep: ->RP-242117; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:40%->99%; WID: RP-242120->RP-241648; Stat Rep: RP-242117->RP-242494; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:99%->100%; Stat Rep: R",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[312,1040131,"Introduction of NR bands n87 and n88 ","NR_bands_n87_n88",1,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-242501",null,"Nokia ",null,"26/9/24: WID:RP-241663->RP-242338; 24/1/25: WID:RP-242338->RP-242501",null,104,53,null,null,"Tue 23/07/24","Fri 24/01/25"]
[313,1041131,"   Core part: Introduction of NR bands n87 and n88 ","NR_bands_n87_n88-Core",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-242501","RP-250149","Nokia ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->33%; Stat Rep: ->RP-241816; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:33%->66%; Stat Rep: RP-241816->RP-242500; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:66%->100%; Stat Rep: RP-242500->RP-250149; ",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[314,1042131,"   Perf. part: Introduction of NR bands n87 and n88 ","NR_bands_n87_n88-Perf",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-242501","RP-250149","Nokia ",null,"4/9/24: FCD:03/03/2025->25/03/2025; Compl:0%->33%; Stat Rep: ->RP-241816; ; 6/12/24: Compl:33%->66%; Stat Rep: RP-241816->RP-242500; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:66%->100%; Stat Rep: RP-242500->RP-250149; ",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[315,1040132,"Introduction of NR band n68 ","NR_band_n68",1,"Rel-19","R4","Thu 06/06/24","Thu 12/12/24",1,"RP-250763",null,"Ericsson ",null,"24/1/25: WID:RP-241664->RP-242606; 3/4/25: WID:RP-242606->RP-250763",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[316,1041132,"   Core part: Introduction of NR band n68 ","NR_band_n68-Core",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-250763","RP-250525","Ericsson ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->25%; WID: RP-241664->RP-231664; Stat Rep: ->RP-241861; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:25%->60%; WID: RP-231664->RP-241664; Stat Rep: RP-241861->RP-242605; ; 6/3/25: FCD:09/12/2024->03/03/2025; C",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[317,1042132,"   Perf. part: Introduction of NR band n68 ","NR_band_n68-Perf",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-250763","RP-250525","Ericsson ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->25%; WID: RP-241664->RP-231664; Stat Rep: ->RP-241861; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:25%->60%; WID: RP-231664->RP-241664; Stat Rep: RP-241861->RP-242605; ; 6/3/25: FCD:09/12/2024->03/03/2025; C",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[318,1040121,"Additional NR bands for NR features in Rel-19 ","NR_bands_xFeature_R19",1,"Rel-19","R4","Thu 06/06/24","Mon 09/09/24",0.75,"RP-250211",null,"ZTE ",null,"26/9/24: WID:RP-241677->RP-241922; 24/1/25: WID:RP-241922->RP-242572; 3/4/25: WID:RP-242572->RP-250211",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[319,1041121,"   Core part: Additional NR bands for NR features in Rel-19 ","NR_bands_xFeature_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.75,"RP-250211","RP-251251","ZTE ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-241923; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->35%; Stat Rep: RP-241923->RP-242573; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:35%->50%; Stat Rep: RP-242573->RP-250212; ; 6/6/2",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[320,1040120,"Rel-19 NR CA/DC for x bands DL with y bands UL (x<7, y<3) and SUL/CA band combinations with a single SUL or two SUL cells ","NR_CADC_SUL_R19",1,"Rel-19","R4","Thu 06/06/24","Mon 09/09/24",0.44,"RP-250214",null,"Ericsson ",null,"26/9/24: WID:RP-241674->RP-241833; 3/4/25: WID:RP-241833->RP-250214",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[321,1041120,"   Core part: Rel-19 NR Carrier Aggregation (CA)/Dual Connectivity (DC) for x bands DL with y bands UL (x<7, y<3) and Supplementary Uplink (SUL) band combinations/CA band combinations with a single SUL or two SUL cells ","NR_CADC_SUL_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.44,"RP-250214","RP-251256","Ericsson ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->20%; Stat Rep: ->RP-241832; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:20%->34%; Stat Rep: RP-241832->RP-242753; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:34%->35%; WID: RP-241833->RP-242754; Stat Rep: RP",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[322,1050120,"Multi-carrier enhancements for NR Phase 2 ","NR_MC_enh2",1,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.9,"RP-242904",null,"Lenovo ",null,"24/1/25: WID:RP-242408->RP-242904",null,105,53,null,null,"Thu 26/09/24","Fri 24/01/25"]
[323,1051120,"   Core part: Multi-carrier enhancements for NR Phase 2 ","NR_MC_enh2-Core",2,"Rel-19","R1","Mon 09/09/24","Tue 09/09/25",0.9,"RP-242904","RP-251421","Lenovo ",null,"6/12/24: FCD:09/09/2025->06/06/2025; Compl:0%->40%; Stat Rep: ->RP-242903; ; 6/3/25: FCD:16/03/2025->09/09/2025; Compl:40%->80%; Stat Rep: RP-242903->RP-250413; ; 6/6/25: Compl:80%->90%; Stat Rep: RP-250413->RP-251421; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[324,0,"Rel-19 Radio: NR-only, topics other than band",null,1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,null,null,null,null,null,null,null,null,null,null,"Thu 07/12/23","NA"]
[325,1060082,"Low band carrier aggregation via switching ","NR_LBCA_Sw",1,"Rel-19",null,"Thu 06/03/25","Tue 03/03/26",0.2,"RP-250247",null,"AT&T ",null,"3/4/25: WID:RP-243317->RP-250247",null,106,54,null,null,"Fri 24/01/25","Thu 03/04/25"]
[326,1061082,"   Core part: Low band carrier aggregation via switching ","NR_LBCA_Sw-Core",2,"Rel-19","R4","Thu 06/03/25","Tue 09/09/25",0.6,"RP-250247","RP-251316","AT&T ",null,"6/3/25: Compl:0%->10%; Stat Rep: ->RP-250246; ; 26/3/25: 38.768 added;; 6/6/25: Compl:10%->60%; Stat Rep: RP-250246->RP-251316; List of Impacted TS & TR updated; ",38.768000000000001,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[327,1062082,"   Perf. part: Low band carrier aggregation via switching ","NR_LBCA_Sw-Perf",2,"Rel-19","R4","Thu 06/03/25","Tue 03/03/26",0,"RP-250247","RP-251316","AT&T ",null,"6/3/25: Stat Rep: ->RP-250246; ; 6/6/25: Stat Rep: RP-250246->RP-251316; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[328,1050126,"mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection ","NR_mmWave_protect",1,"Rel-19",null,"Mon 09/09/24","Fri 06/06/25",1,"RP-250818",null,"China Unicom ",null,"24/1/25: WID:RP-242371->RP-242611; 3/4/25: WID:RP-242611->RP-250818",null,105,53,null,null,"Thu 26/09/24","Thu 03/04/25"]
[329,1051126,"   Core part: mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection ","NR_mmWave_protect-Core",2,"Rel-19","R4","Mon 09/09/24","Fri 06/06/25",1,"RP-250818","RP-251593","China Unicom ",null,"6/12/24: Compl:0%->40%; Stat Rep: ->RP-242612; ; 6/3/25: FCD:16/03/2025->06/06/2025; Compl:40%->80%; Stat Rep: RP-242612->RP-250429; ; 6/6/25: Compl:80%->100%; Stat Rep: RP-250429->RP-251593; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[330,1052126,"   Perf. part: mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection ","NR_mmWave_protect-Perf",2,"Rel-19","R4","Mon 09/09/24","Fri 06/06/25",1,"RP-250818","RP-251593","China Unicom ",null,"6/12/24: Compl:0%->40%; Stat Rep: ->RP-242612; ; 6/3/25: FCD:16/03/2025->06/06/2025; Compl:40%->80%; Stat Rep: RP-242612->RP-250429; ; 6/6/25: Compl:80%->100%; Stat Rep: RP-250429->RP-251593; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[331,1040100,"Study on spatial channel model for demodulation performance requirements for NR ","FS_NR_demod_SCM",1,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.7,"RP-250577","RP-251258","Nokia ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->15%; Stat Rep: ->RP-241844; ; 26/9/24: WID:RP-241610->RP-241848; 26/9/24: 38.753 added;; 6/12/24: Compl:15%->40%; WID: RP-241848->RP-241610; Stat Rep: RP-241844->RP-242465; ; 6/3/25: FCD:14/02/2025->06/06/202",38.753,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[332,1040101,"Study on NR FR1 DL fragmented carriers ","FS_NR_FR1_DL_Frag_Carrier",1,"Rel-19","R4","Thu 06/06/24","Fri 06/06/25",1,"RP-243002","RP-251287","Mediatek ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->5%; Stat Rep: ->RP-242054; ; 26/9/24: WID:RP-241669->RP-242404; 26/9/24: 38.755 added;; 6/12/24: Compl:5%->25%; Stat Rep: RP-242054->RP-243001; ; 24/1/25: WID:RP-242404->RP-243002; 6/3/25: FCD:14/02/2025->06/",38.755000000000003,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[333,1020081,"Study on channel modelling enhancements for 7-24GHz for NR ","FS_NR_7_24GHz_CHmod",1,"Rel-19","R1","Wed 13/12/23","Fri 06/06/25",1,"RP-234018","RP-251240","LEE Daewon, Intel Corporation","daewon.lee@intel.com","14/3/24: Stat Rep: ->RP-240265; Rapporteur: Intel->LEE Daewon, Intel Corporation; Rap eMail: ->daewon.lee@intel.com; ; 13/6/24: Compl:0%->15%; Stat Rep: RP-240265->RP-241099; ; 4/9/24: FCD:06/06/2025->25/06/2025; Compl:15%->35%; Stat Rep: RP-241099->RP-24",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[334,1050125,"Additional topological enhancements for NR ","NR_WAB_5GFemto",1,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.85,"RP-243009",null,"NTT DOCOMO ",null,"24/1/25: WID:RP-242395->RP-243009",null,105,53,null,null,"Thu 26/09/24","Fri 24/01/25"]
[335,1051125,"   Core part: Additional topological enhancements for NR ","NR_WAB_5GFemto-Core",2,"Rel-19","R3","Mon 09/09/24","Tue 09/09/25",0.85,"RP-243009","RP-251410","NTT DOCOMO ",null,"6/12/24: Compl:0%->30%; Stat Rep: ->RP-243006; ; 6/3/25: FCD:20/05/2025->09/09/2025; Compl:30%->60%; Stat Rep: RP-243006->RP-250357; ; 6/6/25: Compl:60%->85%; Stat Rep: RP-250357->RP-251410; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[336,1020082,"Study on additional topological enhancements for NR ","FS_NR_WAB_5GFemto",1,"Rel-19","R3","Mon 09/09/24","Tue 09/09/25",1,"RP-241264","RP-241963","Min, Tianyang, NTT DOCOMO","tianyang.min.ex@nttdocomo.com","14/3/24: FCD:28/05/2021->09/09/2024; Stat Rep: ->RP-240320; Rapporteur: NTT DOCOMO->Min, Tianyang, NTT DOCOMO; Rap eMail: ->tianyang.min.ex@nttdocomo.com; ; 2/4/24: WID:RP-234041->RP-240319; 3/4/24: 38.799 added;; 13/6/24: Compl:0%->70%; Stat Rep: RP-2...","38.799",102,52,null,null,"Tue 02/01/24","Thu 26/09/24"]
[337,1030084,"NR Sidelink: Intra-band Carrier Aggregation in ITS band ","NR_SL_intraB_CA_ITS",1,"Rel-19",null,"Sun 03/03/24","Mon 09/09/24",1,"RP-240840",null,"OPPO ",null,null,null,103,52,null,null,"Tue 02/04/24","NA"]
[338,1031084,"   Core part: NR Sidelink: Intra-band Carrier Aggregation in ITS band ","NR_SL_intraB_CA_ITS-Core",2,"Rel-19","R4","Sun 03/03/24","Fri 06/06/25",1,"RP-240840","RP-250996","OPPO ",null,"14/5/24: 38.787 added;; 13/6/24: Compl:0%->15%; Stat Rep: ->RP-241152; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:15%->25%; Stat Rep: RP-241152->RP-241843; ; 6/12/24: FCD:09/09/2024->04/03/2024; Compl:25%->0%; Stat Rep: RP-241843->RP-242789; ; 6/3/25: FC",38.786999999999999,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[339,1040114,"NR sidelink multi-hop relay ","NR_SL_relay_multihop",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.85,"RP-250188",null,"LG Electronics ",null,"26/9/24: WID:RP-241609->RP-242349; 3/4/25: WID:RP-242349->RP-250188",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[340,1041114,"   Core part: NR sidelink multi-hop relay ","NR_SL_relay_multihop-Core",2,"Rel-19","R2","Thu 06/06/24","Tue 09/09/25",0.85,"RP-250188","RP-250969","LG Electronics ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-241750; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->40%; Stat Rep: RP-241750->RP-242529; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:40%->60%; Stat Rep: RP-242529->RP-250187; ; 6/6/2",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[341,1020089,"NR MIMO Phase 5 ","NR_MIMO_Ph5",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.55000000000000004,"RP-242394",null,"Samsung ",null,"2/4/24: WID:RP-234007->RP-240087; 26/9/24: WID:RP-240087->RP-242394",null,102,52,null,null,"Tue 02/01/24","Thu 26/09/24"]
[342,1021089,"   Core part: NR MIMO Phase 5 ","NR_MIMO_Ph5-Core",2,"Rel-19","R1","Wed 13/12/23","Tue 09/09/25",0.95,"RP-242394","RP-251014","Eko Onggosanusi, Samsung","eko.o@samsung.com","14/3/24: Compl:0%->15%; Stat Rep: ->RP-240086; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com; ; 13/6/24: Compl:15%->35%; WID: RP-240087->RP-234007; Stat Rep: RP-240086->RP-241051; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[343,1022089,"   Perf. part: NR MIMO Phase 5 ","NR_MIMO_Ph5-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0.1,"RP-242394","RP-251014","Eko Onggosanusi, Samsung","eko.o@samsung.com","14/3/24: Stat Rep: ->RP-240086; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com; ; 13/6/24: WID: RP-240087->RP-234007; Stat Rep: RP-240086->RP-241051; ; 4/9/24: FCD:03/03/2026->26/03/2025; WID: RP-234007->RP-240087; Stat Rep:",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[344,1020090,"Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.55000000000000004,"RP-241614",null,"Huawei ",null,"2/4/24: WID:RP-234035->RP-240789; 23/7/24: WID:RP-240789->RP-241614",null,102,52,null,null,"Tue 02/01/24","Tue 23/07/24"]
[345,1021090,"   Core part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo-Core",2,"Rel-19","R1","Wed 13/12/23","Tue 09/09/25",0.93,"RP-241614","RP-251644","Xinghua Song, He (Jackson) Wang, Huawei, Samsung","songxinghua@huawei.com, h0809.wang@samsung.com","14/3/24: Compl:0%->7%; Stat Rep: ->RP-240171; Rapporteur: Huawei->Xinghua Song, He (Jackson) Wang, Huawei, Samsung; Rap eMail: ->songxinghua@huawei.com, h0809.wang@samsung.com; ; 13/6/24: Compl:7%->18%; Stat Rep: RP-240171->RP-241286; ; 4/9/24: FCD:09/09/",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[346,1022090,"   Perf. part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0.13,"RP-241614","RP-251644","Xinghua Song, He (Jackson) Wang, Huawei, Samsung","songxinghua@huawei.com, h0809.wang@samsung.com","14/3/24: Stat Rep: ->RP-240171; Rapporteur: Huawei->Xinghua Song, He (Jackson) Wang, Huawei, Samsung; Rap eMail: ->songxinghua@huawei.com, h0809.wang@samsung.com; ; 13/6/24: Stat Rep: RP-240171->RP-241286; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: R",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[347,1020091,"NR mobility enhancements Phase 4 ","NR_Mob_Ph4",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.59,"RP-250339",null,"Apple ",null,"2/4/24: WID:RP-234036->RP-240299; 23/7/24: WID:RP-240299->RP-241515; 26/9/24: WID:RP-241515->RP-242356; 3/4/25: WID:RP-242356->RP-250339",null,102,52,null,null,"Tue 02/01/24","Thu 03/04/25"]
[348,1021091,"   Core part: NR mobility enhancements Phase 4 ","NR_Mob_Ph4-Core",2,"Rel-19","R2","Wed 13/12/23","Tue 09/09/25",0.91,"RP-250339","RP-251187","Naveen Palle, Apple Inc.","naveen.palle@apple.com","14/3/24: Stat Rep: ->RP-240298; Rapporteur: Apple->Naveen Palle, Apple Inc.; Rap eMail: ->naveen.palle@apple.com; ; 13/6/24: Compl:0%->5%; Stat Rep: RP-240298->RP-241514; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:5%->20%; Stat Rep: RP-241514->RP-241915;",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[349,1022091,"   Perf. part: NR mobility enhancements Phase 4 ","NR_Mob_Ph4-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0,"RP-250339","RP-251187","Naveen Palle, Apple Inc.","naveen.palle@apple.com","14/3/24: Stat Rep: ->RP-240298; Rapporteur: Apple->Naveen Palle, Apple Inc.; Rap eMail: ->naveen.palle@apple.com; ; 13/6/24: Stat Rep: RP-240298->RP-241514; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241514->RP-241915; ; 6/12/24: FCD:03/03/2025->0",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[350,1040023,"   Security aspects of NR mobility enhancement Phase 4 ","NR_Mob_Ph4_Sec",2,"Rel-19","S3","Tue 16/07/24","Fri 06/06/25",1,"SP-240652",null,"Rajavelsamy R ","rajvel@samsung.com ","; 6/3/25: 0%->70; 6/3/25: FCD:03/03/2025->/25; 5/6/25: 70%->100; 5/6/25: FCD:Thu 27/02/->/25","33.501 ",104,53,null,null,"Tue 16/07/24","Thu 05/06/25"]
[351,1020092,"Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 ","NR_ENDC_SON_MDT_Ph4",1,"Rel-19",null,"Wed 13/12/23","Mon 09/09/24",0.85,"RP-234038",null,"China Unicom ",null,null,null,102,52,null,null,"Tue 02/01/24","NA"]
[352,1021092,"   Core part: Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 ","NR_ENDC_SON_MDT_Ph4-Core",2,"Rel-19","R3","Wed 13/12/23","Tue 09/09/25",0.85,"RP-234038","RP-251000","Xufei Dong, China Unicom","dongxf37@chinaunicom.cn","14/3/24: Stat Rep: ->RP-240118; Rapporteur: China Unicom->Xufei Dong, China Unicom; Rap eMail: ->dongxf37@chinaunicom.cn; ; 13/6/24: Compl:0%->15%; Stat Rep: RP-240118->RP-241081; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:15%->30%; Stat Rep: RP-241081->",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[353,780060,"Study on 6 GHz for LTE and NR","FS_6GHz_LTE_NR",1,"Rel-19","RP","Fri 15/12/17","Sun 03/03/24",1,"RP-234033","RP-231702","Dominique Everaere, Ericsson","dominique.everaere@ericsson.com","27/3/18: Compl:0%->25%27/3/18: WID: RP-172804->RP-180168¦27/3/18: 37.890 added;¦27/3/18: 37.107 added;¦27/6/18: Compl:25%->30%¦27/6/18: CD:Fri 15/¦26/3/19: WID:RP-181019->RP-190681; 26/6/19: WID:RP-190681->RP-190957¦01/24: Rel-18->Rel-19; 2/1/24: WID:R...","37.890; 37.107",78,40,null,null,"Mon 08/01/18","Tue 02/04/24"]
[354,1030074,"Study on NR FR2 OTA (Over the Air) testing Phase 3 ","FS_NR_FR2_OTA_Ph3",1,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.98,"RP-242833","RP-251277","Qualcomm ",null,"13/6/24: Compl:0%->30%; Stat Rep: SI ->RP-241157; ; 23/7/24: WID:RP-240856->RP-241158; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:30%->70%; Stat Rep: RP-241157->RP-241845; ; 26/9/24: WID:RP-241158->RP-242400; 26/9/24: 38.771 added;; 6/12/24: FCD:09/09/2024",38.771000000000001,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[355,1030075,"Study on IMT parameters for NR for 4400 to 4800 MHz, 7125 to 8400 MHz and 14800 to 15350 MHz ","FS_NR_IMT_4400_7125_14800MHz",1,"Rel-19","R4","Thu 07/03/19","Mon 03/03/25",1,"RP-242944","RP-250538","Ericsson ",null,"14/5/24: 38.922 added;; 23/7/24: WID:RP-240787->RP-241326; 4/9/24: FCD:09/03/2021->24/12/2024; Compl:0%->50%; Stat Rep: SI ->RP-241840; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:50%->95%; Stat Rep: RP-241840->RP-242943; ; 24/1/25: WID:RP-241326->RP-242","38.922",103,52,null,null,"Tue 02/04/24","Thu 06/03/25"]
[356,1030078,"NR base station (BS) RF requirement evolution for FR1/FR2 and testing ","NR_BS_RF_req_evo",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.53,"RP-243270",null,"ZTE ",null,"23/7/24: WID:RP-240829->RP-241284; 26/9/24: WID:RP-241284->RP-242010; 24/1/25: WID:RP-242010->RP-243270",null,103,52,null,null,"Tue 02/04/24","Fri 24/01/25"]
[357,1031078,"   Core part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing ","NR_BS_RF_req_evo-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.7,"RP-243270","RP-251435","ZTE ",null,"13/6/24: Compl:0%->10%; Stat Rep: ->RP-241285; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:10%->20%; Stat Rep: RP-241285->RP-242011; ; 26/9/24: 38.908 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:20%->30%; Stat Rep: RP-242011->RP-242831; ; 6/3/25: F",38.908000000000001,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[358,1032078,"   Perf. part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing ","NR_BS_RF_req_evo-Perf",2,"Rel-19","R4","Sun 03/03/24","Tue 03/03/26",0.4,"RP-243270","RP-251435","ZTE ",null,"13/6/24: Stat Rep: ->RP-241285; ; 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->5%; Stat Rep: RP-241285->RP-242011; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:5%->10%; Stat Rep: RP-242011->RP-242831; ; 6/3/25: FCD:22/07/2025->03/03/2026; Compl:10%->30%;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[359,1030079,"NR Radio Resource Management (RRM) Phase 5 ","NR_RRM_Ph5",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.56999999999999995,"RP-242380",null,"Apple ",null,"26/9/24: WID:RP-240830->RP-242380",null,103,52,null,null,"Tue 02/04/24","Thu 26/09/24"]
[360,1031079,"   Core part: NR Radio Resource Management (RRM) Phase 5 ","NR_RRM_Ph5-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.9,"RP-242380","RP-251343","Apple ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241268; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:5%->25%; Stat Rep: RP-241268->RP-241971; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:25%->60%; Stat Rep: RP-241971->RP-242569; ; 6/3/25: FCD:23/03/2025->09/09/2025;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[361,1032079,"   Perf. part: NR Radio Resource Management (RRM) Phase 5 ","NR_RRM_Ph5-Perf",2,"Rel-19","R4","Sun 13/10/24","Tue 03/03/26",0.2,"RP-242380","RP-251343","Apple ",null,"13/6/24: Stat Rep: ->RP-241268; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241268->RP-241971; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-241971->RP-242569; ; 6/3/25: Stat Rep: RP-242569->RP-250320; ; 6/6/25: Compl:0%->20%; Stat Rep: RP-25",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[362,1030080,"NR demodulation performance Phase 5 ","NR_demod_Ph5",1,"Rel-19",null,"Sun 03/03/24","Mon 09/09/24",0.86,"RP-241297",null,"China Telecom ",null,"23/7/24: WID:RP-240831->RP-241297",null,103,52,null,null,"Tue 02/04/24","Tue 23/07/24"]
[363,1032080,"   Perf. part: NR demodulation performance Phase 5 ","NR_demod_Ph5-Perf",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.86,"RP-241297","RP-251447","China Telecom ",null,"13/6/24: FCD:03/03/2026->09/09/2025; Stat Rep: ->RP-241296; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->14%; Stat Rep: RP-241296->RP-241996; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:14%->43%; Stat Rep: RP-241996->RP-242855; ; 6/3/25: FCD:23/03/202",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[364,1030081,"NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2",1,"Rel-19",null,"Sun 03/03/24","Fri 06/06/25",1,"RP-250781",null,"Intel ",null,"23/7/24: WID:RP-240832->RP-241622; 24/1/25: WID:RP-241622->RP-243309; 3/4/25: WID:RP-243309->RP-250781",null,103,52,null,null,"Tue 02/04/24","Thu 03/04/25"]
[365,1031081,"   Core part: NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2-Core",2,"Rel-19","R4","Sun 03/03/24","Mon 03/03/25",1,"RP-250781","RP-250462","Intel ",null,"13/6/24: Compl:0%->25%; Stat Rep: ->RP-241496; ; 4/9/24: FCD:12/12/2024->24/12/2024; Compl:25%->70%; Stat Rep: RP-241496->RP-242031; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:73%->99%; Stat Rep: RP-242031->RP-243146; ; 6/3/25: FCD:12/11/2024->03/03/202",null,103,52,null,null,"Tue 02/04/24","Thu 06/03/25"]
[366,1032081,"   Perf. part: NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2-Perf",2,"Rel-19","R4","Sun 21/07/24","Fri 06/06/25",1,"RP-250781","RP-251669","Intel ",null,"13/6/24: Stat Rep: ->RP-241496; ; 6/12/24: Stat Rep: RP-241496->RP-243146; ; 6/3/25: Compl:0%->30%; Stat Rep: RP-243146->RP-250462; ; 6/6/25: Compl:30%->100%; Stat Rep: RP-250462->RP-251669; ",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[367,1030083,"Enhancements for Air-to-ground network for NR ","NR_ATG_enh",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.63,"RP-243285",null,"CMCC ",null,"23/7/24: WID:RP-240839->RP-241213; 26/9/24: WID:RP-241213->RP-242381; 24/1/25: WID:RP-242381->RP-243285",null,103,52,null,null,"Tue 02/04/24","Fri 24/01/25"]
[368,1031083,"   Core part: Enhancements for Air-to-ground network for NR ","NR_ATG_enh-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.9,"RP-243285","RP-251400","CMCC ",null,"13/6/24: Compl:0%->10%; Stat Rep: ->RP-241214; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:10%->25%; Stat Rep: RP-241214->RP-241933; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:25%->55%; Stat Rep: RP-241933->RP-242960; ; 6/3/25: FCD:23/03/2025->09/09/202",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[369,1032083,"   Perf. part: Enhancements for Air-to-ground network for NR ","NR_ATG_enh-Perf",2,"Rel-19","R4","Sun 13/10/24","Tue 03/03/26",0.33,"RP-243285","RP-251400","CMCC ",null,"13/6/24: Stat Rep: ->RP-241214; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241214->RP-241933; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-241933->RP-242960; ; 6/3/25: Stat Rep: RP-242960->RP-250271; ; 6/6/25: Compl:0%->33%; Stat Rep: RP-25",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[370,1040123,"Rel-19 High power UE (power class 1.5 or 2) for NR intra-band Carrier Aggregation (CA) or NR inter-band CA/Dual connectivity (DC) band combinations with/without NR Supplementary Uplink (UL)","HPUE_NR_CADC_SUL_R19",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.65,"RP-250806",null,"China Telecom ",null,"26/9/24: WID:RP-241679->RP-242003; 24/1/25: WID:RP-242003->RP-242754; 24/1/25: WID:RP-242754->RP-242865; 3/4/25: WID:RP-242865->RP-250806",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[371,1041123,"   Core part: Rel-19 High power UE (power class 1.5 or 2) for NR intra-band Carrier Aggregation (CA) or NR inter-band CA/Dual connectivity (DC) band combinations with/without NR Supplementary Uplink (UL)","HPUE_NR_CADC_SUL_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.65,"RP-242865","RP-251451","China Telecom ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-242004; ; 26/9/24: 38.794 added;; 26/9/24: 38.746 added;; 26/9/24: 38.750 added;; 26/9/24: 38.792 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:10%->30%; Stat Rep: RP-242004->RP-24286","38.794; 38.746; 38.750; 38.792",104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[372,1040124,"Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA UEs, and high power UE operation (power class 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band","HPUE_NR_FR1_bands_R19",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.85,"RP-241932",null,"CMCC ",null,"26/9/24: WID:RP-241680->RP-241932",null,104,53,null,null,"Tue 23/07/24","Thu 26/09/24"]
[373,1041124,"   Core part: Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA Ues, and high power UE operation (power class 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band","HPUE_NR_FR1_bands_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.85,"RP-241932","RP-251401","CMCC ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-241931; ; 26/9/24: 38.795 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->30%; Stat Rep: RP-241931->RP-242959; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:30%->55%; Stat Rep: RP-24",38.795000000000002,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[374,1040128,"Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 ","NR_n28_PC2_40MHz_CBW",1,"Rel-19",null,"Thu 06/06/24","Thu 12/12/24",0.77,"RP-243321",null,"CMCC ",null,"26/9/24: WID:RP-241660->RP-241930; 24/1/25: WID:RP-241930->RP-243321",null,104,53,null,null,"Tue 23/07/24","Fri 24/01/25"]
[375,1041128,"   Core part: Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 ","NR_n28_PC2_40MHz_CBW-Core",2,"Rel-19","R4","Thu 06/06/24","Fri 06/06/25",1,"RP-243321","RP-250273","CMCC ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->20%; Stat Rep: ->RP-241929; ; 6/12/24: Compl:20%->99%; Stat Rep: RP-241929->RP-242957; ; 6/3/25: FCD:15/10/2024->06/06/2025; Compl:99%->100%; Stat Rep: RP-242957->RP-250273; ",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[376,1070062,"   UE Conformance - Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 ","NR_n28_PC2_40MHz_CBW-UEConTest",2,"Rel-19","R5","Mon 03/03/25","Tue 03/03/26",0.54,"RP-250249","RP-251380","CMCC ",null,"6/6/25: Compl:0%->54%; Stat Rep: ->RP-251380; ",null,107,54,null,null,"Wed 26/03/25","Fri 06/06/25"]
[377,0,"Rel-19 Radio: NR and LTE","-",1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[378,1040118,"Rel-19 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R19",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.8,"RP-250369",null,"China Telecom ",null,"basket WI; no Perf. part; compare DL_intrpt_combos_TxSW_R18; TR 37.8xx ; 3/4/25: WID:RP-241672->RP-250369",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[379,1041118,"   Core part: Rel-19 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.8,"RP-250369","RP-251449","China Telecom ",null,"basket WI; no Perf. part; compare DL_intrpt_combos_TxSW_R18; TR 37.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-241999; ; 26/9/24: 37.887 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:10%->20%; Stat Rep: RP-241999->RP-2428",37.887,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[380,1040126,"Adding channel bandwidth(s) support to existing NR bands and CA/ENDC combinations in REL-19 ","NR_bands_CA_ENDC_R19_BWs",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.9,"RP-250524",null,"Ericsson ",null,"basket WI; no Perf. part; compare: NR_bands_R18_BWs; TR 37.8xx ; 26/9/24: WID:RP-241684->RP-242402; 24/1/25: WID:RP-242402->RP-242604; 3/4/25: WID:RP-242604->RP-250524",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[381,1041126,"   Core part: Adding channel bandwidth(s) support to existing NR bands and CA/ENDC combinations in REL-19 ","NR_bands_CA_ENDC_R19_BWs-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.9,"RP-250524","RP-251159","Ericsson ",null,"basket WI; no Perf. part; compare: NR_bands_R18_BWs; TR 37.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->5%; WID: RP-241684->RP-231684; Stat Rep: ->RP-241757; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:5%->15%; Stat Rep: RP-241757->RP-242603; ; 6",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[382,1040122,"Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) ","HPUE_DC_LTE_NR_R19",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.6,"RP-250424",null,"China Unicom ",null,"basket WI; no Perf. part; compare HPUE_FR1_DC_LTE_NR_R18 and DC_R19_xBLTE_yBNR ; 26/9/24: WID:RP-241678->RP-242341; 24/1/25: WID:RP-242341->RP-242609; 3/4/25: WID:RP-242609->RP-250424",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[383,1041122,"   Core part: Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) ","HPUE_DC_LTE_NR_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.6,"RP-250424","RP-251594","China Unicom ",null,"basket WI; no Perf. part; compare HPUE_FR1_DC_LTE_NR_R18 and DC_R19_xBLTE_yBNR ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-242019; ; 26/9/24: 37.898 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->30%; Stat Rep: RP-242019-",37.898000000000003,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[384,1040125,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-19 ","LTE_NR_R19_Simult_RxTx",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.75,"RP-242088",null,"Huawei ",null,"basket WI; no Perf. part; compare REL-18 WI LTE_NR_Simult_RxTx_R18 and REL-17 WI LTE_NR_Simult_RxTx; TR 37.8xx ; 26/9/24: WID:RP-241682->RP-242088",null,104,53,null,null,"Tue 23/07/24","Thu 26/09/24"]
[385,1041125,"   Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-19 ","LTE_NR_R19_Simult_RxTx-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.75,"RP-242088","RP-251535","Huawei ",null,"basket WI; no Perf. part; compare REL-18 WI LTE_NR_Simult_RxTx_R18 and REL-17 WI LTE_NR_Simult_RxTx; TR 37.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-242087; ; 26/9/24: 38.793 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Comp",38.792999999999999,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[386,1040119,"Rel-19 Dual connectivity (DC) of x LTE band(s), y NR band(s) (1<=x<6, 1<=y<6, x+y<=6) and single or two NR Supplementary Uplink (SUL) bands","DC_R19_xBLTE_yBNR",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.5,"RP-250143",null,"Nokia ",null,"26/9/24: WID:RP-241673->RP-241786; 24/1/25: WID:RP-241786->RP-243257; 3/4/25: WID:RP-243257->RP-250143",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[387,1041119,"   Core part: Rel-19 Dual connectivity (DC) of x LTE band(s), y NR band(s) (1<=x<6, 1<=y<6, x+y<=6) and single or two NR Supplementary Uplink (SUL) bands","DC_R19_xBLTE_yBNR-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.5,"RP-250143","RP-250965","Nokia ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-241785; ; 26/9/24: 37.719-11-11 added;; 26/9/24: 37.719-21-11 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:10%->15%; Stat Rep: RP-241785->RP-242535; ; 6/3/25: FCD:19/04/2025->09/09/2","37.719-11-10; 37.719-11-11; 37.719-21-11",104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[388,1030077,"UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 ","NR_ENDC_RF_Ph4",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.69,"RP-250780",null,"Huawei ",null,"23/7/24: WID:RP-240828->RP-241656; 3/4/25: WID:RP-241656->RP-250780",null,103,52,null,null,"Tue 02/04/24","Thu 03/04/25"]
[389,1031077,"   Core part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 ","NR_ENDC_RF_Ph4-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.8,"RP-250780","RP-251532","Huawei ",null,"13/6/24: Compl:0%->20%; Stat Rep: ->RP-241236; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:20%->35%; Stat Rep: RP-241236->RP-242084; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:35%->50%; Stat Rep: RP-242084->RP-243011; ; 6/3/25: FCD:23/03/2025->09/09/202",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[390,1032077,"   Perf. part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 ","NR_ENDC_RF_Ph4-Perf",2,"Rel-19","R4","Sun 03/03/24","Tue 03/03/26",0.6,"RP-250780","RP-251532","Huawei ",null,"4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->15%; Stat Rep: ->RP-242084; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:15%->20%; Stat Rep: RP-242084->RP-243011; ; 6/3/25: FCD:22/07/2025->03/03/2026; Stat Rep: RP-243011->RP-250280; ; 6/6/25: Compl:20%->60%",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[391,1030082,"Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) ","NonCol_intraB_ENDC_NR_CA_Ph2",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.42,"RP-242083",null,"KDDI ",null,"26/9/24: WID:RP-240838->RP-242083",null,103,52,null,null,"Tue 02/04/24","Thu 26/09/24"]
[392,1031082,"   Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) ","NonCol_intraB_ENDC_NR_CA_Ph2-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.8,"RP-242083","RP-251278","KDDI ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->35%; Stat Rep: ->RP-242079; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:35%->45%; Stat Rep: RP-242079->RP-242842; ; 6/3/25: FCD:23/03/2025->09/09/2025; Compl:45%->50%; Stat Rep: RP-242842->RP-250279; ; 6/6/25",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[393,1032082,"   Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) ","NonCol_intraB_ENDC_NR_CA_Ph2-Perf",2,"Rel-19","R4","Sun 13/10/24","Tue 03/03/26",0,"RP-242083","RP-251278","KDDI ",null,"4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: ->RP-242079; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-242079->RP-242842; ; 6/3/25: Stat Rep: RP-242842->RP-250279; ; 6/6/25: Stat Rep: RP-250279->RP-251278; ",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[394,1030085,"FR1 TRP, TRS and MIMO OTA testing enhancement Phase 3 ","TRP_TRS_MIMO_OTA_Ph3",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.67,"RP-250197",null,"Vivo ",null,"23/7/24: WID:RP-240841->RP-241623; 24/1/25: WID:RP-241623->RP-243277; 3/4/25: WID:RP-243277->RP-250197",null,103,52,null,null,"Tue 02/04/24","Thu 03/04/25"]
[395,1031085,"   Core part: FR1 TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 ","TRP_TRS_MIMO_OTA_Ph3-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.9,"RP‑250197","RP-251201","Vivo ",null,"13/6/24: Compl:0%->10%; Stat Rep: ->RP-241043; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:10%->20%; Stat Rep: RP-241043->RP-241828; ; 26/9/24: 38.762 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:20%->45%; Stat Rep: RP-241828->RP-242623; ; 6/3/25: F",38.762,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[396,1032085,"   Perf. Part: FR1 TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 ","TRP_TRS_MIMO_OTA_Ph3-Perf",2,"Rel-19","R4","Sun 03/03/24","Tue 03/03/26",0.5,"RP‑250197","RP-251201","Vivo ",null,"13/6/24: Stat Rep: ->RP-241043; ; 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->5%; Stat Rep: RP-241043->RP-241828; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:5%->25%; Stat Rep: RP-241828->RP-242623; ; 6/3/25: FCD:22/07/2025->03/03/2026; Compl:25%->35%;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[397,1070063,"UE Conformance - Rel-19 NR CA and DC; and NR and LTE DC Configurations ","NR_CADC_NR_LTE_DC_R19-UEConTest",1,"Rel-19","R5","Mon 03/03/25","Fri 11/12/26",0.05,"RP-250452","RP-251492","Huawei ",null,"6/6/25: FCD:Sat 12/12/26->Fri 11/12/26; Compl:0%->5%; Stat Rep: ->RP-251492; ",null,107,54,null,null,"Wed 26/03/25","Fri 06/06/25"]
[398,0,"Rel-19 Radio: LTE","-",1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[399,1070064,"New LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite ","LTE_band_5G_bcast_GSO",1,"Rel-19","R4","Mon 03/03/25","Tue 03/03/26",0.26,"RP-250788",null,"Astrum Mobile ",null,null,null,107,54,null,null,"Wed 26/03/25","NA"]
[400,1071064,"   Core part: New LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite ","LTE_band_5G_bcast_GSO-Core",2,"Rel-19","R4","Mon 03/03/25","Tue 09/09/25",0.75,"RP-251419","RP-251276","Astrum Mobile ",null,"6/6/25: Compl:0%->75%; WID: RP-250788->RP-251419; Stat Rep: ->RP-251276; ",null,107,54,null,null,"Wed 26/03/25","Fri 06/06/25"]
[401,1072064,"   Perf. part: New LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite ","LTE_band_5G_bcast_GSO-Perf",2,"Rel-19","R4","Mon 03/03/25","Tue 03/03/26",0,"RP-251419","RP-251276","Astrum Mobile ",null,"6/6/25: WID: RP-250788->RP-251419; Stat Rep: ->RP-251276; ",null,107,54,null,null,"Wed 26/03/25","Fri 06/06/25"]
[402,1060081,"LTE-based 5G Broadcast Phase 2 ","LTE_terr_bcast_Ph2",1,"Rel-19",null,"Sun 19/05/24","Fri 12/12/25",0.43,"RP-250794",null,"EBU ",null,"3/4/25: WID:RP-243290->RP-250794",null,106,54,null,null,"Fri 24/01/25","Thu 03/04/25"]
[403,1061081,"   Core part: LTE-based 5G Broadcast Phase 2 ","LTE_terr_bcast_Ph2-Core",2,"Rel-19","R1","Mon 14/10/24","Tue 09/09/25",0.95,"RP-250794","RP-251143","EBU ",null,"6/3/25: FCD:07/09/2025->09/09/2025; Compl:0%->40%; Stat Rep: ->RP-250238; ; 6/6/25: Compl:40%->95%; Stat Rep: RP-250238->RP-251143; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[404,1062081,"   Perf. part: LTE-based 5G Broadcast Phase 2 ","LTE_terr_bcast_Ph2-Perf",2,"Rel-19","R4","Mon 11/11/24","Fri 12/12/25",0,"RP-250794","RP-251143","EBU ",null,"6/3/25: Stat Rep: ->RP-250238; ; 6/6/25: Stat Rep: RP-250238->RP-251143; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[405,1060080,"New bands for LTE based 5G terrestrial broadcast for early deployments ","LTE_terr_bcast_bands_sub_108",1,"Rel-19",null,"Sun 19/05/24","Fri 06/06/25",1,"RP-250793",null,"EBU ",null,"3/4/25: WID:RP-243268->RP-250793",null,106,54,null,null,"Fri 24/01/25","Thu 03/04/25"]
[406,1061080,"   New bands for LTE based 5G terrestrial broadcast for early deployments ","LTE_terr_bcast_bands_sub_108-Core",2,"Rel-19","R4","Sat 14/09/24","Fri 06/06/25",1,"RP-250793","RP-251141","EBU ",null,"6/3/25: Compl:0%->40%; Stat Rep: ->RP-250235; ; 6/6/25: Compl:40%->100%; Stat Rep: RP-250235->RP-251141; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[407,1040117,"Introduction of LTE FDD band in 1800–1830 MHz for Canada ","LTE_FDD_1800_1830MHz_CAN",1,"Rel-19",null,"Thu 06/06/24","Mon 03/03/25",1,"RP-242461",null,"Novamint ",null,"; 26/9/24: WID:RP-241649->RP-241739; 24/1/25: WID:RP-241739->RP-242461",null,104,53,null,null,"Tue 23/07/24","Fri 24/01/25"]
[408,1041117,"   Core part: Introduction of LTE FDD band in 1800–1830 MHz for Canada ","LTE_FDD_1800_1830MHz_CAN-Core",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-242461","RP-250105","Novamint ",null,"; 4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->25%; Stat Rep: ->RP-241738; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:25%->99%; Stat Rep: RP-241738->RP-242460; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:99%->100%; Stat Rep: RP-242460->RP-250105; ",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[409,1042117,"   Perf.part: Introduction of LTE FDD band in 1800–1830 MHz for Canada ","LTE_FDD_1800_1830MHz_CAN-Perf",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-242461","RP-250105","Novamint ",null,"; 4/9/24: FCD:03/03/2025->25/03/2025; Stat Rep: ->RP-241738; ; 6/12/24: Compl:0%->99%; Stat Rep: RP-241738->RP-242460; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:99%->100%; Stat Rep: RP-242460->RP-250105; ",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[410,1040116,"Rel-19 High power UE (power class 2) and high power operation (power class 1) for fixed-wireless/vehicle-mounted use cases in a single LTE band ","HPUE_LTE_bands_R19",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.1,"RP-241681",null,"Nokia ",null,"basket WI; no Perf. part; TR 36.8xx ",null,104,53,null,null,"Tue 23/07/24","NA"]
[411,1041116,"   Core part: Rel-19 High power UE (power class 2) and high power operation (power class 1) for fixed-wireless/vehicle-mounted use cases in a single LTE band ","HPUE_LTE_bands_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.1,"RP-242086","RP-250899","Nokia ",null,"basket WI; no Perf. part; TR 36.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-241814; ; 26/9/24: 36.767 added;; 6/12/24: FCD:09/09/2024->09/09/2025; WID: RP-241681->RP-242086; Stat Rep: RP-241814->RP-242499; ; 6/3/25: FCD:19/04/",36.767000000000003,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[412,1040115,"Rel-19 LTE-Advanced Carrier Aggregation for x bands (1<=x<= 6) DL with y bands (y=1, 2) UL","LTE_CA_R19_xBDL_yBUL",1,"Rel-19",null,"Thu 06/06/24","Fri 06/06/25",0.65,"RP-250282",null,"Huawei ",null,"basket WI; no Perf. part; TR 36.8xx; compare REL-18 WI LTE_CA_R18_xBDL_yBUL ; 26/9/24: WID:RP-241676->RP-242086; 24/1/25: WID:RP-242086->RP-243014; 3/4/25: WID:RP-243014->RP-250282",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[413,1041115,"   Core part: Rel-19 LTE-Advanced Carrier Aggregation for x bands (1<=x<= 6) DL with y bands (y=1, 2) UL","LTE_CA_R19_xBDL_yBUL-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.65,"RP-250282","RP-251533","Huawei ",null,"basket WI; no Perf. part; TR 36.8xx; compare REL-18 WI LTE_CA_R18_xBDL_yBUL ; 4/9/24: FCD:09/09/2025->24/06/2025; Compl:0%->10%; Stat Rep: ->RP-242085; ; 26/9/24: 36.719-01-01 added;; 6/12/24: FCD:06/06/2025->09/09/2025; Compl:10%->31%; Stat Rep: RP-2420","36.719-01-01",104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[414,0,"Rel-19 other topics","-",1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[415,1070023,"Specification of example algorithm for alternative f5* (f5**) function","Crypto_f5**",1,"Rel-19","S3","Thu 06/03/25","Fri 06/06/25",0,"SP-250360",null,"Ferhat Karakoc ","ferhat.karakoc@ericsson.com ","; 26/3/25: 35.249 added;; 26/3/25: 23.369 added;; 26/3/25: 23.700-14 added;","33.102; 35.205; 35.231 ; 35.249; 23.369; 23.700-14",107,54,null,null,"Wed 05/03/25","Wed 26/03/25"]
[416,1060056,"Study on 3GPP Cryptographic Inventory ","FS_CryptoInv",1,"Rel-19","S3","Thu 05/12/24","Fri 06/06/25",1,"SP-241955",null,"Stawros Orkopoulos","stawros.orkopoulos@nokia.com","6/3/25: 0%->25; 5/6/25: 25%->100",null,106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[417,1040012,"CHF Segmentation ","CHFSeg",1,"Rel-19","S5","Wed 12/06/24","Tue 09/09/25",0.9,"SP-250122",null,"Cetinkaya Egemen Kemal,Verizon ","(egemen.cetinkaya@verizon.com) ","; 4/9/24: 5%->25; 5/12/24: 25%->55; 6/3/25: 55%->60; 26/3/25: WID:SP-241001->SP-250122; 26/3/25: FCD:11/12/2024->/25; 6/6/25: 60%->90","32.290; 32.291 ",104,53,null,null,"Wed 12/06/24","Fri 06/06/25"]
[418,1050121,"Introduction of BDS (BeiDou Navigation Satellite System) B2b Signal in A-GNSS for LTE and NR ","LCS_BDS_B2b_LTE_NR",1,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.99,"RP-250767",null,"CAICT ",null,"24/1/25: WID:RP-242413->RP-242459; 3/4/25: WID:RP-242459->RP-250767",null,105,53,null,null,"Thu 26/09/24","Thu 03/04/25"]
[419,1051121,"   Core part: Introduction of BDS (BeiDou Navigation Satellite System) B2b Signal in A-GNSS for LTE and NR ","LCS_BDS_B2b_LTE_NR-Core",2,"Rel-19","R2","Mon 09/09/24","Tue 09/09/25",0.99,"RP-250767","RP-251012","CAICT ",null,"6/12/24: FCD:06/06/2025->09/09/2025; Compl:0%->70%; Stat Rep: ->RP-242580; ; 6/3/25: FCD:20/05/2025->09/09/2025; Compl:70%->99%; WID: RP-242459->RP-250330; Stat Rep: RP-242580->RP-250329; ; 6/6/25: Stat Rep: RP-250329->RP-251012; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[420,1052121,"   Perf. part: Introduction of BDS (BeiDou Navigation Satellite System) B2b Signal in A-GNSS for LTE and NR ","LCS_BDS_B2b_LTE_NR-Perf",2,"Rel-19","R4","Mon 30/12/24","Tue 09/09/25",0.99,"RP-250767","RP-251012","CAICT ",null,"6/12/24: Stat Rep: ->RP-242580; ; 6/3/25: WID: RP-242459->RP-250330; Stat Rep: RP-242580->RP-250329; ; 6/6/25: Compl:0%->99%; Stat Rep: RP-250329->RP-251012; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[421,1050122,"Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE ","LCS_NAVIC_L1_SPS_NR_LTE",1,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.99,"RP-243247",null,"Reliance Jio ",null,"24/1/25: WID:RP-242414->RP-243247",null,105,53,null,null,"Thu 26/09/24","Fri 24/01/25"]
[422,1051122,"   Core part: Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE ","LCS_NAVIC_L1_SPS_NR_LTE-Core",2,"Rel-19","R2","Mon 09/09/24","Tue 09/09/25",0.99,"RP-243247","RP-251554","Reliance Jio ",null,"6/12/24: Compl:0%->50%; Stat Rep: ->RP-243246; ; 6/3/25: FCD:16/03/2025->06/06/2025; Compl:50%->80%; Stat Rep: RP-243246->RP-250047; ; 6/6/25: FCD:Fri 06/06/25->Tue 09/09/25; Compl:80%->99%; Stat Rep: RP-250047->RP-251554; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[423,1052122,"   Perf. part: Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE ","LCS_NAVIC_L1_SPS_NR_LTE-Perf",2,"Rel-19","R4","Mon 30/12/24","Fri 06/06/25",1,"RP-243247","RP-251554","Reliance Jio ",null,"6/12/24: Stat Rep: ->RP-243246; ; 6/3/25: Stat Rep: RP-243246->RP-250047; ; 6/6/25: FCD:Tue 09/09/25->Fri 06/06/25; Compl:0%->100%; Stat Rep: RP-250047->RP-251554; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[424,1050033,"Data management regarding subscriptions and reporting ","Data_SREP",1,"Rel-19","S5","Sat 28/12/24","Tue 09/09/25",0.4,"SP-241380",null,"Robert Petersen (Ericsson) ","robert.petersen@ericsson.com ","; 6/6/25: 0%->40","28.537; 28.550; 28.532; 32.421; 32.422; 32.423; 28.404; 28.405; 28.622; 28.623 ",105,53,null,null,"Wed 04/09/24","Fri 06/06/25"]
[425,1040071,"Study on MC services support on IOPS mode of operation for 5G ","FS_Generic_IOPS",1,"Rel-19","S6","Tue 16/07/24","Thu 12/12/24",1,"SP-241017",null,"FirstNet, Mark Lipford ","mark.lipford@firstnet.gov ","4/9/24: 0%->40; 26/9/24: 23.700-09 added;; 5/12/24: 40%->100; 5/12/24: FCD:06/06/2025->12/24; 5/12/24: 40%->100","23.700-09",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[426,1050036,"MC services for generic support on IOPS mode of operation","Generic_IOPS",1,"Rel-19","S6","Wed 04/09/24","Thu 12/12/24",1,"SP-241382",null,"FirstNet, Mark Lipford ","mark.lipford@firstnet.gov ","; 5/12/24: 0%->100; 5/12/24: 100%->65; 6/3/25: 65%->100","23.180 ",105,53,null,null,"Wed 04/09/24","Thu 06/03/25"]
[427,1050114,"Monitoring of signalling traffic in 5G ","MonSTra",1,"Rel-19","S1","Mon 06/05/24","Thu 12/12/24",0.28999999999999998,"SP-240793",null,"Cristina Romaguera ","cristina.romaguera@vodafone.com ","; 12/6/24: 0%->100","22.261 ",105,53,null,null,"Wed 12/06/24","Wed 12/06/24"]
[428,1040082,"   Stage 1 for MonSta","MonSTra",2,"Rel-19","S1","Mon 06/05/24","Thu 06/06/24",1,"SP-240793",null,"Cristina Romaguera ","cristina.romaguera@vodafone.com ","; 12/6/24: 0%->100","22.261 ",104,53,null,null,"Wed 12/06/24","Wed 12/06/24"]
[429,1050028,"   Security for MonStra ","MonStra-Sec",2,"Rel-19","S3","Fri 04/10/24","Thu 12/12/24",0,"SP-241376",null,"Vodafone, Susana Sabater","susana.sabatr@vodafone.com",null,"33.501 ",105,53,null,null,"Wed 04/09/24","NA"]
[430,1060012,"   Management for MonStra ","Monstra-OAM",2,"Rel-19","S5","Thu 05/12/24","Tue 10/12/24",1,"SP-241945",null,"Susana Sabater (Vodafone)","susana.sabater@vodafone.com","5/12/24: 0%->80; 6/6/25: 80%->100",null,106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[431,1040036,"Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",1,"Rel-19",null,"Thu 04/01/24","Tue 09/09/25",0.75,"SP-241284",null,"Changhong Shan (Intel) ","chang.hong.shan@intel.com ","; 26/9/24: WID:SP-240996->SP-241284; 6/3/25: 82%->","23.501; 23.502; 23.548; 23.503 ",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[432,1020004,"   Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","FS_eEDGE_5GC_Ph3",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-240962",null,"Changhong Shan (Intel) ","chang.hong.shan@intel.com ","14/3/24: 0%->50; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 50%->90; 16/7/24: WID:SP-231796->SP-240962; 4/9/24: 90%->100",null,102,52,null,null,"Wed 03/01/24","Wed 04/09/24"]
[433,1030036,"   Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 ","FS_EDGE_Ph3",2,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240510",null,"Ge Yao, ","yaog9@chinaunicom.cn ","3/4/24: 33.749 added;; 13/6/24: 0%->30; 5/9/24: 30%->60; 5/12/24: 60%->95; 6/3/25: 95%->100; 5/6/25: 100%->100","33.749",103,52,null,null,"Thu 14/03/24","Thu 05/06/25"]
[434,1060064,"   Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 ","EDGE_Ph3",2,"Rel-19","S3","Thu 02/01/25","Mon 03/03/25",0,"SP-241959",null,"TBD ",null,null,"33.501; 33.558 ",106,54,null,null,"Thu 05/12/24","NA"]
[435,1050050,"   Stage 2 of Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-241505",null,"Meghashree Dattatri Kedalagudde (Intel); ","meghashree.dattatri.kedalagudde@intel.com","; 4/9/24: 0%->30; 5/12/24: 30%->97; 8/1/25: WID:SP-240996->SP-241505 (Rapp change); 6/3/25: 97%->100","23.501; 23.502; 23.548; 23.503 ",105,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[436,1050006,"   CT aspects of Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",2,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.64,"CP-250016",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,"29.244, 29.502, 29.503, 29.504, 29.510, 29.556 , 29.571, 29.512, 29.513, 29.514, 29.519, 29.522, 29.591, 29.244, 29.502, 29.503, 29.504, 29.510, 29.556 , 29.571, 29.512, 29.513, 29.514, 29.519, 29.522, 29.591, 29.518",105,53,null,null,"Wed 12/06/24","NA"]
[437,1050051,"      CT3 aspects of Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.96,"CP-250016",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[438,1050052,"      CT4 aspects of Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.9,"CP-250016",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[439,1050056,"Multi-Access (ATSSS_Ph4) ","MASSS",1,"Rel-19",null,"Thu 04/01/24","Tue 09/09/25",0.76,"SP-240994",null,"Krisztian Kiss (Apple), ","krisztian@apple.com ",null,"23.501; 23.502; 23.503 ",105,53,null,null,"Wed 12/06/24","NA"]
[440,1020070,"   Study on Multi-Access (DualSteer and ATSSS_Ph4) ","FS_MASSS",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-240467",null,"Krisztian Kiss (Apple) ","krisztian@apple.com ","14/3/24: 0%->30; 2/4/24: WID:SP-231802->SP-240467; 2/4/24: FCD:09/09/2024->/24; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 30%->70; 4/9/24: 70%->100",null,102,52,null,null,"Wed 03/01/24","Wed 04/09/24"]
[441,1030037,"   Study on security aspects for Multi-Access (DualSteer + ATSSS Ph-4) ","FS_MASSS_Sec",2,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240511",null,"Kolekar, Abhijeet (Intel) ","abhijeet.kolekar@intel.com ","3/4/24: 33.754 added;; 13/6/24: 0%->45; 5/9/24: 45%->95; 5/12/24: 95%->100; 6/3/25: 100%->100","33.754",103,52,null,null,"Thu 14/03/24","Thu 06/03/25"]
[442,1040034,"   Stage 2 of Multi-Access (ATSSS_Ph4) ","MASSS",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-241331",null,"Krisztian Kiss (Apple), ","krisztian@apple.com ","; 4/9/24: 0%->50; 26/9/24: WID:SP-240994->SP-241331; 5/12/24: 50%->100","23.501; 23.502; 23.503 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[443,1050020,"   CT aspects of Multi-Access (ATSSS_Ph4) ","MASSS",2,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.66,"CP-243265",null,"Gupta, Vivek, Apple","vivek_g_gupta@apple.com",null,"24.193, 24.501, 29.512, 29.244, 29.571",105,53,null,null,"Wed 12/06/24","NA"]
[444,1050057,"      CT1 aspects of Multi-Access (ATSSS_Ph4) ","MASSS",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.95,"CP-243265",null,"Gupta, Vivek, Apple","vivek_g_gupta@apple.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[445,1050058,"      CT3 aspects of Multi-Access (ATSSS_Ph4) ","MASSS",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.95,"CP-243265",null,"Gupta, Vivek, Apple","vivek_g_gupta@apple.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[446,1050059,"      CT4 aspects of Multi-Access (ATSSS_Ph4) ","MASSS",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.95,"CP-243265",null,"Gupta, Vivek, Apple","vivek_g_gupta@apple.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[447,1050066,"System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",1,"Rel-19",null,"Wed 20/09/23","Tue 09/09/25",0.63,"SP-240985",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 16/7/24: WID:SP-240625->SP-240985","23.228; 23.502 ",105,53,null,null,"Wed 12/06/24","Tue 16/07/24"]
[448,1010030,"   Study on system architecture for next generation real time communication services phase 2 ","FS_NG_RTC_Ph2",2,"Rel-19","S2","Wed 20/09/23","Mon 09/09/24",1,"SP-231196",null,"Yi Jiang (China Mobile) ","jiangyi@chinamobile.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-77 added;; 8/12/23: 0%->15; 14/3/24: 15%->45; 13/6/24: FCD:05/06/2024->/24; 13/6/24: 45%->95; 5/12/24: 95%->100","23.700-77",101,51,null,null,"Wed 20/09/23","Thu 05/12/24"]
[449,1040016,"   Study on Charging aspects of next generation real time communication services phase 2 ","FS_NG_RTC_Ph2_CH",2,"Rel-19","S5","Wed 12/06/24","Wed 11/12/24",1,"SP-240982",null,"Chen Ai, China Mobile ","chenai@chinamobile.com ","13/6/24: 0%->10; 4/9/24: 10%->45; 26/9/24: 28.851 added;; 5/12/24: 45%->75; 5/12/24: FCD:12/12/2024->/25; 6/3/25: 75%->100","28.851",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[450,1040026,"   Stage 2 of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",2,"Rel-19","S2","Wed 12/06/24","Thu 17/10/24",0.99,"SP-241384",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 16/7/24: WID:SP-240625->SP-240985; 4/9/24: 0%->10; 26/9/24: WID:SP-240985->SP-241384; 5/12/24: 10%->70; 6/3/25: 70%->98; 5/6/25: 98%->99","23.228; 23.502 ",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[451,1050022,"   CT aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",2,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.47,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"Wed 12/06/24","Tue 16/07/24"]
[452,1050067,"      CT1 aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.8,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"Wed 12/06/24","Tue 16/07/24"]
[453,1050068,"      CT3 aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.85,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"Wed 12/06/24","Tue 16/07/24"]
[454,1050069,"      CT4 aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.85,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"Wed 12/06/24","Tue 16/07/24"]
[455,1050070,"      CT6 aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",3,"Rel-19","C6","Mon 30/12/24","Tue 09/09/25",0,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"Wed 12/06/24","Tue 16/07/24"]
[456,1070016,"   Charging aspects of next generation real time communication services phase 2 ","NG_RTC_Ph2-CH",2,"Rel-19","S5","Wed 26/03/25","Tue 09/09/25",0.7,"SP-250367",null,"Chen Ai, China Mobile ","chenai@chinamobile.com ","; 6/6/25: 0%->70","32.254; 32.255; 32.260; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[457,1070044,"Rel-19 Application Data Analytics Enablement Service ","TEI19_ADAES",1,"Rel-19",null,"Sat 07/12/24","Tue 09/09/25",0.76,"SP-241695",null,"Yue, Jing, Ericsson ","jing.yue@ericsson.com ",null,"23.436 ",107,54,null,null,"Thu 05/12/24","NA"]
[458,1060068,"   Stage 2 of Rel-19 Application Data Analytics Enablement Service ","TEI19_ADAES",2,"Rel-19","S6","Sat 07/12/24","Thu 12/12/24",1,"SP-241695",null,"Yue, Jing, Ericsson ","jing.yue@ericsson.com ","; 3/4/25: 0%->100","23.436 ",106,54,null,null,"Thu 05/12/24","Thu 03/04/25"]
[459,1070004,"   CT aspects of Rel-19 Application Data Analytics Enablement Service ","TEI19_ADAES",2,"Rel-19",null,"Thu 06/03/25","Tue 09/09/25",0.75,"CP-250074",null,"Pastushok, Igor, Ericsson","igor.pastushok@ericsson.com",null,"29.549",107,54,null,null,"Thu 05/12/24","NA"]
[460,1070045,"      CT3 aspects of Rel-19 Application Data Analytics Enablement Service ","TEI19_ADAES",3,"Rel-19","C3","Thu 06/03/25","Tue 09/09/25",0.75,"CP-250074",null,"Pastushok, Igor, Ericsson","igor.pastushok@ericsson.com",null,"29.549",107,54,null,null,"Thu 05/12/24","NA"]
[461,1070046,"MSISDN verification operation support to Nnef_UEId Service ","TEI19_MVOSNS",1,"Rel-19",null,"Sat 07/12/24","Fri 06/06/25",1,"SP-241498",null,"Rohit Abhishek (AT&T) ","ra503n@att.com ",null,"23.502; 23.501 ",107,54,null,null,"Thu 05/12/24","NA"]
[462,1060028,"   Stage 2 of MSISDN verification operation support to Nnef_UEId Service ","TEI19_MVOSNS",2,"Rel-19","S2","Sat 07/12/24","Thu 12/12/24",1,"SP-241498",null,"Rohit Abhishek (AT&T) ","ra503n@att.com ","; 26/3/25: 0%->100","23.502; 23.501 ",106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[463,1070007,"   CT aspects of MSISDN verification operation support to Nnef_UEId Service ","TEI19_MVOSNS",2,"Rel-19",null,"Mon 03/03/25","Fri 06/06/25",1,"CP-250077",null,"Shahram Mohajeri, AT&T","sm7084@att.com",null,"29.522",107,54,null,null,"Thu 05/12/24","NA"]
[464,1070047,"      CT3 aspects of MSISDN verification operation support to Nnef_UEId Service ","TEI19_MVOSNS",3,"Rel-19","C3","Mon 03/03/25","Fri 06/06/25",1,"CP-250077",null,"Shahram Mohajeri, AT&T","sm7084@att.com",null,"29.522",107,54,null,null,"Thu 05/12/24","NA"]
[465,1070041,"Network Controlled Network Slice Selection ","TEI19_SliceSel",1,"Rel-19",null,"Sat 07/12/24","Tue 09/09/25",0.95,"SP-241502",null,"Saito, Koji, KDDI ","kj-saitou_at_kddi_dot_com ",null,"23.501; 23.502; 23.503 ",107,54,null,null,"Thu 05/12/24","NA"]
[466,1060030,"   Stage 2 of Network Controlled Network Slice Selection ","TEI19_SliceSel",2,"Rel-19","S2","Sat 07/12/24","Thu 12/12/24",1,"SP-241502",null,"Saito, Koji, KDDI ","kj-saitou_at_kddi_dot_com ","; 26/3/25: 0%->100","23.501; 23.502; 23.503 ",106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[467,1070003,"   CT aspects of Network Controlled Network Slice Selection ","TEI19_SliceSel",2,"Rel-19",null,"Mon 03/03/25","Tue 09/09/25",0.95,"CP-250073",null,"Xiaojian Yan, ZTE","yan.xiaojian@zte.com.cn",null,"29.522,29.534,29.519,29.507,29.523,29.513,29.502,29.504,29.518",107,54,null,null,"Thu 05/12/24","NA"]
[468,1070042,"      CT3 aspects of Network Controlled Network Slice Selection ","TEI19_SliceSel",3,"Rel-19","C3","Mon 03/03/25","Tue 09/09/25",0.9,"CP-250073",null,"Xiaojian Yan, ZTE","yan.xiaojian@zte.com.cn",null,"29.522,29.534,29.519,29.507,29.523,29.513,29.502,29.504,29.518",107,54,null,null,"Thu 05/12/24","NA"]
[469,1070043,"      CT4 aspects of Network Controlled Network Slice Selection ","TEI19_SliceSel",3,"Rel-19","C4","Mon 03/03/25","Tue 09/09/25",1,"CP-250073",null,"Xiaojian Yan, ZTE","yan.xiaojian@zte.com.cn",null,"29.522,29.534,29.519,29.507,29.523,29.513,29.502,29.504,29.518",107,54,null,null,"Thu 05/12/24","NA"]
[470,1070039,"PRU Usage Extension supported by Core Network ","TEI19_PRUE",1,"Rel-19",null,"Sat 07/12/24","Fri 06/06/25",1,"SP-241504",null,"Hou, Yunjing, CATT ","houyunjing@catt.cn ",null,null,107,54,null,null,"Thu 05/12/24","NA"]
[471,1060031,"   Stage 2 of PRU Usage Extension supported by Core Network ","TEI19_PRUE",2,"Rel-19","S2","Sat 07/12/24","Thu 12/12/24",1,"SP-241504",null,"Hou, Yunjing, CATT ","houyunjing@catt.cn ","26/3/25: 0%->100",null,106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[472,1070001,"   CT aspects of PRU Usage Extension supported by Core Network ","TEI19_PRUE",2,"Rel-19",null,"Mon 03/03/25","Fri 06/06/25",1,"CP-250017",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com",null,"29.572",107,54,null,null,"Thu 05/12/24","NA"]
[473,1070040,"      CT4 aspects of PRU Usage Extension supported by Core Network ","TEI19_PRUE",3,"Rel-19","C4","Mon 03/03/25","Fri 06/06/25",1,"CP-250017",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com",null,"29.572",107,54,null,null,"Thu 05/12/24","NA"]
[474,1050078,"On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",1,"Rel-19",null,"Tue 02/04/24","Tue 09/09/25",1,"SP-240487",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ",null,"23.502; 23.273 ",103,52,null,null,"Wed 13/03/24","NA"]
[475,1030010,"   Stage 2 of On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",2,"Rel-19","S2","Tue 02/04/24","Thu 12/12/24",1,"SP-240487",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ","; 4/9/24: 0%->100","23.502; 23.273 ",103,52,null,null,"Wed 13/03/24","Wed 04/09/24"]
[476,1050003,"   CT aspects of On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",2,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",1,"CP-242023",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com",null,null,103,52,null,null,"Wed 13/03/24","NA"]
[477,1050079,"      CT4 aspects of On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",1,"CP-242023",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com",null,null,103,52,null,null,"Wed 13/03/24","NA"]
[478,1080039,"ATSSS Rule Provisioning via 3GPP access connected to EPC ","TEI19_ARP3E",1,"Rel-19","S2","Sat 07/12/24","Fri 06/06/25",1,"SP-241500",null,"Chunhui Zhu (NEC) ","zhu_chunhui@nec.cn ","; 26/3/25: 0%->100","23.502 ",106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[479,1060029,"   Stage 2 of ATSSS Rule Provisioning via 3GPP access connected to EPC ","TEI19_ARP3E",2,"Rel-19","S2","Sat 07/12/24","Thu 12/12/24",1,"SP-241500",null,"Chunhui Zhu (NEC) ","zhu_chunhui@nec.cn ","; 26/3/25: 0%->100","23.502 ",106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[480,1080020,"   CT aspects of ATSSS Rule Provisioning via 3GPP access connected to EPC ","TEI19_ARP3E-CT",2,"Rel-19","C1","Fri 06/06/25","Fri 06/06/25",1,"CP-251217",null,"Chunhui Zhu (NEC) ","zhu_chunhui@nec.cn ","; 26/3/25: 0%->100","24.193",106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[481,1080040,"      CT1 aspects of ATSSS Rule Provisioning via 3GPP access connected to EPC ","TEI19_ARP3E-CT",3,"Rel-19","C1","Fri 06/06/25","Fri 06/06/25",1,"CP-251217",null,"Chunhui Zhu (NEC) ","zhu_chunhui@nec.cn ","; 26/3/25: 0%->100","24.193",106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[482,1030012,"Minimize the Number of Policy Associations ","TEI19_MINPA",1,"Rel-19",null,"Mon 17/06/24","Mon 03/03/25",1,"SP-240118",null,"Ericsson, Belen Pancorbo ","belen . pancorbo {@} ericsson . com) ",null,"23.502; 23.501; 23.503 ",103,52,null,null,"Wed 13/03/24","NA"]
[483,1040078,"   Stage 2 of Minimize the Number of Policy Associations","TEI19_MINPA",2,"Rel-19","S2","Mon 17/06/24","Mon 03/03/25",1,"SP-240118",null,"Ericsson, Belen Pancorbo ","belen . pancorbo {@} ericsson . com) ","13/6/24: 0%->100",null,101,51,null,null,"Wed 06/09/23","Thu 13/06/24"]
[484,1040004,"   CT Aspects on Minimize the Number of Policy Associations","TEI19_MINPA",2,"Rel-19",null,"Mon 17/06/24","Mon 03/03/25",1,"CP-241295",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,"TS 29.503,TS 29.507,TS 29.513,TS 29.518,TS 29.525",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[485,1040052,"      CT3 Aspects on Minimize the Number of Policy Associations","TEI19_MINPA",3,"Rel-19","C3","Mon 17/06/24","Mon 03/03/25",1,"CP-241295",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[486,1040053,"      CT4 Aspects on Minimize the Number of Policy Associations","TEI19_MINPA",3,"Rel-19","C4","Mon 17/06/24","Mon 03/03/25",1,"CP-241295",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[487,1050089,"Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",1,"Rel-19",null,"Wed 13/03/24","Thu 12/12/24",1,"SP-240486",null,"uri baniel, oracle ","uri dot baniel at oracle dot com","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.502; 23.501; 23.503 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[488,1030014,"   Stage 2 of Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",2,"Rel-19","S2","Wed 13/03/24","Thu 06/06/24",1,"SP-240486",null,"uri baniel, oracle ","uri dot baniel at oracle dot com","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.502; 23.501; 23.503 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[489,1050011,"   CT aspects of Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",2,"Rel-19",null,"Mon 09/09/24","Thu 12/12/24",1,"CP-242060",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[490,1050090,"      CT3 aspects of Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",3,"Rel-19","C3","Mon 09/09/24","Thu 12/12/24",1,"CP-242060",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[491,1030015,"Enhancing Parameter Provisioning with static UE IP address and UP security policy ","TEI19_IP_SP_EXP",1,"Rel-19",null,"Tue 26/12/23","Fri 06/06/25",1,"SP-240121",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ",null,"23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","NA"]
[492,1040079,"   Stage 2 of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",2,"Rel-19","S2","Tue 26/12/23","Thu 12/12/24",1,"SP-240121",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ","19/6/24: FCD:06/06/2025->12/20; 4/9/24: 0%->100",null,101,51,null,null,"Wed 06/09/23","Wed 04/09/24"]
[493,1040007,"   CT aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",2,"Rel-19",null,"Mon 17/06/24","Fri 06/06/25",1,"CP-243076",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,"29.503,29.522,29.503,29.522",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[494,1040056,"      CT3 aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",3,"Rel-19","C3","Mon 17/06/24","Fri 06/06/25",1,"CP-243076",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[495,1040057,"      CT4 aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",3,"Rel-19","C4","Mon 17/06/24","Fri 06/06/25",1,"CP-243076",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[496,1030017,"Multiple Location Procedure for Emergency LCS Routing ","TEI19_MLR4RTR",1,"Rel-19","S2","Wed 13/03/24","Thu 12/12/24",1,"SP-240123",null,"Simon Cai (Nokia Shanghai-Bell)Simon<dot>Ca<at> nokia<dash>sbell<dot>com ","Simon<dot>Ca<at> nokia<dash>sbell<dot>com ","; 5/12/24: 0%->100","23.273 ",103,52,null,null,"Wed 13/03/24","Thu 05/12/24"]
[497,1030018,"Roaming traffic offloading via session breakout in HPLMN ","TEI19_HSBO",1,"Rel-19","S2","Tue 02/04/24","Thu 12/12/24",1,"SP-240491",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ","; 5/12/24: 0%->100","23.501 ",103,52,null,null,"Wed 13/03/24","Thu 05/12/24"]
[498,1060043,"Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",1,"Rel-19",null,"Wed 13/03/24","Mon 03/03/25",1,"SP-240125",null,"Richard, Batorfi, Ericsson, ","richard.batorfi@ericsson.com ",null,"23.273 ",103,52,null,null,"Wed 13/03/24","NA"]
[499,1030019,"   Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",2,"Rel-19","S2","Wed 13/03/24","Thu 12/12/24",1,"SP-240125",null,"Richard, Batorfi, Ericsson, ","richard.batorfi@ericsson.com ","; 5/12/24: 0%->100","23.273 ",103,52,null,null,"Wed 13/03/24","Thu 05/12/24"]
[500,1060004,"   CT aspects of Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",2,"Rel-19","C4","Mon 02/12/24","Mon 03/02/25",1,"CP-243048",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,"29.515, 29.518, 29.572",103,52,null,null,"Wed 13/03/24","NA"]
[501,1060044,"      CT4 aspects of Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",3,"Rel-19","C4","Mon 02/12/24","Mon 03/03/25",1,"CP-243048",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,null,103,52,null,null,"Wed 13/03/24","NA"]
[502,1050084,"QoS monitoring enhancement ","TEI19_QME",1,"Rel-19",null,"Tue 02/04/24","Fri 06/06/25",1,"SP-240961",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100; 16/7/24: WID:SP-240489->SP-240961","23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","Tue 16/07/24"]
[503,1030020,"   Stage 2 of QoS monitoring enhancement ","TEI19_QME",2,"Rel-19","S2","Tue 02/04/24","Thu 06/06/24",1,"SP-240961",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100; 16/7/24: WID:SP-240489->SP-240961","23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","Tue 16/07/24"]
[504,1050012,"   CT aspects of QoS monitoring enhancement ","TEI19_QME",2,"Rel-19",null,"Mon 09/09/24","Fri 06/06/25",1,"CP-243312",null,"Huang, Zhenning, China Mobile","huangzhenning@chinamobile.com",null,"29.122, 29.502, 29.512, 29.514, 29.522, 29.565",103,52,null,null,"Wed 13/03/24","Tue 16/07/24"]
[505,1050085,"      CT3 aspects of QoS monitoring enhancement ","TEI19_QME",3,"Rel-19","C3","Mon 09/09/24","Fri 06/06/25",1,"CP-243312",null,"Huang, Zhenning, China Mobile","huangzhenning@chinamobile.com",null,null,103,52,null,null,"Wed 13/03/24","Tue 16/07/24"]
[506,1050086,"      CT4 aspects of QoS monitoring enhancement ","TEI19_QME",3,"Rel-19","C4","Mon 09/09/24","Fri 06/06/25",1,"CP-243312",null,"Huang, Zhenning, China Mobile","huangzhenning@chinamobile.com",null,null,103,52,null,null,"Wed 13/03/24","Tue 16/07/24"]
[507,1060045,"Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",1,"Rel-19",null,"Wed 13/03/24","Thu 12/12/24",1,"SP-240127",null,"Sebastian Speicher, Qualcomm ","speicher AT qti DOT qualcomm DOT com) ","; 4/9/24: 0%->100",null,103,52,null,null,"Wed 13/03/24","Wed 04/09/24"]
[508,1030021,"   Stage 2 of Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",2,"Rel-19","S2","Wed 13/03/24","Thu 12/12/24",1,"SP-240127",null,"Sebastian Speicher, Qualcomm ","speicher AT qti DOT qualcomm DOT com) ","; 4/9/24: 0%->100","23.401 ",103,52,null,null,"Wed 13/03/24","Wed 04/09/24"]
[509,1060001,"   CT aspects of Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",2,"Rel-19",null,"Mon 02/12/24","Thu 12/12/24",1,"CP-243017",null,"Hanna Lim, Qualcomm Incorporated","hannalim@qti.qualcomm.com",null,"29.272, 29.274, 29.230, 23.008 ",103,52,null,null,"Wed 13/03/24","Wed 04/09/24"]
[510,1060046,"      CT4 aspects of Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",3,"Rel-19","C4","Mon 02/12/24","Thu 12/12/24",1,"CP-243017",null,"Hanna Lim, Qualcomm Incorporated","hannalim@qti.qualcomm.com",null,null,103,52,null,null,"Wed 13/03/24","Wed 04/09/24"]
[511,1030022,"Providing per-subscriber VLAN instructions from UDM and DN-AAA ","TEI19_VLANSUB",1,"Rel-19",null,"Tue 26/12/23","Fri 06/06/25",1,"SP-240128",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ",null,"23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","NA"]
[512,1040080,"   Stage 2 of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",2,"Rel-19","S2","Tue 26/12/23","Thu 12/12/24",1,"SP-240128",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ","19/6/24: FCD:06/06/2025->12/20; 5/12/24: 0%->100",null,101,51,null,null,"Wed 06/09/23","Thu 05/12/24"]
[513,1040006,"   CT aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",2,"Rel-19",null,"Mon 17/06/24","Fri 06/06/25",1,"CP-250078",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,"29.503,29.561,29.230,29.244",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[514,1040054,"      CT3 aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",3,"Rel-19","C3","Mon 17/06/24","Fri 06/06/25",1,"CP-250078",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[515,1040055,"      CT4 aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",3,"Rel-19","C4","Mon 17/06/24","Fri 06/06/25",1,"CP-250078",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[516,1050076,"NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",1,"Rel-19",null,"Tue 02/04/24","Tue 09/09/25",1,"SP-240490",null,"Dr. Thomas Belling, Nokia, ","thomas (dot) belling (at) nokia (dot) com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[517,1030023,"   Stage 2 of NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",2,"Rel-19","S2","Tue 02/04/24","Thu 06/06/24",1,"SP-240490",null,"Dr. Thomas Belling, Nokia, ","thomas (dot) belling (at) nokia (dot) com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[518,1050005,"   CT aspects of NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",1,"CP-242025",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[519,1050077,"      CT4 aspects of NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",1,"CP-242025",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[520,1020057,"Integrated Sensing and Communication ","Sensing",1,"Rel-19",null,"Thu 10/03/22","Tue 12/12/23",1,"SP-230750",null,"Aleksiev, Vasil, Deutsche Telekom AG ","vasil.aleksiev@magenta.at ","6/9/23: 0%->80; 8/12/23: 80%->100","22.137",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[521,950003,"   Study on Integrated Sensing and Communication ","FS_Sensing",2,"Rel-19","S1","Thu 10/03/22","Sat 09/09/23",1,"SP-220717",null,"Aleksiev, Vasil, Deutsche Telekom ","Vasil.Aleksiev@magenta.at ","5/4/22: 22.837 added;; 4/6/22: 0%->10; 21/6/22: WID:SP-220084->SP-220717; 9/9/22: 10%->40; 10/12/22: 40%->65; 17/3/23: 65%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100","22.837",95,48,null,null,"Thu 10/03/22","Wed 06/09/23"]
[522,1000026,"   Stage 1 of Integrated Sensing and Communication ","Sensing",2,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230750",null,"Aleksiev, Vasil, Deutsche Telekom AG ","vasil.aleksiev@magenta.at ","6/9/23: 0%->80; 8/12/23: 80%->100","22.137",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[523,1020086,"Study on channel modelling for Integrated Sensing And Communication (ISAC) for NR ","FS_Sensing_NR",1,"Rel-19","R1","Wed 13/12/23","Fri 06/06/25",1,"RP-242348","RP-251474","Yingyang Li, Jerome Vogedes, Xiaomi, AT&T","liyingyang@xiaomi.com, jerome.vogedes@att.com","14/3/24: Compl:0%->6%; Stat Rep: ->RP-240114; Rapporteur: Xiaomi->Yingyang Li, Jerome Vogedes, Xiaomi, AT&T; Rap eMail: ->liyingyang@xiaomi.com, jerome.vogedes@att.com; ; 2/4/24: WID:RP-234069->RP-240799; 13/6/24: Compl:6%->22%; Stat Rep: RP-240114->RP...",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[524,1020059,"Uncrewed Aerial System Phase 3 ","UAS_Ph3",1,"Rel-19",null,"Thu 02/06/22","Tue 09/09/25",0.94,"SP-230518",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","6/9/23: 0%->95; 8/12/23: 95%->100",null,100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[525,960017,"   Study on (Stage 1 of) UAV Phase 3 ","FS_UAV_Ph3",2,"Rel-19","S1","Thu 02/06/22","Sat 09/09/23",1,"SP-220954",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","17/8/22: WID:SP-220444->SP-220680; 9/9/22: 0%->20; 23/9/22: WID:SP-220680->SP-220954; 10/12/22: 20%->45; 17/3/23: 45%->65; 8/6/23: 65%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 95%->100",null,96,49,null,null,"Thu 02/06/22","Wed 06/09/23"]
[526,1020069,"   Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM ","FS_UAS_Ph3",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-231801",null,"LaeYoung Kim (LG Electronics) ","laeyoung.kim@lge.com ","14/3/24: 0%->50; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 50%->90; 4/9/24: 90%->100",null,102,52,null,null,"Wed 03/01/24","Wed 04/09/24"]
[527,1000032,"   Stage 1 of Uncrewed Aerial System Phase 3 ","UAS_Ph3",2,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230518",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","6/9/23: 0%->95; 8/12/23: 95%->100",null,100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[528,1040037,"   (Stage 2 of) UAS, UAV and UAM Phase 3 ","UAS_Ph3",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-241287",null,"LaeYoung Kim (LG Electronics) ","laeyoung.kim@lge.com ","; 4/9/24: 0%->65; 26/9/24: WID:SP-240997->SP-241287; 5/12/24: 65%->99; 6/3/25: 99%->100; 5/6/25: 100%->100","23.256; 23.288; 23.503; 23.502; 23.401 ",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[529,1050013,"   CT aspects of UAS, UAV and UAM Phase 3 ","UAS_Ph3",2,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.95,"CP-243077",null,"Sunhee Kim, LG Electronics","sunhee.kim@lge.com",null,"24.501, 24.301, 27.007, 29.122, 29.255, 29.256, 29.503, 29.518, 29.520, 29.522",105,53,null,null,"Wed 12/06/24","NA"]
[530,1050091,"      CT1 aspects of UAS, UAV and UAM Phase 3 ","UAS_Ph3",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",1,"CP-243077",null,"Sunhee Kim, LG Electronics","sunhee.kim@lge.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[531,1050092,"      CT3 aspects of UAS, UAV and UAM Phase 3 ","UAS_Ph3",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.95,"CP-243077",null,"Sunhee Kim, LG Electronics","sunhee.kim@lge.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[532,1060047,"      CT4 aspects of UAS, UAV and UAM Phase 3 ","UAS_Ph3",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.9,"CP-243077",null,"Sunhee Kim, LG Electronics","sunhee.kim@lge.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[533,1060058,"   Security of Uncrewed Aerial System Phase 3 ","UAS_Ph3_Sec",2,"Rel-19","S3","Thu 02/01/25","Mon 03/03/25",0,"SP-241773",null,"Markus Hanhisalo, Ericsson ","markus.hanhisalo@ericsson.com ",null,"33.256 ",106,54,null,null,"Thu 05/12/24","NA"]
[534,1070017,"   Charging for Uncrewed Aerial Systems Phase 3 ","UAS_Ph3-CH",2,"Rel-19","S5","Wed 26/03/25","Tue 09/09/25",0.45,"SP-250396",null,"Jia Dong, China Mobile ","dongjia@chinamobile.com ","; 6/6/25: 0%->45","32.240; 32.255; 32.256; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[535,1010008,"   Application Architecture for UAS applications Phase 3 ","UASAPP_Ph3",2,"Rel-19","S6","Thu 07/09/23","Thu 12/12/24",1,"SP-240741",null,"Roy, Michel, InterDigital ","michel.roy@interdigital.com","; 8/12/23: 0%->20; 14/3/24: 20%->40; 13/6/24: 40%->60; 16/7/24: WID:SP-230991->SP-240741; 4/9/24: 60%->75; 5/12/24: 75%->100","23.255; 23.434 ",101,51,null,null,"Thu 07/09/23","Thu 05/12/24"]
[536,1040043,"   CT Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3","UASAPP_Ph3",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.99,"CP-241281",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[537,1040069,"      CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3","UASAPP_Ph3",3,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.98,"CP-241281",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[538,1040070,"      CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3","UASAPP_Ph3",3,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",1,"CP-241281",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[539,1030033,"   UAS security enhancements ","FS_UAS_Ph3_Sec",2,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240504",null,"Markus Hanhisalo, ","markus.hanhisalo@ericsson.com ","3/4/24: 33.759 added;; 13/6/24: 0%->50; 5/12/24: 50%->100; 6/3/25: 100%->100","33.759",103,52,null,null,"Thu 14/03/24","Thu 06/03/25"]
[540,960018,"Study on Upper layer traffic steering, switching and split over dual 3GPP access ","FS_DualSteer",1,"Rel-19","S1","Thu 02/06/22","Sat 09/09/23",1,"SP-220445",null,"Francesco Pica; Qualcomm ",null,"13/7/22: 22.841 added;; 9/9/22: 0%->30; 10/12/22: 30%->60; 17/3/23: 60%->75; 8/6/23: 75%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95; 8/12/23: 95%->100","22.841",96,49,null,null,"Thu 02/06/22","Fri 08/12/23"]
[541,1040017,"Study on Charging aspects of Uncrewed Aerial Systems ","FS_UAS_CH",1,"Rel-19","S5","Wed 12/06/24","Wed 11/12/24",1,"SP-240983",null,"Jia Dong, China Mobile, ","dongjia@chinamobile.com ","4/9/24: 0%->40; 26/9/24: 28.853 added;; 5/12/24: 40%->75; 5/12/24: FCD:12/12/2024->/25; 6/3/25: 75%->100","28.853",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[542,1020031,"Upper layer traffic steering and switching over dual 3GPP access ","DualSteer",1,"Rel-19","S1","Thu 07/12/23","Sun 10/12/23",0.95,"SP-231412",null,"Pica Francesco, Qualcomm ","fpica<at>qti.qualcomm.com ","; 8/12/23: 0%->95","22.261 ",102,52,null,null,"Thu 07/12/23","Fri 08/12/23"]
[543,1010022,"Edge Computing Considering the Operational Needs of Service Hosting Environment ","EdgeOpNeeds",1,"Rel-19","S1","Mon 21/08/23","Sat 09/09/23",1,"SP-231037",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 6/9/23: 0%->100","22.261 ",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[544,1060048,"5G NR Femto","5G_Femto",1,"Rel-19","S2","Thu 04/01/24","Tue 09/09/25",0.76,"SP-241327",null,"Malla Reddy Sama ","sama@docomolab-euro.com ","; 4/9/24: 0%->30; 26/9/24: WID:SP-240629->SP-241327","23.501; 23.502 ",104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[545,1020002,"   Study on System aspects of 5G NR Femto ","FS_5G_Femto",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-231797",null,"Malla Reddy Sama (NTT DOCOMO) ","sama@docomolab-euro.com ","14/3/24: 0%->40; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 40%->90; 4/9/24: 90%->100; 4/9/24: 100%->",null,102,52,null,null,"Wed 03/01/24","Wed 04/09/24"]
[546,1040028,"   System aspects of 5G NR Femto ","5G_Femto",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-241327",null,"Malla Reddy Sama ","sama@docomolab-euro.com ","; 4/9/24: 0%->30; 26/9/24: WID:SP-240629->SP-241327; 5/12/24: 30%->100","23.501; 23.502 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[547,1060002,"   CT aspects of 5G NR Femto","5G_Femto",2,"Rel-19","C4","Thu 12/12/24","Tue 09/09/25",0.74,"CP-250020",null,"Dojiri, Shunsuke, NTT DOCOMO","dojiri@nttdocomo.com",null,"29.503, 29.504, 29.505, 29.522, 29.571",104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[548,1060049,"      CT3 aspects of 5G NR Femto","5G_Femto",3,"Rel-19","C3","Thu 12/12/24","Tue 09/09/25",0.99,"CP-250020",null,"Dojiri, Shunsuke, NTT DOCOMO","dojiri@nttdocomo.com",null,null,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[549,1060050,"      CT4 aspects of 5G NR Femto","5G_Femto",3,"Rel-19","C4","Thu 12/12/24","Tue 09/09/25",0.99,"CP-250020",null,"Dojiri, Shunsuke, NTT DOCOMO","dojiri@nttdocomo.com",null,null,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[550,1030028,"   Study on security aspects of 5G NR Femto Document for: Approval ","FS_5G_Femto_Sec",2,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240505",null,"Peilin LIU (ZTE) ","liu.peilin@zte.com.cn , ","3/4/24: 33.745 added;; 13/6/24: 0%->30; 5/9/24: 30%->60; 5/12/24: 60%->98; 6/3/25: 98%->100; 5/6/25: 100%->100","33.745",103,52,null,null,"Thu 14/03/24","Thu 05/06/25"]
[551,1060062,"   Security aspects of 5G NR Femto ","5G_Femto_Sec",2,"Rel-19","S3","Thu 30/01/25","Fri 06/06/25",0,"SP-241958",null,"Liu,Peilin liu.peilin@zte.com.cn ","Song,Hua songhua@chinamobile.com ",null,null,106,54,null,null,"Thu 05/12/24","NA"]
[552,1050115,"Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",1,"Rel-19","S1","Thu 04/01/24","Tue 09/09/25",0.76,"SP-231037",null,"Hugh Shieh (AT&T) ","hs6220@att.com ",null,null,102,52,null,null,"Wed 06/09/23","Wed 06/09/23"]
[553,1020066,"   Study on Proximity-based Services in 5GS Phase 3 ","FS_5G_ProSe_Ph3",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-231798",null,"Hugh Shieh (AT&T) ","hs6220@att.com ","14/3/24: 0%->45; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 45%->90; 4/9/24: 90%->100",null,102,52,null,null,"Wed 03/01/24","Wed 04/09/24"]
[554,1040030,"   Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-240988",null,"Nassima Toumi (KPN N.V.)","nassima.toumi@tno.nl","; 4/9/24: 0%->70; 5/12/24: 70%->100","23.304 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[555,1050023,"   CT aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",2,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.65,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com","; 26/9/24: WID:CP-242108->SP-241290","24.554, 24.555, 24.501, 24.587, 29.519, 29.522, 29.525, 29.503, 29.504, 29.518, 29.510, 29.555, 29.559, 29.571, 31.102",105,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[556,1050038,"      CT1 aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.85,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[557,1050116,"      CT3 aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.8,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[558,1050039,"      CT4 aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.9,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[559,1050040,"      CT6 aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",3,"Rel-19","C6","Mon 30/12/24","Tue 09/09/25",0.9,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[560,1060057,"   Security Aspects of Proximity Based Services in 5GS Phase 3 ","5G_ProSe_Sec_Ph3",2,"Rel-19","S3","Thu 05/12/24","Mon 03/03/25",1,"SP-241956",null,"Primary Rapporteur: Ao Lei (Huawei) ","leiao@huawei.com ","; 6/3/25: 0%->95; 6/3/25: FCD:03/03/2025->/25; 5/6/25: 95%->100","33.503 ",106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[561,1050030,"   Charging for 5G ProSe Ph3 ","5G_ProSe_Ph3_CH",2,"Rel-19","S5","Sat 28/12/24","Tue 09/09/25",1,"SP-241377",null,"Xiaoqian Jia (China Telecom)","jiaxq1@chinatelecom.cn ","; 6/3/25: 0%->100","32.277; 32.291; 32.298 ",105,53,null,null,"Wed 04/09/24","Thu 06/03/25"]
[562,1030034,"Study on Security Aspects of Enhancement for Proximity Based Services in 5GS Phase 3 ","FS_5G_ProSe_Ph3_SEC",1,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240513",null,"Lei, Ao (Huawei) ","leiao@huawei.com ","3/4/24: 33.743 added;; 13/6/24: 0%->30; 5/9/24: 30%->60; 5/12/24: 60%->100","33.743",103,52,null,null,"Thu 14/03/24","Thu 05/12/24"]
[563,1050100,"Vehicle Mounted Relays Phase 2 ","VMR_Ph2",1,"Rel-19","S2","Thu 04/01/24","Fri 06/06/25",1,"SP-240989",null,"Hong Cheng (Qualcomm) ","hongc@qti.qualcomm.com ",null,"23.501; 23.502; 23.273 ",105,53,null,null,"Wed 12/06/24","NA"]
[564,1020067,"   Study on Vehicle Mounted Relays Phase 2 ","FS_VMR_Ph2",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-240493",null,"Primary Rapporteur: Hong Cheng (Qualcomm) ","hongc@qti.qualcomm.com ","14/3/24: 0%->40; 2/4/24: WID:SP-231799->SP-240493; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 40%->95; 5/12/24: 95%->100",null,102,52,null,null,"Wed 03/01/24","Thu 05/12/24"]
[565,1040031,"   Stage 2 of Vehicle Mounted Relays Phase 2 ","VMR_Ph2",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-240989",null,"Hong Cheng (Qualcomm) ","hongc@qti.qualcomm.com ","; 4/9/24: 0%->40; 5/12/24: 40%->100","23.501; 23.502; 23.273 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[566,1050026,"   CT aspects of Vehicle Mounted Relays Phase 2 ","VMR_Ph2",2,"Rel-19","C1","Mon 09/09/24","Fri 06/06/25",1,"CP-242253",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com ",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[567,1050101,"      CT1 aspects of Vehicle Mounted Relays Phase 2 ","VMR_Ph2",3,"Rel-19","C1","Mon 09/09/24","Fri 06/06/25",1,"CP-242253",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com ",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[568,1050102,"      CT4 aspects of Vehicle Mounted Relays Phase 2 ","VMR_Ph2",3,"Rel-19","C4","Mon 09/09/24","Fri 06/06/25",1,"CP-242253",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com ",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[569,1050093,"Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",1,"Rel-19","S2","Thu 04/01/24","Tue 09/09/25",0.89,"SP-240971",null,"Michael Starsinic, Interdigital","Michael.Starsinic@Interdigital.com",null,null,105,53,null,null,"Thu 20/06/24","NA"]
[570,1020063,"   Study on User Identities and Authentication Architecture ","FS_UIA_ARC",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-231804",null,"Michael Starsinic, Interdigital ","Michael.Starsinic@Interdigital.com ","14/3/24: 0%->35; 14/3/24: 23.700-32 added;; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 35%->90; 4/9/24: 90%->93; 5/12/24: 93%->100","23.700-32",102,52,null,null,"Wed 03/01/24","Thu 05/12/24"]
[571,1040085,"   Stage 2 of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",2,"Rel-19","S2","Thu 20/06/24","Thu 12/12/24",1,"SP-240971",null,"Michael Starsinic, Interdigital","Michael.Starsinic@Interdigital.com","4/9/24: 0%->15; 5/12/24: 15%->90; 6/3/25: 90%->100; 5/6/25: 100%->100",null,104,53,null,null,"Thu 20/06/24","Thu 05/06/25"]
[572,1050009,"   CT aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",2,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.87,"CP-242029",null,"Sethi, Anuj, InterDigital","anuj.sethi@interdigital.com",null,null,105,53,null,null,"Thu 20/06/24","NA"]
[573,1050094,"      CT1 aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.7,"CP-242029",null,"Sethi, Anuj, InterDigital","anuj.sethi@interdigital.com",null,null,105,53,null,null,"Thu 20/06/24","NA"]
[574,1050095,"      CT3 aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.95,"CP-242029",null,"Sethi, Anuj, InterDigital","anuj.sethi@interdigital.com",null,null,105,53,null,null,"Thu 20/06/24","NA"]
[575,1050096,"      CT4 aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.95,"CP-242029",null,"Sethi, Anuj, InterDigital","anuj.sethi@interdigital.com",null,null,105,53,null,null,"Thu 20/06/24","NA"]
[576,1030032,"Study on security aspects of User Identities and Authentication ","FS_UIA_Sec",1,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240507",null,"Samir Ferdi, ","Samir.Ferdi@InterDigital.com ","3/4/24: 33.700-32 added;; 13/6/24: 0%->35; 5/9/24: 35%->65; 5/12/24: 65%->100","33.700-32",103,52,null,null,"Thu 14/03/24","Thu 05/12/24"]
[577,950007,"Study on FRMCS Phase 5","FS_FRMCS_Ph5",1,"Rel-19","S1","Thu 10/03/22","Tue 12/12/23",1,"SP-241693",null,"Patrick WIMART, UIC","wimart@uic.org","; 4/6/22: 0%->15; 21/6/22: WID:SP-220088->SP-220437. FS_FRMCS_Ph3->FS_FRMCS_Ph5; 9/9/22: 15%->30; 10/12/22: 30%->50; 8/6/23: 50%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90; 8/12/23: 90%->100; 8/1/25: WID:SP-220437->SP-241693","22.989 ",95,48,null,null,"Thu 10/03/22","Wed 08/01/25"]
[578,1000031,"FRMCS Phase 5 ","FRMCS_Ph5",1,"Rel-19","S1","Thu 08/06/23","Tue 09/09/25",0.75,"SP-230512",null,"Nikolopoulou, Vassiliki, UIC ","nikolopoulou@uic.org ","; 6/9/23: 0%->50; 8/12/23: 50%->100","22.280; 22.179; 22.289; 22.261 ",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[579,1000038,"   Stage 2 of Railways specific Enhancements to Mission Critical Services ","FRMCS_Ph5",2,"Rel-19","S6","Thu 08/06/23","Thu 12/12/24",1,"SP-230780",null,"Oettl, Martin, Nokia, ","martin.oettl@nokia.com ","; 7/9/23: 0%->10; 8/12/23: 10%->30; 14/3/24: 30%->40. 14/5/24: acronym: enh4FRMCS ->FRMCS_Ph5 ; 13/6/24: 40%->55; 4/9/24: 55%->70; 5/12/24: 70%->100","23.280; 23.281; 23.282; 23.379; 23.283; 23.289 ",100,51,null,null,"Thu 08/06/23","Thu 05/12/24"]
[580,1050018,"   CT aspects of Railways specific Enhancements to Mission Critical Services ","FRMCS_Ph5",2,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.48,"CP-242102",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,100,51,null,null,"Thu 08/06/23","Thu 13/06/24"]
[581,1050103,"      CT1 aspects of Railways specific Enhancements to Mission Critical Services ","FRMCS_Ph5",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.7,"CP-242102",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,100,51,null,null,"Thu 08/06/23","Thu 13/06/24"]
[582,850044,"Study on Supporting of Railway Smart Station Services ","FS_RAILSS",1,"Rel-19","S1","Thu 19/09/19","Thu 08/09/22",1,"SP-190838",null,"Han, Andrew Min-gyu, Hansung University ","andyhan(at)hansung(dot)ac(dot)kr ","; 8/10/19: 22.890 added;; 6/12/19: 0%->5; 5/12/20: 5%->15; 19/3/21: FCD:12/06/2020->09/21; 19/3/21: 15%->30; 13/9/21: 30%->35; 10/12/21: 35%->45; 11/03/22: Rel-18->Rel-19; 9/9/22: 45%->100","New ; 22.890",85,43,null,null,"Fri 13/09/19","Fri 09/09/22"]
[583,960020,"Study on Network of Service Robots with Ambient Intelligence ","FS_SOBOT",1,"Rel-19","S1","Thu 02/06/22","Tue 12/12/23",1,"SP-220447",null,"LEE, Ki-Dong, LG Electronics ","kidong.lee@lge.com ","13/7/22: 22.916 added;; 9/9/22: 0%->10; 10/12/22: 10%->40; 17/3/23: FCD:03/03/2023->9/9/23; 17/3/23: 40%->70; 8/6/23: 70%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90; 8/12/23: 90%->100","22.916",96,49,null,null,"Thu 02/06/22","Fri 08/12/23"]
[584,990053,"Study on Interconnect of SNPN ","FS_ISN",1,"Rel-19","S1","Thu 08/06/23","Thu 27/06/24",0.4,"SP-230236",null,"Thierry Bérisot, Novamint ","tberisot@novamint.com ","8/6/23: 0%->30; 6/9/23: 30%->60; 8/12/23: FCD:12/12/2023->/2024; 8/12/23: 60%->65","22.848",99,50,null,null,"Thu 16/03/23","Fri 08/12/23"]
[585,1030041,"Interconnect of SNPN ","ISN",1,"Rel-19","S1","Wed 13/03/24","Fri 29/03/24",1,"SP-240194",null,"Thierry Bérisot, Novamint, ","tberisot@novamint.com ","; 14/3/24: 0%->100","22.261 ",103,52,null,null,"Wed 13/03/24","Thu 14/03/24"]
[586,990050,"Edge Computing for Industrial Scenarios ","EDGINDUS",1,"Rel-19","S1","Thu 02/02/23","Fri 03/03/23",1,"SP-230229",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 17/3/23: 0%->100","22.104 ",99,50,null,null,"Thu 16/03/23","Fri 17/03/23"]
[587,990049,"PS Data Off for IMS Data Channel Service ","IMSDCDataOff",1,"Rel-19","S1","Thu 02/02/23","Fri 03/03/23",1,"SP-230227",null,"Yue Hu, China Mobile ","huyueyjy@chinamobile.com ","; 9/8/23: 0%->100","22.011 ",99,50,null,null,"Thu 16/03/23","Wed 09/08/23"]
[588,970044,"Multi-path relay ","MultiRelay",1,"Rel-19","S1","Thu 01/09/22","Mon 19/09/22",1,"SP-220943",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 9/9/22: 0%->100","22.261 ",97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[589,1000025,"UE-to-UE multi-hop relay ","UEMHopRelay",1,"Rel-19","S1","Mon 22/05/23","Tue 06/06/23",1,"SP-230521",null,"Lipford, Mark, FirstNet Authority, ","mark.lipford@firstnet.gov ","; 8/6/23: 100%->","22.261; 22.280 ",100,51,null,null,"Thu 08/06/23","Thu 08/06/23"]
[590,970043,"Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services ","DTT4MBS",1,"Rel-19","S1","Thu 01/09/22","Mon 19/09/22",1,"SP-220941",null,"Saha, Anindya, Saankhya Labs ","anindya@saankhyalabs.com ","; 9/9/22: 0%->100","22.261 ",97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[591,1040083,"MPS for Messaging services ","MPS4msg",1,"Rel-19",null,"Thu 01/09/22","Tue 20/05/25",0.94,"SP-220939",null,"Singh, Ray, Peraton Labs ","rsingh@peratonlabs.com ","; 9/9/22: 0%->100","22.153 ",97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[592,970042,"   (stage 1 of) MPS for Messaging services ","MPS4msg",2,"Rel-19","S1","Thu 01/09/22","Mon 19/09/22",1,"SP-220939",null,"Singh, Ray, Peraton Labs ","rsingh@peratonlabs.com ","; 9/9/22: 0%->100","22.153 ",97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[593,1040029,"   (stage 2 of) MPS for IMS Messaging and SMS services ","MPS4msg",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-240987",null,"Robert Streijl (Peraton Labs), ","rstreijl@peratonlabs.com ","; 4/9/24: 0%->80; 5/12/24: 80%->100","23.401; 23.203; 23.501; 23.502; 23.503; 23.682; 23.204; 23.272; 23.228 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[594,1010031,"   Study on MPS for IMS Messaging and SMS services ","FS_MPS4msg",2,"Rel-19","S2","Wed 03/01/24","Thu 06/06/24",1,"SP-231197",null,"Robert Streijl (Peraton Labs) ","rstreijl@peratonlabs.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-75 added;; 8/12/23: 0%->20; 14/3/24: 0%->70; 13/6/24: 70%->100; 4/9/24: 99%->100","23.700-75",101,51,null,null,"Wed 20/09/23","Wed 04/09/24"]
[595,1050007,"   CT aspects of MPS for IMS Messaging and SMS services ","MPS4msg",2,"Rel-19","C4","Mon 09/09/24","Tue 20/05/25",0.92,"CP-243047",null,"Monnes, Peter (Peraton Labs)","pmonnes@peratonlabs.com",null,"23.540, 24.229, 24.247, 24.301, 24.341, 29.122, 29.128, 29.213, 29.214, 29.228, 29.272, 29.336, 29.338, 24.501, 29.503, 29.513, 29.514, 29.518, 29.522, 29.562, 29.577, 23.540, 24.229, 24.247, 24.301, 24.341, 29.122, 29.128, 29.213, 29.214, 29.228, 29.272,",105,53,null,null,"Wed 12/06/24","NA"]
[596,1050063,"      CT1 aspects of MPS for IMS Messaging and SMS services ","MPS4msg",3,"Rel-19","C1","Mon 09/09/24","Tue 20/05/25",0.93,"CP-243047",null,"Monnes, Peter (Peraton Labs)","pmonnes@peratonlabs.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[597,1050064,"      CT3 aspects of MPS for IMS Messaging and SMS services ","MPS4msg",3,"Rel-19","C3","Mon 09/09/24","Tue 20/05/25",0.9,"CP-243047",null,"Monnes, Peter (Peraton Labs)","pmonnes@peratonlabs.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[598,1050065,"      CT4 aspects of MPS for IMS Messaging and SMS services ","MPS4msg",3,"Rel-19","C4","Mon 09/09/24","Tue 20/05/25",0.92,"CP-243047",null,"Monnes, Peter (Peraton Labs)","pmonnes@peratonlabs.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[599,1050104,"Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",1,"Rel-19","S1","Thu 01/09/22","Tue 09/09/25",0.36,"SP-220992",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 9/9/22: 0%->100","22.261 ",97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[600,1050029,"   Study on MINT support in EPS for 5G-only national roaming UE","FS_MINT_Ph2",2,"Rel-19","C1","Mon 09/09/24","Thu 12/12/24",1,"CP-243260",null,"Li Mingxue, China Telecom","limx36@chinatelecom.cn","3/4/25: WID:CP-242249->CP-243260",null,97,49,null,null,"Fri 09/09/22","Thu 03/04/25"]
[601,970041,"   Stage 2 of Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",2,"Rel-19","S1","Thu 01/09/22","Mon 19/09/22",1,"SP-220992",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 9/9/22: 0%->100","22.261 ",97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[602,1080022,"   CT aspects of Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",2,"Rel-19","C1","Fri 06/06/25","Tue 09/09/25",0,"CP-251218",null,"Li Mingxue, China Telecom","limx36@chinatelecom.cn","; 9/9/22: 0%->100","23.122, 24.301, 31.102",97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[603,1080037,"      CT1 aspects of Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",3,"Rel-19","C1","Fri 06/06/25","Tue 09/09/25",0,"CP-251218",null,"Li Mingxue, China Telecom","limx36@chinatelecom.cn","; 9/9/22: 0%->100","23.122, 24.301, 31.102",97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[604,1080038,"      CT6 aspects of Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",3,"Rel-19","C6","Fri 06/06/25","Tue 09/09/25",0,"CP-251218",null,"Li Mingxue, China Telecom","limx36@chinatelecom.cn","; 9/9/22: 0%->100","23.122, 24.301, 31.102",97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[605,980108,"Measurement Data Collection ","MeasureData",1,"Rel-19","S1","Fri 09/12/22","Tue 20/12/22",1,"SP-221263",null,"Yingjun Zhou, ZTE Corporation ","zhou.yingjun@zte.com.cn ","; 10/12/22: 0%->100","22.261 ",98,50,null,null,"Fri 09/12/22","Sat 10/12/22"]
[606,1010025,"Local traffic routing for multi-access UE ","LTR_MA",1,"Rel-19","S1","Mon 21/08/23","Sat 09/09/23",1,"SP-231035",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 6/9/23: 0%->100","22.261 ",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[607,980008,"Study on Diverse audio Capturing system for End-user Devices ","FS_DaCED",1,"Rel-19","S4","Tue 13/12/22","Thu 12/12/24",1,"SP-221330",null,"Wang Bin, Xiaomi ","wangbin23@xiaomi.com ","; 17/3/23: 0%->5; 17/3/23: 26.933 added;; 8/6/23: 5%->30; 7/9/23: 30%->35; 8/12/23: 35%->45; 14/3/24: 45%->70; 13/6/24: 70%->85; 4/9/24: 85%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100","26.933",98,50,null,null,"Fri 09/12/22","Thu 05/12/24"]
[608,1000034,"Study on Service aspects for supporting the eMMTel service ","FS_eMMTelAPP",1,"Rel-19","S6","Thu 08/06/23","Thu 12/12/24",1,"SP-230779",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 30/6/23: 23.700-92 added;; 7/9/23: 0%->10; 8/12/23: 10%->20; 14/3/24: 20%->35; 13/6/24: 35%->70; 4/9/24: 70%->80; 5/12/24: 80%->100; 5/12/24: FCD:09/09/2024->12/24","23.222 ; 23.700-92",100,51,null,null,"Thu 08/06/23","Thu 05/12/24"]
[609,1070036,"Application enablement aspects for MMTel ","MMTel_App",1,"Rel-19","S6","Tue 16/07/24","Tue 09/09/25",0.56999999999999995,"SP-241019",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","4/9/24: 0%->10; 26/9/24: 23.792 added;; 5/12/24: 10%->60","23.792",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[610,1040073,"   Stage 2 of Application enablement aspects for MMTel ","MMTel_App",2,"Rel-19","S6","Tue 16/07/24","Mon 28/10/24",1,"SP-241019",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","4/9/24: 0%->10; 26/9/24: 23.792 added;; 5/12/24: 10%->60; 6/3/25: 60%->100","23.792",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[611,1070008,"   CT aspects of Application enablement aspects for MMTel ","MMTel_App",2,"Rel-19","C1","Thu 06/03/25","Tue 09/09/25",0.45,"CP-250249",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,"24.542",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[612,1070037,"      CT1 aspects of Application enablement aspects for MMTel ","MMTel_App",3,"Rel-19","C1","Thu 06/03/25","Tue 09/09/25",0.6,"CP-250249",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,"24.542",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[613,1070038,"      CT3 aspects of Application enablement aspects for MMTel ","MMTel_App",3,"Rel-19","C3","Thu 06/03/25","Tue 09/09/25",0.3,"CP-250249",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,"24.542",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[614,1050053,"Enhanced application layer support for location services ","eLSAPP",1,"Rel-19","S6","Thu 08/06/23","Tue 09/09/25",0.77,"SP-241005",null,"Liping Wu, CATT ","wuliping@cictmobile.com ",null,"23.434; 23.436 ",105,53,null,null,"Wed 12/06/24","NA"]
[615,1000035,"   Study on enhanced application layer support for location services ","FS_eLSAPP",2,"Rel-19","S6","Thu 08/06/23","Mon 09/09/24",1,"SP-230778",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 30/6/23: 23.700-72 added;; 7/9/23: 0%->15; 8/12/23: 15%->25; 14/3/24: 25%->40; 2/4/24: WID:SP-230778->SP-240295; 2/4/24: FCD:05/06/2024->/24; 13/6/24: 40%->85; 13/6/24: WID:SP-240295->SP-230778; 4/9/24: 85%->100","23.434 ; 23.700-72",100,51,null,null,"Thu 08/06/23","Wed 04/09/24"]
[616,1040072,"   Stage 2 of Enhanced application layer support for location services ","eLSAPP",2,"Rel-19","S6","Wed 12/06/24","Thu 12/12/24",1,"SP-241005",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 4/9/24: 0%->30; 5/12/24: 30%->100","23.434; 23.436 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[617,1050015,"   CT aspects of Enhanced application layer support for location services ","eLSAPP",2,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.62,"CP-242064",null,"Wang, Baixiao (CATT)","wangbaixiao@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[618,1050054,"      CT1 aspects of Enhanced application layer support for location services ","eLSAPP",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.85,"CP-242064",null,"Wang, Baixiao (CATT)","wangbaixiao@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[619,1050055,"      CT3 aspects of Enhanced application layer support for location services ","eLSAPP",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.95,"CP-242064",null,"Wang, Baixiao (CATT)","wangbaixiao@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[620,1000036,"Sharing of administrative configuration between interconnected MC service systems ","MCShAC",1,"Rel-19","S6","Thu 08/06/23","Thu 12/12/24",1,"SP-230692",null,"andreas.flander@bdbos.bund.de ","andreas.flander@bdbos.bund.de ","; 7/9/23: 0%->5; 8/12/23: 5%->40; 14/3/24: 40%->90; 13/6/24: 90%->90; 4/9/24: 90%->100","23.280; 23.379; 23.281; 23.282 ",100,51,null,null,"Thu 08/06/23","Wed 04/09/24"]
[621,1060051,"5GMSG Service phase 3 ","5GMARCH_Ph3",1,"Rel-19","S6","Thu 08/06/23","Tue 09/09/25",0.64,"SP-230781",null,"Liu, Yue, China Mobile, ","liuyueyjy@chinamobile.com ","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50",null,100,51,null,null,"Thu 08/06/23","Wed 04/09/24"]
[622,1000037,"   5GMSG Service phase 3 ","5GMARCH_Ph3",2,"Rel-19","S6","Thu 08/06/23","Thu 12/12/24",1,"SP-230781",null,"Liu, Yue, China Mobile, ","liuyueyjy@chinamobile.com ","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50; 5/12/24: 50%->100; 5/12/24: FCD:09/09/2024->12/24",null,100,51,null,null,"Thu 08/06/23","Thu 05/12/24"]
[623,1060019,"   CT aspects for enabling MSGin5G Service phase 3","5GMARCH_Ph3",2,"Rel-19","C1","Mon 02/12/24","Tue 09/09/25",0.28999999999999998,"CP-243258",null,"Liu, Yue, China Mobile","liuyueyjy@chinamobile.com","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50","24.538, 24.544, 24.546, 29.538",100,51,null,null,"Thu 08/06/23","Wed 04/09/24"]
[624,1060052,"      CT1 aspects for enabling MSGin5G Service phase 3","5GMARCH_Ph3",3,"Rel-19","C1","Mon 02/12/24","Tue 09/09/25",0.75,"CP-243258",null,"Liu, Yue, China Mobile","liuyueyjy@chinamobile.com","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50","24.538, 24.544, 24.546, 29.538",100,51,null,null,"Thu 08/06/23","Wed 04/09/24"]
[625,1060053,"      CT3 aspects for enabling MSGin5G Service phase 3","5GMARCH_Ph3",3,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.5,"CP-243258",null,"Liu, Yue, China Mobile","liuyueyjy@chinamobile.com","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50","24.538, 24.544, 24.546, 29.538",100,51,null,null,"Thu 08/06/23","Wed 04/09/24"]
[626,1030030,"   Security aspects for MSGin5G Service Phase 3 ","5GMARCH_SEC_Ph3",2,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240516",null,"Xiaoting Huang, ","huangxiaoting@chinamobile.com ","; 13/6/24: 0%->70; 5/9/24: 70%->100","33.501 ",103,52,null,null,"Thu 14/03/24","Thu 05/09/24"]
[627,1000039,"Enhanced Mission Critical Architecture","enhMC",1,"Rel-19","S6","Thu 08/06/23","Thu 12/12/24",1,"SP-241691",null,"Negalaguli, Harish, Motorola Solutions, ","harish.negalaguli@motorolasolutions.com ","; 7/9/23: WID:SP-230695->SP-230988; 7/9/23: 0%->5; 8/12/23: 5%->30; 14/3/24: 30%->40; 13/6/24: 40%->60; 4/9/24: 60%->75; 5/12/24: 75%->100; 8/1/25: WID:SP-230988->SP-241691","23.280; 23.379; 23.281; 23.282; 23.283; 23.289 ",100,51,null,null,"Thu 08/06/23","Wed 08/01/25"]
[628,1050071,"SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",1,"Rel-19","S6","Thu 07/09/23","Tue 09/09/25",0.84,"SP-230989",null,"Cuili Ge, Huawei ","gecuili@huawei.com ","8/12/23: 0%->25; 14/3/24: 25%->35; 13/6/24: 35%->70",null,101,51,null,null,"Thu 07/09/23","Thu 13/06/24"]
[629,1010006,"   Stage 2 of SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",2,"Rel-19","S6","Thu 07/09/23","Thu 12/12/24",1,"SP-230989",null,"Cuili Ge, Huawei ","gecuili@huawei.com ","8/12/23: 0%->25; 14/3/24: 25%->35; 13/6/24: 35%->70; 4/9/24: 70%->80; 5/12/24: 80%->100",null,101,51,null,null,"Thu 07/09/23","Thu 05/12/24"]
[630,1050017,"   CT aspects of SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",2,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.78,"CP-243261",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"24.543, 24.548, 29.548, 29.549",101,51,null,null,"Thu 07/09/23","Thu 13/06/24"]
[631,1050072,"      CT1 aspects of SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.8,"CP-243261",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,101,51,null,null,"Thu 07/09/23","Thu 13/06/24"]
[632,1050073,"      CT3 aspects of SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",1,"CP-243261",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,101,51,null,null,"Thu 07/09/23","Thu 13/06/24"]
[633,1040081,"Architecture for enabling Edge Applications Phase 3 ","EDGEAPP_Ph3",1,"Rel-19",null,"Thu 07/09/23","Tue 09/09/25",0.76,"SP-231160",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ","; 8/12/23: 0%->15; 14/3/24: 15%->35","23.558 ",101,51,null,null,"Thu 07/09/23","Thu 14/03/24"]
[634,1010007,"   Stage 2 of enabling Edge Applications Phase 3 ","EDGEAPP_Ph3",2,"Rel-19","S6","Thu 07/09/23","Thu 12/12/24",1,"SP-231160",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ","; 8/12/23: 0%->15; 14/3/24: 15%->35; 13/6/24: 35%->80; 4/9/24: 80%->85; 5/12/24: 85%->100","23.558 ",101,51,null,null,"Thu 07/09/23","Thu 05/12/24"]
[635,1040008,"   CT aspects for Enabling Edge Applications Phase 3","EDGEAPP_Ph3",2,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.66,"CP-241074",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com",null,"24.558,29.558",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[636,1040058,"      CT1 aspects for Enabling Edge Applications Phase 3","EDGEAPP_Ph3",3,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.98,"CP-241074",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","16/7/24: FCD:06/06/2025->/25",null,101,51,null,null,"Wed 06/09/23","Tue 16/07/24"]
[637,1040059,"      CT3 aspects for Enabling Edge Applications Phase 3","EDGEAPP_Ph3",3,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.7,"CP-241074",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","16/7/24: 0%->100",null,101,51,null,null,"Wed 06/09/23","Tue 16/07/24"]
[638,0,"Rel-19 miscellaneous Security",null,1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,null,null,null,null,null,null,null,null,null,null,"Thu 07/12/23","NA"]
[639,1030029,"Security Assurance Specification for maintenance of 5G features ","SCAS_5G_Maint",1,"Rel-19","S3","Tue 02/04/24","Mon 03/03/25",1,"SP-240515",null,"Rong Wu (Huawei) ","raina.wu@huawei.com ","5/9/24: 0%->50; 5/12/24: 50%->100",null,103,52,null,null,"Thu 14/03/24","Thu 05/12/24"]
[640,1010010,"5G Security Assurance Specification (SCAS) for the Unified Data Repository (UDR) ","SCAS_5G_UDR",1,"Rel-19","S3","Wed 06/09/23","Tue 21/05/24",0.8,"SP-230864",null,"Andreas, Joerg, BSI Germany ","joerg.andreas@bsi.bund.de ","; 8/12/23: 0%->10; 3/4/24: 33.530 added;; 13/6/24: 10%->50; 5/9/24: 50%->60; 5/12/24: 60%->80","33.926 ; 33.530",101,51,null,null,"Wed 06/09/23","Thu 05/12/24"]
[641,1010011,"5G Security Assurance Specification (SCAS) for the Short Message Service Function (SMSF) ","SCAS_5G_SMSF",1,"Rel-19","S3","Wed 06/09/23","Mon 09/09/24",1,"SP-231158",null,"Manjesh K. Hanawal, IIT Bombay","mhanawal@iitb.ac.in","8/12/23: 0%->10; 4/1/24: 33.529 added;; 14/3/24: 10%->40; 13/6/24: 40%->70; 5/9/24: 70%->40; 5/9/24: 40%->100; 5/12/24: 100%->100","33.529",101,51,null,null,"Wed 06/09/23","Thu 05/12/24"]
[642,1010012,"Addition of 256-bit security Algorithms ","256_Algo",1,"Rel-19","S3","Wed 06/09/23","Sun 03/03/24",1,"SP-240476",null,"Orkopoulos, Stawros ","stawros.orkopoulos@nokia.com ","8/12/23: 0%->10; 4/1/24: 35.248 added;; 14/3/24: 10%->100; 2/4/24: WID:SP-231159->SP-240476","35.248; 35.247; 35.246; 35.245; 35.244; 35.243; 35.242; 35.241; 35.240",101,51,null,null,"Wed 06/09/23","Tue 02/04/24"]
[643,1020036,"Addition of Milenage-256 algorithm ","Milenage_256",1,"Rel-19","S3","Wed 03/01/24","Thu 12/12/24",1,"SP-241087",null,"Mireille Pauliac ","mireille.pauliac@thalesgroup.com ","4/1/24: 35.237 added;; 4/1/24: 35.236 added;; 4/1/24: 35.235 added;; 4/1/24: 35.234 added;; 14/3/24: 0%->5; 5/9/24: 5%->65; 26/9/24: WID:SP-231792->SP-241087; 5/12/24: 65%->100","35.237; 35.236; 35.235; 35.234",102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[644,1020041,"Study on enabling a cryptographic algorithm transition to 256-bits ","FS_CAT256",1,"Rel-19","S3","Wed 03/01/24","Thu 12/12/24",1,"SP-231788",null,"Yuto Nakano ","yt-nakano@kddi.com ","4/1/24: 33.700-41 added;; 14/3/24: 0%->10; 13/6/24: 10%->90; 5/9/24: 90%->100","33.700-41",102,52,null,null,"Thu 07/12/23","Thu 05/09/24"]
[645,1020034,"Study on enablers for Zero Trust Security ","FS_eZTS",1,"Rel-19","S3","Wed 03/01/24","Thu 12/12/24",1,"SP-231784",null,"Sheeba Backia Mary Baskaran ","smary@lenovo.com ","4/1/24: 33.794 added;; 14/3/24: 0%->20; 13/6/24: 20%->50; 5/9/24: 50%->75; 5/12/24: 75%->95; 6/3/25: 95%->100; 5/6/25: 100%->100","33.794",102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[646,1020035,"Mission critical security enhancements for release 19 ","MCXSec4",1,"Rel-19","S3","Thu 04/01/24","Fri 30/08/24",0.99,"SP-231783",null,"Woodward, Tim, Motorola Solutions, Inc. ","tim.woodward@motorolasolutions.com ","; 14/3/24: 0%->10; 5/9/24: 10%->50; 5/12/24: 50%->90; 6/3/25: 90%->95; 5/6/25: 95%->99","33.180 ",102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[647,1020038,"Study on the security support for the Next Generation Real Time Communication services phase 2 ","FS_NG_RTC_SEC_Ph2",1,"Rel-19","S3","Wed 03/01/24","Mon 30/12/24",1,"SP-240233",null,"Vlasios Tsiatsis ","vlasios.tsiatsis@ericsson.com ","4/1/24: 33.790 added;; 14/3/24: 0%->17; 2/4/24: WID:SP-231785->SP-240233; 13/6/24: 17%->40; 5/9/24: 40%->60; 5/12/24: 60%->80; 6/3/25: 80%->80; 6/3/25: FCD:12/12/2024->/25; 5/6/25: 80%->100","33.790",102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[648,1060063,"Security support for the Next Generation Real Time Communication services Phase 2 ","NG_RTC_SEC_Ph2",1,"Rel-19","S3","Thu 02/01/25","Mon 03/03/25",0,"SP-250078",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 26/3/25: WID:SP-241778->SP-250078","33.203 ",106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[649,1020040,"Study of ACME for Automated Certificate Management in SBA ","FS_ACME_SBA",1,"Rel-19","S3","Wed 03/01/24","Thu 12/12/24",1,"SP-231787",null,"Charles Eckel ","eckelcu(at)cisco.com ","4/1/24: 33.776 added;; 14/3/24: 0%->15; 13/6/24: 15%->45; 13/6/24: FCD:06/06/2024->12/24; 5/9/24: 45%->55; 5/12/24: 55%->100; 6/3/25: 100%->100; 5/6/25: 100%->100","33.776",102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[650,1060066,"Automatic Certificate Management Environment (ACME) for the Service Based Architecture (SBA) ","ACME_SBA",1,"Rel-19","S3","Thu 05/12/24","Fri 06/06/25",1,"SP-241960",null,"Charles Eckel (Cisco)","eckelcu(at)cisco.com","; 6/3/25: 0%->55; 5/6/25: 55%->100","33.310 ",106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[651,1080043,"Roaming and interconnect authorization aspects in indirect communication ","SBA_RoamInt-SEC",1,"Rel-19","S3","Thu 05/06/25","Fri 06/06/25",0,"SP-250651",null,"tbd ",null,null,"33.501 ",null,null,null,null,"Thu 05/06/25","NA"]
[652,1080046,"Public key distribution and Issuer claim verification of the Access Token ","SBA_KDATV-SEC",1,"Rel-19","S3","Thu 05/06/25","Fri 06/06/25",0,"SP-250655",null,"TBD ",null,null,"33.501 ",null,null,null,null,"Thu 05/06/25","NA"]
[653,1020042,"3GPP profiles for cryptographic algorithms and security protocols ","CryptoSP",1,"Rel-19","S3","Wed 03/01/24","Thu 12/12/24",1,"SP-231793",null,"Mohsin Khan A ","mohsin.a.khan@ericsson.com ","; 14/3/24: 0%->20; 13/6/24: 20%->50; 5/9/24: 50%->80; 5/12/24: 80%->100; 6/3/25: 100%->100; 5/6/25: 100%->100","33.127; 33.203; 33.210; 33.222; 33.246; 33.259; 33.303; 33.310; 33.401; 33.402; 33.434; 33.501 ",102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[654,1020043,"Study on mitigations against bidding down attacks ","FS_MiBiDA",1,"Rel-19","S3","Wed 03/01/24","Thu 12/12/24",1,"SP-231789",null,"Noamen Ben Henda ","noamen.ben.henda@huawei.com ","4/1/24: 33.701 added;; 14/3/24: 0%->20; 13/6/24: 20%->85; 13/6/24: FCD:05/06/2024->12/24; 5/9/24: 85%->100","33.701",102,52,null,null,"Thu 07/12/23","Thu 05/09/24"]
[655,1060054,"Mobility over non-3GPP access to avoid full primary authentication ","Non3GPPMob_Sec",1,"Rel-19","S3","Wed 03/01/24","Tue 09/09/25",0.53,"SP-241088",null,"Khare, Saurabh ","saurabh.khare@nokia.com ","; 26/9/24: WID:SP-240653->SP-241088","33.501 ",104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[656,1020045,"   Study on Security for mobility over non-3GPP access to avoid full primary authentication ","FS_Non3GPPMob_Sec",2,"Rel-19","S3","Wed 03/01/24","Fri 30/08/24",0.25,"SP-231791",null,"Saurabh Khare, Nokia ","Saurabh.Khare@nokia.com ","4/1/24: 33.702 added;; 14/3/24: 0%->25","33.702",102,52,null,null,"Thu 07/12/23","Thu 14/03/24"]
[657,1040024,"   Security for mobility over non-3GPP access to avoid full primary authentication ","Non3GPPMob_Sec",2,"Rel-19","S3","Wed 07/08/24","Thu 12/12/24",0,"SP-241088",null,"Khare, Saurabh ","saurabh.khare@nokia.com ","; 26/9/24: WID:SP-240653->SP-241088","33.501 ",104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[658,1060020,"   CT aspects of security for mobility over non-3GPP access to avoid full primary authentication","Non3GPPMob_Sec",2,"Rel-19","C1","Mon 02/12/24","Tue 09/09/25",1,"CP-250133",null,"Nassar, Mohamed Amin, Nokia","mohamed.a.nassar@nokia.com",null,"24.502",104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[659,0,"Rel-19 miscellaneous OAM&charging",null,1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,null,null,null,null,null,null,null,null,null,null,"Thu 07/12/23","NA"]
[660,1070020,"Charging aspects for Multi-Operator Core Network (MOCN) Network Sharing ","CH_MOCN_NetShare",1,"Rel-19","S5","Wed 26/03/25","Tue 09/09/25",0.75,"SP-250371",null,"Robert Törnkvist, Ericsson, ","robert.tornkvist@ericsson.com ","; 6/6/25: 0%->75","32.130; 32.240; 32.255; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[661,1060006,"Service Based Management Architecture enhancement phase 3 ","SBMA_Ph3",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.9,"SP-241939",null,"Kai Zhang (Huawei)","kai.zhangkai@huawei.com","; 6/3/25: 0%->40; 6/6/25: 40%->90","32.156; 28.532; 28.533; 28.537; 28.622; 28.623; 28.530; 28.550; 32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.552; 28.554; 28.558; 32.130; 28.313; 28.314; 28.623; 28.310; 28.530; 28.531; 28.111; 28.550; 28.621; 28.623; 32.421; 32.422; 28.404; 28.405;",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[662,1020019,"Study on Management Data Analytics (MDA) Phase 3 ","FS_eMDAS_Ph3",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-241157",null,"Brendan T Hassett (Huawei) ","brendan.t.hassett@huawei.com ","13/6/24: 0%->70; 16/7/24: WID:SP-231726->SP-240968; 4/9/24: 70%->90; 4/9/24: FCD:09/09/2024->12/24; 26/9/24: WID:SP-240968->SP-241157; 5/12/24: 90%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[663,1060014,"Management Data Analytics phase 3 ","eMDAS_Ph3",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.85,"SP-241947",null,"Brendan T Hassett (Huawei)","brendan.t.hassett@huawei.com","; 6/3/25: 0%->30; 6/6/25: 30%->85","28.104 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[664,1020008,"Study on intent driven management services for mobile network phase 3 ","FS_IDMS_MN_Ph3",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231737",null,"Ruiyue Xu (Huawei) ","xuruiyue@huawei.com ","14/3/24: 0%->5; 13/6/24: 5%->70; 4/9/24: 70%->95; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 95%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[665,1060013,"Intent driven management services for mobile network phase 3 ","IDMS_MN_Ph3",1,"Rel-19","S5","Thu 30/01/25","Fri 06/06/25",1,"SP-241946",null,"Ruiyue Xu (Huawei)","xuruiyue@huawei.com","; 6/3/25: 0%->65; 6/6/25: 65%->100","28.312 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[666,1020009,"Study on closed control loop management ","FS_CCLM",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231735",null,"Deepanshu Gautam (Samsung) ","deepanshu.g@samsung.com ","14/3/24: 0%->5; 13/6/24: 5%->40; 4/9/24: 40%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[667,1020018,"Study on management aspects of Network Digital Twin ","FS_NDT",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231727",null,"Yushuang Hu (China Mobile) ","huyushuang@chinamobile.com ","4/1/24: 28.915 added;; 14/3/24: 0%->5; 13/6/24: 5%->65; 13/6/24: WID:SP-231428->SP-231727; 4/9/24: 65%->95; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 95%->100","28.915",102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[668,1060005,"Management aspects of Network Digital Twins ","NDT",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.95,"SP-241938",null,"Yushuang Hu (China Mobile) ","huyushuang@chinamobile.com","6/3/25: 0%->10; 6/6/25: 10%->95",null,106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[669,1020010,"Study on Cloud Aspects of Management and Orchestration ","FS_Cloud_OAM",1,"Rel-19","S5","Wed 03/01/24","Tue 09/09/25",0.9,"SP-241566",null,"Guangjing Cao (CMCC)","caoguangjing@chinamobile.com","14/3/24: 0%->2; 13/6/24: 2%->40; 4/9/24: 40%->80; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 80%->90; 8/1/25: WID:SP-231781->SP-241566 (rapp changed); 6/3/25: 90%->85; 6/3/25: FCD:30/08/2024->/25; 6/6/25: 85%->90",null,102,52,null,null,"Thu 07/12/23","Fri 06/06/25"]
[670,1020016,"Study on Enablers for Security Monitoring ","FS_SECM",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231736",null,"Clifton Fernandes (Nokia) ","clifton.fernandes@nokia.com ","4/1/24: 28.870 added;; 4/9/24: 0%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100","28.870",102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[671,1020011,"Study on Service Based Management Architecture enhancement phase 3 ","FS_SBMA_Ph3",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-241569",null,"Kai Zhang (Huawei) ","kai.zhangkai@huawei.com ","13/6/24: 0%->45; 4/9/24: 45%->75; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 75%->100; 8/1/25: WID:SP-231725->SP-241569",null,102,52,null,null,"Thu 07/12/23","Wed 08/01/25"]
[672,1020033,"Study on Management of planned configurations ","FS_PlanM",1,"Rel-19","S5","Thu 04/01/24","Mon 09/09/24",1,"SP-231721",null,"Olaf Pollakowski (Nokia) ","olaf.pollakowski@nokia.com ","4/1/24: 28.872 added;; 13/6/24: 0%->60; 4/9/24: 60%->100","28.872",102,52,null,null,"Wed 03/01/24","Wed 04/09/24"]
[673,1050032,"Management of planned configurations ","PlanM",1,"Rel-19","S5","Wed 04/09/24","Tue 09/09/25",0.75,"SP-241379",null,"Olaf Pollakowski (Nokia)","olaf.pollakowski@nokia.com","26/9/24: 28.572 added;; 5/12/24: 0%->60; 6/3/25: 60%->75; 6/6/25: 75%->75; 6/6/25: FCD:Fri 06/06/->/25","28.572",105,53,null,null,"Wed 04/09/24","Fri 06/06/25"]
[674,1060010,"Closed Control Loop Management ","CCLM",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.8,"SP-241943",null,"Deepanshu Gautam (Samsung)","deepanshu.g@samsung.com","; 6/3/25: 0%->10; 6/6/25: 10%->80","28.535; 28.536; 28.622; 32.161 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[675,1020025,"Data management phase 2 ","MADCOL_Ph2",1,"Rel-19","S5","Wed 03/01/24","Tue 09/09/25",0.88,"SP-250116",null,"Sreekumar Pothera Kalloor (Nokia)","sreekumar.pk@nokia.com","; 13/6/24: 0%->50; 16/7/24: WID:SP-231746->SP-240877; 4/9/24: 50%->80; 5/12/24: 80%->88. 03/25: Rapporteur updated from sivaramakrishnan.swaminathan@nokia.com; 26/3/25: WID:SP-240877->SP-250116; 26/3/25: FCD:30/12/2024->/25; 6/6/25: 88%->88; 6/6/25: FCD:","28.622; 28.623 ",102,52,null,null,"Thu 07/12/23","Fri 06/06/25"]
[676,1020012,"Study on data management regarding subscriptions and reporting ","FS_Data_SREP",1,"Rel-19","S5","Wed 03/01/24","Mon 09/09/24",1,"SP-231732",null,"Robert Petersen (Ericsson) ","robert.petersen@ericsson.com ","13/6/24: 0%->60; 4/9/24: 60%->100",null,102,52,null,null,"Thu 07/12/23","Wed 04/09/24"]
[677,1020026,"5G performance measurements and KPIs phase 4 ","PM_KPI_5G_Ph4",1,"Rel-19","S5","Wed 03/01/24","Tue 09/09/25",0.9,"SP-241155",null,"Ruan bang qiu","ruan.bangqiu@zte.com.cn","; 13/6/24: 0%->20; 4/9/24: 20%->30; Rapporteur update: Xiebaoguo->Ruan bang qiu (ruan.bangqiu@zte.com.cn); 26/9/24: WID:SP-231747->SP-241155; 5/12/24: 30%->65; 6/3/25: 65%->75; 6/6/25: 75%->90; 6/6/25: FCD:Mon 30/12/->/25","28.552; 32.425; 28.554; 28.532; 28.550; 28.abc ",102,52,null,null,"Thu 07/12/23","Fri 06/06/25"]
[678,1020027,"5G Advanced NRM features phase 3 ","AdNRM_Ph3",1,"Rel-19","S5","Wed 03/01/24","Fri 06/06/25",1,"SP-250123",null,"Sean Sun (Nokia) ","sean.sun@nokia-sbell.com ","; 13/6/24: 0%->15; 16/7/24: WID:SP-231745->SP-240875; 4/9/24: 15%->30; 5/12/24: 30%->60; 8/1/25: WID:SP-240875->SP-241565; 6/3/25: 60%->75; 26/3/25: WID:SP-241565->SP-250123; 26/3/25: FCD:30/12/2024->/25; 6/6/25: 75%->100","28.540; 28.541; 28.622; 28.623 ",102,52,null,null,"Thu 07/12/23","Fri 06/06/25"]
[679,1020028,"Subscriber and Equipment Trace and QoE collection management ","TraceQoE_OAM",1,"Rel-19","S5","Wed 03/01/24","Tue 09/09/25",0.8,"SP-250115",null,"Zu Qiang (Ericsson) ","zu.qiang@ericsson.com ","; 13/6/24: 0%->20; 4/9/24: 20%->40; 5/12/24: 40%->75; 6/3/25: 75%->80; 26/3/25: WID:SP-231748->SP-250115; 6/6/25: FCD:Mon 30/12/->/25","32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.622; 28.623 ",102,52,null,null,"Thu 07/12/23","Fri 06/06/25"]
[680,1020013,"Study on Management Aspects of NTN Phase 2 ","FS_NTN_OAM_Ph2",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231733",null,"MingRui Sun (China Unicom) ","sunmr19@chinaunicom.cn ","13/6/24: 0%->65; 4/9/24: 65%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[681,1020014,"Study on management of IAB nodes ","FS_NR_mobile_IAB_OAM",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231729",null,"JunFeng Wang (Ericsson) ","junfeng.a.wang@ericsson.com ","13/6/24: 0%->40; 13/6/24: FCD:09/09/2024->12/24; 4/9/24: 40%->90; 5/12/24: 90%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[682,1060015,"Management of IAB nodes ","NR_MOBILE_IAB_OAM",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.7,"SP-241948",null,"JunFeng Wang (Ericsson)","junfeng.a.wang@ericsson.com","; 6/6/25: 0%->70","28.541; 28.540; 28.531; 28.314; 28.315 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[683,1020017,"Study on management aspects of RedCap feature ","FS_NR_RedCap_OAM",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231734",null,"Zhen Xing (China Unicom) ","xingz12@chinaunicom.cn ","13/6/24: 0%->50; 4/9/24: 50%->75; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 75%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[684,1020020,"Study on Enhancement of Management Aspects related to NWDAF Phase 2 ","FS_NWDAF_OAM_Ph2",1,"Rel-19","S5","Wed 03/01/24","Mon 09/09/24",1,"SP-231724",null,"Primary Rapporteur: Song Zhao (China Telecom) ","zhaosong1@chinatelecom.cn ","13/6/24: 0%->75; 4/9/24: 75%->100",null,102,52,null,null,"Thu 07/12/23","Wed 04/09/24"]
[685,1050031,"Enhancement of Management Aspects Related of NWDAF Phase 2 ","NWDAF_OAM_Ph2",1,"Rel-19","S5","Wed 04/09/24","Fri 06/06/25",1,"SP-241378",null,"Song Zhao (China Telecom) ","zhaosong1@chinatelecom.cn ","; 5/12/24: 0%->60; 6/3/25: 60%->65; 6/6/25: 65%->100","28.552; 28.541 ",105,53,null,null,"Wed 04/09/24","Fri 06/06/25"]
[686,1020015,"Study on Management of Network Sharing Phase3 ","FS_NetShare_OAM_Ph3",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-240966",null,"ZhaoNing Wang (China Unicom) ","wangzn18@chinaunicom.cn ","13/6/24: 0%->50; 16/7/24: WID:SP-231731->SP-240966; 4/9/24: 50%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[687,1020022,"Study on Enhanced OAM for management exposure to external consumers ","FS_MExpo",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-241570",null,"Srilakshmi Srinivasaraju (Nokia)","srilakshmi.s@nokia.com","14/3/24: 0%->5; 13/6/24: 5%->50; 16/7/24: WID:SP-231728->SP-240967; 4/9/24: 50%->60; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 60%->100; 8/1/25: WID:SP-240967->SP-241570",null,102,52,null,null,"Thu 07/12/23","Wed 08/01/25"]
[688,0,"Rel-19 other",null,1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,null,null,null,null,null,null,null,null,null,null,"Thu 07/12/23","NA"]
[689,1060055,"Reducing Information Exposure over SBI ","RedInfExp_SBI",1,"Rel-19",null,"Wed 07/06/23","Tue 09/09/25",1,"CP-243308",null,"Nivedya P S, Samsung","nivedya.ps@samsung.com","30/6/23: 29.857 added;; 3/4/25: WID:CP-243019->CP-243308",null,100,51,null,null,"Wed 07/06/23","Thu 03/04/25"]
[690,1000001,"   Study on Reducing Information Exposure over SBI ","FS_RedInfExp_SBI",2,"Rel-19","C4","Wed 07/06/23","Tue 12/12/23",1,"CP-231350",null,"Varini Gupta, Samsung ","varini.gupta@samsung.com ","30/6/23: 29.857 added;","29.857",100,51,null,null,"Wed 07/06/23","Fri 30/06/23"]
[691,1060003,"   Reducing Information Exposure over SBI ","RedInfExp_SBI",2,"Rel-19","C4","Mon 02/12/24","Tue 09/09/25",1,"CP-243308",null,"Nivedya P S, Samsung","nivedya.ps@samsung.com","30/6/23: 29.857 added;","29.510, 29.500",100,51,null,null,"Wed 07/06/23","Fri 30/06/23"]
[692,1010003,"Study on IMS Disaster Prevention and Restoration Enhancement","FS_IMS_RES",1,"Rel-19","C4","Thu 25/08/22","Sun 03/03/24",1,"CP-232281",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn","21/9/23: 29.866 added;","29.xxx; 29.866",96,49,null,null,"Fri 03/06/22","Thu 21/09/23"]
[693,1080001,"IMS Disaster Prevention and Restoration Enhancement","IMS_RES-CT",1,"Rel-19","C4","Tue 28/11/23","Tue 09/09/25",0.5,"CP-251016",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn",null,"23.380, 24.229, 23.334, 29.244, 29.500, 29.562, 29.213, 29.513",96,49,null,null,"Fri 03/06/22","Thu 21/09/23"]
[694,1080035,"   CT3 aspects of IMS Disaster Prevention and Restoration Enhancement","IMS_RES-CT",2,"Rel-19","C3","Tue 28/11/23","Sun 03/03/24",0,"CP-251016",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn",null,"23.380, 24.229, 23.334, 29.244, 29.500, 29.562, 29.213, 29.513",96,49,null,null,"Fri 03/06/22","Thu 21/09/23"]
[695,1080036,"   CT4 aspects of IMS Disaster Prevention and Restoration Enhancement","IMS_RES-CT",2,"Rel-19","C4","Fri 06/06/25","Tue 09/09/25",1,"CP-251016",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn",null,"23.380, 24.229, 23.334, 29.244, 29.500, 29.562, 29.213, 29.513",96,49,null,null,"Fri 03/06/22","Thu 21/09/23"]
[696,1000016,"Study on Film Grain Synthesis ","FS_FGS",1,"Rel-19","S4","Thu 08/06/23","Mon 09/09/24",1,"SP-241389",null,"Brian Lee (Dolby Laboratories) ","Brian.Lee@dolby.com ","; 7/9/23: 0%->10; 8/12/23: 10%->20; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 20%->30; 14/3/24: FCD:03/03/2024->3/3/25; Rel-18->Rel-19; 13/6/24: 30%->; 4/9/24: 30%->100; 4/9/24: FCD:03/03/2025->09/24; 4/9/24: WID:SP-230539->SP-241120 ; 26/9/24: WID:SP-...","26.955 ; 26.855",100,51,null,null,"Thu 08/06/23","Thu 26/09/24"]
[697,1000019,"Study of Avatars in Real-Time Communication Services ","FS_AVATAR",1,"Rel-19","S4","Thu 08/06/23","Mon 03/03/25",1,"SP-230544",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi AT qti DOT qualcomm DOT com ","7/9/23: 0%->5; 21/9/23: 26.813 added;; 8/12/23: 5%->20; 14/3/24: 20%->30; 14/3/24: FCD:03/03/2024->12/24; ; Rel-18->Rel-19; 13/6/24: 30%->50; 4/9/24: 50%->55; 5/12/24: 55%->60; 5/12/24: FCD:12/12/2024->/25; 6/3/25: 60%->100","26.813",100,51,null,null,"Thu 08/06/23","Thu 06/03/25"]
[698,1040001,"Service Based Interface Protocol Improvements Release 19","SBIProtoc19",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.5,"CP-241021",null,"Wang Rong, China Mobile","wangrongyjy@chinamobile.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[699,1040050,"   CT3 aspects of Service Based Interface Protocol Improvements Release 19","SBIProtoc19",2,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.85,"CP-241021",null,"Wang Rong, China Mobile","wangrongyjy@chinamobile.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[700,1040051,"   CT4 aspects of Service Based Interface Protocol Improvements Release 19","SBIProtoc19",2,"Rel-19","C4","Mon 17/06/24","Tue 09/09/25",0.6,"CP-241021",null,"Wang Rong, China Mobile","wangrongyjy@chinamobile.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[701,1040003,"Subscriber Data Migration","SUBDMIG",1,"Rel-19","C4","Mon 17/06/24","Tue 09/09/25",0.95,"CP-241023",null,"Jesus de Gregorio, Ericsson","Jesus de Gregorio, jesus.de.gregorio@ericsson.com",null,"23.527,29.503,29.504,29.510,29.571",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[702,1050010,"Rel-19 Enhancements of Network Automation Enablers","eNetAE19",1,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.9,"CP-243078",null,"Xuefei Zhang (Huawei)","summer.xuefei@huawei.com",null,"29.508, 29.517, 29.520, 29.522, 29.552, 29.574, 29.575, 29.576, 29.591",101,51,null,null,"Wed 06/09/23","Thu 26/09/24"]
[703,1040005,"Study on Protocol for AI Data Collection from UPF","FS_PAIDC_UPF",1,"Rel-19","C4","Mon 17/06/24","Tue 09/09/25",0.9,"CP-241025",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[704,1080002,"Study on IMS resiliency","FS_IMSResil",1,"Rel-19","C4","Fri 06/06/25","Tue 09/09/25",0.1,"CP-251017",null,"Kenichi Yamamoto, KDDI","kc-yamamoto@kddi.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[705,1040039,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc19",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.43,"CP-241285",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[706,1040062,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc19",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-241285",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[707,1040063,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc19",2,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.85,"CP-241285",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[708,1040041,"Protocol enhancements for Mission Critical Services","MCProtoc19",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.46,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[709,1040064,"   CT1 aspects of Protocol enhancements for Mission Critical Services","MCProtoc19",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[710,1040065,"   CT3 aspects of Protocol enhancements for Mission Critical Services","MCProtoc19",2,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.85,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[711,1040066,"   CT4 aspects of Protocol enhancements for Mission Critical Services","MCProtoc19",2,"Rel-19","C4","Sun 03/11/24","Tue 09/09/25",0,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[712,1040042,"Enhancement of controlling RAT utilization","ECRATU",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.68,"CP-243268",null,"Yang Lu, Vodafone","yang.lu@vodafone.com",null,"24.301, 24.501, 23.122, 29.272, 29.503",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[713,1040067,"   CT1 aspects of Enhancement of controlling RAT utilization","ECRATU",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.99,"CP-243268",null,"Yang Lu, Vodafone","yang.lu@vodafone.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[714,1040068,"   CT4 aspects of Enhancement of controlling RAT utilization","ECRATU",2,"Rel-19","C4","Mon 17/06/24","Tue 09/09/25",0.98,"CP-243268",null,"Yang Lu, Vodafone","yang.lu@vodafone.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[715,1040045,"Enhanced Mission Critical Location Management","enhMCLoc",1,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.8,"CP-241288",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,"24.281,24.282,24.283,24.379,24.481,24.482,24.483,24.484,29.379",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[716,1050027,"Alignment of eCall over IMS with CEN","eCallCEN",1,"Rel-19","C1","Mon 09/09/24","Fri 06/06/25",1,"CP-242254",null,"Osama Lotfallah, Qualcomm Incorporated","osamal@qti.qualcomm.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[717,1060075,"UE Conformance - Alignment of eCall over IMS with CEN ","eCallCEN-UEConTest",1,"Rel-19","R5","Sat 14/09/24","Fri 12/12/25",0.9,"RP-242495","RP-251190","Qualcomm ",null,"6/3/25: Compl:0%->80%; Stat Rep: ->RP-250112; ; 6/6/25: FCD:Fri 06/06/25->Fri 12/12/25; Compl:80%->90%; Stat Rep: RP-250112->RP-251190; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[718,1060025,"Rel-19 Enhancements of UE Policy","UEP19",1,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.9,"CP-243073",null,"Susana Fernández, Ericsson","Susana.fernandez@ericsson.com",null,"29.525, 29.523, 29.519, 29.522, 29.513",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[719,1070005,"Rel-19 Enhancements of SM Policy","SMPC19",1,"Rel-19","C3","Mon 03/03/25","Tue 09/09/25",0.7,"CP-250075",null,"Chi Zhang, Huawei","margo.zhangchi@huawei.com",null,"29.512, 29.513",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[720,1070006,"CT Aspects for IP Domain usage","IPD",1,"Rel-19","C3","Mon 03/03/25","Tue 09/09/25",0.5,"CP-250248",null,"Zhenning Huang, China Mobile","huangzhenning@chinamobile.com",null,"29.213, 29.513",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[721,1060018,"NAS layer overhead reduction for data transfer using CP CIoT","NORDAT_CP",1,"Rel-19","C1","Mon 02/12/24","Tue 09/09/25",0.8,"CP-250251",null,"Amer Catovic","amerc@qti.qualcomm.com",null,"24.301, 24.007",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[722,1070009,"Support for PWS in Satellite E-UTRAN and Satellite NG-RAN","PWS_NTN",1,"Rel-19",null,"Mon 03/03/25","Tue 09/09/25",0.81,"CP-250132",null,"Amer Catovic","amerc@qti.qualcomm.com",null,"23.041,29.168,29.518",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[723,1070049,"   CT1 aspects of Support for PWS in Satellite E-UTRAN and Satellite NG-RAN","PWS_NTN",2,"Rel-19","C1","Mon 03/03/25","Tue 09/09/25",0.9,"CP-250132",null,"Amer Catovic","amerc@qti.qualcomm.com",null,"23.041,29.168,29.518",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[724,1070050,"   DELETED - CT4 aspects of Support for PWS in Satellite E-UTRAN and Satellite NG-RAN","PWS_NTN",2,"Rel-19","C4","Thu 06/03/25","Tue 09/09/25",1,"CP-250132",null,"Amer Catovic","amerc@qti.qualcomm.com",null,"23.041,29.168,29.518",101,51,108,null,"Wed 06/09/23","Wed 06/09/23"]
[725,1040044,"Stage-3 5GS NAS protocol development 18 ","5GProtoc19",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.28000000000000003,"CP-241280",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,null,96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[726,1040046,"   Stage-3 5GS NAS protocol development 18 general aspects","5GProtoc19",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-241280",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,null,96,49,null,null,"Fri 03/06/22","NA"]
[727,1040047,"   Stage-3 5GS NAS protocol development 18 non 3GPP aspects","5GProtoc19-non3GPP",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-241280",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,null,96,49,null,null,"Fri 03/06/22","NA"]
[728,1040040,"Stage-3 SAE Protocol Development ","SAES19",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.28000000000000003,"CP-241284",null,"Sethi, Anuj, InterDigital ",null,null,null,96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[729,1040048,"   Stage-3 SAE Protocol Development general","SAES19",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-241284",null,"Sethi, Anuj, InterDigital ",null,null,null,96,49,null,null,"Fri 03/06/22","NA"]
[730,1040049,"   Stage-3 SAE Protocol Development non 3GPP","SAES19-non3GPP",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-241284",null,"Sethi, Anuj, InterDigital ",null,null,null,96,49,null,null,"Fri 03/06/22","NA"]
[731,970002,"Lawful Interception Rel-19 ","LI19",1,"Rel-19","S3LI","Fri 24/03/23","Sat 30/03/24",0.15,"SP-250372",null,"Koen Jaspers, PIDS","kbj@xs4all.nl","; 16/3/23: WID:SP-220752->SP-230242; 16/3/23: FCD:03/03/2024->9/9/2024. Rapporteur changed from Alex Leadbeater; 5/9/24: 0%->10; 5/12/24: 10%->15; 26/3/25: WID:SP-230242->SP-250372","33.107; 33.108; 33.126; 33.127; 33.128 ",97,49,null,null,"Sun 11/09/22","Wed 26/03/25"]
[732,1040010,"Lawful Interception Guidance Rel-19 ","LI19_Guide",1,"Rel-19","S3LI","Tue 16/07/24","Sun 22/12/24",0.52,"SP-240562",null,"Nag Rao, Nokia, ","nagaraja.rao@nokia.com ","5/12/24: 0%->52",null,104,53,null,null,"Tue 16/07/24","Thu 05/12/24"]
[733,1080003,"Harmonization of test case definitions for cross-RAT usability","TestHarmon_CrossRAT",1,"Rel-19","C6","Fri 06/06/25","Tue 03/03/26",0,"CP-251036",null,"Arne Marquordt, COMPRION GmbH","amarquordt@comprion.com",null,"TS 31.117, TS 31.121, TS 31.124, TS 31.127",106,54,null,null,"Fri 24/01/25","Thu 06/03/25"]
[734,980130,"(Small) Technical Enhancements and Improvements for Rel-19","TEI19",1,"Rel-19",null,"Fri 09/09/22","Sat 12/11/22",0,null,null,null,null,null,null,92,47,null,null,"Mon 15/06/15","Mon 15/06/15"]
[735,1080051,"Lawful Interception Rel-19 ","FS_LIHOPES",1,"Rel-19","S3LI","Thu 05/06/25","Tue 03/03/26",0,"SP-250445",null,"Mats Näslund, NDRE ","mats.naslund@fra.se ",null,null,null,null,null,null,"Thu 05/06/25","NA"]
[736,0,"--- RELEASE 18 ---","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[737,0,"Rel-18 Satellite (5GSAT), NTN","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[738,970056,"5G system with satellite backhaul ","5GSATB",1,"Rel-18",null,"Fri 11/06/21","Tue 12/12/23",1,"SP-230111",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;","22.261 ",92,47,null,null,"Fri 11/06/21","Fri 10/12/21"]
[739,920035,"   Stage 1 of 5GSATB","5GSATB",2,"Rel-18","S1","Fri 11/06/21","Fri 18/06/21",1,"SP-210528",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;","22.261 ",92,47,null,null,"Fri 11/06/21","Fri 10/12/21"]
[740,940060,"   Study on Support of Satellite Backhauling in 5GS ","FS_5GSATB",2,"Rel-18","S2","Mon 20/12/21","Fri 03/03/23",1,"SP-211639",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","21/1/22: 23.700-27 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->80; 10/12/22: 80%->100","23.700-27",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[741,970018,"   Stage 2 of 5GSATB","5GSATB",2,"Rel-18","S2","Mon 12/09/22","Tue 06/06/23",1,"SP-230111",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","; 10/12/22: 0%->30; 15/3/23: FCD:03/03/2023->06/23; 15/3/23: 30%->65; 15/3/23: WID:SP-220808->SP-230111; 8/6/23: 65%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[742,980053,"   CT3 aspects of 5GSATB","5GSATB",2,"Rel-18","C3","Fri 16/12/22","Tue 12/12/23",1,"CP-232131",null,"Hou, Yunjing, CATT","houyunjing@catt.cn","6/6/23: Compl:30%->60%","29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[743,980054,"   CT4 aspects of 5GSATB","5GSATB",2,"Rel-18","C4","Fri 16/12/22","Tue 12/12/23",1,"CP-232131",null,"Hou, Yunjing, CATT","houyunjing@catt.cn",null,"29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564",97,49,null,null,"Sun 11/09/22","NA"]
[744,1020024,"Charging aspects of Satellite Backhaul in 5GS ","5GSATB_CH",1,"Rel-18","S5","Thu 07/12/23","Sun 03/03/24",1,"SP-240266",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","SP-231707 shows UID 1020023 but this duplicates with SP-231706, so changed here to 1020024.; 15/3/24: 0%->100; 2/4/24: WID:SP-231707->SP-240266","32.240; 32.255; 32.256; 32.254; 32.257; 32.291; 32.298 ",102,52,null,null,"Thu 07/12/23","Tue 02/04/24"]
[745,1020029,"Management aspects of 5G system supporting satellite backhaul ","5GSATB_OAM",1,"Rel-18","S5","Thu 07/12/23","Sun 03/03/24",1,"SP-231708",null,"Wen Qi, China Telecom ","qiw@chinatelecom.cn ","; 14/3/24: 0%->100","28.541; 28.552 ",102,52,null,null,"Wed 03/01/24","Thu 14/03/24"]
[746,920034,"5G system with satellite access to Support Control and/or Video Surveillance ","SCVS",1,"Rel-18","S1","Fri 11/06/21","Wed 08/09/21",1,"SP-210527",null,"Dong Chen, Xiaomi ","chendong7@xiaomi.com ","; 10/12/21: 0%->100","22.261 ",92,47,null,null,"Fri 11/06/21","Fri 10/12/21"]
[747,940074,"Study on 5GC enhancement for satellite access Phase 2 ","FS_5GSAT_Ph2",1,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211651",null,"Fine, Jean-Yves, Thales ","jean-yves.fine@thalesgroup.com. ","21/1/22: 23.700-28 added;; 12/3/22: 0%->12; 4/6/22: 12%->50; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-28",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[748,989998,"Satellite access Phase 2 ","5GSAT_Ph2",1,"Rel-18",null,"Fri 09/12/22","Sun 03/03/24",1,"SP-230109",null,"Rapporteur: Jean-Yves Fine, Thales ","jean-yves.fine@thalesgroup.com ",null,"23.501; 23.502; 23.503; 23.401 ",98,50,null,null,"Fri 09/12/22","NA"]
[749,980014,"   (Stage 2 of 5GSAT_Ph2) 5GC/EPC enhancement for satellite access Phase 2 ","5GSAT_Ph2",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230109",null,"Rapporteur: Jean-Yves Fine, Thales ","jean-yves.fine@thalesgroup.com ","; 15/3/23: 0%->70; 15/3/23: WID:SP-221344->SP-230109; 8/6/23: 70%->100","23.501; 23.502; 23.503; 23.401 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[750,990024,"   CT1 aspects of 5GSAT_Ph2","5GSAT_Ph2",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-240269",null,"Amer Catovic, Qualcomm Incorporated","amerc@qti.qualcomm.com","6/6/23: Compl:0%->10%","24.501.24.301.23.122.27.007.29.122.29.522.31.102",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[751,990056,"   deleted - CT6 aspects of 5GSAT_Ph2","5GSAT_Ph2",2,"Rel-18","C6","Mon 13/03/23","Sun 03/03/24",1,"CP-240269",null,"Amer Catovic, Qualcomm Incorporated","amerc@qti.qualcomm.com","; 15/3/24: 0%->100","24.501.24.301.23.122.27.007.29.122.29.522.31.102",99,50,null,null,"Fri 09/12/22","Fri 15/03/24"]
[752,1010018,"   Charging aspects of 5GSAT","5GSAT_Ph2_CH",2,"Rel-18","S5","Thu 07/09/23","Sun 03/03/24",1,"SP-231152",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","; 8/12/23: 0%->35; 14/3/24: 35%->100","32.255; 32.256; 32.291; 32.298 ",101,51,null,null,"Thu 07/09/23","Thu 14/03/24"]
[753,941006,"NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh",1,"Rel-18",null,"Mon 13/12/21","Fri 12/12/25",0.77,"RP-240779",null,"Thales",null,"compare REL-17 WI NR_NTN_solutions; 5/4/22: WID:RP-213690->RP-220953; 12/7/22: WID:RP-220953->RP-221819; 23/9/22: WID:RP-221819->RP-222654; 9/1/23: WID:RP-222654->RP-223534; 29/3/23: WID:RP-223534->RP-230809; 6/10/23: WID:RP-230809->RP-232669; 2/1/24: ...",null,94,48,null,null,"Thu 06/01/22","Tue 02/04/24"]
[754,941106,"   Core part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Core",2,"Rel-18","R2","Mon 13/12/21","Thu 06/06/24",1,"RP-232669","RP-240921","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","compare REL-17 WI NR_NTN_solutions; 22/3/22: Stat Rep: ->RP-220383; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->5%; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace....",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[755,941206,"   Perf. part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Perf",2,"Rel-18","R2","Wed 15/12/21","Thu 06/06/24",1,"RP-232669","RP-240921","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","; ; 20/6/22: WG: R4->R2; FCD:12/06/2024->24/06/2022; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com13/7/22: FCD:24/06/2022->06/20 ...; 9/12/22: FCD:24/06/2023->0...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[756,1050130,"   UE Conformance - NR NTN (non-Terrestrial Networks) enhancements plus CT aspects ","NR_NTN_enh_plus_CT-UEConTest",2,"Rel-18","R5","Mon 09/09/24","Fri 12/12/25",0.15,"RP-242024","RP-251231","Qualcomm ",null,"6/12/24: Compl:0%->6%; Stat Rep: ->RP-242899; ; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:6%->10%; Stat Rep: RP-242899->RP-250397; ; 6/6/25: Compl:10%->15%; Stat Rep: RP-250397->RP-251231; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[757,941004,"IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.92,"RP-241351",null,"MediaTek",null,"no Perf. part; 5/4/22: WID:RP-213596->RP-220979; 12/7/22: WID:RP-220979->RP-221806; 9/1/23: WID:RP-221806->RP-223519; 2/1/24: WID:RP-223519->RP-234073; 23/7/24: WID:RP-234073->RP-241351",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[758,940104,"   Core part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-241351","RP-233260","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","no Perf. Part. Slight misalignment in UID numberring scheme (940104 instead of 941104) but it was decided to leave it as such to avoid further potential problems by changing a UID; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->3%; Stat Rep: ->RP-22155...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[759,950284,"   Perf. Part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Perf",2,"Rel-18","R4","Mon 07/03/22","Thu 06/06/24",1,"RP-241351","RP-241350","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","20/6/22: WG: R4->R2; FCD:07/06/2024->24/06/2022; Stat Rep: ->RP-221553 / 1759; Rapporteur: MediaTek->Abhishek Roy, MediaTek; Rap eMail: ->abhishek.roy@mediatek.com ...; 17/3/23: FCD:23/12/2022->06/06/2024; Stat Rep: ->RP-230633; Rapporteur: MediaTek...",null,95,48,null,null,"Sat 04/06/22","Thu 13/06/24"]
[760,1030073,"   UE Conformance - IoT (Internet of Things) NTN (non-terrestrial network) enhancements plus CT1 aspects ","IoT_NTN_enh_plus_CT1-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.8,"RP-241949","RP-251376","CMCC ",null,"13/6/24: Compl:0%->16%; WID: RP-240784->RP-240144; Stat Rep: ->RP-241198; ; 23/7/24: WID:RP-240144->RP-241197; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:16%->27%; Stat Rep: RP-241198->RP-241950; ; 26/9/24: WID:RP-241197->RP-241949; 6/12/24: FCD:12/12/2024",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[761,981043,"Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband",1,"Rel-18",null,"Tue 13/12/22","Tue 12/12/23",1,"RP-234043",null,"Apple ",null,"29/3/23: WID:RP-223485->RP-230706; 8/6/23: 38.741 added;; 2/1/24: WID:RP-230706->RP-234043","38.741",98,50,null,null,"Mon 09/01/23","Tue 02/01/24"]
[762,981143,"   Core part: Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband-Core",2,"Rel-18","R4","Tue 13/12/22","Tue 12/12/23",1,"RP-234043","RP-233306","Alexander Sayenko, Apple Inc.","asayenko@apple.com","17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->10%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:50%->...",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[763,981243,"   Perf. part: Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband-Perf",2,"Rel-18","R4","Tue 13/12/22","Tue 12/12/23",1,"RP-234043","RP-233306","Alexander Sayenko, Apple Inc.","asayenko@apple.com","17/3/23: Compl:0%->50%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:90%->95%; WID: RP-230706->RP-231179; Stat Rep: RP-230707->RP-...",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[764,970028,"Study on Security Aspects of Satellite Access ","FS_5GSAT_Sec",1,"Rel-18","S3","Mon 12/09/22","Fri 03/03/23",1,"SP-220875",null,"Wei Lu, Xiaomi ","luwei10@xiaomi.com ","23/9/22: 33.700-28 added;; 11/12/22: 0%->15; 17/3/23: 15%->25; 8/6/23: 25%->100; 7/9/23: 100%->","33.700-28",97,49,null,null,"Sun 11/09/22","Thu 07/09/23"]
[765,960026,"Study on Management Aspects of IoT NTN Enhancements ","FS_IoT_NTN",1,"Rel-18","S5","Thu 02/06/22","Tue 06/06/23",1,"SP-220490",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","12/9/22: 0%->30; 11/12/22: 30%->75; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 75%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100",null,96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[766,960091,"Study on requirements and use cases for network verified UE location for Non-Terrestrial-Networks (NTN) in NR ","FS_NR_NTN_netw_verif_UE_loc",1,"Rel-18","RP","Wed 01/06/22","Wed 15/06/22",1,"RP-221820",null,"Thales ",null,null,null,96,49,null,null,"Tue 12/07/22","NA"]
[767,980028,"Study on charging aspects of Satellite in 5GS ","FS_5GSAT_CH",1,"Rel-18","S5","Wed 01/06/22","Tue 12/12/23",1,"SP-221162",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","17/3/23: 0%->5; 17/3/23: 22.844 added;; 8/6/23: 5%->30; 7/9/23: 0%->80; 8/12/23: 80%->100; 8/12/23: 99%->100","22.844",98,50,null,null,"Fri 09/12/22","Fri 08/12/23"]
[768,1000060,"30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) ","NR_NTN_CBW_30MHz",1,"Rel-18","R4","Wed 07/06/23","Fri 08/09/23",1,"RP-232647",null,"Thales ",null,"6/10/23: WID:RP-231499->RP-232647",null,100,51,null,null,"Thu 29/06/23","Fri 06/10/23"]
[769,1001060,"   Core part: 30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) ","NR_NTN_CBW_30MHz-Core",2,"Rel-18","R4","Wed 07/06/23","Fri 08/09/23",1,"RP-232647","RP-232646","Dorin Panaitopol, THALES","dorin.panaitopol@thalesgroup.com","6/9/23: Compl:0%->50%; Stat Rep: ->RP-231568; Rapporteur: Thales->Dorin Panaitopol, THALES; Rap eMail: ->dorin.panaitopol@thalesgroup.com; ; 21/9/23: FCD:12/12/2023->08/09/2023; Compl:50%->100%; Stat Rep: RP-231568->RP-232646; ",null,100,51,null,null,"Thu 29/06/23","Thu 21/09/23"]
[770,991041,"Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband",1,"Rel-18","R4","Fri 03/03/23","Fri 06/06/25",1,"RP-240741",null,"Inmarsat ",null,"7/9/23: WID:RP-230790->RP-231487; 6/10/23: WID:RP-231487->RP-232686; 2/1/24: WID:RP-232686->RP-233856; 2/4/24: WID:RP-233856->RP-240741",null,99,50,null,null,"Wed 29/03/23","Tue 02/04/24"]
[771,991141,"   Core part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-Core",2,"Rel-18","R4","Fri 03/03/23","Sun 03/03/24",1,"RP-240741","RP-232609","Luca Lodigiani, Inmarsat","Luca.lodigiani@inmarsat.com","; 7/6/23: Compl:0%->11%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:11%->30%; WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:22/09/2023->12/12/2...",null,99,50,null,null,"Wed 29/03/23","Tue 02/04/24"]
[772,991241,"   Perf. part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-Perf",2,"Rel-18","R4","Fri 03/03/23","Thu 06/06/24",1,"RP-240741","RP-232609","Luca Lodigiani, Inmarsat","Luca.lodigiani@inmarsat.com","6/9/23: WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:12/12/2023->06/06/2024; Stat Rep: RP-232459->RP-232609; ; 8/12/23: FCD:06/06/2024->12/12...",null,99,50,null,null,"Wed 29/03/23","Tue 23/07/24"]
[773,1040110,"   UE Conformance - Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 06/06/25",1,"RP-241355","RP-251292","Mediatek ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->5%; Stat Rep: ->RP-242049; ; 6/12/24: Compl:5%->95%; Stat Rep: RP-242049->RP-242993; ; 6/3/25: FCD:14/02/2025->06/06/2025; Stat Rep: RP-242993->RP-250476; ; 6/6/25: Compl:95%->100%; Stat Rep: RP-250476->RP-25",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[774,991043,"Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band",1,"Rel-18","R4","Fri 03/03/23","Mon 03/03/25",1,"RP-241353",null,"MediaTek ",null,"2/1/24: WID:RP-230792->RP-234060; 2/4/24: WID:RP-234060->RP-240451; 23/7/24: WID:RP-240451->RP-241353",null,99,50,null,null,"Wed 29/03/23","Tue 23/07/24"]
[775,991143,"   Core part: Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-Core",2,"Rel-18","R4","Fri 03/03/23","Tue 12/12/23",1,"RP-241353","RP-241352","Huanren FU, MediaTek Inc.","huanren.fu@mediatek.com","; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->60%; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-232313->RP-233258; ; 4/1/2...","36.764",99,50,null,null,"Wed 29/03/23","Thu 13/06/24"]
[776,991243,"   Perf. part: Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-Perf",2,"Rel-18","R4","Mon 06/03/23","Thu 06/06/24",1,"RP-241353","RP-241352","Huanren FU, MediaTek Inc.","huanren.fu@mediatek.com","; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ; 8/12/23: Stat Rep: RP-232313->RP-233258; ...",null,99,50,null,null,"Wed 29/03/23","Thu 13/06/24"]
[777,1040109,"   UE Conformance - Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Thu 12/12/24",1,"RP-242992","RP-242991","Mediatek ",null,"4/9/24: FCD:03/03/2025->25/03/2025; Compl:0%->95%; Stat Rep: ->RP-242048; ; 6/12/24: FCD:03/03/2025->12/12/2024; Compl:95%->99%; Stat Rep: RP-242048->RP-242991; ; 24/1/25: WID:RP-241354->RP-242992; 24/1/25: 99%->100",null,104,53,null,null,"Tue 23/07/24","Fri 24/01/25"]
[778,950074,"NB-IoT/eMTC Core and Perf requirements for NTN","LTE_NBIOT_eMTC_NTN_req",1,"Rel-18",null,"Tue 15/03/22","Sun 03/03/24",1,"RP-223437",null,"MediaTek ",null,"TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 12/7/22: WID:RP-220938->RP-221556; 9/1/23: WID:RP-221556->RP-223437; 23/7/24: 99%->100",null,95,48,null,null,"Tue 05/04/22","Tue 23/07/24"]
[779,950174,"   Core part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIoT_eMTC_NTN_req-Core",2,"Rel-18","R4","Tue 15/03/22","Thu 01/12/22",1,"RP-221556","RP-223231","Tim Frost, MediaTek Inc.","Tim.frost@mediatek.com","TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 20/6/22: FCD:15/12/2022->22/12/2022; Stat Rep: ->RP-221555; Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: 36.1...;...","36.102; 36.105; 36.108",95,48,null,null,"Tue 05/04/22","Mon 09/01/23"]
[780,950274,"   Perf. part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIoT_eMTC_NTN_req-Perf",2,"Rel-18","R4","Tue 15/03/22","Tue 06/06/23",1,"RP-223437","RP-230634","Hsuanli Lin, MediaTek Inc.","hsuanli.lin@mediatek.com","TS 36.1XX; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 6/6/22: CD:15/06/2023->23/06/2022; 6/6/22: Stat Rep: ->RP-221555; 20/6/22: Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: ...;...","36.181",95,48,null,null,"Tue 05/04/22","Wed 07/06/23"]
[781,981034,"   UE Conformance - NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIOT_eMTC_NTN_req-UEConTest",2,"Rel-18","R5","Tue 13/12/22","Sun 03/03/24",1,"RP-240147","RP-240146","Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.","songdan@chinamobile.com, Danbo.Fu@mediatek.com","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230284; Rapporteur: CMCC->Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.; Rap eMail: ->songdan@chinamobile.com, Danbo.Fu@mediatek.com; 17/3/23: 36.521-4 added;; 29/3/23: WID:RP-223064->RP-230285; ...; 21/9/23...","36.521-4",98,50,null,null,"Mon 09/01/23","Tue 02/04/24"]
[782,0,"Rel-18 Internet of Things (IoT), MTC, Energy, complexity saving","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[783,930029,"Personal IoT and Residential networks","PIRates",1,"Rel-18",null,"Thu 25/06/20","Sun 03/03/24",1,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 10/12/21: WID:SP-211055->SP-211505 (chg rapporteur)","22.261 ",93,47,null,null,"Fri 10/09/21","Fri 10/12/21"]
[784,880041,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S1","Thu 25/06/20","Fri 11/06/21",1,"SP-200592",null,"Adrian Buckley, vivo Mobile Communications ","adrian.buckley@vivo.com","28/7/20: 22.859 added;; 12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->90; 13/9/21: 90%->100","22.859",88,45,null,null,"Thu 25/06/20","Mon 13/09/21"]
[785,880040,"   Study on Enhancements for Residential 5G","FS_Resident",2,"Rel-18","S1","Thu 25/06/20","Fri 11/06/21",1,"SP-200576",null,"Toon Norp, KPN","toon.norp@tno.nl","28/7/20: 22.858 added;; 12/9/20: 0%->30; 5/12/20: 30%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->85; 13/9/21: 85%->100","22.858",88,45,null,null,"Thu 25/06/20","Mon 13/09/21"]
[786,930022,"   Stage 1 of PIRates","PIRates",2,"Rel-18","S1","Fri 10/09/21","Fri 10/12/21",1,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 13/9/21: 0%->85; 10/12/21: 85%->100; 10/12/21: WID:SP-211055->SP-211505","22.261 ",93,47,null,null,"Fri 10/09/21","Fri 10/12/21"]
[787,940065,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S2","Mon 20/12/21","Fri 03/03/23",1,"SP-230089",null,"Zhenhua Xie, vivo Mobile Communications Ltd ","zhenhua.xie@vivo.com ","21/1/22: 23.700-88 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 12/9/22: 60%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->95; 15/3/23: FCD:12/12/2022->03/23; 15/3/23: 95%->100; 15/3/23: WID:SP-211643->SP-230089","23.700-88",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[788,980011,"   (Stage 2 of) Personal IoT Networks ","PIN",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-221343",null,"Zhenhua Xie, vivo ","zhenhua.xie@vivo.com ","10/1/23: FCD clarified to be June (and not March) by e-mail; 15/3/23: 0%->60; 8/6/23: 60%->100","23.501; 23.502; 23.503 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[789,990018,"   CT1 aspects of PIN","PIN",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com","6/6/23: Compl:0%->50%","24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[790,990058,"   CT3 aspects of PIN","PIN",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com","9/6/23: 0%->20","24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"Fri 09/12/22","Fri 09/06/23"]
[791,990059,"   CT4 aspects of PIN","PIN",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com",null,"24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"Fri 09/12/22","NA"]
[792,990106,"Application layer support for Personal IoT Network ","PINAPP",1,"Rel-18",null,"Mon 13/12/21","Sun 03/03/24",1,"SP-221236",null,"Huazhang Lv, vivo Mobile Communications Ltd, ","huazhang.lv@vivo.com ",null,null,99,50,null,null,"Fri 09/12/22","NA"]
[793,940021,"   Study on Application layer support for Personal IoT Networks","FS_PINAPP",2,"Rel-18","S6","Mon 13/12/21","Mon 12/12/22",1,"SP-220095",null,"Huazhang Lv, vivo Mobile Communications Ltd ","huazhang.lv@vivo.com ","7/1/22: 23.700-78 added;; 12/3/22: WID:SP-211515->SP-220095; 12/3/22: 0%->15; 4/6/22: 15%->40; 12/9/22: 40%->60; 12/9/22: FCD:12/09/2022->12/20; 11/12/22: 60%->100; 31/3/23: 24.583 added;","23.700-78; 24.583",94,48,null,null,"Mon 13/12/21","Fri 31/03/23"]
[794,980052,"   Stage 2 of PINAPP","PINAPP",2,"Rel-18","S6","Fri 09/12/22","Tue 06/06/23",1,"SP-221236",null,"Huazhang Lv, vivo Mobile Communications Ltd, ","huazhang.lv@vivo.com ","17/3/23: FCD:03/03/2023->/23; 17/3/23: 0%->50; 17/3/23: 23.542 added;; 8/6/23: 50%->100","23.542",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[795,990017,"   CT1 aspects of PINAPP","PINAPP",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-233218",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","6/6/23: Compl:0%->40%","27.007",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[796,990061,"   CT3 aspects of PINAPP","PINAPP",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-233218",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","31/3/23: 29.583 added;; 9/6/23: 5%->10","27.007; 29.583",99,50,null,null,"Fri 09/12/22","Fri 09/06/23"]
[797,960027,"Study on Personal IoT Networks Security Aspects ","FS_PIN_Sec",1,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220525",null,"Zhenhua Xie, vivo Mobile Communications Co. Ltd ","zhuenhua.xie@vivo.com ","13/7/22: 33.882 added;; 12/9/22: 0%->20; 11/12/22: 20%->50; 17/3/23: 50%->60; 8/6/23: 60%->100","33.882",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[798,920016,"Study on Application Capability Exposure for IoT Platforms ","FS_ACE_IOT",1,"Rel-18","S6","Fri 11/06/21","Thu 09/06/22",1,"SP-220093",null,"Mladin, Catalina; Convida Wireless ","Mladin.Catalina@convidawireless.com ","2/7/21: 23.700-97 added;; 13/9/21: 0%->15; 13/12/21: 15%->40; 12/3/22: 40%->55; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210478->SP-220093; 4/6/22: 55%->60; 12/9/22: 60%->75; 11/12/22: 75%->75; 17/3/23: 75%->95; 8/6/23: 95%->100","23.700-97",92,47,null,null,"Fri 11/06/21","Thu 08/06/23"]
[799,0,"See also IoT_NTN_en under Satellite and LPHP under Verticals","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[800,0,"See also \" NB-IoT/eMTC requirements for NTN\" (UID 950074) under Satellite ","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[801,940085,"Study on low-power wake-up signal and receiver for NR","FS_NR_LPWUS",1,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-232672","RP-233067","Xueming Pan, vivo","panxueming@vivo.com","21/1/22: 38.869 added;; 22/3/22: Stat Rep: ->RP-2205966/6/22: CD:12/12/2023->23/12/20226/6/22: Stat Rep: RP-220596->RP-221270; 20/6/22: Rapporteur: vivo->Xiaodong Shen, vivo Communication Technology; Rap eMail: ->shenxiaodong@vivo.com12/7/22: WID:R...;...","38.869",94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[802,970080,"Enhanced support of reduced capability NR devices ","NR_redcap_enh",1,"Rel-18",null,"Sun 12/12/21","Thu 12/12/24",0.88,"RP-233637",null,"Ericsson ",null,"9/1/23: WID:RP-222675->RP-223544; 6/10/23: WID:RP-223544->RP-232671; 2/1/24: WID:RP-232671->RP-233637",null,97,49,null,null,"Fri 23/09/22","Tue 02/01/24"]
[803,970180,"   Core part: Enhanced support of reduced capability NR devices ","NR_redcap_enh-Core",2,"Rel-18","R1","Thu 08/09/22","Tue 12/12/23",1,"RP-233637","RP-233636","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222827->RP-230111; ;.....",null,97,49,null,null,"Fri 23/09/22","Fri 08/12/23"]
[804,970280,"   Perf. part: Enhanced support of reduced capability NR devices ","NR_redcap_enh-Perf",2,"Rel-18","R1","Tue 13/09/22","Thu 06/06/24",1,"RP-233637","RP-241124","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","9/12/22: WG: R4->R1; FCD:10/06/2023->01/06/2024; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: Stat Rep: RP-222827->RP-230111; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep:...",null,97,49,null,null,"Fri 23/09/22","Tue 23/07/24"]
[805,940086,"   Study on further NR RedCap (reduced capability) UE complexity reduction","FS_NR_redcap_enh",2,"Rel-18","R1","Sun 12/12/21","Fri 09/09/22",1,"RP-221161","RP-221160","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","TR 38.8xx; compare REL-17 SI FS_NR_redcap and REL-17 WI NR_redcap; 21/1/22: 38.865 added;; 22/3/22: Stat Rep: ->RP-220470 ; 6/6 ; 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com12/7/22: WID:RP-213661-...; 23","38.865",94,48,null,null,"Thu 06/01/22","Fri 23/09/22"]
[806,1030062,"   UE Conformance - Enhanced support of reduced capability NR devices plus CT1 aspects ","NR_redcap_enh_plus_CT1-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.7,"RP-242487","RP-251504","China Unicom ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-240919; ; 23/7/24: WID:RP-240054->RP-240920; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->28%; Stat Rep: RP-240919->RP-241883; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:28%->53%; Stat Rep: RP-241883->RP-242486; ; ",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[807,940056,"Study on RedCap Phase 2","FS_REDCAP_Ph2",1,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220074",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","21/01/22: name corrected; 21/1/22: 23.700-68 added;; 12/3/22: 0%->30; 12/3/22: WID:SP-211635->SP-220074; 4/6/22: 30%->70; 12/9/22: 70%->99; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 99%->100","23.700-68",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[808,980113,"NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",1,"Rel-18",null,"Thu 15/12/22","Wed 13/12/23",1,"SP-220803",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ",null,"23.501; 23.502 ",97,49,null,null,"Sun 11/09/22","NA"]
[809,970013,"   (Stage 2 of) NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",2,"Rel-18","S2","Mon 12/09/22","Fri 03/03/23",1,"SP-230171",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","; 10/12/22: 0%->60; 15/3/23: WID:SP-220803->SP-230171; 15/3/23: 60%->95; 8/6/23: 95%->100; 4/1/24: 28.876 added;","23.501; 23.502 ; 28.876",97,49,null,null,"Sat 10/12/22","Thu 04/01/24"]
[810,980068,"   CT4 aspects of NR_REDCAP_Ph2","NR_REDCAP_Ph2",2,"Rel-18","C4","Thu 15/12/22","Tue 12/12/23",1,"CP-223021",null,"Frank Yong Yang, Ericsson","frank.yong.yang@ericsson.com","6/6/23: Compl:60%->90%","24.008; 29.502; 29.518",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[811,980069,"   CT1 aspects of NR_REDCAP_Ph2","NR_REDCAP_Ph2",2,"Rel-18","C1","Fri 16/12/22","Tue 12/12/23",1,"CP-223021",null,"Frank Yong Yang, Ericsson","frank.yong.yang@ericsson.com",null,"24.008; 29.502; 29.518",97,49,null,null,"Sun 11/09/22","NA"]
[812,991039,"Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18","NR_FDD_bands_R18_redcap",1,"Rel-18",null,"Mon 06/03/23","Mon 03/03/25",1,"RP-232894",null,"Ericsson",null,"2/1/24: WID:RP-230743->RP-232894",null,99,50,null,null,"Fri 07/04/23","Tue 02/01/24"]
[813,991139,"   Core part: Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18","NR_FDD_bands_R18_redcap-Core",2,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-232894","RP-232xyz","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->50%; WID: RP-230743->RP-231049; Stat Rep: ->RP-231881; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 8/12/23: Compl:50%->100%; Stat Rep: RP-231881->RP-232xyz; ",null,99,50,null,null,"Fri 07/04/23","Fri 08/12/23"]
[814,1060076,"   UE Conformance - New NR FDD bands for RedCap (Reduced Capability) in Rel-18 ","NR_FDD_bands_R18_redcap-UEConTest",2,"Rel-18","R5","Wed 28/08/24","Mon 03/03/25",1,"RP-250289","RP-250288","Ericsson ",null,"6/3/25: FCD:09/09/2025->03/03/2025; Compl:0%->100%; Stat Rep: ->RP-250288; ; 3/4/25: WID:RP-242648->RP-250289",null,106,54,null,null,"Fri 24/01/25","Thu 03/04/25"]
[815,981037,"Network energy savings for NR ","Netw_Energy_NR",1,"Rel-18",null,"Mon 13/12/21","Fri 12/12/25",0.96,"RP-234009",null,"Huawei ",null,"2/1/24: WID:RP-223540->RP-234009",null,98,50,null,null,"Mon 09/01/23","Tue 02/01/24"]
[816,981137,"   Core part: Network energy savings for NR ","Netw_Energy_NR-Core",2,"Rel-18","R1","Tue 13/12/22","Tue 12/12/23",1,"RP-234009","RP-233655","Yi Wang, Huawei","wangyi6@huawei.com","17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->15%; Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230565->RP-230714; ;...; 6/9/23: Compl:55%->75%; Stat Re...",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[817,981237,"   Perf. part: Network energy savings for NR ","Netw_Energy_NR-Perf",2,"Rel-18","R4","Wed 14/12/22","Thu 06/06/24",1,"RP-234009","RP-241239","Yi Wang, Huawei","wangyi6@huawei.com","17/3/23: Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:06/06/2024->06/06/2023; Stat Rep: RP-230565->RP-230714; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-230714->RP-231926; ; 8/12/...",null,98,50,null,null,"Mon 09/01/23","Tue 23/07/24"]
[818,1030067,"   UE Conformance - Network energy savings for NR ","Netw_Energy_NR-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.9,"RP-240291","RP-251490","Huawei ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241378; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->24%; Stat Rep: RP-241378->RP-242075; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:24%->54%; Stat Rep: RP-242075->RP-243092; ; 6/3/25: FCD:28/05/2025->12/12/2025;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[819,940080,"   Study on network energy savings for NR","FS_Netw_Energy_NR",2,"Rel-18","R1","Mon 13/12/21","Thu 01/12/22",1,"RP-230566","RP-223002","Yi Wang, Huawei","wangyi6@huawei.com","21/1/22: 38.864 added;; 22/3/22: Stat Rep: ->RP-220296; 5/4/22: WID:RP-213554->RP-220297 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com12/7/22: WID:RP-220297->RP-221443; 9/12/22: FCD:22/12/2022->...","38.864",94,48,null,null,"Thu 06/01/22","Wed 29/03/23"]
[820,0,"Rel-18 Uncrewed Aerial Vehicles (UAV), UAS, UAM","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[821,990107,"Further Architecture Enhancement for UAV and UAM","UAS_Ph2",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-221323",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","10/1/23: FCD clarified to be June (and not March) by e-mail ","23.256 ",99,50,null,null,"Fri 09/12/22","NA"]
[822,940051,"   Study on Phase 2 of UAS, UAV and UAM ","FS_UAS_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211632",null,"Stefano Faccin ","sfaccin@qti.qualcomm.com ","; 21/1/22: 23.700-58 added;; 12/3/22: 0%->20; 4/6/22: 20%->50; 4/6/22: FCD:10/06/2022->09/22; 12/9/22: 50%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->98; 15/3/23: 98%->100","23.256 ; 23.700-58",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[823,980012,"   (Stage 2 of UAS Ph2) Further Architecture Enhancement for UAV and UAM","UAS_Ph2",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230091",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","10/1/23: FCD clarified to be June (and not March) by e-mail ; 15/3/23: 0%->85; 15/3/23: WID:SP-221323->SP-230091; 8/6/23: 85%->100","23.256 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[824,960034,"   Study on Security of Phase 2 for UAS, UAV and UAM ","FS_UAS_Ph2_SEC",2,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220532",null,"Escott, Adrian, Qualcomm Incorporated, ","aescott@qti.qualcomm.com ","13/7/22: 33.891 added;; 11/12/22: 0%->65; 17/3/23: 65%->100","33.891",96,49,null,null,"Thu 02/06/22","Fri 17/03/23"]
[825,990036,"   Security of UAV and UAM Phase 2 ","UAS_Ph2",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230149",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 8/6/23: 0%->60; 7/9/23: 60%->100","33.256 ",99,50,null,null,"Thu 16/03/23","Thu 07/09/23"]
[826,990012,"   CT1 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","31/3/23: 24.578 added;; 31/3/23: 24.577 added;6/6/23: Compl:0%->50%","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102; 24.578; 24.577",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[827,990063,"   CT3 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","9/6/23: 0%->30","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"Fri 09/12/22","Fri 09/06/23"]
[828,990064,"   CT4 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","6/6/23: Compl:0%->10%","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[829,990105,"   CT6 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C6","Mon 13/03/23","Sun 03/03/24",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com",null,"24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"Fri 09/12/22","NA"]
[830,930012,"Study on enhanced architecture for UAS Applications ","FS_eUASAPP",1,"Rel-18","S6","Mon 13/09/21","Mon 12/12/22",1,"SP-220465",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","13/12/21: 0%->10; 13/12/21: WID:SP-210954->SP-211511; 13/12/21: FCD:Fri 10/06/->09/22; 12/3/22: 10%->30; 12/3/22: WID:SP-211511->SP-22009; 22/3/22: 23.700-55 added;; 4/6/22: 30%->50; 4/6/22: WID:SP-22009->SP-220465; 12/9/22: 50%->80; 12/9/22: FCD:12/09...","23.700-55",93,47,null,null,"Mon 13/09/21","Sun 11/12/22"]
[831,980126,"Architecture for UAS Applications, Phase 2 ","UASAPP_Ph2",1,"Rel-18",null,"Fri 09/09/22","Tue 12/12/23",1,"SP-220915",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ",null,"23.255 ",97,49,null,null,"Sun 11/09/22","NA"]
[832,970038,"   Stage 2 of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","S6","Fri 09/09/22","Tue 06/06/23",1,"SP-221228",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","; 11/12/22: 0%->25; 9/1/23: WID:SP-220915->SP-221228; 17/3/23: 25%->65; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100","23.255 ",97,49,null,null,"Sun 11/12/22","Thu 08/06/23"]
[833,980055,"   CT1 aspects of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","C1","Fri 16/12/22","Tue 12/12/23",1,"CP-240273",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com ","6/6/23: Compl:5%->60%","27.007; 24.257; 29.257",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[834,980056,"   CT3 aspects of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","C3","Fri 16/12/22","Tue 12/12/23",1,"CP-240273",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com ","; 9/6/23: 0%->40","27.007; 24.257; 29.257",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[835,941005,"NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV",1,"Rel-18","R2","Mon 13/12/21","Tue 03/03/26",0.7,"RP-233386",null,"Nokia",null,"no Perf. part; no RAN1 spec affected so far; 9/1/23: WID:RP-213600->RP-223545; 29/3/23: WID:RP-223545->RP-230782; 2/1/24: WID:RP-230782->RP-233386",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[836,941105,"   Core part: NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-233386","RP-233385","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","no Perf. part; no RAN1 spec affected so far; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221498; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com13/7/22: FCD:23/12/2022->12/20...; 17/3/23:...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[837,1070060,"   UE Conformance - NR Support for UAV (Uncrewed Aerial Vehicles) plus CT1 aspects ","NR_UAV_plus_CT1-UEConTest",2,"Rel-18","R5","Mon 03/03/25","Tue 03/03/26",0.28000000000000003,"RP-250062","RP-251507","China Unicom ",null,"6/6/25: Compl:0%->28%; Stat Rep: ->RP-251507; ",null,107,54,null,null,"Wed 26/03/25","Fri 06/06/25"]
[838,991035,"Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) ","LTE_UAV_enh",1,"Rel-18","R2","Fri 03/03/23","Tue 12/12/23",1,"RP-233389",null,"Nokia ",null,"2/1/24: WID:RP-230783->RP-233389",null,99,50,null,null,"Wed 29/03/23","Tue 02/01/24"]
[839,991135,"   Core part: Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) ","LTE_UAV_enh-Core",2,"Rel-18","R2","Fri 03/03/23","Tue 12/12/23",1,"RP-233389","RP-233388","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","; 7/6/23: Compl:0%->60%; 6/9/23: Compl:60%->80%; Stat Rep: ->RP-231865; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com; ; 8/12/23: Compl:80%->100%; Stat Rep: RP-231865->RP-233388; ",null,99,50,null,null,"Wed 29/03/23","Fri 08/12/23"]
[840,0,"Rel-18 Sidelink, Proximity, Location and Positioning","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[841,910040,"Ranging-based Service and sidelink positioning ","Ranging",1,"Rel-18",null,"Thu 25/06/20","Mon 03/03/25",1,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ",null,"22.261 ",91,46,null,null,"Thu 18/03/21","NA"]
[842,880039,"   Study on Ranging","FS_Ranging",2,"Rel-18","S1","Thu 25/06/20","Fri 11/06/21",1,"SP-200575",null,"Xiaowei jiang ","jiangxiaowei@xiaomi.com","28/7/20: 22.855 added;; 12/9/20: 0%->40; 5/12/20: 40%->80; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 80%->85; 11/6/21: 85%->100","22.855",88,45,null,null,"Thu 25/06/20","Fri 11/06/21"]
[843,910034,"   Stage 1 for Ranging","Ranging",2,"Rel-18","S1","Thu 18/03/21","Fri 11/06/21",1,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ","; 11/6/21: 0%->100","22.261 ",91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[844,940069,"   Study on Ranging based services and sidelink positioning ","FS_Ranging_SL",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211647",null,"Shen, Sherry (Yang), Xiaomi, ","shenyang6@xiaomi.com ","21/1/22: 23.700-86 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->70; 10/12/22: 70%->85; 15/3/23: 85%->100","23.700-86",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[845,980015,"   Stage 2 of Ranging_SL","Ranging_SL",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230106",null,"Shen, Sherry (Yang), Xiaomi ","shenyang6@xiaomi.com ","\"Architecture Enhancement to support Ranging based services and Sidelink Positioning\" ; 15/3/23: 0%->50; 15/3/23: WID:SP-221325->SP-230106; 17/3/23: 23.586 added;; 8/6/23: 50%->100","23.304; 23.287; 23.273; 23.502; 23.503 ; 23.586",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[846,960036,"   Study on Security Aspects of Ranging Based Services and Sidelink Positioning ","FS_Ranging_SL_Sec",2,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220534",null,"Wei Lu, Xiaomi, ","luwei10@xiaomi.com ","13/7/22: 33.893 added;; 12/9/22: 0%->20; 11/12/22: 20%->40; 17/3/23: 40%->70; 8/6/23: 70%->100","33.893",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[847,990046,"   Security Aspects of Ranging_SL","Ranging_SL_Sec",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230769",null,"Lu, Wei, Xiaomi ","luwei10@xiaomi.com ","31/3/23: 33.533 added;; 8/6/23: 0%->40; 30/6/23: WID:SP-230159->SP-230769; 7/9/23: 40%->100","33.533",99,50,null,null,"Thu 16/03/23","Thu 07/09/23"]
[848,990014,"   CT1 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-240298",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","; 31/3/23: 24.514 added;6/6/23: Compl:0%->15%","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 24.514",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[849,990066,"   CT3 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-240298",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","; 16/7/24: 99%->100","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572",99,50,null,null,"Fri 09/12/22","Tue 16/07/24"]
[850,990067,"   CT4 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-240298",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","6/6/23: Compl:0%->30%; 4/1/24: 29.586 added;","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 29.586",99,50,null,null,"Fri 09/12/22","Thu 04/01/24"]
[851,1040013,"   Charging Aspects of Ranging and Sidelink Positioning","Ranging_SL_CH",2,"Rel-18","S5","Mon 06/05/24","Mon 03/03/25",1,"SP-241002",null,"Zhiwei Mo, China Telecom, ","mozw@chinatelecom.cn ","; 4/9/24: 20%->50; 5/12/24: 50%->100","32.240; 32.290; 32.271; 32.291; 32.298 ",104,53,null,null,"Thu 13/06/24","Thu 05/12/24"]
[852,1000009,"   Charging Aspects of Ranging and Sidelink Positioning ","FS_Ranging_SL_CH",2,"Rel-18","S5","Thu 08/06/23","Sun 03/03/24",1,"SP-230622",null,"Zhiwei Mo, China Telecom, ","mozw<at>chinatelecom<dot>cn ","30/6/23: 28.845 added;; 7/9/23: 0%->15; 8/12/23: 15%->70; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 70%->100","28.845",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[853,980111,"5GC LoCation Services - Phase 3 ","5G_eLCS_Ph3",1,"Rel-18",null,"Fri 30/09/22","Sun 03/03/24",1,"SP-220811",null,"Ming Ai, CATT ","aiming@catt.cn ",null,"23.273 ",97,49,null,null,"Sun 11/09/22","NA"]
[854,940058,"   Study on Enhancement to the 5GC LoCation Services-Phase 3 ","FS_eLCS_Ph3",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220069",null,"Ming Ai, CATT ","aiming@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-71 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211637->SP-220069; 4/6/22: 15%->55; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 55%->80; 10/12/22: 80%->100","23.700-71",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[855,970021,"   (stage 2 of) 5GC LoCation Services - Phase 3 ","5G_eLCS_Ph3",2,"Rel-18","S2","Fri 30/09/22","Tue 06/06/23",1,"SP-230093",null,"Ming Ai, CATT ","aiming@catt.cn ","; 10/12/22: WID:SP-220811->SP-221123; 10/12/22: 0%->30; 10/12/22: 0%->30; 9/1/23: WID:SP-221123->SP-221338; 15/3/23: 30%->65; 15/3/23: WID:SP-221338->SP-230093; 15/3/23: FCD:03/03/2023->06/20; 8/6/23: 65%->100","23.273 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[856,980057,"   CT1 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-240233",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","6/6/23: Compl:5%->15%","23.273 ",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[857,980058,"   CT3 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-240233",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","; 9/6/23: 20%->30","23.273 ",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[858,980059,"   CT4 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C4","Fri 16/12/22","Sun 03/03/24",1,"CP-240233",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","; 9/6/23: 25%->65","23.273 ",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[859,1070019,"Charging aspects of 5GC LoCation Services ","CH_5G_eLCS_Ph3",1,"Rel-19","S5","Wed 26/03/25","Tue 09/09/25",1,"SP-250370",null,"Zhiwei Mo, China Telecom ","mozw@chinatelecom.cn ","; 6/6/25: 0%->100","32.271; 32.290; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[860,981038,"Expanded and improved NR positioning ","NR_pos_enh2",1,"Rel-18",null,"Tue 13/12/22","Fri 05/06/26",0.69,"RP-241186",null,"Intel ",null,"29/3/23: WID:RP-223549->RP-230328; 6/10/23: WID:RP-230328->RP-232670; 2/1/24: WID:RP-232670->RP-233382; 2/4/24: WID:RP-233382->RP-240778; 23/7/24: WID:RP-240778->RP-241186",null,98,50,null,null,"Mon 09/01/23","Tue 23/07/24"]
[861,981138,"   Core part: Expanded and improved NR positioning ","NR_pos_enh2-Core",2,"Rel-18","R1","Tue 13/12/22","Mon 03/03/25",1,"RP-241186","RP-241919","Debdeep Chatterjee","debdeep.chatterjee@intel.com","17/3/23: Compl:0%->15%; Stat Rep: ->RP-230327; Rapporteur: Intel->Debdeep Chatterjee, Intel Corporation; Rap eMail: ->debdeep.chatterjee@intel.com; 17/3/23: 38.355 added;; ;...; 6/9/23: Compl:50%->70%; WID: RP-230328->RP-231460; Stat Rep: RP-230327->R...","38.355",98,50,null,null,"Mon 09/01/23","Wed 04/09/24"]
[862,981238,"   Perf. part: Expanded and improved NR positioning ","NR_pos_enh2-Perf",2,"Rel-18","R4","Thu 15/12/22","Sat 04/05/24",0.99,"RP-241186","RP-242766","Debdeep Chatterjee","debdeep.chatterjee@intel.com","Study in Rel-17 UID820025; 13/12/21: 0%->15; 12/3/22: 15%->30; 22/3/22: 23.545 added;; 4/6/22: 30%->50; 12/9/22: 50%->55; 11/12/22: 55%->65; 11/12/22: FCD:09/12/2022->/23; 9/1/23: WID:SP-210957->SP-221233; 17/3/23: 65%->75; 8/6/23: 75%->100; 30/6/23: ...",null,98,50,null,null,"Mon 09/01/23","Fri 06/12/24"]
[863,1040107,"   UE Conformance - Expanded and improved NR positioning ","NR_pos_enh2-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 05/06/26",0.09,"RP-241342","RP-251627","CATT ",null,"4/9/24: FCD:06/06/2026->26/06/2025; Compl:0%->5%; Stat Rep: ->RP-242124; ; 26/9/24: WID:RP-241342->RP-242125; 6/12/24: FCD:06/06/2025->05/06/2026; Compl:5%->6%; WID: RP-242125->RP-241342; Stat Rep: RP-242124->RP-243121; ; 6/3/25: FCD:23/10/2025->05/06/20",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[864,940081,"   Study on expanded and improved NR positioning","FS_NR_pos_enh2",2,"Rel-18","R1","Tue 13/12/22","Wed 05/06/24",1,"RP-222616","RP-222982","Debdeep Chatterjee, Intel Corporation","debdeep.chatterjee@intel.com","compare REL-17 SI FS_NR_pos; TR 38.8xx; 21/1/22: 38.859 added; ; 6/6/22: Compl:0%->12% 20/6/22: Rapporteur: Intel->Alexey Khoryaev, Intel Corporation; Rap eMail: ->alexey.khoryaev@intel.com12/7/22: WID:RP-213588->RP-221814 ;...; 23/9/22: WID:RP-213588...","38.859",94,48,null,null,"Thu 06/01/22","Mon 09/01/23"]
[865,940097,"NR sidelink evolution","NR_SL_enh2",1,"Rel-18",null,"Mon 13/12/21","Thu 06/06/24",1,"RP-232789",null,"OPPO",null,"TR 38.8xx; compare REL-17 WI NR_SL_enh; 5/4/22: WID:RP-213678->RP-220300; 12/7/22: WID:RP-220300->RP-221798; 23/9/22: WID:RP-221798->RP-221938; 9/1/23: WID:RP-221938->RP-222806; 29/3/23: WID:RP-222806->RP-230077; 2/1/24: WID:RP-230077->RP-232789",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[866,940197,"   Core part: NR sidelink evolution","NR_SL_enh2-Core",2,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-232789","RP-232786","Kevin Lin, OPPO","Kevin.Lin@oppo.com","TR 38.8xx; compare REL-17 WI NR_SL_enh; 22/3/22: Stat Rep: ->RP-220320 6/6/22: Compl:0%->7% ; ; 20/6/22: Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01/12/2023; Comp...","38.786",94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[867,940297,"   Perf. part: NR sidelink evolution","NR_SL_enh2-Perf",2,"Rel-18","R1","Wed 15/12/21","Thu 06/06/24",1,"RP-232789","RP-240928","Kevin Lin, OPPO","Kevin.Lin@oppo.com","; 22/3/22: CD:12/09/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220320 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: ; 20/6/22: WG: R4->R1; Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD...",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[868,941002,"NR sidelink relay enhancements","NR_SL_relay_enh",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.95,"RP-232972",null,"LG Electronics",null,"compare REL-17 WI NR_SL_relay; 6/1/22: WID:RP-213585->RP-212819; 5/4/22: WID:RP-212819->RP-221010; 12/7/22: WID:RP-221010->RP-221262; 9/1/23: WID:RP-221262->RP-223501; 2/1/24: WID:RP-223501->RP-232972",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[869,941102,"   Core part: NR sidelink relay enhancements","NR_SL_relay_enh-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-232972","RP-232971","Youngdae LEE, LG Electronics Inc.","youngdae.lee@lge.com","compare REL-17 WI NR_SL_relay; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 20/6/22: Rapporteur: LG Electronics->Youngdae LEE, LG Electronics; Rap eMail: ->youngdae.lee@lge.com13/7/22: ...;...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[870,941202,"   Perf. part: NR sidelink relay enhancements","NR_SL_relay_enh-Perf",2,"Rel-18","R2","Wed 15/12/21","Thu 06/06/24",1,"RP-223501","RP-241088","Youngdae LEE, LG Electronics Inc.","youngdae.lee@lge.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 6/6/22: CD:12/06/2024->24/06/2022 20/6/22: WG: R4->R2; FCD:24/06/2022->22/06/2022; Rapporteur: LG Electronics->Youngdae LEE, LG Electronics;...;...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[871,960083,"   UE Conformance - NR Sidelink Relay ","NR_SL_relay-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Tue 09/09/25",0.9,"RP-221447","RP-251629","Xiaozhong CHEN, CATT","chenxiaozhong@catt.cn","9/9/22: Comp...; 23/9/22: WID:RP-221447->RP-222378; 9/12/22: FCD:23/09/2022->01/09/2023; WID: RP-222378->RP-221447; Stat Rep: ->RP-223141; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023.....",null,96,49,null,null,"Tue 12/07/22","Fri 06/06/25"]
[872,941000,"Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.95,"RP-234010",null,"ZTE",null,"no Perf. part; 9/1/23: WID:RP-213583->RP-222993; 2/1/24: WID:RP-222993->RP-234010",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[873,941100,"   Core part: Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-234010","RP-232887","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","no Perf. part ; 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Rep: RP-220215->RP-221310; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[874,1040103,"   UE Conformance - Mobile Terminated-Small Data Transmission (MT-SDT) for NR ","NR_MT_SDT-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 12/12/25",0.9,"RP-241127","RP-251189","Qualcomm ",null,"4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->10%; Stat Rep: ->RP-241914; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:10%->40%; Stat Rep: RP-241914->RP-242496; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:40%->65%; Stat Rep: RP-242496->RP-250111; ; 6/6/2",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[875,950048,"Study on Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",1,"Rel-18","S2","Mon 20/12/21","Fri 10/03/23",1,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 14/3/24: 95%->100","23.700-33",95,48,null,null,"Sun 19/12/21","Thu 14/03/24"]
[876,940077,"   Study on Stage 2 for Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->75; 10/12/22: 75%->100","23.700-33",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[877,950024,"   Study on Security Aspects of Proximity Based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S3","Thu 10/03/22","Fri 10/03/23",1,"SP-220202",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","4/6/22: 0%->5; 13/7/22: 33.740 added;; 13/7/22: 33.741 added;; 12/9/22: 5%->40; 11/12/22: 40%->75; 17/3/23: 75%->80; 8/6/23: 80%->90","33.740; 33.741",95,48,null,null,"Thu 10/03/22","Thu 08/06/23"]
[878,980112,"Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",1,"Rel-18",null,"Tue 27/09/22","Tue 12/12/23",1,"SP-220806",null,"Deng Qiang, CATT ","dengqiang1@catt.cn ",null,"23.304; 23.501; 23.502; 23.503 ",97,49,null,null,"Wed 19/10/22","NA"]
[879,970016,"   (stage 2 of) Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",2,"Rel-18","S2","Tue 27/09/22","Tue 06/06/23",1,"SP-230097",null,"Deng Qiang, CATT ","dengqiang1@catt.cn ","; 9/1/23: WID:SP-220806->SP-221206; 15/3/23: WID:SP-221206->SP-230097; 15/3/23: 0%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100","23.304; 23.501; 23.502; 23.503 ",97,49,null,null,"Wed 19/10/22","Thu 08/06/23"]
[880,980060,"   CT1 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C1","Fri 16/12/22","Tue 12/12/23",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","; 9/6/23: 15%->70","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"Wed 19/10/22","Fri 09/06/23"]
[881,980061,"   CT3 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C3","Fri 16/12/22","Tue 12/12/23",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","; 9/6/23: 0%->20","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"Wed 19/10/22","Fri 09/06/23"]
[882,980062,"   CT4 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C4","Fri 16/12/22","Tue 12/12/23",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","6/6/23: Compl:0%->30%","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"Wed 19/10/22","Tue 06/06/23"]
[883,980063,"   CT6 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C6","Fri 16/12/22","Tue 12/12/23",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn",null,"24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"Wed 19/10/22","NA"]
[884,990045,"   Security Aspects of Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230158",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 8/6/23: 0%->90; 8/12/23: 90%->95; 15/3/24: 95%->100","33.503 ",99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[885,990108,"5G-enabled fused location service capability exposure ","5GFLS",1,"Rel-18",null,"Fri 11/06/21","Sun 03/03/24",1,"SP-221234",null,"Liping Wu, CATT ","wuliping@cictmobile.com ",null,"23.434 ",99,50,null,null,"Fri 09/12/22","NA"]
[886,920015,"   Study on 5G-enabled fused location service capability exposure ","FS_5GFLS",2,"Rel-18","S6","Fri 11/06/21","Mon 12/09/22",1,"SP-220097",null,"Zhang, Ling, CATT ","zhangling@catt.cn ","2/7/21: 23.700-96 added;; 13/9/21: 0%->20; 13/12/21: 20%->40; 13/12/21: WID:SP-210477->SP-211512; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: FCD:10/06/2022->9/22; 12/3/22: WID:SP-211512->SP-220097; 4/6/22: 40%->55; 12/9/22: 55%->75; 11/12/22: 75%->100","23.700-96",92,47,null,null,"Fri 11/06/21","Sun 11/12/22"]
[887,980109,"   Stage 2 of 5GFLS","5GFLS",2,"Rel-18","S6","Fri 09/12/22","Tue 06/06/23",1,"SP-221234",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 17/3/23: 0%->60; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.434 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[888,990016,"   CT1 aspects of 5GFLS","5GFLS",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-230195",null,"Zhao, Xiaoxue, CATT","zhaoxiaoxue@cictmobile.com","6/6/23: Compl:0%->60%","24.545; 29.549",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[889,990069,"   CT3 aspects of 5GFLS","5GFLS",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-230195",null,"Zhao, Xiaoxue, CATT","zhaoxiaoxue@cictmobile.com","; 9/6/23: 0%->70","24.545; 29.549",99,50,null,null,"Fri 09/12/22","Fri 09/06/23"]
[890,0,"See also MCOver5GProSe under Mission Critical and LPHP under Verticals","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[891,0,"Rel-18 Verticals, Industries, Factories, Northbound API","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[892,930023,"Service exposure interfaces for industry ","EXPOSE",1,"Rel-18","S1","Fri 10/09/21","Mon 20/09/21",1,"SP-211056",null,"Joachim W. Walewski ","joachim.walewski@siemens.com ","; 13/12/21: 0%->100","22.261 ",93,47,null,null,"Fri 10/09/21","Mon 13/12/21"]
[893,1010009,"Guidelines for CAPIF Usage ","CAPIF_EXT",1,"Rel-18","S6","Thu 07/09/23","Mon 09/09/24",1,"SP-241692",null,"Junpei Uoshima, NTT DOCOMO ","junpei.uoshima.mt@nttdocomo.com ","8/12/23: 0%->20; 4/1/24: 23.946 added;; 14/3/24: 20%->55; 13/6/24: 55%->80; 4/9/24: 80%->90; 5/12/24: 90%->100; 8/1/25: WID:SP-231161->SP-241692 (change Rel-19->Rel-18)","23.946",101,51,null,null,"Thu 07/09/23","Wed 08/01/25"]
[894,990109,"Generic group management, exposure and communication enhancements ","GMEC",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-221339",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339","23.501; 23.502; 23.503 ",97,49,null,null,"Fri 23/09/22","Mon 09/01/23"]
[895,940061,"   Study on generic group management, exposure and communication enhancements ","FS_GMEC",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211603",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","21/1/22: 23.700-74 added;; 12/3/22: 0%->25; 4/6/22: 25%->70; 12/9/22: 70%->90; 10/12/22: 90%->95; 10/12/22: FCD:12/09/2022->12/22; 15/3/23: 95%->100","23.700-74",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[896,970069,"   Stage 2 of GMEC","GMEC",2,"Rel-18","S2","Fri 23/09/22","Fri 03/03/23",1,"SP-230101",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339; 15/3/23: WID:SP-221339->SP-230101; 15/3/23: 30%->70; 8/6/23: 70%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Fri 23/09/22","Thu 08/06/23"]
[897,990009,"   CT3 aspects of GMEC","GMEC",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-240296",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:15%->40%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"Fri 23/09/22","Tue 06/06/23"]
[898,990071,"   CT4 aspects of GMEC","GMEC",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-240296",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:5%->40%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"Fri 23/09/22","Tue 06/06/23"]
[899,990072,"   CT1 aspects of GMEC","GMEC",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-240296",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:0%->75%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"Fri 23/09/22","Tue 06/06/23"]
[900,930015,"Application layer support for Factories of the Future (FF) ","FFAPP",1,"Rel-18","S6","Fri 10/09/21","Fri 03/03/23",1,"SP-230751",null,"Shao Weixiang, ZTE Corporation ","shao.weixiang@zte.com.cn ",null,"23.434 ; 23.545",93,47,null,null,"Fri 10/09/21","Fri 30/06/23"]
[901,980131,"Service Enabler Architecture Layer for Verticals Phase 3","SEAL_Ph3",1,"Rel-18",null,"Fri 10/12/21","Sat 09/09/23",1,"SP-211518",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ",null,"23.434 ",94,48,null,null,"Fri 10/12/21","Mon 12/09/22"]
[902,940024,"   Stage 2 of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","S6","Sun 12/12/21","Tue 06/06/23",1,"SP-230276",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","; 12/3/22: 0%->5; 4/6/22: 5%->20; 12/9/22: 20%->35; 11/12/22: 35%->60. Acronym: eSEAL_Ph2->SEAL_Ph3; 11/12/22: FCD:12/12/2022->/23; 17/3/23: WID:SP-211518->SP-230276; 17/3/23: FCD:03/03/2023->6/6//23; change rapport (was Basavaraj (Basu) Pattan, Samsu...","23.434 ",94,48,null,null,"Sun 11/12/22","Thu 08/06/23"]
[903,980064,"   CT1 aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","C1","Sun 12/12/21","Mon 12/12/22",1,"CP-233219",null,"Vijay Sangameshwara (Samsung Electronics)","s.vijay@samsung.com","6/6/23: Compl:10%->45%","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549",94,48,null,null,"Fri 10/12/21","Tue 06/06/23"]
[904,980065,"   CT3 aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","C3","Fri 10/12/21","Fri 09/12/22",1,"CP-233219",null,"Vijay Sangameshwara (Samsung Electronics)","s.vijay@samsung.com","9/6/23: 15%->45","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549",94,48,null,null,"Fri 10/12/21","Fri 09/06/23"]
[905,990047,"   Security aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230365",null,"Rajavelsamy Rajadurai, Samsung ","rajvel@samsung.com ","; 8/6/23: 0%->80; 15/3/24: 80%->100","33.434 ",99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[906,980124,"SEAL data delivery enabler for vertical applications ","SEALDD",1,"Rel-18",null,"Mon 13/09/21","Sun 03/03/24",1,"SP-220914",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 23/9/22: 23.433 added;","23.434 ; 23.433",97,49,null,null,"Sun 11/09/22","Fri 23/09/22"]
[907,930013,"   Study on SEAL data delivery enabler for vertical applications ","FS_SEALDD",2,"Rel-18","S6","Mon 13/09/21","Mon 12/09/22",1,"SP-220467",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 12/3/22: 30%->45; 22/3/22: 23.700-34 added;; 4/6/22: 45%->60; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210955->SP-220467; 12/9/22: 60%->85; 11/12/22: 85%->100","23.700-34",93,47,null,null,"Mon 13/09/21","Sun 11/12/22"]
[908,970037,"   (Stage 2 of Seal DD) SEAL data delivery enabler for vertical applications","SEALDD",2,"Rel-18","S6","Fri 09/09/22","Tue 06/06/23",1,"SP-221232",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 23/9/22: 23.433 added;; 11/12/22: 0%->60; 9/1/23: WID:SP-220914->SP-221232; 17/3/23: 60%->85; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","23.434 ; 23.433; 23.558",97,49,null,null,"Sun 11/12/22","Thu 08/06/23"]
[909,980066,"   CT1 aspects of SEALDD","SEALDD",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-240272",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","30/6/23: WID:CP-230338->CP-231284","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558",97,49,null,null,"Sun 11/09/22","Fri 30/06/23"]
[910,980067,"   CT3 aspects of SEALDD","SEALDD",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-240272",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/3/23: 29.548 added;; 9/6/23: 5%->25","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558; 29.548",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[911,1000006,"   Security aspects of SEAL Data Delivery enabler ","SEALDD",2,"Rel-18","S3","Thu 08/06/23","Sat 09/09/23",1,"SP-230560",null,"Ao Lei, Huawei, ","leiao@huawei.com ","; 15/3/24: 0%->100","33.434 ",100,51,null,null,"Thu 08/06/23","Fri 15/03/24"]
[912,910036,"Low Power High Accuracy Positioning for industrial IoT scenarios ","LPHAP",1,"Rel-18","S1","Thu 18/03/21","Fri 11/06/21",1,"SP-210216",null,"Yuan Wang, Huawei ","wangyuan5@huawei.com ","; 19/3/21: 0%->40; 11/6/21: 40%->100","22.104; 22.261 ",91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[913,890024,"Subscriber-aware Northbound API access ","SNA",1,"Rel-18","S1","Tue 01/09/20","Thu 17/09/20",1,"SP-200797",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ",null,"22.261 ",89,45,null,null,"Fri 11/09/20","NA"]
[914,990117,"Application enablement aspects for subscriber-aware northbound API access ","SNAAPP",1,"Rel-18",null,"Thu 02/06/22","Sat 09/09/23",1,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","; 11/12/22: 0%->55","23.222; 23.434 ",96,49,null,null,"Thu 02/06/22","Sun 11/12/22"]
[915,960012,"   Stage 2 of SNAAPP","SNAAPP",2,"Rel-18","S6","Thu 02/06/22","Fri 03/03/23",1,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","; 11/12/22: 0%->55; 17/3/23: 15%->90; 8/6/23: 90%->100","23.222; 23.434 ",96,49,null,null,"Thu 16/03/23","Thu 08/06/23"]
[916,960028,"   Study on SNAAPP securitY ","FS_SNAAPPY",2,"Rel-18","S3","Thu 02/06/22","Mon 12/12/22",1,"SP-220526",null,"Zugenmaier, Alf, NTT DOCOMO, ","zugenmai@hm.edu ","13/7/22: 33.884 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->60; 8/6/23: 60%->100","33.884",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[917,990048,"   Security aspects of SNAPP ","SNAAPPY",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230161",null,"Zugenmaier, Alf, NTT DOCOMO ","zugenmai@hm.edu ","; 8/6/23: 0%->50; 8/12/23: 50%->85; 15/3/24: 85%->100","33.122 ",99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[918,1010002,"   CT3 aspects of SNAAPP","SNAAPP",2,"Rel-18","C3","Thu 16/03/23","Sat 09/09/23",1,"CP-232128",null,"Eitoku, Haruka, NTT","haruka.eitoku@ntt.com",null,"29.222",99,50,null,null,"Thu 16/03/23","Thu 08/06/23"]
[919,920039,"Smart Energy and Infrastructure ","SEI",1,"Rel-18",null,"Thu 25/06/20","Fri 10/12/21",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ",null,"22.104;22.261 ",92,47,null,null,"Fri 11/06/21","NA"]
[920,880038,"   Study on 5G Smart Energy and Infrastructure","FS_5GSEI",2,"Rel-18","S1","Thu 25/06/20","Fri 11/06/21",1,"SP-200574",null,"XIA Xu, China Telecom","xiaxu@chinatelecom.cn","28/7/20: 22.867 added;; 12/9/20: 0%->20; 5/12/20: 20%->60; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 60%->75; 11/6/21: 75%->90; 13/9/21: 90%->100","22.867",88,45,null,null,"Thu 25/06/20","Mon 13/09/21"]
[921,920032,"   Stage 1 of Smart Energy and Infrastructure ","SEI",2,"Rel-18","S1","Fri 11/06/21","Fri 10/12/21",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ","; 13/9/21: 0%->95; 10/12/21: 95%->100","22.104;22.261 ",92,47,null,null,"Fri 11/06/21","Fri 10/12/21"]
[922,940040,"Study on Network and Service Operations for Energy Utilities ","FS_NSOEU",1,"Rel-18","S5","Mon 13/12/21","Tue 06/06/23",1,"SP-211622",null,"Erik Guttman , Samsung ","erik.guttman@samsung.com ","7/1/22: 28.902 added;; 4/6/22: 0%->25; 12/9/22: 25%->45; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 45%->55; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 55%->79; 8/6/23: 79%->100","28.902",94,48,null,null,"Mon 13/12/21","Thu 08/06/23"]
[923,920014,"Study on application enablement aspects for subscriber-aware northbound API access ","FS_SNAAPP",1,"Rel-18","S6","Fri 11/06/21","Fri 10/06/22",1,"SP-220094",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","2/7/21: 23.700-95 added;; 13/9/21: 0%->20; 13/12/21: 20%->65; 12/3/22: 65%->75; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210476->SP-220094; 4/6/22: 75%->85; 12/9/22: 85%->90; 11/12/22: 90%->100","23.700-95",92,47,null,null,"Fri 11/06/21","Sun 11/12/22"]
[924,960022,"Rel-18 Enhancements of 3GPP Northbound and Application Layer interfaces and APIs","NBI18",1,"Rel-18",null,"Fri 03/06/22","Sun 03/03/24",1,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","30/6/23: WID:CP-221105->CP-231190",null,96,49,null,null,"Fri 03/06/22","Fri 30/06/23"]
[925,960053,"   CT1 aspects of NBI18","NBI18",2,"Rel-18","C1","Mon 06/06/22","Sun 03/03/24",1,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:25%->40%6/6/23: WID: CP-221105->CP-231190; 9/6/23: 40%->45; 9/6/23: 45%->","24.558 ",96,49,null,null,"Fri 03/06/22","Fri 09/06/23"]
[926,960054,"   CT3 aspects of NBI18","NBI18",2,"Rel-18","C3","Fri 03/06/22","Sun 03/03/24",1,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:30%->60%6/6/23: WID: CP-221105->CP-231190","29.116; 29.122; 29.222; 29.255; 29.257; 29.343; 29.486; 29.522; 29.538; 29.549; 29.558",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[927,980027,"Study on Structure of Charging for Verticals ","FS_SCV",1,"Rel-18","S5","Fri 09/12/22","Tue 12/12/23",1,"SP-230178",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","16/3/23: WID:SP-221161->SP-230178; 17/3/23: 0%->8; 17/3/23: 28.843 added;; 8/6/23: 8%->80; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 80%->100","28.843",98,50,null,null,"Fri 09/12/22","Thu 07/09/23"]
[928,1010015,"Charging Aspects of B2B","B2B_CH",1,"Rel-18","S5","Wed 06/09/23","Sun 03/03/24",1,"SP-231155",null,"Deng, Yimeng, Huawei ","dengyimeng at huawei dot com ","; 8/12/23: 0%->80; 14/3/24: 80%->100","32.240; 32.290 ",101,51,null,null,"Wed 06/09/23","Thu 14/03/24"]
[929,0,"Rel-18 Mission Critical and emergencies","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[930,960014,"SMS over IMS to emergency centre ","SMS2EC",1,"Rel-18","S1","Thu 02/06/22","Fri 10/06/22",1,"SP-220438",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 4/6/22: 0%->45; 12/9/22: 45%->100","22.101 ",96,49,null,null,"Thu 02/06/22","Mon 12/09/22"]
[931,940015,"Mission critical security enhancements phase 3 ","MCXSec3",1,"Rel-18","S3","Fri 10/12/21","Fri 03/03/23",1,"SP-211363",null,"Woodward, Tim, Motorola Solutions, Inc. ","tim.woodward@motorolasolutions.com ","; 4/6/22: 0%->10; 12/9/22: 10%->15; 11/12/22: 15%->35; 17/3/23: 35%->75; 8/6/23: 75%->100","33.180 ",94,48,null,null,"Fri 10/12/21","Thu 08/06/23"]
[932,1000042,"Enhanced Mission Critical Push-to-talk architecture phase 4 ","enh4MCPTT",1,"Rel-18",null,"Fri 10/12/21","Sun 03/03/24",1,"SP-211519",null,"Lazara, Dom, Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"Fri 10/12/21","Fri 17/03/23"]
[933,940025,"   Stage 2 of enh4MCPTT","enh4MCPTT",2,"Rel-18","S6","Fri 10/12/21","Fri 03/03/23",1,"SP-211519",null,"Lazara, Dom, Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80; 8/6/23: 80%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"Fri 10/12/21","Thu 08/06/23"]
[934,1000020,"   CT aspects of enh4MCPTT","enh4MCPTT",2,"Rel-18","C1","Wed 07/06/23","Sun 03/03/24",1,"CP-240297",null,"Kiran Kapale, Samsung, ","kiran.kapale@samsung.com ","; 30/6/23: 24.283 added;","24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 24.283",100,51,null,null,"Wed 07/06/23","Fri 30/06/23"]
[935,930043,"Gateway UE function for Mission Critical Communication ","MCGWUE",1,"Rel-18",null,"Thu 25/06/20","Sun 03/03/24",1,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"Fri 10/09/21","NA"]
[936,880033,"   Study of Gateway UE function for Mission Critical Communication ","FS_MCGWUE",2,"Rel-18","S6","Thu 25/06/20","Mon 20/09/21",1,"SP-200335",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-79 added;; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->60; 13/9/21: 60%->100","23.700-79",88,45,null,null,"Fri 26/06/20","Mon 13/09/21"]
[937,930017,"   (Stage 2 of) Gateway UE function for Mission Critical Communication ","MCGWUE",2,"Rel-18","S6","Fri 10/09/21","Fri 10/06/22",1,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->75; 4/6/22: 75%->90; 12/9/22: 90%->100","23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"Fri 10/09/21","Mon 12/09/22"]
[938,990011,"   CT1 aspects of MCGWUE","MCGWUE",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-232164",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,"24.281.24.282.24.379.24.380.24.483.24.484.24.581.24.582",93,47,null,null,"Fri 10/09/21","Mon 12/09/22"]
[939,970054,"Mission Critical Services over 5MBS ","MCOver5MBS",1,"Rel-18",null,"Thu 07/03/19","Tue 12/12/23",1,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85","23.289 ",93,47,null,null,"Fri 10/09/21","Sat 04/06/22"]
[940,930016,"   Stage 2 of Mission Critical Services over 5MBS ","MCOver5MBS",2,"Rel-18","S6","Thu 07/03/19","Fri 11/03/22",1,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85; 12/9/22: 0%->98; 12/9/22: FCD:10/06/2020->03/22; 11/12/22: 98%->100","23.289 ",93,47,null,null,"Fri 10/09/21","Sun 11/12/22"]
[941,970033,"   CT1 aspects of Mission Critical Services over 5MBS","MCOver5MBS",2,"Rel-18","C1","Tue 13/09/22","Tue 12/12/23",1,"CP-222175",null,"Chen, Ying, TD Tech Ltd.","chenying@td-tech.com","6/6/23: Compl:20%->40%","24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 42.581; 24.582",97,49,null,null,"Mon 05/09/22","Tue 06/06/23"]
[942,970055,"Mission Critical Services over 5GProSe ","MCOver5GProSe",1,"Rel-18",null,"Thu 07/03/19","Tue 12/12/23",1,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87","23.289 ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[943,940023,"   Stage 2 of Mission Critical Services over 5GProSe ","MCOver5GProSe",2,"Rel-18","S6","Thu 07/03/19","Mon 12/09/22",1,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87; 12/9/22: 0%->100; 12/9/22: FCD:10/06/2020->09/22","23.289 ",94,48,null,null,"Fri 10/12/21","Mon 12/09/22"]
[944,970034,"   CT1 aspects of Mission Critical Services over 5GProSe","MCOver5GProSe",2,"Rel-18","C1","Tue 13/09/22","Tue 12/12/23",1,"CP-233210",null,"Mengdi Ji, Huawei","jimengdi@huawei.com, ","3/24: rapporteur changed (was weihaitao@huawei.com)","24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 24.581; 24.582",97,49,null,null,"Mon 05/09/22","NA"]
[945,970027,"Stopped - ProSe Secondary Authentication ","PROSESA",1,"Rel-18","S3","Mon 12/09/22","Fri 03/03/23",1,"SP-220874",null,"Samir Ferdi , Interdigital ","samir. ferdi @ interdigital . com ","; 17/3/23: 0%->30; 8/6/23: 30%->90. 9/23: stopped at 90%","33.503 ",97,49,101,null,"Sun 11/09/22","Thu 08/06/23"]
[946,930026,"Sharing administrative configuration between interconnected MCX Service systems ","SACI_MCS",1,"Rel-18","S1","Fri 10/09/21","Fri 10/12/21",1,"SP-211059",null,"Toobe, Jens, BDBOS ","jens.toobe@bdbos.bmi.bund.de ","; 13/9/21: 0%->80; 10/12/21: 80%->100","22.280 ",93,47,null,null,"Fri 10/09/21","Fri 10/12/21"]
[947,930025,"Ad hoc Group Communication support in Mission Critical Services ","AHGC",1,"Rel-18","S1","Fri 10/09/21","Mon 20/09/21",1,"SP-211058",null,"Erik.Guttman, Samsung ","Erik.Guttman@samsung.com ","; 10/12/21: 0%->100","22.280 ",93,47,null,null,"Fri 10/09/21","Fri 10/12/21"]
[948,1010020,"Mission Critical ad hoc group Communications ","MC_AHGC",1,"Rel-18","S6","Fri 09/12/22","Sun 03/03/24",1,"SP-221235",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ","; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100","23.280; 23.379; 23.281; 23.282 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[949,980051,"   Stage 2 of Mission Critical ad hoc group Communications ","MC_AHGC",2,"Rel-18","S6","Fri 09/12/22","Tue 06/06/23",1,"SP-221235",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ","; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100","23.280; 23.379; 23.281; 23.282 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[950,1010004,"   CT1 aspects of Mission Critical ad hoc group Communications ","MC_AHGC",2,"Rel-18","C1","Sat 09/09/23","Sun 03/03/24",1,"CP-232162",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ",null,"24.379, 24.380, 24.281, 24.581, 24.282, 24.582, 24.481, 24.483, 24.484",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[951,850043,"Study on sharing administrative configuration between interconnected MCX Service systems ","FS_SACI_MCS",1,"Rel-18","S1","Thu 19/09/19","Fri 10/12/21",1,"SP-190837",null,"Toobe, Jens, BDBOS","jens.toobe at bdbos.bmi.bund.de","; 8/10/19: 22.881 added;; 6/12/19: 0%->5; 12/9/20: 5%->20; 19/3/21: 20%->55; 19/3/21: FCD:12/06/2020->12/21; 11/6/21: 55%->90; 13/9/21: 90%->100","New ; 22.881",85,43,null,null,"Fri 13/09/19","Mon 13/09/21"]
[952,940020,"Study on sharing of administrative configuration between interconnected MC service systems ","FS_MCShAC",1,"Rel-18","S6","Mon 13/12/21","Fri 03/03/23",1,"SP-211514",null,"Azem, Dania, BDBOS ","dania.azem@bdbos.bmi.bund.de ","7/1/22: 23.700-38 added;; 12/3/22: 0%->5; 4/6/22: 5%->25; 12/9/22: 25%->25; 11/12/22: 25%->65; 17/3/23: 65%->80; 8/6/23: 80%->100","23.700-38",94,48,null,null,"Mon 13/12/21","Thu 08/06/23"]
[953,940022,"Study on Mission Critical ad hoc group communications ","FS_MCAHGC",1,"Rel-18","S6","Mon 13/12/21","Mon 12/12/22",1,"SP-211516",null,"Arunprasath Ramamoorthy, Samsung ","arun.prasath@samsung.com ","7/1/22: 23.700-76 added;; 12/3/22: 0%->25; 4/6/22: 25%->75; 12/9/22: 75%->90; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 90%->95; 17/3/23: 95%->100","23.700-76",94,48,null,null,"Mon 13/12/21","Fri 17/03/23"]
[954,800023,"Study on Mission Critical services support over 5G System","FS_MCOver5GS",1,"Rel-18","S6","Wed 06/06/18","Fri 10/06/22",1,"SP-200837",null,"Verweij, Kees, The Police of the Netherlands","kees.verweij@politie.nl","6/8/18: 23.783 added;¦10/9/18: 0%->5¦7/12/18: 5%->35¦7/12/18: FCD:03/19->09/19¦14/12/18: WID:SP-180383->SP-181136. 03/19: Rel corrected (was shown as Rel-17); 31/5/19: 35%->40; 26/3/20: FCD:12/09/2019->09/20; 26/3/20: 40%->45; Rel-16->17; 03/22:Rel17-> ","New; 23.783",80,41,null,null,"Wed 06/06/18","Sat 04/06/22"]
[955,0,"Rel-18 Artificial Intelligence (AI)/Machine Learning (ML)","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[956,920037,"AI/ML model transfer in 5GS ","AIML_MT",1,"Rel-18",null,"Fri 06/12/19","Fri 10/12/21",1,"SP-210520",null,"Jia SHEN, OPPO, sj@oppo.com ",null,null,"22.261",92,47,null,null,"Fri 11/06/21","Wed 13/07/22"]
[957,860009,"   Study on traffic characteristics and performance requirements for AI/ML model transfer in 5GS ","FS_AIML_MT",2,"Rel-18","S1","Fri 06/12/19","Fri 11/06/21",1,"SP-220441",null,"Jia SHEN, Oppo . ","sj@oppo.com ","28/7/20: 33.852 added;; 12/9/20: 0%->40; 5/12/20: 40%->70; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 70%->75; 11/6/21: 75%->95; 13/9/21: 95%->100. 06/22: FS_AMMT->FS_AIML_MT; 21/6/22: WID:SP-191040->SP-220441","22.874",86,44,null,null,"Fri 06/12/19","Tue 21/06/22"]
[958,920030,"   Stage 1 of AMMT ","AIML_MT",2,"Rel-18","S1","Fri 11/06/21","Fri 10/12/21",1,"SP-220440",null,"Jia SHEN, OPPO, sj@oppo.com ",null,"; 13/9/21: 0%->80; 11/3/22: 80%->10006/22: AMMT->AIML_MT; 21/6/22: WID:SP-210587->SP-220440","22.261 ",92,47,null,null,"Fri 11/06/21","Tue 21/06/22"]
[959,940084,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface","FS_NR_AIML_air",1,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-250792","RP-233132","Juan Montojo (RAN1); Mattias Frenne (RAN2); Xiaofeng Liu (RAN4), Qualcomm; Ericsson; CAICT","juanm@qti.qualcomm.com; mattias.frenne@ericsson.com; liuxiaofeng1@caict.ac.cn","TR 38.8xx; compare REL-18 WI NR_AIML_NGRAN-Core; 21/1/22: 38.843 added;; 22/3/22: Stat Rep: ->RP-220534 ; 6/6/22: Compl:0%->5% 20/6/22: Acronym:FS_NR_AIML_air->FS_NR_AIML_Air; Rapporteur: Qualcomm->Juan Montojo, Qualcomm; Rap eMail: ->juanm@qti....;...","38.843",94,48,null,null,"Thu 06/01/22","Thu 03/04/25"]
[960,989997,"Artificial Intelligence (AI)/Machine Learning (ML) ","AIMLsys",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-231278",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","10/12/22: 0%->5; 3/1/24: WID:SP-221329->SP-231278","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"Fri 09/12/22","Wed 03/01/24"]
[961,960037,"   Study on Security and Privacy of AI/ML-based Services and Applications in 5G ","FS_AIML",2,"Rel-18","S3","Tue 21/06/22","Fri 03/03/23",1,"SP-220687",null,"Marcus Wong, OPPO ","marcus.wong@oppo.com ","13/7/22: 33.898 added;; 12/9/22: 0%->5; 11/12/22: 5%->25; 17/3/23: 25%->35; 7/9/23: 35%->100","33.898",96,49,null,null,"Tue 21/06/22","Thu 07/09/23"]
[962,940071,"   Study on 5G System Support for AI/ML-based Services ","FS_AIMLsys",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220071",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","21/1/22: 23.700-80 added;; 12/3/22: 0%->10; 12/3/22: WID:SP-211648->SP-220071; 4/6/22: 10%->60; 12/9/22: 60%->70; 10/12/22: 70%->100; 10/12/22: FCD:12/09/2022->12/22","23.700-80",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[963,980019,"   (Stage 2 for AIML) System Support for AI/ML-based Services","AIMLsys",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-231278",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","10/12/22: 0%->5; 15/3/23: WID:SP-221329->SP-230095; 15/3/23: 5%->50; 8/6/23: 50%->100; 3/1/24: WID:SP-230095->SP-231278","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"Fri 09/12/22","Wed 03/01/24"]
[964,990008,"   CT3 aspects of AIML","AIMLsys",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-230329",null,"Tangudu, Narendranath Durga, Samsung","n.tangudu@samsung.com","31/3/23: 29.543 added;6/6/23: Compl:10%->50%","29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510; 29.543",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[965,990074,"   CT4 aspects of AIML","AIMLsys",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-230329",null,"Tangudu, Narendranath Durga, Samsung","n.tangudu@samsung.com","6/6/23: Compl:0%->60%","29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[966,941010,"Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN",1,"Rel-18",null,"Mon 13/12/21","Mon 01/05/23",0.8,"RP-233441",null,"CMCC",null,"no Perf. part; compare REL-18 SI FS_NR_AIML_air; 5/4/22: WID:RP-213602->RP-220635; 2/1/24: WID:RP-220635->RP-233441",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[967,941110,"   Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN-Core",2,"Rel-18","R3","Mon 13/12/21","Mon 01/05/23",0.8,"RP-233441","RP-232673","Fang Xie, Angelo Centonza, CMCC, Ericsson","xiefang@chinamobile.com, angelo.centonza@ericsson.com","no Perf. part; compare REL-18 SI FS_NR_AIML_air; 20/6/22: FCD:23/06/2023->23/06/2022; WID: RP-220635->RP-213602; Stat Rep: ->RP-221381; Rapporteur: CMCC->Fang Xie, Angelo Centonza, CMCC, Ericsson; Rap eMail: ->xiefang@chinamobile.com, angelo.centonza@e...",null,94,48,null,null,"Thu 06/01/22","Thu 21/09/23"]
[968,960031,"Study on the security aspects of Artificial Intelligence (AI)/Machine Learning (ML) for the NG-RAN ","FS_NR_AIML_NGRAN_SEC",1,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220529",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","13/7/22: 33.877 added; 17/8/22: WID in SP-220529 marked as withdrawn in SA#96 tdoc list; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70. 030/6/23: \"undeleted\" as per Mirko+Vlasios email; 7/9/23: 70%->100","33.877",96,49,null,null,"Thu 02/06/22","Thu 07/09/23"]
[969,940039,"Study on AI/ML management ","FS_AIML_MGMT",1,"Rel-18","S5","Mon 13/12/21","Tue 06/06/23",1,"SP-211443",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","7/1/22: 28.908 added;; 4/6/22: 0%->10; 12/9/22: 10%->55; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 55%->85; 11/12/22: FCD:10/03/2023->/23; 8/6/23: 85%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","28.908",94,48,null,null,"Mon 13/12/21","Thu 08/06/23"]
[970,990119,"AI/ML management ","AIML_MGT",1,"Rel-18","S5","Fri 17/03/23","Sun 03/03/24",1,"SP-230335",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 8/6/23: 0%->20; 7/9/23: 20%->35; 14/3/24: 35%->100; 14/3/24: FCD:12/12/2023->/24","28.105; 28.552; 32.425; 28.554; 28.541 ",99,50,null,null,"Fri 17/03/23","Thu 14/03/24"]
[971,1020023,"NEF Charging enhancement to support AI/ML in 5GS ","AIMLsysNEF_CH",1,"Rel-18","S5","Thu 07/12/23","Tue 12/12/23",1,"SP-231706",null,"Alla Goldner, OPPO ","v-alla.goldner@oppo.com ","; 14/3/24: 0%->100; 14/3/24: 100%->100","32.254; 32.291 ",102,52,null,null,"Thu 07/12/23","Thu 14/03/24"]
[972,0,"Rel-18 Multicast and Broadcast Services (MBS)","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[973,940099,"Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh",1,"Rel-18",null,"Mon 13/12/21","Fri 12/12/25",0.66,"RP-232993",null,"CATT",null,"no Perf. part; compare REL-17 WI NR_MBS-Core; 12/7/22: WID:RP-213568->RP-221458; 6/10/23: WID:RP-221458->RP-231829; 2/1/24: WID:RP-231829->RP-232993",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[974,940199,"   Core part: Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-232993","RP-232992","Rui Zhou, CATT","zhourui@catt.cn","no Perf. part; compare REL-17 WI NR_MBS-Core; 22/3/22: Stat Rep: ->RP-220734 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220734->RP-221459; 20/6/22: Rapporteur: CATT->Erlin Zeng, CATT; Rap eMail: ->erlin.zeng@catt.cn13/7/22: FCD:23...;...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[975,1060077,"   UE Conformance - Enhancements of NR Multicast and Broadcast Services including CT aspects ","NR_MBS_enh_5MBS_Ph2-UEConTest",2,"Rel-18","R5","Thu 06/03/25","Fri 12/12/25",0.05,"RP-243116","RP-251630","CATT ",null,"6/3/25: Compl:0%->5%; Stat Rep: ->RP-250503; ; 3/4/25: WID:RP-243116->RP-250504; 6/6/25: FCD:Thu 13/11/25->Fri 12/12/25; WID: RP-250504->RP-243116; Stat Rep: RP-250503->RP-251630; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[976,989999,"5G multicast-broadcast services Phase 2","5MBS_Ph2",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-221131",null,"Meng Li, Huawei, Huawei ","raymond.limeng@huawei.com ",null,"23.501; 23.502; 23.247 ",98,50,null,null,"Fri 09/12/22","NA"]
[977,940067,"   Study on architectural enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220072",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","21/1/22: 23.700-47 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211645->SP-220072; 4/6/22: 15%->55; 12/9/22: 55%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-47",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[978,980013,"   (Stage 2 of 5MBS_Ph2) Architectural enhancements for 5G multicast-broadcast services Phase 2","5MBS_Ph2",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230099",null,"Meng Li, Huawei, Huawei ","raymond.limeng@huawei.com ","; 15/3/23: WID:SP-221131->SP-230099; 15/3/23: 0%->75; 8/6/23: 75%->100","23.501; 23.502; 23.247 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[979,990001,"   CT1 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-232031",null,"Rezagah, Roya, Huawei","roya.rezagah@huawei.com","6/6/23: Compl:0%->65%; 30/6/23: WID:CP-230023->CP-231024. 03/24: rapporteur changed (was giorgi.gulbani@huawei.com)",null,99,50,null,null,"Fri 09/12/22","Fri 30/06/23"]
[980,990076,"   CT3 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-232031",null,"Rezagah, Roya, Huawei","roya.rezagah@huawei.com","; 9/6/23: 15%->40",null,99,50,null,null,"Fri 09/12/22","Fri 09/06/23"]
[981,990077,"   CT4 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-232031",null,"Rezagah, Roya, Huawei","roya.rezagah@huawei.com","; 17/3/23: 5%->206/6/23: Compl:20%->70%",null,99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[982,1000005,"   Security Enhancements for 5G Multicast-Broadcast Services Phase 2 ","5MBS_Ph2",2,"Rel-18","S3","Thu 08/06/23","Sat 09/09/23",1,"SP-230559",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","; 15/3/24: 0%->100","33.501 ",100,51,null,null,"Thu 08/06/23","Fri 15/03/24"]
[983,960041,"   Study on security enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_SEC_Ph2",2,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220539",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","13/7/22: 33.883 added;; 12/9/22: 0%->12; 11/12/22: 12%->50; 17/3/23: 50%->55; 8/6/23: 55%->100","33.883",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[984,920071,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2",1,"Rel-18",null,"Tue 15/06/21","Fri 12/12/25",0.62,"RP-223378",null,"EBU ",null,"RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 5/4/22: WID:RP-211145->RP-220518; 23/9/22: WID:RP-220518->RP-222224; 9/1/23: WID:RP-222224->RP-223378",null,92,47,null,null,"Fri 02/07/21","Mon 09/01/23"]
[985,920171,"   Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2-Core",2,"Rel-18","R4","Tue 15/06/21","Fri 08/09/23",1,"RP-232590","RP-235288","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 13/9/21: CD:Wed 15/03/23->Wed 23/03/22 ; 22/3/22: CD:23/03/2022->12/06/2023; 22/3/22: Stat Rep: RP ; 6/6/22: CD:12/06/2023->23/0 ; 20/6/22: Rappor...","36.792",92,47,null,null,"Fri 02/07/21","Fri 06/10/23"]
[986,1050131,"   UE Conformance - New bands and bandwidth allocation for LTE based 5G terrestrial broadcast ","LTE_terr_bcast_bands_part2-UEConTest",2,"Rel-18","R5","Mon 09/09/24","Fri 12/12/25",0.15,"RP-242026","RP-251233","Qualcomm ",null,"6/12/24: Compl:0%->5%; Stat Rep: ->RP-242900; ; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:5%->15%; Stat Rep: RP-242900->RP-250398; ; 6/6/25: Stat Rep: RP-250398->RP-251233; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[987,990078,"UE pre-configuration for 5MBS","UEConfig5MBS",1,"Rel-18",null,"Fri 03/03/23","Sun 03/03/24",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com",null,"31.102",92,47,null,null,"Fri 02/07/21","Mon 09/01/23"]
[988,990022,"   CT1 aspects of UEConfig5MBS","UEConfig5MBS",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com","6/6/23: Compl:85%->95%6/6/23: CD:24/03/2023->03/03/2024","31.102",92,47,null,null,"Fri 02/07/21","Tue 06/06/23"]
[989,990079,"   CT6 aspects of UEConfig5MBS","UEConfig5MBS",2,"Rel-18","C6","Fri 03/03/23","Fri 03/03/23",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com",null,"31.102",92,47,null,null,"Fri 02/07/21","Mon 09/01/23"]
[990,0,"See also MCOver5MBS under Mission Critical","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[991,0,"See also TEI18_MBS4V2X under Autonomous Driving","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[992,0,"Rel-18 Slice","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[993,910095,"Study on 5G NR UE full stack testing for Network Slicing ","FS_NR_Slice_Test",1,"Rel-18","R5","Fri 12/03/21","Thu 22/09/22",1,"RP-211976","RP-221363","Dan SONG, Yu SHI, CMCC, CU","songdan@chinamobile.com, shiyu19@chinaunicom.cn","TR 38.9XX; compare RAN2 REL-17 SI FS_NR_slice; related to REL-15 WI 5GS_Ph1 and REL-16 WI eNS) ; 2/7/21: 0%->10; 13/9/21: Compl:10%->28%; ; 29/9/21: WID:RP-210371->RP-211977; 04/22: Rel-17->Rel-18; 20/6/22: FCD:22/03/2022->22/09/2022; Compl:28%->82%; ...",null,91,46,null,null,"Wed 07/04/21","Fri 23/09/22"]
[994,910026,"Study on network slice management capability exposure ","FS_NSCE",1,"Rel-18","S5","Thu 18/03/21","Tue 06/06/23",1,"SP-220350",null,"Xiaobo Yu, Alibaba Group ","shibo.yxb@alibaba-inc.com ","; 11/6/21: 0%->5; 11/6/21: FCD:Fri 10/12/->12/21; 13/9/21: 5%->25; 13/12/21: 25%->65; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 22/3/22: WID:SP-210131->SP-220350; 4/6/22: 65%->80; 4/6/22: FCD:11/03/2022->03/23; 12/9/22: 80%->83; 12/9/2...","New ",91,46,null,null,"Thu 18/03/21","Thu 08/06/23"]
[995,910038,"Enhanced Access to and Support of Network Slice ","EASNS",1,"Rel-18",null,"Thu 25/06/20","Sun 03/03/24",1,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ",null,"22.261 ",91,46,null,null,"Thu 18/03/21","NA"]
[996,880035,"   Study on EASNS","FS_EASNS",2,"Rel-18","S1","Thu 25/06/20","Wed 17/03/21",1,"SP-200571",null,"Chun, SungDuck, LG Electronics Inc","sungduck.chun@lge.com ","12/9/20: 0%->20; 25/9/20: 22.835 added;; 5/12/20: 20%->60; 19/3/21: 60%->85; 11/6/21: 85%->100","22.835",88,45,null,null,"Thu 25/06/20","Fri 11/06/21"]
[997,910032,"   Stage 1 for EASNS","EASNS",2,"Rel-18","S1","Thu 18/03/21","Fri 10/09/21",1,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ","; 11/6/21: 0%->100","22.261 ",91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[998,1000023,"   Stopped – CT1 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C1","Wed 07/06/23","Sun 03/03/24",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","8/8/23: acronym changed SbPS to PLMNsel_NS","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"Wed 07/06/23","NA"]
[999,1000044,"   Stopped – CT4 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C4","Wed 07/06/23","Sun 03/03/24",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","stopped","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"Wed 07/06/23","NA"]
[1000,1000045,"   Stopped – CT6 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C6","Wed 07/06/23","Sun 03/03/24",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","stopped","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"Wed 07/06/23","NA"]
[1001,980127,"Network Slicing Phase 3 ","eNS_Ph3",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-221135",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502; 23.503 ",98,50,null,null,"Fri 09/12/22","NA"]
[1002,940063,"   Study on Enhancement of Network Slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220073",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","21/1/22: 23.700-41 added;; 21/1/22: 23.700-17 added;; 12/3/22: 0%->5; 12/3/22: WID:SP-211641->SP-220073; 4/6/22: 5%->50; 12/9/22: 50%->70; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 70%->100","23.700-41; 23.700-17",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1003,960029,"   Study on enhanced security for network slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220527",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","13/7/22: 33.886 added;; 11/12/22: 0%->15; 17/3/23: 15%->50; 8/6/23: 50%->90; 15/3/24: 90%->100","33.886",96,49,null,null,"Thu 02/06/22","Fri 15/03/24"]
[1004,980017,"   Stage 2 of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230104",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 15/3/23: WID:SP-221327->SP-230104; 15/3/23: 0%->50; 8/6/23: 50%->100","23.501; 23.502; 23.503 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[1005,990015,"   CT1 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","6/6/23: Compl:0%->40%","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1006,990081,"   CT3 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","; 9/6/23: 0%->30","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"Fri 09/12/22","Fri 09/06/23"]
[1007,990082,"   CT4 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","6/6/23: Compl:5%->45%","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1008,1030024,"   Network Slice Replacement charging ","eNS_Ph3_CH",2,"Rel-18","S5","Fri 02/02/24","Sun 03/03/24",1,"SP-240475",null,"Maryse Gardella, MATRIXX Software, ","Maryse dot Gardella at Matrixx dot com) ","; 2/4/24: 0%->100","32.255; 32.256; 32.291; 32.298 ",103,52,null,null,"Thu 14/03/24","Tue 02/04/24"]
[1009,991037,"Network Slicing Phase 3: NR aspects ","eNS_Ph3-NR",1,"Rel-18","R3","Fri 03/03/23","Tue 12/12/23",1,"RP-232793",null,"ZTE ",null,"2/1/24: WID:RP-230787->RP-232793",null,99,50,null,null,"Wed 29/03/23","Tue 02/01/24"]
[1010,991137,"   Core part: Network Slicing Phase 3: NR aspects ","eNS_Ph3-NR-Core",2,"Rel-18","R3","Fri 03/03/23","Tue 12/12/23",1,"RP-232793","RP-232866","Dapeng Li, ZTE","Li.dapeng@zte.com.cn","; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->70%; WID: RP-230787->RP-231396; Stat Rep: ->RP-231889; Rapporteur: ZTE->Dapeng Li, ZTE; Rap eMail: ->Li.dapeng@zte.com.cn; ; 8/12/23: Compl:70%->100%; Stat Rep: RP-231889->RP-232866; ",null,99,50,null,null,"Wed 29/03/23","Fri 08/12/23"]
[1011,940045,"Network slicing provisioning rules ","NSRULE",1,"Rel-18","S5","Fri 10/12/21","Tue 12/12/23",1,"SP-211449",null,"Robert Petersen, Ericsson ","robert.petersen@ericsson.com ","; 4/6/22: 0%->35; 12/9/22: 35%->45; 12/9/22: FCD:12/09/2022->06/23; 11/12/22: 45%->55; 17/3/23: 55%->60; 8/6/23: 60%->60; 8/6/23: FCD:09/06/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->12/23; 8/12/23: 70%->100","28.531; 28.541 ",94,48,null,null,"Fri 10/12/21","Fri 08/12/23"]
[1012,950039,"Study on intent-driven management for network slicing ","FS_NETSLICE_IDMS",1,"Rel-18","S5","Thu 10/03/22","Tue 12/12/23",1,"SP-220278",null,"Jan Groenendijk , Ericsson ","Jan.Groenendijk@ericsson.com ","5/4/22: 28.836 added;; 11/9/22: FCD:12/09/2022->06/23; 12/9/22: 0%->40; 12/9/22: FCD:12/06/2023->12/22; 11/12/22: 40%->50; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 50%->85; 8/6/23: FCD:06/06/2023->/23; 7/9/23: 85%->85; 7/9/23: FCD:09/09/2023->12/23; 8/12/23","28.836",95,48,null,null,"Thu 10/03/22","Fri 08/12/23"]
[1013,990030,"Intent driven Management Service for Mobile Network phase 2 ","IDMS_MN_ph2",1,"Rel-18","S5","Thu 16/03/23","Tue 12/12/23",1,"SP-230180",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","; 8/6/23: 0%->40; 8/6/23: 40%->; 7/9/23: 40%->75; 8/12/23: 75%->100; 4/1/24: 28.914 added;","28.312 ; 28.914",99,50,null,null,"Thu 16/03/23","Thu 04/01/24"]
[1014,910023,"Study on enhanced security for network slicing Phase 2 ","FS_eNS2_SEC",1,"Rel-18","S3","Thu 18/03/21","Fri 10/12/21",1,"SP-210106",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","; 19/3/21: 0%->10; 9/4/21: FCD:11/06/2021->09/21; 11/6/21: 10%->15; 11/6/21: FCD:Wed 08/09/->12/21; 2/7/21: 33.874 added;; 13/9/21: 15%->30; 13/3/22: Rel-17->Rel-18; 4/6/22: 30%->100","New ; 33.874",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1015,960048,"Study on Media Streaming aspects of Network Slicing Phase 2","FS_MS_NS_Ph2",1,"Rel-18","S4","Wed 15/06/22","Tue 12/12/23",1,"SP-220675",null,"Prakash Kolan, samsung ","p.kolan@samsung.com ","3/8/22: 26.941 added; 17/8/22: FS_eNS_Ph3->FS_MS_NS_Ph2; WID:SP-220615->SP-220675; 12/9/22: 0%->15; 11/12/22: 15%->20; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 20%->25; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 25%->40; 7/9/23: 40%->65; 8/12/23: 65%->100","26.941",96,49,null,null,"Fri 03/06/22","Fri 08/12/23"]
[1016,940013,"Enhanced security for Phase 2 network slicing ","eNS2_SEC",1,"Rel-18","S3","Fri 10/12/21","Fri 11/03/22",1,"SP-211361",null,"Lei, Zander, Huawei ","lei.zhongding@huawei.com ","12/3/22: 0%->70; 13/3/22: Rel-17->Rel-18; 4/6/22: 70%->100","33.501; ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1017,910022,"Study on Network Slice Capability Exposure for Application Layer Enablement ","FS_NSCALE",1,"Rel-18","S6","Thu 18/03/21","Mon 12/09/22",1,"SP-211509",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","2/7/21: 23.700-99 added;; 13/9/21: 0%->25; 13/12/21: 25%->55; 13/12/21: FCD:Fri 11/03/->06/22; 13/12/21: WID:SP-210177->SP-211509; 12/3/22: 55%->70; 4/6/22: 70%->85; 12/9/22: 85%->95; 12/9/22: FCD:10/06/2022->09/22; 11/12/22: 95%->100","23.700-99",91,46,null,null,"Thu 18/03/21","Sun 11/12/22"]
[1018,1020049,"Network Slice Capability Exposure for Application Layer Enablement ","NSCALE",1,"Rel-18",null,"Thu 02/06/22","Fri 15/03/24",1,"SP-220470",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100","23.434 ; 23.435",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1019,960013,"   (Stage 2 of NSCALE) Network Slice Capability Exposure for Application Layer Enablement","NSCALE",2,"Rel-18","S6","Thu 02/06/22","Fri 03/03/23",1,"SP-220470",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100","23.434 ; 23.435",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1020,1020050,"   CT1 aspects of NSCALE","NSCALE",2,"Rel-18","C1","Thu 02/06/22","Sun 03/03/24",1,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,"24.549",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1021,1020006,"   CT3 aspects of NSCALE","NSCALE",2,"Rel-18","C3","Thu 02/06/22","Sun 03/03/24",1,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,"29.222, 29.520, 29.522, 29.549",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1022,1020046,"   CT4 aspects of NSCALE","NSCALE",2,"Rel-18","C4","Thu 02/06/22","Fri 15/03/24",1,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,"29.536",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1023,960005,"Study on new UICC application for network slice-specific authentication and authorization (NSSAA)","FS_NS_Slice-USIM",1,"Rel-18","C6","Fri 03/06/22","Sat 09/09/23",1,"CP-221186",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","13/7/22: 31.826 added;","31.826",96,49,null,null,"Fri 03/06/22","Wed 13/07/22"]
[1024,900023,"Study on Charging Aspects for Network Slicing Phase 2 ","FS_NETSLICE_CH_Ph2",1,"Rel-18","S5","Tue 12/01/21","Fri 03/03/23",1,"SP-201082",null,"Matrixx, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","21/3/21: 0%->15; 13/9/21: 15%->50; 13/9/21: FCD:Fri 10/09/->12/21; 12/3/22: 50%->70; 4/6/22: 70%->75; 4/6/22: FCD:10/12/2021->03/23; 21/6/22: 75%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85...",null,90,46,null,null,"Tue 12/01/21","Fri 17/03/23"]
[1025,980025,"Charging Aspects of Network Slicing Phase 2 ","NETSLICE_CH_Ph2",1,"Rel-18","S5","Mon 12/12/22","Sun 03/03/24",1,"SP-231448",null,"Gerald Görmer, MATRIXX Software ","Gerald dot Goermer at Matrixx dot com ","; 16/3/23: FCD:09/09/2023->12/20; 16/3/23: WID:SP-221159->SP-230176; 17/3/23: 0%->5; 17/3/23: 28.203 added;; 8/6/23: 5%->40; 7/9/23: 40%->50; 8/12/23: 50%->75; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-230176->SP-231448; 14/3/24: 75%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.203",98,50,null,null,"Fri 09/12/22","Thu 14/03/24"]
[1026,1000002,"Enhancement of Network Slicing UICC application for network slice-specific authentication and authorization ","eNS_UICC",1,"Rel-18","C6","Fri 30/06/23","Sun 03/03/24",1,"CP-231351",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","21/9/23: 31.105 added;","31.105",100,51,null,null,"Fri 30/06/23","Thu 21/09/23"]
[1027,0,"Rel-18 eXtended, Augmented and Virtual Reality (XR, AR, VR), immersive ","-",1,"Rel-18",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1028,981039,"XR (eXtended Reality) enhancements for NR ","NR_XR_enh",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.89,"RP-232778",null,"Nokia ",null,"29/3/23: WID:RP-223502->RP-230786; 2/1/24: WID:RP-230786->RP-232778",null,98,50,null,null,"Mon 09/01/23","Tue 02/01/24"]
[1029,981139,"   Core part: XR (eXtended Reality) enhancements for NR ","NR_XR_enh-Core",2,"Rel-18","R2","Tue 13/12/22","Tue 12/12/23",1,"RP-223502","RP-232779","Benoist S bire, Nokia","benoist.sebire@nokia.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230277; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; 31/3/23: WID: RP-230786->RP-223502; Stat Rep: RP-230277->RP-230785; ;...; 6/9/23: Compl:45%->68%; Stat Rep: RP-230785->RP-2...",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[1030,940087,"   Study on XR (eXtended Reality) enhancements for NR","FS_NR_XR_enh",2,"Rel-18","R2","Mon 13/12/21","Fri 03/03/23",1,"RP-220285","RP-230276","Benoist S bire, Nokia","benoist.sebire@nokia.com","TR 38.8xx; basic XR functionality introduced in REL-15 WI NR_newRAT; 22/3/22: Stat Rep: ->RP-220511; 5/4/22: WID:RP-213587->RP-220285 6/6 ; 20/6/22: Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com13/7/22: 38.835 add...;...","38.835",94,48,null,null,"Thu 06/01/22","Fri 17/03/23"]
[1031,1030063,"   UE Conformance - XR (eXtended Reality) enhancements for NR plus CT1 aspects ","NR_XR_enh_plus_CT1-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.8,"RP-241588","RP-250986","Nokia ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-240936; ; 23/7/24: WID:RP-240088->RP-241588; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->40%; Stat Rep: RP-240936->RP-241790; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:40%->60%; Stat Rep: RP-241790->RP-242607; ; ",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1032,990110,"Architecture Enhancements for XR (Extended Reality) and media service","XRM",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-221326",null,"Dan WANG, China Mobile","wangdanyjy@chinamobile.com ",null,"23.501; 23.502; 23.503 ",99,50,null,null,"Fri 09/12/22","NA"]
[1033,940068,"   Study on architecture enhancement for XR and media services ","FS_XRM",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220705",null,"Dan Wang, China Mobile ","wangdanyjy@chinamobile.com ","21/1/22: 23.700-60 added;; 12/3/22: 0%->15; 4/6/22: 15%->40; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211646->SP-220705; 12/9/22: 40%->75; 10/12/22: 75%->100","23.700-60",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1034,980016,"   (Stage 2 for XRM) Architecture Enhancements for XR (Extended Reality) and media service","XRM",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230092",null,"Dan WANG, China Mobile","wangdanyjy@chinamobile.com ","15/3/23: WID:SP-221326->SP-230092; 15/3/23: 0%->55; 8/6/23: 55%->98; 7/9/23: 98%->100","23.501; 23.502; 23.503 ",98,50,null,null,"Fri 09/12/22","Thu 07/09/23"]
[1035,1030048,"   CT1 aspects of XRM","XRM",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-240081",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:20%->65%6/6/23: WID: CP-230115->CP-231196; 2/4/24: 0%->98","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"Fri 09/12/22","Tue 02/04/24"]
[1036,990006,"   CT3 aspects of XRM","XRM",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-240081",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:20%->65%6/6/23: WID: CP-230115->CP-231196","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1037,990084,"   CT4 aspects of XRM","XRM",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-240081",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:0%->65%6/6/23: WID: CP-230115->CP-231196","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1038,950012,"Study on immersive Real-time Communication for WebRTC Phase 2","FS_eiRTCW",1,"Rel-18","S4","Thu 10/03/22","Sun 03/03/24",1,"SP-230166",null,"Yoshihiro INOUE, NTT","Yoshihiro.inoue@ntt-at.co.jp","4/6/22: 0%->10; 17/8/22: FS_iRTCW_Ph2->FS_eiRTCW ; 12/9/22: 10%->30; 16/3/23: WID:SP-220239->SP-230166; 16/3/23: FCD:06/06/2023->3/3/24. Rapporteur changed from Naotaka MORITA, NTT .; 17/3/23: 30%->35; 17/3/23: FCD:03/03/2024->/24; 8/6/23: 35%->45; 7/9...","26.930",95,48,null,null,"Thu 10/03/22","Thu 14/03/24"]
[1039,950014,"Immersive Real-time Communication for WebRTC ","iRTCW",1,"Rel-18","S4","Tue 15/03/22","Thu 06/06/24",1,"SP-230977",null,"Kyunghun Jung, Facebook ","kyunghun@fb.com ","5/4/22: 26.113 added;; 4/6/22: 0%->5; 12/9/22: 5%->10; 11/12/22: 10%->20; 11/12/22: WID:SP-220241->SP-221032; 17/3/23: 20%->30; 8/6/23: 30%->55; 7/9/23: WID:SP-221032->SP-230977; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 55%->60; 14/3/24: FCD:03/03/2024->/...","26.113",95,48,null,null,"Thu 10/03/22","Thu 13/06/24"]
[1040,950013,"Study on Smartly Tethering AR Glasses ","FS_SmarTAR",1,"Rel-18","S4","Thu 10/03/22","Tue 06/06/23",1,"SP-220240",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","; 5/4/22: 26.806 added;; 4/6/22: 0%->30; 12/9/22: 30%->40; 12/9/22: FCD:10/03/2023->03/23; 11/12/22: 40%->60; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100","26.998 ; 26.806",95,48,null,null,"Thu 10/03/22","Thu 08/06/23"]
[1041,950015,"Media Capabilities for Augmented Reality ","MeCAR",1,"Rel-18","S4","Thu 10/03/22","Sun 03/03/24",1,"SP-220242",null,"Emmanuel Thomas, Xiaomi ","thomase@xiaomi.com ","; 5/4/22: 26.119 added;; 4/6/22: 0%->8; 12/9/22: 8%->15; 11/12/22: 15%->30; 11/12/22: FCD:10/03/2023->12/23; 17/3/23: 30%->40; 8/6/23: 40%->60; 7/9/23: 60%->65; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 65%->80; 8/12/23: FCD:03/03/2024->/2024; 14/3/24: 80%->","26.511; 26.117; 26.925; 26.XXX ; 26.119",95,48,null,null,"Thu 10/03/22","Thu 14/03/24"]
[1042,960042,"IMS-based AR Conversational Services ","IBACS",1,"Rel-18","S4","Fri 03/06/22","Thu 06/06/24",1,"SP-230165",null,"Gunkel, Simon, KPN N.V. ","Simon.Gunkel@tno.nl ","3/8/22: 26.264 added; 17/8/22: IMS4AR->IBACS; 17/8/22: WID:SP-220609->SP-220668; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->12/23; 16/3/23: WID:SP-220668->SP-230165; 17/3/23: 15%->20; 8/6/23: 20%->30; 8/6/23: FCD:12/12/2023->03/20; 8/1...","26.264",96,49,null,null,"Fri 03/06/22","Thu 13/06/24"]
[1043,960044,"Generic architecture for RT and AR/MR ","GA4RTAR",1,"Rel-18","S4","Fri 03/06/22","Tue 06/06/23",1,"SP-220672",null,"Hakju Ryan Lee, Samsung ","hakju00.lee@samsung.com ","17/8/22: GA4RTARMR-> GA4RTAR; 17/8/22: WID:SP-220611->SP-220672; 12/9/22: 0%->25; 11/12/22: 25%->60; 11/12/22: FCD:08/12/2023->03/23; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100",null,96,49,null,null,"Fri 03/06/22","Thu 08/06/23"]
[1044,960046,"Real-time Transport Protocol Configurations ","5G_RTP",1,"Rel-18","S4","Fri 03/06/22","Sun 03/03/24",1,"SP-230541",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","3/8/22: 26.522 added; 17/8/22: RTPconfig->5G_RTP; 12/9/22: 0%->3; 11/12/22: 3%->7; 11/12/22: FCD:08/06/2023->/23; 17/3/23: 7%->15; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 15%->35; 8/6/23: FCD:12/12/2023->03/20; 8/6/23: WID:SP-220613->SP-230541; 7/9/23:...","26.522",96,49,null,null,"Fri 03/06/22","Thu 14/03/24"]
[1045,830005,"Terminal Audio quality performance and Test methods for Immersive Audio Services","ATIAS",1,"Rel-18","S4","Thu 07/03/19","Thu 06/06/24",1,"SP-190040",null,"Stéphane Ragot, Orange","stephane.ragot@orange.com ","31/5/19: 0%->10; 25/3/20: 10%->15; 5/12/20: 15%->20; 5/12/20: FCD:04/12/2020->12/20. 12/21: Rel-17->Rel-18; 4/6/22: 20%->; 11/12/22: 20%->25; 11/12/22: FCD:02/12/2022->12/23; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->50; 7/9/23: FCD:12/12/2023->/...","26.260; new",83,42,null,null,"Thu 14/03/19","Thu 13/06/24"]
[1046,1030047,"EVS Codec Extension for Immersive Voice and Audio Services","IVAS_Codec",1,"Rel-18",null,"Fri 08/09/17","Thu 06/06/24",1,"SP-220608",null,"Bin Wang, Huawei Technologies Co Ltd","binbin.wang@huawei.com","15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35; 12/9/22: 35%->40; 11/12/22: 40%->45; ...","26.114; new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997",77,39,null,null,"Fri 08/09/17","Fri 08/12/23"]
[1047,770024,"   EVS Codec Extension for Immersive Voice and Audio Services","IVAS_Codec",2,"Rel-18","S4","Fri 08/09/17","Thu 06/06/24",1,"SP-220608",null,"Bin Wang, Huawei Technologies Co Ltd","binbin.wang@huawei.com","15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35; 12/9/22: 35%->40; 11/12/22: 40%->45; ...","26.114; new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997",77,39,null,null,"Fri 08/09/17","Thu 13/06/24"]
[1048,1030025,"   CT3 aspects of IVAS_Codec","IVAS_Codec",2,"Rel-18","C3","Sun 03/03/24","Thu 06/06/24",1,"CP-240021",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,"23.333, 29.333, 23.334, 29.334, 29.162, 29.238, 29.163, 29.332, 29.292, 29.232, 24.229",77,39,null,null,"Fri 08/09/17","Fri 08/12/23"]
[1049,1030001,"   CT4 aspects of IVAS_Codec","IVAS_Codec",2,"Rel-18","C4","Sun 03/03/24","Thu 06/06/24",1,"CP-240021",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,"23.333, 29.333, 23.334, 29.334, 29.162, 29.238, 29.163, 29.332, 29.292, 29.232, 24.229",77,39,null,null,"Fri 08/09/17","Fri 08/12/23"]
[1050,990025,"Immersive Audio for Split Rendering Scenarios ","ISAR",1,"Rel-18","S4","Thu 16/03/23","Thu 06/06/24",1,"SP-231291",null,"Stefan Bruhn, Dolby Laboratories Inc ","stefan.bruhn@dolby.com ","; 8/6/23: 0%->10; 8/6/23: 26.566 added;; 8/6/23: 26.866 added;; 8/6/23: 26.865 added;; 7/9/23: 10%->15; 8/12/23: 15%->25; 8/12/23: WID:SP-230167->SP-231291; 14/3/24: 25%->35; 14/3/24: FCD:03/03/2024->/24; 3/4/24: 26.249 added; 26.996 added;; 13/6/24: 35%","26.119 ; 26.566; 26.866; 26.865; 26.249; 26.996",99,50,null,null,"Thu 16/03/23","Thu 13/06/24"]
[1051,960045,"Split Rendering Media Service Enabler ","SR_MSE",1,"Rel-18","S4","Fri 03/06/22","Thu 06/06/24",1,"SP-231291",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi@qti.qualcomm.com ","3/8/22: 26.565 added;; 17/8/22: WID:SP-220612->SP-220685; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->09/23; 17/3/23: 15%->25; 17/3/23: FCD:09/09/2023->12/23; 8/6/23: 25%->40; 8/6/23: FCD:12/12/2023->03/20; 7/9/23: 40%->50; 8/12/23: 50%...","26.565",96,49,null,null,"Fri 03/06/22","Thu 13/06/24"]
[1052,960049,"Study on AR and MR QoE Metrics ","FS_ARMRQoE",1,"Rel-18","S4","Fri 03/06/22","Sun 03/03/24",1,"SP-220708",null,"Shuai Gao, chinaunicom ","gaos30@chinaunicom.cn ","13/7/22: 26.812 added;; 17/8/22: WID:SP-220616->SP-220708; 12/9/22: 0%->5; 11/12/22: 5%->10; 17/3/23: 10%->15; 8/6/23: 15%->27; 7/9/23: 27%->50; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 50%->65; 14/3/24: 65%->100","26.812",96,49,null,null,"Fri 03/06/22","Thu 14/03/24"]
[1053,960050,"Study on Audio Aspects for Glasses-type AR/MR Devices ","FS_Audio_5GSTAR",1,"Rel-18","S4","Fri 03/06/22","Thu 08/12/22",1,"SP-220617",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","17/8/22: FS_ARMRglass->FS_Audio_5GSTAR; 12/9/22: 0%->5; 11/12/22: 5%->100","26.998; ",96,49,null,null,"Fri 03/06/22","Sun 11/12/22"]
[1054,0,"Rel-18 Transportations (Railways, V2X)","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1055,880036,"Study on Off-Network for Rail","FS_OffNetRail",1,"Rel-18","S1","Thu 25/06/20","Fri 10/12/21",1,"SP-200572",null,"Guillaume Gach","Ext.gach <at> uic.org ","28/7/20: 22.990 added;; 12/9/20: 0%->10; 5/12/20: 10%->30; 19/3/21: FCD:17/03/2021->12/21; 19/3/21: 30%->50; 13/9/21: 50%->90; 10/12/21: 90%->100","22.990",88,45,null,null,"Thu 25/06/20","Fri 10/12/21"]
[1056,880034,"Study of Interconnection and Migration Aspects for Railways ","FS_IRail",1,"Rel-18","S6","Thu 25/06/20","Thu 16/09/21",1,"SP-200336",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-90 added;; 21/3/21: 10%->15; 11/6/21: 15%->30; 13/9/21: 30%->60; 13/12/21: 60%->85; 12/3/22: 85%->100","23.700-90",88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[1057,980122,"Interconnection and Migration Aspects for Railways ","IRail",1,"Rel-18",null,"Thu 03/03/22","Tue 12/12/23",1,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"Thu 10/03/22","Mon 12/09/22"]
[1058,950025,"   Stage 2 of Irail","IRail",2,"Rel-18","S6","Thu 03/03/22","Mon 12/12/22",1,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 4/6/22: 0%->40; 12/9/22: 40%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->100","23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"Sun 11/12/22","Thu 08/06/23"]
[1059,980070,"   CT1 aspects of eMCSMI_IRail","eMCSMI_IRail",2,"Rel-18","C1","Fri 16/12/22","Tue 12/12/23",1,"CP-240270",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com","6/6/23: Compl:10%->15%","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283",95,48,null,null,"Thu 10/03/22","Tue 06/06/23"]
[1060,980071,"   deleted - CT4 aspects of eMCSMI_IRail","eMCSMI_IRail",2,"Rel-18","C4","Fri 16/12/22","Tue 12/12/23",1,"CP-240270",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com","2/4/24: deleted at 100%","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283",95,48,null,null,"Thu 10/03/22","Tue 02/04/24"]
[1061,900026,"Study on FRMCS Phase 4","FS_FRMCS_Ph4",1,"Rel-18","S1","Fri 04/12/20","Fri 10/12/21",1,"SP-220436",null,"Guillaume Gach; UIC ","Guillaume Gach; gach <at> uic.org ","22.989 ; 19/3/21: FCD:12/09/2021->12/21; 19/3/21: 0%->20; 13/9/21: 20%->80; 10/12/21: 80%->100; 21/6/22: WID:SP-201038->SP-220436. FS_eFRMCS -> FS_FRMCS_Ph4",null,90,46,null,null,"Fri 04/12/20","Tue 21/06/22"]
[1062,930014,"Study on enhancements to application layer support for V2X services; Phase 2 ","FS_eV2XAPP2",1,"Rel-18","S6","Mon 13/09/21","Mon 12/09/22",1,"SP-220466",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 22/3/22: 23.700-64 added;; 4/6/22: 30%->65; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210956->SP-220466; 12/9/22: 65%->85; 11/12/22: 85%->100","23.700-64",93,47,null,null,"Mon 13/09/21","Sun 11/12/22"]
[1063,980125,"Application layer support for V2X services; Phase 3","V2XAPP_Ph3",1,"Rel-18",null,"Fri 09/09/22","Sun 03/03/24",1,"SP-220916",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ",null,"23.286; 23.434 ",97,49,null,null,"Sun 11/09/22","NA"]
[1064,970039,"   Stage 2 of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","S6","Fri 09/09/22","Tue 06/06/23",1,"SP-221229",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 11/12/22: 0%->45; 9/1/23: WID:SP-220916->SP-221229; 17/3/23: 45%->75; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","23.286; 23.434 ",97,49,null,null,"Sun 11/12/22","Thu 08/06/23"]
[1065,980072,"   CT1 aspects of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-233214",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","6/6/23: Compl:0%->20%; 30/6/23: WID:CP-223107->CP-231285","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558",97,49,null,null,"Sun 11/09/22","Fri 30/06/23"]
[1066,980073,"   CT3 aspects of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-233214",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558",97,49,null,null,"Sun 11/09/22","NA"]
[1067,1000043,"MBS support for V2X services ","TEI18_MBS4V2X",1,"Rel-18",null,"Mon 12/09/22","Sun 03/03/24",1,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ","; 22/3/23: 0%->100","23.287; 23.501 ",97,49,null,null,"Sun 11/09/22","Wed 22/03/23"]
[1068,970003,"   (Stage 2 of) MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","S2","Mon 12/09/22","Fri 03/03/23",1,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ","; 22/3/23: 0%->100","23.287; 23.501 ",97,49,null,null,"Sun 11/09/22","Wed 22/03/23"]
[1069,1000022,"   CT1 aspects of MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","C1","Wed 07/06/23","Sun 03/03/24",1,"CP-231357",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ",null,"24.587; 24.588; 31.102 ",100,51,null,null,"Wed 07/06/23","NA"]
[1070,1010021,"   CT6 aspects of MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","C6","Wed 07/06/23","Sun 03/03/24",1,"CP-231357",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ",null,"24.587; 24.588; 31.102 ",101,51,null,null,"Wed 07/06/23","NA"]
[1071,950079,"Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh",1,"Rel-18",null,"Tue 15/03/22","Thu 12/12/24",0.75,"RP-222272",null,"Samsung ",null,"compare REL-17 WI NR_HST_FR2 ; 23/9/22: WID:RP-220985->RP-222272",null,95,48,null,null,"Tue 05/04/22","Fri 23/09/22"]
[1072,950179,"   Core part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Core",2,"Rel-18","R4","Tue 15/03/22","Fri 08/09/23",1,"RP-222272","RP- 241272","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","compare REL-17 WI NR_HST_FR2 ; 6/6/22: CD:15/09/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/202...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1073,950279,"   Perf. part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Perf",2,"Rel-18","R4","Wed 16/03/22","Thu 06/06/24",1,"RP-222272","RP- 241272","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:24/03/2023->03/20 ; ...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1074,1030071,"   UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.38,"RP-240371","RP-251018","Samsung ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241278; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->36%; Stat Rep: RP-241278->RP-241981; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:36%->38%; Stat Rep: RP-241981->RP-242595; ; 6/3/25: FCD:28/05/2025->12/12/2025;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1075,0,"Rel-18 User Plane traffic and services","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1076,920036,"Evolution of IMS Multimedia Telephony Service ","eMMTEL",1,"Rel-18",null,"Thu 19/09/19","Fri 12/12/25",0.95,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com ",null,"22.261;22.173 ",92,47,null,null,"Fri 11/06/21","NA"]
[1077,850042,"   Study on evolution of IMS multimedia telephony service ","FS_MMTELin5G",2,"Rel-18","S1","Thu 19/09/19","Wed 08/09/21",1,"SP-190836",null,"Yan Di, China Mobile","yandi@chinamobile.com ","; 8/10/19: 22.873 added;; 6/12/19: 0%->10; 12/9/20: 10%->15; 5/12/20: 15%->40; 19/3/21: 40%->75; 19/3/21: FCD:11/12/2020->09/21; 11/6/21: 75%->95; 13/9/21: 95%->100","New ; 22.873",85,43,null,null,"Fri 13/09/19","Mon 13/09/21"]
[1078,920029,"   Stage 1 of Evolution of IMS Multimedia Telephony Service ","eMMTEL",2,"Rel-18","S1","Fri 11/06/21","Fri 10/12/21",1,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com","; 13/9/21: 0%->100","22.261;22.173 ",92,47,null,null,"Fri 11/06/21","Mon 13/09/21"]
[1079,940066,"   Study on system architecture for next generation real time communication services ","FS_NG_RTC",2,"Rel-18","S2","Mon 20/12/21","Fri 03/03/23",1,"SP-220288",null,"Yi Jiang ","jiangyi at chinamobile dot com ","21/1/22: 23.700-87 added;; 12/3/22: 0%->20; 5/4/22: WID:SP-211644->SP-220288; 4/6/22: 20%->55; 12/9/22: 55%->79; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 79%->85; 15/3/23: 85%->100; 16/3/23: FCD:12/12/2022->/23","23.700-87",94,48,null,null,"Sun 19/12/21","Thu 16/03/23"]
[1080,970014,"   System architecture for Next Generation Real time Communication services ","NG_RTC",2,"Rel-18","S2","Mon 12/09/22","Tue 06/06/23",1,"SP-230098",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 15/3/23: WID:SP-220804->SP-230098; 15/3/23: 0%->60; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.228; 23.502 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1081,990023,"   CT1 aspects of NG_RTC","NG_RTC",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 24.186 added;6/6/23: Compl:0%->15%","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 24.186",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1082,990086,"   CT3 aspects of NG_RTC","NG_RTC",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,"24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333",97,49,null,null,"Sun 11/09/22","NA"]
[1083,990087,"   CT4 aspects of NG_RTC","NG_RTC",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 29.176 added;; 31/3/23: 29.175 added;6/6/23: Compl:0%->25%; 4/1/24: 29.330 added;","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 29.176; 29.175; 29.330",97,49,null,null,"Sun 11/09/22","Thu 04/01/24"]
[1084,1030027,"   CT6 aspects of NG_RTC","NG_RTC",2,"Rel-18","C6","Mon 13/03/23","Sun 03/03/24",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 29.176 added;; 31/3/23: 29.175 added;6/6/23: Compl:0%->25%; 4/1/24: 29.330 added;","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 29.176; 29.175; 29.330",97,49,null,null,"Sun 11/09/22","Thu 04/01/24"]
[1085,960032,"   Study on security support for Next Generation Real Time Communication services ","FS_NG_RTC_SEC",2,"Rel-18","S3","Thu 02/06/22","Tue 06/06/23",1,"SP-220530",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ","13/7/22: 33.890 added;; 12/9/22: 0%->40; 11/12/22: 40%->70; 17/3/23: 70%->90; 8/6/23: 90%->100","33.890",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1086,990038,"   Security support for Next Generation Real Time Communication services ","NG_RTC_SEC",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230151",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ","; 15/3/24: 0%->100","33.328 ",99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[1087,1050133,"   UE Conformance - IMS Data Channel for NG RTC (Real Time Communication) ","NG_RTC_IMS_dataCH-UEConTest",2,"Rel-18","R5","Mon 09/09/24","Fri 12/12/25",0.71,"RP-242078","RP-251491","Huawei ",null,"6/12/24: Compl:0%->5%; Stat Rep: ->RP-243093; ; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:5%->21%; Stat Rep: RP-243093->RP-250451; ; 6/6/25: Compl:21%->71%; Stat Rep: RP-250451->RP-251491; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[1088,1000008,"Charging Aspects of IMS Data Channel ","IDC_CH",1,"Rel-18","S5","Thu 08/06/23","Sun 03/03/24",1,"SP-230621",null,"Chen, Ai, China Mobile, ","chenai at chinamobile dot com ","; 8/12/23: 0%->40; 14/3/24: 40%->100","32.260; 32.255; 32.291; 32.298 ",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[1089,990111,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 ","ATSSS_Ph3",1,"Rel-18",null,"Mon 20/12/21","Tue 03/03/26",0.77,"SP-221334",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","; 9/1/23: WID:SP-220813->SP-221334","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Mon 09/01/23"]
[1090,940070,"   Study on Access Traffic Steering, Switching and Splitting support in the 5G system architecture; Phase 3 ","FS_ATSSS_Ph3",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211612",null,"Salkintzis, Apostolis, Lenovo, ","y1026c@lenovo.com ","21/1/22: 23.700-53 added;; 12/3/22: 0%->20; 4/6/22: 20%->70; 12/9/22: 70%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-53",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1091,970023,"   Stage 2 of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","S2","Mon 12/09/22","Tue 06/06/23",1,"SP-221334",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","; 9/1/23: WID:SP-220813->SP-221334; 15/3/23: 0%->85; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1092,990021,"   CT1 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","6/6/23: Compl:0%->50%","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1093,990089,"   CT3 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","9/6/23: 0%->60","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1094,990090,"   CT4 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","6/6/23: Compl:5%->50%","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1095,1070061,"   UE Conformance - Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 ","ATSSS_Ph3-UEConTest",2,"Rel-18","R5","Mon 03/03/25","Tue 03/03/26",0.05,"RP-250067","RP-250896","China Telecom ",null,"6/6/25: Compl:0%->5%; Stat Rep: ->RP-250896; ",null,107,54,null,null,"Wed 26/03/25","Fri 06/06/25"]
[1096,940076,"Study on UPF enhancement for Exposure And SBA ","FS_UPEAS",1,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220417",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","21/1/22: 23.700-62 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211652->SP-220417; 12/9/22: 60%->80; 10/12/22: 80%->98; 15/3/23: 98%->100","23.700-62",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[1097,990112,"UPF enhancement for Exposure and SBA ","UPEAS",1,"Rel-18",null,"Mon 12/09/22","Sun 03/03/24",1,"SP-220809",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","; 10/12/22: 0%->20","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Sat 10/12/22"]
[1098,970019,"   Stage 2 of UPEAS","UPEAS",2,"Rel-18","S2","Mon 12/09/22","Tue 06/06/23",1,"SP-230103",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","; 10/12/22: 0%->20; 15/3/23: WID:SP-220809->SP-230103; 15/3/23: 20%->75; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1099,990002,"   CT4 aspects of UPF enhancement for exposure and SBA","UPEAS",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-240022",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com","17/3/23: 10%->406/6/23: Compl:40%->70%","29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1100,990092,"   CT3 aspects of UPF enhancement for exposure and SBA","UPEAS",2,"Rel-18","C3","Tue 18/04/23","Sun 03/03/24",1,"CP-240022",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com","9/6/23: 0%->90","29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1101,930027,"Tactile and multi-modality communication services ","TACMM",1,"Rel-18",null,"Fri 04/12/20","Fri 10/12/21",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ",null,"22.261 ",93,47,null,null,"Fri 10/09/21","NA"]
[1102,900027,"   Study on TACMM","FS_TACMM",2,"Rel-18","S1","Fri 04/12/20","Fri 11/06/21",1,"SP-210209",null,"Shi, Xiaonan, China Mobile","shixiaonan@chinamobile.com","10/2/21: 22.847 added;; 19/3/21: 0%->30; 11/6/21: 30%->40; 13/9/21: 40%->85; 14/9/21: WID:SP-201039->SP-210209; 10/12/21: 85%->100","22.847",90,46,null,null,"Fri 04/12/20","Fri 10/12/21"]
[1103,930020,"   Stage 1 of TACMM","TACMM",2,"Rel-18","S1","Fri 10/09/21","Fri 10/12/21",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 10/12/21: 0%->100","22.261 ",93,47,null,null,"Fri 10/09/21","Fri 10/12/21"]
[1104,0,"Rel-18 Edge computing","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1105,980132,"Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",1,"Rel-18",null,"Fri 09/09/22","Tue 12/12/23",1,"SP-221231",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ",null,null,97,49,null,null,"Sun 11/09/22","Mon 12/09/22"]
[1106,970040,"   (Stage 2 of EDGEAPP_Ph2) Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",2,"Rel-18","S6","Fri 09/09/22","Fri 03/03/23",1,"SP-221231",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ","; 12/9/22: 0%->5; 11/12/22: 0%->30; 9/1/23: WID:SP-220917->SP-221231; 17/3/23: 30%->70; 8/6/23: 70%->100","23.558; 23.958",97,49,null,null,"Sun 11/12/22","Thu 08/06/23"]
[1107,980074,"   CT1 aspects of EDGEAPP_Ph2","EDGEAPP_Ph2",2,"Rel-18","C1","Thu 15/12/22","Tue 12/12/23",1,"CP-233114",null,"Narendranath Durga Tangudu","n.tangudu@samsung.com","; 6/6/23: Compl:5%->40%; 6/6/23: WID: CP-223207->CP-231197","24.558; 29.558; 29.222",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1108,980075,"   CT3 aspects of EDGEAPP_Ph2","EDGEAPP_Ph2",2,"Rel-18","C3","Thu 15/12/22","Tue 12/12/23",1,"CP-233114",null,"Narendranath Durga Tangudu","n.tangudu@samsung.com","; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-223207->CP-231197","24.558; 29.558; 29.222",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1109,960011,"Edge Application Standards in 3GPP and alignment with External Organizations ","EDGEAPP_EXT",1,"Rel-18","S6","Thu 02/06/22","Tue 12/12/23",1,"SP-220990",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com","13/7/22: 23.958 added;; 12/9/22: 0%->5; 12/9/22: WID:SP-220468->SP-220912; 17/3/23: 5%->10; 8/6/23: 10%->50; 7/9/23: 50%->65; 13/9/23: FCD:06/06/2023->12/20; 13/9/23: WID:SP-220990->SP-231156; 15/3/24: 65%->98; 13/6/24: 98%->100; 13/6/24: WID:SP-231156->S","23.958",96,49,null,null,"Thu 02/06/22","Thu 13/06/24"]
[1110,920017,"Study on enhanced architecture for enabling Edge Applications ","FS_eEDGEAPP",1,"Rel-18","S6","Fri 11/06/21","Fri 10/06/22",1,"SP-211510",null,"Gupta, Nishant, Samsung ","nishant.gup@samsung.com ","2/7/21: 23.700-98 added;; 13/9/21: 0%->10; 13/12/21: 10%->45; 13/12/21: WID:SP-210479->SP-211510; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: 45%->55; 4/6/22: 55%->75; 12/9/22: 75%->90; 11/12/22: 90%->100","23.700-98",92,47,null,null,"Fri 11/06/21","Sun 11/12/22"]
[1111,980123,"Edge Computing Phase 2","FS_EDGE_Ph2",1,"Rel-18",null,"Mon 20/12/21","Thu 06/06/24",1,null,null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"Sun 11/12/22","NA"]
[1112,950049,"   Study on Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220070",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"Sun 19/12/21","Sat 12/03/22"]
[1113,940059,"   Study on Stage 2 of Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220352",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070; 4/6/22: 13%->55; 12/9/22: 55%->83; 10/12/22: 83%->100","23.700-48",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1114,950023,"   Study on Security of Edge Computing phase 2 ","FS_EDGE_Ph2",2,"Rel-18","S3","Thu 10/03/22","Mon 12/12/22",1,"SP-220201",null,"Bo Zhang, Huawei ","zhangbo6@huawei.com ","4/6/22: 0%->30; 13/7/22: 33.739 added;; 12/9/22: 30%->40; 11/12/22: 40%->70; 17/3/23: 70%->80; 8/6/23: 80%->90; 15/3/24: 90%->100","33.739",95,48,null,null,"Thu 10/03/22","Fri 15/03/24"]
[1115,970026,"   (stage 2 of) Edge Computing Phase 2 ","EDGE_Ph2",2,"Rel-18","S2","Fri 23/09/22","Tue 06/06/23",1,"SP-230112",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","; 10/12/22: 0%->15; 9/1/23: WID:SP-220987->SP-221337; 15/3/23: WID:SP-221337->SP-230112; 15/3/23: 15%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100","23.548; 23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1116,1040038,"   CT1 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C1","Fri 16/12/22","Thu 06/06/24",1,"CP-241027",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","9/6/23: 30%->35","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1117,980076,"   CT3 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C3","Fri 16/12/22","Thu 06/06/24",1,"CP-241027",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","9/6/23: 30%->35","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1118,980077,"   CT4 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C4","Fri 16/12/22","Thu 06/06/24",1,"CP-241027",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","; 6/6/23: Compl:20%->45%; 16/7/24: WID:CP-233026->CP-241027","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"Sun 11/09/22","Tue 16/07/24"]
[1119,990039,"   Security Aspects of Support for Edge Computing in 5GC phase 2 ","EDGE_Ph2",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230366",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","31/3/23: WID:SP-230152->SP-230366; 7/9/23: 0%->95; 15/3/24: 95%->100","33.558; 33.501 ",99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[1120,0,"Rel-18 Non-Public Networks","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1121,920038,"5G Networks Providing Access to Localized Services ","PALS",1,"Rel-18",null,"Wed 16/09/20","Wed 08/09/21",1,"SP-210522",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ",null,"22.261 ",92,47,null,null,"Fri 11/06/21","NA"]
[1122,890023,"   Study on PALS ","FS_PALS",2,"Rel-18","S1","Wed 16/09/20","Fri 11/06/21",1,"SP-200799",null,"Jack Nasielski ","jackn <at> qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: 35%->77; 11/6/21: 77%->95; 13/9/21: 95%->100","22.844",89,45,null,null,"Thu 10/09/20","Mon 13/09/21"]
[1123,920031,"   Stage 1 of PALS ","PALS",2,"Rel-18","S1","Fri 11/06/21","Wed 08/09/21",1,"SP-210588",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ","; 10/12/21: 0%->100","22.261 ",92,47,null,null,"Fri 11/06/21","Fri 10/12/21"]
[1124,980128,"Non-Public Networks Phase 2 ","eNPN_Ph2",1,"Rel-18",null,"Mon 13/12/21","Fri 12/12/25",0.87,"SP-220805",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","; 10/12/22: 0%->50","23.501; 23.502; 23.402 ",97,49,null,null,"Sun 11/09/22","Sat 10/12/22"]
[1125,940075,"   Study on enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220418",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","21/1/22: 23.700-08 added;; 12/3/22: 0%->10; 4/6/22: 10%->50; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211656->SP-220418; 12/9/22: 50%->75; 12/9/22: FCD:12/12/2022->12/22; 10/12/22: 75%->98; 15/3/23: 98%->100","23.700-08",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[1126,970015,"   Stage 2 of Non-Public Networks Phase 2 ","eNPN_Ph2",2,"Rel-18","S2","Mon 12/09/22","Tue 06/06/23",1,"SP-230096",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","; 10/12/22: 0%->50; 9/1/23: WID:SP-220805->SP-221340; 15/3/23: 50%->90; 15/3/23: WID:SP-221340->SP-230096; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 90%->100","23.501; 23.502; 23.402 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1127,960033,"   Study on security aspects of enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2_SEC",2,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220531",null,"Jost, Christine, Ericsson, ","(christine.jost@ericsson.com) ","13/7/22: 33.858 added;; 12/9/22: 0%->10; 11/12/22: 10%->60; 17/3/23: 60%->78; 8/6/23: 78%->99; 15/3/24: 99%->100","33.858",96,49,null,null,"Thu 02/06/22","Fri 15/03/24"]
[1128,990043,"   Security aspects of support of Non-Public Networks phase 2 ","eNPN_Ph2",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230156",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 8/6/23: 0%->65; 7/9/23: 65%->90; 14/3/24: 90%->100","33.501 ",99,50,null,null,"Thu 16/03/23","Thu 14/03/24"]
[1129,980078,"   CT1 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 6/6/23: Compl:33%->60%; 30/6/23: WID:CP-223104->CP-231286","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"Sun 11/09/22","Fri 30/06/23"]
[1130,980079,"   CT3 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C3","Thu 15/12/22","Sun 03/03/24",1,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 9/6/23: 30%->60","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1131,980080,"   CT4 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C4","Thu 15/12/22","Sun 03/03/24",1,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 6/6/23: Compl:50%->65%","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1132,940043,"   Study on Charging Aspects for Enhanced Support of Non-Public Networks ","FS_eNPN_CH",2,"Rel-18","S5","Mon 13/12/21","Fri 03/03/23",1,"SP-211447",null,"Chen, Ai, China Mobile ","chenai@chinamobile.com ","7/1/22: 28.828 added;; 12/9/22: 0%->60; 11/12/22: 60%->75; 17/3/23: 75%->100","28.828",94,48,null,null,"Mon 13/12/21","Fri 17/03/23"]
[1133,990028,"   Charging Aspects for Enhanced Support of Non-Public Networks ","eNPN_CH",2,"Rel-18","S5","Thu 16/03/23","Sun 03/03/24",1,"SP-230177",null,"Chen, Ai, China Mobile ","chenai at chinamobile dot com ","; 8/6/23: 0%->10; 7/9/23: 10%->30; 8/12/23: 30%->65; 14/3/24: 65%->100","32.255; 32.256; 28.203; 32.291; 32.298 ",99,50,null,null,"Thu 16/03/23","Thu 14/03/24"]
[1134,991138,"   Core part: Non-Public Networks Phase 2: NG-RAN aspects","eNPN_Ph2-NGRAN-Core",2,"Rel-18","R3","Mon 06/03/23","Tue 12/12/23",1,"RP-233569","RP-233567","Shengnan Liu, China Telecom","liushn@chinatelecom.cn","; 7/6/23: Compl:0%->97%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:97%->100%; WID: RP-230788->RP-231185; Stat Rep: ->RP-232261; Rapporteur: China Telecom->Shengnan Liu, China Telecom; Rap eMail: ->liushn@chinatelecom.cn; ; 21/9/23: FCD:22/09/2023->12/1...",null,99,50,null,null,"Fri 07/04/23","Tue 02/01/24"]
[1135,1040106,"   UE Conformance - Non-Public Networks Phase 2: NG-RAN aspects plus CT1 aspects ","eNPN_Ph2-NGRAN_plus_CT1-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 12/12/25",0.32,"RP-241307","RP-251463","China Telecom ",null,"6/12/24: Compl:0%->5%; Stat Rep: ->RP-242870; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:5%->17%; Stat Rep: RP-242870->RP-250379; ; 6/6/25: Compl:17%->32%; Stat Rep: RP-250379->RP-251463; ",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1136,0,"Rel-18 AM and UE Policy","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1137,840020,"Study on enhancement of 5G UE Policy ","FS_eUEPO",1,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211649",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","26/6/19: 23.760 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940072, temporarily mistakenly added as FS_eUEPO_Ph2; WID:SP-190449->SP-211649; 12/3/22: 0%->25; 4/6/22: 25%->70; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 70%->80; 10/12/22: ...","New ; 23.760",84,43,null,null,"Fri 31/05/19","Wed 15/03/23"]
[1138,980114,"Enhancement of 5G UE Policy ","eUEPO",1,"Rel-18",null,"Fri 09/09/22","Thu 06/06/24",1,"SP-220980",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"Fri 23/09/22","NA"]
[1139,970025,"   (Stage 2 of) Enhancement of 5G UE Policy ","eUEPO",2,"Rel-18","S2","Fri 09/09/22","Tue 06/06/23",1,"SP-230094",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","; 9/1/23: WID:SP-220980->SP-221342; 15/3/23: 0%->65; 15/3/23: WID:SP-221342->SP-230094; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sat 10/12/22","Thu 08/06/23"]
[1140,980081,"   CT1 aspects of eUEPO","eUEPO",2,"Rel-18","C1","Fri 16/12/22","Thu 06/06/24",1,"CP-241076",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192; 23/7/24: WID:CP-240080->CP-241076","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"Fri 23/09/22","Tue 23/07/24"]
[1141,980082,"   CT3 aspects of eUEPO","eUEPO",2,"Rel-18","C3","Fri 16/12/22","Thu 06/06/24",1,"CP-241076",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"Fri 23/09/22","Tue 06/06/23"]
[1142,990093,"   CT4 aspects of eUEPO","eUEPO",2,"Rel-18","C4","Fri 16/12/22","Thu 06/06/24",1,"CP-241076",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"Fri 23/09/22","Tue 06/06/23"]
[1143,1000041,"Spending Limits for AM and UE Policies in the 5GC ","TEI18_SLAMUP",1,"Rel-18",null,"Mon 12/09/22","Tue 12/12/23",1,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ","; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20","23.503; 23.501; 23.502 ",97,49,null,null,"Sun 11/09/22","Wed 22/03/23"]
[1144,970004,"   Stage 2 of TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","S2","Mon 12/09/22","Tue 06/06/23",1,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ","; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20; 8/6/23: 80%->100","23.503; 23.501; 23.502 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1145,1000040,"   CT3 aspects on TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","C3","Wed 07/06/23","Tue 12/12/23",1,"CP-233125",null,"SUN, Yue, China Telecom ","suny20@chinatelecom.cn ",null,"29.513; 29.519; 29.594 ",100,51,null,null,"Wed 07/06/23","NA"]
[1146,1020048,"   CT4 aspects on TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","C4","Wed 07/06/23","Tue 12/12/23",1,"CP-233125",null,"SUN, Yue, China Telecom ","suny20@chinatelecom.cn ",null,"29.513; 29.519; 29.594 ",102,52,null,null,"Wed 07/06/23","NA"]
[1147,970001,"Rel-18 Enhancements of UE Policy","UEP18",1,"Rel-18",null,"Thu 07/03/19","Wed 13/12/23",1,"CP_233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,"29.525; 29.507; 29.513; 29.518",97,49,null,null,"Thu 10/03/22","NA"]
[1148,970045,"   CT3 aspects of UEP18","UEP18",2,"Rel-18","C3","Thu 07/03/19","Tue 12/12/23",1,"CP-233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:20%->50%","29.525; 29.507; 29.513",97,49,null,null,"Wed 07/09/22","Tue 06/06/23"]
[1149,970046,"   CT4 aspects of UEP18","UEP18",2,"Rel-18","C4","Mon 11/03/19","Tue 12/12/23",1,"CP-233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,"29.518",97,49,null,null,"Wed 07/09/22","NA"]
[1150,990113,"5G AM Policy ","AMP",1,"Rel-18",null,"Thu 07/03/19","Sun 03/03/24",1,"SP-221335",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Mon 09/01/23"]
[1151,940064,"   Study on 5G AM Policy","FS_AMP",2,"Rel-18","S2","Mon 20/12/21","Mon 12/09/22",1,"SP-220647",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","21/1/22: 23.700-89 added;; 4/6/22: 0%->80; 21/6/22: WID:SP-211642->SP-220647; 12/9/22: 80%->100","23.700-89",94,48,null,null,"Sun 19/12/21","Mon 12/09/22"]
[1152,970017,"   Stage 2 of 5G AM Policy ","AMP",2,"Rel-18","S2","Thu 07/03/19","Thu 07/03/19",1,"SP-221335",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335; 15/3/23: 80%->100;","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Wed 15/03/23"]
[1153,990007,"   CT3 aspects of 5G AM Policy ","AMP",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-232130",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->85%; 6/6/23: CD:16/06/2023->09/09/2023; 6/6/23: WID: CP-230116->CP-231302","29.507; 29.513; 29.274",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1154,990095,"   CT4 aspects of 5G AM Policy ","AMP",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-232130",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->90%; 6/6/23: WID: CP-230116->CP-231302","29.507; 29.513; 29.274",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1155,990114,"Dynamically Changing AM Policies in the 5GC Phase 2 ","TEI18_DCAMP_Ph2",1,"Rel-18",null,"Mon 20/12/21","Sat 09/09/23",1,"SP-220799",null,"Yubing Liu ","liuyb9@chinatelecom.cn ",null,"23.502 ",97,49,null,null,"Sun 11/09/22","NA"]
[1156,970009,"   Stage 2 of TEI18_DCAMP_Ph2","TEI18_DCAMP_Ph2",2,"Rel-18","S2","Mon 20/12/21","Tue 06/06/23",1,"SP-230102",null,"Yubing Liu ","liuyb9@chinatelecom.cn ","; 16/3/23: FCD:12/09/2022->/23; 16/3/23: WID:SP-220799->SP-230102","23.502 ",97,49,null,null,"Sun 11/09/22","Thu 16/03/23"]
[1157,990005,"   CT3 aspects on Dynamically Changing AM Policies in the 5GC Phase 2","TEI18_DCAMP_Ph2",2,"Rel-18","C3","Mon 20/12/21","Sat 09/09/23",1,"CP-233124",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023","29.513; 29.519; 29.522; 29.534",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1158,1020047,"   CT4 aspects on Dynamically Changing AM Policies in the 5GC Phase 2","TEI18_DCAMP_Ph2",2,"Rel-18","C4","Mon 20/12/21","Sat 09/09/23",1,"CP-233124",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023","29.513; 29.519; 29.522; 29.534",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1159,0,"Rel-18 User plane improvements","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1160,1000017,"Study on new HEVC profiles and operating points ","FS_HEVC_Profiles",1,"Rel-18","S4","Thu 08/06/23","Sun 03/03/24",1,"SP-230540",null,"Waqar Zia ","waqar_zia (at) apple.com ","; 7/9/23: 0%->30; 21/9/23: 26.966 added;; 8/12/23: 30%->65; 14/3/24: 65%->100","26.955 ; 26.966",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[1161,940010,"Study on 5G Media Service Enablers ","FS_5G_MSE",1,"Rel-18","S4","Mon 13/12/21","Mon 12/12/22",1,"SP-211338",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","12/3/22: 0%->20; 4/6/22: 20%->30; 12/9/22: 30%->60; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 60%->100",null,94,48,null,null,"Mon 13/12/21","Sun 11/12/22"]
[1162,960043,"UE Testing Phase 2 ","eUET",1,"Rel-18","S4","Thu 02/06/22","Sun 03/03/24",1,"SP-220610",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","; 3/8/22: 26.130 added; 17/8/22: UETest_Ph2-> eUET; 12/9/22: 0%->10; 11/12/22: 10%->15; 17/3/23: 15%->20; 8/6/23: 20%->30; 7/9/23: 30%->35; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 35%->65; 14/3/24: 65%->100","26.131; 26.132; 26.801 ; 26.130",96,49,null,null,"Fri 03/06/22","Thu 14/03/24"]
[1163,980009,"5G Media Streaming Audio codec phase 2 for 5G-Advanced ","5GMS_Audio_Ph2",1,"Rel-18","S4","Fri 09/12/22","Fri 03/03/23",1,"SP-221033",null,"Frédéric Gabin (Dolby Laboratories Inc.) ","frederic.gabin@dolby.com ","17/3/23: 0%->100","26.117; 26.511 ",98,50,null,null,"Fri 09/12/22","Fri 17/03/23"]
[1164,960047,"5G Media Streaming Architecture Phase 2 ","5GMS_Ph2",1,"Rel-18","S4","Thu 02/06/22","Tue 06/06/23",1,"SP-230164",null,"Iraj Sodagar, Tencent ","<irajs@live.com> ","17/8/22: 5GMSA_Ph2-> 5GMS_Ph2; 17/8/22: WID:SP-220614->SP-220667; 12/9/22: 0%->15; 11/12/22: 15%->25; 16/3/23: WID:SP-220667->SP-230164; 16/3/23: FCD:03/03/2023->/23; 17/3/23: 25%->50; 8/6/23: 50%->100","26.501 ",96,49,null,null,"Fri 03/06/22","Thu 08/06/23"]
[1165,980007,"Enhanced Multiparty RTT ","MP_RTT",1,"Rel-18","S4","Mon 12/12/22","Sun 03/03/24",1,"SP-231709",null,"Huan-yu Su, Huawei ","su.huanyu@huawei.com ","; 17/3/23: 0%->5; 8/6/23: 5%->30; 7/9/23: 30%->50; 8/12/23: 50%->75; 8/12/23: FCD:12/12/2023->/2024; 8/12/23: WID:SP-221346->SP-231290; 3/1/24: WID:SP-231290->SP-231709; 14/3/24: 75%->100; 3/4/24: 26.982 added;","26.114 ; 26.982",98,50,null,null,"Fri 09/12/22","Wed 03/04/24"]
[1166,870013,"Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems ","FS_XRTraffic",1,"Rel-18","S4","Wed 25/03/20","Sat 09/09/23",1,"SP-210043",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","10/6/20: 0%->15; 28/06/20: Rel-16->Rel-17; 5/12/20: 15%->40; 21/3/21: 40%->50; 21/3/21: FCD:18/06/2020->09/21; 11/6/21: 50%->65. 2/7/21: name change from \"Study on Typical Traffic Characteristics for XR Services and other Media\"; 13/9/21: 65%->70; 13/1...","26.925 ",87,44,null,null,"Fri 06/12/19","Thu 07/09/23"]
[1167,1000015,"5G-Advanced media profiles for messaging services ","PROMISE",1,"Rel-18","S4","Thu 08/06/23","Sun 03/03/24",1,"SP-230542",null,"Frédéric Gabin (Dolby Laboratories Inc.) – ","frederic.gabin@dolby.com ","30/6/23: 26.143 added;; 7/9/23: 0%->15; 8/12/23: 15%->40; 14/3/24: 40%->100","26.140; 26.141 ; 26.143",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[1168,1000018,"5G Media Streaming Protocols Phase 2 ","5GMS_Pro_Ph2",1,"Rel-18","S4","Thu 08/06/23","Thu 06/06/24",1,"SP-230976",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","; 7/9/23: WID:SP-230543->SP-230976; 7/9/23: 0%->25; ; 21/9/23: 26.510 added;; 8/12/23: 25%->55; 14/3/24: 55%->75; 14/3/24: FCD:03/03/2024->/24; 13/6/24: 75%->100","26.512; 26.247; 26.517; 26.532 ; 26.510",100,51,null,null,"Thu 08/06/23","Thu 13/06/24"]
[1169,0,"Rel-18 Other topics","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1170,1030040,"AKMA service disabling in roaming ","AKMA_Disable",1,"Rel-18","S3","Fri 02/02/24","Sun 03/03/24",1,"SP-240246",null,"Khare, Saurabh ","saurabh.khare@nokia.com ","15/3/24: 0%->100",null,103,52,null,null,"Thu 14/03/24","Fri 15/03/24"]
[1171,980110,"Support for Wireless and Wireline Convergence Phase 2 ","5WWC_Ph2",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-220904",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","NA"]
[1172,840085,"   Study on the support for 5WWC Phase 2","FS_5WWC_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220419",null,"Laurent Thiebaut, Nokia","laurent.thiebaut@nokia.com","26/6/19: 23.700-16 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940062, temporarily mistakenly added as FS_5WWV_Ph3; WID:SP-190562->SP-211640; 12/3/22: 0%->30. 4/6/22: 30%->60; 21/6/22: WID:SP-211640...; 12/9/22: FCD:12/09/2022->12/20...","23.700-17",84,43,null,null,"Sat 03/06/17","Wed 15/03/23"]
[1173,960030,"   Study on Security aspects for 5WWC Phase 2 ","FS_5WWC_Ph2_Sec",2,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-221144",null,"Saurabh Khare, Nokia ","Saurabh.khare@nokia.com ","13/7/22: 33.887 added;; 12/9/22: 0%->30; 11/12/22: 30%->60; 9/1/23: WID:SP-220528->SP-221144; 17/3/23: 60%->80; 8/6/23: 80%->100","33.887",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1174,970010,"   Stage 2 of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","S2","Mon 20/12/21","Tue 06/06/23",1,"SP-230367",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","; 15/3/23: 30%->45; 15/3/23: WID:SP-220904->SP-230100; 15/3/23: FCD:12/12/2022->/23; 31/3/23: WID:SP-230100->SP-230367; 8/6/23: 45%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Fri 09/12/22","Thu 08/06/23"]
[1175,980083,"   CT1 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-223114->CP-231302; 30/6/23: WID:CP-231302->CP-231287","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"Sun 11/09/22","Fri 30/06/23"]
[1176,980084,"   CT3 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 9/6/23: 15%->40","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1177,980085,"   CT4 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C4","Thu 15/12/22","Sun 03/03/24",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:40%->65%","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1178,990035,"   Security aspects for 5WWC Phase 2 ","5WWC_Ph2_Sec",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230148",null,"Khare, Saurabh, Nokia ","saurabh.khare@nokia.com ","; 8/6/23: 0%->80; 15/3/24: 80%->100","33.501 ",99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[1179,1010016,"   Charging Aspects of 5WWC phase 2 ","5WWC_Ph2",2,"Rel-18","S5","Wed 06/09/23","Sun 03/03/24",1,"SP-231154",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","; 8/12/23: 0%->40; 14/3/24: 40%->100","32.255; 32.291; 32.298 ",101,51,null,null,"Wed 06/09/23","Thu 14/03/24"]
[1180,980129,"Enhancement of NSAC for maximum number of UEs with at least one PDU session/PDN connection ","eNSAC",1,"Rel-18",null,"Fri 09/09/22","Tue 12/12/23",1,"SP-220988",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502 ",97,49,null,null,"Fri 23/09/22","NA"]
[1181,970058,"   Stage 2 of eNSAC","eNSAC",2,"Rel-18","S2","Fri 09/09/22","Tue 06/06/23",1,"SP-230113",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 16/3/23: FCD:03/03/2023->/23; 16/3/23: WID:SP-220988->SP-230113; 8/6/23: 0%->100","23.501; 23.502 ",97,49,null,null,"Mon 12/12/22","Thu 08/06/23"]
[1182,980086,"   CT3 aspects of eNSAC","eNSAC",2,"Rel-18","C3","Thu 15/12/22","Tue 06/06/23",1,"CP-232025",null,"Li, Zhijun, ZTE","li.zhijun3@zte.com.cn",null,"29.510; 29.536; 29.571; 29.122; 29.522",97,49,null,null,"Fri 23/09/22","NA"]
[1183,980087,"   CT4 aspects of eNSAC","eNSAC",2,"Rel-18","C4","Thu 15/12/22","Tue 12/12/23",1,"CP-232025",null,"Li, Zhijun, ZTE","li.zhijun3@zte.com.cn","; 6/6/23: Compl:0%->25%","29.510; 29.536; 29.571; 29.122; 29.522",97,49,null,null,"Fri 23/09/22","Tue 06/06/23"]
[1184,970031,"Management Data Analytics phase 2 ","eMDAS_Ph2",1,"Rel-18","S5","Fri 23/09/22","Sun 03/03/24",1,"SP-240267",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 11/12/22: 0%->5; 17/3/23: 5%->15; 8/6/23: 15%->25; 8/6/23: 25%->25; 7/9/23: 25%->50; 8/12/23: 50%->87; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 87%->100; 2/4/24: WID:SP-220981->SP-240267","28.104; 28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533 ",97,49,null,null,"Sun 11/09/22","Tue 02/04/24"]
[1185,990115,"Application Data Analytics Enablement Service ","ADAES",1,"Rel-18",null,"Mon 13/12/21","Sun 03/03/24",1,"SP-220913",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->","23.434 ; 23.436",97,49,null,null,"Sun 11/09/22","Sun 11/12/22"]
[1186,940019,"   Study on Application Data Analytics Enablement Service ","FS_ADAES",2,"Rel-18","S6","Mon 13/12/21","Mon 12/09/22",1,"SP-211513",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","7/1/22: 23.700-36 added;; 12/3/22: 0%->15; 4/6/22: 15%->55; 12/9/22: 55%->95; 11/12/22: 95%->100","23.700-36",94,48,null,null,"Mon 13/12/21","Sun 11/12/22"]
[1187,970036,"   Stage 2 of ADAES","ADAES",2,"Rel-18","S6","Mon 12/09/22","Tue 06/06/23",1,"SP-230275",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->; 17/3/23: FCD:03/03/2023->/23; 17/3/23: WID:SP-220913->SP-230275; 17/3/23: 45%->80; 8/6/23: 80%->100","23.434 ; 23.436",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1188,990020,"   CT1 aspects of ADAES","ADAES",2,"Rel-18","C1","Mon 12/09/22","Sun 03/03/24",1,"CP-240268",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","31/3/23: 24.559 added;; 6/6/23: Compl:0%->5%","29.549; 24.559",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1189,990097,"   CT3 aspects of ADAES","ADAES",2,"Rel-18","C3","Mon 12/09/22","Sun 03/03/24",1,"CP-240268",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","9/6/23: 0%->5","29.549",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1190,940079,"Study on Seamless UE context recovery ","FS_SUECR",1,"Rel-18","S2","Mon 20/12/21","Mon 12/09/22",1,"SP-211654",null,"Lalith Kumar ","lalith.kumar@samsung.com ","21/1/22: 23.700-61 added;; 12/3/22: 0%->25; 4/6/22: 25%->100","23.700-61",94,48,null,null,"Sun 19/12/21","Sat 04/06/22"]
[1191,980116,"Seamless UE context recovery ","SUECR",1,"Rel-18",null,"Thu 08/09/22","Sat 09/09/23",1,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ",null,"23.501; 23.502 ",97,49,null,null,"Sun 11/09/22","NA"]
[1192,970020,"   Stage 2 of Seamless UE context recovery ","SUECR",2,"Rel-18","S2","Thu 08/09/22","Mon 12/12/22",1,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ","; 10/12/22: 0%->100","23.501; 23.502 ",97,49,null,null,"Sat 10/12/22","Sat 10/12/22"]
[1193,980088,"   CT1 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C1","Fri 16/12/22","Sat 09/09/23",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com","; 6/6/23: Compl:90%->95%","24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1194,980089,"   CT3 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C3","Fri 16/12/22","Sat 09/09/23",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com","; 9/6/23: 60%->80","24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1195,980090,"   CT4 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C4","Fri 16/12/22","Sat 09/09/23",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com",null,"24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"Sun 11/09/22","NA"]
[1196,980115,"5G System Enabler for Service Function Chaining ","SFC",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-220802",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","NA"]
[1197,970012,"   Stage 2 of 5G System Enabler for Service Function Chaining ","SFC",2,"Rel-18","S2","Fri 09/09/22","Tue 06/06/23",1,"SP-230120",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ","; 9/1/23: WID:SP-220802->SP-221336; 15/3/23: 0%->60; 15/3/23: WID:SP-221336->SP-230120; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sat 10/12/22","Thu 08/06/23"]
[1198,980091,"   CT3 aspects of SFC","SFC",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-231193",null,"Yue Sun, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:10%->90%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223210->CP-231193. 2/4/23: rapporteur: Thomas Luetzenkirchen, Intel-> Yue Sun, China Telecom","29.244; 29.512; 29.513; 29.514; 29.519; 29.522",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1199,980092,"   CT4 aspects of SFC","SFC",2,"Rel-18","C4","Mon 20/12/21","Tue 12/12/23",1,"CP-231193",null,"Yue Sun, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:100%->80%; 6/6/23: CD:12/12/2022->12/12/2023; 6/6/23: WID: CP-223210->CP-231193. 2/4/23: rapporteur: Thomas Luetzenkirchen, Intel-> Yue Sun, China Telecom","29.244; 29.512; 29.513; 29.514; 29.519; 29.522",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1200,940052,"   Study on System Enabler for Service Function Chaining ","FS_SFC",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220415",null,"Meghashree D Kedalagudde, Intel","meghashree.dattatri.kedalagudde@intel.com","21/1/22: 23.700-18 added;; 12/3/22: 0%->25; 4/6/22: 25%->60; 21/6/22: WID:SP-211594->SP-220415: rap change; 12/9/22: 60%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-18",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1201,940054,"Study on Extensions to the TSC Framework to support Deterministic Networking (DetNet)","FS_DetNet",1,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211633",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","21/1/22: 23.700-46 added;; 12/3/22: 0%->10; 4/6/22: 10%->70; 12/9/22: 70%->90; 12/9/22: FCD:12/09/2022->12/22; 15/3/23: 90%->100","23.700-46",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[1202,980119,"Extensions to the TSC Framework to support DetNet ","DetNet",1,"Rel-18",null,"Thu 08/09/22","Sun 03/03/24",1,"SP-220801",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","NA"]
[1203,970011,"   Stage 2 of Extensions to the TSC Framework to support DetNet ","DetNet",2,"Rel-18","S2","Thu 08/09/22","Tue 06/06/23",1,"SP-230172",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","; 15/3/23: WID:SP-220801->SP-230172; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sat 10/12/22","Thu 08/06/23"]
[1204,980093,"   CT1 aspects of Detnet","DetNet",2,"Rel-18","C1","Fri 16/12/22","Tue 12/12/23",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:90%->100%; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1205,980094,"   CT3 aspects of Detnet","DetNet",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:50%->80%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1206,1020064,"      (IETF) CT3 part of DetNet (draft-ietf-detnet-yang)","DetNet",3,"Rel-18","C3-IETF","Fri 16/12/22","Sun 03/03/24",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","CT3 part complete. SA2 reference cleanup pending","29.513, 29.565",97,49,null,null,"Sun 11/09/22","Tue 02/04/24"]
[1207,980095,"   CT4 aspects of Detnet","DetNet",2,"Rel-18","C4","Fri 16/12/22","Tue 12/12/23",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:10%->80%; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1208,980117,"Multiple location report for MT-LR Immediate Location Request for regulatory services ","TEI18_MLR",1,"Rel-18",null,"Thu 08/09/22","Tue 06/06/23",1,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ",null,"23.273 ",97,49,null,null,"Sun 11/09/22","NA"]
[1209,970005,"   Stage 2 of TEI18_MLR","TEI18_MLR",2,"Rel-18","S2","Thu 08/09/22","Mon 12/12/22",1,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ","; 10/12/22: 0%->100","23.273 ",97,49,null,null,"Sat 10/12/22","Sat 10/12/22"]
[1210,980002,"   CT4 aspects on TEI18_MLR","TEI18_MLR",2,"Rel-18","C4","Fri 16/12/22","Tue 06/06/23",1,"CP-223022",null,"Jones Yunjie, Lu, Ericsson","jones.lu@ericsson.com","; 6/6/23: Compl:80%->100%; 6/6/23: CD:12/12/2023->06/06/2023","29.571; 29.518",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1211,980120,"TEI18 on Enhancement of Application Detection Event Exposure ","TEI18_ADEE",1,"Rel-18",null,"Thu 08/09/22","Tue 06/06/23",1,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ",null,"23.503; 23.502 ",97,49,null,null,"Sun 11/09/22","NA"]
[1212,970006,"   Stage 2 of TEI18_ADEE","TEI18_ADEE",2,"Rel-18","S2","Thu 08/09/22","Fri 03/03/23",1,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","; 22/3/23: 0%->100","23.503; 23.502 ",97,49,null,null,"Sat 10/12/22","Wed 22/03/23"]
[1213,980030,"   CT3 aspects of TEI18_ADEE","TEI18_ADEE",2,"Rel-18","C3","Thu 15/12/22","Tue 06/06/23",1,"CP-223202",null,"Zhenning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:0%->100%","29.522; 29.514; 29.512",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1214,980121,"General Support of IPv6 Prefix Delegation in 5GS ","TEI18_IPv6PD",1,"Rel-18",null,"Thu 08/09/22","Tue 12/12/23",1,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ",null,"23.501; 23.502; 23.503; 23.304; 23.316 ",97,49,null,null,"Sun 11/09/22","NA"]
[1215,970007,"   Stage 2 of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","S2","Thu 08/09/22","Fri 03/03/23",1,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ","; 22/3/23: 0%->100","23.501; 23.502; 23.503; 23.304; 23.316 ",97,49,null,null,"Sat 10/12/22","Wed 22/03/23"]
[1216,980096,"   CT1 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C1","Fri 16/12/22","Tue 12/12/23",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ","; 6/6/23: Compl:95%->100%; 6/6/23: WID: CP-223203->CP-230121","24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1217,980097,"   CT3 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C3","Fri 16/12/22","Tue 12/12/23",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ",null,"24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"Sun 11/09/22","NA"]
[1218,980098,"   CT4 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C4","Fri 16/12/22","Tue 12/12/23",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ",null,"24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"Sun 11/09/22","NA"]
[1219,980118,"Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",1,"Rel-18",null,"Thu 08/09/22","Sun 03/03/24",1,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502 ",97,49,null,null,"Sun 11/09/22","NA"]
[1220,970008,"   Stage 2 of Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",2,"Rel-18","S2","Thu 08/09/22","Mon 12/12/22",1,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","; 10/12/22: 0%->100","23.501; 23.502 ",97,49,null,null,"Sat 10/12/22","Sat 10/12/22"]
[1221,980099,"   CT1 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:80%->90%","24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1222,980100,"   CT3 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ","; 9/6/23: 96%->","24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1223,980101,"   CT4 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C4","Fri 16/12/22","Sun 03/03/24",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ",null,"24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"Sun 11/09/22","NA"]
[1224,990116,"Message Service within the 5G system (MSGin5G) Phase 2","5GMARCH_Ph2",1,"Rel-18",null,"Thu 10/03/22","Tue 12/12/23",1,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70","23.554 ",95,48,null,null,"Thu 10/03/22","Sun 11/12/22"]
[1225,950026,"   Stage 2 of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","S6","Thu 10/03/22","Fri 03/03/23",1,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70; 17/3/23: 70%->80; 8/6/23: 80%->100","23.554 ",95,48,null,null,"Thu 10/03/22","Thu 08/06/23"]
[1226,990019,"   CT1 aspects of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","C1","Mon 13/03/23","Tue 12/12/23",1,"CP-230198",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 6/6/23: Compl:0%->15%","24.538; 24.544; 24.546; 29.538; 29.222",95,48,null,null,"Thu 10/03/22","Tue 06/06/23"]
[1227,990099,"   CT3 aspects of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","C3","Mon 13/03/23","Tue 12/12/23",1,"CP-230198",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","9/6/23: 0%->80","24.538; 24.544; 24.546; 29.538; 29.222",95,48,null,null,"Thu 10/03/22","Fri 09/06/23"]
[1228,990041,"   Security aspects of MSGin5G Ph2 ","5GMARCH_Ph2_SEC",2,"Rel-18","S3","Thu 02/02/23","Fri 03/03/23",1,"SP-230154",null,"Huang Xiaoting, China Mobile ","huangxiaoting@chinamobile.com ","; 8/6/23: 0%->100","33.501 ",99,50,null,null,"Thu 16/03/23","Thu 08/06/23"]
[1229,910039,"5G Timing Resiliency System ","5TRS",1,"Rel-18",null,"Thu 25/06/20","Sun 03/03/24",1,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ",null,"22.261; 22.104 ",91,46,null,null,"Thu 18/03/21","NA"]
[1230,880037,"   Study on 5TRS","FS_5TRS",2,"Rel-18","S1","Thu 25/06/20","Fri 12/03/21",1,"SP-200573",null,"Betsy Covell, Nokia","betsy.covell@nokia.com","28/7/20: 22.878 added;; 12/9/20: 0%->10; 5/12/20: 10%->75; 19/3/21: FCD:16/12/2020->03/21; 19/3/21: 75%->97; 11/6/21: 97%->100","22.878",88,45,null,null,"Thu 25/06/20","Fri 11/06/21"]
[1231,940055,"   Study on 5G Timing Resiliency and TSC&URLLC enhancements ","FS_5TRS_URLLC",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211634",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","21/1/22: 23.700-25 added;; 12/3/22: 0%->25; 4/6/22: 25%->65; 12/9/22: 65%->83; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 83%->98; 15/3/23: 98%->100","23.700-25",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[1232,910033,"   Stage 1 for 5TRS","5TRS",2,"Rel-18","S1","Thu 18/03/21","Fri 10/09/21",1,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ","; 11/6/21: 0%->100","22.261; 22.104 ",91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[1233,970024,"   Stage 2 of Timing Resiliency and URLLC enhancements ","TRS_URLLC",2,"Rel-18","S2","Mon 12/09/22","Fri 03/03/23",1,"SP-230107",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","; 10/12/22: 0%->50; 9/1/23: WID:SP-220814->SP-221341; 15/3/23: 50%->80; 15/3/23: WID:SP-221341->SP-230107; 8/6/23: 80%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1234,980102,"   CT1 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:70%->95%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: WID:CP-231198->CP-231360","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539",97,49,null,null,"Sun 11/09/22","Fri 30/06/23"]
[1235,980103,"   CT3 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:25%->75%; 6/6/23: WID: CP-223205->CP-231198","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1236,980104,"   CT4 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C4","Fri 16/12/22","Tue 12/12/23",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:40%->55%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: 29.585 added;","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244; 29.585",97,49,null,null,"Sun 11/09/22","Fri 30/06/23"]
[1237,950028,"Study on Management Aspects of URLLC ","FS_URLLC_Mgt",1,"Rel-18","S5","Thu 10/03/22","Tue 06/06/23",1,"SP-230772",null,"Wang,Zhaoning,China Unicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.832 added;; 4/6/22: 0%->15; 12/9/22: 15%->40; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 40%->60; 17/3/23: 60%->62; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 62%->100; 30/6/23: WID:SP-220146->SP-230772","28.832",95,48,null,null,"Thu 10/03/22","Fri 30/06/23"]
[1238,940088,"Study on enhancement for resiliency of gNB-CU (Central Unit)-CP (Control Plane)","FS_gNB_CU_CP_resiliency",1,"Rel-18","R3","Mon 13/12/21","Thu 22/09/22",1,"RP-222249","RP-221439","Masato Taniguchi, NTT DOCOMO, INC.","masato.taniguchi.mf@nttdocomo.com","; 22/3/22: CD:12/09/2022->12/09/2023; 22/3/22: Stat Rep: ->RP-2205556/6/22: CD:12/09/2023->22/09/20226/6/22: Stat Rep: RP-220555->RP-221439; 20/6/22: Rapporteur: NTT DOCOMO->Masato Taniguchi, NTT DOCOMO, INC.; Rap eMail: ->masato.taniguchi.mf@nttdocomo...","38.879",94,48,null,null,"Thu 06/01/22","Fri 23/09/22"]
[1239,991036,"NR Timing Resiliency and URLLC enhancements ","TRS_URLLC-NR",1,"Rel-18","R3","Fri 03/03/23","Tue 12/12/23",1,"RP-232863",null,"Nokia ",null,"2/1/24: WID:RP-230754->RP-232863",null,99,50,null,null,"Wed 29/03/23","Tue 02/01/24"]
[1240,991136,"   Core part: NR Timing Resiliency and URLLC enhancements ","TRS_URLLC-NR-Core",2,"Rel-18","R3","Fri 03/03/23","Tue 12/12/23",1,"RP-232863","RP-232864","Sean Kelley, Nokia","sean.kelley@nokia.com","; ...; 6/9/23: Compl:25%->60%; WID: RP-230754->RP-231106; Stat Rep: ->RP-231581; Rapporteur: Nokia->Sean Kelley, Nokia; Rap eMail: ->sean.kelley@nokia.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-231581->RP-232864; ",null,99,50,null,null,"Wed 29/03/23","Fri 08/12/23"]
[1241,930028,"Vehicle-Mounted Relays ","VMR",1,"Rel-18",null,"Wed 16/09/20","Sun 03/03/24",1,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ",null,"22.261 ",93,47,null,null,"Fri 10/09/21","NA"]
[1242,890022,"   Study on VMR","FS_VMR",2,"Rel-18","S1","Wed 16/09/20","Wed 08/09/21",1,"SP-200798",null,"Francesco Pica ","fpica@qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: FCD:11/06/2021->09/21; 19/3/21: 35%->60; 11/6/21: 60%->85; 13/9/21: 85%->100","22.839",89,45,null,null,"Thu 10/09/20","Mon 13/09/21"]
[1243,930021,"   Stage 1 of VMR","VMR",2,"Rel-18","S1","Fri 10/09/21","Fri 10/12/21",1,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ","; 13/9/21: 0%->95; 14/12/21: 95%->100","22.261 ",93,47,null,null,"Fri 10/09/21","Tue 14/12/21"]
[1244,980018,"   (Stage 2 for VMR) Architecture Enhancements for Vehicle Mounted Relays","VMR",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230105",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","; 10/12/22: 0%->20; 15/3/23: WID:SP-221328->SP-230105; 15/3/23: 20%->40; 8/6/23: 40%->100; 4/1/24: 28.875 added;","23.501; 23.502; 23.503; 23.273 ; 28.875",98,50,null,null,"Fri 09/12/22","Thu 04/01/24"]
[1245,990013,"   CT1 aspects of VMR","VMR",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-232168",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","; 6/6/23: Compl:0%->20%","23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1246,990102,"   CT4 aspects of VMR","VMR",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-232168",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","; 6/6/23: Compl:0%->25%","23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1247,940057,"   Study on Architecture Enhancements for Vehicle Mounted Relays ","FS_VMR",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211636",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","21/1/22: 23.700-05 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-05",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1248,941009,"Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB",1,"Rel-18",null,"Mon 13/12/21","Thu 06/06/24",1,"RP-240104",null,"Qualcomm",null,"compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh; no Perf. part; 5/4/22: WID:RP-213601->RP-220843; 12/7/22: WID:RP-220843->RP-221815; 23/9/22: WID:RP-221815->RP-222671; 6/10/23: WID:RP-222671->RP-232643; 2/1/24: WID:RP-232643->RP-233320; 2/4/24: WID:RP-2",null,94,48,null,null,"Thu 06/01/22","Tue 02/04/24"]
[1249,941109,"   Core part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Core",2,"Rel-18","R3","Mon 13/12/21","Tue 12/12/23",1,"RP-240319","RP-241123","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh;; 22/3/22: Stat Rep: ->RP-220430 6/6/22: CD:12/12/2023->23/12/2022 6/6/22: Stat Rep: RP- ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com13...;...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[1250,941209,"   Perf. part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Perf",2,"Rel-18","R3","Wed 15/12/21","Thu 06/06/24",1,"RP-240319","RP-241123","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220430 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220430->RP ; 20/6/22: WG: R4->R3; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualco...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[1251,941008,"Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh",1,"Rel-18",null,"Mon 13/12/21","Tue 12/12/23",1,"RP-223488",null,"China Unicom",null,"compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 12/7/22: WID:RP-213594->RP-221803; 9/1/23: WID:RP-221803->RP-223488",null,94,48,null,null,"Thu 06/01/22","Mon 09/01/23"]
[1252,941108,"   Core part: Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh-Core",2,"Rel-18","R3","Mon 13/12/21","Tue 12/12/23",1,"RP-223488","RP-233603","Pei Li, China Unicom","lip104@chinaunicom.cn","compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221244; Rapporteur: China Unicom->Pei Li, China Unicom; Rap eMail: ->lip104@chinaunicom.cn13/7/22: FCD:23/12/2022->12/20;...;...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1253,940032,"Study on Key Quality Indicators (KQIs) for 5G service experience ","FS_KQI_5G",1,"Rel-18","S5","Mon 13/12/21","Sun 03/03/24",1,"SP-231432",null,"Man WANG, Huawei ","wangman1@huawei.com ","7/1/22: 28.863 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 20%->35; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 35%->; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 35%->65; 8/12/23: 65%->100; 3/1/24: WID:SP-211433->SP-231432","28.863",94,48,null,null,"Mon 13/12/21","Wed 03/01/24"]
[1254,950031,"Additional NRM features phase 2 ","AdNRM_ph2",1,"Rel-18","S5","Thu 10/03/22","Sun 03/03/24",1,"SP-231440",null,"Sean Sun, Nokia ","sean.sun@nokia-sbell.com ","4/6/22: 0%->7; 12/9/22: 7%->30; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 30%->55; 17/3/23: 55%->65; 8/6/23: 65%->80; 8/6/23: FCD:03/03/2023->/24; 8/6/23: 80%->; 7/9/23: 80%->88; 8/12/23: 88%->99; 3/1/24: WID:SP-220351->SP-231440; 14/3/24: 99%->100",null,95,48,null,null,"Thu 10/03/22","Thu 14/03/24"]
[1255,940031,"MPS when access to EPC/5GC is WLAN ","MPS_WLAN",1,"Rel-18",null,"Fri 10/09/21","Sun 03/03/24",1,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ",null,null,94,48,null,null,"Fri 10/09/21","Fri 07/01/22"]
[1256,930024,"   Stage 1 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S1","Fri 10/09/21","Fri 10/12/21",1,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ","10/12/21: 0%->100","22.153 ",93,47,null,null,"Fri 10/09/21","Fri 10/12/21"]
[1257,940053,"   Stage 2 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S2","Mon 20/12/21","Tue 06/06/23",1,"SP-230108",null,"Robert C Streijl; Peraton Labs ","rstreijl@peratonlabs.com ","; 10/12/22: 0%->0; 10/12/22: FCD:12/09/2022->03/23; 15/3/23: 0%->50; 15/3/23: WID:SP-211595->SP-230108; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 50%->100","23.401; 23.402; 23.501; 23.502 ",94,48,null,null,"Sun 19/12/21","Thu 08/06/23"]
[1258,1000021,"   CT1 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C1","Wed 07/06/23","Sun 03/03/24",1,"CP-240299",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"Wed 07/06/23","NA"]
[1259,1000046,"   CT4 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C4","Wed 07/06/23","Sun 03/03/24",1,"CP-240299",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"Wed 07/06/23","NA"]
[1260,1030049,"   CT6 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C6","Wed 07/06/23","Sun 03/03/24",1,"CP-240299",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"Wed 07/06/23","NA"]
[1261,941007,"Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2",1,"Rel-18",null,"Fri 01/01/21","Tue 12/12/23",1,"RP-233438",null,"CMCC",null,"compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 5/4/22: WID:RP-213553->RP-221000; 12/7/22: WID:RP-221000->RP-221825; 2/1/24: WID:RP-221825->RP-233438",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1262,941107,"   Core part: Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2-Core",2,"Rel-18","R3","Fri 01/01/21","Tue 12/12/23",1,"RP-233438","RP-233437","Liang LIU, CMCC","liuliang@chinamobile.com","compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 20/6/22: FCD:31/12/2021->23/12/2022; Stat Rep: ->RP-221372; Rapporteur: CMCC->Liang LIU, CMCC; Rap eMail: ->liuliang@chinamobile.com13/7/22: FCD:23/12/2022->12...;...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1263,950064,"   UE Conformance - Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) ","NR_ENDC_SON_MDT_enh-UEConTest",2,"Rel-17","R5","Tue 15/03/22","Fri 22/09/23",1,"RP-233438","RP-232241","Danni Song, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_ENDC_SON_MDT_enh 6/6/22: Compl:0%->5% 6/6/22: CD:15/06/2 ; 20/6/22: Rapporteur: CMCC->Luting Kong, CMCC; Rap eMail: ->kongluting@chinamobile.com12/7/22: WID:RP-220620->RP-221365 ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:7%-...",null,95,48,null,null,"Tue 05/04/22","Fri 06/10/23"]
[1264,940030,"Self-Configuration of RAN Network Entities ","RANSC",1,"Rel-18","S5","Fri 10/12/21","Sun 03/03/24",1,"SP-211431",null,"Hu, Yaxi, China Mobile ","huyaxi@cmdi.chinamobile.com ","; 7/1/22: 28.317 added;; 4/6/22: 0%->5; 11/12/22: 5%->45; 17/3/23: 45%->50; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 50%->55; 8/6/23: 55%->55; 7/9/23: 55%->65; 8/12/23: 65%->90; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 90%->100","28.313; ; 28.317",94,48,null,null,"Fri 10/12/21","Thu 14/03/24"]
[1265,900028,"Support for Service Function Chaining ","SFChain",1,"Rel-18","S1","Fri 04/12/20","Fri 12/03/21",1,"SP-201040",null,"Ellen Liao; Intel ","ellen.c.liao at intel.com ","22.261; 22.101; 22.115 ; 5/12/20: 0%->100",null,90,46,null,null,"Fri 04/12/20","Sat 05/12/20"]
[1266,910035,"Data Integrity in 5GS ","DI_5G",1,"Rel-18","S1","Thu 18/03/21","Thu 25/03/21",1,"SP-210213",null,"Qun wei, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 19/3/21: 0%->100","22.261 ",91,46,null,null,"Thu 18/03/21","Fri 19/03/21"]
[1267,920033,"Signal level Enhanced Network Selection ","SENSE",1,"Rel-18","S1","Fri 16/09/22","Fri 01/03/24",1,"SP-210525",null,"Bischinger, Kurt; Deutsche Telekom ","kurt.bischinger@magenta.at ","; 11/6/21: 0%->40; 10/12/21: 40%->100","22.011 ",92,47,null,null,"Fri 11/06/21","Fri 10/12/21"]
[1268,970059,"   CT1 aspects of SENSE","SENSE",2,"Rel-18","C1","Fri 16/12/22","Tue 06/06/23",1,"CP-222237",null,"Reinhard Lauster, Deutsche Telekom","reinhard.lauster@magenta.at","; 6/6/23: Compl:65%->95%; 6/6/23: CD:16/12/2022->06/06/2023","23.122; 24.501; 27.007",97,49,null,null,"Mon 19/09/22","Tue 06/06/23"]
[1269,970060,"   CT6 aspects of SENSE","SENSE",2,"Rel-18","C6","Fri 16/09/22","Fri 16/09/22",1,"CP-222237",null,"Reinhard Lauster, Deutsche Telekom","reinhard.lauster@magenta.at",null,"31.102",97,49,null,null,"Mon 19/09/22","NA"]
[1270,1010052,"   UE Conformance - Signal level Enhanced Network Selection ","SENSE-UEContest",2,"Rel-18","R5","Sat 09/09/23","Fri 01/03/24",1,"RP-233770","RP-240288","Ya Zhao, Huawei Technologies. Co., Ltd","zhaoya@hisilicon.com","8/12/23: Compl:0%->5%; Stat Rep: ->RP-233769; Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com; ; 2/1/24: WID:RP-232362->RP-233770; 14/3/24: FCD:05/06/2024->01/03/2024; Compl:5%->100%; Stat Rep: RP-233769->RP-",null,101,51,null,null,"Fri 06/10/23","Thu 14/03/24"]
[1271,940017,"SECAM and SCAS for 3GPP virtualized network products ","VNP_SECAM_SCAS",1,"Rel-18","S3","Fri 10/12/21","Fri 03/03/23",1,"SP-211365",null,"Qi Minpeng, China Mobile ","qiminpeng@chinamobile.com ","7/1/22: 33.527 added;; 12/9/22: 0%->40; 11/12/22: 40%->65; 17/3/23: 65%->75; 15/3/24: 75%->100","33.527; 33.927; 33.936",94,48,null,null,"Fri 10/12/21","Fri 15/03/24"]
[1272,950016,"Security Assurance Specification (SCAS) for 5G Rel-17 Features ","SCAS_5G_Ph2",1,"Rel-18","S3","Thu 10/03/22","Mon 12/12/22",1,"SP-220192",null,"Rong Wu, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","; 4/6/22: 0%->10; 17/3/23: 10%->30; 15/3/24: 30%->100","33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519; 33.520; 33.521; 33.522; 33.326 ",95,48,null,null,"Thu 10/03/22","Fri 15/03/24"]
[1273,960035,"Study on URSP rules to securely identify applications ","FS_USIA",1,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220533",null,"Andreas Kunz, Lenovo ","akunz@lenovo.com ","13/7/22: 33.892 added;; 12/9/22: 0%->30; 11/12/22: 30%->50; 17/3/23: 50%->80; 7/9/23: 80%->100","33.892",96,49,null,null,"Thu 02/06/22","Thu 07/09/23"]
[1274,810032,"Study on 5G security enhancement against false base stations","FS_5GFBS",1,"Rel-18","S3","Thu 06/09/18","Fri 09/12/22",1,"SP-180690",null,"Ivy Guo, Apple","ivy_guo@apple.com","7/12/18: 0%->10¦20/3/19: FCD:019->09/19¦20/3/19: 10%->50; 31/5/19: 50%->65; 13/9/19: 65%->66; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 66%->75; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 75%->80; 26/6/20: FCD:12/03/2020->12/20; ; ","New",81,41,null,null,"Thu 06/09/18","Thu 08/06/23"]
[1275,960040,"Security Enhancement on RRCResumeRequest Message Protection ","SERP",1,"Rel-18","S3","Thu 02/06/22","Mon 12/12/22",1,"SP-220538",null,"Ivy Guo, Apple ","<ivy_guo@apple.com> ","7/9/23: 0%->100",null,96,49,null,null,"Thu 02/06/22","Thu 07/09/23"]
[1276,960055,"Stage-3 5GS NAS protocol development 18 ","5GProtoc18",1,"Rel-18",null,"Fri 03/06/22","Tue 12/12/23",1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 6/6/23: Compl:30%->40%","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1277,960007,"   Stage-3 5GS NAS protocol development 18 general aspects","5GProtoc18",2,"Rel-18","C1","Fri 03/06/22","Tue 12/12/23",1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"Fri 03/06/22","NA"]
[1278,960056,"   Stage-3 5GS NAS protocol development 18 non 3GPP aspects","5GProtoc18-non3GPP",2,"Rel-18","C1","Fri 03/06/22","Tue 12/12/23",1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"Fri 03/06/22","NA"]
[1279,960057,"Stage-3 SAE Protocol Development ","SAES18",1,"Rel-18",null,"Fri 03/06/22","Tue 12/12/23",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,"; 6/6/23: Compl:30%->40%","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1280,960008,"   Stage-3 SAE Protocol Development general","SAES18",2,"Rel-18","C1","Fri 03/06/22","Tue 12/12/23",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"Fri 03/06/22","NA"]
[1281,960058,"   Stage-3 SAE Protocol Development CSFB","SAES18-CSFB",2,"Rel-18","C1","Fri 03/06/22","Tue 12/12/23",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"Fri 03/06/22","NA"]
[1282,960059,"   Stage-3 SAE Protocol Development non 3GPP","SAES18-non3GPP",2,"Rel-18","C1","Fri 03/06/22","Tue 12/12/23",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"Fri 03/06/22","NA"]
[1283,960009,"Protocol enhancements for Mission Critical Services ","MCProtoc18",1,"Rel-18",null,"Fri 03/06/22","Sun 03/03/24",1,"CP-232163",null,"AXELL, Jörgen, Ericsson","jorgen.axell@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"Fri 03/06/22","Mon 20/06/22"]
[1284,980105,"   CT1 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C1","Fri 03/06/22","Sun 03/03/24",1,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 30%->40","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"Fri 03/06/22","Fri 09/06/23"]
[1285,980106,"   CT3 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C3","Mon 06/06/22","Sun 03/03/24",1,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 10%->30","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"Fri 03/06/22","Fri 09/06/23"]
[1286,980107,"   CT4 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C4","Fri 03/06/22","Sun 03/03/24",1,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 6/6/23: Compl:...","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1287,960010,"MPS for Supplementary Services ","MPSSupServ",1,"Rel-18","C1","Fri 03/06/22","Thu 08/12/22",1,"CP-221271",null,"Peter Monnes, Peraton Labs","pmonnes@peratonlabs.com","20/6/22: FCD:12/12/2022->08/12/2022WID: C1-221271->CP-221271Rapporteur: Peter Monnes, Peraton Labs ->Peter Monnes, Peraton LabsRap eMail: pmonnes@peratonlabs.com ->pmonnes@peratonlabs.comList of Impacted TS & TR updated","24.229; 24.173; 24.629; 24.605; 24.239; 24.604; 24.642",96,49,null,null,"Fri 03/06/22","Mon 20/06/22"]
[1288,970035,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc18",1,"Rel-18",null,"Fri 03/06/22","Tue 12/12/23",1,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com",null,"23.218; 24.229; 24.930; 29.163; 29.165; 29.292",96,49,null,null,"Fri 03/06/22","Mon 20/06/22"]
[1289,970047,"   CT1 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C1","Fri 03/06/22","Tue 12/12/23",1,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com","; 6/6/23: Compl:30%->40%","23.218; 24.229; 24.930; 29.163; 29.165; 29.292",97,49,null,null,"Wed 07/09/22","Tue 06/06/23"]
[1290,970048,"   CT3 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C3","Fri 03/06/22","Tue 12/12/23",1,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com","9/6/23: 30%->60","23.218; 24.229; 24.930; 29.163; 29.165; 29.292",97,49,null,null,"Wed 07/09/22","Fri 09/06/23"]
[1291,980004,"Enhancement of Shared Data ID and Handling","ShDatID_H",1,"Rel-18","C4","Mon 07/03/22","Sun 03/03/24",1,"CP-232030",null,"Jing, Hao, Huawei","hao.jing@huawei.com","; 6/6/23: Compl:0%->40%","29.503; 29.504; 29.505",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1292,1050016,"UE conformance test for NB-IoT/eMTC Non-Terrestrial Networks in EPS","IoT_SAT_UEConTest",1,"Rel-18","C6","Mon 09/09/24","Tue 09/09/25",1,"CP-242075",null,"Daiwei Zhou, MediaTek Inc","daiwei.zhou@mediatek.com",null,null,96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1293,1050008,"Test method of GBA_U Based APIs","TEST_GBA_U_APIs",1,"Rel-18","C6","Mon 09/09/24","Fri 06/06/25",1,"CP-242028",null,"Huo Weijing(China Mobile)","huoweijing@chinamobile.com",null,null,96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1294,980036,"Rel-18 enhancements of session management policy control","SMPC18",1,"Rel-18","C3","Thu 15/12/22","Tue 12/12/23",1,"CP-223208",null,"Xiaoyun Zhou, Huawei","zhouxiaoyun8@huawei.com","; 6/6/23: Compl:25%->60%","29.512; 29.513; 29.514",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1295,990003,"Enhancements on Service-based support for SMS in 5GC","eSMS_SBI",1,"Rel-18","C4","Mon 13/03/23","Fri 15/12/23",1,"CP-230025",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn","; 6/6/23: Compl:0%->50%","23.540; 29.338; 29.329; 29.230",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1296,1010026,"Modified PRINS for roaming service providers in 5G ","Roaming5G",1,"Rel-18","S1","Tue 08/08/23","Sat 09/09/23",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected","22.261; 33.501 ",101,51,null,null,"Wed 20/09/23","NA"]
[1297,1010027,"   Stage 1 of Roaming5G ","Roaming5G",2,"Rel-18","S1","Tue 08/08/23","Sat 09/09/23",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected","22.261",101,51,null,null,"Wed 20/09/23","NA"]
[1298,1010028,"   Stage 3 of Roaming5G ","Roaming5G",2,"Rel-18","S3","Tue 08/08/23","Sat 09/09/23",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected; 8/12/23: 100%->100","33.501 ",101,51,null,null,"Wed 20/09/23","Fri 08/12/23"]
[1299,1020001,"NRF API enhancements to avoid signalling and storing of redundant data","NRFe",1,"Rel-18","C4","Tue 12/12/23","Fri 15/03/24",1,"CP-233025",null,"Wiehe, Ulrich, Nokia","ulrich.wiehe@nokia.com",null,"29.510, 29.571, 29.504",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1300,0,"Rel-18 Other Security aspects","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1301,950019,"Security Assurance Specification for AKMA Anchor Function Function (AAnF) ","SCAS_5G_AAnF",1,"Rel-18","S3","Thu 10/03/22","Fri 03/03/23",1,"SP-220197",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 4/6/22: 0%->10; 13/7/22: 33.537 added;; 11/12/22: 10%->70; 17/3/23: 70%->90; 8/6/23: 90%->95; 15/3/24: 95%->100","33.926 ; 33.537",95,48,null,null,"Thu 10/03/22","Fri 15/03/24"]
[1302,990044,"5G Security Assurance Specification (SCAS) for the Policy Control Function (PCF) ","SCAS_5G_PCF",1,"Rel-18","S3","Thu 16/03/23","Tue 12/12/23",1,"SP-230157",null,"Andreas, Joerg, BSI Germany ","joerg.andreas@bsi.bund.de ","; 31/3/23: 33.528 added;; 7/9/23: 0%->40; 7/9/23: FCD:09/09/2023->12/23; 15/3/24: 40%->100","33.926 ; 33.528",99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[1303,980021,"IETF DTLS protocol profile for AKMA and GBA ","AKMA_GBA_DTLS",1,"Rel-18","S3","Fri 09/12/22","Tue 06/06/23",1,"SP-221143",null,"Liu, yuze, ZTE ","liu.yuze@zte.com.cn ","; 8/6/23: 0%->90; 7/9/23: 90%->100","33.535; 33.220; 33.222 ",98,50,null,null,"Fri 09/12/22","Thu 07/09/23"]
[1304,980023,"IETF OSCORE protocol profiles for GBA and AKMA ","AKMA_GBA_OSCORE",1,"Rel-18","S3","Fri 09/12/22","Sat 09/09/23",1,"SP-221146",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 8/6/23: 0%->80; 7/9/23: FCD:06/06/2023->/23; 15/3/24: 80%->100","33.535; 33.220; 33.222 ",98,50,null,null,"Fri 09/12/22","Fri 15/03/24"]
[1305,950022,"SCAS for split-gNB product classes ","SCAS_5G_split_gNB",1,"Rel-18","S3","Thu 10/03/22","Fri 03/03/23",1,"SP-220200",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 4/6/22: 0%->5; 13/7/22: 33.742 added;; 12/9/22: 5%->25; 11/12/22: 25%->60; 17/3/23: 60%->85; 17/3/23: 33.523 added;; 8/6/23: 85%->99; 15/3/24: 99%->100","33.926 ; 33.742; 33.523",95,48,null,null,"Thu 10/03/22","Fri 15/03/24"]
[1306,1010019,"Home network triggered primary authentication ","HN_Auth",1,"Rel-18","S3","Thu 10/03/22","Sun 03/03/24",1,"SP-221147",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","; 15/3/24: 99%->100","33.501; 33.535 ",98,50,null,null,"Fri 09/12/22","Fri 15/03/24"]
[1307,950020,"   Study of Security aspect of home network triggered primary authentication ","FS_HN_Auth",2,"Rel-18","S3","Thu 10/03/22","Mon 12/12/22",1,"SP-220198",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","4/6/22: 0%->30; 12/9/22: 30%->60; 11/12/22: 60%->80; 17/3/23: 80%->100",null,95,48,null,null,"Thu 10/03/22","Fri 17/03/23"]
[1308,980024,"   Security aspects of home network triggered primary authentication ","HN_Auth",2,"Rel-18","S3","Fri 09/12/22","Tue 06/06/23",1,"SP-221147",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","; 7/9/23: 0%->100","33.501; 33.535 ",98,50,null,null,"Fri 09/12/22","Thu 07/09/23"]
[1309,1010001,"   CT aspects of home network triggered primary authentication ","HN_Auth",2,"Rel-18","C4","Sat 09/09/23","Sun 03/03/24",1,"CP-232028",null,"Jing, Hao, Huawei","hao.jing@huawei.com",null,"29.503, 29.504, 29.505, 29.518",98,50,null,null,"Fri 09/12/22","NA"]
[1310,950018,"Study on AKMA Phase 2","FS_AKMA_Ph2",1,"Rel-18","S3","Thu 10/03/22","Mon 12/12/22",1,"SP-220991",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","4/6/22: 0%->15; 13/7/22: 33.737 added;; 12/9/22: 15%->35; 23/9/22: WID:SP-220327->SP-220991; 11/12/22: 35%->70; 17/3/23: 70%->80; 8/6/23: 80%->95; 15/3/24: 95%->100","33.737",95,48,null,null,"Thu 10/03/22","Fri 15/03/24"]
[1311,990040,"AKMA phase 2 ","AKMA_Ph2",1,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230153",null,"Huang Xiaoting, China Mobile ","huangxiaoting@chinamobile.com ","; 8/6/23: 0%->95; 15/3/24: 95%->100","33.535 ",99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[1312,940016,"Study of privacy of identifiers over radio access ","FS_Id_Prvc",1,"Rel-18","S3","Mon 13/12/21","Fri 03/03/23",1,"SP-211364",null,"Brusilovsky, Alec, Interdigital ","alec.brusilovsky@interdigital.com ","7/1/22: 33.870 added;; 12/3/22: 0%->5; 4/6/22: 5%->10; 12/9/22: 10%->12; 17/3/23: 12%->25; 8/6/23: 25%->40; 7/9/23: 40%->80; 15/3/24: 80%->100","33.870",94,48,null,null,"Mon 13/12/21","Fri 15/03/24"]
[1313,820007,"Study on Security Impacts of Virtualisation ","FS_SIV",1,"Rel-18","S3","Thu 13/12/18","Fri 09/12/22",1,"SP-181236",null,"Alex Leadbeater, BT Plc","alex.leadbeater@bt.com","20/3/19: 0%->2¦20/3/19: 0%->2; 31/5/19: 2%->10; 13/9/19: FCD:19/09/2019->12/20; 13/9/19: 10%->12; 6/12/19: 12%->45; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 45%-> ; ",null,82,42,null,null,"Thu 06/12/18","Thu 07/09/23"]
[1314,960038,"Study on Zero Trust Security principles in mobile networks ","FS_ZTS",1,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220674",null,"Sheeba Backia Mary B, Lenovo ","smary@lenovo.com ","13/7/22: 33.894 added; 17/8/22: WID:SP-220536->SP-220674; 12/9/22: 0%->6; 11/12/22: 6%->25; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->100","33.894",96,49,null,null,"Thu 02/06/22","Thu 07/09/23"]
[1315,960039,"Study of Security aspects on User Consent for 3GPP Services Phase 2 ","FS_UC3S_Ph2",1,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220537",null,"Rong Wu, Huawei, ","Raina.wu@huawei.com ","13/7/22: 33.896 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->100","33.896",96,49,null,null,"Thu 02/06/22","Fri 17/03/23"]
[1316,1000004,"Security aspects on User Consent for 3GPP services Phase 2 ","UC3S_SEC_Ph2",1,"Rel-18","S3","Mon 01/05/23","Tue 06/06/23",1,"SP-230557",null,"Rong Wu, Huawei Technologies, ","Raina.wu@huawei.com ","; 15/3/24: 0%->100","33.501 ",100,51,null,null,"Thu 08/06/23","Fri 15/03/24"]
[1317,1010013,"Security Assurance Specification for 5G Phase 3 ","SCAS_5G_Ph3",1,"Rel-18","S3","Wed 06/09/23","Sun 03/03/24",1,"SP-230867",null,"Wu, Rong, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","; 8/12/23: 0%->10; 15/3/24: 10%->100","33.926 ",101,51,null,null,"Wed 06/09/23","Fri 15/03/24"]
[1318,0,"Rel-18 NR-only: topics other than band","-",1,"Rel-18",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1319,950073,"NR demodulation performance evolution ","NR_demod_enh3",1,"Rel-18",null,"Tue 15/03/22","Thu 12/12/24",0.9,"RP-241292",null,"China Telecom ",null,"compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 29/3/23: WID:RP-220932->RP-230314; 6/10/23: WID:RP-230314->RP-232685; 2/1/24: WID:RP-232685->RP-233586; 23/7/24: WID:RP-233586->RP-241292",null,95,48,null,null,"Tue 05/04/22","Tue 23/07/24"]
[1320,1001061,"   Core part: NR demodulation performance evolution ","NR_demod_enh3-Core",2,"Rel-18","R4","Wed 07/06/23","Tue 12/12/23",1,"RP-241292","RP-233584","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","6/9/23: Compl:0%->33%; Stat Rep: ->RP-232250; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn; ; 8/12/23: Compl:33%->100%; Stat Rep: RP-232250->RP-233584; ",null,100,51,null,null,"Thu 29/06/23","Fri 08/12/23"]
[1321,950273,"   Perf. part: NR demodulation performance evolution ","NR_demod_enh3-Perf",2,"Rel-18","R4","Tue 15/03/22","Thu 06/06/24",1,"RP-241292","RP-241293","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221287; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn12/7/22: WID:RP-2...;...","38.878",95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1322,1040105,"   UE Conformance - NR demodulation performance evolution ","NR_demod_enh3-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 12/12/25",0.77,"RP-241298","RP-251462","China Telecom ",null,"4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->8%; Stat Rep: ->RP-241995; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:8%->41%; Stat Rep: RP-241995->RP-242854; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:41%->57%; Stat Rep: RP-242854->RP-250378; ; 6/6/25:",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1323,991045,"NR channel raster enhancement","NR_channel_raster_enh",1,"Rel-18","R4","Mon 06/03/23","Mon 13/11/23",0.95,"RP-234025",null,"Ericsson",null,"2/1/24: WID:RP-230813->RP-234025",null,99,50,null,null,"Fri 07/04/23","Tue 02/01/24"]
[1324,991145,"   Core part: NR channel raster enhancement","NR_channel_raster_enh-Core",2,"Rel-18","R4","Mon 06/03/23","Mon 13/11/23",0.95,"RP-234025","RP-233392","Christian Bergljung, Ericsson","Christian.Bergljung@ericsson.com","; 7/6/23: Compl:0%->25%; ;...; 6/9/23: Compl:25%->50%; WID: RP-230813->RP-231469; Stat Rep: ->RP-231756; Rapporteur: Ericsson->Christian Bergljung, Ericsson; Rap eMail: ->Christian.Bergljung@ericsson.com; ; 8/12/23: FCD:12/12/2023->01/03/2024; Compl:50%->",null,99,50,null,null,"Fri 07/04/23","Fri 08/12/23"]
[1325,981042,"Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18",1,"Rel-18",null,"Tue 13/12/22","Fri 06/06/25",1,"RP-240251",null,"ZTE ",null,"29/3/23: WID:RP-223541->RP-230137; 6/10/23: WID:RP-230137->RP-231844; 2/1/24: WID:RP-231844->RP-234004; 2/4/24: WID:RP-234004->RP-240251",null,98,50,null,null,"Mon 09/01/23","Tue 02/04/24"]
[1326,981142,"   Core part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-Core",2,"Rel-18","R4","Tue 13/12/22","Fri 01/03/24",1,"RP-240251","RP-240252","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ; 8/12/23: FCD:12/12/2023-...",null,98,50,null,null,"Mon 09/01/23","Thu 14/03/24"]
[1327,981242,"   Stopped - Perf. part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-Perf",2,"Rel-18","R4","Tue 13/12/22","Fri 01/03/24",1,"RP-240251","RP-240252","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ; 8/12/23: FCD:12/12/2023-...",null,98,50,null,null,"Mon 09/01/23","Tue 02/04/24"]
[1328,1040102,"   UE Conformance - 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 06/06/25",1,"RP-250164","RP-250990","ZTE ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->13%; Stat Rep: ->RP-241772; ; 6/12/24: Compl:13%->52%; Stat Rep: RP-241772->RP-242810; ; 24/1/25: WID:RP-241093->RP-242811; 6/3/25: FCD:14/02/2025->06/06/2025; Compl:52%->95%; Stat Rep: RP-242810->RP-250163; ",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1329,970085,"High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18",1,"Rel-18",null,"Mon 12/09/22","Fri 06/06/25",0.72,"RP-223499",null,"CMCC ",null,"9/1/23: WID:RP-222351->RP-223499",null,97,49,null,null,"Wed 19/10/22","Mon 09/01/23"]
[1330,970185,"   Core part: High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-Core",2,"Rel-18","R4","Mon 12/09/22","Tue 12/12/23",1,"RP-223499","RP-233448","Chunxia Guo, CMCC","guochunxia@chinamobile.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->30%; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-223053->RP-230280; 17/3/23: 38.895 added;; ;...;...","38.895",97,49,null,null,"Wed 19/10/22","Fri 08/12/23"]
[1331,970285,"   Perf. part: High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-Perf",2,"Rel-18","R4","Tue 31/01/23","Tue 12/12/23",0,"RP-223499","RP-223053","Chunxia Guo, CMCC","guochunxia@chinamobile.com","9/12/22: FCD:12/12/2023->01/12/2023; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; ",null,97,49,null,null,"Wed 19/10/22","Fri 09/12/22"]
[1332,1000053,"   UE Conformance - High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-UEConTest",2,"Rel-18","R5","Thu 08/06/23","Fri 06/06/25",1,"RP-241199","RP-241200","Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei","songdan@chinamobile.com, haoyuxin@huawei.com","21/9/23: Compl:0%->29%; Stat Rep: ->RP-232245; Rapporteur: CMCC->Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei; Rap eMail: ->songdan@chinamobile.com, haoyuxin@huawei.com; ; 8/12/23: Compl:29%->35%; Stat Rep: RP-232245->RP-233416; ; 14/3/24: FCD:05/...",null,100,51,null,null,"Thu 29/06/23","Tue 23/07/24"]
[1333,970086,"High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18",1,"Rel-18",null,"Mon 12/09/22","Thu 12/12/24",0.68,"RP-241314",null,"China Unicom ",null,"9/1/23: WID:RP-222625->RP-222967; 29/3/23: WID:RP-222967->RP-230352; 6/10/23: WID:RP-230352->RP-232216; 2/1/24: WID:RP-232216->RP-233031; 2/4/24: WID:RP-233031->RP-240120; 23/7/24: WID:RP-240120->RP-241314",null,97,49,null,null,"Wed 19/10/22","Tue 23/07/24"]
[1334,970186,"   Core part: High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-Core",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-241314","RP-241315","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; 17/3/23: ...;...","38.896",97,49,null,null,"Wed 19/10/22","Thu 13/06/24"]
[1335,970286,"   Perf. part: High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-Perf",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-241314","RP-241315","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; ;...; 6/9/23:...",null,97,49,null,null,"Wed 19/10/22","Thu 13/06/24"]
[1336,1000051,"   UE Conformance - High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-UEConTest",2,"Rel-18","R5","Thu 08/06/23","Tue 09/09/25",0.34,"RP-232774","RP-251508","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","6/9/23: Compl:0%->5%; Stat Rep: ->RP-231549; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ; 8/12/23: Stat Rep: RP-231549->RP-232773; ; 2/1/24: WID:RP-230869->RP-232774; 14/3/24: FCD:05/06/2024->12/12/2024; Compl:...",null,100,51,null,null,"Thu 29/06/23","Fri 06/06/25"]
[1337,970087,"High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18",1,"Rel-18",null,"Mon 12/09/22","Thu 06/06/24",1,"RP-241254",null,"Huawei ",null,"9/1/23: WID:RP-222647->RP-223356; 29/3/23: WID:RP-223356->RP-230479; 6/10/23: WID:RP-230479->RP-232377; 2/1/24: WID:RP-232377->RP-233975; 2/4/24: WID:RP-233975->RP-240428; 23/7/24: WID:RP-240428->RP-241254",null,97,49,null,null,"Wed 19/10/22","Tue 23/07/24"]
[1338,970187,"   Core part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18-Core",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-241254","RP-241253","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->20%; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->30%; W.....","38.897",97,49,null,null,"Wed 19/10/22","Thu 13/06/24"]
[1339,970287,"   Stopped - Perf. part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18-Perf",2,"Rel-18","R4","Tue 13/09/22","Fri 01/03/24",1,"RP-240428","RP-233204","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","9/12/22: FCD:12/12/2023->01/12/2023; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: WID: RP-223356->RP- 223356; Stat Rep: RP-223355->RP-230478; ; ...",null,97,49,102,null,"Wed 19/10/22","Tue 02/01/24"]
[1340,970089,"Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18",1,"Rel-18",null,"Mon 12/09/22","Thu 06/06/24",1,"RP-241302",null,"China Telecom ",null,"9/1/23: WID:RP-222623->RP-223496; 29/3/23: WID:RP-223496->RP-230309; 6/10/23: WID:RP-230309->RP-232256; 2/1/24: WID:RP-232256->RP-233561; 2/4/24: WID:RP-233561->RP-240763; 23/7/24: WID:RP-240763->RP-241302",null,97,49,null,null,"Wed 19/10/22","Tue 23/07/24"]
[1341,970189,"   Core part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18-Core",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-241302","RP-241303","Lei GAO, China Telecom","gaol8@chinatelecom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222941->RP-230310; ...;...","38.899",97,49,null,null,"Wed 19/10/22","Thu 13/06/24"]
[1342,970289,"   Stopped: Perf. part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18-Perf",2,"Rel-18","R4","Mon 12/09/22","Mon 12/09/22",1,"RP-241302","RP-241303","Lei GAO, China Telecom","gaol8@chinatelecom.cn","9/12/22: FCD:12/12/2023->01/12/2022; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:01/12/2022->12/12/2023; Stat Rep: RP-222941->RP-230310; ;...; 6/9/23: WID: RP-230309->RP-23...",null,97,49,null,null,"Wed 19/10/22","Tue 23/07/24"]
[1343,970090,"Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18",1,"Rel-18",null,"Mon 12/09/22","Thu 06/06/24",1,"RP-241317",null,"China Unicom ",null,"9/1/23: WID:RP-222626->RP-222968; 29/3/23: WID:RP-222968->RP-230354; 2/1/24: WID:RP-230354->RP-234017; 2/4/24: WID:RP-234017->RP-240123; 23/7/24: WID:RP-240123->RP-241317",null,97,49,null,null,"Wed 19/10/22","Tue 23/07/24"]
[1344,970190,"   Core part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18-Core",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-241317","RP-241318","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; 17/3/23: ...;...","38.850",97,49,null,null,"Wed 19/10/22","Thu 13/06/24"]
[1345,970290,"   Stopped - Perf. Part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18-Perf",2,"Rel-18","R4","Mon 12/09/22","Fri 01/03/24",1,"RP-240123","RP-241318","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; ;...; 6/9/23:...",null,97,49,102,null,"Wed 19/10/22","Thu 13/06/24"]
[1346,970083,"Adding new channel bandwidth(s) support to existing NR bands ","NR_bands_R18_BWs",1,"Rel-18",null,"Thu 08/09/22","Fri 01/03/24",1,"RP-232952",null,"Ericsson ",null,"9/1/23: WID:RP-222629->RP-222898; 29/3/23: WID:RP-222898->RP-230756; 6/10/23: WID:RP-230756->RP-231706; 2/1/24: WID:RP-231706->RP-232952",null,97,49,null,null,"Fri 23/09/22","Tue 02/01/24"]
[1347,970183,"   Core part: Adding new channel bandwidth(s) support to existing NR bands ","NR_bands_R18_BWs-Core",2,"Rel-18","R4","Thu 08/09/22","Fri 01/03/24",1,"RP-232952","RP-240275","Dominique Everaere, Ericsson","dominique.everaere@erisson.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->2%; Stat Rep: ->RP-222899; Rapporteur: Ericsson->Dominique Everaere, Ericsson; Rap eMail: ->dominique.everaere@erisson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2%->5%; Stat Rep: RP-222899->RP-230.....",null,97,49,null,null,"Fri 23/09/22","Thu 14/03/24"]
[1348,970081,"Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs ","NR_MIMO_OTA_enh",1,"Rel-18","R4","Thu 08/09/22","Fri 06/06/25",1,"RP-240736",null,"CAICT ",null,"9/1/23: WID:RP-222668->RP-223509; 6/10/23: WID:RP-223509->RP-232679; 6/10/23: 38.761 added;; 2/1/24: WID:RP-232679->RP-233742; 2/4/24: WID:RP-233742->RP-240736","38.761",97,49,null,null,"Fri 23/09/22","Tue 02/04/24"]
[1349,970181,"   Core part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs ","NR_MIMO_OTA_enh-Core",2,"Rel-18","R4","Thu 08/09/22","Tue 12/12/23",1,"RP-240736","RP-241290","Zhu, Siting, CAICT","zhusiting@caict.ac.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->35%; Stat Rep: RP-223185->RP-230367; ...; 6/9/23: Com...",null,97,49,null,null,"Fri 23/09/22","Thu 13/06/24"]
[1350,970281,"   Perf. Part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs ","NR_MIMO_OTA_enh-Perf",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-240736","RP-241290","Zhu, Siting, CAICT","zhusiting@caict.ac.cn","9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: Stat Rep: RP-223185->RP-230367; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat Rep: RP-2303...",null,97,49,null,null,"Fri 23/09/22","Thu 13/06/24"]
[1351,1040112,"   UE Conformance - Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirements for NR UEs ","NR_MIMO_OTA_enh-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 06/06/25",1,"RP-241504","RP-251177","Apple ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->45%; ; 6/12/24: Compl:45%->65%; Stat Rep: ->RP-242479; ; 6/3/25: FCD:14/02/2025->06/06/2025; Compl:65%->80%; Stat Rep: RP-242479->RP-250154; ; 6/6/25: Compl:80%->100%; Stat Rep: RP-250154->RP-251177; ",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1352,981047,"Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18",1,"Rel-18",null,"Tue 13/12/22","Fri 01/03/24",1,"RP-240796",null,"CMCC ",null,"29/3/23: WID:RP-223553->RP-230719; 6/10/23: WID:RP-230719->RP-232688; 2/1/24: WID:RP-232688->RP-233446; 2/4/24: WID:RP-233446->RP-240796",null,98,50,null,null,"Mon 09/01/23","Tue 02/04/24"]
[1353,981147,"   Core part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18-Core",2,"Rel-18","R4","Tue 13/12/22","Fri 01/03/24",1,"RP-240796","RP-240159","Xiaoran ZHANG, CMCC","zhangxiaoran@chinamobile.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 17/3/23: 38.718-00-02 added;; 31/3/23: Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->50%; Stat Rep: RP-230718->...","38.718-00-02",98,50,null,null,"Mon 09/01/23","Thu 14/03/24"]
[1354,981247,"   Stopped - Perf. part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18-Perf",2,"Rel-18","R4","Tue 13/12/22","Fri 01/03/24",1,"RP-240796","RP-233445","Xiaoran ZHANG, CMCC","zhangxiaoran@chinamobile.com","17/3/23: FCD:12/12/2023->06/06/2024; Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 31/3/23: FCD:06/06/2024->12/12/2023; Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->...",null,98,50,null,null,"Mon 09/01/23","Tue 02/04/24"]
[1355,941012,"NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.92,"RP-234027",null,"Nokia",null,"5/4/22: WID:RP-213603->RP-220401; 23/9/22: WID:RP-220401->RP-222645; 29/3/23: WID:RP-222645->RP-230186; 6/10/23: WID:RP-230186->RP-231713; 2/1/24: WID:RP-231713->RP-234027",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1356,941112,"   Core part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Core",2,"Rel-18","R4","Mon 13/12/21","Tue 12/12/23",1,"RP-234027","RP-232749","Man Hung Ng, Nokia","man_hung.ng@nokia.com","; 22/3/22: Stat Rep: ->RP-220402 6/6/22: CD:12/12/2023->13/12/2022 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: FCD:13/12/2022->23/12/2022; Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: FCD:23/12/20...;...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1357,941212,"   Perf. part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Perf",2,"Rel-18","R4","Wed 15/12/21","Thu 06/06/24",1,"RP-233963","RP-240063","Man Hung Ng, Nokia","man_hung.ng@nokia.com","; 22/3/22: CD:23/06/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220402 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: ...;...",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[1358,1030060,"   UE Conformance - NR support for dedicated spectrum less than 5MHz for FR1 ","NR_FR1_lessthan_5MHz_BW-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.78,"RP-240044","RP-250881","Nokia ",null,"13/6/24: Compl:0%->22%; Stat Rep: ->RP-240908; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:22%->43%; Stat Rep: RP-240908->RP-241737; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:43%->46%; Stat Rep: RP-241737->RP-242457; ; 6/3/25: FCD:28/05/2025->12/12/202",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1359,940093,"Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh",1,"Rel-18",null,"Mon 13/12/21","Thu 06/06/24",1,"RP-232957",null,"Ericsson",null,"compare REL-17 WI NR_DSS-Core; 12/7/22: WID:RP-213575->RP-221622; 2/1/24: WID:RP-221622->RP-232957",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1360,940193,"   Core part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Core",2,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-232957","RP-232956","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","compare REL-17 WI NR_DSS-Core; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1361,940293,"   Perf. part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Perf",2,"Rel-18","R1","Wed 15/12/21","Thu 06/06/24",1,"RP-232957","RP-241174","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220589->RP-221621; 20/6/22: WG: R4->R1; Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson...",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[1362,940094,"Multi-carrier enhancements for NR","NR_MC_enh",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.98,"RP-234012",null,"NTT DOCOMO",null,"5/4/22: WID:RP-213577->RP-220834; 12/7/22: WID:RP-220834->RP-221435; 23/9/22: WID:RP-221435->RP-222251; 2/1/24: WID:RP-222251->RP-234012",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1363,940194,"   Core part: Multi-carrier enhancements for NR","NR_MC_enh-Core",2,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-240321","RP-241266","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada.sv@nttdocomo.com","; 22/3/22: CD:23/06/2023->12/06/2023; 22/3/22: Stat Rep: ->RP-220616 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:23/12/2022->12/20 ...; 23/9/22: WID:RP-...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[1364,940294,"   Perf. part: Multi-carrier enhancements for NR","NR_MC_enh-Perf",2,"Rel-18","R1","Wed 15/12/21","Thu 06/06/24",1,"RP-240321","RP-241266","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada.sv@nttdocomo.com","; 22/3/22: Stat Rep: ->RP-220616 6/6/22: CD:12/12/2023->24/06/2022 6/6/22: Stat Rep: RP-220616->RP-221436; 20/6/22: WG: R4->R1; Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:24/06/2...;...",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[1365,1030070,"   UE Conformance - Multi-carrier enhancements for NR ","NR_MC_enh-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.95,"RP-240346","RP-251460","China Telecom ",null,"13/6/24: Compl:0%->18%; Stat Rep: ->RP-241301; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:18%->80%; Stat Rep: RP-241301->RP-242000; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:80%->87%; Stat Rep: RP-242000->RP-242852; ; 6/3/25: FCD:28/05/2025->12/12/202",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1366,940095,"Further NR coverage enhancements","NR_cov_enh2",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.91,"RP-241295",null,"China Telecom",null,"compare REL-17 WI NR_cov_enh; 5/4/22: WID:RP-213579->RP-220937; 12/7/22: WID:RP-220937->RP-221858; 2/1/24: WID:RP-221858->RP-233558; 23/7/24: WID:RP-233558->RP-241295",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[1367,940195,"   Core part: Further NR coverage enhancements","NR_cov_enh2-Core",2,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-241295","RP-233557","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","compare REL-17 WI NR_cov_enh; 22/3/22: Stat Rep: ->RP-220566 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: WID: RP-220937->RP- 220937 ; 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: Rapporteur: China Telecom->Nanxi LI, China Telecom; Rap eMail: ->li...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1368,940295,"   Perf. part: Further NR coverage enhancements","NR_cov_enh2-Perf",2,"Rel-18","R1","Wed 15/12/21","Thu 06/06/24",1,"RP-241295","RP-241294","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220566 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: WID: RP-220937->RP- 220937 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: WG: R4->R1; Rapporteur: China Telecom->Nanxi LI, China Telecom; R...",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[1369,1030069,"   UE Conformance - Further NR coverage enhancements ","NR_cov_enh2-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.76,"RP-240345","RP-251459","China Telecom ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241300; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->28%; Stat Rep: RP-241300->RP-241992; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:28%->29%; Stat Rep: RP-241992->RP-242851; ; 6/3/25: FCD:28/05/2025->12/12/2025;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1370,940096,"NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.85,"RP-233028",null,"Samsung",null,"compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 9/1/23: WID:RP-213598->RP-223276; 2/1/24: WID:RP-223276->RP-233028",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1371,940196,"   Core part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Core",2,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-233028","RP-232913","Eko Onggosanusi, Samsung","eko.o@samsung.com","compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 22/3/22: Stat Rep: ->RP-220669 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/22: FCD:23/12/2022->12/20 ;...; 9/12/22: FCD:23/12/202...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1372,940296,"   Perf. part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Perf",2,"Rel-18","R1","Wed 15/12/21","Thu 06/06/24",1,"RP-233028","RP-241282","Eko Onggosanusi, Samsung","eko.o@samsung.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220669 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: Stat Rep: RP-220669->RP-221393; 20/6/22: WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/...;...",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[1373,1030072,"   UE Conformance - NR MIMO evolution for downlink and uplink ","NR_MIMO_evo_DL_UL-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.59,"RP-250103","RP-251019","Samsung ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241279; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->19%; Stat Rep: RP-241279->RP-241982; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:19%->37%; Stat Rep: RP-241982->RP-242596; ; 6/3/25: FCD:28/05/2025->12/12/2025;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1374,940082,"Study on evolution of NR duplex operation","FS_NR_duplex_evo",1,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-223041","RP-233435","Fei WANG, CMCC","wangfei@chinamobile.com","21/1/22: 38.858 added;; 22/3/22: Stat Rep: ->RP-220632; 5/4/22: WID:RP-213591->RP-220633 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: CMCC->Fei WANG, CMCC; Rap eMail: ->wangfei@chinamobile.com12/7/22: WID:RP-220633->RP-221352; 13/7/22: FCD:23/12...; 23/...","38.858",94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1375,970079,"NR network-controlled repeaters ","NR_netcon_repeater",1,"Rel-18",null,"Thu 08/09/22","Thu 06/06/24",1,"RP-232886",null,"ZTE ",null,"9/1/23: WID:RP-222673->RP-223505; 29/3/23: WID:RP-223505->RP-230175; 2/1/24: WID:RP-230175->RP-232886",null,97,49,null,null,"Fri 23/09/22","Tue 02/01/24"]
[1376,970179,"   Core part: NR network-controlled repeaters ","NR_netcon_repeater-Core",2,"Rel-18","R1","Thu 08/09/22","Tue 12/12/23",1,"RP-232886","RP-240930","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->80%; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:80%->90%; WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP.....",null,97,49,null,null,"Fri 23/09/22","Thu 13/06/24"]
[1377,970279,"   Perf. part: NR network-controlled repeaters ","NR_netcon_repeater-Perf",2,"Rel-18","R1","Mon 12/09/22","Thu 06/06/24",1,"RP-232886","RP-240930","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","9/12/22: WG: R4->R1; FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP-230174; ...; 6/9/23: FCD:06/06/2023->06/06/2024;...",null,97,49,null,null,"Fri 23/09/22","Tue 23/07/24"]
[1378,940083,"   Study on NR network-controlled repeaters","FS_NR_netcon_repeater",2,"Rel-18","R1","Thu 08/09/22","Wed 05/06/24",1,"RP-221229","RP-221231","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","compare REL-17 WI NR_repeaters; TR 38.8xx; 21/1/22: 38.867 added;; 22/3/22: Stat Rep: ->RP-220214 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn12/7/22: WID:RP-213700->RP-221229 ;...; 23/9/22: 0%->10","38.867",94,48,null,null,"Thu 06/01/22","Fri 23/09/22"]
[1379,940098,"Further NR mobility enhancements","NR_Mob_enh2",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.9,"RP-233970",null,"MediaTek",null,"compare REL-16 WI NR_Mob_enh; 12/7/22: WID:RP-213565->RP-221799; 23/9/22: WID:RP-221799->RP-222332; 9/1/23: WID:RP-222332->RP-223520; 2/1/24: WID:RP-223520->RP-233970",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1380,940198,"   Core part: Further NR mobility enhancements","NR_Mob_enh2-Core",2,"Rel-18","R2","Mon 13/12/21","Fri 01/03/24",1,"RP-233970","RP-241347","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","compare REL-16 WI NR_Mob_enh; 22/3/22: CD:12/12/2023->12/09/2023; 22/3/22: Stat Rep: ->RP-220760 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Re ; 20/6/22: Acronym:NR_Mob_enh2-Core->NR_mob_enh2-Core; Rapporteur: MediaTek->Li-Chuan Tseng, MediaTek Inc...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[1381,940298,"   Perf. part: Further NR mobility enhancements","NR_Mob_enh2-Perf",2,"Rel-18","R2","Wed 15/12/21","Thu 06/06/24",1,"RP-233970","RP-241347","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","; 22/3/22: CD:24/06/2024->12/12/2023; 22/3/22: Stat Rep: ->RP-220760 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220760->RP-221557; 20/6/22: Acronym:NR_Mob_enh2-Perf->NR_mob_enh2-Perf; WG: R4->R2; Rapporteur: MediaTek->Li-Chuan Tseng, Me...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[1382,1040108,"   UE Conformance - Further NR mobility enhancements ","NR_Mob_enh2-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 12/12/25",0.7,"RP-241348","RP-251291","Mediatek ",null,"4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->20%; Stat Rep: ->RP-242047; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:20%->40%; Stat Rep: RP-242047->RP-242990; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:40%->55%; Stat Rep: RP-242990->RP-250475; ; 6/6/2",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1383,941003,"In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh",1,"Rel-18",null,"Mon 13/12/21","Fri 05/06/26",0.73,"RP-233485",null,"Xiaomi",null,"MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 12/7/22: WID:RP-213589->RP-221281; 2/1/24: WID:RP-221281->RP-233485",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1384,941103,"   Core part: In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-233485","RP-233484","Yumin Wu, Xiaomi","wuyumin@xiaomi.com","MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 20/6/22: Acronym:NR_IDC_enh-Core->NR_IDC_Enh-Core; FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221280; Rapporteur: Xiaomi->Yumin Wu, Xiaomi; Rap eMail: ->wuyumin@xiaomi.com13/7/22: FCD:23/12/2022->1...;...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1385,1040104,"   UE Conformance - In-Device Co-existence (IDC) enhancements for NR and MR-DC ","NR_IDC_enh-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 05/06/26",0.55000000000000004,"RP-241195","RP-251377","CMCC ",null,"4/9/24: FCD:06/06/2026->26/06/2025; Compl:0%->5%; Stat Rep: ->RP-241948; ; 6/12/24: FCD:06/06/2025->05/06/2026; Compl:5%->18%; Stat Rep: RP-241948->RP-242978; ; 6/3/25: FCD:23/10/2025->05/06/2026; Compl:18%->39%; Stat Rep: RP-242978->RP-250252; ; 6/6/25:",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1386,950072,"BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh",1,"Rel-18",null,"Tue 15/03/22","Tue 12/12/23",1,"RP-233976",null,"Ericsson ",null,"compare REL-15 WI AASenh_BS_LTE_UTRA ; 2/1/24: WID:RP-220916->RP-233976",null,95,48,null,null,"Tue 05/04/22","Tue 02/01/24"]
[1387,950172,"   Core part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-233976","RP-233683","Aurelian Bria, Ericsson","Aurelian.Bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA ; 6/6/22: CD:15/06/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/09/2022->09/20 ;...; 9/12/22: FCD...",null,95,48,null,null,"Tue 05/04/22","Fri 08/12/23"]
[1388,950272,"   Perf. part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Perf",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-233976","RP-233683","Aurelian Bria, Ericsson","Aurelian.Bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/12/2022->12/20...; 9/12/22: FCD:23/12...",null,95,48,null,null,"Tue 05/04/22","Fri 08/12/23"]
[1389,950075,"Air-to-ground network for NR ","NR_ATG",1,"Rel-18",null,"Tue 15/03/22","Fri 06/06/25",0.84,"RP-240732",null,"CMCC ",null,"TR 38.8xx ; 12/7/22: WID:RP-220962->RP-221369; 29/3/23: WID:RP-221369->RP-230279; 2/1/24: WID:RP-230279->RP-234023; 2/4/24: WID:RP-234023->RP-240732",null,95,48,null,null,"Tue 05/04/22","Tue 02/04/24"]
[1390,950175,"   Core part: Air-to-ground network for NR ","NR_ATG-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-240732","RP-240158","Guo Chunxia, CMCC","guochunxia@chinamobile.com","TR 38.8xx 6/6/22: CD:15/12/2023->23/12/20226/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep...",null,95,48,null,null,"Tue 05/04/22","Thu 14/03/24"]
[1391,950275,"   Perf. part: Air-to-ground network for NR ","NR_ATG-Perf",2,"Rel-18","R4","Wed 16/03/22","Fri 01/03/24",1,"RP-240732","RP-240158","Guo Chunxia, CMCC","guochunxia@chinamobile.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:24/03/2023->03/20 ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-221370->RP-2230...",null,95,48,null,null,"Tue 05/04/22","Thu 14/03/24"]
[1392,1020087,"   UE Conformance - Air-to-ground network for NR ","NR_ATG-UEConTest",2,"Rel-18","R5","Wed 13/12/23","Fri 12/12/25",0.64,"RP-240750","RP-251379","Dan SONG, CMCC","songdan@chinamobile.com","14/3/24: Compl:0%->50%; Stat Rep: ->RP-240148; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com; ; 2/4/24: WID:RP-233412->RP-240750. corrected: Rel-19->Rel-18; 13/6/24: WID: RP-240750->RP-233412; Stat Rep: RP-240148->RP-241201; ; ...",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[1393,950076,"NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3",1,"Rel-18",null,"Tue 15/03/22","Mon 03/03/25",0.86,"RP-240940",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 ; 12/7/22: WID:RP-220967->RP-221862; 23/9/22: WID:RP-221862->RP-222228; 9/1/23: WID:RP-222228->RP-222909; 2/1/24: WID:RP-222909->RP-232791; 23/7/24: WID:RP-232791->RP-240940",null,95,48,null,null,"Tue 05/04/22","Tue 23/07/24"]
[1394,950176,"   Core part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-240940","RP-240939","Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi","hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com","compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:23/12/2022->12/20...;...","38.891",95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1395,950276,"   Perf. part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Perf",2,"Rel-18","R4","Tue 15/03/22","Thu 06/06/24",1,"RP-240940","RP-240939","Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi","hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com","; 6/6/22: CD:15/03/2024->24/03/2023 ; 6/6/22: Stat Rep: ->RP-221207; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:24/03/2023->03/20 ; ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Compl:10%...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1396,1030065,"   UE Conformance - NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.65,"RP-240125","RP-251506","Apple ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241175; ; 4/9/24: FCD:03/03/2025->25/03/2025; Compl:5%->15%; Stat Rep: RP-241175->RP-242219; ; 6/12/24: Compl:15%->40%; Stat Rep: RP-242219->RP-242600; ; 6/3/25: FCD:12/11/2024->06/06/2025; Stat Rep: RP-242600->RP-250",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1397,950077,"Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL",1,"Rel-18",null,"Tue 15/03/22","Thu 30/11/23",0.75,"RP-241534","RP-223153","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","; 12/7/22: WID:RP-220974->RP-221753; 9/12/22: Acronym:NR_FR2_multiRX_DL->FS_NR_FR2_OTA_enh; FCD:01/03/2024->01/12/2023; Compl:11%->25%; WID: RP-221753->RP-222652; Stat Rep: ->RP-223153; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail:...",null,95,48,null,null,"Tue 05/04/22","Tue 23/07/24"]
[1398,950177,"   Core part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-241534","RP-241535","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/09/2023->23/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qti.qualcomm.com13/7/22: FC...;...","38.751",95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1399,950277,"   Perf. part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Perf",2,"Rel-18","R4","Tue 15/03/22","Thu 06/06/24",1,"RP-241534","RP-241535","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/03/2024->24/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: FCD:24/09/2022->24/03/2023; Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qt...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1400,1040113,"   UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 12/12/25",0.3,"RP-241653","RP-251232","Qualcomm ",null,"4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->5%; Stat Rep: ->RP-242040; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:5%->9%; Stat Rep: RP-242040->RP-242898; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:9%->20%; Stat Rep: RP-242898->RP-250396; ; 6/6/25: C",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1401,950078,"Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3",1,"Rel-18",null,"Tue 15/03/22","Thu 06/06/24",1,"RP-233496",null,"Apple ",null,"compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 12/7/22: WID:RP-220977->RP-221696; 2/1/24: WID:RP-221696->RP-233496",null,95,48,null,null,"Tue 05/04/22","Tue 02/01/24"]
[1402,950178,"   Core part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-221696","RP-241267","Jie Cui, Apple","jie_cui@apple.com","compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221697; Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:23/12/2022->12/20; ...; 9/1...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1403,950278,"   Perf. part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Perf",2,"Rel-18","R4","Thu 17/03/22","Thu 06/06/24",1,"RP-221696","RP-241267","Jie Cui, Apple","jie_cui@apple.com","6/6/22: CD:15/06/2024->24/06/2022 6/6/22: Stat Rep: ->RP-221697; 20/6/22: Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD:24/06/2023->01/06/2024; WID: RP-220977->RP-221696; Stat ...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1404,950080,"Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2",1,"Rel-18",null,"Tue 15/03/22","Fri 06/06/25",0.82,"RP-233186",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh ; 12/7/22: WID:RP-220987->RP-221496; 9/1/23: WID:RP-221496->RP-223478; 29/3/23: WID:RP-223478->RP-230753; 6/10/23: WID:RP-230753->RP-232366; 2/1/24: WID:RP-232366->RP-233186",null,95,48,null,null,"Tue 05/04/22","Tue 02/01/24"]
[1405,950180,"   Core part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-233186","RP-233185","Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC.","leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com","compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:23/12/2022->12/20; 13/7...;...","38.881",95,48,null,null,"Tue 05/04/22","Fri 08/12/23"]
[1406,950280,"   Perf. part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Perf",2,"Rel-18","R4","Tue 15/03/22","Thu 06/06/24",1,"RP-232366","RP-241240","Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC.","leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:24/06/2022->06/20 ; ;...; 9/12/22: FCD:23/06/2023->31/05/2024; Compl:10%->20...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1407,1030066,"   UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1 ","NR_ENDC_RF_FR1_enh2-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.54,"RP-240290","RP-251488","Huawei ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241377; ; 4/9/24: FCD:06/06/2025->25/06/2025; Compl:5%->12%; Stat Rep: RP-241377->RP-242074; ; 6/12/24: Compl:12%->34%; Stat Rep: RP-242074->RP-243091; ; 6/3/25: FCD:17/01/2025->12/12/2025; Compl:34%->35%; Stat Rep: R",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1408,950081,"Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA",1,"Rel-18",null,"Tue 15/03/22","Tue 12/12/23",0.97,"RP-233513",null,"KDDI ",null,"; 12/7/22: WID:RP-221012->RP-221809; 23/9/22: WID:RP-221809->RP-222309; 29/3/23: WID:RP-222309->RP-230742; 2/1/24: WID:RP-230742->RP-233513",null,95,48,null,null,"Tue 05/04/22","Tue 02/01/24"]
[1409,950181,"   Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 30/05/23",0.95,"RP-233513","RP-232113","Yasuki Suzuki, KDDI","ui-suzuki@kddi.com","; 20/6/22: FCD:15/09/2023->23/09/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:10%->20%; Stat Rep: RP-221742->RP-222956;...",null,95,48,null,null,"Tue 05/04/22","Wed 06/09/23"]
[1410,950281,"   Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Perf",2,"Rel-18","R4","Wed 16/03/22","Tue 12/12/23",1,"RP-233513","RP-232113","Yasuki Suzuki, KDDI","ui-suzuki@kddi.com","; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: RP-221742->RP-222956; Rapporteur: Yas...",null,95,48,null,null,"Tue 05/04/22","Tue 02/04/24"]
[1411,950082,"Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2",1,"Rel-18",null,"Tue 15/03/22","Fri 12/12/25",0.86,"RP-234021",null,"MediaTek ",null,"compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 5/4/22: WID:RP-221018 ->RP-220772; 23/9/22: WID:RP-220772->RP-222337; 29/3/23: WID:RP-222337->RP-230755; 6/10/23: WID:RP-230755->RP-232440; 2/1/24: WID:RP-232440->RP-234021",null,95,48,null,null,"Tue 05/04/22","Tue 02/01/24"]
[1412,950182,"   Core part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-232440","RP-241349","Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, meng.zhang@intel.com","compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 20/6/22: FCD:15/12/2023->23/12/2022; WID: RP-220772->RP-221018; Stat Rep: ->RP-221560; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1413,950282,"   Perf. part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Perf",2,"Rel-18","R4","Tue 15/03/22","Thu 06/06/24",1,"RP-232440","RP-241349","Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, meng.zhang@intel.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: WID: RP-220772->RP-221018 ; 6/6/22: Stat Rep: ->RP-221560; 20/6/22: Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui.huang@int...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1414,1050132,"   UE Conformance - Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-UEConTest",2,"Rel-18","R5","Mon 09/09/24","Fri 12/12/25",0.55000000000000004,"RP-242046","RP-251293","Mediatek ",null,"6/12/24: Compl:0%->10%; Stat Rep: ->RP-242994; ; 24/1/25: WID:RP-242046->RP-242995; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:10%->35%; WID: RP-242995->RP-242046; Stat Rep: RP-242994->RP-250477; ; 6/6/25: Compl:35%->55%; Stat Rep: RP-250477->RP-251293; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[1415,941001,"Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM",1,"Rel-18","R2","Mon 13/12/21","Fri 06/06/25",1,"RP-233071",null,"vivo",null,"compare REL-17 WI LTE_NR_MUSIM-Core; no Perf. part; 5/4/22: WID:RP-213584->RP-220955; 9/1/23: WID:RP-220955->RP-223492; 29/3/23: WID:RP-223492->RP-230751; 2/1/24: WID:RP-230751->RP-233071",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1416,941101,"   Core part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-233071","RP-233070","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","6/6/22: CD:12/09/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221273; 20/6/22: Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: RP...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1417,950283,"   Perf. Part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Perf",2,"Rel-18","R2","Tue 15/03/22","Thu 06/06/24",1,"RP-231461","RP-241045","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","20/6/22: WG: R4->R2; FCD:14/06/2024->24/06/2022; Stat Rep: ->RP-221273; Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:24/06/2022->06/20 ;...; 17/3/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-221273->RP-2303...",null,95,48,null,null,"Sat 04/06/22","Thu 13/06/24"]
[1418,1030061,"   UE Conformance - Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR ","NR_DualTxRx_MUSIM-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 06/06/25",1,"RP-240045","RP-250894","China Telecom ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-240909; ; 4/9/24: FCD:06/06/2025->25/06/2025; Compl:5%->14%; Stat Rep: RP-240909->RP-241957; ; 6/12/24: Compl:14%->72%; Stat Rep: RP-241957->RP-242471; ; 6/3/25: FCD:17/01/2025->06/06/2025; Compl:72%->90%; Stat Rep: R",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1419,0,"Rel-18 NR-only: band related","-",1,"Rel-18",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1420,991042,"Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76",1,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-233245",null,"Vodafone",null,"6/10/23: WID:RP-230791->RP-232636; 2/1/24: WID:RP-232636->RP-233245",null,99,50,null,null,"Fri 07/04/23","Tue 02/01/24"]
[1421,991142,"   Core part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76-Core",2,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-233245","RP- 233244","Wael Boukley Hasan, Vodafone","Wael.boukleyhasan@vodafone.com","; 7/6/23: Compl:0%->43%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:43%->80%; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:22/09/2023->1...",null,99,50,null,null,"Fri 07/04/23","Fri 08/12/23"]
[1422,991242,"   Perf. part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76-Perf",2,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-233245","RP- 233244","Wael Boukley Hasan, Vodafone","Wael.boukleyhasan@vodafone.com","6/9/23: FCD:09/09/2023->23/09/2023; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:23/09/2023->12/12/2023; Stat Rep: RP-231747->RP-232630; ;",null,99,50,null,null,"Fri 07/04/23","Fri 08/12/23"]
[1423,991044,"Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor",1,"Rel-18","R4","Mon 06/03/23","Thu 06/06/24",1,"RP-233999",null,"Vodafone",null,"6/10/23: WID:RP-230805->RP-232677; 2/1/24: WID:RP-232677->RP-233999",null,99,50,null,null,"Fri 07/04/23","Tue 02/01/24"]
[1424,991144,"   Core part: Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor-Core",2,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-232677","RP-241057","Diogo Martins, Vodafone","diogo.martins@vodafone.com","; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->60%; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-231924->RP-233039; ; 14/...",null,99,50,null,null,"Fri 07/04/23","Thu 13/06/24"]
[1425,991244,"   Perf. part: Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor-Perf",2,"Rel-18","R4","Wed 08/03/23","Thu 06/06/24",1,"RP-232677","RP-241057","Diogo Martins, Vodafone","diogo.martins@vodafone.com","; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ; 8/12/23: Stat Rep: RP-231924->RP-233039...",null,99,50,null,null,"Fri 07/04/23","Thu 13/06/24"]
[1426,1010055,"Introduction of NR bands n31 and n72 ","NR_bands_n31_n72",1,"Rel-18","R4","Sat 09/09/23","Tue 12/12/23",1,"RP-233950",null,"Nokia ",null,"2/1/24: WID:RP-232691->RP-233950",null,101,51,null,null,"Fri 06/10/23","Tue 02/01/24"]
[1427,1011055,"   Core part: Introduction of NR bands n31 and n72 ","NR_bands_n31_n72-Core",2,"Rel-18","R4","Sat 09/09/23","Tue 12/12/23",1,"RP-233950","RP-233181","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","8/12/23: Compl:0%->100%; Stat Rep: ->RP-233181; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; ",null,101,51,null,null,"Fri 06/10/23","Fri 08/12/23"]
[1428,1012055,"   Perf. part: Introduction of NR bands n31 and n72 ","NR_bands_n31_n72-Perf",2,"Rel-18","R4","Sat 09/09/23","Tue 12/12/23",1,"RP-233950","RP-233181","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","8/12/23: FCD:06/06/2024->12/12/2023; Compl:0%->100%; Stat Rep: ->RP-233181; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; ",null,101,51,null,null,"Fri 06/10/23","Fri 08/12/23"]
[1429,991046,"Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh",1,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-233991",null,"CATT",null,"6/10/23: WID:RP-230764->RP-232680; 2/1/24: WID:RP-232680->RP-233991",null,99,50,null,null,"Fri 07/04/23","Tue 02/01/24"]
[1430,991146,"   Core part: Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh-Core",2,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-233991","RP-233005","Shan Huiping, CATT","shanhuiping@catt.cn","; 7/6/23: Compl:0%->50%; 6/9/23: Compl:50%->80%; WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn; ; 8/12/23: Compl:80%->100%; Stat Rep: RP-231833->RP-233005; ",null,99,50,null,null,"Fri 07/04/23","Fri 08/12/23"]
[1431,991246,"   Stopped - Perf. part: Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh-Perf",2,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-233991","RP-231833","Shan Huiping, CATT","shanhuiping@catt.cn","6/9/23: WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn¦01/24: stopped at 0% at RAN#102",null,99,50,102,null,"Fri 07/04/23","Tue 02/01/24"]
[1432,981044,"Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54",1,"Rel-18",null,"Mon 12/12/22","Fri 03/03/23",1,"RP-230062",null,"Ligado Networks ",null,"29/3/23: WID:RP-223514->RP-230062",null,98,50,null,null,"Mon 09/01/23","Wed 29/03/23"]
[1433,981144,"   Core part: Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54-Core",2,"Rel-18","R4","Mon 12/12/22","Fri 03/03/23",1,"RP-230062","RP-230061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,98,50,null,null,"Mon 09/01/23","Fri 17/03/23"]
[1434,981244,"   Perf. part: Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54-Perf",2,"Rel-18","R4","Mon 12/12/22","Fri 03/03/23",1,"RP-230062","RP-230061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,98,50,null,null,"Mon 09/01/23","Fri 17/03/23"]
[1435,981045,"Introduction of 900 MHz NR band in the US ","NR_900MHz_US",1,"Rel-18",null,"Tue 13/12/22","Tue 22/08/23",0.25,"RP-234044",null,"Anterix ",null,"29/3/23: WID:RP-223529->RP-230723; 2/1/24: WID:RP-230723->RP-234044",null,98,50,null,null,"Mon 09/01/23","Tue 02/01/24"]
[1436,981145,"   Core Part: Introduction of 900 MHz NR band in the US ","NR_900MHz_US-Core",2,"Rel-18","R4","Tue 13/12/22","Tue 22/08/23",0.25,"RP-234044","RP-231956","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","17/3/23: Compl:0%->5%; Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:5%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated; Ra",null,98,50,null,null,"Mon 09/01/23","Thu 21/09/23"]
[1437,981245,"   Perf. part: Introduction of 900 MHz NR band in the US ","NR_900MHz_US-Perf",2,"Rel-18","R4","Tue 13/12/22","Tue 22/08/23",0.25,"RP-234044","RP-231956","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","17/3/23: Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:0%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated; Rap eMail: eolbr",null,98,50,null,null,"Mon 09/01/23","Thu 21/09/23"]
[1438,961010,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241222",null,"ZTE ",null,"23/9/22: WID:RP-221876->RP-222079; 9/1/23: WID:RP-222079->RP-222904; 29/3/23: WID:RP-222904->RP-230133; 6/10/23: WID:RP-230133->RP-231840; 2/1/24: WID:RP-231840->RP-232920; 2/4/24: WID:RP-232920->RP-240761; 23/7/24: WID:RP-240761->RP-241222",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1439,961110,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241222","RP-241223","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","9/9/22: Comp...; 23/9/22: 38.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2.....","38.718-02-01",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1440,961210,"   Stopped - Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-240761","RP-241223","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222905->.....",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1441,961011,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241089",null,"ZTE ",null,"23/9/22: WID:RP-221877->RP-222092; 9/1/23: WID:RP-222092->RP-222834; 29/3/23: WID:RP-222834->RP-230084; 6/10/23: WID:RP-230084->RP-231860; 2/1/24: WID:RP-231860->RP-233231; 2/4/24: WID:RP-233231->RP-240166; 23/7/24: WID:RP-240166->RP-241089",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1442,961111,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241089","RP-241090","Zhifeng Ma, ZTE","ma.zhifeng@zte.com.cn","9/9/22: Comp...; 23/9/22: 38.718-03-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:1.....","38.718-03-01",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1443,961211,"   Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Perf",2,"Rel-18","R4","Thu 16/06/22","Thu 06/06/24",1,"RP-241089","RP-241090","Zhifeng Ma, ZTE","ma.zhifeng@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: Compl:0%->40%; Stat Rep: RP-222835->RP-230085; ...; 6/9/23: Compl:60%->75%; WID: RP...",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1444,961013,"High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101",1,"Rel-18",null,"Thu 01/12/22","Tue 12/12/23",0,"RP-221878",null,"Union Internationale Chemins de Fer (UIC) ",null,null,null,96,49,null,null,"Wed 03/08/22","NA"]
[1445,961113,"   Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101-Core",2,"Rel-18","R4","Thu 01/12/22","Tue 12/12/23",0,"RP-221878","RP-222544","Union Internationale Chemins de Fer (UIC) ",null,null,null,96,49,null,null,"Wed 03/08/22","NA"]
[1446,961007,"Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241140",null,"Ericsson ",null,"23/9/22: WID:RP-221835->RP-222105; 9/1/23: WID:RP-222105->RP-222846; 29/3/23: WID:RP-222846->RP-230067; 6/10/23: WID:RP-230067->RP-231623; 2/1/24: WID:RP-231623->RP-233990; 2/4/24: WID:RP-233990->RP-240238; 23/7/24: WID:RP-240238->RP-241140",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1447,961107,"   Core part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241140","RP-241139","Per Lindell, Ericsson","per.lindell@ericsson.com","9/9/22: CD:1...; 23/9/22: 38.718-01-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/.....","38.718-01-01",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1448,961207,"   Stopped - Perf. part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-241140","RP-241139","Per Lindell, Ericsson","per.lindell@ericsson.com","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:71%->57%; Stat Rep.....",null,96,49,102,null,"Wed 03/08/22","Thu 13/06/24"]
[1449,961008,"Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241327",null,"Ericsson ",null,"23/9/22: WID:RP-221838->RP-222318; 9/1/23: WID:RP-222318->RP-223438; 29/3/23: WID:RP-223438->RP-230421; 6/10/23: WID:RP-230421->RP-231738; 2/1/24: WID:RP-231738->RP-233696; 2/4/24: WID:RP-233696->RP-240501; 23/7/24: WID:RP-240501->RP-241327",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1450,961108,"   Core part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241327","RP-241328","Reihaneh Malekafzaliardakani, Ericsson","reihaneh.malekafzaliardakani@ericsson.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1.....",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1451,961208,"   Perf. part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Perf",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241327","RP-241328","Reihaneh Malekafzaliardakani, Ericsson","reihaneh.malekafzaliardakani@ericsson.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1.....",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1452,960097,"APT 600MHz NR band ","NR_600MHz_APT",1,"Rel-18",null,"Wed 15/06/22","Fri 03/03/23",1,"RP-230060",null,"Spark NZ Ltd ",null,"9/1/23: WID:RP-221778->RP-223265; 29/3/23: WID:RP-223265->RP-230060",null,96,49,null,null,"Wed 03/08/22","Wed 29/03/23"]
[1453,960197,"   Core part: APT 600MHz NR band ","NR_600MHz_APT-Core",2,"Rel-18","R4","Wed 15/06/22","Fri 03/03/23",1,"RP-221778","RP-230053","Mansoor Shafi, Spark New Zealand","Mansoor.shafi@spark.co.nz","9/9/22: Comp...; 23/9/22: 38.892 added;; 9/12/22: FCD:22/12/2022->01/03/2023; Compl:10%->95%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:95%->...","38.892",96,49,null,null,"Wed 03/08/22","Fri 17/03/23"]
[1454,960297,"   Perf. part: APT 600MHz NR band ","NR_600MHz_APT-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 03/03/23",1,"RP-221778","RP-230053","Mansoor Shafi, Spark New Zealand","Mansoor.shafi@spark.co.nz","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:10%->60%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:60%->100%; WID: RP-223265->RP...",null,96,49,null,null,"Wed 03/08/22","Fri 17/03/23"]
[1455,960098,"Stopped - Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands",1,"Rel-18",null,"Thu 16/06/22","Tue 12/12/23",1,"RP-222498",null,"Huawei ",null,"23/9/22: WID:RP-221845->RP-22249801/24: stopped at 0% at RAN#102",null,96,49,102,null,"Wed 03/08/22","Tue 02/01/24"]
[1456,960198,"   Stopped - Core part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Core",2,"Rel-18","R4","Thu 16/06/22","Tue 12/12/23",1,"RP-222498","RP-233184","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","9/9/22: CD:1…; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation¦01/24: stopped at 0% at RAN#102...",null,96,49,102,null,"Wed 03/08/22","Tue 02/01/24"]
[1457,960298,"   Stopped - Perf. part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Perf",2,"Rel-18","R4","Thu 16/06/22","Tue 12/12/23",1,"RP-222498","RP-233184","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->liu...; 8/12/23: S",null,96,49,102,null,"Wed 03/08/22","Tue 02/01/24"]
[1458,960095,"Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18",1,"Rel-18",null,"Wed 15/06/22","Thu 12/12/24",1,"RP-240422",null,"Huawei ",null,"23/9/22: WID:RP-221844->RP-222509; 9/1/23: WID:RP-222509->RP-223516; 6/10/23: WID:RP-223516->RP-232374; 2/1/24: WID:RP-232374->RP-234040; 2/4/24: WID:RP-234040->RP-240422",null,96,49,null,null,"Wed 03/08/22","Tue 02/04/24"]
[1459,960195,"   Core part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Core",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-240422","RP-240421","Xiang Gao, Huawei","gaoxiang74@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-223.....",null,96,49,null,null,"Wed 03/08/22","Thu 14/03/24"]
[1460,960295,"   stopped - Perf. part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-240422","RP-233198","Xiang Gao, Huawei","gaoxiang74@huawei.com","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-2233.....; 8/12/23: F",null,96,49,102,null,"Wed 03/08/22","Tue 02/01/24"]
[1461,1000050,"   UE Conformance - Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-UEConTest",2,"Rel-18","R5","Thu 08/06/23","Fri 06/06/25",1,"RP-251511","RP-251509","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","6/9/23: Compl:0%->49%; Stat Rep: ->RP-231550; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ; 8/12/23: Stat Rep: RP-231550->RP-232771; ; 2/1/24: WID:RP-230868->RP-232772; 14/3/24: FCD:05/06/2024->12/12/2024; Stat ...",null,100,51,null,null,"Thu 29/06/23","Fri 06/06/25"]
[1462,960093,"Enhancements of NR shared spectrum bands ","NR_unlic_enh",1,"Rel-18",null,"Wed 15/06/22","Tue 06/06/23",0.99,"RP-230730",null,"Apple ",null,"23/9/22: WID:RP-221813->RP-222174; 29/3/23: WID:RP-222174->RP-230730",null,96,49,null,null,"Wed 03/08/22","Wed 29/03/23"]
[1463,960193,"   Core part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Core",2,"Rel-18","R4","Wed 15/06/22","Tue 06/06/23",1,"RP-230730","RP-230729","Daniel Popp, Apple Inc.","d_popp@apple.com","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:15%->50%; Stat Rep: ->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: FCD:03/03/2023->08/09/2023; Compl:50%->85%; Stat Rep: RP-223...",null,96,49,null,null,"Wed 03/08/22","Wed 07/06/23"]
[1464,960293,"   Perf. part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Perf",2,"Rel-18","R4","Wed 15/06/22","Thu 16/02/23",0.99,"RP-230730","RP-230729","Daniel Popp, Apple Inc.","d_popp@apple.com","9/12/22: FCD:15/03/2023->01/03/2023; Compl:0%->50%; Stat Rep: RP-222175->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: Compl:50%->100%; Stat Rep: RP-223194->RP-230152; 31/3/23: FCD:03/03/2023->06/06...",null,96,49,null,null,"Wed 03/08/22","Fri 31/03/23"]
[1465,950071,"Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz",1,"Rel-18",null,"Tue 15/03/22","Tue 12/12/23",1,"RP-222831",null,"Ligado Networks ",null,"9/1/23: WID:RP-220971->RP-222831",null,95,48,null,null,"Tue 05/04/22","Mon 09/01/23"]
[1466,950171,"   Core part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Core",2,"Rel-18","R4","Tue 15/03/22","Thu 01/12/22",1,"RP-222831","RP-222830","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: Compl:0%->15% ; 6/6 ; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com ...; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:50%->100%; Stat Rep: RP-221061->RP-222830; 9/1/23: 100%->100",null,95,48,null,null,"Tue 05/04/22","Mon 09/01/23"]
[1467,950271,"   Perf. part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Perf",2,"Rel-18","R4","Tue 15/03/22","Thu 01/12/22",1,"RP-222831","RP-222830","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: CD:15/12/2022->22/12/2022; 6/6/22: Stat Rep: ->RP-221061; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:0%->100%; Stat Rep: RP-221061->RP...",null,95,48,null,null,"Tue 05/04/22","Mon 09/01/23"]
[1468,991032,"   UE Conformance - Introduction of LTE TDD band in 1670 – 1675 MHz ","LTE_TDD_1670_1675MHz-UEConTest",2,"Rel-18","R5","Fri 03/03/23","Tue 12/12/23",1,"RP-232783","RP-232784","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 7/6/23: Compl:0%->83%; 7/6/23: CD:09/09/2023->...; 6/9/23: Compl:83%->99%; WID: RP-230063->RP-230907; Stat Rep: ->RP-231546; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ; 6/10/23: WID:RP-230907->RP...",null,99,50,null,null,"Wed 29/03/23","Tue 02/01/24"]
[1469,960092,"Study on UE support of regionally-defined subsets of an NR band ","FS_NR_subset_band_support",1,"Rel-18","RP","Wed 15/06/22","Fri 03/03/23",1,"RP-223556","RP-230340","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","23/9/22: FCD:15/12/2022->12/20; 23/9/22: 0%->40; 23/9/22: WID:RP-221872->RP-222220; 23/9/22: 38.893 added;; 9/1/23: WID:RP-222220->RP-223556; 29/3/23: FCD:12/12/2023->03/23; 29/3/23: 40%->100; 31/3/23: Stat Rep: RP-222222->RP-230340; Rapporteur: Qualcomm-","38.893",96,49,null,null,"Tue 12/07/22","Fri 31/03/23"]
[1470,1000058,"UE Conformance - New Rel-18 NR licensed bands and extension of existing NR bands ","NR_lic_bands_BW_R18-UEConTest",1,"Rel-18","R5","Thu 08/06/23","Thu 12/12/24",1,"RP-243089","RP-243088","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232360; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 6/10/23: WID:RP-231249->RP-232361; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep...",null,100,51,null,null,"Thu 29/06/23","Fri 24/01/25"]
[1471,0,"Rel-18 Other NR and LTE","-",1,"Rel-18",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1472,1010053,"Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC ","R18_3Tx_NR_CA_ENDC",1,"Rel-18","R4","Sat 09/09/23","Thu 06/06/24",1,"RP-241149",null,"Oppo ",null,"2/1/24: WID:RP-232674->RP-232941; 2/4/24: WID:RP-232941->RP-240307; 23/7/24: WID:RP-240307->RP-241149",null,101,51,null,null,"Fri 06/10/23","Tue 23/07/24"]
[1473,1011053,"   Core pat: Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC ","R18_3Tx_NR_CA_ENDC-Core",2,"Rel-18","R4","Sat 09/09/23","Thu 06/06/24",1,"RP-241149","RP-241150","Jinqiang Xing, OPPO","xingjinqiang@oppo.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->30%; Stat Rep: ->RP-232940; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 4/1/24: 38.880 added;; 14/3/24: FCD:01/03/2024->06/06/2024; Compl:30%->70%; Stat Rep: RP-232940->RP...","38.88",101,51,null,null,"Fri 06/10/23","Thu 13/06/24"]
[1474,970088,"Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18",1,"Rel-18",null,"Mon 12/09/22","Thu 06/06/24",1,"RP-241144",null,"Ericsson ",null,"9/1/23: WID:RP-222660->RP-222848; 29/3/23: WID:RP-222848->RP-230069; 6/10/23: WID:RP-230069->RP-231625; 2/1/24: WID:RP-231625->RP-233977; 2/4/24: WID:RP-233977->RP-240241; 23/7/24: WID:RP-240241->RP-241144",null,97,49,null,null,"Wed 19/10/22","Tue 23/07/24"]
[1475,970188,"   Core part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18-Core",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-241144","RP-241143","Per Lindell, Ericsson","per.lindell@ericsson.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; 17/...;...","38.898",97,49,null,null,"Wed 19/10/22","Thu 13/06/24"]
[1476,970288,"   Stopped - Perf. part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18-Perf",2,"Rel-18","R4","Mon 12/09/22","Tue 12/12/23",1,"RP-241144","RP-240240","Per Lindell, Ericsson","per.lindell@ericsson.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; ;...; 6...",null,97,49,102,null,"Wed 19/10/22","Tue 23/07/24"]
[1477,1000054,"UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations; ","HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest",1,"Rel-18","R5","Thu 08/06/23","Fri 12/12/25",0.9,"RP-231199","RP-251458","Lei GAO, China Telecom","gaol8@chinatelecom.cn","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232259; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; ; 8/12/23: FCD:06/06/2024->06/06/2025; Compl:5%->15%; Stat Rep: RP-232259->RP-233565; ; 14/3...",null,100,51,null,null,"Thu 29/06/23","Fri 06/06/25"]
[1478,961012,"High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18",1,"Rel-18",null,"Wed 15/06/22","Thu 12/12/24",1,"RP-240941",null,"Nokia ",null,"19/10/22: acronym corrected; 9/1/23: WID:RP-221841->RP-223424; 6/10/23: WID:RP-223424->RP-231615; 2/1/24: WID:RP-231615->RP-233180; 2/4/24: WID:RP-233180->RP-240361; 23/7/24: WID:RP-240361->RP-240941",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1479,961112,"   Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-240941","RP-240942","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","9/9/22: Comp...; 23/9/22: 37.829 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; WID: RP-222058->RP-221841; Stat Rep: ->RP-222825; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; 17/3/23:.....","37.829",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1480,1000059,"   UE Conformance - High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands in Rel-18 ","LTE_NR_HPUE_FWVM_R18-UEConTest",2,"Rel-18","R5","Thu 08/06/23","Thu 12/12/24",1,"RP-242837","RP-242836","Tuomo S yn j kangas, Nokia","tuomo.saynajakangas@nokia.com","6/9/23: Compl:0%->18%; Stat Rep: ->RP-231612; Rapporteur: Nokia->Tuomo S yn j kangas, Nokia; Rap eMail: ->tuomo.saynajakangas@nokia.com; ; 6/10/23: WID:RP-231429->RP-231613; 8/12/23: WID: RP-231615->RP-231613; Stat Rep: RP-231612->RP-232856; ; 14/3/24:...",null,100,51,null,null,"Thu 29/06/23","Fri 24/01/25"]
[1481,1000057,"UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations ","NR_CADC_NR_LTE_DC_R18-UEConTest",1,"Rel-18","R5","Thu 08/06/23","Fri 12/12/25",0.76,"RP-240285","RP-251487","Chunying GU, Huawei Technologies. Co., Ltd.","guchunying@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232359; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep: RP-232359->RP-233767; ; 14/3/24: ...",null,100,51,null,null,"Thu 29/06/23","Fri 06/06/25"]
[1482,981041,"4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC",1,"Rel-18",null,"Tue 13/12/22","Tue 12/12/23",1,"RP-234046",null,"Oppo ",null,"29/3/23: WID:RP-223517->RP-230161; 6/10/23: WID:RP-230161->RP-231719; 2/1/24: WID:RP-231719->RP-234046",null,98,50,null,null,"Mon 09/01/23","Tue 02/01/24"]
[1483,981141,"   Core part: 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-Core",2,"Rel-18","R4","Tue 13/12/22","Tue 12/12/23",1,"RP-234046","RP-232937","Jinqiang Xing, OPPO","xingjinqiang@oppo.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230160; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 29/6/23: 10%->70; 6/9/23: Compl:70%->85%; WID: RP-230161->RP-231013; Stat Rep: RP-231012->RP-231718; ; 8/12/23: Compl:85%->100%; S",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[1484,1020088,"UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-UEConTest",1,"Rel-18","R5","Wed 13/12/23","Mon 03/03/25",1,"RP-250447","RP-250446","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","14/3/24: Compl:0%->7%; Stat Rep: ->RP-240289; Rapporteur: Huawei->Yaping ZHANG, Huawei; Rap eMail: ->zhangyaping13@huawei.com; 2/4/24: corrected: rel-19->Rel-18; 13/6/24: Compl:7%->26%; Stat Rep: RP-240289->RP-241376; ; 4/9/24: FCD:06/06/2025->25/06/2025;",null,102,52,null,null,"Tue 02/01/24","Thu 03/04/25"]
[1485,970084,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18",1,"Rel-18",null,"Thu 08/09/22","Mon 09/09/24",1,"RP-241251",null,"Huawei ",null,"9/1/23: WID:RP-222648->RP-223354; 2/1/24: WID:RP-223354->RP-234002; 2/4/24: WID:RP-234002->RP-240425; 23/7/24: WID:RP-240425->RP-241251",null,97,49,null,null,"Fri 23/09/22","Tue 23/07/24"]
[1486,970184,"   Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-Core",2,"Rel-18","R4","Thu 08/09/22","Thu 06/06/24",1,"RP-241251","RP-241250","Dan Hu, Huawei","hudan11@huawei.com","9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Core->LTE_NR _Simult_RxTx_R18-Core; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C.....","38.894",97,49,null,null,"Fri 23/09/22","Thu 13/06/24"]
[1487,970284,"   Stopped - Perf. part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-Perf",2,"Rel-18","R4","Thu 08/09/22","Fri 01/03/24",1,"RP-240425","RP-233201","Dan Hu, Huawei","hudan11@huawei.com","9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Perf->LTE_NR _Simult_RxTx_R18-Perf; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C.....",null,97,49,102,null,"Fri 23/09/22","Tue 02/01/24"]
[1488,1030068,"   UE Conformance - Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Mon 09/09/24",1,"RP-242077","RP-242076","Huawei ",null,"13/6/24: Compl:0%->58%; Stat Rep: ->RP-241379; ; 4/9/24: FCD:06/06/2025->24/09/2024; Compl:58%->100%; Stat Rep: RP-241379->RP-242076; ; 26/9/24: WID:RP-240292->RP-242077",null,103,52,null,null,"Tue 02/04/24","Thu 26/09/24"]
[1489,970082,"Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh",1,"Rel-18",null,"Thu 08/09/22","Fri 06/06/25",1,"RP-234064",null,"Vivo ",null,"9/1/23: WID:RP-222669->RP-223112; 2/1/24: WID:RP-223112->RP-234064",null,97,49,null,null,"Fri 23/09/22","Tue 02/01/24"]
[1490,970182,"   Core part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-Core",2,"Rel-18","R4","Thu 08/09/22","Mon 23/12/24",1,"RP-234064","RP-241829","Wang, Ruixin, vivo","ruixin.wang@vivo.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-223111->RP-230375; 17/3/23: 38.87...;...","38.87",97,49,null,null,"Fri 23/09/22","Wed 04/09/24"]
[1491,970282,"   Perf. Part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-Perf",2,"Rel-18","R4","Mon 12/09/22","Mon 09/09/24",1,"RP-242327","RP-241829","Wang, Ruixin, vivo","ruixin.wang@vivo.com","9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: Compl:0%->5%; Stat Rep: RP-223111->RP-230375; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat ...",null,97,49,null,null,"Fri 23/09/22","Thu 26/09/24"]
[1492,1040111,"   UE Conformance - Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 06/06/25",1,"RP-241503","RP-251178","Apple ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->5%; Stat Rep: ->RP-241899; ; 6/12/24: Compl:5%->30%; Stat Rep: RP-241899->RP-242480; ; 24/1/25: WID:RP-241503->RP-242602; 6/3/25: FCD:14/02/2025->06/06/2025; Compl:30%->70%; WID: RP-242602->RP-241503; Stat Re",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1493,961009,"Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241248",null,"Huawei ",null,"23/9/22: WID:RP-221839->RP-222507; 9/1/23: WID:RP-222507->RP-223537; 29/3/23: WID:RP-223537->RP-230475; 6/10/23: WID:RP-230475->RP-232372; 2/1/24: WID:RP-232372->RP-233197; 2/4/24: WID:RP-233197->RP-240420; 23/7/24: WID:RP-240420->RP-241248",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1494,961109,"   Core part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241248","RP-241247","Zhang, Peng, Huawei","zhangpeng169@huawei.com","9/9/22: Comp...; 23/9/22: 37.718-00-00 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023.....","37.718-00-00",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1495,961209,"   Stopped - Perf. Part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-241248","RP-241247","Zhang, Peng, Huawei","zhangpeng169@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP.....",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1496,961001,"Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241233",null,"CHTTL ",null,"23/9/22: WID:RP-221264->RP-222091; 9/1/23: WID:RP-222091->RP-223078; 29/3/23: WID:RP-223078->RP-230338; 6/10/23: WID:RP-230338->RP-232302; 2/1/24: WID:RP-232302->RP-233242; 2/4/24: WID:RP-233242->RP-240482; 23/7/24: WID:RP-240482->RP-241233",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1497,961101,"   Core part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241233","RP-241219","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","9/9/22: Comp...; 23/9/22: 37.718-11-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077;...","37.718-11-11",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1498,961201,"   Perf. part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Perf",2,"Rel-18","R4","Thu 16/06/22","Thu 06/06/24",1,"RP-241233","RP-241219","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077; Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTT...",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1499,961002,"Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",0.87,"RP-241274",null,"Samsung ",null,"23/9/22: WID:RP-221400->RP-222237; 2/1/24: WID:RP-222237->RP-233989; 2/4/24: WID:RP-233989->RP-240374; 23/7/24: WID:RP-240374->RP-241274",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1500,961102,"   Core part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241274","RP-241273","Yuanyuan Zhang, Samsung","Tina55.zhang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re.....",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1501,961202,"   Perf. part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Perf",2,"Rel-18","R4","Wed 15/06/22","Tue 27/06/23",0.7,"RP-241274","RP-241273","Yuanyuan Zhang, Samsung","Tina55.zhang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re.....",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1502,961003,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241052",null,"LG Electronics ",null,"23/9/22: WID:RP-221800->RP-221944; 9/1/23: WID:RP-221944->RP-222840; 29/3/23: WID:RP-222840->RP-230725; 6/10/23: WID:RP-230725->RP-231723; 2/1/24: WID:RP-231723->RP-233488; 2/4/24: WID:RP-233488->RP-240758; 23/7/24: WID:RP-240758->RP-241052",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1503,961103,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241052","RP-241053","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","9/9/22: Comp...; 23/9/22: 37.718-11-21 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2.....","37.718-11-21",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1504,961203,"   Stopped - Perf. Part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R18_xBLTE_2BNR_yDL2UL-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-241052","RP-241053","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30.....",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1505,961004,"Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241245",null,"Huawei ",null,"23/9/22: WID:RP-221832->RP-222505; 9/1/23: WID:RP-222505->RP-223348; 29/3/23: WID:RP-223348->RP-230473; 6/10/23: WID:RP-230473->RP-232370; 2/1/24: WID:RP-232370->RP-233987; 2/4/24: WID:RP-233987->RP-240417; 23/7/24: WID:RP-240417->RP-241245",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1506,961104,"   Core part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241245","RP-241244","Liehai Liu, Huawei","liuliehai@huawei.com","9/9/22: Comp...; 23/9/22: 37.718-21-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Co.....","37.718-21-11",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1507,961204,"   Stopped - Perf. part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-241245","RP-233192","Liehai Liu, Huawei","liuliehai@huawei.com","9/9/22: Comp…; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->50%¦01/24: stopped at 85% at RAN#102",null,96,49,102,null,"Wed 03/08/22","Tue 02/01/24"]
[1508,961005,"Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241166",null,"Nokia ",null,"23/9/22: WID:RP-221833->RP-222312; 9/1/23: WID:RP-222312->RP-222876; 29/3/23: WID:RP-222876->RP-230090; 6/10/23: WID:RP-230090->RP-232248; 2/1/24: WID:RP-232248->RP-233988; 2/4/24: WID:RP-233988->RP-240384; 23/7/24: WID:RP-240384->RP-241166",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1509,961105,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241166","RP-241165","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; S.....",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1510,961205,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-241166","RP-240382","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: RP-2228.....",null,96,49,null,null,"Wed 03/08/22","Thu 14/03/24"]
[1511,961006,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241225",null,"ZTE ",null,"23/9/22: WID:RP-221834->RP-222094; 9/1/23: WID:RP-222094->RP-222906; 29/3/23: WID:RP-222906->RP-230135; 6/10/23: WID:RP-230135->RP-231842; 2/1/24: WID:RP-231842->RP-232923; 2/4/24: WID:RP-232923->RP-240760; 23/7/24: WID:RP-240760->RP-241225",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1512,961106,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241225","RP-24xxxx","Wubin Zhou, ZTE","Zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-.....",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1513,961206,"   Stopped - Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-240760","RP-24xxxx","Wubin Zhou, ZTE","Zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-.....",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1514,960096,"Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18",1,"Rel-18",null,"Wed 15/06/22","Tue 12/12/23",1,"RP-230390",null,"CATT ",null,"23/9/22: WID:RP-221879->RP-222385; 29/3/23: WID:RP-222385->RP-230390",null,96,49,null,null,"Wed 03/08/22","Wed 29/03/23"]
[1515,960196,"   Core part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Core",2,"Rel-18","R4","Wed 15/06/22","Tue 12/12/23",1,"RP-230390","RP-233006","Qiuge Guo, CATT","guoqiuge@catt.cn","9/9/22: Comp...; 23/9/22: 37.878 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:5%->50%; Stat Rep: ->RP-230389; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; ; 6/9/23: Stat Rep: RP-230389->RP-231834; ; 8/12/23: Compl:5","37.878",96,49,null,null,"Wed 03/08/22","Fri 08/12/23"]
[1516,960296,"   Perf. part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Perf",2,"Rel-18","R4","Wed 15/06/22","Tue 12/12/23",1,"RP-230390","RP-233006","Qiuge Guo, CATT","guoqiuge@catt.cn","9/9/22: CD:1...; 9/12/22: Acronym:NR_LTE_V2X_PC5_combos_R18-Perf->NR_LTE_V2X_PC5_combos_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->50%; Stat Rep: ->RP-223146; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; 17/3/23.....",null,96,49,null,null,"Wed 03/08/22","Fri 08/12/23"]
[1517,960094,"Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18",1,"Rel-18",null,"Wed 15/06/22","Fri 06/06/25",1,"RP-233588",null,"China Telecom ","LTE, NR ","23/9/22: WID:RP-221843->RP-222288; 2/1/24: WID:RP-222288->RP-233588",null,96,49,null,null,"Wed 03/08/22","Tue 02/01/24"]
[1518,960194,"   Core part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Core",2,"Rel-18","R4","Wed 15/06/22","Tue 12/12/23",1,"RP-233588","RP-233587","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","9/9/22: Comp...; 23/9/22: 37.877 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:10%->99%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-230319; Rapporteur: China Telecom->Liu, Bo, China Telecom; Rap eMail: LTE, NR->liubo1@chinate...","37.877",96,49,null,null,"Wed 03/08/22","Fri 08/12/23"]
[1519,960294,"   Perf. part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Perf",2,"Rel-18","R4","Wed 15/06/22","Tue 12/12/23",1,"RP-233588","RP-233587","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","9/9/22: CD:1...; 9/12/22: Acronym:DL_intrpt_combos_TxSW_R18-Perf->DL_intrpt_combos_TxSW_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->20%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-222939; Rapporteur: China Telecom->Liu, Bo, Ch...",null,96,49,null,null,"Wed 03/08/22","Fri 08/12/23"]
[1520,1050129,"   UE Conformance - Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-UEConTest",2,"Rel-18","R5","Mon 09/09/24","Fri 06/06/25",1,"RP-242001","RP-251464","China Telecom ",null,"6/12/24: Compl:0%->67%; Stat Rep: ->RP-242853; ; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:67%->69%; Stat Rep: RP-242853->RP-250380; ; 6/6/25: FCD:Fri 12/12/25->Fri 06/06/25; Compl:69%->100%; Stat Rep: RP-250380->RP-251464; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[1521,0,"Rel-18 Other LTE-only","-",1,"Rel-18",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1522,1010054,"High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14",1,"Rel-18","R4","Sat 09/09/23","Fri 01/03/24",1,"RP-232946",null,"AT&T ",null,"2/1/24: WID:RP-232676->RP-232946",null,101,51,null,null,"Fri 06/10/23","Tue 02/01/24"]
[1523,1011054,"   Core part: High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14-Core",2,"Rel-18","R4","Sat 09/09/23","Fri 01/03/24",1,"RP-232946","RP-240075","Borsato, Ron","ronald.borsato@att.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->50%; Stat Rep: ->RP-232945; Rapporteur: AT&T->Borsato, Ron; Rap eMail: ->ronald.borsato@att.com; ; 4/1/24: 36.770 added;; 14/3/24: Compl:50%->100%; Stat Rep: RP-232945->RP-240075; List of Impacted TS & TR up","36.77",101,51,null,null,"Fri 06/10/23","Thu 14/03/24"]
[1524,1012054,"   Perf. part: High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14-Perf",2,"Rel-18","R4","Sat 09/09/23","Fri 01/03/24",1,"RP-232946","RP-240075","Borsato, Ron","ronald.borsato@att.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->80%; Stat Rep: ->RP-232945; Rapporteur: AT&T->Borsato, Ron; Rap eMail: ->ronald.borsato@att.com; ; 14/3/24: Compl:80%->100%; Stat Rep: RP-232945->RP-240075; ",null,101,51,null,null,"Fri 06/10/23","Thu 14/03/24"]
[1525,981048,"Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2",1,"Rel-18",null,"Tue 13/12/22","Tue 12/12/23",1,"RP-232892",null,"Ericsson ",null,"2/1/24: WID:RP-222824->RP-232892",null,98,50,null,null,"Mon 09/01/23","Tue 02/01/24"]
[1526,981148,"   Core part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2-Core",2,"Rel-18","R4","Tue 13/12/22","Tue 12/12/23",1,"RP-232892","RP- 232891","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ; 8/12/23: Compl:99%->100%; Stat Rep: RP-231880->RP- 232891; ",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[1527,981248,"   Perf. part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2-Perf",2,"Rel-18","R4","Tue 13/12/22","Tue 12/12/23",1,"RP-232892","RP- 232891","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ; 8/12/23: Compl:99%->100%; Stat Rep: RP-231880->RP- 232891; ",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[1528,981046,"Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US",1,"Rel-18",null,"Mon 12/12/22","Mon 03/03/25",0.83,"RP-230722",null,"Anterix ",null,"29/3/23: WID:RP-223530->RP-230722",null,98,50,null,null,"Mon 09/01/23","Wed 29/03/23"]
[1529,981146,"   Core part: Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-Core",2,"Rel-18","R4","Mon 12/12/22","Tue 06/06/23",1,"RP-230722","RP-231218","Emil Olbrich, Anterix","eolbrich@anterix.com","17/3/23: Compl:0%->20%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 29/6/23: 20%->100",null,98,50,null,null,"Mon 09/01/23","Thu 29/06/23"]
[1530,981246,"   Perf. part: Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-Perf",2,"Rel-18","R4","Mon 12/12/22","Thu 13/04/23",0.1,"RP-230722","RP-231218","Emil Olbrich, Anterix","eolbrich@anterix.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ",null,98,50,null,null,"Mon 09/01/23","Fri 17/03/23"]
[1531,1030064,"   UE Conformance - Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Tue 09/09/25",0.96,"RP-240096","RP-250888","Nokia ",null,"13/6/24: Compl:0%->85%; Stat Rep: ->RP-240915; ; 4/9/24: FCD:03/03/2025->25/03/2025; Stat Rep: RP-240915->RP-241747; ; 6/12/24: Stat Rep: RP-241747->RP-242838; ; 6/3/25: FCD:12/11/2024->06/06/2025; Stat Rep: RP-242838->RP-250081; ; 6/6/25: FCD:Fri 06/06/2",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1532,981040,"Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz ","LTE_intra_CA_MPR_35MHz_gap",1,"Rel-18",null,"Mon 12/12/22","Fri 03/03/23",1,"RP-230705",null,"Huawei ",null,"29/3/23: WID:RP-223511->RP-230705",null,98,50,null,null,"Mon 09/01/23","Wed 29/03/23"]
[1533,981140,"   Core part: Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz ","LTE_intra_CA_MPR_35MHz_gap-Core",2,"Rel-18","R4","Mon 12/12/22","Fri 03/03/23",1,"RP-230705","RP-230480","Mohammad Abdi Abyaneh, Huawei, HiSilicon","Mohammad.abdi.abyaneh@huawei.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230480; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->Mohammad.abdi.abyaneh@huawei.com; ",null,98,50,null,null,"Mon 09/01/23","Fri 17/03/23"]
[1534,960099,"Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241242",null,"Huawei ","LTE ","23/9/22: WID:RP-221831->RP-222503; 9/1/23: WID:RP-222503->RP-223489; 29/3/23: WID:RP-223489->RP-230471; 6/10/23: WID:RP-230471->RP-232368; 2/1/24: WID:RP-232368->RP-233927; 2/4/24: WID:RP-233927->RP-240414; 23/7/24: WID:RP-240414->RP-241242",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1535,960199,"   Core part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241242","RP-241241","Mohammad Abdi Abyaneh, Huawei- HiSilicon","Mohammad.abdi.abyaneh@huawei.com","9/9/22: Comp...; 23/9/22: 36.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:.....","36.718-02-01",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1536,960299,"   Stopped - Perf. part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-240414","RP-233189","Mohammad Abdi Abyaneh, Huawei- HiSilicon","Mohammad.abdi.abyaneh@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat R.....; 2/1/24: St",null,96,49,102,null,"Wed 03/08/22","Tue 02/01/24"]
[1537,961000,"LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8",1,"Rel-18","R4","Wed 15/06/22","Thu 22/12/22",1,"RP-221846",null,"China Mobile ","LTE ",null,null,96,49,null,null,"Wed 03/08/22","NA"]
[1538,961100,"   Core part: LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 22/12/22",1,"RP-221846",null,"China Mobile ","LTE ","9/9/22: Comp...; 9/1/23: 99%->100",null,96,49,null,null,"Wed 03/08/22","Mon 09/01/23"]
[1539,991040,"Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW",1,"Rel-18","R4","Mon 29/05/23","Tue 12/12/23",0,"RP-230745",null,"T-Mobile USA ",null,null,null,99,50,null,null,"Wed 29/03/23","NA"]
[1540,991140,"   Core part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW-Core",2,"Rel-18","R4","Mon 29/05/23","Tue 12/12/23",0,"RP-230745",null,"T-Mobile USA ",null,"; 7/6/23: CD:06/06/2023->12/12/2023",null,99,50,null,null,"Wed 29/03/23","Wed 07/06/23"]
[1541,991240,"   Perf. part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW-Perf",2,"Rel-18","R4","Mon 29/05/23","Tue 12/12/23",0,"RP-230745",null,"T-Mobile USA ",null,"; 7/6/23: CD:09/09/2023->12/12/2023",null,99,50,null,null,"Wed 29/03/23","Wed 07/06/23"]
[1542,0,"Rel-18 RAN Studies","-",1,"Rel-18",null,"Fri 15/12/17","Fri 15/12/17",0.34,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1543,991031,"Study on enhancement for sub-1GHz NR band combinations ","FS_NR_sub1GHz_combo_enh",1,"Rel-18","R4","Fri 03/03/23","Fri 08/09/23",1,"RP-231141","RP-232661","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 7/6/23: Compl:0%->86%; 7/6/23: CD:06/06/2023->09/09/2023; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:86%->80%; WID: RP-230789->RP-231141; Stat Rep: ->RP-232378; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ; 21/9/23: FC",null,99,50,null,null,"Wed 29/03/23","Thu 21/09/23"]
[1544,991030,"Study on self-evaluation towards the IMT-2020 submission of the 3GPP Satellite Radio Interface Technology ","FS_IMT2020_SAT_eval",1,"Rel-18","RP","Fri 03/03/23","Tue 12/12/23",1,"RP-231945","RP-231944","Asbj rn Gr vlen, Ericsson","asbjorn.grovlen@ericsson.com","29/6/23: 0%->20; 21/9/23: Compl:20%->40%; WID: RP-230736->RP-231945; Stat Rep: RP-231291->RP-231944; Rapporteur: Asbjörn Grövlen, Ericsson->Asbj rn Gr vlen, Ericsson; ; 21/9/23: 37.911 added;; 2/1/24: 40%->100","37.911",99,50,null,null,"Wed 29/03/23","Tue 02/01/24"]
[1545,970078,"Study on Ambient IoT (Internet of Things) in RAN ","FS_Ambient_IoT_RAN",1,"Rel-18","RP","Thu 08/09/22","Fri 08/09/23",1,"RP-232404","RP-232403","Matthew Webb, Huawei","matthew.webb@huawei.com","9/1/23: WID:RP-222685->RP-223396; 17/3/23: 38.848 added;; 31/3/23: Compl:0%->50%; WID: RP-223396->RP-222685; Stat Rep: ->RP-230669; Rapporteur: Huawei->Matthew Webb, Huawei; Rap eMail: ->matthew.webb@huawei.com; ; 29/6/23: 50%->60; 29/6/23: FCD:06/06/...","38.848",97,49,null,null,"Fri 23/09/22","Fri 06/10/23"]
[1546,950067,"Study on simplification of band combination specification for NR and LTE ","FS_SimBC",1,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-231468","RP-233234","Zhifeng Ma, ZTE Corporation","ma.zhifeng@zte.com.cn","TR 37.8xx; LTE only combos will not be considered ; 20/6/22: FCD:15/06/2023->23/06/2022; Stat Rep: ->RP-221266 / 1769; Rapporteur: ZTE->Zhifeng Ma, ZTE Corporation; Rap eMail: ->ma.zhifeng@zte.com.cn12/7/22: WID:RP-220956->RP-221790; 13/7/22: FCD:...;...","38.846",95,48,null,null,"Tue 05/04/22","Fri 08/12/23"]
[1547,950068,"Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements ","FS_NR_FR2_OTA_enh",1,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-233171","RP-233170","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","compare REL-16 SI FS_NR_test_methods and REL-17 SI FS_FR2_enhTestMethods; TR 38.3xx ; 6/6/22: CD:15/12/2023->23/12/2022; 6/6/22: Stat Rep: ->RP-221391; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com...","38.871",95,48,null,null,"Tue 05/04/22","Tue 02/01/24"]
[1548,950069,"Study on NR base station (BS) RF requirement evolution ","FS_NR_BS_RF_evo",1,"Rel-18","R4","Tue 15/03/22","Tue 06/06/23",1,"RP-222501","RP-230469","Liehai Liu, Huawei","liuliehai@huawei.com","for NR FR2 mmWave BSs; TR 38.8xx 6/6/22: CD:15/06/2023->23/06/20226/6/22: Stat Rep: ->RP-221530; 20/6/22: Rapporteur: Huawei->Richard Kybett, Huawei; Rap eMail: ->Richard.kybett@huawei.com13/7/22: FCD:23/06/2022->06/20; 13/7/22: 38.877 added;;...; 23/...","38.877",95,48,null,null,"Tue 05/04/22","Wed 07/06/23"]
[1549,950070,"Study on enhancement for 700/800/900MHz band combinations for NR ","FS_NR_700800900_combo_enh",1,"Rel-18","R4","Thu 03/03/22","Fri 03/03/23",1,"RP-222554","RP-230388","Huiping Shan, CATT","shanhuiping@catt.cn","TR 38.8xx ; 6/6/22: CD:08/06/2021->23/03/2023; 6/6/22: Stat Rep: ->RP-221460; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn12/7/22: WID:RP-221016->RP-221464; 13/7/22: 38.872 added ; ;...; 23/9/22: WID:RP-221464->RP-2225...","38.872",95,48,null,null,"Tue 05/04/22","Fri 17/03/23"]
[1550,850071,"Study on enhanced test methods for FR2 NR UEs","FS_FR2_enhTestMethods",1,"Rel-18","R4","Thu 19/09/19","Wed 22/06/22",1,"RP-221574","RP-221575","Anatoliy IOFFE, Ruixin WANG, Aida Vera LOPEZ, Apple Inc., vivo, Intel Corporation","aioffe@apple.com, ruixin.wang@vivo.com, aida.l.vera.lopez@intel.com","TR 38.8XX; 14/1/20: WID:RP-192322->RP-192430; 28/7/20: WID:RP-192430->RP-201110; 25/9/20: WID:RP-201110->RP-201862; 7/4/21: WID:RP-201862->RP-210633; 2/7/21: WID:RP-210633->RP-211600; ; 04/22: Rel-17->Rel-18 ; ; 20/6/22: Rapporteur: Apple->Anatoliy ...",null,85,43,null,null,"Tue 08/10/19","Tue 12/07/22"]
[1551,890040,"Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths ","FS_NR_eff_BW_util",1,"Rel-18","R4","Thu 17/09/20","Fri 03/03/23",1,"RP-222618","RP-230579","Esther Sienkiewicz, Ericsson","esther dot sienkiewicz at ericsson dot com","TR 38.8xx ; 6/1/21: WID:RP-202103->RP-202339; 7/4/21: WID:RP-202339->RP-210706; 2/7/21: WID:RP-210706->RP-211468; 13/9/21: Compl:0%->50%; ; 6/1/22: WID:RP‑211468->RP-213657 ; 5/4/22: WID:RP-213657->RP-220461; 04/22: Rel-17->Rel-18; ; 20/6/22: Rappor...","38.844",89,45,null,null,"Fri 25/09/20","Fri 17/03/23"]
[1552,0,"Rel-18 Network automation","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1553,990118,"Enablers for Network Automation for 5G phase 3 ","eNA_Ph3",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-221345",null,"Aihua Li, China Mobile ","liaihua@chinamobile ","10/12/22: 0%->25","23.501; 23.502; 23.503; 23.288 ",99,50,null,null,"Fri 09/12/22","Sat 10/12/22"]
[1554,940073,"   Study on Enablers for Network Automation for 5G - phase 3 ","FS_eNA_Ph3",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220678",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","21/1/22: 23.700-81 added;; 21/1/22: 23.700-85 added;; 12/3/22: 0%->13; 4/6/22: 13%->50; 21/6/22: WID:SP-211650->SP-220678; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-81; 23.700-85",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1555,950021,"   Study on security aspects of enablers for Network Automation for 5G - phase 3 ","FS_eNA_SEC_Ph3",2,"Rel-18","S3","Thu 10/03/22","Fri 03/03/23",1,"SP-220199",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","4/6/22: 0%->10; 13/7/22: 33.738 added;; 12/9/22: 10%->35; 11/12/22: 35%->60; 17/3/23: 60%->80; 8/6/23: 80%->95; 15/3/24: 95%->100","33.738",95,48,null,null,"Thu 10/03/22","Fri 15/03/24"]
[1556,990042,"   Security aspects of enablers for Network Automation for 5G - phase 3 ","eNA_Ph3_SEC",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230155",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 8/6/23: 0%->65; 15/3/24: 65%->100","33.501 ",99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[1557,980020,"   (stage 2 of eNA_Ph3) Enablers for Network Automation for 5G phase 3 ","eNA_Ph3",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230110",null,"Aihua Li, China Mobile ","liaihua@chinamobile ","10/12/22: 0%->25; 15/3/23: 13%->65; 15/3/23: WID:SP-221345->SP-230110; 8/6/23: 65%->100","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[1558,990010,"   CT3 aspects of eNA_Ph3","eNA_Ph3",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-240079",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:15%->65%","29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1559,990104,"   CT4 aspects of eNA_Ph3","eNA_Ph3",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-240079",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:5%->30%","29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1560,980039,"Enhancement of Network Automation Enablers","eNetAE",1,"Rel-18","C3","Thu 15/12/22","Sun 03/03/24",1,"CP-231191",null,"Xuefei Zhang, Huawei","summer.xuefei@huawei.com","; 6/6/23: Compl:70%->90%; 6/6/23: CD:12/12/2023->03/03/2024; ;...","29.517; 29.520; 29.522; 29.552; 29.574; 29.575; 29.576; 29.591",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1561,0,"Rel-18 other Studies","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1562,860010,"Guidelines for Extra-territorial 5G Systems ","FS_5GET",1,"Rel-18","S1","Fri 06/12/19","Fri 10/12/21",1,"SP-191042",null,"Cyril MICHEL,Thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->20; 5/12/20: 20%->40; 19/3/21: FCD:11/09/2020->12/21; 19/3/21: 40%->50; 11/6/21: 50%->60; 13/9/21: 60%->80; 10/12/21: 80%->100",null,86,44,null,null,"Fri 06/12/19","Fri 10/12/21"]
[1563,960002,"Study on NRF API enhancements to avoid signalling and storing of redundant data","FS_NRFe",1,"Rel-18","C4","Thu 02/06/22","Sat 09/09/23",1,"CP-231022",null,"Wiehe, Ulrich, Nokia","Ulrich.wiehe@nokia.com","13/7/22: 29.831 added;; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-221088->CP-231022","29.xxx; 29.831",96,49,null,null,"Mon 20/06/22","Fri 30/06/23"]
[1564,0,"Rel-18 Management-only Features","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1565,1000007,"Management of cloud-native Virtualized Network Functions ","MCVNF",1,"Rel-18","S5","Fri 30/06/23","Sun 03/03/24",1,"SP-230764",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","; 7/9/23: 0%->30; 8/12/23: 30%->95; 14/3/24: 95%->100","28.531; 28.533; 28.526 ",100,51,null,null,"Fri 30/06/23","Thu 14/03/24"]
[1566,1000011,"Charging enhancement for Network Slice based wholesale in roaming ","CHNSWO",1,"Rel-18","S5","Mon 01/05/23","Tue 06/06/23",1,"SP-230625",null,"Maryse Gardella, MATRIXX Software, ","Maryse dot Gardella at Matrixx dot com ","; 8/12/23: 0%->100","32.240; 32.255; 32.256; 32.291; 32.298 ",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[1567,1000014,"Network and Service Operations for Energy Utilities ","NSOEU",1,"Rel-18","S5","Thu 08/06/23","Sun 03/03/24",1,"SP-230632",null,"Erik Guttman , Samsung; ","<erik.guttman@samsung.com ","; 30/6/23: 28.318 added;; 7/9/23: 0%->30; 8/12/23: 30%->60; 4/1/24: 28.879 added;; 14/3/24: 60%->100","28.552; 28.554; 28.622 ; 28.318; 28.879",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[1568,980026,"Study on CHF Segmentation ","FS_CHFSeg",1,"Rel-18","S5","Mon 12/12/22","Sun 03/03/24",1,"SP-221160",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","17/3/23: 0%->5; 17/3/23: 28.840 added;; 8/6/23: 5%->12; 7/9/23: 12%->18; 8/12/23: 18%->55; 8/12/23: FCD:09/09/2023->/2024; 14/3/24: 55%->100","28.840",98,50,null,null,"Fri 09/12/22","Thu 14/03/24"]
[1569,980029,"Management of Trace/MDT phase 2 ","5GMDT_Ph2",1,"Rel-18","S5","Mon 12/12/22","Sun 03/03/24",1,"SP-230777",null,"Swaminathan, Sivaramakrishnan, Nokia ","sivaramakrishnan<dot>swaminathan<at>nokia<dot>com ","; 8/6/23: 0%->; 30/6/23: WID:SP-221163->SP-230777; 7/9/23: 0%->40; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 40%->90; 14/3/24: 90%->100","28.621; 28.622; 28.623; 32.421; 32.422; 32.423 ",98,50,null,null,"Fri 09/12/22","Thu 14/03/24"]
[1570,940037,"Enhancements of EE for 5G Phase 2 ","EE5GPLUS_Ph2",1,"Rel-18","S5","Fri 10/12/21","Tue 12/12/23",1,"SP-211441",null,"Cornily Jean-Michel, Huawei","jean.michel.cornily@huawei.com","; 12/9/22: 0%->10; 12/9/22: FCD:10/03/2023->06/23; 11/12/22: 10%->25; 17/3/23: 25%->30; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 30%->35; 7/9/23: 35%->55; 8/12/23: 55%->100","28.310; 28.552; 28.554; 28.541 ",94,48,null,null,"Fri 10/12/21","Fri 08/12/23"]
[1571,940014,"Security Assurance Specification for Management Function (MnF) ","SCAS_5G_MF",1,"Rel-18","S3","Fri 10/12/21","Fri 09/12/22",1,"SP-211362",null,"Noamen Ben Henda, Huawei Technologies Co., Ltd. ","noamen.ben.henda@huawei.com ","; 7/1/22: 33.526 added;; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->95; 7/9/23: 95%->100","33.926 ; 33.526",94,48,null,null,"Fri 10/12/21","Thu 07/09/23"]
[1572,960023,"Multimedia Messaging Service Charging using service-based interface","MMS_CH_SBI",1,"Rel-18","S5","Thu 02/06/22","Mon 12/12/22",1,"SP-220689",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericson(dot)com ","; 17/8/22: WID:SP-220486->SP-220689; 12/9/22: 0%->25; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 25%->100","32.240; 32.270; 32.290; 32.291; 32.298 ",96,49,null,null,"Thu 02/06/22","Sun 11/12/22"]
[1573,960025,"5G performance measurements and KPIs phase 3","PM_KPI_5G_Ph3",1,"Rel-18","S5","Thu 02/06/22","Sun 03/03/24",1,"SP-240271",null,"Chen, Xiumin, China Telecom ","(chenxiumin<at>chinatelecom<dot>cn) ","; 17/8/22: WID:SP-220489->SP-220690; 12/9/22: 0%->15; 11/12/22: 15%->50; 17/3/23: 50%->60; 8/6/23: 60%->70; 8/6/23: 70%->; 7/9/23: 70%->80; 8/12/23: 80%->99; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-220690->SP-231710; 4/1/24: 28.558 added;; 14/3...","28.552; 32.425; 28.554; 28.550 ; 28.558",96,49,null,null,"Thu 02/06/22","Tue 02/04/24"]
[1574,870027,"Enhancement of QoE Measurement Collection ","eQoE",1,"Rel-18","S5","Wed 25/03/20","Tue 12/12/23",1,"SP-200193",null,"Bagher Zadeh, Ericsson ","Bagher Zadeh <at>ericsson<dot>ericsson ","; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->20; 13/9/21: 20%->40; 13/9/21: FCD:Thu 16/09/->03/22; 13/12/21: 40%->60; 12/3/22: 60%->90; 4/6/22: 90%->95; 4/6/22: FCD:11/03/2022->12/22; Rel-17->Rel-18; 12/9/22: 95%->70; 12/9/22: FCD:12/12/2022->12/2...","28.307; 28.308; 28.309; 28.404; 28.405; 28.406; 28.622; 28.623; 28.533 ",87,44,null,null,"Fri 06/12/19","Thu 08/06/23"]
[1575,950036,"Enhanced Edge Computing Management ","eECM",1,"Rel-18","S5","Thu 10/03/22","Sun 03/03/24",1,"SP-230775",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 4/6/22: 0%->10; 12/9/22: 10%->35; 11/12/22: 35%->50; 17/3/23: 50%->50; 17/3/23: FCD:03/03/2023->12/23; 17/3/23: FCD:12/12/2023->/23; 17/3/23: 50%->100; 30/6/23: WID:SP-220154->SP-230775; 8/12/23: 100%->70; 8/12/23: FCD:03/03/2023->/2024; 14/3/24: 70%->","28.541; 28.538; 28.552; 28.554; 28.531; 28.532 ",95,48,null,null,"Thu 10/03/22","Thu 14/03/24"]
[1576,890016,"Study on access control for management service ","FS_MNSAC",1,"Rel-17","S5","Wed 16/09/20","Wed 08/09/21",1,"SP-200853",null,"Jing Ping, Nokia ","jing.ping@nokia-sbell.com ","25/9/20: WID:SP-200764->SP-200853; 5/12/20: 0%->5; 21/3/21: 5%->35; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 35%->80; 11/6/21: FCD:Wed 08/09/->09/21; 13/9/21: 80%->100",null,89,45,null,null,"Fri 11/09/20","Mon 13/09/21"]
[1577,930010,"Access control for management service ","MSAC",1,"Rel-18","S5","Fri 10/09/21","Sun 03/03/24",1,"SP-231711",null,"Clifton Fernandes, Nokia ","Clifton.fernandes@nokia.com ","; 12/3/22: 0%->60; 4/6/22: 60%->67; 4/6/22: FCD:10/12/2021->12/22; Rel-17->Rel-18; 11/12/22: 67%->68; 11/12/22: FCD:12/12/2022->12/23; 17/3/23: 68%->69; 8/6/23: 69%->72; 7/9/23: 72%->73; 8/12/23: 73%->75; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP...","28.319",93,47,null,null,"Fri 10/09/21","Thu 14/03/24"]
[1578,940033,"Network slice provisioning enhancement ","eNETSLICE_PRO",1,"Rel-18","S5","Fri 10/09/21","Tue 12/12/23",1,"SP-211434",null,"Deepanshu Gautam , Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 12/3/22: 0%->50; 4/6/22: 50%->85; 4/6/22: FCD:11/03/2022->09/22; Rel=-17->Rel-18; 12/9/22: 85%->85; 12/9/22: FCD:12/09/2022->12/12/22; 11/12/22: 85%->90; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 90%->90; 17/3/23: FCD:03/03/2023->12/23; 7/9/23: 90%->100","28.531; 28.541 ",94,48,null,null,"Fri 10/12/21","Thu 07/09/23"]
[1579,890017,"Study on YANG PUSH ","FS_YANG",1,"Rel-18","S5","Wed 16/09/20","Thu 10/03/22",1,"SP-200765",null,"Lengyel, Balazs, Ericsson ","balazs.lengyel@ericsson.com ","5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 10%->10; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 8/12/23: 10%->100",null,89,45,null,null,"Thu 10/09/20","Fri 08/12/23"]
[1580,910028,"Study on Continuous integration continuous delivery support for 3GPP NFs. ","FS_CICDNS",1,"Rel-18","S5","Thu 18/03/21","Fri 11/03/22",1,"SP-211427",null,"Vaishnavi, Ishan, Lenovo ","ivaishnavi@lenovo.com ","; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/9/21: FCD:Fri 10/09/->12/21; 13/12/21: 30%->75; 13/12/21: FCD:Fri 10/12/->03/22; 7/1/22: 28.901 added;12/3/22: Rel-17->Rel-18; 4/6/22: 75%->100","New ; 28.901",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1581,910031,"Study on Enhancement of service-based management architecture ","FS_eSBMA",1,"Rel-18","S5","Thu 18/03/21","Tue 06/06/23",1,"SP-210136",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 11/6/21: 0%->10; 13/9/21: 10%->15; 13/12/21: 15%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 4/6/22: 45%->60; 12/9/22: 60%->75; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 75%->80; 17/3/23: 80%->85; 17/3/23: FCD:03/03/2023->/23; 8/6/23","New ",91,46,null,null,"Thu 18/03/21","Thu 08/06/23"]
[1582,990026,"Service based management architecture ","eSBMA",1,"Rel-18","S5","Thu 16/03/23","Sun 03/03/24",1,"SP-231443",null,"Zhang Kai, Huawei ","kai.zhangkai@huawei.com","; 31/3/23: 28.111 added;; 30/6/23: WID:SP-230174->SP-230776; 7/9/23: 0%->10; 21/9/23: 32.161 added;; 8/12/23: 10%->55; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-230776->SP-231443; 4/1/24: 28.871 added;; 14/3/24: 55%->100","32.404; 28.622; 28.623; 32.300; 28.532; 28.545; 28.532; 28.532; 28.532; 28.158; 28.532 ; 28.111; 32.161; 28.871",99,50,null,null,"Thu 16/03/23","Thu 14/03/24"]
[1583,940034,"Study on Enhancement of the management aspects related to NWDAF ","FS_MANWDAF",1,"Rel-18","S5","Mon 13/12/21","Tue 06/06/23",1,"SP-211435",null,"ZHAO, Song, China Telecom ","zhaosong1@chinatelecom.cn ","7/1/22: 28.864 added;; 4/6/22: 0%->30; 12/9/22: 30%->65; 11/12/22: 65%->75; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 75%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","28.864",94,48,null,null,"Mon 13/12/21","Thu 08/06/23"]
[1584,990031,"Management Aspects related to NWDAF ","MANWDAF",1,"Rel-18","S5","Thu 16/03/23","Tue 12/12/23",1,"SP-230181",null,"Niu, Yuxia, China Telecom ","niuyx@chinatelecom.cn ","; 8/6/23: 0%->50; 7/9/23: 50%->75; 8/12/23: 75%->100; 4/1/24: 28.877 added;","28.541; 28.552; 28.554 ; 28.877",99,50,null,null,"Thu 16/03/23","Thu 04/01/24"]
[1585,940035,"Study on enhancement of management of non-public networks ","FS_OAM_eNPN",1,"Rel-18","S5","Mon 13/12/21","Fri 03/03/23",1,"SP-230185",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","7/1/22: 28.907 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 16/3/23: WID:SP-211436->SP-230185; 17/3/23: 90%->100","28.907",94,48,null,null,"Mon 13/12/21","Fri 17/03/23"]
[1586,940036,"Study on new aspects of EE for 5G networks Phase 2 ","FS_EE5G_Ph2",1,"Rel-18","S5","Mon 13/12/21","Tue 06/06/23",1,"SP-211440",null,"Cornily Jean-Michel, Orange ","jean.michel.cornily@huawei.com","7/1/22: 28.913 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->50; 17/3/23: 50%->50; 8/6/23: 50%->100","28.913",94,48,null,null,"Mon 13/12/21","Thu 08/06/23"]
[1587,940038,"Study on Deterministic Communication Service Assurance ","FS_DCSA",1,"Rel-18","S5","Mon 13/12/21","Sun 03/03/24",1,"SP-240269",null,"<Zhang>, <Jian>, <Huawei> ","justincn.zhang@huawei.com ","7/1/22: 28.865 added;; 4/6/22: 0%->30; 12/9/22: 30%->32; 12/9/22: FCD:12/12/2023->12/22; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 32%->45; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 45%->60; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 60%->; 8/12/23: 60%->92; 14/3/...","28.865",94,48,null,null,"Mon 13/12/21","Tue 02/04/24"]
[1588,940041,"Study on evaluation of autonomous network levels ","FS_ANLEVA",1,"Rel-18","S5","Mon 13/12/21","Sun 03/03/24",1,"SP-211445",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.909 added;; 4/6/22: 0%->10; 11/12/22: 10%->10; 8/6/23: 10%->60; 8/6/23: FCD:10/03/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->/24; 8/12/23: 70%->80; 14/3/24: 80%->100","28.909",94,48,null,null,"Mon 13/12/21","Thu 14/03/24"]
[1589,940042,"Study on enhancement of autonomous network levels ","FS_eANL",1,"Rel-18","S5","Mon 13/12/21","Tue 12/12/23",1,"SP-211446",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.910 added;; 4/6/22: 0%->25; 12/9/22: 25%->30; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 30%->30; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 30%->75; 8/6/23: FCD:03/03/2023->12/23; 7/9/23: 75%->85; 8/12/23: 85%->100","28.910",94,48,null,null,"Mon 13/12/21","Fri 08/12/23"]
[1590,940046,"Study on enhanced intent driven management services for mobile networks ","FS_eIDMS_MN",1,"Rel-18","S5","Mon 13/12/21","Tue 06/06/23",1,"SP-211450",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","7/1/22: 28.912 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 90%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 90%->100","28.912",94,48,null,null,"Mon 13/12/21","Thu 08/06/23"]
[1591,950027,"Study on Basic SBMA enabler enhancements ","FS_eSBMAe",1,"Rel-18","S5","Thu 10/03/22","Tue 06/06/23",1,"SP-230774",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","5/4/22: 28.831 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->35; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 35%->70; 8/6/23: 70%->100; 30/6/23: WID:SP-220145->SP-230774","28.831",95,48,null,null,"Thu 10/03/22","Fri 30/06/23"]
[1592,950029,"Study on alignment with ETSI MEC for Edge computing management ","FS_MEC_ECM",1,"Rel-18","S5","Thu 10/03/22","Tue 06/06/23",1,"SP-220147",null,"Shitao Li, Huawei ","lishitao<at>huawei<dot>com ","5/4/22: 28.903 added;; 4/6/22: 0%->15; 12/9/22: 15%->50; 12/9/22: FCD:12/09/2022->03/23; 17/3/23: 50%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100","28.903",95,48,null,null,"Thu 10/03/22","Thu 08/06/23"]
[1593,950030,"Study on Management Aspect of 5GLAN ","FS_5GLAN_Mgt",1,"Rel-18","S5","Thu 10/03/22","Fri 03/03/23",1,"SP-220324",null,"Xiaowen Sun, CMCC ","sunxiaowen@chinamobile.com ","5/4/22: 28.833 added;; 4/6/22: 0%->25; 12/9/22: 25%->65; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 65%->98; 17/3/23: 98%->100; 8/6/23: 100%->","28.833",95,48,null,null,"Thu 10/03/22","Thu 08/06/23"]
[1594,990027,"Management Aspect of 5GLAN ","5GLAN_Mgt",1,"Rel-18","S5","Thu 16/03/23","Tue 12/12/23",1,"SP-230175",null,"Yushuang Hu, CMCC, ","huyushuang@chinamobile.com ","; 8/6/23: 0%->45; 7/9/23: 45%->90; 8/12/23: 90%->100","28.541; 28.552; 28.554 ",99,50,null,null,"Thu 16/03/23","Fri 08/12/23"]
[1595,950032,"Study on Management of Cloud Native Virtualized Network Functions ","FS_MCVNF",1,"Rel-18","S5","Thu 10/03/22","Tue 06/06/23",1,"SP-220150",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","5/4/22: 28.834 added;; 4/6/22: 0%->5; 12/9/22: 5%->30; 11/12/22: 30%->70; 17/3/23: 70%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100; 4/1/24: 28.869 added;","28.834; 28.869",95,48,null,null,"Thu 10/03/22","Thu 04/01/24"]
[1596,950033,"Study on Management Aspects of 5G MOCN Network Sharing Phase2 ","FS_MANS_ph2",1,"Rel-18","S5","Thu 10/03/22","Tue 06/06/23",1,"SP-220151",null,"Zhaoning Wang, ChinaUnicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.835 added;; 4/6/22: 0%->30; 12/9/22: 30%->75; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 75%->90; 17/3/23: 90%->94; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 94%->100; 4/1/24: 28.878 added;","28.835; 28.878",95,48,null,null,"Thu 10/03/22","Thu 04/01/24"]
[1597,1000012,"Management Aspects of 5G Network Sharing Phase2 ","MANS_ph2",1,"Rel-18","S5","Thu 08/06/23","Sun 03/03/24",1,"SP-230629",null,"Wang Zhaoning, China Unicom, ","wangzn18@chinaunicom.cn, ","; 7/9/23: 0%->30; 8/12/23: 30%->60; 14/3/24: 60%->100","32.130; 28.541; 28.552 ",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[1598,950034,"Study on Management of Trace/MDT phase 2 ","FS_5GMDT_Ph2",1,"Rel-18","S5","Thu 10/03/22","Tue 06/06/23",1,"SP-230773",null,"Sivaramaskrishnan Swaminathan, Nokia ","sivaramakrishnan.swaminathan@nokia.com","5/4/22: 28.837 added;; 4/6/22: 0%->15; 12/9/22: 15%->25; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 25%->35; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 35%->60; 8/6/23: 60%->100; 30/6/23: WID:SP-220152->SP-230773","28.837",95,48,null,null,"Thu 10/03/22","Fri 30/06/23"]
[1599,950035,"Study on Fault Supervision Evolution ","FS_FSEV",1,"Rel-18","S5","Thu 10/03/22","Sun 03/03/24",1,"SP-220153",null,"Deng LingLi (China Mobile)",null,"5/4/22: 28.830 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 8/6/23: 20%->; 8/6/23: 20%->30; 8/6/23: FCD:03/03/2023->/24; 7/9/23: 30%->40; 8/12/23: 40%->65; 14/3/24: 65%->100","28.830",95,48,null,null,"Thu 10/03/22","Thu 14/03/24"]
[1600,960024,"Study on measurement data collection to support RAN intelligence ","FS_MEDACO_RAN",1,"Rel-18","S5","Thu 02/06/22","Mon 12/12/22",1,"SP-220488",null,"Chou, Joey, Intel ","joey<dot>chou<at>intel<dot>com ","12/9/22: 0%->10; 11/12/22: 10%->100; 8/6/23: 100%->",null,96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1601,920020,"Study on Nchf charging services phase 2","FS_NCHF_Ph2",1,"Rel-18","S5","Fri 11/06/21","Tue 12/12/23",1,"SP-210390",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","12/3/22: 0%->40; 4/6/22: 40%->60; 4/6/22: FCD:11/03/2022->03/23; 21/6/22: 60%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->70; 11/12/22: 70%->94; 11/12/22: 94%->75; 17/3/23: 75%->98; 17/3/23: 98%->88; 8/6/23...",null,92,47,null,null,"Fri 11/06/21","Fri 08/12/23"]
[1602,990029,"CHF Distributed Availability ","DIST_CH",1,"Rel-18","S5","Thu 16/03/23","Sat 09/09/23",1,"SP-230179",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","; 8/12/23: 0%->100","32.240; 32.290 ",99,50,null,null,"Thu 16/03/23","Fri 08/12/23"]
[1603,920021,"Study on 5G roaming charging architecture for wholesale and retail scenarios ","FS_CHROAM",1,"Rel-18","S5","Fri 11/06/21","Sat 09/09/23",1,"SP-210391",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","13/9/21: 0%->10; 12/3/22: 10%->50; 4/6/22: 50%->100; 4/6/22: FCD:11/03/2022->03/23; 4/6/22: 100%->75; 4/6/22: 0%->75; 21/6/22: 75%->100 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85%->90; 17/3/23: ...",null,92,47,null,null,"Fri 11/06/21","Thu 07/09/23"]
[1604,1010017,"Charging for roaming and additional actor using CHF to CHF interface ","CHRACHF",1,"Rel-18","S5","Wed 06/09/23","Sun 03/03/24",1,"SP-231153",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","; 8/12/23: 0%->40; 14/3/24: 40%->100","32.240; 32.255; 32.256; 32.290; 32.291; 32.298 ",101,51,null,null,"Wed 06/09/23","Thu 14/03/24"]
[1605,970030,"Methodology for deprecation ","OAM_MetDep",1,"Rel-18","S5","Mon 12/09/22","Fri 10/03/23",1,"SP-220843",null,"Lengyel, Balázs, Ericsson ","balazs.lengyel@ericsson.com ","; 11/12/22: 0%->95; 17/3/23: 95%->100","32.156; 32.160 ",97,49,null,null,"Sun 11/09/22","Fri 17/03/23"]
[1606,970029,"Study on Data management phase 2 ","FS_MADCOL_ph2",1,"Rel-18","S5","Mon 12/09/22","Sun 03/03/24",1,"SP-220842",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","; 23/9/22: 28.842 added;; 11/12/22: 0%->5; 11/12/22: FCD:12/06/2023->/23; 17/3/23: 5%->10; 8/6/23: 10%->25; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 25%->45; 8/12/23: 45%->80; 4/1/24: 28.873 added;; 14/3/24: 80%->100","; 28.842; 28.873",97,49,null,null,"Sun 11/09/22","Thu 14/03/24"]
[1607,970032,"Study on Time Sensitive Networking (TSN) Charging ","FS_TSNCH",1,"Rel-18","S5","Mon 12/09/22","Tue 12/12/23",1,"SP-220979",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","23/9/22: 28.839 added;; 11/12/22: 0%->10; 17/3/23: 10%->25; 8/6/23: 25%->70; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 70%->100","28.839",97,49,null,null,"Sun 11/09/22","Thu 07/09/23"]
[1608,1010014,"Charging Aspects of TSN ","TSN_CH",1,"Rel-18","S5","Wed 06/09/23","Sun 03/03/24",1,"SP-240268",null,"Deng, Yimeng, Huawei, ","dengyimeng at huawei dot com ","; 21/9/23: 32.282 added;; 8/12/23: 0%->60; 14/3/24: 60%->100; 2/4/24: WID:SP-231151->SP-240268","32.240; 32.254; 32.255; 32.291; 32.298; 32.297 ; 32.282",101,51,null,null,"Wed 06/09/23","Tue 02/04/24"]
[1609,990032,"Charging Aspects for NSSAA ","NSSAA_CH",1,"Rel-18","S5","Thu 16/03/23","Sun 03/03/24",1,"SP-230182",null,"Gerald Görmer, MATRIXX Software ","Gerald dot Goermer at Matrixx dot com ","; 31/3/23: 28.204 added;; 8/6/23: 0%->10; 7/9/23: 10%->40; 8/12/23: 40%->80; 14/3/24: 80%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.204",99,50,null,null,"Thu 16/03/23","Thu 14/03/24"]
[1610,990033,"Management Aspects of NTN ","OAM_NTN",1,"Rel-18","S5","Thu 16/03/23","Tue 12/12/23",1,"SP-230183",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","; 7/9/23: 0%->30; 8/12/23: 30%->100","28.541; 28.552; 28.554; 28.658 ",99,50,null,null,"Thu 16/03/23","Fri 08/12/23"]
[1611,990034,"Management of non-public networks phase 2 ","OAM_NPN_Ph2",1,"Rel-18","S5","Thu 16/03/23","Sun 03/03/24",1,"SP-230184",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","; 8/6/23: 0%->10; 7/9/23: 10%->40; 8/12/23: 40%->65; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 65%->100","28.557; 28.541; 28.531; 28.533; 28.552 ",99,50,null,null,"Thu 16/03/23","Thu 14/03/24"]
[1612,0,"Rel-18 service-based aspects","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1613,920022,"Study on Standardising Automated Certificate Management in SBA ","FS_ACM_SBA",1,"Rel-18","S3","Fri 11/06/21","Fri 03/03/23",1,"SP-220325",null,"BT, Niraj Rathod ","Niraj.rathod@bt.com ","Was previously listed under Rel-18 but according to SA#92 report, it is Rel-17; 1/10/21: 33.876 added;; 10/3/22: WID:SP-210419->SP-220195. Rel-17->Rel-18; 12/3/22: 0%->5; 12/3/22: FCD:10/06/2022->9/22; 4/6/22: 5%->35; 12/9/22: 35%->60; 17/3/23: 60%->90...","33.876",92,47,null,null,"Fri 11/06/21","Thu 08/06/23"]
[1614,990037,"Automated certificate management in SBA ","ACM_SBA",1,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230768",null,"Peinado, German, Nokia ","german.peinado@nokia.com ","; 8/6/23: 0%->35; 30/6/23: WID:SP-230150->SP-230768; 7/9/23: 35%->100","33.310 ",99,50,null,null,"Thu 16/03/23","Thu 07/09/23"]
[1615,980022,"Security Aspects of the 5G Service Based Architecture Phase 2 ","5G_eSBA_Ph2",1,"Rel-18","S3","Fri 09/12/22","Fri 03/03/23",1,"SP-221145",null,"Anja Jerichow, Nokia ","anja.jerichow@nokia.com ","; 8/6/23: 0%->95; 15/3/24: 95%->100","33.501 ",98,50,null,null,"Fri 09/12/22","Fri 15/03/24"]
[1616,960052,"Service Based Interface Protocol Improvements Release 18 ","SBIProtoc18",1,"Rel-18",null,"Fri 03/06/22","Tue 12/12/23",1,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,null,"29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"Fri 03/06/22","NA"]
[1617,960001,"   CT4 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C4","Fri 03/06/22","Tue 12/12/23",1,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,"; 6/6/23: Compl:25%->50%","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.524; 29.531; 29.532; 29.536; 29.540; 29.541; 29.542; 29.544; 29.550; 29.555; 29.556; 29.559; 29.562; 29.563; 29.564; 29.571; 29.572; 29.573; 29.577; 29.578; 29.579;",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1618,960060,"   CT3 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C3","Fri 03/06/22","Tue 12/12/23",1,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,"; 9/6/23: 30%->60","29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"Fri 03/06/22","Fri 09/06/23"]
[1619,960004,"Study on GBA_U Based APIs ","FS_GBA_U_API",1,"Rel-18","C6","Fri 03/06/22","Fri 03/03/23",1,"CP-221185",null,"Huo Weijing, China Mobile ","huoweijing@chinamobile.com ","13/7/22: 31.822 added","31.121 ; 31.822",96,49,null,null,"Fri 03/06/22","Wed 13/07/22"]
[1620,1000003,"GBA_U Based APIs ","GBA_U_APIs",1,"Rel-18","C6","Wed 07/06/23","Sun 03/03/24",1,"CP-231353",null,"Huo Weijing(China Mobile) ","huoweijing@chinamobile.com ","; 30/6/23: 31.122 added;","31.102; 31.130; 31.116 ; 31.122",100,51,null,null,"Wed 07/06/23","Fri 30/06/23"]
[1621,800045,"Study on IETF QUIC Transport for Service Based Interfaces","FS_QUIC",1,"Rel-18","C4","Tue 12/12/23","Tue 12/12/23",1,"CP-183245",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","6/8/18: 29.893 added;¦10/9/18: 0%->40¦10/12/18: FCD:03/19->06/19¦10/12/18: WID:CP-181194->CP-183245¦14/3/19: 50%->75; 31/5/19: 75%->80. 02/07/20: moved Rel-16->Rel-17; 13/9/20: FCD:12/06/2019->09/21; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22:rel-17->18","New; 29.893",80,41,null,null,"Wed 06/06/18","Mon 13/09/21"]
[1622,0,"Rel-18 other aspects","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1623,920042,"(Small) Technical Enhancements and Improvements for Rel-18","TEI18",1,"Rel-18",null,"Fri 12/03/21","Sun 24/07/22",0,null,null,null,null,null,null,92,47,null,null,"Mon 15/06/15","Mon 15/06/15"]
[1624,920003,"Lawful Interception Rel-18 ","LI18",1,"Rel-18","S3LI","Fri 12/03/21","Fri 02/12/22",0.96,"SP-230241",null,"Koen Jaspers, PIDS","kbj@xs4all.nl","10/9/21: WID:SP-210300->SP-210830; 4/6/22: 0%->5; 12/9/22: 5%->15; 11/12/22: 15%->20; 16/3/23: FCD:03/03/2023->/2023; 16/3/23: WID:SP-210830->SP-230241. Rapporteur changed from Alex Leadbeater; 31/3/23: 33.928 added;; 5/9/24: 20%->90; 5/12/24: 90%->96","33.128;33.127;33.126;33.108;33.107 ; 33.928",92,47,null,null,"Fri 11/06/21","Thu 05/12/24"]
[1625,959999,"Limbo: code to be used for not-approved CRs related to never-approved WIDs ","Limbo",1,"-",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","\"Dummy\" is a temporary code for CRs related to not-yet-approved WIDs. If a WID ended up not being approved at pleanry, then all related CRs have to be changed from \"Dummy\" to \"Limbo\"",null,95,48,null,null,"Sun 13/03/22","NA"]
[1626,999999,"Test - (Small) Technical Enhancements and Improvements for Rel-18 ","TEI18_Test",1,"Rel-18","R5","Wed 05/01/22","Thu 16/03/23",1,null,null,null,null,"8/6/23: 0%->100",null,99,50,null,null,"Thu 08/06/23","Thu 08/06/23"]
[1627,1040002,"Update of conformance test specifications to Rel-18","UEConTest_R18",1,"Rel-18","C6","Thu 29/06/23","Fri 06/06/25",0.4,"CP-241022",null,"Arne Marquordt, COMPRION GmbH","amarquordt@comprion.com",null,null,92,47,null,null,"Thu 12/08/21","NA"]
[1628,0,"--- RELEASE 17 ---","-",1,"Rel-17",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1629,0,"Rel-17 on Use of 5G by different sectors (\"verticals\")","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1630,840050,"Enhancements for cyber-physical control applications in vertical domains ","eCAV",1,"Rel-17",null,"Thu 07/03/19","Thu 12/12/19",1,"SP-190310",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ",null,"22.104; 22.261 ",84,43,null,null,"Fri 31/05/19","NA"]
[1631,830020,"   Study on eCAV","FS_eCAV",2,"Rel-17","S1","Thu 07/03/19","Thu 05/09/19",1,"SP-190092","-","Michael Bahr, Siemens AG","bahr et siemens dod com ","14/3/19: 0%->5; 31/5/19: 5%->60; 13/9/19: 60%->85; 6/12/19: 85%->95; 26/6/20: 95%->100","New",83,42,null,null,"Thu 14/03/19","Fri 26/06/20"]
[1632,840041,"   Stage 1 of eCAV","eCAV",2,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-191043",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ","31/5/19: 0%->10; 13/9/19: 10%->80; 20/9/19: WID:SP-190310->SP-190945; 6/12/19: 80%->95; 12/12/19: WID:SP-190945->SP-191043; 26/6/20: 95%->100","22.104; 22.261 ",84,43,null,null,"Fri 31/05/19","Fri 26/06/20"]
[1633,840024,"Study on enhanced support of Non-Public Networks ","FS_eNPN",1,"Rel-17","S2","Thu 06/06/19","Fri 12/03/21",1,"SP-200094",null,"Peter Hedman ","peter . hedman @ ericsson . com ","8/10/19: 23.700-07 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190453->SP-200094; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->35; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/ ","New ; 23.700-07",84,43,null,null,"Fri 31/05/19","Fri 19/03/21"]
[1634,910065,"Enhanced support of Non-Public Networks ","eNPN",1,"Rel-17",null,"Fri 12/06/20","Fri 10/06/22",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ",null,"23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"Thu 03/12/20","NA"]
[1635,900015,"   Stage 2 for eNPN","eNPN",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ","19/3/21: 0%->20; 14/6/21: 20%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->95; 10/12/21: 95%->97; 12/3/22: 97%->100","23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"Thu 03/12/20","Sat 12/03/22"]
[1636,910016,"   CT aspects of eNPN","eNPN",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 10/9/21: WID:CP-210139->CP-212103","23.003; 23.122; 24.008; 24.167; 24.229; 24.368; 24.501; 24.526; 27.007; 29.503; 29.505; 29.509; 29.513; 29.522; 29.525; 29.561 ",91,46,null,null,"Thu 18/03/21","Fri 10/09/21"]
[1637,910066,"      CT1 aspects of eNPN","eNPN",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->20; 13/9/21: 20%->40; 13/12/21: 40%->65; 12/3/22: 65%->93; 4/6/22: 93%->99; 20/6/22: Compl:99%->100%",null,91,46,null,null,"Thu 18/03/21","Mon 20/06/22"]
[1638,910067,"      CT3 aspects of eNPN","eNPN",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 13/9/21: 0%->45; 13/12/21: 45%->75; 13/12/21: WID:CP-212103->CP-213072; 12/3/22: 75%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1639,910068,"      CT4 aspects of eNPN","eNPN",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->98; 4/6/22: 98%->100",null,91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1640,920025,"   Security Aspects of eNPN ","eNPN",2,"Rel-17","S3","Fri 11/06/21","Fri 10/06/22",1,"SP-210422",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 13/9/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100","33.501 ",92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1641,880008,"   Study on enhanced security support for Non-Public Networks ","FS_eNPN_SEC",2,"Rel-17","S3","Fri 12/06/20","Fri 10/06/22",1,"SP-200353",null,"Normann, Henrik, Ericsson ","henrik.normann@ericsson.com ","28/7/20: 33.857 added;; 12/9/20: 0%->10; 5/12/20: 10%->35; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 35%->65; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->90; 12/3/22: 90%->90; 12/3/22: FCD:10/12/2021-> ","33.857",88,45,null,null,"Thu 25/06/20","Sat 04/06/22"]
[1642,840045,"Audio-Visual Service Production ","AVPROD",1,"Rel-17",null,"Wed 06/06/18","Thu 12/12/19",1,"SP-190304",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ",null,"22.261 ",84,43,null,null,"Fri 31/05/19","NA"]
[1643,800014,"   Study on AVPROD","FS_AVPROD",2,"Rel-17","S1","Wed 06/06/18","Wed 12/06/19",1,"SP-181015",null,"Roland Beutler, EBU","Roland.Beutler@swr.de","6/8/18: 22.827 added;¦10/9/18: 0%->10¦4/12/18: 10%->50¦14/12/18: WID:SP-180340->SP-181015¦14/12/18: FCD:03/19->06/19¦14/3/19: 50%->80; 31/5/19: 80%->95; 13/9/19: 95%->100","22.827",80,41,null,null,"Wed 06/06/18","Fri 13/09/19"]
[1644,840031,"   Stage 1 of AVPROD","AVPROD",2,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-191041",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ","13/9/19: 0%->80; 6/12/19: 80%->100; 12/12/19: WID:SP-190304->SP-191041","22.261 ",84,43,null,null,"Fri 31/05/19","Thu 12/12/19"]
[1645,910001,"Study on Media Production over 5G NPN ","FS_NPN4AVProd",1,"Rel-17","S4","Thu 18/03/21","Fri 10/06/22",1,"SP-210241",null,"Lohmar, Thorsten, Ericsson ","Thorsten.Lohmar@ericsson.com ","; 9/4/21: 26.805 added;; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/12/21: 30%->60; 12/3/22: 60%->80; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 80%->100","New 26.805",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1646,820025,"Study on application layer support for Factories of the Future in 5G network","FS_FFAPP",1,"Rel-17","S6","Thu 07/03/19","Fri 11/06/21",1,"SP-200836",null,"Shao Weixiang, ZTE Corporation","shao.weixiang@zte.com.cn","14/3/19: 0%->5; 31/5/19: 5%->15; 13/9/19: 15%->20; 13/9/19: FCD:12/03/2020->09/20; 20/9/19: WID:SP-181139->SP-190724; 6/12/19: 20%->40; 26/3/20: 40%->50; 25/6/20: WID:SP-190724->; 28/6/20: 50%->60; 13/9/20: 60%->70; 13/9/20: WID:->SP-200836; 13/9/20: F ","new",82,42,null,null,"Thu 06/12/18","Mon 13/09/21"]
[1647,840025,"Stopped - Study on enhancement of support for 5G LAN-type service ","FS_5GLAN_enh",1,"Rel-17","S2","Thu 06/06/19","Thu 12/03/20",1,"SP-190626",null,"Runze Zhou, Huawei ","zhourunze@huawei.com ","20/9/19: WID:SP-190454->SP-190626; 8/10/19: 23.762 added;; 22/3/22: Stopped at 0% (Puneet: deprioritized as part of the Rel-17 prioritization exercise)","New ; 23.762",84,43,96,null,"Fri 31/05/19","Tue 22/03/22"]
[1648,900022,"Study on Charging Aspect of 5G LAN-type Services ","FS_5GLAN_CH",1,"Rel-17","S5","Fri 04/12/20","Fri 10/12/21",1,"SP-201081",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","21/3/21: 0%->10; 2/7/21: 28.822 added;; 13/9/21: 10%->60; 13/9/21: FCD:Fri 11/06/->12/21; 12/3/22: 60%->100","28.822",90,46,null,null,"Fri 04/12/20","Sat 12/03/22"]
[1649,940029,"Charging Aspects of 5G LAN VN Group ","5GLAN_CH",1,"Rel-17","S5","Fri 10/12/21","Fri 10/06/22",1,"SP-220291",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","; 12/3/22: 0%->35; 22/3/22: WID:SP-211430->SP-220291; 4/6/22: 35%->100","32.240; 32.255; 32.291; 32.298 ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1650,840042,"Complete Gap Analysis for Railways Mobile Communication System ","MONASTERYEND",1,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-190312",null,"Gach, Guillaume, UIC ","ext.gach@uic.org ","31/5/19: 0%->20; 13/9/19: 20%->80; 6/12/19: 80%->100","22.280; 22.281; 22.282; 22.179; 22.289 ",84,43,null,null,"Fri 31/05/19","Fri 06/12/19"]
[1651,890035,"Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 ","eMONASTERY2",1,"Rel-17",null,"Thu 06/06/19","Fri 11/03/22",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"Fri 31/05/19","Sun 28/06/20"]
[1652,840037,"   Stage 2 of eMONASTERY2","eMONASTERY2",2,"Rel-17","S6","Thu 06/06/19","Fri 11/09/20",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85; 13/9/20: 85%->100","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"Fri 31/05/19","Sun 13/09/20"]
[1653,890063,"   Stage 3 of eMONASTERY2 ","eMONASTERY2",2,"Rel-17","C1","Wed 16/09/20","Fri 11/03/22",1,"CP-202256",null,"Gkatzikis, Lazaros, Nokia(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->50; 13/9/21: 50%->55; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 55%->70; 12/3/22: 70%->80; 4/6/22: 80%->98","24.379 ; 24.282 ; 24.481 ; 24.483 ; 24.484 ; 24.582 ",89,45,null,null,"Fri 25/09/20","Sat 04/06/22"]
[1654,840043,"Study on Future Railway Mobile Communication System3 ","FS_FRMCS3",1,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-200578",null,"Gach, Guillaume, UIC, ","ext.gach@uic.org ","31/5/19: 0%->40; 13/9/19: 40%->80; 6/12/19: 80%->100; 25/6/20: WID:SP-190321->SP-200578","22.989 ",84,43,null,null,"Fri 31/05/19","Thu 25/06/20"]
[1655,850046,"Asset Tracking for 5G ","ATRAC",1,"Rel-17",null,"Thu 06/09/18","Thu 12/12/19",1,"SP-190816",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ",null,"22.261 ",85,43,null,null,"Fri 13/09/19","NA"]
[1656,810017,"   Study on ATRAC","FS_5G_ATRAC",2,"Rel-17","S1","Thu 06/09/18","Fri 14/06/19",1,"SP-180922",null,"Thierry Berisot, NOVAMINT","tberisot@novamint.com","4/12/18: 0%->15¦14/3/19: 15%->45; 31/5/19: 45%->50; 13/9/19: 50%->100","22.836",81,41,null,null,"Thu 06/09/18","Fri 13/09/19"]
[1657,850037,"   Stage 1 of ATRAC","ATRAC",2,"Rel-17","S1","Thu 19/09/19","Thu 12/12/19",1,"SP-190931",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ","; 13/9/19: 0%->95; 6/12/19: 95%->100","22.261 ",85,43,null,null,"Fri 13/09/19","Fri 06/12/19"]
[1658,910052,"Enhancement to the 5GC LoCation Services-Phase 2 ","5G_eLCS_ph2",1,"Rel-17",null,"Wed 25/03/20","Fri 11/03/22",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20","23.273",87,44,null,null,"Fri 31/05/19","Sat 05/12/20"]
[1659,870001,"   Stage 2 of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","S2","Wed 25/03/20","Wed 08/09/21",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20; 19/3/21: 20%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100","23.273",87,44,null,null,"Fri 31/05/19","Fri 10/12/21"]
[1660,910006,"   CT aspects of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: WID:CP-210075->CP-211090",null,91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[1661,910053,"      CT1 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/12/21: 0%->50; 12/3/22: 50%->98; 20/6/22: Compl:98%->100%","24.501; 24.571; 27.007",91,46,null,null,"Thu 18/03/21","Mon 20/06/22"]
[1662,910054,"      CT3 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/9/21: 0%->10; 13/12/21: 10%->60; 12/3/22: 60%->100","29.522; 29.122",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1663,910055,"      CT4 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->75; 12/3/22: 75%->98; 4/6/22: 98%->100; 20/6/22: Compl:99%->100%","29.515; 29.572; 24.080; 29.518; 29.503; 29.571",91,46,null,null,"Thu 18/03/21","Mon 20/06/22"]
[1664,900060,"RAN aspects of NR positioning enhancements ","NR_pos_enh",1,"Rel-17",null,"Thu 07/03/19","Thu 12/12/24",1,"RP-210903",null,"Intel ",null,"follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202900->RP-210903",null,90,46,null,null,"Wed 06/01/21","Wed 07/04/21"]
[1665,860034,"   Study on NR positioning enhancements","FS_NR_pos_enh",2,"Rel-17","R1","Thu 07/03/19","Wed 03/06/20",1,"RP-202094",null,"CATT",null,"affects: NR. compare REL-16 NR_pos WI; TR 38.8xx; 26/3/20: WID:RP-193237->RP-200218; 28/7/20: WID:RP-200218->RP-200928; 25/9/20: WID:RP-200928->RP-202094; 7/4/21: 0%->100",null,86,44,null,null,"Tue 14/01/20","Wed 07/04/21"]
[1666,900160,"   Core part: NR positioning enhancements ","NR_pos_enh-Core",2,"Rel-17","R1","Mon 14/12/20","Tue 22/03/22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com; ",null,90,46,null,null,"Wed 06/01/21","Mon 20/06/22"]
[1667,900260,"   Perf. part: NR positioning enhancements ","NR_pos_enh-Perf",2,"Rel-17","R1","Mon 14/12/20","Thu 22/09/22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh ; 20/6/22: WG: R4->R1; FCD:08/09/2022->22/09/2022; Compl:0%->40%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com ; ;...; 23/9/22: 100%->100",null,90,46,null,null,"Wed 06/01/21","Fri 23/09/22"]
[1668,970075,"   UE Conformance - NR Positioning Enhancements ","NR_pos_enh-UEConTest",2,"Rel-17","R5","Thu 08/09/22","Thu 12/12/24",1,"RP-243120","RP-243119","Xiaoyang TIAN, CATT","tianxiaoyang@catt.cn","9/12/22: FCD:10/06/2024->31/05/2024; Compl:0%->5%; Stat Rep: ->RP-223137; Rapporteur: CATT->Xiaoyang TIAN, CATT; Rap eMail: ->tianxiaoyang@catt.cn; 17/3/23: Compl:5%->7%; Stat Rep: RP-223137->RP-230394; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:1...",null,97,49,null,null,"Fri 23/09/22","Fri 24/01/25"]
[1669,840047,"Communication Service Requirements for Critical Medical Applications ","CMED",1,"Rel-17",null,"Thu 06/09/18","Thu 12/12/19",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ",null,"22.261; 22.104 ",84,43,null,null,"Fri 31/05/19","NA"]
[1670,810016,"   Study on CMED","FS_CMED",2,"Rel-17","S1","Thu 06/09/18","Fri 13/09/19",1,"SP-180783",null,"Mathieu Lagrange, b<>com","mathieu.lagrange@b-com.com ","4/12/18: 0%->15¦14/3/19: 15%->65; 31/5/19: 65%->90; 6/12/19: 90%->100","22.826",81,41,null,null,"Thu 06/09/18","Fri 06/12/19"]
[1671,840033,"   Stage 1 of CMED","CMED",2,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ","13/9/19: 0%->80; 6/12/19: 80%->100","22.261; 22.104 ",84,43,null,null,"Fri 31/05/19","Fri 06/12/19"]
[1672,0,"Rel-17 drone/UAS/UAV/EAV","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-","06/21: \"unmanned\" changed to \"uncrewed\" as per SA#91 discussions","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1673,840083,"5G Enhancement for UAVs ","EAV",1,"Rel-17",null,"Thu 06/09/18","Fri 13/12/19",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,"22.125; 22.261 ",84,43,null,null,"Fri 31/05/19","NA"]
[1674,810019,"   Study on EAV","FS_EAV",2,"Rel-17","S1","Thu 06/09/18","Fri 13/12/19",1,"SP-180909",null,"Qun Wei, China Unicom","weiqun5@chinaunicom.cn","-; 31/5/19: 70%->90; 13/9/19: 90%->100","22.829",81,41,null,null,"Thu 06/09/18","Fri 13/09/19"]
[1675,840039,"   Stage 1 of EAV","EAV",2,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ","26.118¦26.247 ; 13/9/19: 0%->80; 6/12/19: 80%->100","26.118; 26.247¦22.125",84,43,null,null,"Fri 31/05/19","Fri 06/12/19"]
[1676,820011,"Study on supporting Uncrewed Aerial Systems Connectivity, Identification, and Tracking","FS_ID_UAS_SA2",1,"Rel-17","S2","Thu 06/12/18","Tue 15/12/20",1,"SP-200097",null,"Qualcomm Incorporated, Stefano Faccin ","sfaccin@qti.qualcomm.com","25/3/20: WID:SP-181114->SP-200097; 25/3/20: 0%->25; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 25%->50; 12/9/20: 50%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->100",null,82,42,null,null,"Thu 06/12/18","Sat 05/12/20"]
[1677,820026,"Study on application layer support for Uncrewed Aerial System (UAS) ","FS_UASAPP",1,"Rel-17","S6","Thu 06/12/18","Fri 12/03/21",1,"SP-200111",null,"Niranth Amogh, Huawei","namogh@huawei.com ","31/5/19: 0%->10; 13/9/19: 10%->25; 6/12/19: 25%->35; 6/12/19: FCD:13/12/2019->03/20; 25/3/20: WID:SP-181252->SP-200111; 25/3/20: FCD:12/03/2020->09/20; 28/6/20: 35%->45; 13/9/20: 45%->55; 5/12/20: 55%->75; 5/12/20: FCD:11/09/2020->03/20; 21/3/21: 75%->100","new 23.755",82,42,null,null,"Thu 06/12/18","Sun 21/03/21"]
[1678,920045,"Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",1,"Rel-17",null,"Fri 04/12/20","Fri 11/03/22",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","23.434 ; 21/3/21: 0%->25",null,90,46,null,null,"Fri 04/12/20","Sun 21/03/21"]
[1679,900025,"   Stage 2 of Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",2,"Rel-17","S6","Fri 04/12/20","Fri 11/06/21",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","21/3/21: 0%->25; 11/6/21: 25%->100; 2/7/21: 23.255 added;","23.434 ; new 23.255",90,46,null,null,"Fri 04/12/20","Fri 02/07/21"]
[1680,920004,"   CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C1","Fri 11/06/21","Fri 11/03/22",1,"CP-211111",null,"Lin Shu, Huawei, ","shulin@huawei.com ","; 2/7/21: 24.257 added;; 13/9/21: 0%->40; 13/12/21: 40%->80; 12/3/22: 80%->100","24.548;24.545;27.007 ; 24.257",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1681,920046,"   CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C3","Fri 11/06/21","Fri 11/03/22",1,"CP-220303",null,"Lin Shu, Huawei ","shulin@huawei.com ","; 11/6/21: 0%->5; 2/7/21: 29.257 added;; 13/9/21: 5%->30; 13/12/21: 30%->75; 13/12/21: WID:CP-211111->CP-213076; 12/3/22: 75%->100; 12/3/22: WID:CP-213076->CP-220303","29.549 ; 29.257",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1682,880007,"Study on security aspects of Uncrewed Aerial Systems (UAS)","FS_UAS_SEC",1,"Rel-17","S3","Fri 12/06/20","Fri 10/12/21",1,"SP-200352",null,"Adrian Escott, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","12/9/20: 0%->15; 12/9/20: FCD:15/01/2021->03/21; 5/12/20: 15%->30; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 30%->65; 11/6/21: 65%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 90%->90; 31/3/23: 90%->100","33.854",88,45,null,null,"Thu 25/06/20","Fri 31/03/23"]
[1683,810049,"Remote Identification of Uncrewed Aerial Systems","ID_UAS",1,"Rel-17",null,"Thu 06/09/18","Thu 12/12/24",1,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com",null,null,81,41,null,null,"Thu 06/09/18","NA"]
[1684,810013,"   Stage 1 of Remote Identification of Uncrewed Aerial Systems","ID_UAS",2,"Rel-17","S1","Thu 06/09/18","Fri 14/12/18",1,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com","10/9/18: 0%->5¦4/12/18: 5%->100. Initially Rel-16","22.125",81,41,null,null,"Thu 06/09/18","Tue 04/12/18"]
[1685,900014,"   (Stage 2 of) Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-200979",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","19/3/21: 0%->15; 14/6/21: 15%->80; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->98; 10/12/21: 98%->100","23.501; 23.502; 23.503; 23.401 ",90,46,null,null,"Thu 03/12/20","Fri 10/12/21"]
[1686,910017,"   CT aspects for ID_UAS","ID_UAS",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: WID:CP-210287->CP-211112","24.501; 24.301; 24.008; 27.007; 29.502; 29.503; 29.504; 29.505; 29.510; 29.518; 29.571; 29.274; 29.522; 29.122; 29.512; 29.513; 29.514; 29.561; 29.519 ",91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[1687,910069,"      CT1 aspects for ID_UAS","ID_UAS",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->70; 12/3/22: 70%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1688,910070,"      CT3 aspects for ID_UAS","ID_UAS",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 2/7/21: 29.255 added;; 2/7/21: 29.257 added;; 13/9/21: 0%->20; 13/12/21: 20%->80; 12/3/22: 80%->100","29.255; 29.257",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1689,910071,"      CT4 aspects for ID_UAS","ID_UAS",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->80; 12/3/22: 80%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1690,920028,"   Security aspects of Uncrewed Aerial Systems ","ID_UAS",2,"Rel-17","S3","Fri 11/06/21","Fri 11/03/22",1,"SP-210425",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","1/10/21: 33.256 added;; 13/12/21: 0%->50; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 50%->100","33.256",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1691,991034,"   UE Conformance - Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS-UEConTest",2,"Rel-17","R5","Fri 03/03/23","Thu 12/12/24",1,"RP-241591","RP-241126","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","; 7/6/23: Compl:0%->6%; 7/6/23: CD:12/12/2024->12/12/2023; 6/9/23: Compl:6%->40%; Stat Rep: ->RP-231997; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; ; 14/3/24: FCD:12/12/2023->12/12/2024; Compl:40%->95%; ...",null,99,50,null,null,"Wed 29/03/23","Tue 23/07/24"]
[1692,0,"Rel-17 Satellite/Non-Terrestrial (NTN) related ","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1693,890034,"Integration of satellite components in the 5G architecture ","5GSAT_ARCH",1,"Rel-17",null,"Wed 06/06/18","Fri 11/03/22",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ",null,"23.501; 23.502; 23.503 ",86,44,null,null,"Fri 06/12/19","NA"]
[1694,800048,"   Stage 1 of 5GSAT","5GSAT",2,"Rel-17","S1","Wed 06/06/18","Fri 14/09/18",1,"SP-180326",null,"MICHEL, Cyril, Thales","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->95¦4/12/18: 95%->100. 09/20: moved to Rel-17 since St 2 and 3 are Rel-17","22.261",80,41,null,null,"Wed 06/06/18","Tue 04/12/18"]
[1695,800026,"   Study on architecture aspects for using satellite access in 5G","FS_5GSAT_ARCH",2,"Rel-17","S2","Wed 06/06/18","Thu 25/06/20",1,"SP-181253",null,"MICHEL, Cyril","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->15¦10/9/18: FCD:06/19->03/19¦7/12/18: 15%->35¦14/12/18: WID:SP-180505->SP-181253¦14/12/18: FCD:03/19->09/19¦14/3/19: 35%->50; 5/6/19: 50%->60; 13/9/19: 60%->70. Moved to R17.; 6/12/19: 70%->85; 26/6/20: FCD:12/09/2019->06/20; 26/6/20: 85%- ","New",80,41,null,null,"Wed 06/06/18","Fri 26/06/20"]
[1696,860005,"   (Stage 2 of) Integration of satellite components in the 5G architecture ","5GSAT_ARCH",2,"Rel-17","S2","Fri 06/12/19","Wed 08/09/21",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->10; 12/9/20: FCD:11/09/2020->03/21; 5/12/20: 10%->50; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->98; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 98%->99; 10/12/21: 99%->100","23.501; 23.502; 23.503 ",86,44,null,null,"Fri 06/12/19","Fri 10/12/21"]
[1697,911030,"   CT aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",2,"Rel-17","ct","Wed 16/09/20","Fri 11/03/22",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: WID:CP-202244->CP-210149","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"Sat 12/09/20","Fri 11/06/21"]
[1698,890005,"      CT1 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C1","Wed 16/09/20","Fri 11/03/22",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 13/9/21: 80%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 75%->85; 4/6/22: 85%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"Sat 12/09/20","Sat 04/06/22"]
[1699,920057,"      CT3 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C3","Wed 16/09/20","Fri 10/09/21",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"Sat 12/09/20","Sat 12/03/22"]
[1700,911031,"      CT4 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C4","Wed 16/09/20","Fri 11/03/22",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 0%->80; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 80%->90; 12/3/22: 90%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"Sat 12/09/20","Sat 12/03/22"]
[1701,930044,"      CT6 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C6","Mon 13/09/21","Fri 11/03/22",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","CT6 aspects introduced as per CT6 report in CP-212127; 12/3/22: 0%->96; 4/6/22: 96%->97",null,93,47,null,null,"Sat 12/09/20","Sat 04/06/22"]
[1702,860046,"Solutions for NR to support non-terrestrial networks (NTN)","NR_NTN_solutions",1,"Rel-17",null,"Mon 16/12/19","Thu 12/12/24",0.97,"RP-220208",null,"Thales",null,"affects: NR. Follow-up WI of REL-16 SI FS_NR_NTN_solutions; 28/7/20: WID:RP-193234->RP-201256; 6/1/21: WID:RP-201256->RP-202908; 7/4/21: WID:RP-202908->RP-210908; 1/10/21: 38.108 & 38.181 added;; 5/4/22: WID:RP-210908->RP-220208","38.108; 38.181",86,44,null,null,"Tue 14/01/20","Tue 05/04/22"]
[1703,860146,"   Core part: Solutions for NR for NTN","NR_NTN_solutions-Core",2,"Rel-17","R4","Mon 16/12/19","Mon 06/06/22",1,"RP-221169","RP-230115","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR. follow-up WI of REL-16 SI FS_NR_NTN_solutions; 1/10/21: 38.863 added;; 7/1/22: 38.101-5 added ; ; 6/6/22: Compl:90%->0% ; 20/6/22: Compl:0%->100%; Stat Rep: RP-221168->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap e...","38.863; 38.101-5",86,44,null,null,"Tue 14/01/20","Fri 17/03/23"]
[1704,860246,"   Perf. Part: Solutions for NR for NTN","NR_NTN_solutions-Perf",2,"Rel-17","R4","Mon 16/12/19","Fri 03/03/23",1,"RP-222556","RP-230115","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/12/2022; Compl:40%->20%; WID: RP-220208->RP-213691; Stat Rep: RP-220132->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->nicolas.chuberre@thalesaleniaspace.com; ;...;...",null,86,44,null,null,"Tue 14/01/20","Fri 17/03/23"]
[1705,960074,"   UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) plus CT aspects ","NR_NTN_solutions_plus_CT-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Fri 12/12/25",0.93,"RP-221241","RP-251229","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 23/9/22: WID:RP-221241->RP-222537; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->13%; WID: RP-222537->RP-221241; Stat Rep: ->RP-223386; Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qual...","38.521-5",96,49,null,null,"Tue 12/07/22","Fri 06/06/25"]
[1706,920069,"NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","Tue 15/06/21","Fri 01/03/24",1,"RP-211601",null,"MediaTek ",null,"follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ",null,92,47,null,null,"Fri 02/07/21","NA"]
[1707,920169,"   Core part: NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN-Core",2,"Rel-17","R1","Tue 15/06/21","Wed 22/06/22",1,"RP-211601","RP-221546","Gilles Charbit, MediaTek","Gilles.charbit@mediatek.com","follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ; 20/6/22: Release: Rel-17->Rel-18; Rapporteur: MediaTek->Gilles Charbit, MediaTek; Rap eMail: ->Gilles.charbit@mediatek.com; ",null,92,47,null,null,"Fri 02/07/21","Mon 20/06/22"]
[1708,960087,"   UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects ","LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Fri 01/03/24",1,"RP-233250","RP-240442","Daiwei Zhou, MediaTek Inc.","daiwei.zhou@mediatek.com","9/9/22: Comp...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:45%->95%; Stat Rep: ->RP-223229; Rapporteur: MediaTek->Daiwei Zhou, MediaTek Inc.; Rap eMail: ->daiwei.zhou@mediatek.com; 17/3/23: FCD:09/09/2023->08/09/2023; Compl:95%->96%; Sta.....",null,96,49,null,null,"Tue 12/07/22","Thu 14/03/24"]
[1709,930019,"   Architecture support for NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","S2","Fri 10/09/21","Fri 10/12/21",1,"SP-211306",null,"SEBIRE, Guillaume, MediaTek Inc. ","guillaume dot sebire at mediatek dot com ","; 7/1/22: WID:SP-211124->SP-211306; 7/1/22: 0%->95; 12/3/22: 95%->100","23.203; 23.271; 23.401; 23.682 ",93,47,null,null,"Fri 10/09/21","Sat 12/03/22"]
[1710,940001,"   CT1 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C1","Mon 13/12/21","Tue 15/03/22",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 20%->80;; 20/6/22: FCD:13/12/2021->15/03/2022Compl:80%->95%","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",94,48,null,null,"Sat 12/03/22","Mon 20/06/22"]
[1711,970049,"   CT3 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C3","Mon 13/12/21","Tue 15/03/22",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"Sat 12/03/22","Sat 12/03/22"]
[1712,950045,"   CT4 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C4","Mon 13/12/21","Tue 15/03/22",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"Sat 12/03/22","Sat 12/03/22"]
[1713,950046,"   CT6 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C6","Mon 13/12/21","Tue 15/03/22",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 0%->80","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"Sat 12/03/22","Sat 04/06/22"]
[1714,830025,"Study on management and orchestration aspects with integrated satellite components in a 5G network","FS_5GSAT_MO",1,"Rel-17","S5","Thu 07/03/19","Fri 12/03/21",1,"SP-190138",null,"Floris Drijver, TNO","floris.drijver@tno.nl ","31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->30; 26/3/20: 30%->60; 26/3/20: FCD:05/12/2019->06/20; 28/6/20: 60%->65; 13/9/20: 65%->70; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 90%->100","New",83,42,null,null,"Thu 14/03/19","Sun 21/03/21"]
[1715,860033,"Study on NB-IoT/eMTC support for NTN","FS_LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","Mon 16/12/19","Tue 15/06/21",1,"RP-202689",null,"MediaTek",null,"affects: LTE. connecting LTE NB-IoT and LTE eMTC to NTN of NR; TR 36.7xx; 25/9/20: 36.763 added;; 6/1/21: WID:RP-193235->RP-202689; 2/7/21: 0%->100","36.763",86,44,null,null,"Tue 14/01/20","Fri 02/07/21"]
[1716,0,"Rel-17 IoT related ","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1717,850012,"Study on enhanced support of Industrial IoT ","FS_IIoT",1,"Rel-17","S2","Thu 19/09/19","Fri 12/03/21",1,"SP-200298",null,"Nokia, Devaki Chandramouli, ","devaki.chandramouli@nokia.com ","; 8/10/19: 23.700-20 added;; 6/12/19: 0%->20; 25/3/20: WID:SP-190932->SP-200298; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->95; 5/ ","New ; 23.700-20",85,43,null,null,"Fri 13/09/19","Fri 11/06/21"]
[1718,880010,"Study on security for enhanced support of Industrial IoT ","FS_IIoT_SEC",1,"Rel-17","S3","Fri 12/06/20","Fri 11/06/21",1,"SP-200355",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","28/7/20: 33.851 added;; 12/9/20: 0%->15; 5/12/20: 15%->60; 5/12/20: FCD:11/12/2020->06/20; 19/3/21: 60%->90; 11/6/21: 90%->100","33.851",88,45,null,null,"Thu 25/06/20","Fri 11/06/21"]
[1719,920024,"Security for enhanced support of Industrial IoT ","IIoT_SEC",1,"Rel-17","S3","Fri 11/06/21","Fri 18/06/21",1,"SP-210421",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","; 24/3/22: 0%->100","33.501 ",92,47,null,null,"Fri 11/06/21","Thu 24/03/22"]
[1720,910059,"Support of Enhanced Industrial IIoT ","IIoT",1,"Rel-17",null,"Thu 03/12/20","Fri 11/03/22",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ",null,null,90,46,null,null,"Thu 03/12/20","NA"]
[1721,900008,"   Stage 2 for IIoT","IIoT",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ","19/3/21: 0%->35; 11/6/21: 35%->90; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->100","23.501; 23.502; 23.503 ",90,46,null,null,"Thu 03/12/20","Mon 13/09/21"]
[1722,910014,"   CT aspects of support of enhanced Industrial IoT ","IIoT",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 10/9/21: WID:CP-211114->CP-212100","24.501; 24.519; 24.535; 29.512; 29.513; 29.514; 29.519; 29.522; 29.591; 29.244 ",91,46,null,null,"Thu 18/03/21","Fri 10/09/21"]
[1723,910060,"      CT1 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->65; 2/7/21: 24.539 added;; 13/9/21: 65%->90; 13/12/21: 90%->95; 12/3/22: 95%->100","24.539",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1724,910061,"      CT3 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->45; 11/6/21: WID:CP-210279->CP-211114; 13/9/21: 45%->65; 1/10/21: 29.565 added;; 13/12/21: 65%->85; 12/3/22: 85%->98; 4/6/22: 98%->100","29.565",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1725,910062,"      CT4 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->60; 13/9/21: 60%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1726,940044,"Charging enhancements for 5G CIoT ","5G_CIoT_CH",1,"Rel-17","S5","Fri 10/12/21","Fri 10/06/22",1,"SP-211448",null,"Zhu, Lei, Huawei ","Lei.zhu@huawei.com ","; 12/3/22: 0%->60; 4/6/22: 60%->100","32.255; 32.291; 32.298 ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1727,860044,"Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6",1,"Rel-17",null,"Thu 07/03/19","Thu 22/09/22",1,"RP-220529",null,"Huawei",null,"affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 28/7/20: WID:RP-193264->RP-201306; 2/7/21: WID:RP-201306->RP-211340; 5/4/22: WID:RP-211340->RP-220529",null,86,44,null,null,"Tue 14/01/20","Tue 05/04/22"]
[1728,860144,"   Core part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Core",2,"Rel-17","R1","Tue 21/12/21","Tue 22/03/22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 13/9/21: Com ; 20/6/22: Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 1...",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1729,860244,"   Perf. part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Perf",2,"Rel-17","R1","Thu 07/03/19","Thu 22/09/22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21 ; 22/3/22: Compl:0%->30% ; 20/6/22: WG: R4->R1; Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 0%->70; 20/6/22...",null,86,44,null,null,"Tue 14/01/20","Fri 09/09/22"]
[1730,860051,"NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE",1,"Rel-17",null,"Mon 16/12/19","Thu 12/12/24",1,"RP-222364",null,"ZTE",null,"affects: NR.; 28/7/20: WID:RP-193252->RP-201305; 7/4/21: WID:RP-201305->RP-210870; 29/9/21: WID:RP-210870->RP-212594; 23/9/22: WID:RP-212594->RP-222364",null,86,44,null,null,"Tue 14/01/20","Fri 23/09/22"]
[1731,860151,"   Core part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Core",2,"Rel-17","R2","Mon 16/12/19","Tue 22/03/22",1,"RP-222364","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; ; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn; ",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1732,860251,"   Perf. part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Perf",2,"Rel-17","R2","Mon 16/12/19","Wed 21/12/22",1,"RP-222364","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211871; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211871->RP-220153 20/6/22: WG: R4->R2; Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->es...; 9/",null,86,44,null,null,"Tue 14/01/20","Mon 09/01/23"]
[1733,960072,"   UE Conformance - NR small data transmissions in INACTIVE state ","NR_SmallData_INACTIVE-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Thu 12/12/24",1,"RP-221238","RP-242497","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:15%->30%; Stat Rep: ->RP-223385; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->75%; S.....",null,96,49,null,null,"Tue 12/07/22","Fri 24/01/25"]
[1734,860045,"Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR","NR_IIOT_URLLC_enh",1,"Rel-17",null,"Mon 16/12/19","Tue 12/12/23",1,"RP-220152",null,"Nokia",null,"affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 7/4/21: WID:RP-201310->RP-210854; 5/4/22: WID:RP-210854->RP-220152",null,86,44,null,null,"Tue 14/01/20","Tue 05/04/22"]
[1735,860145,"   Core part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Core",2,"Rel-17","R2","Mon 16/12/19","Tue 01/03/22",1,"RP-220152","RP-223027","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 28/7/20: WID:RP-193233->RP-201310; 13/9/21: Compl:0%->55% ; ; 20/6/22: Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; 9/12/22: FCD:22/03/2022->...",null,86,44,null,null,"Tue 14/01/20","Fri 09/12/22"]
[1736,860245,"   Perf. Part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Perf",2,"Rel-17","R2","Mon 15/06/20","Thu 01/12/22",1,"RP-220152","RP-223027","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","; 13/9/21: CD:Tue 15/03/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211938; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211938->RP-220151 20/6/22: WG: R4->R2; Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; ...; 9/",null,86,44,null,null,"Fri 25/09/20","Fri 09/12/22"]
[1737,960082,"   UE Conformance - Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR ","NR_IIOT_URLLC_enh-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Tue 12/12/23",1,"RP-221416","RP-232885","Matti Kangas, Nokia, Nokia Shanghai Bell","matti.kangas@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Stat Rep: ->RP-223013; Rapporteur: Nokia->Matti Kangas, Nokia, Nokia Shanghai Bell; Rap eMail: ->matti.kangas@nokia.com; 31/3/23: Compl:5%->74%; Stat Rep: RP-223013->RP-230700; ;...; 6/9...",null,96,49,null,null,"Tue 12/07/22","Fri 08/12/23"]
[1738,0,"Rel-17 V2V/D2D/Sidelink related ","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1739,860042,"NR Sidelink enhancement","NR_SL_enh",1,"Rel-17",null,"Mon 16/12/19","Mon 03/03/25",0.76,"RP-202846",null,"LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 28/7/20: WID:RP-193257->RP-201385; 25/9/20: WID:RP-201385->RP-201516; 6/1/21: WID:RP-201516->RP-202846",null,86,44,null,null,"Tue 14/01/20","Wed 06/01/21"]
[1740,860142,"   Core part: NR Sidelink enhancement","NR_SL_enh-Core",2,"Rel-17","R1","Mon 16/12/19","Fri 11/03/22",1,"RP-202846","RP-220520","LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 13/9/21: Compl:0%->63%; ; ",null,86,44,null,null,"Tue 14/01/20","Tue 22/03/22"]
[1741,860242,"   Perf. part: NR Sidelink enhancement","NR_SL_enh-Perf",2,"Rel-17","R4","Mon 16/12/19","Thu 22/09/22",1,"RP-221863","RP-221186","Seungmin Lee, LG Electronics","Edison.lee@lge.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; ; 22/3/22: Compl:0%->10%; 22/3/22: CD:22/09/2021->12/09/2022 20/6/22: FCD:12/09/2022->22/09/2022; Compl:10%->95%; Stat Rep: RP-220520->RP-221186; Rapporteur: LG Electronics->Seungmin Lee, LG El...; 23",null,86,44,null,null,"Tue 14/01/20","Fri 23/09/22"]
[1742,960084,"   UE Conformance - NR Sidelink enhancement ","NR_SL_enh-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Tue 09/09/25",0.5,"RP-221448","RP-251628","Xiaozhong CHEN, CATT","chenxiaozhong@catt.cn","9/9/22: Comp...; 9/12/22: FCD:23/09/2022->01/09/2023; Stat Rep: ->RP-223140; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023->08/09/2023; Stat Rep: RP-223140->RP-230396; ...; 6/9/23: FCD:0...",null,96,49,null,null,"Tue 12/07/22","Fri 06/06/25"]
[1743,860038,"Study on NR Sidelink relay","FS_NR_SL_relay",1,"Rel-17","R2","Mon 16/12/19","Tue 15/09/20",1,"RP-202208",null,"OPPO",null,"affects: NR. TR 38.8xx; 25/9/20: WID:RP-193253->RP-201474; 6/1/21: WID:RP-201474->RP-202208; 7/4/21: 0%->100",null,86,44,null,null,"Tue 14/01/20","Wed 07/04/21"]
[1744,840035,"Study on enhancements to application layer support for V2X services ","FS_eV2XAPP",1,"Rel-17","S6","Thu 06/06/19","Fri 12/06/20",1,"SP-200110",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/9/19: 0%->25; 8/10/19: 23.764 added;; 6/12/19: 25%->35; 25/3/20: WID:SP-190477->SP-200110; 25/3/20: FCD:12/03/2020->06/20; 26/3/20: 35%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 22/3/22: 95%->100","23.764",84,43,null,null,"Fri 31/05/19","Tue 22/03/22"]
[1745,910075,"Enhanced application layer support for V2X services ","eV2XAPP",1,"Rel-17",null,"Wed 16/09/20","Fri 11/03/22",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21","23.286; 23.434 ",89,45,null,null,"Fri 11/09/20","Wed 10/02/21"]
[1746,890036,"   Stage 2 of eV2XAPP","eV2XAPP",2,"Rel-17","S6","Wed 16/09/20","Tue 15/06/21",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 35%->55; 11/6/21: 55%->100","23.286; 23.434 ",89,45,null,null,"Fri 11/09/20","Fri 11/06/21"]
[1747,910019,"   CT aspects of eV2XAPP","eV2XAPP",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: WID:CP-210273->CP-211109","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549 ",91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[1748,910076,"      CT1 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 12/3/22: 85%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1749,910077,"      CT3 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1750,910037,"Support of advanced V2X services - Phase 2 ","eV2XARC_Ph2",1,"Rel-17",null,"Thu 19/09/19","Fri 11/03/22",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ",null,"23.287 ",91,46,null,null,"Thu 18/03/21","NA"]
[1751,850013,"   Study on V2X services – Phase 2 ","FS_eV2XARC_Ph2",2,"Rel-17","S2","Thu 19/09/19","Fri 12/03/21",1,"SP-190631",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->25; 12/9/20: 25%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->86; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 86%->100","New ",85,43,null,null,"Fri 13/09/19","Fri 19/03/21"]
[1752,910021,"   Stage 2 of eV2XARC_Ph2 ","eV2XARC_Ph2",2,"Rel-17","S2","Thu 18/03/21","Wed 08/09/21",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 14/6/21: 0%->70; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100","23.287 ",91,46,null,null,"Thu 18/03/21","Fri 10/12/21"]
[1753,920005,"   CT1 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C1","Fri 11/06/21","Fri 11/03/22",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->90; 12/3/22: 90%->100","24.588;24.587 ",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1754,920047,"   Deleted- CT3 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C3","Fri 11/06/21","Fri 11/03/22",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","03/22: No task for CT3; 22/3/22: 0%->100","31.102;29.522;29.525;29.519 ",92,47,null,null,"Fri 11/06/21","Tue 22/03/22"]
[1755,920048,"   CT6 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C6","Fri 11/06/21","Fri 11/03/22",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 4/6/22: 0%->100","31.102 ",92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1756,0,"Rel-17 NR enhancements","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1757,920070,"UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD",1,"Rel-17","R4","Tue 15/06/21","Fri 22/09/23",1,"RP-211940",null,"Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 29/9/21: WID:RP-211597->RP-211940",null,92,47,null,null,"Fri 02/07/21","Wed 29/09/21"]
[1758,920170,"   Core part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Core",2,"Rel-17","R4","Tue 15/06/21","Fri 11/03/22",1,"RP-211940","RP-220467","Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; 1/10/21: 38.837 added ; ","38.837",92,47,null,null,"Fri 02/07/21","Tue 22/03/22"]
[1759,920270,"   Perf. part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Perf",2,"Rel-17","R4","Tue 15/06/21","Fri 11/03/22",1,"RP-211940","RP-220467","Qualcomm ",null,"; 13/9/21: Compl:0%->10%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; ; ",null,92,47,null,null,"Fri 02/07/21","Tue 22/03/22"]
[1760,940092,"   UE Conformance - UE RF requirements for Transparent Tx Diversity (TxD) for NR","NR_RF_TxD-UEConTest",2,"Rel-17","R5","Mon 13/12/21","Fri 22/09/23",1,"RP-231240","RP-232351","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","tested: REL-17 WI NR_RF_TxD; 22/3/22: Compl:0%->5%; 22/3/22: Stat Rep: ->RP-220420 6/6/22: Compl:5%->23% 20/6/22: Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com12/7/22: WID:RP-213229->RP-221491 ...; 9/12/22: FCD:22/12/202...",null,94,48,null,null,"Thu 06/01/22","Wed 06/09/23"]
[1761,860040,"Further enhancements on MIMO for NR","NR_feMIMO",1,"Rel-17",null,"Mon 16/12/19","Mon 09/09/24",1,"RP-212535",null,"Samsung",null,"affects: NR. compare REL-16 WI NR_eMIMO; 25/9/20: WID:RP-193133->RP-202024; 2/7/21: WID:RP-202024->RP-211586; 29/9/21: WID:RP-211586->RP-212535",null,86,44,null,null,"Tue 14/01/20","Wed 29/09/21"]
[1762,860140,"   Core part: Further enhancements on MIMO for NR","NR_FeMIMO-Core",2,"Rel-17","R1","Mon 16/12/19","Tue 22/03/22",1,"RP-212535","RP-221403","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR. compare REL-16 WI NR_eMIMO; 13/9/21: Compl:0%->70%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211788 ; 20/6/22: Acronym:NR_feMIMO-Core->NR_FeMIMO-Core; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ...",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1763,860240,"   Perf. part: Further enhancements on MIMO for NR","NR_feMIMO-Perf",2,"Rel-17","R1","Mon 16/12/19","Thu 01/12/22",1,"RP-212535","RP-222928","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211788; 22/3/22: Compl:0%->25%; 20/6/22: Acronym:NR_feMIMO-Perf->NR_FeMIMO-Perf; WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.c...;...",null,86,44,null,null,"Tue 14/01/20","Mon 09/01/23"]
[1764,960079,"   UE Conformance - Further enhancements on MIMO for NR ","NR_feMIMO-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Mon 09/09/24",1,"RP-241983","RP-241980","Runsen Tang, Samsung","runsen.tang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->R5-226804; Rapporteur: Samsung->Runsen Tang, Samsung; Rap eMail: ->runsen.tang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: R5-226804->RP-2301.....",null,96,49,null,null,"Tue 12/07/22","Thu 26/09/24"]
[1765,860043,"NR Dynamic spectrum sharing (DSS)","NR_DSS",1,"Rel-17",null,"Mon 16/12/19","Tue 22/03/22",1,"RP-211345",null,"Ericsson",null,"affects: NR. no Perf. part; 2/7/21: WID:RP-193260->RP-211345",null,86,44,null,null,"Tue 14/01/20","Fri 02/07/21"]
[1766,860143,"   Core part: NR DSS","NR_DSS-Core",2,"Rel-17","R1","Mon 16/12/19","Tue 22/03/22",1,"RP-211345","RP-220463","Ravikiran Nory","ravikiran.nory@ericsson.com","affects: NR. no Perf. part; 20/6/22: FCD:15/03/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220463; Rapporteur: Ericsson->Ravikiran Nory; Rap eMail: ->ravikiran.nory@ericsson.com; ",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1767,860047,"UE power saving enhancements for NR","NR_UE_pow_sav_enh",1,"Rel-17",null,"Mon 16/12/19","Fri 01/03/24",1,"RP-221543",null,"MediaTek",null,"affects: NR. compare REL-16 WI NR_UE_pow_sav; 26/3/20: WID:RP-193239->RP-200494; 30/6/20: WID:RP-200494->RP-193239; 28/7/20: WID:RP-193239->RP-200938; 29/9/21: WID:RP-200938->RP-212630; 5/4/22: WID:RP-212630->RP-220748; 12/7/22: WID:RP-220748->RP-221543",null,86,44,null,null,"Tue 14/01/20","Tue 12/07/22"]
[1768,860147,"   Core part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Core",2,"Rel-17","R2","Mon 16/12/19","Tue 22/03/22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR. compare REL-16 WI NR_UE_pow_sav; ; 20/6/22: FCD:11/03/2022->22/03/2023; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn; ",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1769,860247,"   Perf. part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Perf",2,"Rel-17","R2","Mon 16/12/19","Thu 22/09/22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:35%->65%; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn9/9/22: 65%->100; 23/9/22: 100%->100",null,86,44,null,null,"Tue 14/01/20","Fri 23/09/22"]
[1770,880071,"   UE Conformance Test Aspects -UE Power Saving in NR","NR_UE_pow_sav-UEConTest",2,"Rel-16","R5","Mon 22/06/20","Thu 01/12/22",1,"RP-213291","RP-223138","Huiying ZHANG, CATT","zhanghuiying@catt.cn","8/10/20: 0%->5; 6/1/21: WID:RP-200930->RP-202726; 8/4/21: 5%->39; 2/7/21: FCD:Mon 21/06/->09/21; 2/7/21: 39%->52; 6/1/22: WID:RP-202726->RP-213291; 20/6/22: Rapporteur: CATT->Huiying ZHANG, CATT; Rap eMail: ->zhanghuiying@catt.cn ; ...; 9/12/22: FCD...",null,88,45,null,null,"Tue 28/07/20","Mon 09/01/23"]
[1771,960086,"   UE Conformance - UE power saving enhancements for NR ","NR_UE_pow_sav_enh_plus_CT-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Fri 01/03/24",1,"RP-233247","RP-233246","Eniko Sokondar, Vijay Balasubramanian, MediaTek, Qualcomm","eniko.sokondar[at]mediatek.com, vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:3%->20%; Stat Rep: ->RP-223228; Rapporteur: MediaTek->Eniko Sokondar, Vijay Balasubramanian, MediaTek, Qualcomm; Rap eMail: ->eniko.sokondar[at]mediatek.com, vijayb[at]qti.qualcomm...",null,96,49,null,null,"Tue 12/07/22","Tue 02/04/24"]
[1772,860049,"Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2",1,"Rel-17",null,"Mon 16/12/19","Thu 06/06/24",1,"RP-201040",null,"Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; 28/7/20: WID:RP-193249->RP-201040",null,86,44,null,null,"Tue 14/01/20","Tue 28/07/20"]
[1773,860149,"   Core part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Core",2,"Rel-17","R2","Mon 16/12/19","Fri 11/03/22",1,"RP-201040","RP-220409","Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; ",null,86,44,null,null,"Tue 14/01/20","Tue 22/03/22"]
[1774,860249,"   Perf. part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Perf",2,"Rel-17","R4","Mon 16/12/19","Thu 22/09/22",1,"RP-201040","RP-220409","Matti Kangas","matti.kangas@nokia.com","affects: LTE, NR.; 22/3/22: CD:15/12/2021->12/09/2022; 22/3/22: Stat Rep: ->RP-220409; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:0%->30%; Stat Rep: RP-220409->RP-221500; Rapporteur: Huawei->David Lecompte, Huawei; Rap eMail: ->david.lecomp...",null,86,44,null,null,"Tue 14/01/20","Fri 09/09/22"]
[1775,991033,"   UE Conformance - Further Multi-RAT Dual-Connectivity enhancement ","LTE_NR_DC_enh2-UEConTest",2,"Rel-17","R5","Fri 03/03/23","Thu 06/06/24",1,"RP-233764","RP-241372","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","; 7/6/23: Compl:0%->5%; 6/9/23: Compl:5%->46%; Stat Rep: ->RP-232355; Rapporteur: Huawei->Yaping ZHANG, Huawei; Rap eMail: ->zhangyaping13@huawei.com; ; 8/12/23: FCD:03/03/2024->01/03/2024; Compl:46%->94%; Stat Rep: RP-232355->RP-233763; ; 2/1/24: WID...",null,99,50,null,null,"Wed 29/03/23","Thu 13/06/24"]
[1776,860050,"Enhancements to Integrated Access and Backhaul (IAB) for NR","NR_IAB_enh",1,"Rel-17",null,"Mon 11/03/19","Thu 22/09/22",1,"RP-221177",null,"Qualcomm",null,"affects: NR. compare REL-16 WI NR_IAB; 28/7/20: WID:RP-193251->RP-201293; 7/4/21: WID:RP-201293->RP-210758; 2/7/21: WID:RP-210758->RP-211548; 6/1/22: WID:RP-211548->RP-213668; 12/7/22: WID:RP-213668->RP-221177",null,86,44,null,null,"Tue 14/01/20","Tue 12/07/22"]
[1777,860150,"   Core part: Enhancements to IAB for NR","NR_IAB_enh-Core",2,"Rel-17","R2","Mon 16/12/19","Wed 22/06/22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR. compare REL-16 WI NR_IAB; 13/9/21: Compl:0%->41%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211767 ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com; ",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1778,860250,"   Perf. part: Enhancements to IAB for NR","NR_IAB_enh-Perf",2,"Rel-17","R2","Mon 16/12/19","Thu 22/09/22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211767; 22/3/22: Compl:0%->20%; 22/3/2 20/6/22: WG: R4->R2; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com9/9/22: ...",null,86,44,null,null,"Tue 14/01/20","Fri 09/09/22"]
[1779,830021,"   Study on Security for NR_IAB","FS_NR_IAB_Sec",2,"Rel-17","S3","Mon 11/03/19","Fri 10/12/21",1,"SP-201016",null,"Rajavelsamy Rajadurai, Samsung, ","rajvel{@]samsung.com ","31/5/19: 0%->20; 13/9/19: 20%->50; 13/9/19: FCD:09/09/2019->12/20; 26/6/20: FCD:12/12/2019->12/20; 12/9/20: 50%->75; 5/12/20: FCD:15/12/2020->03/20; 5/12/20: WID:SP-190106->SP-201016, Rel-16->17; 9/4/21: FCD:12/03/2021->06/21; 11/6/21: 75%->78; 11/6/21 ","33.824",83,42,null,null,"Thu 14/03/19","Sat 12/03/22"]
[1780,860052,"Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN","LTE_NR_arch_evo_enh",1,"Rel-17",null,"Mon 16/12/19","Wed 09/03/22",1,"RP-213667",null,"China Unicom",null,"affects: LTE, NR. No Perf. Part; compare REL-16 WI LTE_NR_arch_evo; 2/7/21: WID:RP-193181->RP-211409; 6/1/22: WID:RP-211409->RP-213667; 7/1/22: 37.483 added;; 7/1/22: 37.480 added;","37.483; 37.482; 37.481; 37.480; 37.480; ",86,44,null,null,"Tue 14/01/20","Fri 21/01/22"]
[1781,860152,"   Core part: LTE_NR_arch_evo_enh","LTE_NR_arch_evo_enh-Core",2,"Rel-17","R3","Mon 16/12/19","Wed 09/03/22",1,"RP-213667","RP-220557","Gen Cao","caogen@chinaunicom.cn","affects: LTE, NR. no Perf. part; compare REL-16 WI LTE_NR_arch_evo; 6/1/22: WID:RP-211409->RP-213667; 20/6/22: FCD:15/12/2020->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220557; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinaunicom.cn2...",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1782,890055,"Further enhancement on NR demodulation performance ","NR_demod_enh2",1,"Rel-17",null,"Tue 15/09/20","Mon 09/09/24",1,"RP-221285",null,"China Telecom ",null,"demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 6/1/21: WID:RP-202000->RP-202828; 7/4/21: WID:RP-202828->RP-210920; 2/7/21: WID:RP-210920->RP-211135; 29/9/21: WID:RP-211135->RP-2126 ; ",null,89,45,null,null,"Sun 11/10/20","Tue 12/07/22"]
[1783,941114,"   Core part: Further enhancement on NR demodulation performance","NR_demod_enh2-Core",2,"Rel-17","R4","Tue 14/12/21","Wed 22/06/22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","; 20/6/22: Rapporteur: China Telecom->Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation; Rap eMail: ->yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com; ",null,94,48,null,null,"Tue 22/03/22","Mon 20/06/22"]
[1784,890255,"   Perf. part: NR_demod_enh2","NR_demod_enh2-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 2/7/21: 38.833 added;; 13/9/21: Compl:0%->45%; 13/9/21: C ; 6/1/22: WID:RP-212636->RP-213656 20/6/22: FCD:10/06/2022->22/09/2022;...","38.833",89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1785,960075,"   UE Conformance - Further enhancement on NR demodulation performance ","NR_demod_enh2-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Mon 09/09/24",1,"RP-241994","RP-241993","Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc","wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222947; Rapporteur: ChinaTelecom->Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc; Rap eMail: ->wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com; 17/3.....",null,96,49,null,null,"Tue 12/07/22","Thu 26/09/24"]
[1786,890056,"Introduction of DL 1024QAM for NR frequency range 1 (FR1)","NR_DL1024QAM_FR1",1,"Rel-17",null,"Tue 15/09/20","Tue 12/12/23",1,"RP-213654",null,"Ericsson ",null,"; 6/1/21: WID:RP-202044->RP-202886; 6/1/22: WID:RP-202886->RP-213654",null,89,45,null,null,"Sun 11/10/20","Thu 06/01/22"]
[1787,890156,"   Core part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Core",2,"Rel-17","R4","Tue 15/09/20","Tue 22/03/22",1,"RP-213654","RP-220190","Yi GUO","yi.guo@intel.com","; 20/6/22: FCD:08/09/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220190; Rapporteur: Ericsson->Yi GUO; Rap eMail: ->yi.guo@intel.com; ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1788,890256,"   Perf. part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Perf",2,"Rel-17","R4","Tue 15/09/20","Wed 22/06/22",1,"RP-213654","RP-221226 /1771","Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Nokia, Ericsson","kevin (dot) wanuga (at) nokia (dot) com; kazuyoshi (dot) uesaka (at) ericsson (dot) com","; 13/9/21: Compl:0%->90%; 13/9/21: CD:Sat 12/03/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211770; ; 20/6/22: FCD:11/03/2022->22/06/2022; Stat Rep: RP-220190->RP-221226 /1771; Rapporteur: Ericsson->Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Nokia, ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1789,960073,"   UE Conformance - Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Tue 12/12/23",1,"RP-221240","RP-233873","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:5%->34%; Stat Rep: ->RP-223384; Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qualcomm.com; 17/3/23: FCD:03/03/2023->08/09/2023; Stat Rep: RP-.....",null,96,49,null,null,"Tue 12/07/22","Fri 08/12/23"]
[1790,890057,"NR RRM further enhancement ","NR_RRM_enh2",1,"Rel-17",null,"Tue 15/09/20","Thu 22/09/22",1,"RP-213067",null,"Apple ",null,"LTE impacts? ; 6/1/21: WID:RP-202053->RP-202874; 6/1/22: WID:RP-202874->RP-213067",null,89,45,null,null,"Sun 11/10/20","Thu 06/01/22"]
[1791,890157,"   Core part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Core",2,"Rel-17","R4","Tue 15/09/20","Tue 22/03/22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 4/6/22: 0%->100; 20/6/22: FCD:08/09/2021->22/03/2023; Stat Rep: ->RP-221699; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com; ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1792,890257,"   Perf. part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22 ; ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->50%; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com 9/9...",null,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1793,890058,"Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh",1,"Rel-17",null,"Tue 15/09/20","Tue 06/06/23",1,"RP-210833",null,"CMCC ",null,"follow-up WI of REL-16 WI NR_HST ; 6/1/21: WID:RP-202106->RP-202335; 7/4/21: WID:RP-202335->RP-210833",null,89,45,null,null,"Sun 11/10/20","Wed 07/04/21"]
[1794,890158,"   Core part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Core",2,"Rel-17","R4","Tue 15/09/20","Tue 22/03/22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->70%; 13/9/ ; ; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com; ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1795,890258,"   Perf. part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->50%; 1 ; 22/3/22: Compl:50%->70%; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com ; 9/9/22: Compl:85%->100%",null,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1796,960077,"   UE Conformance - Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Tue 06/06/23",1,"RP-221359","RP-230283","Dan SONG, CMCC","songdan@chinamobile.com","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:23%->62%; Stat Rep: ->RP-223063; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com; 17/3/23: Compl:62%->71%; Stat Rep: RP-223063->RP-230283; ...",null,96,49,null,null,"Tue 12/07/22","Wed 07/06/23"]
[1797,890059,"Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2",1,"Rel-17",null,"Tue 15/09/20","Fri 01/03/24",1,"RP-221784",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh ; 6/1/21: WID:RP-202107->RP-202409; 7/4/21: WID:RP-202409->RP-210914; 2/7/21: WID:RP-210914->RP-211538; 2/7/21: 38.851 added;; 29/9/21: WID:RP-211538->RP-212092; 6/1/22: WID:RP-212092->RP-213666; 5/4/22: WID:RP-21366 ; ","38.851",89,45,null,null,"Sun 11/10/20","Tue 12/07/22"]
[1798,890159,"   Core part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Core",2,"Rel-17","R4","Tue 15/09/20","Wed 22/06/22",1,"RP-220968","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->55%; ; 22/3/22: Compl:55%->75%; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com; ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1799,890259,"   Perf. part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-221784","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->25%; ; 22/3/22: CD:22/06/2022->10/06/2022 ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com 9/9/22: Compl:80%...",null,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1800,970070,"   UE Conformance - Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2-UEConTest",2,"Rel-17","R5","Thu 08/09/22","Fri 01/03/24",1,"RP-240751","RP-240092","Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple","tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->6%; Stat Rep: ->RP-222732; Rapporteur: Nokia->Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple; Rap eMail: ->tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com; 17/3/23: FCD:30/11/2023->12/12/2023; Com.....",null,97,49,null,null,"Fri 23/09/22","Tue 02/04/24"]
[1801,890060,"NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2",1,"Rel-17",null,"Tue 15/09/20","Thu 12/12/24",0.82,"RP-210800",null,"Samsung ",null,"follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 6/1/21: WID:RP-202118->RP-202538; 7/4/21: WID:RP-202538->RP-210800",null,89,45,null,null,"Sun 11/10/20","Wed 07/04/21"]
[1802,890160,"   Core part: NR support for high speed train scenario in FR2","NR_HST_FR2-Core",2,"Rel-17","R4","Tue 15/09/20","Tue 22/03/22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 13/9/21: Compl:0%->50%; ; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com; ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1803,890260,"   Perf. Part: NR support for high speed train scenario in FR2","NR_HST_FR2-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->20% ; 22/3/22: Compl:20%->50%; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com ; 9/9/22: Compl:80%->100%",null,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1804,960080,"   UE Conformance - NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Fri 12/12/25",0.7,"RP-221402","RP-251016","Runsen Tang, Samsung","runsen.tang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->R5-226806; Rapporteur: Samsung->Runsen Tang, Samsung; Rap eMail: ->runsen.tang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:7%->18%; Stat Rep: R5-226806->RP-2301.....",null,96,49,null,null,"Tue 12/07/22","Fri 06/06/25"]
[1805,890061,"NR measurement gap enhancements ","NR_MG_enh",1,"Rel-17",null,"Tue 15/09/20","Thu 06/06/24",1,"RP-213658",null,"MediaTek ",null,"measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 6/1/21: WID:RP-202119->RP-202658; 7/4/21: WID:RP-202658->RP-210679; 2/7/21: WID:RP-210679->RP-211591; 6/1/22: WID:RP-211591->RP-213658",null,89,45,null,null,"Sun 11/10/20","Thu 06/01/22"]
[1806,890161,"   Core part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Core",2,"Rel-17","R4","Tue 15/09/20","Tue 22/03/22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:08/09/2021->22/03/2023; Compl:0%->100%; WID: RP-213658->RP-220772; Stat Rep: ->RP-221549; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation;",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1807,890261,"   Perf. part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->40%; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui....",null,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1808,981035,"   UE Conformance - NR and MR-DC measurement gap enhancements ","NR_MG_enh-UEConTest",2,"Rel-17","R5","Wed 14/12/22","Thu 06/06/24",1,"RP-223246","RP-241346","Daiwei Zhou, MediaTek Inc.","daiwei.zhou@mediatek.com","17/3/23: FCD:03/03/2024->01/03/2024; Compl:0%->31%; Stat Rep: ->RP-230638; Rapporteur: MediaTek->Daiwei Zhou, MediaTek Inc.; Rap eMail: ->daiwei.zhou@mediatek.com; ;...; 6/9/23: Compl:55%->63%; Stat Rep: RP-230638->RP-232306; ; 8/12/23: FCD:03/03/2024...",null,98,50,null,null,"Mon 09/01/23","Thu 13/06/24"]
[1809,890062,"RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh",1,"Rel-17",null,"Tue 15/09/20","Fri 01/03/24",1,"RP-220681",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 ; 6/1/21: WID:RP-202088->RP-202799; 7/4/21: WID:RP-202799->RP-210899; 29/9/21: WID:RP-210899->RP-212527; 5/4/22: WID:RP-212527->RP-220681",null,89,45,null,null,"Sun 11/10/20","Tue 05/04/22"]
[1810,890162,"   Core part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Core",2,"Rel-17","R4","Tue 15/09/20","Tue 22/03/22",1,"RP-220681","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->90%; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com; ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1811,890262,"   Perf. part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-221502","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: CD:Sat 11/12/21->Wed 22/09/21; ; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-212170->RP-220680 ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com12/7/22...",null,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1812,960090,"   UE Conformance - RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Fri 01/03/24",1,"RP-221848","RP-240280","Chunying GU, Huawei","guchunying@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-223222; Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:11%->20%; Stat Rep: RP-223222->RP-230702;.....",null,96,49,null,null,"Tue 12/07/22","Thu 14/03/24"]
[1813,941013,"4Rx support for NR band n8","NR_4Rx_Bn8_FWA",1,"Rel-17","R4","Mon 13/12/21","Thu 22/09/22",1,"RP-220395",null,"CHTTL",null,"5/4/22: WID:RP-213659->RP-220395",null,94,48,null,null,"Thu 06/01/22","Tue 05/04/22"]
[1814,941113,"   Core part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Core",2,"Rel-17","R4","Mon 13/12/21","Fri 11/03/22",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"Thu 06/01/22","Tue 22/03/22"]
[1815,941213,"   Perf. part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Perf",2,"Rel-17","R4","Mon 13/12/21","Fri 11/03/22",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"Thu 06/01/22","Tue 22/03/22"]
[1816,960071,"   UE Conformance - 4Rx support for NR band n8 ","NR_4Rx_Bn8_FWA-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Thu 22/09/22",1,"RP-222137",null,"ChinaUnicom ",null,"9/9/22: Comp...; 23/9/22: WID:RP-221159->RP-222137",null,96,49,null,null,"Tue 12/07/22","Fri 23/09/22"]
[1817,0,"Rel-17 Self-Organizing (SON)/Autonomous Networks","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1818,860053,"Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh",1,"Rel-17",null,"Mon 16/12/19","Tue 22/03/22",1,"RP-220821",null,"CMCC",null,"affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 6/1/22: WID:RP-193255->RP-213574; 5/4/22: WID:RP-213574->RP-220821",null,86,44,null,null,"Tue 14/01/20","Tue 05/04/22"]
[1819,860153,"   Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity)","NR_ENDC_SON_MDT_enh-Core",2,"Rel-17","R3","Mon 16/12/19","Tue 22/03/22",1,"RP-213574","RP-220820","Liang LIU, AngeloCentonza","liuliang@chinamobile.com, angelo.centonza@ericsson.com","affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 28/7/20: WID:RP-193255->RP-201281; ; 6/1/22: WID:RP-193255->RP-213574; 20/6/22: Compl:65%",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1820,910029,"Plug and connect support for management of Network Functions ","PACMAN",1,"Rel-17","S5","Thu 18/03/21","Fri 11/03/22",1,"SP-210260",null,"Per Elmdahl, Ericsson ","Per.elmdahl@ericsson.com ","; 11/6/21: 0%->10; 13/9/21: 10%->20; 13/12/21: 20%->70; 13/12/21: FCD:Fri 10/06/->03/22; 12/3/22: 70%->100","28.313 ",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1821,870028,"Enhancements of Self-Organizing Networks (SON) for 5G networks ","eSON_5G",1,"Rel-17","S5","Wed 25/03/20","Fri 11/03/22",1,"SP-200194",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","; 13/9/20: 0%->2; 5/12/20: 2%->5; 21/3/21: 5%->15; 11/6/21: 15%->35; 11/6/21: FCD:Thu 17/06/->12/21; 13/9/21: 35%->70; 13/12/21: 70%->90; 13/12/21: FCD:Fri 10/12/->03/22; 21/6/22: 90%->100","28.313; 28.552; 28.541; 28.545 ",87,44,null,null,"Fri 06/12/19","Tue 21/06/22"]
[1822,850032,"Study on autonomous network levels ","FS_ANL",1,"Rel-17","S5","Thu 19/09/19","Mon 14/09/20",1,"SP-190928",null,"China Mobile ","caoxi@chinamobile.com ","; 8/10/19: 28.810 added;; 26/3/20: 0%->50; 26/3/20: FCD:12/03/2020->06/20; 28/6/20: 50%->85; 13/9/20: 85%->100; 13/9/20: FCD:12/06/2020->09/20. 9/4/21: Rel-16->Rel-17","New ; 28.810",85,43,null,null,"Fri 13/09/19","Sun 13/09/20"]
[1823,880027,"Autonomous network levels ","ANL",1,"Rel-17","S5","Fri 12/06/20","Fri 10/12/21",1,"SP-200464",null,"Cao, Xi, China Mobile ","caoxi@chinamobile.com ","28.533; 28.313; 28.535; 28.809; 28.312; 28.541 ; 13/9/20: 0%->5; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 5%->30; 21/3/21: 30%->50; 11/6/21: 50%->70; 13/9/21: 70%->71; 13/9/21: FCD:Fri 11/06/->12/21; 13/12/21: 71%->100",null,88,45,null,null,"Fri 26/06/20","Mon 13/12/21"]
[1824,0,"Rel-17 Multicast-broadcast Services (MBS) and Mission Critical (MC)","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1825,870014,"Study on Multicast Architecture Enhancements for 5G Media Streaming","FS_5GMS_Multicast",1,"Rel-17","S4","Wed 25/03/20","Fri 11/06/21",1,"SP-200238",null,"Peng Tan, Telus","peng.tan@telus.com","10/6/20: 0%->5; 5/12/20: 5%->25; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 25%->60; 11/6/21: 60%->100","new",87,44,null,null,"Fri 31/05/19","Fri 11/06/21"]
[1826,810055,"Study on location enhancements for mission critical services ","FS_enhMCLoc",1,"Rel-17","S6","Fri 14/09/18","Thu 12/03/20",1,"SP-190725",null,"Dom Lazara, Motorola Solutions","dom.lazara@motorolasolutions.com","7/12/18: 0%->20¦14/3/19: 20%->45¦14/3/19: FCD:03/19->09/19; 31/5/19: 45%->60; 13/9/19: 60%->70; 13/9/19: FCD:12/09/2019->03/20; 20/9/19: WID:SP-180921->SP-190725; 6/12/19: 70%->75; 28/6/20: 75%->90. Moved from Rel-16; 5/12/20: 90%->100","23.744",81,41,null,null,"Fri 14/09/18","Sat 05/12/20"]
[1827,880006,"Study on Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","FS_5MBS_SEC",1,"Rel-17","S3","Fri 12/06/20","Fri 10/12/21",1,"SP-200351",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","28/7/20: 33.850 added;; 12/9/20: 0%->15; 5/12/20: 15%->30; 19/3/21: 30%->60; 19/3/21: FCD:25/03/2021->06/21; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100","33.850",88,45,null,null,"Thu 25/06/20","Sat 12/03/22"]
[1828,850035,"Study on Mission Critical services over 5G multicast-broadcast system ","FS_MC5MBS",1,"Rel-17","S6","Thu 19/09/19","Thu 12/03/20",1,"SP-190929",null,"Val Oprescu, AT&T ",null,"; 13/9/19: 0%->20; 8/10/19: 23.774 added;; 8/10/19: 33.524 added;; 6/12/19: 20%->55; 26/3/20: 55%->100","New ; 23.774; 33.524",85,43,null,null,"Fri 13/09/19","Thu 26/03/20"]
[1829,900038,"Multicast-broadcast services in 5G","5MBS",1,"Rel-17",null,"Thu 07/03/19","Sun 03/03/24",1,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"Thu 03/12/20","NA"]
[1830,830030,"   Study on Architectural enhancements for 5MBS","FS_5MBS",2,"Rel-17","S2","Thu 07/03/19","Fri 12/03/21",1,"SP-200690",null,"Meng Li, Huawei","raymond.limeng@huawei.com","7/6/19: WID:SP-190253->SP-190442; 20/9/19: WID:SP-190442->SP-190625; 6/12/19: 0%->15; 25/3/20: WID:SP-190625->SP-200092; 25/3/20: 15%->35; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 35%->50; 12/9/20: 50%->65; 12/9/20: FCD:15/09/2020->12/20; 13/9/20: WID: ","23.757",83,42,null,null,"Thu 14/03/19","Fri 19/03/21"]
[1831,900009,"   Stage 2 for 5MBS","5MBS",2,"Rel-17","S2","Thu 03/12/20","Fri 10/09/21",1,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->20; 14/6/21: 20%->75; 13/9/21: 75%->85; 10/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100",null,90,46,null,null,"Thu 03/12/20","Sat 04/06/22"]
[1832,920043,"   CT1 aspects of 5MBS","5MBS",2,"Rel-17","C1","Fri 11/06/21","Fri 11/03/22",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->80; 12/3/22: 80%->95; 22/3/22: 24.575 added;; 22/3/22: WID:CP-212022->CP-220402; 4/6/22: 95%->97","24.501 ; 24.575",92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1833,920044,"   CT3 aspects of 5MBS","5MBS",2,"Rel-17","C3","Fri 11/06/21","Fri 11/03/22",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/12/21: 0%->40; 13/12/21: WID:CP-212022->CP-213078; 12/3/22: WID:CP-213078->CP-220099; 12/3/22: 40%->65; 22/3/22: 29.580 added;; 4/6/22: 65%->85; 4/6/22: WID:CP-220402->CP-221084; 20/6/22: WID: eSEALCP-221084->CP-220402","29.561;29.525;29.522;29.521;29.520;29.519;29.514;29.513;29.512;29.508 ; 29.580",92,47,null,null,"Fri 11/06/21","Mon 20/06/22"]
[1834,910002,"   CT4 aspect of 5MBS","5MBS",2,"Rel-17","C4","Fri 11/06/21","Fri 11/03/22",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","UID in 91xx range but presented to CT#92; 2/7/21: 29.532 added;; 10/9/21: WID:CP-211093->CP-212022; 13/9/21: 0%->15; 13/12/21: 15%->75; 7/1/22: 29.537 added;; 12/3/22: 75%->80; 22/3/22: 29.581 added;; 20/6/22: Compl:80%->99%","29.571;29.518;29.510;29.503;29.502;29.281;29.244;23.003 ; 29.532; 29.537; 29.581",91,46,null,null,"Fri 11/06/21","Mon 20/06/22"]
[1835,960067,"   CT6 aspects of 5MBS","5MBS",2,"Rel-17","C6","Fri 11/06/21","Fri 11/03/22",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ",null,null,96,49,null,null,"Mon 20/06/22","NA"]
[1836,920023,"   Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","5MBS",2,"Rel-17","S3","Fri 11/06/21","Fri 10/06/22",1,"SP-210420",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","; 12/3/22: 0%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100","33.501 ",92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1837,1000010,"   Charging Aspects for SMF and MB-SMF to Support 5G Multicast-broadcast Services ","5MBS_CH",2,"Rel-18","S5","Thu 08/06/23","Sun 03/03/24",1,"SP-231712",null,"Dong, Jia, China Mobile, ","dongjia at chinamobile dot com ","; 7/9/23: 0%->20; 7/9/23: 20%->30; 8/12/23: 30%->65; 3/1/24: WID:SP-230623->SP-231712; 14/3/24: 65%->100","32.240; 32.255; 32.298; 32.291; 33.279; 33.290",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[1838,850040,"Broadcast / Multicast requirements supporting Mission Critical Services in 5G ","5MBS_eMC",1,"Rel-17","S1","Mon 02/09/19","Thu 12/12/19",1,"SP-190942",null,"Toobe, Jens, BDBOS ","jens.toobe at bdbos.bmi.bund.de ","; 13/9/19: 0%->80; 20/9/19: FCD:19/09/2019->12/19; 6/12/19: 80%->100","22.261 ",85,43,null,null,"Fri 13/09/19","Fri 06/12/19"]
[1839,940008,"5G Multicast-Broadcast Protocols ","5MBP3",1,"Rel-17","S4","Fri 10/12/21","Fri 10/06/22",1,"SP-211335",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@QTI.QUALCOMM.COM ","; 12/3/22: 0%->40; 12/3/22: FCD:15/03/2022->6/22; 4/6/22: 40%->100","26.346; 26.347; 26.512 ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1840,860048,"NR multicast and broadcast services","NR_MBS",1,"Rel-17","R2","Mon 16/12/19","Tue 12/12/23",1,"RP-220428",null,"Huawei",null,"affects: NR. no Perf. part; 5/4/22: WID:RP-193248->RP-220428",null,86,44,null,null,"Tue 14/01/20","Tue 05/04/22"]
[1841,860148,"   Core part: NR multicast and broadcast services","NR_MBS-Core",2,"Rel-17","R2","Mon 16/12/19","Fri 11/03/22",1,"RP-220428","RP-220407","Huawei",null,"affects: NR. no Perf. part; 28/7/20: WID:RP-193248->RP-201038 ; ",null,86,44,null,null,"Tue 14/01/20","Tue 22/03/22"]
[1842,950061,"   UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects ","NR_MBS_5MBS_5MBUSA-UEConTest",2,"Rel-17","R5","Tue 15/03/22","Tue 12/12/23",1,"RP-220423","RP-233760","Ya Zhao, Huawei Technologies. Co., Ltd","zhaoya@hisilicon.com","tested: REL-17 WI NR_MBS-Core, SA/CT REL-17 WI 5MBS, SA4 REL-17 WI 5MBUSA ; 6/6/22: Compl:0%->5% ; 20/6/22: Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl...",null,95,48,null,null,"Tue 05/04/22","Fri 08/12/23"]
[1843,920051,"Mission Critical Services over 5GS ","MCOver5GS",1,"Rel-17",null,"Wed 16/09/20","Fri 11/03/22",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65","23.289",89,45,null,null,"Fri 11/09/20","Sun 21/03/21"]
[1844,890027,"   Stage 2 of MCOver5GS","MCOver5GS",2,"Rel-17","S6","Wed 16/09/20","Tue 15/06/21",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65; 11/6/21: 65%->100","23.289",89,45,null,null,"Fri 11/09/20","Fri 11/06/21"]
[1845,920007,"   CT1 aspects of MCOver5GS","MCOver5GS",2,"Rel-17","C1","Fri 11/06/21","Fri 11/03/22",1,"CP-211118",null,"Gkatzikis, Lazaros, Nokia ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 13/12/21: 0%->25; 12/3/22: 25%->40; 4/6/22: 40%->100","24.582;24.581;24.484;24.483;24.481;24.380;24.379;24.282;24.281 ",92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1846,890039,"Mission Critical Data ","eMCData3",1,"Rel-17",null,"Fri 06/12/19","Fri 11/03/22",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70","23.280; 23.282 ",86,44,null,null,"Fri 06/12/19","Sun 13/09/20"]
[1847,860007,"   Stage 2 of MCData3","eMCData3",2,"Rel-17","S6","Fri 06/12/19","Tue 15/06/21",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70; 5/12/20: 70%->85; 10/2/21: FCD:11/09/2020->06/21; 21/3/21: 85%->90; 11/6/21: 90%->100","23.280; 23.282 ",86,44,null,null,"Fri 06/12/19","Fri 11/06/21"]
[1848,890038,"   CT aspects of eMCData3","eMCData3",2,"Rel-17","C1","Wed 17/06/20","Fri 11/03/22",1,"CP-201177",null,null,null,"5/12/20: 0%->10; 21/3/21: 10%->40; 11/6/21: 40%->45; 13/9/21: 45%->50; 13/12/21: 50%->65; 12/3/22: FCD:15/09/2021->3/22; 12/3/22: 65%->97; 4/6/22: 97%->100",null,89,45,null,null,"Fri 25/09/20","Sat 04/06/22"]
[1849,820040,"Mission Critical system migration and interconnection ","MCSMI_CT",1,"Rel-17","C1","Thu 13/12/18","Fri 11/03/22",1,"CP-190143",null,"Dom Lazara, Motorola Solutions ","dom.lazara@motorolasolutions.com ","¦18/3/19: FCD:019->12/19¦18/3/19: WID:CP-183244->CP-190143; 13/9/19: 0%->5. 1/7/20: Rel-16->Rel-17 (comments during CT#88e presentation); 13/9/21: 5%->10; 13/12/21: 10%->30; 12/3/22: 30%->90; 12/3/22: FCD:12/12/2019->3/22; 4/6/22: 90%->100","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482 ",82,42,null,null,"Fri 07/12/18","Sat 04/06/22"]
[1850,890003,"CT aspects of Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems ","eMCCI_CT",1,"Rel-17","C1","Wed 16/09/20","Wed 08/09/21",1,null,null,"Mike Dolan, FirstNet ","michael.dolan@firstnet.gov ","5/12/20: 0%->60; 13/9/21: 60%->65","29.379; 29.380; 29.582 ",89,45,null,null,"Fri 25/09/20","Mon 13/09/21"]
[1851,0,"Rel-17 Edge computing","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1852,880042,"Architecture for enabling Edge Applications ","EDGEAPP",1,"Rel-17",null,"Thu 07/03/19","Tue 07/06/22",1,"SP-200109",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20","23.222; 23.558",86,44,null,null,"Fri 06/12/19","Thu 26/03/20"]
[1853,830008,"   Study on Application Architecture for enabling Edge Applications","FS_EDGEAPP",2,"Rel-17","S6","Thu 07/03/19","Thu 05/12/19",1,"SP-190065",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","31/5/19: 0%->35; 13/9/19: 35%->70; 6/12/19: 70%->95; 26/3/20: 95%->100","New",83,42,null,null,"Thu 14/03/19","Thu 26/03/20"]
[1854,860006,"   Architecture for enabling Edge Applications ","EDGEAPP",2,"Rel-17","S6","Fri 06/12/19","Tue 15/06/21",1,"SP-200886",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20; 28/6/20: 20%->50; 13/9/20: 50%->70; 13/9/20: WID:SP-200109->SP-200834; 13/9/20: FCD:11/09/2020->12/20; 25/9/20: WID:SP-200834->SP-200886; 5/12/20: 70%->85; 10/2/21: FCD:11/12/2020->06/21; 21/3/21: 85% ","23.222; 23.558",86,44,null,null,"Fri 06/12/19","Fri 11/06/21"]
[1855,900006,"   CT aspects for Enabling Edge Applications ","EDGEAPP",2,"Rel-17",null,"Mon 07/12/20","Tue 07/06/22",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 11/6/21: WID:CP-203106->CP-211196",null,90,46,null,null,"Sat 05/12/20","Fri 11/06/21"]
[1856,900034,"      CT1 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C1","Mon 07/12/20","Fri 11/03/22",1,"CP-221106",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->5; 11/6/21: 5%->30; 13/9/21: 30%->55; 13/12/21: 55%->68; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 68%->85; 4/6/22: 85%->99; 4/6/22: WID:CP-211196->CP-221106",null,90,46,null,null,"Sat 05/12/20","Sat 04/06/22"]
[1857,900035,"      CT3 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C3","Mon 07/12/20","Fri 11/03/22",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->20; 11/6/21: FCD:Fri 10/09/->12/21; 11/6/21: 20%->50; 13/9/21: 50%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 75%->90",null,90,46,null,null,"Sat 05/12/20","Sat 12/03/22"]
[1858,960066,"      CT4 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C4","Mon 07/12/20","Tue 07/06/22",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","CT4 chair input (07/06/2022); 3/8/22: 0%->100",null,90,46,null,null,"Mon 20/06/22","Wed 03/08/22"]
[1859,830032,"Study on enhancement of support for Edge Computing in 5GC","FS_enh_EC",1,"Rel-17","S2","Thu 07/03/19","Tue 15/12/20",1,"SP-200093",null,"Hui Ni, Huawei","Hui.ni@huawei.com","6/12/19: 0%->20; 25/3/20: WID:SP-190185->SP-200093; 25/3/20: FCD:05/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->60; 12/9/20: 60%->70; 12/9/20: FCD:11/09/2020->12/20; 5/12/20: 70%->100","New",83,42,null,null,"Thu 14/03/19","Sat 05/12/20"]
[1860,910048,"Enhancement of support for Edge Computing in 5G Core network ","eEDGE_5GC",1,"Rel-17",null,"Thu 03/12/20","Fri 11/03/22",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"Thu 03/12/20","NA"]
[1861,900016,"   Stage 2 of eEDGE_5GC","eEDGE_5GC",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->35; 11/6/21: 35%->75; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 75%->95; 10/12/21: 95%->100",null,90,46,null,null,"Thu 03/12/20","Fri 10/12/21"]
[1862,910005,"   CT aspects of 5G eEDGE ","eEDGE_5GC",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","10/9/21: WID:CP-211092->CP-212021",null,91,46,null,null,"Thu 18/03/21","Fri 10/09/21"]
[1863,910049,"      CT1 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->95; 4/6/22: 95%->100","24.008; 24.501; 24.526; 27.007",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1864,910050,"      CT3 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 11/6/21: WID:CP-210284->CP-211092; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->100","29.508; 29.512; 29.514; 29.513; 29.522; 29.519; 29.561",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1865,910051,"      CT4 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->25; 13/9/21: 25%->45; 1/10/21: 29.564 added;; 13/12/21: 45%->80; 12/3/22: 80%->98; 4/6/22: 98%->100","29.244; 29.510; 29.502; 29.503; 29.505; 29.571; 29.564",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1866,920026,"   Security Aspects of Enhancements of Support for Edge Computing in 5GC ","eEDGE_5GC",2,"Rel-17","S3","Fri 11/06/21","Fri 10/12/21",1,"SP-210423",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 13/9/21: 0%->30; 1/10/21: 33.558 added;; 13/12/21: 30%->50; 12/3/22: 50%->100","33.501 ; 33.558",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1867,920019,"Edge Computing Management ","ECM",1,"Rel-17","S5","Fri 11/06/21","Fri 11/03/22",1,"SP-210388",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 13/9/21: 0%->10; 13/12/21: 10%->50; 12/3/22: 50%->90; 4/6/22: 90%->100","28.532;28.531;28.554;28.552;28.541 ",92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1868,880002,"Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC ","FS_eEDGE_Sec",1,"Rel-17","S3","Fri 12/06/20","Fri 10/12/21",1,"SP-200347",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:25/03/2021->06/21; 19/3/21: 50%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100","33.839",88,45,null,null,"Thu 25/06/20","Sat 12/03/22"]
[1869,940009,"Edge Extensions to 5GMS Stage 3 ","5GMS_EDGE_3",1,"Rel-17","S4","Fri 10/12/21","Fri 10/06/22",1,"SP-211336",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 12/3/22: 0%->60; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 60%->100","26.512; ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1870,930034,"Charging aspects of Edge Computing ","EDGE_CH",1,"Rel-17","S5","Thu 25/06/20","Fri 11/03/22",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 22/3/22: 32.257 added;","32.240; 32.291; 32.298; 32.297 ; 32.257",93,47,null,null,"Fri 10/09/21","Tue 22/03/22"]
[1871,880030,"   Study on charging aspects of Edge Computing ","FS_EDGE_CH",2,"Rel-17","S5","Thu 25/06/20","Fri 10/12/21",1,"SP-200467",null,"Yizhi Yao, Intel ","yizhi<dot>yao<at>intel<dot>com ","5/12/20: 0%->30; 21/3/21: 30%->60; 21/3/21: FCD:19/03/2021->09/21; 13/9/21: 60%->90; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 90%->100","28.815",88,45,null,null,"Fri 26/06/20","Tue 21/06/22"]
[1872,930011,"   Charging aspects of Edge Computing ","EDGE_CH",2,"Rel-17","S5","Fri 10/09/21","Fri 11/03/22",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 12/3/22: 0%->70; 4/6/22: 70%->100","32.240; 32.291; 32.298; 32.297 ",93,47,null,null,"Fri 10/09/21","Sat 04/06/22"]
[1873,870029,"Study on enhancements of edge computing management ","FS_eEDGE_Mgt",1,"Rel-17","S5","Wed 25/03/20","Wed 08/09/21",1,"SP-200195",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","13/9/20: 0%->15; 5/12/20: 15%->25; 5/12/20: FCD:17/12/2020->03/20; 21/3/21: 25%->75; 11/6/21: 75%->90; 11/6/21: FCD:Fri 12/03/->09/21; 13/9/21: 90%->100","New",87,44,null,null,"Fri 06/12/19","Mon 13/09/21"]
[1874,0,"Rel-17 Slicing","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1875,920058,"Rel-17 Enhancements of 3GPP Northbound Interfaces and Application Layer APIs ","NBI17",1,"Rel-17",null,"Fri 11/06/21","Fri 11/03/22",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","01/22: Rapp changed from yanyali@huawei.com ; 28/4/22: WID:CP-211197->CP-220058",null,92,47,null,null,"Fri 11/06/21","Thu 28/04/22"]
[1876,920013,"   CT1 aspects of NBI17 ","NBI17",2,"Rel-17","C1","Fri 11/06/21","Fri 11/03/22",1,"CP-211197",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 13/9/21: 0%->85; 13/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100; 20/6/22: WID: CP-220058->CP-211197","24.558 ",92,47,null,null,"Fri 11/06/21","Mon 20/06/22"]
[1877,920053,"   CT3 aspects of NBI17 ","NBI17",2,"Rel-17","C3","Fri 11/06/21","Fri 11/03/22",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 13/12/21: WID:CP-211197->CP-213262; 12/3/22: 85%->100; 12/3/22: FCD:10/03/2023->3/22","29.558;29.549;29.522;29.486;29.343;29.222;29.122;29.116 ",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1878,920054,"   CT4 aspects of NBI17 ","NBI17",2,"Rel-17","C4","Fri 11/06/21","Fri 11/03/22",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 12/3/22: 0%->100","29.518;29.503;29.272;29.336;29.571 ",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1879,920012,"Enhancement of 5G PCC related services in Rel-17 ","en5GPccSer17",1,"Rel-17","C3","Fri 11/06/21","Fri 11/03/22",1,"CP-211193",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","; 11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->70; 12/3/22: 70%->100","29.214;29.519;29.594;29.521;29.514;29.513;29.512 ",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1880,900032,"Enhancement of Network Slicing Phase 2 ","eNS_Ph2",1,"Rel-17",null,"Thu 19/09/19","Tue 06/06/23",1,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ",null,90,46,null,null,"Thu 03/12/20","NA"]
[1881,850010,"   Study on Enhancement of Network Slicing Phase 2 ","FS_eNS_Ph2",2,"Rel-17","S2","Thu 19/09/19","Fri 12/03/21",1,"SP-190931",null,"So, Tricci, ZTE ","tso@ztetx.com ","; 8/10/19: 23.700-40 added;; 6/12/19: 0%->15; 25/3/20: 15%->35; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 90%->100","New ; 23.700-40",85,43,null,null,"Fri 13/09/19","Fri 19/03/21"]
[1882,900011,"   Stage 2 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ; 19/3/21: 0%->5; 14/6/21: 5%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->97; 10/12/21: 97%->99; 22/3/22: 99%->100",null,90,46,null,null,"Thu 03/12/20","Tue 22/03/22"]
[1883,920059,"   Stage 3 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","ct","Thu 18/03/21","Tue 06/06/23",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","1/10/21: WID:CP-210288->CP-211091",null,91,46,null,null,"Thu 18/03/21","Fri 01/10/21"]
[1884,910041,"      CT1 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 13/12/21: 45%->80; 12/3/22: 80%->100","24.501",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1885,910042,"      CT3 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->96; 4/6/22: 96%->100","29.522",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1886,910043,"      CT4 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 1/10/21: WID:CP-210288->CP-211091; 13/12/21: 45%->80; 12/3/22: 80%->100","29.510; 29.518; 29.502; 29.524",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1887,950065,"      UE Conformance - Enhancement of Network Slicing Phase 2 ","eNS_Ph2-UEConTest",3,"Rel-17","R5","Tue 15/03/22","Tue 06/06/23",1,"RP-230289","RP-230286","Danni Song, Xiaozhong Chen, CMCC, CATT","songdan@chinamobile.com, chenxiaozhong@catt.cn","tested: SA/CT REL-17 WI eNS_Ph2 (note: This WI is not testing NR_slice-Core) 6/6/22: Compl:0%->10% ; ; 20/6/22: Rapporteur: CMCC->Luting Kong, Xiaozhong Chen, CMCC, CATT; Rap eMail: ->kongluting@chinamobile.com, chenxiaozhong@catt.cn ; ;...; 9/12/22:...",null,95,48,null,null,"Tue 05/04/22","Wed 07/06/23"]
[1888,911007,"Enhancement of RAN slicing for NR ","NR_slice",1,"Rel-17","R2","Thu 07/03/19","Fri 22/09/23",1,"RP-221377",null,"CMCC ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 2/7/21: WID:RP-210912->RP-211290; 29/9/21: WID:RP-211290->RP-212534; 12/7/22: WID:RP-212534->RP-221377",null,91,46,null,null,"Wed 07/04/21","Tue 12/07/22"]
[1889,911107,"   Core part: Enhancement of RAN slicing for NR ","NR_slice-Core",2,"Rel-17","R2","Fri 12/03/21","Wed 22/06/22",1,"RP-221377","RP-221375","Ningyu Chen, CMCC","chenningyu@chinamobile.com","follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 20/6/22: FCD:12/03/2022->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221375; Rapporteur: CMCC->Ningyu Chen, CMCC; Rap eMail: ->chenningyu@chinamobile.com; ",null,91,46,null,null,"Wed 07/04/21","Mon 20/06/22"]
[1890,960078,"   UE Conformance - Enhancement of RAN slicing for NR ","NR_slice-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Fri 22/09/23",1,"RP-223067","RP-232242","Danni Song, CMCC","songdan@chinamobile.com","9/9/22: Comp...; 23/9/22: WID:RP-221364->RP-222118; 9/12/22: FCD:22/09/2022->01/09/2023; Compl:12%->13%; Stat Rep: ->RP-223068; Rapporteur: CMCC->Danni Song, CMCC; Rap eMail: ->songdan@chinamobile.com; 9/1/23: WID:RP-222118->RP-223067; 17...; ",null,96,49,null,null,"Tue 12/07/22","Wed 06/09/23"]
[1891,960006,"   CT1 aspects of enhancement of RAN Slicing for NR ","NRslice",2,"Rel-17","C1","Fri 03/06/22","Mon 20/06/22",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100","24.501; 29.531; 29.571 ",96,49,null,null,"Fri 03/06/22","Sat 04/06/22"]
[1892,960069,"   CT4 aspects on enhancement of RAN slicing for NR","NRslice",2,"Rel-17","C4","Thu 07/03/19","Thu 07/03/19",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100; 3/8/22: 99%->100","24.501; 29.531; 29.571 ",96,49,null,null,"Mon 20/06/22","Wed 03/08/22"]
[1893,860022,"Study on network slice management enhancement ","FS_NSMEN",1,"Rel-17","S5","Fri 06/12/19","Fri 10/12/21",1,"SP-200766",null,"Brendan Hassett, Huawei Technologies Sweden AB, ","brendan.t.hassett@huawei.com","13/9/20: 0%->5; 13/9/20: WID:SP-191192->SP-200766; 5/12/20: 5%->20; 21/3/21: 20%->40; 11/6/21: 40%->80; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->90; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: 90%->100",null,86,44,null,null,"Fri 06/12/19","Mon 13/12/21"]
[1894,950038,"Network Slice charging based on 5G Data Connectivity ","NETSLICE_DC_CH",1,"Rel-17","S5","Thu 10/03/22","Fri 11/03/22",1,"SP-220158",null,"MATRIXX Software, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","; 12/3/22: 0%->100","32.255 ",95,48,null,null,"Thu 10/03/22","Sat 12/03/22"]
[1895,0,"Rel-17 Multi-(U)SIM","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1896,840049,"Support for Multi-USIM Devices ","MUSIM",1,"Rel-17",null,"Thu 07/03/19","Fri 11/03/22",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ",null,"22.261; 22.278; 22.101 ",84,43,null,null,"Fri 31/05/19","NA"]
[1897,830019,"   Study on MUSIM","FS_MUSIM",2,"Rel-17","S1","Thu 07/03/19","Fri 06/09/19",1,"SP-190091","-","Liao, Ellen C, Intel","ellen.c.liao@intel.com","14/3/19: 0%->5; 31/5/19: 5%->95; 13/9/19: 95%->98; 6/12/19: 98%->100","New",83,42,null,null,"Thu 14/03/19","Fri 06/12/19"]
[1898,840040,"   Stage 1 of MUSIM","MUSIM",2,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ","13/9/19: 0%->50; 6/12/19: 50%->100","22.261; 22.278; 22.101 ",84,43,null,null,"Fri 31/05/19","Fri 06/12/19"]
[1899,820012,"   Study on Stage 2 (System Enablers) for MUSIM","FS_MUSIM",2,"Rel-17","S2","Thu 07/03/19","Fri 12/03/21",1,"SP-200297",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com)","21/3/19: WID:SP-181251->SP-190248; 6/12/19: 0%->29; 25/3/20: WID:SP-190248->SP-200297; 25/3/20: 29%->45; 26/6/20: FCD:11/06/2020->09/20; 26/6/20: 45%->60; 12/9/20: 60%->80; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 80%->90; 5/12/20: FCD:15/12/2020->03/2 ","23.761",82,42,null,null,"Thu 06/12/18","Mon 13/09/21"]
[1900,900013,"   System enablers for Multi-USIM devices ","MUSIM",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-210091",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com ","23.501; 23.502; 23.401; 23.228 ; 19/3/21: 0%->20; 13/6/21: WID:SP-200978->SP-210091; 14/6/21: 20%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->98; 10/12/21: 98%->100",null,90,46,null,null,"Thu 03/12/20","Fri 10/12/21"]
[1901,910015,"   CT aspects of MUSIM","MUSIM",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 10/9/21: WID:CP-210280->CP-212102; 01/22: rapporteur changed from Vivek Gupta","24.501; 24.301; 27.007; 29.274 ",91,46,null,null,"Thu 18/03/21","Fri 10/09/21"]
[1902,910063,"      CT1 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->90; 12/3/22: 90%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1903,910064,"      CT4 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/12/21: 40%->90; 12/3/22: 90%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1904,900017,"   Study on the security of the system enablers for devices having multiple Universal Subscriber Identity Modules (USIM) ","FS_MUSIM_SEC",2,"Rel-17","S3","Fri 04/12/20","Fri 10/12/21",1,"SP-201018",null,"Abhijeet Kolekar, Intel Corporation ","abhijeet.kolekar@intel.com ","5/12/20: 0%->10; 10/2/21: 33.873 added;; 19/3/21: 10%->35; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 35%->96; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 96%->100","33.873",90,46,null,null,"Fri 04/12/20","Mon 13/09/21"]
[1905,860063,"Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM",1,"Rel-17",null,"Mon 09/12/19","Fri 22/09/23",1,"RP-213679",null,"Vivo",null,"28/7/20: WID:RP-193263->RP-201309. 6/1/21: WID:RP-193263->RP-202895; 7/4/21: WID:RP-202895->RP-210316; 2/7/21: WID:RP-210316->RP-211561; 29/9/21: WID:RP-211561->RP-212610; 6/1/22: WID:RP-212610->RP-213679",null,86,44,null,null,"Wed 10/06/20","Thu 06/01/22"]
[1906,860163,"   Core part: Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM-Core",2,"Rel-17","R2","Mon 09/12/19","Tue 22/03/22",1,"RP-213679","RP-220603","Xiaodong Yang","Yangxiaodong5g@vivo.com","20/6/22: FCD:17/06/2021->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220603; Rapporteur: Vivo->Xiaodong Yang; Rap eMail: ->Yangxiaodong5g@vivo.com20/6/22: 0%->100",null,86,44,null,null,"Wed 10/06/20","Mon 20/06/22"]
[1907,950060,"   UE Conformance - Multi-SIM devices for LTE/NR ","LTE_NR_MUSIM_plus_CT1-UEConTest",2,"Rel-17","R5","Tue 15/03/22","Fri 22/09/23",1,"RP-220127","RP-231824","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","tested: REL-17 WI LTE_NR_MUSIM-Core and REL-17 CT1 WI MUSIM 6/6/22: Compl:0%->5% 6/6/ ; 20/6/22: Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn12/7/22: WID:RP-220127->RP-221193; 23/9/22: 5%->25; 23/9/22: FCD:...",null,95,48,null,null,"Tue 05/04/22","Wed 06/09/23"]
[1908,0,"Rel-17 other cross-TSG Features","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1909,930030,"Support of the 5GMSG Service ","FS_5GMARCH",1,"Rel-17",null,"Thu 06/06/19","Fri 10/12/21",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"Fri 31/05/19","Fri 11/06/21"]
[1910,840036,"   Study on support of the 5GMSG Service ","FS_5GMARCH",2,"Rel-17","S6","Thu 06/06/19","Fri 11/12/20",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"Fri 31/05/19","Fri 11/06/21"]
[1911,890010,"   Study on security aspects of the 5GMSG Service (St1 in Rel16)","FS_SEC_5GMSG",2,"Rel-17","S3","Wed 16/09/20","Fri 10/12/21",1,"SP-200878",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","25/9/20: WID:SP-200717->SP-200878; 5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->45; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 45%->75; 12/3/22: 75%->100","33.862",89,45,null,null,"Thu 10/09/20","Sat 12/03/22"]
[1912,930005,"   Security aspects of the 5GMSG Service ","5GMSG",2,"Rel-17","S3","Fri 10/09/21","Fri 10/12/21",1,"SP-210835",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 12/3/22: 0%->100","33.501 ",93,47,null,null,"Fri 10/09/21","Sat 12/03/22"]
[1913,930040,"Application Architecture for MSGin5G Service ","5GMARCH",1,"Rel-17",null,"Wed 16/09/20","Fri 11/03/22",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","Stage 1 in Rel-16, UID 810014","23.554",89,45,null,null,"Fri 11/09/20","Fri 11/06/21"]
[1914,890026,"   Application Architecture for MSGin5G Service ","5GMARCH",2,"Rel-17","S6","Wed 16/09/20","Tue 15/06/21",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","25/9/20: 23.554 added;; 5/12/20: 0%->5; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 5%->25; 11/6/21: 25%->75; 13/9/21: 75%->90; 13/12/21: 90%->100","23.554",89,45,null,null,"Fri 11/09/20","Mon 13/12/21"]
[1915,930004,"   CT aspects for enabling MSGin5G Service ","5GMARCH",2,"Rel-17","ct","Fri 10/09/21","Fri 11/03/22",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,"29.222 ",93,47,null,null,"Fri 10/09/21","NA"]
[1916,930041,"      CT1 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C1","Fri 10/09/21","Fri 11/03/22",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 24.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->75; 4/6/22: 75%->100","24.538",93,47,null,null,"Fri 10/09/21","Sat 04/06/22"]
[1917,930042,"      CT3 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C3","Fri 10/09/21","Fri 11/03/22",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 29.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->100","29.538",93,47,null,null,"Fri 10/09/21","Sat 12/03/22"]
[1918,930002,"IMS voice service support and network usability guarantee for UE s E-UTRA capability disabled scenario in SA 5GS ","ING_5GS",1,"Rel-17","ct","Wed 29/09/21","Thu 06/06/24",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ",null,null,93,47,null,null,"Wed 29/09/21","NA"]
[1919,930047,"   CT1 aspects of ING_5GS","ING_5GS",2,"Rel-17","C1","Wed 29/09/21","Fri 11/03/22",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","13/12/21: 0%->85; 12/3/22: 85%->100","24.301; 24.368; 24.501",93,47,null,null,"Wed 29/09/21","Sat 12/03/22"]
[1920,930046,"   CT6 aspects of ING_5GS","ING_5GS",2,"Rel-17","C6","Wed 29/09/21","Fri 11/03/22",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","12/3/22: 0%->100; 4/6/22: 100%->","31.102",93,47,null,null,"Wed 29/09/21","Sat 04/06/22"]
[1921,1000052,"   UE Conformance - ING_5GS","ING_5GS-UEConTest",2,"Rel-17","R5","Thu 08/06/23","Thu 06/06/24",1,"RP-230873","RP-240910","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","6/9/23: FCD:06/06/2024->03/03/2024; Compl:0%->5%; Stat Rep: ->RP-231826; Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn; ; 14/3/24: FCD:03/03/2024->06/06/2024; Compl:5%->74%; Stat Rep: RP-231826->RP-240115; ; ...",null,100,51,null,null,"Thu 29/06/23","Thu 13/06/24"]
[1922,930031,"User Consent for 3GPP services ","UC3S",1,"Rel-17",null,"Wed 16/09/20","Thu 09/06/22",1,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21","33.867",89,45,null,null,"Fri 25/09/20","Fri 11/06/21"]
[1923,890037,"   Study on User Consent for 3GPP services ","FS_UC3S",2,"Rel-17","S3","Wed 16/09/20","Thu 09/06/22",1,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->80; 12/3/22: 80%->95; 12/3/22: FCD:10/12/2021->6/22; 31/3/23: 95%->100","33.867",89,45,null,null,"Fri 25/09/20","Fri 31/03/23"]
[1924,930006,"   Security aspects on User Consent for 3GPP services ","UC3S_SEC",2,"Rel-17","S3","Fri 10/09/21","Thu 09/06/22",1,"SP-210836",null,"Rong Wu, Huawei Technologies ","Raina.wu@huawei.com ","; 13/12/21: 0%->85; 12/3/22: 85%->95; 12/3/22: FCD:10/12/2021->6/22; 31/3/23: 95%->100","33.501 ",93,47,null,null,"Fri 10/09/21","Fri 31/03/23"]
[1925,910025,"User Plane Integrity Protection for LTE ","UPIP_SEC_LTE",1,"Rel-17","S3","Thu 18/03/21","Fri 10/12/21",1,"SP-210105",null,"Evans, Tim, Vodafone ","tim.evans1@vodafone.com ","; 11/6/21: 0%->85; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 85%->100","33.401; 33.501 ",91,46,null,null,"Thu 18/03/21","Mon 13/12/21"]
[1926,941011,"User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN",1,"Rel-17","R3","Mon 13/12/21","Fri 01/03/24",1,"RP-230070",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 29/3/23: WID:RP-213669->RP-230070",null,94,48,null,null,"Thu 06/01/22","Wed 29/03/23"]
[1927,941111,"   Core part: User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN-Core",2,"Rel-17","R3","Mon 13/12/21","Tue 22/03/22",1,"RP-230070",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 4/6/22: 0%->100",null,94,48,null,null,"Thu 06/01/22","Sat 04/06/22"]
[1928,970074,"   UE Conformance - User Plane Integrity Protection support for EPC connected architectures (incl. CT/SA aspects) ","UPIP_SEC_LTE-RAN-UEConTest",2,"Rel-17","R5","Thu 08/09/22","Fri 01/03/24",1,"RP-240048","RP-240047","Petra RAUER, Vodafone","Petra[dot]Rauer[at]Vodafone[dot]com","17/3/23: FCD:09/09/2023->08/09/2023; Compl:0%->5%; Stat Rep: ->RP-230071; Rapporteur: Vodafone->Petra RAUER, Vodafone; Rap eMail: ->Petra[dot]Rauer[at]Vodafone[dot]com; ...; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:28%->62%; Stat Rep: RP-230071->RP-2...",null,97,49,null,null,"Fri 23/09/22","Tue 02/04/24"]
[1929,910007,"Start of Pause of Charging via User Plane ","SPOCUP",1,"Rel-17","C4","Thu 18/03/21","Fri 11/06/21",1,"CP-210076",null,"YONG, YANG, Ericsson, frank ","yong.yang@ericsson.com ","; 21/3/21: 0%->85; 11/6/21: 85%->100","29.244; 29.060; 29.281; 29.274; 29.502 ",91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[1930,920060,"NPN support of PWS ","NPN_PWS",1,"Rel-17","S1","Sat 12/06/21","Sat 12/06/21",1,"SP-210585",null,"Francesco Pica, Qualcomm","fpica <at> qti.qualcomm.com","11/3/22: 0%->100","22.261",92,47,null,null,"Thu 12/08/21","Fri 11/03/22"]
[1931,940048,"Enhancements of 3GPP profiles for cryptographic algorithms and security protocols ","eCryptPr",1,"Rel-17",null,"Thu 18/03/21","Fri 11/03/22",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"Thu 18/03/21","Mon 13/09/21"]
[1932,910024,"   Stage 2 for eCryptPr","eCryptPr",2,"Rel-17","S3","Thu 18/03/21","Fri 10/12/21",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85; 13/12/21: 85%->95; 12/3/22: 95%->100","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1933,940007,"   Stage 3 CT1 for eCryptPr","eCryptPr",2,"Rel-17","C1","Fri 10/12/21","Fri 11/03/22",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->97; 4/6/22: 97%->100","24.109; 24.141; 24.229; 24.259; 24.424; 24.481; 24.482; 24.486; 24.545; 24.547; 24.548; 24.623",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1934,940049,"   Stage 3 CT3 for eCryptPr","eCryptPr",2,"Rel-17","C3","Fri 10/12/21","Fri 11/03/22",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->100","29.079; 29.116; 29.122; 29.155; 29.201; 29.222; 29.486; 29.517; 29.522; 29.549",94,48,null,null,"Fri 10/12/21","Sat 12/03/22"]
[1935,940050,"   Stage 3 CT4 for eCryptPr","eCryptPr",2,"Rel-17","C4","Fri 10/12/21","Fri 11/03/22",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 7/1/22: 0%->60; 12/3/22: 60%->90; 4/6/22: 90%->100","23.008; 29.228; 29.229; 29.240; 23.333; 23.334; 29.334; 29.335 ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1936,950043,"AKMA TLS protocol profiles ","AKMA_TLS",1,"Rel-17","S3","Fri 11/06/21","Fri 10/06/22",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 4/6/22: 95%->100; 12/9/22: 100%->","33.535 ",92,47,null,null,"Fri 11/06/21","Mon 12/09/22"]
[1937,920027,"   Security aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","S3","Fri 11/06/21","Fri 10/06/22",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 12/3/22: FCD:15/12/2021->6/22; 4/6/22: 100%->100","33.535 ",92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1938,950010,"   CT aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","C1","Thu 10/03/22","Fri 11/03/22",1,"CP-220307",null,"Chaponniere, Lena, Qualcomm Incorporated ","lguellec@qti.qualcomm.com ","; 12/3/22: 0%->80; 4/6/22: 100%->100","24.109 ",95,48,null,null,"Thu 10/03/22","Sat 04/06/22"]
[1939,900002,"Restoration of PDN Connections in PGW-C/SMF Set ","RPCPSET",1,"Rel-17","C4","Mon 07/12/20","Fri 18/12/20",1,"CP-203020",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","23.007; 29.274; 29.303; 23.003 ; 5/12/20: 0%->100; 5/12/20: 0%->100",null,90,46,null,null,"Sat 05/12/20","Sat 05/12/20"]
[1940,900037,"Enhancement of Inter-PLMN Roaming ","EoIPR",1,"Rel-17","C4","Mon 07/12/20","Fri 11/03/22",1,"CP-203021",null,"Caixia Qi, Huawei ","Caixia.qi@huawei.com ","29.510; 29.531; 29.573 ; 21/3/21: 0%->30; 11/6/21: 30%->35; 13/12/21: 35%->80; 13/12/21: FCD:Fri 10/09/->03/22; 12/3/22: 80%->100",null,90,46,null,null,"Sat 05/12/20","Sat 12/03/22"]
[1941,911037,"Reliable Data Service Serialization Indication ","RDSSI",1,"Rel-17",null,"Thu 07/03/19","Fri 10/09/21",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ",null,"23.682; 23.501; 23.502 ",84,43,null,null,"Fri 31/05/19","Thu 06/06/19"]
[1942,840017,"   Stage 2 of RDSSI","RDSSI",2,"Rel-17","S2","Thu 09/05/19","Thu 06/06/19",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ","6/6/19: 0%->100. 9/4/21: Rel-16->Rel-17","23.682; 23.501; 23.502 ",84,43,null,null,"Fri 31/05/19","Thu 06/06/19"]
[1943,900005,"   CT aspects of RDSSI","RDSSI",2,"Rel-17","C1","Thu 07/03/19","Fri 10/09/21",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","24.250; 29.122 ; 21/3/21: 0%->100",null,90,46,null,null,"Sat 05/12/20","Sun 21/03/21"]
[1944,970050,"      CT1 aspects of RDSSI","RDSSI",3,"Rel-17","C1","Thu 07/03/19","Fri 10/09/21",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","23/9/22: 99%->100",null,97,49,null,null,"Wed 07/09/22","Fri 23/09/22"]
[1945,970051,"      CT3 aspects of RDSSI","RDSSI",3,"Rel-17","C3","Thu 07/03/19","Fri 10/09/21",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","23/9/22: 99%->100",null,97,49,null,null,"Wed 07/09/22","Fri 23/09/22"]
[1946,900019,"Adapting BEST for use in 5G networks ","BEST_5G",1,"Rel-17","S3","Fri 04/12/20","Fri 10/12/21",1,"SP-201020",null,"Keesmaat, Iko, KPN ","iko.keesmaat@tno.nl ","33.163 ; 19/3/21: 0%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 70%->85; 13/12/21: 85%->100",null,90,46,null,null,"Fri 04/12/20","Mon 13/12/21"]
[1947,920049,"Enhanced Service Enabler Architecture Layer for Verticals ","eSEAL",1,"Rel-17",null,"Fri 04/12/20","Fri 11/03/22",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35",null,92,47,null,null,"Fri 04/12/20","Sun 21/03/21"]
[1948,900024,"   Stage 2 of eSEAL","eSEAL",2,"Rel-17","S6","Fri 04/12/20","Tue 15/06/21",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35; 11/6/21: 35%->80; 13/9/21: 80%->100",null,90,46,null,null,"Fri 04/12/20","Mon 13/09/21"]
[1949,920006,"   CT1 aspects of eSEAL","eSEAL",2,"Rel-17","C1","Fri 11/06/21","Fri 11/03/22",1,"CP-212098",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 2/7/21: 24.549 added;; 10/9/21: WID:CP-211117->CP-212098; 13/9/21: 0%->20; 13/12/21: 20%->60; 12/3/22: 60%->92; 4/6/22: 92%->99","29.549;24.548;24.547;24.546;24.545 ; 24.549",92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1950,920050,"   CT3 aspects of eSEAL","eSEAL",2,"Rel-17","C3","Fri 11/06/21","Fri 11/03/22",1,"CP-212098",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 10/9/21: WID:CP-211117->CP-212098; 13/9/21: 0%->10; 13/12/21: 10%->40; 12/3/22: 40%->96; 4/6/22: 96%->100","29.549 ",92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1951,940018,"   Security for eSEAL ","eSEAL",2,"Rel-17","S3","Fri 10/12/21","Fri 10/12/21",1,"SP-211366",null,"Rajavelsamy Rajadurai, Samsung ","rajvel@samsung.com ","; 24/3/22: 0%->100","33.434 ",94,48,null,null,"Fri 10/12/21","Thu 24/03/22"]
[1952,900033,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 ","ATSSS_Ph2",1,"Rel-17",null,"Thu 07/03/19","Thu 06/06/24",1,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"Thu 03/12/20","NA"]
[1953,840084,"   Study on ATSSS_Ph2","FS_ATSSS_Ph2",2,"Rel-17","S2","Thu 07/03/19","Tue 15/12/20",1,"SP-200095",null,"So, Tricci, ZTE","tso@ztetx.com","25/3/20: WID:SP-190558->SP-200095; 26/3/20: 0%->15; 26/6/20: FCD:18/06/2020->09/20; 26/6/20: 15%->35; 12/9/20: 35%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->95; 19/3/21: 95%->100","New 23.700-93",84,43,null,null,"Wed 26/06/19","Fri 19/03/21"]
[1954,900012,"   Stage 2 of ATSSS_Ph2","ATSSS_Ph2",2,"Rel-17","S2","Thu 03/12/20","Fri 11/06/21",1,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->55; 14/6/21: 55%->97; 13/9/21: 97%->100",null,90,46,null,null,"Thu 03/12/20","Mon 13/09/21"]
[1955,910013,"   CT aspects of ATSSS_Ph2","ATSSS_Ph2",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ",null,null,91,46,null,null,"Thu 18/03/21","NA"]
[1956,910056,"      CT1 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->96; 4/6/22: 96%->100","24.193; 24.301; 24.501",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1957,910057,"      CT3 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->50; 13/9/21: 50%->80; 13/12/21: 80%->100","29.512",91,46,null,null,"Thu 18/03/21","Mon 13/12/21"]
[1958,910058,"      CT4 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->5; 14/6/21: 5%->50; 13/9/21: 50%->60; 13/12/21: 60%->90; 12/3/22: 90%->100","29.244; 29.502; 29.518",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1959,1010050,"   UE Conformance - ATSSS_Ph2","ATSSS_Ph2-UEConTest",2,"Rel-17","R5","Mon 11/09/23","Thu 06/06/24",1,"RP-240912","RP-240911","China Telecom ",null,"13/6/24: FCD:09/09/2024->06/06/2024; Compl:0%->100%; Stat Rep: ->RP-240911; ; 23/7/24: WID:RP-231827->RP-240912",null,101,51,null,null,"Fri 06/10/23","Tue 23/07/24"]
[1960,900031,"Enablers for Network Automation for 5G - phase 2 ","eNA_Ph2",1,"Rel-17",null,"Thu 06/06/19","Fri 11/03/22",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ",null,90,46,null,null,"Thu 03/12/20","NA"]
[1961,840022,"   Study on Enablers for Network Automation for 5G - phase 2 ","FS_eNA_Ph2",2,"Rel-17","S2","Thu 06/06/19","Tue 15/12/20",1,"SP-200098",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com ","8/10/19: 23.700-91 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190557->SP-200098; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->32; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 32%->55; 12/9/20: 55%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->97; 19/3/ ","New ; 23.700-91",84,43,null,null,"Fri 31/05/19","Fri 19/03/21"]
[1962,890015,"   Study on security aspects of enablers for Network Automation (eNA) for 5GS Phase 2 ","FS_eNA_SEC",2,"Rel-17","S3","Wed 16/09/20","Fri 11/03/22",1,"SP-200722",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->75; 12/3/22: 75%->100; 12/3/22: FCD:10/12/2021->3/22","33.866",89,45,null,null,"Thu 10/09/20","Sat 12/03/22"]
[1963,900010,"   Stage 2 of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ; 19/3/21: 0%->40; 14/6/21: 40%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->99; 10/12/21: 99%->100",null,90,46,null,null,"Thu 03/12/20","Fri 10/12/21"]
[1964,910012,"   CT aspects of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","ct","Fri 19/03/21","Fri 11/03/22",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: WID:CP-210290->CP-211191","29.503; 29.508; 29.510; 29.513; 29.514; 29.517; 29.518; 29.520; 29.522; 29.523; 29.554; 29.571; 29.591 ",91,46,null,null,"Fri 19/03/21","Fri 11/06/21"]
[1965,910088,"      CT3 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C3","Fri 19/03/21","Fri 11/03/22",1,"CP-213261",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->20; 2/7/21: 29.576 added;; 2/7/21: 29.575 added;; 2/7/21: 29.574 added;; 13/9/21: 20%->30; 13/12/21: 30%->65; 13/12/21: WID:CP-211191->CP-213261; 12/3/22: 65%->96; 4/6/22: 96%->100","29.576; 29.575; 29.574",91,46,null,null,"Fri 19/03/21","Sat 04/06/22"]
[1966,910089,"      CT4 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C4","Fri 19/03/21","Fri 11/03/22",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->5; 14/6/21: 5%->60; 13/9/21: 60%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"Fri 19/03/21","Sat 12/03/22"]
[1967,930007,"   Security aspects of eNA_Ph2","eNA_Ph2",2,"Rel-17","S3","Fri 10/09/21","Fri 10/12/21",1,"SP-210837",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 13/12/21: 0%->90; 12/3/22: 90%->100","33.501 ",93,47,null,null,"Fri 10/09/21","Sat 12/03/22"]
[1968,900030,"Proximity based Services in 5GS ","5G_ProSe",1,"Rel-17",null,"Thu 07/03/19","Fri 10/06/22",1,"SP-200972",null,"TBD ",null,null,null,88,45,null,null,"Thu 03/12/20","NA"]
[1969,830033,"   Study on System enhancement for Proximity based Services in 5GS","FS_5G_ProSe",2,"Rel-17","S2","Thu 07/03/19","Fri 12/03/21",1,"SP-190443",null,"Qiang Deng, CATT","dengqiang1@catt.cn","7/6/19: WID:SP-190186->SP-190443; 8/10/19: 23.752 added;; 6/12/19: 0%->30; 25/3/20: 30%->55; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 55%->65; 12/9/20: 65%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: ","23.752; 23.752 ",83,42,null,null,"Thu 14/03/19","Fri 10/12/21"]
[1970,900007,"   Stage 2 for Proximity based Services in 5GS ","5G_ProSe",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-201096",null,"Qiang Deng, CATT","dengqiang1@catt.cn","19/3/21: 0%->30; 11/6/21: 30%->85; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->98; 10/12/21: 98%->99; 12/3/22: 99%->100",null,90,46,null,null,"Thu 03/12/20","Sat 12/03/22"]
[1971,910018,"   CT aspects of proximity based services in 5GS ","5G_ProSe",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: WID:CP-210292->CP-211110; 10/9/21: WID:CP-211110->CP-212105; 13/7/22: 29.533 added;","23.122; 24.501; 27.007; 29.513; 29.519; 29.522; 29.525; 23.008; 29.502; 29.503; 29.505; 29.510; 29.518; 29.527; 29.571; 31.102 ; 29.533",91,46,null,null,"Thu 18/03/21","Wed 13/07/22"]
[1972,910072,"      CT1 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->50; 13/9/21: 50%->65; 13/12/21: 65%->75; 12/3/22: 75%->85; 4/6/22: 85%->96",null,91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1973,910073,"      CT3 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->35; 2/7/21: 29.557 added;; 13/9/21: 35%->65; 13/12/21: 65%->95; 12/3/22: 95%->100","29.557",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1974,910074,"      CT4 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: 0%->25; 13/9/21: 25%->45; 13/12/21: 45%->80; 22/3/22: 29.559 added;; 4/6/22: 80%->90","29.559",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1975,920081,"      CT6 aspects of 5G_ProSe","5G_ProSe",3,"Rel-17","C6","Thu 18/03/21","Fri 11/03/22",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","2/7/21: added ; 13/12/21: 0%->50; 12/3/22: 50%->60; 4/6/22: 60%->60",null,92,47,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1976,890018,"   Study on charging aspects of Proximity-based Services in 5GS","FS_5G_Prose_CH",2,"Rel-17","S5","Wed 16/09/20","Fri 10/12/21",1,"SP-200767",null,"Shu, Min, CATT ","shumin@catt.cn ","25/9/20: 32.846 added;; 5/12/20: 0%->15; 21/3/21: 15%->40; 13/9/21: 40%->80; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 80%->100","32.846",89,45,null,null,"Thu 10/09/20","Tue 21/06/22"]
[1977,940028,"   Charging aspects of Proximity-based Services in 5GS ","5G_ProSe",2,"Rel-17","S5","Fri 10/12/21","Fri 10/06/22",1,"SP-211429",null,"Shu, Min, CATT ","shumin<at>catt<dot>cn ","; 12/3/22: 0%->40; 4/6/22: 40%->100","32.277; 32.240; 32.290; 32.291; 32.298 ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1978,880005,"   Study on Security Aspects of Enhancement for Proximity Based Services in 5GS ","FS_5G_ProSe_Sec",2,"Rel-17","S3","Fri 12/06/20","Fri 10/06/22",1,"SP-200350",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","28/7/20: 33.847 added;; 12/9/20: 0%->15; 5/12/20: 15%->45; 5/12/20: FCD:15/12/2020->06/20; 19/3/21: 45%->60; 9/4/21: 60%->65; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->85; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: ","33.847",88,45,null,null,"Thu 25/06/20","Sat 04/06/22"]
[1979,930008,"   Security Aspects of Proximity based Services in 5GS","5G_ProSe",2,"Rel-17","S3","Fri 10/09/21","Thu 09/06/22",1,"SP-211120",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 13/12/21: 0%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 45%->65; 12/3/22: FCD:11/03/2022->6/22; 22/3/22: 33.503 added;; 4/6/22: 65%->92; 12/9/22: 92%->83; 31/3/23: 83%->100","New ; 33.503",93,47,null,null,"Fri 10/09/21","Fri 31/03/23"]
[1980,911005,"NR Sidelink Relay ","NR_SL_relay",1,"Rel-17",null,"Fri 12/03/21","Thu 22/09/22",1,"RP-212601",null,"OPPO ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 2/7/21: WID:RP-210904->RP-211050; 29/9/21: WID:RP-211050->RP-212601",null,91,46,null,null,"Wed 07/04/21","Wed 29/09/21"]
[1981,911105,"   Core part: NR Sidelink Relay ","NR_SL_relay-Core",2,"Rel-17","R2","Fri 12/03/21","Tue 22/03/22",1,"RP-212819","RP-220210","Qianxi Lu, Xueyan Huang","qianxi.lu@oppo.com, huangxueyan@chinamoblie.com","follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 2/7/21: 38.351 added;; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; WID: RP-211050->RP-212819; Stat Rep: ->RP-220210; Rapporteur: OPPO->Qianxi Lu, Xueyan Huang; Rap eMail: ->qianxi.lu@oppo.com, huan","38.351",91,46,null,null,"Wed 07/04/21","Mon 20/06/22"]
[1982,911205,"   Perf. part: NR Sidelink Relay ","NR_SL_relay-Perf",2,"Rel-17","R4","Fri 12/03/21","Thu 22/09/22",1,"RP-212819","RP-221187 / 1770","Qianxi Lu, Xueyan Huang, OPPO, CMCC","qianxi.lu@oppo.com, huangxueyan@chinamoblie.com","follow-up WI of RAN2 REL-17 SI FS_NR_SL_relay ; 13/9/21: Compl:0%->55%; 13/9/21: CD:Thu 08/09/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211779 20/6/22: FCD:22/03/2022->22/09/2022; Compl:100%->95%; Stat Rep: RP-220210->RP-221187 / 1770; Rapporteur:...",null,91,46,null,null,"Wed 07/04/21","Fri 09/09/22"]
[1983,890030,"Authentication and key management for applications based on 3GPP credential in 5G ","AKMA",1,"Rel-17",null,"Thu 19/09/19","Fri 11/03/22",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 25/09/20: Rel-16->Rel-17","New ; 33.535",85,43,null,null,"Fri 13/09/19","Fri 26/06/20"]
[1984,850021,"   SA3 aspects of AKMA","AKMA",2,"Rel-17","S3","Thu 19/09/19","Fri 12/06/20",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 12/9/20: 95%->96; 25/09/20: Rel-16->Rel-17; 5/12/20: 96%->97; 19/3/21: 97%->98; 12/3/22: 98%->100","New ; 33.535",85,43,null,null,"Fri 13/09/19","Sat 12/03/22"]
[1985,890008,"   CT aspects of AKMA","AKMA-CT",2,"Rel-17","ct","Wed 16/09/20","Fri 11/03/22",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","25/9/20: WID:CP-202047->CP-202240; 25/9/20: WID:CP-202240->CP-202254",null,89,45,null,null,"Fri 11/09/20","Fri 25/09/20"]
[1986,890031,"      CT1 aspects of AKMA","AKMA-CT",3,"Rel-17","C1","Wed 16/09/20","Fri 11/03/22",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","21/3/21: 0%->95; 13/9/21: 95%->96; 13/12/21: 96%->97; 12/3/22: FCD:12/03/2021->3/22; 12/3/22: 97%->100","24.501",89,45,null,null,"Fri 11/09/20","Sat 12/03/22"]
[1987,890032,"      CT3 aspects of AKMA","AKMA-CT",3,"Rel-17","C3","Wed 16/09/20","Fri 11/03/22",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","5/12/20: 0%->15; 21/3/21: 15%->95; 11/6/21: 95%->97; 13/9/21: 97%->95; 13/9/21: FCD:Fri 12/03/->03/22; 13/12/21: 95%->99; 12/3/22: 99%->100","29.522",89,45,null,null,"Fri 11/09/20","Sat 12/03/22"]
[1988,890033,"      CT4 aspects of AKMA","AKMA-CT",3,"Rel-17","C4","Wed 16/09/20","Fri 11/03/22",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","13/9/20: FCD:12/03/2021->09/21; 5/12/20: 0%->20; 21/3/21: 20%->95; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22: 95%->100","29.503; 29.510; 29.571",89,45,null,null,"Fri 11/09/20","Sat 12/03/22"]
[1989,890049,"Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh",1,"Rel-17","R3","Thu 17/09/20","Mon 09/09/24",1,"RP-212585",null,"China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 6/1/21: WID:RP-202051->RP-202363; 29/9/21: WID:RP-202363->RP-212585",null,89,45,null,null,"Fri 25/09/20","Wed 29/09/21"]
[1990,890149,"   Core part: Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh-Core",2,"Rel-17","R3","Thu 17/09/20","Fri 11/03/22",1,"RP-212585","RP-220561","China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Thu 17/06/21->Tue 22/03/22; 13/9/21: ; ",null,89,45,null,null,"Fri 25/09/20","Tue 22/03/22"]
[1991,960076,"   UE Conformance - Enhancement of Private Network support for NG-RAN including CT aspects ","NG_RAN_PRN_enh_plus_CT-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Mon 09/09/24",1,"RP-242005","RP-242006","Lei GAO, Yogesh Tugnawat, China Telecom, Qualcomm","gaol8@chinatelecom.cn, yogesht@qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222942; Rapporteur: ChinaTelecom->Lei GAO, Yogesh Tugnawat, China Telecom, Qualcomm; Rap eMail: ->gaol8@chinatelecom.cn, yogesht@qti.qualcomm.com; 17/3/23: FCD:30/11/202.....",null,96,49,null,null,"Tue 12/07/22","Thu 26/09/24"]
[1992,840046,"Multimedia Priority Service (MPS) Phase 2 ","MPS2",1,"Rel-17",null,"Fri 15/12/17","Fri 11/03/22",1,"SP-190305",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ",null,"22.953; 22.153 ",84,43,null,null,"Fri 31/05/19","NA"]
[1993,780005,"   Study on MPS2","FS_MPS2",2,"Rel-17","S1","Fri 15/12/17","Thu 12/09/19",1,"SP-190315",null,"Singh, Ray P; Vencore Labs","rsingh@vencorelabs.com","16/3/18: 0%->10¦7/6/18: 10%->30¦10/9/18: 30%->50¦4/12/18: 50%->65¦12/12/18: FCD:03/19->09/19. Rel-16->Rel-17¦14/3/19: 65%->80; 31/5/19: 80%->90; 7/6/19: WID:SP-170996->SP-190315; 17/8/20: 90%->100","22.854",78,40,null,null,"Fri 15/12/17","Mon 17/08/20"]
[1994,850011,"   Stopped - Study on MPS2, Stage 2 ","FS_MPS2_St2",2,"Rel-17","S2","Thu 19/09/19","Fri 12/06/20",1,"SP-190629",null,"Don Lukacs; Perspecta Labs ","dlukacs@perspectalabs.com ","; 8/10/19: 23.775 added;; 22/3/22: 0%->100. Puneet: finally no study phase needed. ","New ; 23.775",85,43,96,null,"Fri 13/09/19","Tue 22/03/22"]
[1995,840032,"   Stage 1 of MPS2","MPS2",2,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-190561",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ","13/9/19: 0%->85; 6/12/19: 85%->100","22.953; 22.153 ",84,43,null,null,"Fri 31/05/19","Fri 06/12/19"]
[1996,870002,"   Stage 2 of MPS2","MPS2",2,"Rel-17","S2","Wed 25/03/20","Fri 11/06/21",1,"SP-200519",null,"Streijl, Robert, Perspecta Labs","rstreijl@perspectalabs.com ","25/9/20: WID:SP-200083->SP-200519; 5/12/20: FCD:16/12/2020->06/20; 5/12/20: 0%->20; 19/3/21: 20%->98; 11/6/21: 98%->99; 12/3/22: 99%->100",null,87,44,null,null,"Wed 25/03/20","Sat 12/03/22"]
[1997,880031,"   Stage 3 of MPS2 ","MPS2",2,"Rel-17","ct","Thu 25/06/20","Fri 11/03/22",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 29.328 ",null,88,45,null,null,"Fri 26/06/20","NA"]
[1998,880050,"      CT1 aspects of MPS2 ","MPS2",3,"Rel-17","C1","Thu 25/06/20","Fri 11/03/22",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 2/7/20: FCD:16/12/2020->03/21; 13/9/20: 0%->50; 5/12/20: 50%->75; 21/3/21: 75%->80; 13/9/21: 80%->90; 13/12/21: 90%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[1999,880058,"      CT3 aspects of MPS2 ","MPS2",3,"Rel-17","C3","Thu 25/06/20","Fri 11/03/22",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","29.212; 29.213; 29.214; 29.512; 29.513; 29.514; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70; 13/9/21: 70%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[2000,880051,"      CT4 aspects of MPS2 ","MPS2",3,"Rel-17","C4","Thu 25/06/20","Fri 11/03/22",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","29.328 ; 2/7/20: FCD:20/09/2021->03/21; 11/6/21: 0%->70; 13/9/21: FCD:Mon 15/03/->03/22; 7/1/22: 70%->95; 12/3/22: 95%->100",null,88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[2004,890072,"   CT3 aspects of PAP/CHAP protocols usage in 5GS ","PAP_CHAP",2,"Rel-17","C3","Wed 16/09/20","Fri 12/03/21",1,"CP-210188",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","29.561; 5/12/20: 0%->75; 21/3/21: 75%->95; 21/3/21: WID:CP-202251->CP-210188; 11/6/21: 95%->100",null,89,45,null,null,"Fri 25/09/20","Fri 11/06/21"]
[2009,810018,"   Study on REFEC","FS_REFEC",2,"Rel-17","S1","Thu 06/09/18","Fri 14/06/19",1,"SP-180785",null,"Jose Luis Almodovar Chico, KPN","jose.almodovarchico@tno.nl","4/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->60; 13/9/19: 60%->95; 6/12/19: 95%->100","22.866",81,41,null,null,"Thu 06/09/18","Fri 06/12/19"]
[2012,800015,"   Study on NCIS","FS_NCIS",2,"Rel-17","S1","Wed 06/06/18","Thu 14/03/19",1,"SP-180341",null,"YANG Ning, Oppo","yangning@oppo.com ","6/8/18: 22.842 added;¦10/9/18: 0%->25¦4/12/18: 25%->60¦14/3/19: 60%->85; 31/5/19: 85%->100","22.842",80,41,null,null,"Wed 06/06/18","Fri 31/05/19"]
[2015,890009,"Points for 8K VR 360 Video over 5G ","8K_VR_5G",1,"Rel-17","S4","Wed 16/09/20","Fri 11/06/21",1,"SP-200667",null,"Ozgur Oyman, Company: Intel ","ozgur.oyman@intel.com ","; 5/12/20: 0%->25; 21/3/21: 25%->85; 21/3/21: FCD:12/03/2021->06/21; 11/6/21: 85%->100","26.118; 26.511; 26.925 ",89,45,null,null,"Thu 10/09/20","Fri 11/06/21"]
[2018,880018,"   Stage 3 of MuDE","MuDe",2,"Rel-17","C1","Thu 25/06/20","Fri 11/12/20",1,"CP-201162",null,"Adrian Buckley ","adrian.buckley@vivo.com ","24.174 ; 13/9/20: 0%->15; 21/3/21: 15%->40; 11/6/21: 40%->100",null,88,45,null,null,"Fri 26/06/20","Fri 11/06/21"]
[2020,920056,"   CT3 aspects of BEPoP","BEPoP",2,"Rel-17","C3","Thu 25/06/20","Fri 11/03/22",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: 0%->60; 10/9/21: FCD:Wed 15/09/->03/22; 13/9/21: 60%->85; 12/3/22: 85%->100","29.820",88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[2023,840038,"MC services support on IOPS mode of operation ","MCIOPS",1,"Rel-17","S6","Thu 06/06/19","Fri 11/09/20",1,"SP-190944","Camilo Solano, Ericsson ","Camilo.solano@ericsson.com ","23.280; 23.379; 23.281; 23.282 ","13/9/19: 0%->10; 20/9/19: WID:SP-190480->SP-190944; 8/10/19: 23.180 added;; 6/12/19: 10%->40; 26/3/20: FCD:12/03/2020->09/20; 26/3/20: 40%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 5/12/20: 95%->100","23.180",84,43,null,null,"Fri 31/05/19","Sat 05/12/20"]
[2027,960051,"5GMS AF Event Exposure ","EVEX",1,"Rel-17","S4","Fri 11/06/21","Fri 10/06/22",1,"SP-210374",null,"Lo, Charles, Qualcomm Inc., ","clo@qti.qualcomm.com ","; 13/9/21: 0%->10; 1/10/21: 26.531 & 26.532 added;; 13/12/21: 10%->40; 12/3/22: 40%->60; 12/3/22: FCD:11/03/2022->6/22","26.512;26.501 ; 26.531; 26.532",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[2031,920010,"5G Multicast-Broadcast User Service Architecture and related 5GMS Extensions ","5MBUSA",1,"Rel-17","S4","Fri 11/06/21","Fri 11/03/22",1,"SP-210376",null,"TAN, PENG, TELUS ","peng.tan@telus.com ","; 13/9/21: 0%->5; 1/10/21: 26.502 added;; 13/12/21: 5%->60; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: 60%->100","26.501 ; 26.502",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[2034,850038,"Enhanced Calling Name Service Analytics Interworking ","eCNAM_An",1,"Rel-17","S1","Mon 02/09/19","Thu 19/09/19",1,"SP-190940",null,"Hala.Mowafy@ericsson.com ",null,"; 13/9/19: 0%->100","22.173 ",85,43,null,null,"Fri 13/09/19","Fri 13/09/19"]
[2036,850039,"   Stage 1 of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","S1","Mon 02/09/19","Fri 18/06/21",1,"SP-190941",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ","; 13/9/19: 0%->100; 5/12/20: 100%->10; 5/12/20: FCD:19/09/2019->06/20; 11/3/22: 10%->100","22.261 ",85,43,null,null,"Fri 13/09/19","Fri 11/03/22"]
[2042,850023,"   Security aspects of Integration of GBA into 5GC ","GBA_5G",2,"Rel-17","S3","Thu 19/09/19","Fri 10/12/21",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 55%->80; 13/12/21: 80%->100","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"Fri 13/09/19","Mon 13/12/21"]
[2045,850045,"Support for Minimization of service Interruption","MINT",1,"Rel-17",null,"Thu 07/03/19","Fri 11/03/22",1,"SP-190814",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com",null,"22.011; 22.261",85,43,null,null,"Fri 13/09/19","NA"]
[2047,850036,"   Stage 1 of MINT","MINT",2,"Rel-17","S1","Fri 13/09/19","Thu 12/12/19",1,"SP-190938",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","13/9/19: 0%->80; 6/12/19: 80%->100","22.011; 22.261",85,43,null,null,"Fri 13/09/19","Fri 06/12/19"]
[2050,930003,"   Stage 3 of MINT","MINT",2,"Rel-17","ct","Wed 29/09/21","Fri 11/03/22",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com",null,"23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"Wed 29/09/21","NA"]
[2054,950017,"   Security Aspects of MINT","MINT",2,"Rel-17","S3","Thu 10/03/22","Fri 11/03/22",1,"SP-220193",null,"Dongjoo Kim, LG Electronics ","dongjoo7.kim@lge.com ","; 22/3/22: 0%->100","33.501 ",95,48,null,null,"Thu 10/03/22","Tue 22/03/22"]
[2058,870020,"Security Assurance Specification for 5G (eSCAS_5G)","eSCAS_5G",1,"Rel-17","S3","Wed 25/03/20","Fri 10/06/22",1,"SP-200149",null,"Rong Wu, Huawei Technologies Co.","Raina.wu@huawei.com","26/6/20: 0%->5","33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519",87,44,null,null,"Wed 25/03/20","Fri 26/06/20"]
[2061,870018,"   eSCAS_5G for 5G NWDAF","SCAS_5G_NWDAF",2,"Rel-17","S3","Wed 25/03/20","Fri 10/06/22",1,"SP-200147",null,"QI Minpeng, China Mobile","qiminpeng@chinamobile.com","26/6/20: 0%->10; 5/12/20: 10%->60; 19/3/21: 60%->70; 19/3/21: FCD:17/03/2021->06/21; 11/6/21: 70%->85; 11/6/21: FCD:Fri 11/06/->12/21; 11/6/21: 85%->; 13/9/21: 85%->90; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: 90%->100","33.521; 33.926",87,44,null,null,"Wed 25/03/20","Sat 04/06/22"]
[2063,880003,"   eSCAS_5Gfor Inter PLMN UP Security ","SCAS_5G_IPUPS",2,"Rel-17","S3","Fri 12/06/20","Fri 10/12/21",1,"SP-200348",null,"Jin PENG, ZTE Corporation ","peng.jin1@zte.com.cn ","33.926; 33.513 ; 12/9/20: 0%->20; 19/3/21: 20%->70; 11/6/21: 70%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 90%->100",null,88,45,null,null,"Thu 25/06/20","Mon 13/09/21"]
[2069,840028,"IMS Charging in 5G System Architecture ","5GSIMSCH",1,"Rel-17","S5","Thu 06/06/19","Fri 10/12/21",1,"SP-190367",null,"Jahangir, Zeeshan, T-Mobile USA ","Zeeshan.jahangir@t-mobile.com ","13/9/19: 0%->10; 6/12/19: 10%->30; 25/03/20: Rel-16->Rel-17; 5/12/20: 30%->40; 5/12/20: FCD:12/03/2020->03/20; 21/3/21: 40%->60; 13/9/21: 60%->80; 13/9/21: FCD:Fri 12/03/->12/21; 12/3/22: 80%->100","32.240; 32.260; 32.275; 32.281; 32.290; 32.291; 32.298; 32.297 ",84,43,null,null,"Fri 31/05/19","Sat 12/03/22"]
[2070,820006,"Study on User Plane Integrity Protection","FS_UP_IP_Sec",1,"Rel-17","S3","Thu 13/12/18","Fri 12/03/21",1,"SP-181035",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","20/3/19: 0%->15¦20/3/19: 0%->15; 31/5/19: 15%->25; 13/9/19: 25%->50; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: 50%->65; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 65%->75; 12/9/20: 75%->85; 5/12/20 ",null,82,42,null,null,"Thu 06/12/18","Fri 11/06/21"]
[2076,950002,"   CT4 aspects of NSWO","NSWO_5G",2,"Rel-17","C4","Thu 10/03/22","Fri 11/03/22",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->98; 4/6/22: 98%->100","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"Thu 10/03/22","Sat 04/06/22"]
[2077,950042,"   CT6 aspects of NSWO","NSWO_5G",2,"Rel-17","C6","Thu 10/03/22","Fri 11/03/22",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->100; 4/6/22: 100%->","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"Thu 10/03/22","Sat 04/06/22"]
[2081,990121,"   (IETF) Messaging Use Cases and Extensions for STIR (draft-ietf-stir-messaging)","LI17",2,"Rel-17","S3-IETF","Tue 10/12/19","Fri 10/06/22",1,null,null,"Lionel Morand, Orange","lionel.morand@orange.com",null,null,99,50,null,null,"Fri 17/03/23","NA"]
[2085,940006,"      Stage 3 for TEI17_IMSGID","TEI17_IMSGID",3,"Rel-17","C1","Wed 11/03/20","Fri 11/03/22",1,"CP-213082",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 12/3/22: 70%->100","24.229 ",94,48,null,null,"Fri 10/12/21","Sat 12/03/22"]
[2088,910003,"      CT aspects on TEI17_SPSFAS","TEI17_SPSFAS",3,"Rel-17","ct","Thu 18/03/21","Wed 08/09/21",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ",null,null,91,46,null,null,"Thu 18/03/21","NA"]
[2090,910046,"         CT4 aspects on TEI17_SPSFAS","TEI17_SPSFAS",4,"Rel-17","C4","Thu 18/03/21","Fri 11/06/21",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ","11/6/21: 0%->80; 13/9/21: 80%->100","29.502; 29.503; 29.504",91,46,null,null,"Thu 18/03/21","Mon 13/09/21"]
[2096,930039,"         CT4 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C4","Fri 10/09/21","Fri 11/03/22",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->100","29.502 ",93,47,null,null,"Fri 10/09/21","Mon 13/12/21"]
[2097,910078,"   Support for Signed Attestation for Priority and Emergency Sessions ","TEI17_SAPES",2,"Rel-17",null,"Wed 25/03/20","Fri 10/09/21",1,"SP-200453",null,"Foti, George, Ericsson ","George.foti@ericsson.com ",null,null,87,44,null,null,"Wed 10/06/20","NA"]
[2103,870005,"      Stage 2 for TEI17_DCAMP","TEI17_DCAMP",3,"Rel-17","S2","Wed 11/03/20","Thu 25/06/20",1,"SP-200446",null,"Pancorbo, Belen (Ericsson)",null,"19/3/21: 0%->100","23.501; 23.502; 23.503",87,44,null,null,"Wed 10/06/20","Fri 19/03/21"]
[2104,910009,"      CT aspects on TEI17_DCAMP","TEI17_DCAMP",3,"Rel-17","ct","Fri 19/03/21","Fri 11/03/22",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 11/6/21: WID:CP-210291->CP-211192; 10/9/21: WID:CP-211192->CP-212163","29.513; 29.507; 29.512; 29.519; 29.521; 29.523; 29.514; 29.504; 29.510; 29.522; 29.571 ",91,46,null,null,"Fri 19/03/21","Fri 10/09/21"]
[2108,910084,"   Dynamic management of group-based event monitoring ","TEI17_GEM",2,"Rel-17",null,"Wed 11/03/20","Fri 11/03/22",1,"SP-200455",null,"Qian XB Chen, Ericsson","Qian.XB.Chen@ericsson.com",null,null,87,44,null,null,"Wed 10/06/20","NA"]
[2112,910086,"         CT4 aspects on TEI17_GEM ","TEI17_GEM",4,"Rel-17","C4","Fri 19/03/21","Fri 11/03/22",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 13/9/21: 0%->80; 7/1/22: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"Fri 19/03/21","Sat 12/03/22"]
[2115,930099,"      CT1 aspects of TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","C1","Fri 11/06/21","Fri 18/06/21",1,"CP-211089",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","; 11/6/21: 0%->100; 1/10/21: 0%->100","24.501;29.571;29.510 ",92,47,null,null,"Fri 11/06/21","Fri 01/10/21"]
[2119,890019,"      SA5 aspects of N40 Interface Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","S5","Wed 16/09/20","Wed 08/09/21",1,"SP-200854",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","25/09/20: acronym: \"NIESGU\"->\"TEI17_NIESGU\"; 25/9/20: WID:SP-200768->SP-200854; 5/12/20: FCD:11/06/2021->09/20; 5/12/20: 0%->5; 21/3/21: 5%->10; 13/9/21: 10%->100","32.240; 32.251; 32.255; 32.290; 32.291; 32.298 ",89,45,null,null,"Fri 11/09/20","Mon 13/09/21"]
[2121,920082,"      CT4 aspects of N7 Interfaces Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","C4","Fri 19/03/21","Fri 10/09/21",1,"CP-211194",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","2/7/21: added; 13/9/21: 0%->100","29.512; 29.513 ",92,47,null,null,"Fri 19/03/21","Mon 13/09/21"]
[2124,880044,"   Stage-3 5GS NAS protocol development 17 general aspects ","5GProtoc17",2,"Rel-17","C1","Thu 25/06/20","Fri 11/03/22",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ; 13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->70; 13/9/21: FCD:Mon 20/09/->0 ",null,88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[2127,880046,"   Stage-3 SAE Protocol Development general aspects","SAES17",2,"Rel-17","C1","Thu 25/06/20","Fri 11/03/22",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->65; 13/12/21: 65%->90; 12/3/22: FCD:20/09/2021->3/22; 12/3/22: 90%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ; ",88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[2130,911034,"IMS Stage-3 IETF Protocol Alignment ","IMSProtoc17",1,"Rel-17","ct","Thu 25/06/20","Thu 06/06/24",1,"CP-201167",null,"Gkatzikis, Lazaros(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","13/9/20: 0%->10; 13/9/20: 10%->15; 5/12/20: 15%->30; 21/3/21: 30%->20","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ; ",88,45,null,null,"Fri 26/06/20","Sun 21/03/21"]
[2135,880013,"Service Based Interface Protocol Improvements Release 17 ","SBIProtoc17",1,"Rel-17",null,"Thu 25/06/20","Fri 11/03/22",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ",null,null,88,45,null,null,"Fri 26/06/20","NA"]
[2139,940002,"Restoration of Profiles related to UDR ","ReP_UDR",1,"Rel-17","C4","Thu 07/03/19","Fri 18/03/22",1,"CP-220100",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ","; 12/3/22: 0%->100; 12/3/22: WID:CP-213070->CP-220100","23.527; 29.503; 29.505; 29.510; 29.519 ",94,48,null,null,"Fri 10/12/21","Sat 12/03/22"]
[2143,940003,"Enhancement on the GTP-U entity restart ","EGTPUR",1,"Rel-17","C4","Fri 10/12/21","Fri 11/03/22",1,"CP-213077",null,"YONG, YANG, Ericsson ","frank.yong.yang@ericsson.com ","; 12/3/22: 0%->100","23.007; 23.527; 29.060; 29.244; 29.281 ",94,48,null,null,"Fri 10/12/21","Sat 12/03/22"]
[2146,950001,"Repository for the 3GPP Allocated Port Numbers for New 3GPP Interfaces ","PortAl",1,"Rel-17","C4","Thu 10/03/22","Fri 11/03/22",1,"CP-220094",null,"Giorgi Gulbani, Huawei ","giorgi.gulbani@huawei.com ","; 12/3/22: 0%->100","29.941 ",95,48,null,null,"Thu 10/03/22","Sat 12/03/22"]
[2148,990004,"Update of conformance test specifications to Rel-17","UEConTest_R17",1,"Rel-17","C6","Mon 14/06/21","Thu 06/06/24",1,"CP-230022",null,"Arne Marquordt, COMPRION GmbH","amarquordt@comprion.com","Tests eV2XARC_Ph2;eCPSOR_CON;5G_ProSe;5GSAT_ARCH-CT;ING_5GS;MINT;NSWO_5G;ARCH_NR_REDCAP;IoT_SAT_ARCH_EPS","31.121; 31.124",92,47,null,null,"Thu 12/08/21","NA"]
[2151,920018,"Study on Management Aspects of 5G Network Sharing ","FS_MANS",1,"Rel-17","S5","Fri 11/06/21","Fri 10/12/21",1,"SP-210387",null,"Mingrui Sun, China Unicom ","sunmr19@chinaunicom.cn ","; 13/9/21: 0%->5; 13/12/21: 5%->100","New ",92,47,null,null,"Fri 11/06/21","Mon 13/12/21"]
[2154,930009,"   Improved support for NSA in the service-based management architecture ","NSA_SBMA",2,"Rel-17","S5","Fri 10/09/21","Fri 11/03/22",1,"SP-210858",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 13/12/21: 0%->20; 12/3/22: 20%->100","28.623; 28.622; 28.659; 28.663 ",93,47,null,null,"Fri 10/09/21","Sat 12/03/22"]
[2157,880026,"Management of the enhanced tenant concept ","eMEMTANE",1,"Rel-17","S5","Fri 26/06/20","Wed 15/12/21",1,"SP-220293",null,"Zhu, Lei, Huawei ","lei.zhu@huawei.com ","28.531; 28.532; 28.533; 28.541 ; 5/12/20: 0%->5; 11/6/21: 5%->15; 13/9/21: 15%->20; 12/3/22: 20%->100; 22/3/22: WID:SP-200463->SP-220293",null,88,45,null,null,"Fri 26/06/20","Tue 22/03/22"]
[2162,850028,"Study on enhancement of Management Data Analytics Service ","FS_eMDAS",1,"Rel-17","S5","Thu 19/09/19","Fri 12/03/21",1,"SP-190930",null,"Yao, Yizhi, Intel ","yizhi.yao@intel.com ","; 20/9/19: WID:SP-190783->SP-190930; 8/10/19: 28.809 added;; 26/3/20: 0%->30; 28/6/20: 30%->50; 13/9/20: 50%->70; 13/9/20: FCD:11/09/2020->03/21; 5/12/20: 70%->90; 21/3/21: 90%->100","New ; 28.809",85,43,null,null,"Fri 13/09/19","Sun 21/03/21"]
[2165,870021,"Study on new aspects of EE for 5G networks ","FS_EE5G",1,"Rel-17","S5","Wed 25/03/20","Fri 10/12/21",1,"SP-200187",null,"Jean-Michel CORNILY, ORANGE","jeanmichel.cornily@orange.com ","28/6/20: 0%->10; 13/9/20: 10%->25; 13/9/20: FCD:16/06/2021->09/21; 5/12/20: 25%->45; 21/3/21: 45%->70; 11/6/21: 70%->75; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 75%->80; 13/12/21: 80%->100",null,87,44,null,null,"Fri 06/12/19","Mon 13/12/21"]
[2170,950037,"5G Charging for Local breakout roaming of data connectivity ","CHROAM",1,"Rel-17","S5","Thu 10/03/22","Fri 10/06/22",1,"SP-220156",null,"Ericsson, Robert Törnkvist ","robert dot tornkvist at ericsson dot com ","12/3/22: FCD:12/03/2022->6/22; 12/3/22: 0%->5; 4/6/22: 5%->100","32.240; 32.255; 32.290; 32.291; 32.298 ",95,48,null,null,"Thu 10/03/22","Sat 04/06/22"]
[2173,911008,"NR QoE magement and optimizations for diverse services ","NR_QoE",1,"Rel-17",null,"Fri 01/01/21","Mon 09/09/24",1,"RP-211406",null,"China Unicom ",null,"follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part ; 2/7/21: WID:RP-210913->RP-211406",null,91,46,null,null,"Fri 04/06/21","Fri 02/07/21"]
[2175,970072,"   UE Conformance - NR QoE management and optimizations for diverse services ","NR_QoE-UEConTest",2,"Rel-17","R5","Thu 08/09/22","Mon 09/09/24",1,"RP-241754","RP-241753","Bo J NSSON, Ericsson","Bo[dot]jonsson[at]ericsson[dot]com","9/12/22: FCD:08/09/2023->01/09/2023; Compl:0%->5%; Stat Rep: ->RP-222818; Rapporteur: Ericsson->Bo J NSSON, Ericsson; Rap eMail: ->Bo[dot]jonsson[at]ericsson[dot]com; 17/3/23: FCD:09/09/2023->08/09/2023; Stat Rep: RP-222818->RP-230267; ;...; 6/9/23: C...",null,97,49,null,null,"Fri 23/09/22","Thu 26/09/24"]
[2178,911209,"   Stopped - Perf. part: NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL","NR_UE_PC2_R17_CADC_SUL_xBDL_yBUL-Perf",2,"Rel-17","R4","Fri 12/03/21","Wed 22/06/22",1,"RP-221516","RP-221515","Wang, Jin, Huawei","jinwang@huawei.com","; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22 ; 22/3/22: CD:22/03/2022->12/06/2022; 22/3/22: Stat Rep: RP-212181->RP-220699 ; 6/6/22: CD:12/06/2022->22/06/2022 ; 20/6/22:Stopped at 0%; Rapporteur: Huawei->Wang, Jin, Huawei; Rap eMail: ->jinwang@huawei.com;",null,91,46,96,null,"Wed 07/04/21","Mon 20/06/22"]
[2181,911110,"   Core part: NR_FR1_TRP_TRS","NR_FR1_TRP_TRS-Core",2,"Rel-17","R4","Fri 12/03/21","Tue 22/03/22",1,"RP-212030","RP-221276","Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC","ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM","compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx ; 2/7/21: 38.834 added ; 20/6/22: Rapporteur: Vivo->Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC; Rap eMail: ->ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM; ","38.834",91,46,null,null,"Wed 07/04/21","Mon 20/06/22"]
[2184,911012,"High power UE (power class 1.5) for NR band n79 ","NR_UE_PC1_5_n79",1,"Rel-17",null,"Fri 12/03/21","Thu 01/12/22",1,"RP-210843",null,"CMCC ",null,null,null,91,46,null,null,"Wed 07/04/21","NA"]
[2189,911113,"   Core part: NR_UE_PC2_n34","NR_UE_PC2_n34-Core",2,"Rel-17","R4","Fri 12/03/21","Wed 08/09/21",1,"RP-210844",null,"CMCC ",null,"; 2/7/21: 0%->100",null,91,46,null,null,"Wed 07/04/21","Fri 02/07/21"]
[2192,911014,"High power UE (power class 2) for NR band n39 ","NR_UE_PC2_n39",1,"Rel-17",null,"Fri 12/03/21","Fri 22/09/23",1,"RP-210845",null,"CMCC ",null,null,null,91,46,null,null,"Wed 07/04/21","NA"]
[2197,911115,"   Core part: NR_FR2_FWA_Bn259","NR_FR2_FWA_Bn259-Core",2,"Rel-17","R4","Fri 12/03/21","Wed 08/09/21",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ; 29/9/21: 0%->100",null,91,46,null,null,"Wed 07/04/21","Wed 29/09/21"]
[2200,911106,"   Core part: NR_UDC","NR_UDC-Core",2,"Rel-17","R2","Fri 12/03/21","Fri 11/03/22",1,"RP-220140","RP-220141","CATT ",null,"no Perf. Part; compare RAN2 REL-15 WI LTE_UDC-Core ; ;…; 5/4/22: WID:RP-211203->RP-220140",null,91,46,null,null,"Wed 07/04/21","Tue 05/04/22"]
[2203,910096,"Study on band combination handling in RAN4 ","FS_NR_ENDC_combo_rules",1,"Rel-17","R4","Fri 12/03/21","Fri 11/03/22",1,"RP-211146","RP-220164","ZTE ",null,"TR 38.8XX; to collect agreements on rules and guidelines of specifying band combinations covering NR CA, NR DC and EN-DC ; 2/7/21: WID:RP-210773->RP-211146; 2/7/21: 38.862 added;13/9/21: Compl:0%->50%13/9/21: CD:Sat 12/03/22->Tue 22/03/2213/9/21: Stat ","38.862",91,46,null,null,"Wed 07/04/21","Tue 22/03/22"]
[2206,880278,"   Perf. Part: NR_MIMO_OTA","NR_MIMO_OTA-Perf",2,"Rel-17","R4","Mon 22/06/20","Thu 22/09/22",1,"RP-222348","RP-222634","Zhu, Siting; Xing, Jinqiang, CAICT, OPPO","zhusiting@caict.ac.cn xingjinqiang@oppo.com","; 13/9/21: Compl:0%->20%; 13/9/21: CD:Wed 15 ; 22/3/22: Compl:20%->35%; ; 6/6/22: Compl:35%->55% 20/6/22: Rapporteur: CAICT->Zhu, Siting; Xing, Jinqiang, CAICT, OPPO; Rap eMail: ->zhusiting@caict.ac.cn xingjinqiang@oppo.com 9/...; 23/9/22: 90%->100; 23",null,88,45,null,null,"Tue 28/07/20","Fri 23/09/22"]
[2208,870064,"Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258","NR_FR2_FWA_Bn257_Bn258",1,"Rel-17",null,"Wed 25/03/20","Thu 12/12/24",0.79,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-200503->RP-201215; 25/9/20: WID:RP-201215->RP-201598; 6/1/21: WID:RP-201598->RP-202565",null,87,44,null,null,"Thu 26/03/20","Wed 06/01/21"]
[2212,880092,"Adding channel bandwidth support to existing NR bands","NR_bands_R17_BWs",1,"Rel-17",null,"Mon 22/06/20","Wed 22/06/22",1,"RP-221212",null,"Ericsson",null,"25/9/20: WID:RP-201294->RP-202062; 6/1/21: WID:RP-202062->RP-202277; 7/4/21: WID:RP-202277->RP-210917; 2/7/21: WID:RP-210917->RP-211599; 29/9/21: WID:RP-211599->RP-212531; 6/1/22: WID:RP-212531->RP-213248; 5/4/22: WID:RP-213248->RP-220160; 12/7/22: WID:RP",null,88,45,null,null,"Tue 28/07/20","Tue 12/07/22"]
[2215,880193,"   Core part: NR_FR1_35MHz_45MHz_BW","NR_FR1_35MHz_45MHz_BW-Core",2,"Rel-17","R4","Thu 19/03/20","Fri 19/03/21",1,"RP-211386",null,"Huawei",null,"29/9/21: 0%->100",null,88,45,null,null,"Tue 28/07/20","Wed 29/09/21"]
[2219,880297,"   Perf. Part: NR_SAR_PC2_interB_SUL_2BUL","NR_SAR_PC2_interB_SUL_2BUL-Perf",2,"Rel-17","R4","Thu 19/03/20","Mon 21/03/22",1,"RP-212530","RP-211830","China Telecom",null,"7/4/21: 0%->100; 13/9/21: CD:Fri 19/03/21->Mon 21/03/22; 13/9/21: WID: RP-211494->RP-201337 RP-201584 RP-211494; 13/9/21: Stat Rep: ->RP-211830",null,88,45,null,null,"Tue 28/07/20","Mon 13/09/21"]
[2224,900261,"   Perf. part: NR_cov_enh","NR_cov_enh-Perf",2,"Rel-17","R1","Mon 14/12/20","Wed 21/12/22",1,"RP-211566","RP-221283 / 1817","Jianchi Zhu, China Telecom","zhujc@chinatelecom.cn","follow-up WI of REL-17 SI FS_NR_cov_enh ; 13/9/21: CD:Thu 08/09/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211826; 22/3/22: Compl:0%->35% 20/6/22: WG: R4->R1; FCD:12/09/2022->22/09/2022; Compl:35%->60%; Stat Rep: RP-220563->RP-221283 / 1817; Rappor...; 9/",null,90,46,null,null,"Wed 06/01/21","Mon 09/01/23"]
[2227,860035,"   Study on support of reduced capability NR devices","FS_NR_redcap",2,"Rel-17","R1","Mon 16/12/19","Mon 15/06/20",1,"RP-220966",null,"Ericsson",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193238->RP-201386; 25/9/20: WID:RP-201386->RP-201677; 6/1/21: WID:RP-201677->RP-202704; 7/4/21: 0%->100",null,86,44,null,null,"Tue 14/01/20","Wed 07/04/21"]
[2230,950066,"   UE Conformance - Support of reduced capability NR devices ","NR_redcap_plus_ARCH-UEConTest",2,"Rel-17","R5","Tue 15/03/22","Fri 01/03/24",1,"RP-240053","RP-240050","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","tested: REL-17 WI NR_redcap-Core and CT1 REL-17 WI ARCH_NR_REDCAP 6/6/22: Compl:0%->13% ; 20/6/22: Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn ...; 23/9/22: WID:RP-222830->RP-222136; 9/12/22: FCD:23/06/2023->...",null,95,48,null,null,"Tue 05/04/22","Tue 02/04/24"]
[2233,950047,"   CT3 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C3","Fri 10/12/21","Fri 11/03/22",1,"CP-221265",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 0%->98; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: WID:CP-213081->CP-220304; 12/3/22: 0%->100; 4/6/22: WID:CP-220304->CP-221265","24.501; 23.122; 24.008; 24.368",95,48,null,null,"Sat 12/03/22","Sat 04/06/22"]
[2235,950044,"   CT6 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C6","Fri 10/12/21","Fri 11/03/22",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 20%->98; 12/3/22: FCD:10/06/2022->3/22; 12/3/22: 0%->100; 4/6/22: 100%->","29.571; 29.502; 29.540; 29.518; 23.008",95,48,null,null,"Fri 07/01/22","Sat 04/06/22"]
[2239,900264,"   Perf. part: NR_bands_UL_MIMO_PC3_R17","NR_bands_UL_MIMO_PC3_R17-Perf",2,"Rel-17","R4","Mon 14/12/20","Wed 22/06/22",1,"RP-221518","RP-221517","Liu Ye, Huawei","leo.liuye@huawei.com","basket WI ; 13/9/21: CD:Sun 12/06/22->Tue 22/03/22; ; 20/6/22: WID: ->RP-213136; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,90,46,null,null,"Wed 06/01/21","Mon 20/06/22"]
[2242,900068,"Downlink interruption for NR and EN-DC band combinations to conduct dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R17",1,"Rel-17",null,"Mon 14/12/20","Fri 01/03/24",1,"RP-210478",null,"China Telecom ",null,"basket WI; TR 37.8xx ; 7/4/21: WID:RP-202885->RP-210478; 2/7/21: 37.867 added;","37.867",90,46,null,null,"Wed 06/01/21","Fri 02/07/21"]
[2246,900069,"High-power UE (power class 1.5) operation in NR bands n77 and n78 ","HPUE_PC1_5_n77_n78",1,"Rel-17",null,"Mon 14/12/20","Thu 01/12/22",1,"RP-202912",null,"Qualcomm ",null,"no Perf. part ",null,90,46,null,null,"Wed 06/01/21","NA"]
[2250,900170,"   Core part: HPUE_PC1_5_n77_n78","NR_repeaters-Core",2,"Rel-17","R4","Mon 14/12/20","Tue 22/03/22",1,"RP-212129","RP-221566","Valentin Gheorghiu","vgheorgh@qti.qualcomm.com","no Perf. part ; 2/7/21: 38.114 added;; 2/7/21: 38.106 added;; 20/6/22: FCD:12/12/2021->22/03/2023; Compl:0%->100%; WID: RP-213514->RP-212129; Stat Rep: ->RP-221566; Rapporteur: Qualcomm->Valentin Gheorghiu; Rap eMail: ->vgheorgh@qti.qualcomm.com; ","38.114; 38.106",90,46,null,null,"Wed 06/01/21","Mon 20/06/22"]
[2251,930250,"   Perf. part: NR repeaters ","NR_repeaters-Perf",2,"Rel-17","R4","Fri 17/09/21","Wed 21/12/22",1,"RP-222275","RP-221566","Valentin Gheorghiu","vgheorgh@qti.qualcomm.com","Core part (UID=900170) started in Dec.20 while Perf. Part (UID=930250) started in 17/09/21 via revised WID RP-212129; TS 38.1??-1, TS 38.1??-2 ; 7/1/22: 38.115-2 and 38.115-1 added;; 20/6/22: FCD:17/09/2022->22/09/2022; Compl:0%->30%; WID: RP-213514->R...","38.115-2; 38.115-1",93,47,null,null,"Wed 29/09/21","Mon 09/01/23"]
[2255,930057,"Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A",1,"Rel-17","R4","Fri 17/09/21","Thu 01/12/22",1,"RP-212917",null,"Puloli ",null,"specs in [ ]; TR 36.8xx ; 6/1/22: WID:RP-212618->RP-212917",null,93,47,null,null,"Wed 29/09/21","Thu 06/01/22"]
[2258,960081,"   UE Conformance - Introduction of upper 700MHz A block E-UTRA band for the US (band 103) ","LTE_upper_700MHz_A-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Thu 01/12/22",1,"RP-221417","RP-222802","Heng Pan, Puloli","heng.pan@puloli.com","9/9/22: Comp...; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:72%->100%; Stat Rep: ->RP-222802; Rapporteur: Puloli->Heng Pan, Puloli; Rap eMail: ->heng.pan@puloli.com; 9/1/23: 100%->100",null,96,49,null,null,"Tue 12/07/22","Mon 09/01/23"]
[2264,0,"   Rel-17 NR intra band Carrier Aggregation (itrabCA)","-",2,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[2266,881105,"   Core part: NR_CA_R17_Intra","NR_CA_R17_Intra-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221319","RP-221314","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->24%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211752 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2269,900063,"High power UE for NR TDD intra-band Carrier Aggregation in frequency range FR1","NR_intra_HPUE_R17",1,"Rel-17",null,"Wed 10/02/21","Wed 22/06/22",1,"RP-221774",null,"Huawei",null,"7/4/21: WID:RP-202818->RP-210555; 29/9/21: WID:RP-210555->RP-212180; 6/1/22: WID:RP-212180->RP-213133; 5/4/22: WID:RP-213133->RP-220930; 12/7/22: WID:RP-220930->RP-221774",null,90,46,null,null,"Wed 10/02/21","Tue 12/07/22"]
[2273,881106,"   Core part: NR_CADC_R17_2BDL_xBUL","NR_CADC_R17_2BDL_xBUL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221250","RP-221251","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2277,881207,"   Perf. part: NR_CA_R17_3BDL_1BUL","NR_CA_R17_3BDL_1BUL-Perf",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221772","RP-221462","Yuexia Song, CATT","songyuexia@catt.cn","; 22/3/22: CD:15/09/2021->12/06/2022; 22/3/22: Stat Rep: ->RP-220737 ; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2278,881008,"NR iterbCA/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R17_3BDL_2BUL",1,"Rel-17",null,"Mon 22/06/20","Wed 22/06/22",1,"RP-221253",null,"ZTE",null,"25/9/20: WID:RP-201374->RP-201541; 6/1/21: WID:RP-201541->RP-202201; 7/4/21: WID:RP-202201->RP-210497; 2/7/21: WID:RP-210497->RP-211060; 29/9/21: WID:RP-211060->RP-212512; 6/1/22: WID:RP-212512->RP-212889; 5/4/22: WID:RP-212889->RP-220146; 12/7/22: WID:RP",null,88,45,null,null,"Tue 28/07/20","Tue 12/07/22"]
[2282,881109,"   Core part: NR_CA_R17_4BDL_1BUL","NR_CA_R17_4BDL_1BUL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221321","RP-221316","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->45%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211754 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2285,881110,"   Core part: NR_CADC_R17_4BDL_2BUL","NR_CADC_R17_4BDL_2BUL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221396","RP-221397","Yue Wu, Samsung","yue.wu@samsung.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221397; Rapporteur: Samsung->Yue Wu, Samsung; Rap eMail: ->yue.wu@samsung.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2291,890154,"   Core part: NR_PC2_CA_R17_2BDL_2BUL","NR_PC2_CA_R17_2BDL_2BUL-Core",2,"Rel-17","R4","Thu 17/09/20","Wed 22/06/22",1,"RP-221866","RP-221301","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","basket WI; related to generic WI NR_SAR_PC2_interB_SUL_2BUL-Core; TR 38.8xx ; 13/9/21: Compl:0%->70%; 13/9/21: CD:Fri 17/12/21->Tue 22/03/22; 13/9/21: WID: RP-211 ; 20/6/22: WID: RP-202102 RP-202373 RP-210476 RP-211131 RP-211831 RP‑213649 RP-220...",null,89,45,null,null,"Fri 25/09/20","Mon 20/06/22"]
[2293,920066,"   UE Conformance - Rel-17 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2) ","NR_PC2_CA_R17_2BDL_2BUL-UEConTest",2,"Rel-17","R5","Tue 15/06/21","Tue 12/12/23",1,"RP-233581","RP-233580","Jingzhou Wu, Dan Song, China Telecom, China Mobile","wujingzhou@chinatelecom.cn, songdan@chinamobile.com","tested: REL-17 WI NR_PC2_CA_R17_2BDL_2BUL-Core ; 13/9/21: Compl:0%->15%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; 1 ; 22/3/22: Compl:15%->18%; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn...;...",null,92,47,null,null,"Fri 02/07/21","Tue 02/01/24"]
[2296,920172,"   Core part: LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39 ","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-Core",2,"Rel-17","R4","Tue 15/06/21","Wed 15/12/21",1,"RP-211996",null,"CMCC ",null,"compare REL-17 WI NR_DSS; no Perf. part ; 29/9/21: WID:RP-211509->RP-211996",null,92,47,null,null,"Fri 02/07/21","Wed 29/09/21"]
[2300,920273,"   Perf. Part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM-Perf",2,"Rel-17","R4","Wed 15/09/21","Wed 22/06/22",1,"RP-221795","RP-221199 / 1775","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","this is not a basket WI ; 13/9/21: CD:Wed 15/06/22->Wed 22/06/22; ; 22/3/22: Compl:0%->50% ; 20/6/22: FCD:22/09/2022->22/06/2022; Stat Rep: RP-221199->RP-221199 / 1775; Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@n...",null,92,47,null,null,"Fri 02/07/21","Mon 20/06/22"]
[2304,911019,"Addition of MSD (Maximum Sensitivity Degradation) for inter-band EN-DC combinations (1 band LTE+1 band NR FR1) due to added channel bandwidths","ENDC_R17_1BLTE_1BNR_MSD",1,"Rel-17","R4","Thu 25/03/21","Thu 25/03/21",0,"RP-220709",null,"Huawei, HiSilicon",null,"basket WI; addition of MSD requirement for cases where new channel bandwidths were added; no Perf. Part; 2/7/21: WID:RP-210891->RP-211384; 29/9/21: WID:RP-211384->RP-212187; 6/1/22: WID:RP-212187->RP-213140; 5/4/22: WID:RP-213140->RP-220709",null,91,46,null,null,"Fri 09/04/21","Tue 05/04/22"]
[2307,911011,"Rel-17 Power Class 2 for EN-DC with x LTE bands + y NR band(s) in DL and with 1 LTE band +1 TDD NR band in UL (either x= 2, 3, y=1 or x=1, 2, y=2) ","ENDC_PC2_R17_xLTE_yNR",1,"Rel-17",null,"Fri 12/03/21","Mon 09/09/24",1,"RP-221322",null,"Ericsson ",null,"basket WI; compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD; TR 37.8xx ; 2/7/21: WID:RP-210816->RP-211172; 29/9/21: WID:RP-211172->RP-211760; 6/1/22: WID:RP-211760->RP-213467; 5/4/22: WID:RP-213467->RP-220828; 12/7/22: WID:RP-220828",null,91,46,null,null,"Wed 07/04/21","Tue 12/07/22"]
[2309,911211,"   Perf. Part: ENDC_PC2_R17_xLTE_yNR","ENDC_PC2_R17_xLTE_yNR-Perf",2,"Rel-17","R4","Fri 12/03/21","Wed 22/06/22",1,"RP-221322","RP-221318","Per Lindell, Ericsson","per.lindell@ericsson.com","compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,91,46,null,null,"Wed 07/04/21","Mon 20/06/22"]
[2312,911118,"   Core part: LTE_NR_Simult_RxTx","LTE_NR_Simult_RxTx-Core",2,"Rel-17","R4","Fri 12/03/21","Wed 22/06/22",1,"RP-221521","RP-221520","Liu Ye, Huawei","leo.liuye@huawei.com","; 13/9/21: Compl:0%->70% ; 1/10/21: 38.839 added; ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ","38.839",91,46,null,null,"Wed 07/04/21","Mon 20/06/22"]
[2318,890153,"   Core part: DC_R17_xBLTE_2BNR_yDL3UL","DC_R17_xBLTE_2BNR_yDL3UL-Core",2,"Rel-17","R4","Thu 17/09/20","Fri 11/03/22",1,"RP-220674","RP-220675","Samsung ",null,"basket WI; TR 37.717-21-22 ; 13/9/21: Compl:0%->70% ; ; ",null,89,45,null,null,"Fri 25/09/20","Tue 22/03/22"]
[2320,880080,"Band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band","NR_LTE_V2X_PC5_combos",1,"Rel-17",null,"Mon 22/06/20","Wed 22/06/22",1,"RP-213297",null,"CATT",null,"25/9/20: WID:RP-200924->RP-201789; 25/9/20: 37.875 added;; 7/4/21: WID:RP-201789->RP-210588; 6/1/22: WID:RP-210588->RP-213297","37.875",88,45,null,null,"Tue 28/07/20","Thu 06/01/22"]
[2323,880094,"High power UE (power class 2) for EN-DC with 1 LTE band + 1 NR TDD band","ENDC_UE_PC2_R17_NR_TDD",1,"Rel-17",null,"Mon 22/06/20","Tue 06/06/23",1,"RP-221227",null,"China Unicom",null,"25/9/20: WID:RP-201328->RP-202079; 6/1/21: WID:RP-202079->RP-202838; 7/4/21: WID:RP-202838->RP-210327; 2/7/21: WID:RP-210327->RP-211073; 29/9/21: WID:RP-211073->RP-211853; 5/4/22: WID:RP-211853->RP-220388; 12/7/22: WID:RP-220388->RP-221227",null,88,45,null,null,"Tue 28/07/20","Tue 12/07/22"]
[2327,880095,"LTE/NR spectrum sharing in Band 38/n38","DSS_LTE_B38_NR_Bn38",1,"Rel-17",null,"Wed 17/06/20","Tue 15/09/20",1,"RP-201314",null,"Vodafone",null,null,null,88,45,null,null,"Tue 28/07/20","NA"]
[2331,880296,"   Perf. part: DSS_LTE_B40_NR_Bn40","DSS_LTE_B40_NR_Bn40-Perf",2,"Rel-17","R4","Wed 17/06/20","Tue 15/09/20",1,"RP-202084",null,"Reliance Jio",null,"25/9/20: 0%->100",null,88,45,null,null,"Tue 28/07/20","Fri 25/09/20"]
[2334,880298,"   Perf. part: DC_R17_1BLTE_1BNR_2DL2UL","DC_R17_1BLTE_1BNR_2DL2UL-Perf",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221257","RP-221256","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 22/3/22: Compl:0%->90%; ; 20/6/22: Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTTL; Rap eMail: ->pohanhsieh@cht.com.tw; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2336,880199,"   Core part: DC_R17_2BLTE_1BNR_3DL2UL","DC_R17_2BLTE_1BNR_3DL2UL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221508","RP-221507","Liehai Liu, Huawei","liuliehai@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->85%; 20/6/22: Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2339,881100,"   Core part: DC_R17_3BLTE_1BNR_4DL2UL","DC_R17_3BLTE_1BNR_4DL2UL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221320","RP-221315","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->74%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211753 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2342,881101,"   Core part: DC_R17_4BLTE_1BNR_5DL2UL","DC_R17_4BLTE_1BNR_5DL2UL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221073","RP-221072","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","; 13/9/21: Compl:0%->60%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211820; 20/6/22: Stat Rep: RP-221151->RP-221072; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2345,881102,"   Core part: DC_R17_xBLTE_2BNR_yDL2UL","DC_R17_xBLTE_2BNR_yDL2UL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221182","RP-221183","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","13/9/21: Compl:0%->80%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211751; 20/6/22: Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2350,881004,"Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and 3 bands NR inter-band CA (3DL/1UL)","DC_R17_xBLTE_3BNR_yDL2UL",1,"Rel-17",null,"Mon 22/06/20","Wed 22/06/22",1,"RP-221235",null,"ZTE",null,"25/9/20: WID:RP-200715->RP-201712; 6/1/21: WID:RP-201712->RP-202194; 7/4/21: WID:RP-202194->RP-210346; 2/7/21: WID:RP-210346->RP-211056; 29/9/21: WID:RP-211056->RP-211805; 6/1/22: WID:RP-211805->RP-212885; 5/4/22: WID:RP-212885->RP-220205; 12/7/22: WID:RP",null,88,45,null,null,"Tue 28/07/20","Tue 12/07/22"]
[2354,881112,"   Core part: NR_SUL_combos_R17","NR_SUL_combos_R17-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221512","RP-221511","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->80%; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2358,911016,"Introduction of 900MHz NR band for Europe for Rail Mobile Radio (RMR) ","NR_RAIL_EU_900MHz",1,"Rel-17",null,"Fri 12/03/21","Thu 22/09/22",1,"RP-221768",null,"Union Internationale Chemins de Fer (UIC) ",null,"FDD: UL: 874.4-880MHz, DL: 919.4-925MHz ; 2/7/21: WID:RP-210878->RP-211495; 12/7/22: WID:RP-211495->RP-221768",null,91,46,null,null,"Wed 07/04/21","Tue 12/07/22"]
[2361,911017,"Introduction of 1900MHz NR TDD band for Europe for Rail Mobile Radio (RMR) ","NR_RAIL_EU_1900MHz_TDD",1,"Rel-17",null,"Fri 12/03/21","Fri 11/03/22",1,"RP-211542",null,"Union Internationale Chemins de Fer (UIC) ",null,"TDD: UL: 1900-1910MHz, DL: 1900 MHz – 1910 MHz ; 2/7/21: WID:RP-210879->RP-211542",null,91,46,null,null,"Wed 07/04/21","Fri 02/07/21"]
[2363,911217,"   Perf. part: NR_RAIL_EU_1900MHz_TDD","NR_RAIL_EU_1900MHz_TDD-Perf",2,"Rel-17","R4","Fri 12/03/21","Fri 11/03/22",1,"RP‑211496","RP-220148","Union Internationale Chemins de Fer (UIC) ",null,"; ",null,91,46,null,null,"Wed 07/04/21","Tue 22/03/22"]
[2366,860241,"   Perf. part: Extending current NR operation to 71GHz","NR_ext_to_71GHz-Perf",2,"Rel-17","R1","Mon 16/12/19","Fri 03/03/23",1,"RP-222656","RP-230662","Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm Incorporated; Intel Corporation","jingsun@qti.qualcomm.com; aida.l.vera.lopez@intel.com","affects: NR.; 13/9/21: CD:Wed 15/09/21->Wed 22/06/22; ; 22/3/22: Compl:0%->25%; 22/3/22: 6/6/22: CD:12/09/2022->22/12/2022 ; 20/6/22: WG: R4->R1; Stat Rep: RP-221349->RP-221349 / 1749; Rapporteur: Qualcomm->Jing Sun (RAN1); Aida Vera Lopez (RAN4), ...",null,86,44,null,null,"Tue 14/01/20","Fri 17/03/23"]
[2370,870163,"   Core part: Introduction of NR band n13","NR_n13-Core",2,"Rel-17","R4","Wed 25/03/20","Tue 15/09/20",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx; 6/1/21: 0%->100",null,87,44,null,null,"Tue 14/01/20","Wed 06/01/21"]
[2372,880082,"Introduction of NR 47GHz band","NR_47GHz_band",1,"Rel-17","R4","Thu 07/03/19","Thu 07/03/19",1,"RP-212528","RP-211772","Ericsson",null,"7/4/21: WID:RP-201232->RP-210827; 2/7/21: WID:RP-210827->RP-211568; 13/9/21: C ",null,88,45,null,null,"Tue 28/07/20","Mon 13/09/21"]
[2377,880284,"   Perf. part: Introduction of NR band 24","NR_band_n24-Perf",2,"Rel-17","R4","Thu 19/03/20","Fri 19/03/21",1,"RP-211505",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"Tue 28/07/20","Wed 07/04/21"]
[2381,920075,"Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full",1,"Rel-17","R4","Tue 15/06/21","Wed 15/06/22",0.43,"RP-213683",null,"Apple ",null,"in contrast to NR_6GHz_unlic_EU this WI targets Region 2 (Canada, Brazil, Peru, Chile) and Region 3 (South Korea); TR 38.8xx ; 29/9/21: WID:RP-211602->RP-212302; 6/1/22: WID:RP-212302->RP-213683",null,92,47,null,null,"Fri 02/07/21","Thu 06/01/22"]
[2385,890151,"   Core part: Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU-Core",2,"Rel-17","R4","Thu 17/09/20","Fri 11/03/22",1,"RP-213604","RP-220325","Nokia ",null,"missing target dates to be updated ; 10/2/21: 38.849 added;; 13/9/21: Compl:0%->30%; 13/9/21: CD:Tue 15/03/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211822; ","38.849",89,45,null,null,"Fri 25/09/20","Tue 22/03/22"]
[2388,900165,"   Core part: Introduction of NR band n67 ","NR_n67-Core",2,"Rel-17","R4","Mon 14/12/20","Fri 11/06/21",1,"RP-202829",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"Wed 06/01/21","Fri 02/07/21"]
[2389,900265,"   Perf. Part: Introduction of NR band n67 ","NR_n67-Perf",2,"Rel-17","R4","Mon 14/12/20","Fri 11/06/21",1,"RP-202829",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"Wed 06/01/21","Fri 02/07/21"]
[2394,880183,"   Core part: NR_SUL_UL_n24","NR_SUL_UL_n24-Core",2,"Rel-17","R4","Thu 19/03/20","Fri 19/03/21",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"Tue 28/07/20","Wed 07/04/21"]
[2397,880185,"   Core part: NR_SUL_band_1880_1920MHz","NR_SUL_band_1880_1920MHz-Core",2,"Rel-17","R4","Mon 22/06/20","Tue 15/12/20",1,"RP-201363",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"Tue 28/07/20","Wed 06/01/21"]
[2399,880086,"Introduction of NR supplemental uplink (SUL) band 2300-2400MHz","NR_SUL_band_2300_2400MHz",1,"Rel-17",null,"Mon 22/06/20","Tue 15/12/20",1,"RP-201364",null,"CMCC",null,null,null,88,45,null,null,"Tue 28/07/20","NA"]
[2404,911020,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 1","LTE_terr_bcast_bands_part1",1,"Rel-17","R1;R2;R3","Fri 01/01/21","Tue 22/03/22",1,"RP-211144",null,"EBU",null,"13/09/21: \"-part 1|\" added' R4->R1, R2, R3",null,91,46,null,null,"Thu 08/04/21","Fri 02/07/21"]
[2408,880279,"   Perf. part: LTE_bands_R17_M1_M2_NB1_NB2","LTE_bands_R17_M1_M2_NB1_NB2-Perf",2,"Rel-17","R4","Mon 08/06/20","Wed 22/06/22",1,"RP-212906","RP-221173","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 13/9/21: Compl:0%->70%; 13/9/21: CD:Wed 15/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP-211856 ; 20/6/22: Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2412,920067,"   UE Conformance - Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits ","LTE_B24_mod-UEConTest",2,"Rel-17","R5","Tue 15/06/21","Wed 15/12/21",1,"RP-212497",null,"Ligado Networks ",null,"tested: REL-17 WI LTE_B24_mod-Core ; 29/9/21: WID:RP-211396->RP-212497; 6/1/22: 0%->100",null,92,47,null,null,"Fri 02/07/21","Thu 06/01/22"]
[2415,880187,"   Core part: LTE_CA_R17_2BDL_1BUL","LTE_CA_R17_2BDL_1BUL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221389","RP-221388","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; WID: RP-220552->RP-212933; Stat Rep: ->RP-221388; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2416,880287,"   Perf. part: LTE_CA_R17_2BDL_1BUL","LTE_CA_R17_2BDL_1BUL-Perf",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221389","RP-221388","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","; 6/6/22: Comp ; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2421,880189,"   Core part: LTE_CA_R17_xBDL_1BUL","LTE_CA_R17_xBDL_1BUL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221305","RP-221306","Iwajlo ANGELOW, Nokia","iwajlo.angelow@nokia.com","; 13/9/21: Compl:0%->85%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 20/6/22: Rapporteur: Nokia->Iwajlo ANGELOW, Nokia; Rap eMail: ->iwajlo.angelow@nokia.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2424,880190,"   Core part: LTE_CA_R17_2BDL_2BUL","LTE_CA_R17_2BDL_2BUL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221528","RP-221527","Liu Ye, Huawei","leo.liuye@huawei.com","; 22/3/22: Compl:0%->70%; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2427,880191,"   Core part: LTE_CA_R17_xBDL_2BUL","LTE_CA_R17_xBDL_2BUL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221188","RP- 221189","Jin Woong Park, LG Electronics","jinwoong.park@lge.com","; 22/3/22: Compl:0%->95%; ; 20/6/22: FCD:11/03/2022->22/06/2022; Compl:95%->100%; Stat Rep: RP-220299->RP- 221189; Rapporteur: LG->Jin Woong Park, LG Electronics; Rap eMail: ->jinwoong.park@lge.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2430,0,"Release 17 other Studies","-",1,"Rel-17",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[2435,880011,"Study on 5G Glass-type AR/MR Devices ","FS_5GSTAR",1,"Rel-17","S4","Thu 25/06/20","Fri 11/03/22",1,"SP-200399",null,"Hakju Ryan Lee ","hakju00.lee@samsung.com ","25/9/20: 26.998 added;; 5/12/20: 0%->10; 21/3/21: 10%->20; 21/3/21: FCD:11/06/2021->09/21; 11/6/21: 20%->65; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 65%->80; 13/12/21: 80%->90; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 90%->100","26.998",88,45,null,null,"Thu 25/06/20","Sat 12/03/22"]
[2438,870015,"Study on Streaming Architecture extensions For Edge processing ","FS_EMSA",1,"Rel-17","S4","Wed 25/03/20","Fri 11/06/21",1,"SP-200056",null,"Bouazizi, Imed, Qualcomm ","bouazizi@qti.qualcomm.com ","10/6/20: 0%->5; 26/6/20: 5%->15; 5/12/20: 15%->30; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 30%->60; 11/6/21: 60%->100",null,87,44,null,null,"Fri 06/12/19","Fri 11/06/21"]
[2439,870011,"Study on 5G Video Codec Characteristics ","FS_5GVideo",1,"Rel-17","S4","Wed 25/03/20","Fri 10/06/22",1,"SP-200052",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","10/6/20: 0%->20; 26/6/20: 20%->20; 5/12/20: 20%->45; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 45%->55; 11/6/21: 55%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 70%->75; 13/12/21: 75%->85; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 85%->90; 12/3/22: FC ",null,87,44,null,null,"Fri 06/12/19","Sat 04/06/22"]
[2443,911036,"   CT3 aspects of FS_eIMS5G2","FS_eIMS5G2",2,"Rel-17","C3","Fri 25/09/20","Fri 11/03/22",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 8/4/21: 15%->30; 11/6/21: 0%->5; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22: 5%->100","23.700-10",88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[2448,860039,"Study on enhancement of RAN slicing for NR","FS_NR_slice",1,"Rel-17","R2","Mon 16/12/19","Tue 15/12/20",1,"RP-201612",null,"CMCC",null,"affects: NR. TR 38.8xx; 25/9/20: WID:RP-193254->RP-201612; 2/7/21: 0%->100",null,86,44,null,null,"Tue 14/01/20","Fri 02/07/21"]
[2451,900058,"Study on high power UE (power class 2) for one NR FDD band ","FS_NR_PC2_UE_FDD",1,"Rel-17","R4","Mon 14/12/20","Tue 21/09/21",1,"RP-212892","RP-211854","China Unicom ",null,"TR 38.8xx ; 13/9/21: Compl:0%->100%; 13/9/21: CD:Wed 08/09/21->Tue 21/09/21; 13/9/21: Stat Rep: ->RP- ; 29/9/21: 100%->100; 6/1/22: WID:RP-202870->RP-212892",null,90,46,null,null,"Wed 06/01/21","Thu 06/01/22"]
[2454,840021,"Stopped - Study on the Usage of User Identifiers in the 5G System ","FS_UUI5",1,"Rel-17","S2","Thu 06/06/19","Fri 12/06/20",1,"SP-190450",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ","26/6/19: 23.700-094 added;; 8/10/19: 23.700-94 added; 21/1/22: stopped at 0%; 21/1/22: 0%->100","New ; 23.700-094; ",84,43,95,null,"Fri 31/05/19","Fri 21/01/22"]
[2457,880004,"Stopped - Study on security aspects of the Disaggregated gNB Architecture ","FS_disagg_gNB_Sec",1,"Rel-17","S3","Thu 25/06/20","Fri 12/03/21",1,"SP-200349",null,"Sen XU, China Telecom ","xusen@chinatelecom.cn ","12/9/20: 0%->5; 5/12/20: 5%->15; 5/12/20: FCD:16/12/2020->03/20; 19/3/21: 15%->100. 13/7/22: marked as stopped (was already at 100%!) as per e-mail from Mirko on 02/06/22 14.03","33.840",88,45,95,null,"Thu 25/06/20","Fri 19/03/21"]
[2462,790008,"   Study on enhancement of URLLC supporting in 5GC ","FS_5G_URLLC",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180118",null,"Hui Ni, Huawei","Hui.ni@huawei.com","7/6/18: 0%->15¦6/8/18: 23.725 added;¦10/9/18: 15%->60¦7/12/18: 60%->85¦14/3/19: 85%->90; 31/5/19: 90%->95; 13/9/19: 95%->100","23.xyz; 23.725",79,40,null,null,"2018-03-15","2019-09-13"]
[2465,840026,"   Security of URLLC for 5GS ","5G_URLLC_SEC",2,"Rel-16","S3","2019-06-06","2020-03-12",1,"SP-190351",null,"Rong Wu, Huawei Technologies ","Raina.wu@huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->80; 6/12/19: FCD:12/12/2019->03/20; 9/4/21: 80%->100",33.500999999999998,84,43,null,null,"2019-05-31","2021-04-09"]
[2466,840005,"   CT Aspects of 5G_URLLC","5G_URLLC",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","16/9/19: WID:CP-191063->CP-192022",null,84,43,null,null,"2019-05-31","2019-09-16"]
[2470,890020,"   Charging enhancement for URLLC ","5G_URLLC",2,"Rel-17","S5","2020-09-16","2021-06-11",1,"SP-200769",null,"Chen, Shan, Huawei ","chenshan@huawei.com ","; 5/12/20: 0%->20; 5/12/20: FCD:12/03/2021->06/20; 21/3/21: 20%->30; 13/9/21: 30%->100","32.255; 32.291; 32.298 ",89,45,null,null,"2020-09-11","2021-09-13"]
[2473,790009,"   Stopped - Study on enht of systems using EPS for UR and Availability using commodity equipment","FS_EPS_URACE",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180119",null,"Chris Pudney","chris.pudney@vodafone.com","7/6/18: 0%->10¦6/8/18: 23.736 added¦6/6/19: stopped at 10% as per SP-190395; 6/6/19: 10%->100","new; 23.736",79,40,84,null,"2018-03-15","2019-06-06"]
[2479,830080,"Support of NR Industrial Internet of Things (IoT)","NR_IIOT",1,"Rel-16","R2","2018-06-15","2022-03-11",1,"RP-192590",null,"Nokia",null,"26/6/19: WID:RP-190728->RP-191561; 8/10/19: WID:RP-191561->RP-192324; 14/1/20: WID:RP-192324->RP-192590",null,83,42,null,null,"2019-03-26","2020-01-14"]
[2481,800098,"   Study on NR Industrial Internet of Things (IoT)","FS_NR_IIOT",2,"Rel-16","R2","2018-06-15","2019-03-15",1,"RP-181479",null,"Nokia",null,"TR 38.8XX?¦6/8/18: 38.825 added;¦26/3/19: 0%->100",38.825000000000003,80,41,null,null,"2018-06-27","2019-03-26"]
[2485,750004,"Study on Communication for Automation in Vertical Domains","FS_CAV",1,"Rel-16","S1","2017-03-02","2018-03-15",1,"SP-170169",null,"Walewski, Joachim, Siemens AG","joachim.walewski@siemens.com ","7/6/17: 0%->30¦25/8/17: FCD:12/17->03/18¦11/9/17: 30%->65¦15/12/17: 65%->85¦16/3/18: 85%->95¦7/6/18: 95%->100",22.803999999999998,75,38,null,null,"2017-03-02","2018-06-07"]
[2488,800028,"   Study on 5GS Enhanced support of Vertical and LAN Services","FS_Vertical_LAN",2,"Rel-16","S2","2018-06-06","2018-12-14",1,"SP-180507",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com","10/9/18: 0%->25¦7/12/18: 25%->88¦14/3/19: 88%->92; 31/5/19: 92%->100",23.734000000000002,80,41,null,null,"2018-06-06","2019-05-31"]
[2492,830010,"   CT aspects of Vertical_LAN","Vertical_LAN",2,"Rel-16","ct","2019-03-14","2020-03-12",1,"CP-193272",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","3/6/19: WID:CP-190195->CP-191157; 16/9/19: WID:CP-191157->CP-192258; 9/12/19: WID:CP-192258->CP-193142; 9/12/19: WID:CP-193142->CP-193272",null,83,42,null,null,"2018-12-06","2019-12-09"]
[2493,830035,"      CT1 aspects of Vertical_LAN","Vertical_LAN",3,"Rel-16","C1","2019-03-14","2020-03-12",1,"CP-193272",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","31/5/19: 0%->20; 3/6/19: WID:CP-190195->CP-191157; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 20%->75; 6/12/19: 75%->90; 26/3/20: 90%->95; 26/6/20: 95%->99; 13/9/20: 99%->100","23.122; 24.368; 24.501; 24.526",83,42,null,null,"2018-12-06","2020-09-13"]
[2497,820027,"   Stage 2 of SEAL","SEAL",2,"Rel-16","S6","2019-03-07","2019-08-29",1,"SP-181141",null,"Basavaraj (Basu) Pattan, Samsung","basavarajjp@samsung.com","14/3/19: 0%->60; 31/5/19: 60%->95; 13/9/19: 0%->100","new 23.434",82,42,null,null,"2018-12-06","2019-09-13"]
[2500,850049,"      CT1 aspects of SEAL ","SEAL",3,"Rel-16","C1","2019-09-19","2020-03-12",1,"CP-192255",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ","; 6/12/19: 0%->60; 6/12/19: 60%->60; 26/3/20: 60%->80; 26/6/20: 80%->100","New ",85,43,null,null,"2019-09-13","2020-06-26"]
[2506,911003,"   UE Conformance Test Aspects - NR-based access to unlicensed spectrum ","NR_unlic-UEConTest",2,"Rel-16","R5","2021-03-12","2025-03-03",1,"RP-250394","RP-250393","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","tested: REL-16 WI NR_unlic-Core ; 2/7/21: 0%->5 ; ; 6/6/22: Compl:18%->20% 20/6/22: Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qualcomm.com ; 9/...; 9/12/22: FCD:22/12/2022->01/06/2023; Compl:25%->28%; Stat Re...",null,91,46,null,null,"2021-04-07","2025-04-03"]
[2508,760007,"   Study on LAN Support in 5G ","FS_5GLAN",2,"Rel-16","S1","2017-06-05","2018-03-15",1,"SP-170456",null,"Nasielski, Jack, Qualcomm Incorporated","jackn@qti.qualcomm.com","11/9/17: 0%->35¦15/12/17: 35%->65¦16/3/18: 65%->100","22.821; ",76,39,null,null,"2017-06-03","2018-03-16"]
[2512,830043,"Cellular IoT support and evolution for the 5G System","5G_CIoT",1,"Rel-16",null,"2017-09-08","2020-06-12",1,"SP-181118",null,null,null,null,null,83,42,null,null,"2018-12-06","NA"]
[2515,830013,"   CT aspects of 5G_CIoT","5G_CIoT",2,"Rel-16","ct","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","3/6/19: WID:CP-190198->CP-111158; 9/12/19: WID:CP-111237->CP-193274; 25/3/20: WID:CP-193274->CP-200147",null,83,42,null,null,"2018-12-06","2020-03-25"]
[2519,830041,"      CT6 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C6","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 26/3/20: 0%->100","TBD",83,42,null,null,"2018-12-06","2020-03-26"]
[2520,850014,"   Security of 5G_CIoT","5G_CIoT",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190897",null,"Henrik Normann, Ericsson ","henrik.normann@ericsson.com ","6/12/19: 0%->50; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 50%->90; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 90%->100",33.500999999999998,85,43,null,null,"2019-09-13","2020-06-26"]
[2524,800183,"   Core part: Additional MTC enhancements for LTE","LTE_eMTC5-Core",2,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-192875",null,"Ericsson",null,"RAN3 impact?¦26/3/19: WID:RP-182891->RP-190770; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2527,800184,"   Core part: Additional enhancements for NB-IoT","NB_IOTenh3-Core",2,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-200293",null,"Huawei",null,"RAN3 impact?¦26/3/19: WID:RP-182902->RP-190757; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2533,790002,"Study on Improvement of V2X Service Handling ","FS_V2XIMP",1,"Rel-16","S1","2018-03-15","2018-06-14",1,"SP-180247",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","7/6/18: 0%->75¦10/9/18: 75%->95¦4/12/18: 95%->100",22.885999999999999,79,40,null,null,"2018-03-15","2018-12-04"]
[2535,840074,"Application layer support for V2X services ","V2XAPP",1,"Rel-16",null,"2017-12-15","2020-03-12",1,"SP-180898",null,"Niranth Amogh, Huawei Telecommunications India","namogh@huawei.com","7/12/18: 0%->25¦14/3/19: 25%->65","New",84,41,null,null,"2018-09-06","2019-03-14"]
[2539,840075,"      CT1 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->10; 6/12/19: 10%->30; 26/3/20: 30%->65; 26/6/20: 65%->100","24.386; 27.007",84,43,null,null,"2019-05-31","2020-06-26"]
[2542,840078,"Architecture enhancements for 3GPP support of advanced V2X services","eV2XARC",1,"Rel-16",null,"2017-06-05","2020-03-12",1,"SP-181121",null,"LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","14/3/19: 0%->30","23.501; 23.502; 23.503; 23.285",84,43,null,null,"2018-12-06","2019-03-14"]
[2546,840079,"      CT1 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->65; 26/3/20: 65%->95; 26/6/20: 95%->99; 13/9/20: 99%->100","23.122; 24.501; 24.301; 27.007",84,43,null,null,"2019-05-31","2020-09-13"]
[2547,840080,"      CT3 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->30; 6/12/19: 30%->80; 26/3/20: 80%->90; 26/6/20: 90%->100; 26/6/20: WID:CP-200291->CP-201199","29.512; 29.513; 29.514; 29.519; 29.122; 29.522",84,43,null,null,"2019-05-31","2020-06-26"]
[2551,800096,"Study on NR Vehicle-to-Everything (V2X)","FS_NR_V2X",1,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-190224",null,"LG Electronics",null,"TR 38.8XX¦compare SA1 REL-15 SI FS_eV2X, RAN1 REL-15 SI FS_LTE_NR_V2X_eval, SA2 REL-16 SI FS_eV2XARC, SA1 REL-16 SI FS_V2XIMP¦26/3/19: WID:RP-181480->RP-190224¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[2555,830178,"   Core part: 5G V2X with NR sidelink","5G_V2X_NRSL-Core",2,"Rel-16","R1","2019-03-01","2020-02-28",1,"RP-200129",null,"LG Electronics",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2558,0,"5G Location and Positionning Services","-",1,"Rel-16",null,"2017-06-05","2017-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2560,760006,"   Study on positioning use cases","FS_5G_HYPOS",2,"Rel-16","S1","2017-06-05","2018-06-15",1,"SP-170589",null,"Ries, Lionel, ESA ","lionel.ries@esa.int","11/9/17: 0%->10¦15/12/17: 10%->50¦15/12/17: FCD:03/18->06/18¦16/3/18: 50%->75¦7/6/18: 75%->90¦10/9/18: 90%->100",22.872,76,39,null,null,"2017-06-03","2018-09-10"]
[2566,830003,"   CT aspects of 5G_eLCS","5G_eLCS",2,"Rel-16","ct","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","17/9/19: WID:CP-190014->CP-192260",null,83,42,null,null,"2018-12-06","2019-09-17"]
[2569,830046,"      CT4 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","31/5/19: 0%->10; 3/6/19: WID:CP-190190->CP-191064; 13/9/19: 10%->20; 6/12/19: 20%->90; 26/3/20: 90%->98; 26/6/20: 98%->100","24.080; 29.518; 29.572; 29.503; 29.505",83,42,null,null,"2018-12-06","2020-06-26"]
[2573,830073,"   Study on local NR positioning in NG-RAN","FS_NR_local_pos",2,"Rel-16","R3","2019-03-01","2019-12-13",1,"RP-191774",null,"CMCC",null,"8/10/19: WID:RP-190754->RP-191774; 8/10/19: 38.856 added;; 14/1/20: 0%->100",38.856000000000002,83,42,null,null,"2019-03-26","2020-01-14"]
[2574,830177,"   Core part: NR positioning support","NR_pos-Core",2,"Rel-16","R1","2019-03-01","2020-02-28",1,"RP-192581",null,"Intel",null,"25/9/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-09-25"]
[2578,840054,"Optimisations on UE radio capability signalling","RACS",1,"Rel-16",null,"2018-06-06","2020-03-12",1,"RP-191460",null,"Haris Zisimopoulos ","harisz@qti.qualcomm.com","26/6/19: WID:SP-190180->RP-191460","23.501; 23.502; 23.401",84,43,null,null,"2019-03-14","2019-06-26"]
[2582,840055,"      CT1 aspects of RACS","RACS",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->50; 6/12/19: 50%->80; 26/3/20: 80%->100","24.301; 24.501; 24.368; 27.007",84,43,null,null,"2019-05-31","2020-03-26"]
[2585,830079,"Optimisations on UE radio capability signalling – NR/E-UTRA Aspects","RACS-RAN",1,"Rel-16","R2","2018-06-15","2023-03-03",0.99,"RP-200164",null,"MediaTek",null,"26/3/20: WID:RP-190657->RP-200164",null,83,42,null,null,"2019-03-26","2020-03-26"]
[2587,830179,"   Core part: Optimisations on UE radio capability signalling – NR/E-UTRA Aspects","RACS-RAN-Core",2,"Rel-16","R2","2019-03-01","2020-02-28",1,"RP-200164",null,"MediaTek",null,"26/6/19: WID:RP-190657->RP-191088; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2593,820020,"   Stage 2 of eNA","eNA",2,"Rel-16","S2","2018-12-06","2019-06-17",1,"SP-181123",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->85; 26/6/19: 29.517 added;; 13/9/19: 85%->92; 6/12/19: 92%->97; 25/3/20: 97%->100","23.501; 23.502; 23.503; 29.517",82,42,null,null,"2018-12-06","2020-03-25"]
[2596,830049,"      CT4 aspects of eNA","eNA",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","31/5/19: 0%->20; 3/6/19: WID:CP-190194->CP-191111; 13/9/19: 20%->25; 6/12/19: 25%->90; 26/3/20: 90%->100","29.244; 29.510; 29.518; 29.503; 29.505",83,42,null,null,"2018-12-06","2020-03-26"]
[2600,830050,"Wireless and Wireline Convergence for the 5G system architecture","5WWC",1,"Rel-16",null,"2018-12-06","2020-06-12",1,"SP-181117",null,"Marco Spini, Huawei Technologies ","m.spini@huawei.com",null,"23.501; 23.502; 23.503",83,42,null,null,"2018-12-06","NA"]
[2601,820014,"   Stage 2 of 5WWC","5WWC",2,"Rel-16","S2","2018-12-06","2019-06-13",1,"SP-181117",null,"Marco Spini, Huawei Technologies ","m.spini@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->85; 13/9/19: 85%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[2604,829912,"      CT3 aspects of 5WWC","5WWC",3,"Rel-16","C3","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/5/19: 0%->15; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 15%->50; 6/12/19: 50%->70; 6/12/19: WID:CP-192079->CP-193145; 26/3/20: 70%->95; 26/6/20: 95%->100","29.512; 29.513; 29.514; 29.507; 29.122; 29.522",82,42,null,null,"2018-12-06","2020-06-26"]
[2609,830182,"      Core part: NG interface usage for WWC","5WWC-NG_interface-Core",3,"Rel-16","R3","2019-03-01","2019-12-13",1,"RP-190999",null,"Huawei",null,"26/6/19: WID:RP-190772->RP-190999; 28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2612,800024,"Study into discreet listening and logging for mission critical services","FS_MCLOG",1,"Rel-16","S6","2018-06-06","2019-06-12",1,"SP-181138",null,"Chater-Lea, David, Motorola Solutions","david.chater-lea@motorolasolutions.com","6/8/18: 23.784 added;¦10/9/18: 0%->10¦7/12/18: 10%->50¦7/12/18: FCD:03/19->06/19¦14/12/18: WID:SP-180384->SP-181138¦14/3/19: 50%->75; 31/5/19: 75%->100","New; 23.784",80,41,null,null,"2018-06-06","2019-05-31"]
[2615,860003,"   CT aspects of enh2MCPTT ","enh2MCPTT-CT",2,"Rel-16","C1","2019-12-06","2020-03-12",1,"CP-193148",null,"Mike Dolan, FirstNet ","michael.dolan@firstnet.gov ","; 26/3/20: 0%->100","24.379; 24.380; 24.481; 24.482; 24.483; 24.484 ",86,44,null,null,"2019-12-06","2020-03-26"]
[2618,830014,"   CT aspects of eMCData2","eMCData2",2,"Rel-16","C1","2019-03-14","2020-03-12",1,"CP-193146",null,"Val Oprescu (AT&T)","vo4887@att.com ","31/5/19: 0%->15; 13/9/19: 15%->25; 17/9/19: WID:CP-190199->CP-192081; 6/12/19: 25%->55; 9/12/19: FCD:12/12/2019->03/20; 9/12/19: WID:CP-192081->CP-193146; 26/3/20: 55%->70; 26/6/20: 70%->100","24.282; 24.582; 24.483; 24.484; 24.zzz",83,42,null,null,"2018-06-06","2020-06-26"]
[2623,970077,"Conformance Test Aspects - Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData) ","MCProtoc16_enh2MCPTT_eMCData2-ConTest",1,"Rel-16","R5","2022-09-08","2024-09-09",1,"RP-242148","RP-242140","Jason Kahn, NIST","jason.kahn@nist.gov","9/12/22: Acronym:MCProtoc16_enh2MCPTT_eMCData2-ConTest->MCProtoc16_enh2MCPTT_eMCData2-UEConTest; FCD:08/09/2024->30/08/2024; Compl:0%->5%; Stat Rep: ->RP-222804; Rapporteur: NIST->Jason Kahn, NIST; Rap eMail: ->jason.kahn@nist.gov; 10/1/23: acronym re...","36.579-9; 36.579-8",97,49,null,null,"2022-09-23","2024-09-26"]
[2627,840013,"Enhancement of 3GPP Northbound APIs ","eNAPIs",1,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-193175",null,"Yali Yan, Huawei ","yanyali@huawei.com ","; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 9/12/19: WID:CP-192184->CP-193175","29.122; 29.222; 29.522; 29.116 ",84,43,null,null,"2019-05-31","2019-12-09"]
[2628,850053,"   CT3 aspects of eNAPIs","eNAPIs",2,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-193175",null,"Yali Yan, Huawei ","yanyali@huawei.com ","; 13/9/19: 0%->50; 17/9/19: WID:CP-191233->CP-192184; 6/12/19: 50%->85; 6/12/19: WID:CP-192184->CP-193175; 26/3/20: 85%->100","29.122; 29.222; 29.522; 29.116 ",85,43,null,null,"2019-05-31","2020-03-26"]
[2631,810054,"Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems","eMCCI",1,"Rel-16",null,"2018-06-06","2019-06-14",1,null,null,"Monnes, Peter, Harris Corporation","pmonnes@harris.com",null,null,80,41,null,null,"2018-09-10","NA"]
[2636,730005,"   Study on enhancements of Public Warning System","FS_ePWS",2,"Rel-16","S1","2016-09-19","2017-09-14",1,"SP-160733",null,"SyncTechno Inc., Hyounhee Koo","koo at synctechno dot com","22.xxx¦1/12/16: 0%->5¦2/3/17: 5%->45¦7/6/17: 45%->75¦30/6/17: 22.869 added;¦25/8/17: 75%->95¦15/12/17: 95%->100",22.869,73,37,null,null,"2016-09-19","2017-12-15"]
[2639,810053,"      Study on stages 2 and 3 of enhancements of ePWS","ePWS",3,"Rel-16","C1","2018-09-10","2019-06-14",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","7/12/18: 0%->10¦21/3/19: 10%->30; 31/5/19: 30%->85; 3/6/19: WID:CP-182228->CP-191155; 13/9/19: 85%->100","New",81,41,null,null,"2018-09-10","2019-09-13"]
[2642,760054,"Mobile Communication System for Railways 2","MONASTERY2",1,"Rel-16",null,"2017-06-05","2020-03-12",1,"SP-170451",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com","15/12/17: 10%->35","New 22.289; 22.280; 22.281; 22.282; 22.179",76,42,null,null,"2017-06-03","2017-12-15"]
[2645,760004,"   Stage 1 of MONASTERY2","MONASTERY2",2,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-170451",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com","16/3/18: 35%->55¦7/6/18: 55%->70¦7/6/18: FCD:06/18->12/18¦10/9/18: 70%->75¦4/12/18: 75%->100","New 22.289; 22.280; 22.281; 22.282; 22.179",76,39,null,null,"2017-06-03","2018-12-04"]
[{"$f":"A2650+1","v":2650},840092,"NR support for high speed train scenario","NR_HST",1,"Rel-16","R4","2019-06-17","2022-06-22",1,"RP-191788",null,"CMCC",null,"8/10/19: WID:RP-191512->RP-191788",null,84,43,null,null,"2019-06-26","2019-10-08"]
[2651,840192,"   Core part: NR support for high speed train scenario","NR_HST-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-191788",null,"CMCC",null,"28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2654,800011,"Maritime Communication Services over 3GPP System","MARCOM",1,"Rel-16","S1","2016-09-19","2018-12-13",1,"SP-180594",null,"Hyounhee Koo, SyncTechno Inc","koo at synctechno dot com",null,"22.179; 22.280; 22.281; 22.282; 22.261; 22.346; 22.468",80,41,null,null,"2018-06-06","NA"]
[2658,800008,"Enhancement of LTE for Efficient delivery of Streaming Service","eLSTR",1,"Rel-16","S1","2016-12-01","2018-09-14",1,"SP-180322",null,"Xia, Xu, China Telecom","xiaxu.bri@chinatelecom.cn",null,"22.278; 22.115",80,41,null,null,"2018-06-06","NA"]
[2662,810003,"Coverage and Handoff Enhancements for Multimedia ","CHEM",1,"Rel-16","S4","2018-09-06","2019-06-07",1,"SP-180664",null,"Nikolai Leung","nleung@qti.qualcomm.com","7/12/18: 0%->70¦7/3/19: 70%->80¦7/3/19: FCD:03/19->06/19; 31/5/19: 80%->90; 13/9/19: 90%->100",26.114000000000001,81,41,null,null,"2018-09-06","2019-09-13"]
[2667,810040,"Media Handling Extensions for 5G Conversational Services","5G_MEDIA_MTSI_ext",1,"Rel-16","S4","2017-06-05","2019-12-12",1,"SP-180663",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ",null,26.114000000000001,81,41,null,null,"2018-09-06","NA"]
[2670,770031,"Study on EVS Float Conformance Non Bit-Exact","FS_EVS_FCNBE",1,"Rel-16","S4","2017-09-08","2018-09-14",1,"SP-170618",null,"Fabrice Plante, Intel","fabrice.m.plante@intel.com","15/12/17: 26.843 added;¦15/12/17: 0%->50¦16/3/18: 50%->60¦16/3/18: FCD:03/18->06/18¦7/6/18: 60%->70¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 70%->100","New; 26.843",77,39,null,null,"2017-09-08","2018-09-10"]
[2672,800003,"Addition of HLG HDR to TV Video Profiles","HLG_HDR",1,"Rel-16","S4","2018-06-06","2018-09-14",1,"SP-180287",null,"Paul Szucs, Sony Europe Limited","paul.szucs@sony.com","10/9/18: 0%->100","26.116; 26.346; 26.234",80,41,null,null,"2018-06-06","2018-09-10"]
[2677,810044,"Multi-device and multi-identity","MuD",1,"Rel-16",null,"2018-06-06","2020-06-15",1,"SP-180315",null,"Peter Bleckert, Ericsson ","Peter.Bleckert@ericsson.com",null,null,80,41,null,null,"2018-06-06","NA"]
[2678,800004,"   Stage 1 of Multi-device and multi-identity","MuD",2,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180315",null,"Peter Bleckert, Ericsson ","Peter.Bleckert@ericsson.com","10/9/18: 85%->90¦4/12/18: 90%->100",22.172999999999998,80,41,null,null,"2018-06-06","2018-12-04"]
[2681,810046,"      CT3 aspects of Multi-device and multi-identity","MuD",3,"Rel-16","C3","2018-09-06","2020-06-15",1,"CP-200148",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","7/12/18: 0%->5; 13/9/19: 5%->95; 6/12/19: 95%->98; 26/3/20: 98%->100; 2/7/20: FCD:25/03/2020->06/20",29.164999999999999,81,41,null,null,"2018-06-06","2020-07-02"]
[2685,820023,"   Stage 2 of eNS","eNS",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181232",null,"ZTE, Tricci So ","tso at ztetx dot com","14/3/19: 0%->60; 31/5/19: 60%->100",null,82,42,null,null,"2018-12-06","2019-05-31"]
[2689,830054,"      CT4 aspects of eNS","eNS",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","31/5/19: 0%->30; 13/9/19: 30%->50; 6/12/19: 50%->95; 26/3/20: 95%->85 (went down); 26/6/20: 85%->100","29.502; 29.503; 29.505; 29.509; 29.518",83,42,null,null,"2018-12-06","2020-06-26"]
[2694,770005,"   Study on Business Role Models for Network Slicing ","FS_BMNS",2,"Rel-16","S1","2017-09-08","2018-09-14",1,"SP-180169",null,"Covell, Betsy, Nokia","betsy.covell@nokia.com","15/12/17: 22.830 added;¦15/12/17: 0%->10¦15/3/18: WID:SP-170705->SP-180169¦16/3/18: 10%->50¦7/6/18: 50%->75¦10/9/18: 75%->95¦4/12/18: 95%->100","New; 22.830",77,39,null,null,"2017-09-08","2018-12-04"]
[2697,810031,"Enhancement of performance assurance for 5G networks including network slicing","5G_SLICE_ePA",1,"Rel-16","S5","2018-09-06","2020-03-12",1,"SP-190247",null,"Xiaowei Sun (China Mobile)",null,"7/12/18: 0%->30¦17/1/19: WID:SP-180843->SP-180906¦14/3/19: 30%->60¦21/3/19: FCD:06/19->12/19¦21/3/19: WID:SP-180906(->SP-190141)->SP-190247; 31/5/19: 60%->70","28.550; 28.532; 28.552; 28.554; 32.425; 32.426; 32.450; 32.451; 32.455; 28.622; 28.623",81,41,null,null,"2018-09-06","2019-05-31"]
[2700,820029,"Study on Charging Aspects of Network Slicing ","FS_NETSLICE_CH",1,"Rel-16","S5","2018-12-13","2019-12-12",1,"SP-181065",null,"Chen Shan, Huawei","chenshan@huawei.com ","14/3/19: 0%->30¦14/3/19: FCD:06/19->09/19; 31/5/19: 30%->45; 13/9/19: 45%->85; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 85%->100",null,82,42,null,null,"2018-12-07","2019-12-06"]
[2703,740002,"   Study on Stage 1 of PARLOS","FS_PARLOS",2,"Rel-15","S1","2016-12-01","2018-09-10",1,"SP-160904",null,"Covell, Betsy","betsy.covell@nokia.com","1/12/16: 0%->75¦2/3/17: 75%->100¦10/9/18: FCD:03/17->09/18",22.82,74,38,null,null,"2016-12-01","2018-09-10"]
[2705,800035,"   Study on Security Aspects of PARLOS","FS_PARLOS_Sec",2,"Rel-16","S3","2018-06-06","2019-09-12",1,"SP-180442",null,"Greg Schumacher, Sprint","Gregory.schumacher@sprint.com","6/8/18: 33.815 added;¦10/9/18: 0%->5¦7/12/18: 5%->50¦20/3/19: FCD:018->09/19¦20/3/19: 50%->55; 31/5/19: 55%->60; 13/9/19: 60%->100","New; 33.815",80,41,null,null,"2018-06-06","2019-09-13"]
[2708,830012,"   CT aspects of PARLOS","PARLOS",2,"Rel-16","ct","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com",null,null,83,42,null,null,"2018-09-06","NA"]
[2712,830065,"      CT6 aspects of PARLOS","PARLOS",3,"Rel-16","C6","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","31/5/19: 0%->10; 26/3/20: 10%->100","31.102; 31.103",83,42,null,null,"2018-09-06","2020-03-26"]
[2716,820013,"   Stage 2 of ETSUN","ETSUN",2,"Rel-16","S2","2018-12-07","2019-06-17",1,"SP-181116",null,null,null,"14/3/19: 0%->45; 31/5/19: 45%->90; 13/9/19: 90%->100",null,82,42,null,null,"2018-12-05","2019-09-13"]
[2721,820044,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture","ATSSS",1,"Rel-16",null,"2017-06-05","2023-06-06",1,"SP-181124",null,"So, Tricci, ZTE","tso@ztetx.com",null,"23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","NA"]
[2724,830016,"   CT aspects of ATSSS","ATSSS",2,"Rel-16","ct","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn",null,null,83,42,null,null,"2018-12-06","NA"]
[2727,830059,"      CT4 aspects of ATSSS","ATSSS",3,"Rel-16","C4","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn","31/5/19: 0%->25; 13/9/19: 25%->45; 6/12/19: 45%->75; 26/3/20: 75%->85; 26/6/20: 85%->100","29.244; 29.502; 29.503; 29.505; 29.518; 29.510; 23.008",83,42,null,null,"2018-12-06","2020-06-26"]
[2730,860018,"   Charging Access of ATSSS ","ATSSS",2,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191187",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com ","; 26/3/20: 0%->15; 28/6/20: 15%->70; 13/9/20: 70%->100","32.255; 32.290; 32.291; 32.298 ",86,44,null,null,"2019-12-06","2020-09-13"]
[2732,810041,"Single radio voice continuity from 5GS to 3G","5G_SRVCC",1,"Rel-16",null,"2018-03-15","2021-12-10",1,"SP-180737",null,"Chi Ren, China Unicom","renchi1@chinaunicom.cn",null,"23.216; 23.501; 23.502",81,41,null,null,"2018-09-06","NA"]
[2735,820008,"   Security aspects of single radio voice continuity from 5GS to UTRAN ","5GS_UTRAN_SEC",2,"Rel-16","S3","2018-12-13","2019-06-12",1,"SP-190703",null,"Feng Gao, China Unicom ","gaofeng149@chinaunicom.cn ","20/3/19: 0%->20; 13/9/19: 20%->100; 20/9/19: WID:SP-181037->SP-190703","33.501; 33.401; 33.220",82,42,null,null,"2018-12-13","2019-09-20"]
[2739,890046,"      UE Conformance Test Aspects - Single Radio Voice Call Continuity from 5G to 3G ","SRVCC_NR_to_UMTS-UEConTest",3,"Rel-16","R5","2020-09-17","2021-12-10",1,"RP-210400",null,"China Unicom ",null,"tested: REL-16 WI SRVCC_NR_to_UMTS-Core ; 7/4/21: WID:RP-201794->RP-210400; 8/4/21: 0%->31; 8/4/21: FCD:08/09/2021->09/21; 2/7/21: FCD:Fri 10/09/->12/21; 2/7/21: 31%->85; 6/1/22: 85%->100",null,89,45,null,null,"2020-09-25","2022-01-06"]
[2743,840059,"      CT4 aspect of 5G_SRVCC","5G_SRVCC",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","13/9/19: 0%->60; 6/12/19: 60%->80; 26/3/20: 80%->100","29.303; 29.503; 29.504; 29.505; 29.518; 29.274",84,43,null,null,"2019-05-31","2020-03-26"]
[2746,820045,"Enhancements to the Service-Based 5G System Architecture","5G_eSBA",1,"Rel-16",null,"2018-03-15","2020-06-12",1,"SP-181125",null,null,null,null,null,82,42,null,null,"2018-12-06","NA"]
[2748,820022,"   Stage 2 of 5G_eSBA","5G_eSBA",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181125",null,"Tao Sun (China Mobile)","suntao@chinamobile.com","14/3/19: 0%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[2754,840062,"SBA aspects of enhanced IMS to 5GC integration","eIMS5G_SBA",1,"Rel-16",null,"2019-03-14","2019-06-13",1,"SP-190181",null,"T-Mobile USA, Christopher Joul",null,null,"23.501; 23.502; 23.503; 23.228",84,42,null,null,"2019-03-14","NA"]
[2757,850056,"      CT1 aspects of eIMS5G_SBA","eIMS5G_SBA",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192023",null,"de Gregorio, Jesus. Ericsson ","jesus.de.gregorio@ericsson.com ","6/12/19: 0%->70; 26/6/20: 70%->100",null,85,43,null,null,"2019-05-31","2020-06-26"]
[2759,840064,"      CT4 aspects of eIMS5G_SBA","eIMS5G_SBA",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-192023",null,"de Gregorio, Jesus. Ericsson ","jesus.de.gregorio@ericsson.com ","13/9/19: 0%->25; 6/12/19: 25%->50; 26/3/20: 50%->90; 26/6/20: 90%->100","29.510; 29.571; 23.380",84,43,null,null,"2019-05-31","2020-06-26"]
[2762,880072,"   UE Conformance Test Aspects - Private Network Support for NG-RAN","NG_RAN_PRN_Vertical_LAN-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-21",1,"RP-201152","RP-221246","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","8/10/20: 0%->5; 8/4/21: 5%->10; 2/7/21: 10%->31; 20/6/22: FCD:15/12/2021->22/12/2022; Compl:31%->89%; Stat Rep: ->RP-221246; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com 9/9/22: Compl:89%->97%; 29/3/23: 97%->10",null,88,45,null,null,"2020-07-28","2023-03-29"]
[2766,830004,"   CT Aspects of E2E_DELAY","E2E_DELAY",2,"Rel-16","ct","2019-03-14","2019-12-12",1,"CP-190193",null,"Luetzenkirchen, Thomas, Intel","Thomas.luetzenkirchen@intel.com",null,null,83,42,null,null,"2018-09-06","NA"]
[2770,830069,"Enhancements for Common API Framework for 3GPP Northbound APIs ","eCAPIF",1,"Rel-16",null,"2018-03-15","2020-03-12",1,"SP-181137",null,"Basavaraj Pattan, Samsung","basavarajjp@samsung.com ","7/6/18: 0%->15¦10/9/18: 15%->30¦7/12/18: 30%->45¦7/12/18: FCD:12/18->06/19¦13/12/18: WID:SP-180161->SP-181137",23.222000000000001,83,42,null,null,"2018-03-15","2018-12-13"]
[2773,850008,"   CT aspects of eCAPIF ","eCAPIF",2,"Rel-16","C3","2019-09-19","2020-03-12",1,"CP-192254",null,"Narendranath Durga, Tangudu (Samsung) ","n.tangudu {@]samsung.com ","; 6/12/19: 0%->65; 26/3/20: 65%->95; 26/6/20: 95%->100",29.222000000000001,85,43,null,null,"2019-09-13","2020-06-26"]
[2775,800055,"   Study on UDICOM","FS_UDICoM",2,"Rel-16","S2","2018-06-15","2019-06-12",1,"SP-190148",null,"Susana Sabater (Vodafone","susana.sabater@vodafone.com","10/9/18: 0%->30¦2/10/18: WID:SP-180620->SP-180735¦7/12/18: 30%->80¦14/12/18: FCD:12/18->03/20¦14/3/19: 80%->100¦21/3/19: WID:SP-181110->SP-190148¦21/3/19: FCD:019->06/19; 13/9/19: 75%->100","23.732; new",80,41,null,null,"2018-06-15","2019-09-13"]
[2781,0,"NR-related Release 16 Features","-",1,"Rel-16",null,"2019-03-07","2019-03-07",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2784,860258,"   Perf. part: Addition of wider channel bandwidth in NR band n3","NR_n3_BW-Perf",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200305",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2788,830075,"UE Power Saving in NR","NR_UE_pow_sav",1,"Rel-16","R1","2018-06-15","2020-09-15",1,"RP-200494",null,"CATT",null,"26/6/19: WID:RP-190727->RP-191607; 30/6/20: WID:RP-191607->RP-200494",null,83,42,null,null,"2019-03-26","2020-06-30"]
[2789,800094,"   Study on UE power saving in NR","FS_NR_UE_pow_sav",2,"Rel-16","R1","2018-06-15","2019-06-14",1,"RP-181463",null,"CATT",null,"TR 38.8xx; 26/6/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-06-26"]
[2793,800172,"   Core part: Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R16-Core",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201018",null,"Huawei",null,"basket WI¦TR 37.716-00-00¦note: WI covers for SA NR: 1 NR SUL band (already defined) + 1 or more NR bands and for NSA NR: 1 NR SUL band (already defined) + 1 or more NR bands + 1 or more LTE bands¦26/3/19: WID:RP-182559->RP-190714; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2797,800173,"      Core part: Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y)","NR_CA_R16_intra-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200656",null,"Ericsson",null,"basket WI¦TR 38.716-01-01¦26/3/19: WID:RP-182256->RP-190689; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2800,800174,"      Core part: Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2)","NR_CADC_R16_2BDL_xBUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201253",null,"ZTE",null,"basket WI¦TR 38.716-02-00¦26/3/19: WID:RP-182501->RP-190494; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2802,830099,"NR inter-band Carrier Aggregation",null,1,"Rel-16",null,"2019-03-01","2024-12-12",0.74,null,null,null,null,null,null,83,42,null,null,"2019-03-26","NA"]
[2808,830196,"      Core part: Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R16_3BDL_2BUL-Core",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200673",null,"ZTE",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2809,830296,"      Perf. part: Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R16_3BDL_2BUL-Perf",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200673",null,"ZTE",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2815,820073,"   Introduction of NR band n18","NR_n18",2,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-191556",null,"KDDI",null,"26/3/19: WID:RP-182826->RP-190173; 26/6/19: WID:RP-190173->RP-191556",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2816,820173,"      Core part: Introduction of NR band n18","NR_n18-Core",3,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-190173",null,"KDDI",null,"26/3/19: WID:RP-182826->RP-190173; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2820,830271,"      Perf. part: Introduction of NR band n48","NR_n48-Perf",3,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190140",null,"Nokia",null,"26/6/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2824,830091,"   Introduction of NR band n30","NR_n30",2,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190967",null,"AT&T",null,"26/6/19: WID:RP-190166->RP-190967",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2827,830097,"   Introduction of NR band n259","NR_n259",2,"Rel-16","R4","2019-03-01","2019-12-13",1,"RP-200249",null,"Ericsson",null,"26/6/19: WID:RP-190765->RP-191416; 8/10/19: WID:RP-191416->RP-191880; 26/3/20: WID:NR_n259->RP-200249",null,83,42,null,null,"2019-03-26","2020-03-26"]
[2831,850167,"      Core part: Introduction of NR band n26","NR_n26-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192736",null,"Sprint",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2833,840097,"   Introduction of NR supplementary DL band n29","NR_n29",2,"Rel-16","R4","2019-06-17","2019-09-13",1,"RP-192236",null,"Dish Network",null,"8/10/19: WID:RP-191474->RP-192236",null,84,43,null,null,"2019-06-26","2019-10-08"]
[2836,850068,"   Introduction of 2010-2025MHz SUL (supplemental uplink) band for NR","NR_SUL_band_2010_2025MHz",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192584",null,"CMCC",null,"14/1/20: WID:RP-192274->RP-192584",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2839,860056,"   Introduction of band n53","NR_n53",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-192409",null,"Globalstar",null,"affects: NR.",null,86,44,null,null,"2020-02-18","NA"]
[{"$f":"A2842+1","v":2842},831001,"New Radio Band-related topics",null,1,"Rel-16","R4","2018-12-13","2023-12-12",0.99,"RP-182258",null,"Dish Network",null,"16/1/19: WID:RP-181445->RP-182258",null,83,42,null,null,"2018-06-27","2019-01-16"]
[2847,830088,"   Add support of NR DL 256QAM for frequency range 2 (FR2)","NR_DL256QAM_FR2",2,"Rel-16","R4","2019-03-01","2022-03-11",1,"RP-200124",null,"China Telecom",null,"26/6/19: WID:RP-190760->RP-190925; 8/10/19: WID:RP-190925->RP-191891; 26/3/20: WID:RP-191891->RP-200124",null,83,42,null,null,"2019-03-26","2020-03-26"]
[2851,830089,"   NR RF requirement enhancements for frequency range 2 (FR2)","NR_RF_FR2_req_enh",2,"Rel-16","R4","2019-03-01","2023-09-22",0.99,"RP-201606",null,"Nokia",null,"26/6/19: WID:RP-190761->RP-191290; 8/10/19: WID:RP-191290->RP-192227; 14/1/20: WID:RP-192227->RP-192653; 26/3/20: WID:RP-192653->RP-200246; 28/7/20: WID:RP-200246->RP-200668; 25/9/20: WID:RP-200668->RP-201606",null,83,42,null,null,"2019-03-26","2020-09-25"]
[2855,830092,"   Introduction of an NR SUL (supplemental uplink) band with same uplink frequency range as NR band n5","NR_SUL_UL_n5",2,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-192080",null,"Huawei",null,"26/6/19: WID:RP-190390->RP-191116; 8/10/19: WID:RP-191116->RP-192080",null,83,42,null,null,"2019-03-26","2019-10-08"]
[2858,820074,"   Adding wider channel bandwidths in NR band n7","NR_n7_BW",2,"Rel-16","R4","2018-12-13","2019-09-13",1,"RP-190137",null,"BT",null,"no Perf. part¦26/3/19: WID:RP-182827->RP-190137",null,82,42,null,null,"2019-01-16","2019-03-26"]
[2860,830093,"   Addition of wider channel bandwidth in NR band n38","NR_n38_BW",2,"Rel-16","R4","2019-03-01","2019-12-13",1,"RP-191472",null,"Huawei",null,"26/6/19: WID:RP-190392->RP-191472; 14/1/20: WID:RP-191472->RP-192513; 13/6/21: WID:RP-192513->RP-191472",null,83,42,null,null,"2019-03-26","2021-06-13"]
[2863,850063,"   Addition of further channel bandwidths in NR band 38","NR_n38_BW2",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192513",null,"Ericsson",null,"13/6/21: WID:RP-192215->RP-192513",null,85,43,null,null,"2019-10-08","2021-06-13"]
[2866,820075,"   Addition of 30MHz channel bandwidth for NR band n41","NR_n41_BW",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-191681",null,"KDDI",null,"26/3/19: WID:RP-182828->RP-190174; 26/6/19: WID:RP-190174->RP-191569; 8/10/19: WID:RP-191569->RP-191681",null,82,42,null,null,"2019-01-16","2019-10-08"]
[2869,820076,"   Adding wider channel bandwidths in NR band n50","NR_n50_BW",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-182829",null,"Huawei",null,"no Perf. part",null,82,42,null,null,"2019-01-16","NA"]
[2874,850065,"   Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25","NR_n25_BW",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192401",null,"Nokia",null,"14/1/20: WID:RP-192219->RP-192401",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2877,850066,"   Addition of wider channel bandwidths in NR band n28","NR_n28_BW",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192656",null,"CBN",null,"14/1/20: WID:RP-192261->RP-192656",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2882,850269,"      Perf. part: Addition of new channel bandwidth in NR band n1","NR_n1_BW2-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192801",null,"China Unicom",null,"28/7/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-07-28"]
[2885,800085,"Enhancements on MIMO for NR","NR_eMIMO",1,"Rel-16","R1","2018-06-15","2022-09-22",1,"RP-200474",null,"Samsung",null,"16/1/19: WID:RP-181453->RP-182863; 8/10/19: WID:RP-182863->RP-192271; 26/3/20: WID:RP-192271->RP-200474",null,80,41,null,null,"2018-06-27","2020-03-26"]
[2887,800285,"   Perf. part: Enhancements on MIMO for NR","NR_eMIMO-Perf",2,"Rel-16","R4","2018-06-15","2020-09-15",1,"RP-200474",null,"Samsung",null,"7/4/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-04-07"]
[2890,800187,"   Core part: NR mobility enhancements","NR_Mob_enh-Core",2,"Rel-16","R2","2018-06-15","2019-12-13",1,"RP-192534",null,"Intel",null,"26/3/19: WID:RP-181433->RP-190489; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2893,820068,"2-step RACH for NR","NR_2step_RACH",1,"Rel-16","R1","2018-12-15","2019-12-15",1,"RP-200085",null,"ZTE",null,"WI was created after REL-16 SI FS_NR_NOMA was completed¦26/3/19: WID:RP-182894->RP-190711; 8/10/19: WID:RP-190711->RP-192330; 26/3/20: WID:RP-192330->RP-200085",null,82,42,null,null,"2019-01-16","2020-03-26"]
[2896,911001,"   UE Conformance Test Aspects - 2-step RACH for NR ","NR_2step_RACH-UEConTest",2,"Rel-16","R5","2021-03-12","2022-09-22",1,"RP-210612","RP-221195","Wei Ma, Jing Zhao, ZTE, China Telecom","ma.wei4@zte.com.cn, zhaoj16@chinatelecom.cn","tested REL-16 WI NR_2step_RACH-Core ; 2/7/21: 0%->25; 13/9/21: Compl:25%->54%; 13/9/21: CD:Fri 11/03/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211763; 20/6/22: Rapporteur: ZTE->Wei Ma, Jing Zhao, ZTE, China Telecom; Rap eMail: ->ma.wei4@zte.com...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[2901,850030,"Self-Organizing Networks (SON) for 5G networks ","SON_5G",1,"Rel-16","S5","2019-09-19","2020-09-14",1,"SP-200763",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","; 13/9/19: 0%->80; 8/10/19: 28.544 added;; 8/10/19: 28.313 added;; 28/6/20: 80%->75; 13/9/20: 75%->100; 13/9/20: WID:SP-190785->SP-200763; 13/9/20: FCD:12/03/2020->09/20","28.552; 28.545 ; 28.544; 28.313",85,43,null,null,"2019-09-13","2020-09-13"]
[2904,840293,"   Perf. part: RRM requirement for CSI-RS based L3 measurement in NR","NR_CSIRS_L3meas-Perf",2,"Rel-16","R4","2019-06-17","2020-09-15",1,"RP-210590",null,"CATT",null,"2/7/21: 0%->100",null,84,43,null,null,"2019-06-26","2021-07-02"]
[2909,840195,"   Core part: NR RRM enhancement","NR_RRM_enh-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-201883",null,"Intel",null,"25/9/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-09-25"]
[2912,840096,"Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL","NR_CA_R16_4BDL_1BUL",1,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-200658",null,"Ericsson",null,"basket WI; TR 38.716-04-01; 8/10/19: WID:RP-191196->RP-191814; 14/1/20: WID:RP-191814->RP-192447; 26/3/20: WID:RP-192447->RP-200103; 28/7/20: WID:RP-200103->RP-200658",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2915,840098,"Addition of wider channel bandwidth in NR band n1","NR_n1_BW",1,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-192009",null,"Ericsson",null,"8/10/19: WID:RP-191595->RP-192009",null,84,43,null,null,"2019-06-26","2019-10-08"]
[2918,840099,"Addition of channel bandwidths in Band n77 and n78","NR_n77_n78_BW",1,"Rel-16","R4","2019-06-17","2019-12-13",1,"RP-191606",null,"Huawei",null,"no Perf. part",null,84,43,null,null,"2019-06-26","NA"]
[2920,841000,"Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL","DC_R16_LTE_NR_3DL3UL",1,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-201254",null,"ZTE",null,"max. 2 NR bands for DL and UL; min. 1 NR FR2 band; TR 37.716-xx-xx; 8/10/19: WID:RP-191598->RP-191882; 14/1/20: WID:RP-191882->RP-192537; 26/3/20: WID:RP-192537->RP-200110; 28/7/20: WID:RP-200110->RP-201254",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2924,841101,"   Core part: Introduction of NR FDD bands with variable duplex and corresponding framework","NR_FDD_bands_varduplex-Core",2,"Rel-16","R4","2019-06-17","2019-12-13",1,"RP-192820",null,"Huawei",null,"no Perf. part as no Perf. part objectives; NR FDD bands are based on NR SDL/SUL bands; framework part will consider interworking with LTE but without normative changes (they may follow later in EN-DC basket WIs; 8/10/19: WID:RP-191567->RP-192285; 14/1/ ",null,84,43,null,null,"2019-06-26","2020-01-14"]
[2927,841102,"   Core part: Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1)","DC_Pcmax_3UL_CC-Core",2,"Rel-16","R4","2019-10-08","2020-03-12",0,"RP-192093",null,"Huawei",null,"no Perf. Part; note: Some combinations were removed from REL-15 due to missing Pc,max; the combinations will be covered in existing REL-16 basket Wis once Pc,max is specified in this WI; 8/10/19: WID:RP-191604->RP-192093",null,84,43,null,null,"2019-07-31","2019-10-08"]
[2931,0,"Release 16 Features impacting both LTE and NR","-",1,"Rel-16",null,"2019-03-07","2019-03-07",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2936,890044,"   UE Conformance Test Aspects - High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) ","ENDC_UE_PC2_FDD_TDD-UEConTest",2,"Rel-16","R5","2020-09-17","2021-12-17",1,"RP-212501",null,"China Unicom ",null,"tested: REL-16 WI ENDC_UE_PC2_FDD_TDD-Core ; 8/4/21: 0%->78; 29/9/21: WID:RP-201776->RP-212501; 29/9/21: 78%->100",null,89,45,null,null,"2020-09-25","2021-09-29"]
[2939,860257,"   Perf. part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band","DC_R16_xBLTE_2BNR_yDL3UL-Perf",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200905",null,"NTT DOCOMO",null,"affects: LTE, NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2942,800088,"LTE-NR & NR-NR Dual Connectivity and NR Carrier Aggregation enhancements","LTE_NR_DC_CA_enh",1,"Rel-16","R2","2018-06-15","2023-06-06",0.99,"RP-200791",null,"Ericsson",null,"RAN3 impact?¦26/3/19: WID:RP-181469->RP-190452; 26/6/19: WID:RP-190452->RP-191600; 8/10/19: WID:RP-191600->RP-192336; 28/7/20: WID:RP-192336->RP-200791",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2945,911004,"   UE Conformance Test Aspects - LTE-NR & NR-NR Dual Connectivity and NR CA enhancements ","LTE_NR_DC_CA_enh-UEConTest",2,"Rel-16","R5","2021-03-12","2023-06-06",1,"RP-231105","RP-230915","Matti Kangas","matti.kangas@nokia.com","lested: REL-16 WI LTE_NR_DC_CA_enh-Core ; 2/7/21: WID:RP-210746->RP-211442; 2/7/21: 0%->5; 5/4/22: WID:RP-211442->RP-220801; 20/6/22: FCD:11/03/2022->22/12/2022; Compl:5%->40%; WID: RP-220801->RP-211442; Stat Rep: ->RP-221416; Rapporteur: Nokia->Matti...",null,91,46,null,null,"2021-04-07","2023-08-09"]
[2947,820061,"   Study on high power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band)","FS_ENDC_UE_PC2_FDD_TDD",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-192268",null,"China Unicom",null,"EN-DC = E-UTRA-NR Dual Connectivity¦TR 37.8xx¦26/3/19: WID:RP-182895->RP-190167; 8/10/19: WID:RP-190167->RP-192268; 14/1/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-01-14"]
[2951,790054,"eNB(s) Architecture Evolution for E-UTRAN and NG-RAN","LTE_NR_arch_evo",1,"Rel-16","R3","2018-03-15","2019-12-13",1,"RP-192917",null,"China Unicom",null,"follow-up WI of REL-15 SI FS_LTE_arch_evo; 14/1/20: WID:RP-180531->RP-192917",null,79,40,null,null,"2018-03-27","2020-01-14"]
[2954,820180,"   Core part: LTE/NR spectrum sharing in Band 41/n41 frequency range","NR_n41_LTE_41_coex-Core",2,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-190175",null,"KDDI",null,"no Perf. part¦changes will happen only on NR side¦26/3/19: WID:RP-182883->RP-190175; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2958,800058,"Dual Connectivity (EN-DC) ",null,1,"Rel-16",null,"2018-06-15","2019-12-13",1,null,null,null,null,null,null,80,41,null,null,"2018-06-27","NA"]
[2962,800067,"   Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_2BLTE_1BNR_3DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201278",null,"Huawei",null,"basket WI¦TR 37.716-02-01¦16/1/19: WID:RP-181357->RP-182557¦26/3/19: WID:RP-182557->RP-190379; 26/6/19: WID:RP-190379->RP-191124; 8/10/19: WID:RP-191124->RP-192087; 14/1/20: WID:RP-192087->RP-192815; 26/3/20: WID:RP-192815->RP-200271; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2963,800167,"      Core part: Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_2BLTE_1BNR_3DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201278",null,"Huawei",null,"basket WI¦TR 37.716-02-01¦26/3/19: WID:RP-182557->RP-190379; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2967,800268,"      Perf. part: Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_3BLTE_1BNR_4DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200657",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182257->RP-190159; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[{"$f":"A2970+1","v":2970},800269,"      Perf. part: Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_4BLTE_1BNR_5DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200648",null,"Nokia",null,"basket WI¦26/3/19: WID:RP-182534->RP-190294; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2976,800271,"      Perf. part: Dual Connectivity (EN-DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R16_xBLTE_2BNR_yDL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200744",null,"LG Electronics",null,"basket WI¦26/3/19: WID:RP-182302->RP-190151; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2978,790057,"E-UTRA 2.4 GHz TDD Band for US","LTE_TDD_2400_US",1,"Rel-16","R4","2018-03-15","2019-06-18",1,"RP-182405",null,"Globalstar",null,"new LTE TDD band for 2483.5 to 2495MHz¦compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US¦6/8/18: 36.791 added;¦16/1/19: WID:RP-180583->RP-182405",36.790999999999997,79,40,null,null,"2018-03-27","2019-01-16"]
[2981,820063,"   UE Conformance Test Aspects - E-UTRA 2.4 GHz TDD Band for US (Band 53)","LTE_TDD_2400_US-UEConTest",2,"Rel-15","R5","2018-12-13","2019-06-18",1,"RP-182406",null,"Globalstar",null,"tested: REL-15 WI LTE_TDD_2400_US-Core; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2985,800260,"      Perf. part: Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y)","LTE_CA_R16_intra-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200655",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182255->RP-190157; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2989,800062,"   Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL","LTE_CA_R16_3BDL_1BUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201012",null,"Huawei",null,"basket WI¦TR 36.716-03-01¦16/1/19: WID:RP-181436->RP-182553¦26/3/19: WID:RP-182553->RP-190375; 26/6/19: WID:RP-190375->RP-191120; 8/10/19: WID:RP-191120->RP-192083; 14/1/20: WID:RP-192083->RP-192811; 26/3/20: WID:RP-192811->RP-200451; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2990,800162,"      Core part: Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL","LTE_CA_R16_3BDL_1BUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201012",null,"Huawei",null,"basket WI¦TR 36.716-03-01¦26/3/19: WID:RP-182553->RP-190375; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2994,800263,"      Perf. part: Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL","LTE_CA_R16_xBDL_1BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201238",null,"Nokia",null,"basket WI¦26/3/19: WID:RP-182330->RP-190138; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2997,800264,"      Perf. part: Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL","LTE_CA_R16_2BDL_2BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201014",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182555->RP-190377; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3003,800091,"   Study on LTE-based 5G terrestrial broadcast","FS_LTE_terr_bcast",2,"Rel-16","R1","2018-06-15","2019-03-15",1,"RP-181342",null,"Qualcomm",null,"TR 36.7xx¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[3005,830276,"   Perf. part: LTE-based 5G terrestrial broadcast","LTE_terr_bcast-Perf",2,"Rel-16","R4","2019-03-01","2020-06-01",1,"RP-193050",null,"Qualcomm",null,"25/9/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-09-25"]
[3008,830294,"   Perf. part: Power class 2 UE for LTE bands 31 and 72","LTE_PC2_B31_B72-Perf",2,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-190665",null,"Nokia",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[3012,800175,"      Core part: Additional LTE bands for UE category M1 and/or NB1 in Rel-16","LTE_bands_R16_M1_NB1-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201200",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182768->RP-190332; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3016,800176,"      Core part: Additional LTE bands for UE category M2 and/or NB2 in Rel-16","LTE_bands_R16_M2_NB2-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201201",null,"Ericsson",null,"basket WI¦no Perf. part¦26/3/19: WID:RP-182769->RP-190333; 28/7/20: WID:RP-200154->RP-201201; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3019,800179,"   Core part: Further performance enhancement for LTE in high speed scenario","LTE_high_speed_enh2-Core",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-181482",null,"NTT DOCOMO",null,"14/1/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-01-14"]
[3021,800082,"Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR","NR_CLI_RIM",1,"Rel-16","R1","2018-06-15","2022-08-03",0.62,"RP-193190",null,"LG Electronics",null,"16/1/19: WID:RP-181431->RP-182864¦26/3/19: WID:RP-182864->RP-190700; 26/6/19: WID:RP-190700->RP-191546; 8/10/19: WID:RP-191546->RP-191997; 14/1/20: WID:RP-191997->RP-193190",null,80,41,null,null,"2018-06-27","2020-01-14"]
[3024,890047,"   UE Conformance Test Aspects - Cross Link Interference (CLI) handling for NR ","NR_CLI-UEConTest",2,"Rel-16","R5","2020-09-17","2022-08-03",0.34,"RP-210716","RP-223381","Vijay Balasubramanian","vijayb[at]qti.qualcomm.com","tested: CLI part of REL-16 WI NR_CLI_RIM-Core ; 7/4/21: WID:RP-201940->RP-210716; 8/4/21: 0%->5; 20/6/22: FCD:17/12/2021->22/12/2022; Compl:5%->19%; Stat Rep: ->RP-221247; Rapporteur: Qualcomm->Vijay Balasubramanian; Rap eMail: ->vijayb@qti.qualcomm.c...",null,89,45,null,null,"2020-09-25","2023-03-31"]
[3030,820072,"Direct data forwarding between NG-RAN and E-UTRAN nodes for inter-system mobility","Direct_data_fw_NR",1,"Rel-16","R3","2018-12-13","2019-06-18",1,"RP-182886",null,"Ericsson",null,"no Perf. part",null,82,42,null,null,"2019-01-16","NA"]
[3032,800089,"Even further mobility enhancement in E-UTRAN","LTE_feMob",1,"Rel-16","R2","2018-06-15","2022-06-22",1,"RP-200148",null,"China Telecom",null,"compare REL-14 WI LTE_eMob¦26/3/19: WID:RP-181475->RP-190272; 26/6/19: WID:RP-190272->RP-190921; 26/3/20: WID:RP-190921->RP-200148",null,80,41,null,null,"2018-06-27","2020-03-26"]
[3035,880066,"   UE Conformance Test Aspects - Even further mobility enhancement in E-UTRAN","LTE_feMob-UEConTest",2,"Rel-16","R5","2020-06-22","2022-06-22",1,"RP-200731","RP-221293","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","8/10/20: 0%->5; 8/4/21: 5%->16; 13/9/21: Compl:16%->32%; 13/9/21: CD:Wed 15/12/21->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211837 ; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn; ",null,88,45,null,null,"2020-07-28","2022-06-20"]
[3039,890041,"   UE Conformance Test Aspects - 410-430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe (Bands 87 and 88) ","LTE410_Europe_PPDR-UEConTest",2,"Rel-16","R5","2020-09-17","2020-12-17",1,"RP-201479",null,"Nokia ",null,"tested: REL-16 WI LTE410_Europe_PPDR-Core ; 6/1/21: 0%->100",null,89,45,null,null,"2020-09-25","2021-01-06"]
[3043,0,"All other Release 16 Features","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3046,880001,"Removal of H.263 and MPEG-4 Visual from 3GPP Services","RM_H263_MP4V",1,"Rel-16","S4","2020-06-25","2020-09-16",1,"SP-200400",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","26.140; 26.114; 26.244; 26.346; 26.234; 26/6/20: 0%->60; 12/9/20: 60%->100",null,88,45,null,null,"2020-06-25","2020-09-12"]
[3048,830186,"   Core part: Introduction of GSM, UTRA, E-UTRA and NR CS(s) to the MSR specifications","MSR_GSM_UTRA_LTE_NR-Core",2,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-190642",null,"Ericsson",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[3051,810021,"   Stage 2 of VBCLTE","VBCLTE",2,"Rel-16","S5","2018-09-06","2019-12-12",1,"SP-180813",null,"Chen, Ai, China Mobile","chenai@chinamobile.com","14/3/19: 0%->50; 13/9/19: 50%->55; 13/9/19: FCD:14/06/2019->12/20; 6/12/19: 55%->100","32.251; 32.260; 32.298; 32.299",81,41,null,null,"2018-09-06","2019-12-06"]
[3054,840068,"      CT3 aspects of VBCLTE","VBCLTE",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-201206",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","6/12/19: 0%->100; 26/6/20: WID:CP-191110->CP-201206","29.212; 29.213; 29.214",84,43,null,null,"2019-05-31","2020-06-26"]
[3057,850009,"   Architecture enhancements for the support of Integrated access and backhaul (IAB) ","IABARC",2,"Rel-16","S2","2019-09-19","2020-03-12",1,"SP-190627",null,"Hong Cheng, Qualcomm Incorporated ","hongc@qti.qualcomm.com ","13/9/19: 0%->33","23.501; 23.502; 23.401 ",85,43,null,null,"2019-09-13","2019-09-13"]
[3062,820270,"   Perf. Part: NR_IAB","NR_IAB-Perf",2,"Rel-16","R4","2019-03-07","2020-03-06",1,"RP-210442",null,"Qualcomm",null,"26/3/19: WID:RP-182882->RP-190712; 8/10/19: WID:RP-190712->RP-192188; 25/9/20: 38.809 added;; 9/4/21: 38.176-1 and 2 added;; 2/7/21: 0%->100","38.809; 38.176-1; 38.176-2",82,42,null,null,"2019-01-16","2021-07-02"]
[3066,820028,"Enhancement of 5G PCC related services ","en5GPccSer",1,"Rel-16","C3","2018-12-13","2019-12-19",1,"CP-183246",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","¦14/3/19: 0%->10; 31/5/19: 10%->60; 13/9/19: 60%->70; 6/12/19: 70%->90; 26/3/20: 90%->100","29.507; 29.512; 29.513; 29.514; 29.551; 29.594; 29.214; 29.519 ",82,42,null,null,"2018-12-07","2020-03-26"]
[3070,780055,"5G Voice Service Continuity ","5GVSC",1,"Rel-16","S1","2017-12-21","2018-03-13",1,"SP-171077",null,"Qun Wei, China Unicom","weiqun5@chinaunico.cn","16/3/18: 0%->100",22.260999999999999,78,40,null,null,"2017-12-21","2018-03-16"]
[3073,800030,"   Stage 2 of xBDT","xBDT",2,"Rel-16","S2","2019-03-07","2019-12-12",1,"SP-180509",null,"Takeshi　Usui KDDI ","ta-usui@kddi.com","31/5/19: 0%->100","23.501; 23.502; 23.503",80,41,null,null,"2018-06-06","2019-05-31"]
[3075,840070,"      CT1 aspects of xBDT","xBDT",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192182",null,"Yan Xiaojian, ZTE ","yan.xiaojian@zte.com.cn ","13/9/19: 0%->100",24.526,84,43,null,null,"2019-05-31","2019-09-13"]
[3078,770020,"Service Interactivity","SerInter",1,"Rel-16","S4","2017-09-08","2019-12-12",1,"SP-170796",null,"Lo, Charles, Qualcomm Incorporated","clo@qti.qualcomm.com","15/12/17: 0%->10¦16/3/18: 10%->20¦7/6/18: 20%->40¦7/6/18: FCD:06/18->12/18. Moved from Rel-15¦10/9/18: 40%->50¦7/12/18: 50%->60¦7/3/19: 60%->70¦7/3/19: FCD:12/18->06/19; 31/5/19: FCD:14/06/2019->09/20; 31/5/19: 70%->80; 13/9/19: FCD:12/09/2019->12/20; ","26.346; 26.247; 26.347",77,39,null,null,"2017-09-08","2019-12-06"]
[3081,790019,"Usage of CAPIF for xMB API","CAPIF4xMB",1,"Rel-16","S4","2018-03-15","2018-12-14",1,"SP-180031",null,"Thorsten Lohmar, Ericsson LM ","Thorsten.lohmar@ericsson.com","7/6/18: 0%->25¦6/8/18: 26.348 added;¦10/9/18: 25%->40¦7/12/18: 40%->100","26.346; new; 26.348",79,40,null,null,"2018-03-15","2018-12-07"]
[3084,800005,"Inter-RAT Mobility requirements for real time service","MOBRT",1,"Rel-16","S1","2018-06-06","2018-09-14",1,"SP-180592",null,"Yang Xu, Oppo","xuyang@oppo.com","10/9/18: 70%->100",22.260999999999999,80,41,null,null,"2018-06-06","2018-09-10"]
[3089,810026,"Methodology for 5G management specifications","METHOGY",1,"Rel-16","S5","2018-09-06","2019-03-15",1,"SP-180822",null,"Groenendijk, Jan, Ericsson","jan<dot>Groenendijk<at>ericsson<dot>com","7/12/18: 0%->60¦14/3/19: 60%->85; 13/9/19: 85%->100","New; 32.156",81,41,null,null,"2018-09-06","2019-09-13"]
[3093,820033,"Network Exposure Charging in 5G System Architecture ","5GS_Ph1_NEFCH",1,"Rel-16","S5","2018-12-13","2019-12-19",1,"SP-181070",null,"Tornkvist, Robert, Ericsson ","robert(dot)tornkvist(at)Ericsson(dot)com ","¦14/3/19: 0%->20; 31/5/19: 20%->50; 13/9/19: 50%->60; 6/12/19: 60%->100","32.240; 32.254; 32.290; 32.291; 32.298 ",82,42,null,null,"2018-12-07","2019-12-06"]
[3097,820038,"IMS Stage-3 IETF Protocol Alignment ","IMSProtoc16",1,"Rel-16","C1","2018-12-13","2020-03-25",1,"CP-183084",null,"Leis, Peter, Nokia ","peter.leis@nokia.com ","¦14/3/19: 0%->25; 31/5/19: 25%->45; 13/9/19: 45%->65; 6/12/19: 65%->90; 26/3/20: 90%->100; 30/6/20: 99%->100","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ",82,42,null,null,"2018-12-07","2020-06-30"]
[3100,870078,"   (IETF) Location Source Parameter for the SIP Geolocation Header Field (draft-ietf-sipcore-locparam)","5GProtoc16",2,"Rel-16","C1-IETF","2018-12-13","2020-03-25",1,"CP-200146",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","¦14/3/19: 0%->25; 31/5/19: 25%->50; 13/9/19: 50%->65; 6/12/19: 65%->90; 25/3/20: FCD:19/12/2019->03/20; 26/3/20: 90%->98; 30/6/20: 90%->100; 9/4/21: RFC 8787 added;","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 ; RFC 8787",87,44,null,null,"2018-12-07","2021-04-09"]
[3101,820041,"Stage-3 5GS NAS protocol development ","5GProtoc16",1,"Rel-16","C1","2018-12-13","2020-03-25",1,"CP-200146",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 25/3/20: WID:CP-183087->CP-200146","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 ",82,42,null,null,"2018-12-07","2020-03-25"]
[3106,820047,"   Stage-3 SAE Protocol Development for Rel16 for CS Fallback in EPS","SAES16-CSFB",2,"Rel-16","C1","2018-12-13","2019-12-19",1,"CP-183088",null,"Aghili, Behrouz, InterDigital Communications","behrouz.aghili@interdigital.com ","14/3/19: 0%->25; 31/5/19: 25%->50; 30/6/20: 50%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",82,42,null,null,"2018-12-07","2020-06-30"]
[3109,840002,"Service Based Interface Protocol Improvements ","SBIProtoc16",1,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-191060",null,"Yue Song, China Mobile ","songyue (at) chinamobile (dot) com ",null,null,84,43,null,null,"2019-05-31","NA"]
[3111,840053,"   CT4 aspects of SBIProtoc16","SBIProtoc16",2,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-191060",null,"Yue Song, China Mobile ","songyue (at) chinamobile (dot) com ","31/5/19: 0%->10; 6/12/19: 10%->90; 26/3/20: 90%->95; 26/6/20: 95%->100","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.531; 29.540; 29.518; 29.571; 29.572; 29.573",84,43,null,null,"2019-05-31","2020-06-26"]
[3116,850026,"Closed loop SLS Assurance ","COSLA",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190781",null,"Groenendijk, Jan, Ericsson ","jan.groenendijk@ericsson.com ","; 8/10/19: 28.536 added;; 26/3/20: 0%->55; 28/6/20: 55%->100","28.533; 28.540; 28.541; 28.530; 28.531; 28.545; 28.546; 28.550; 28.552; 28.553 ; 28.536; 28.535",85,43,null,null,"2019-09-13","2020-06-28"]
[3120,850034,"Management Aspects of 5G Service-Level Agreement ","MA5SLA",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-200185",null,"Hu, Yushuang, CMCC ","huyushuang@chinamobile.com ","; 25/3/20: WID:SP-190789->SP-200185; 26/3/20: 0%->100","28.540; 28.541 ",85,43,null,null,"2019-09-13","2020-03-26"]
[3124,850054,"   C4 aspects of LOLC ","LOLC",2,"Rel-16","C4","2019-09-19","2020-03-12",1,"CP-200059",null,"Giorgi Gulbani (Huawei) ","giorgi.gulbani@huawei.com ","; 26/3/20: 0%->90; 26/6/20: 90%->100","29.500; 29.510",85,43,null,null,"2019-09-13","2020-06-26"]
[3127,850005,"   C4 aspects of 5GS_OTAF","5GS_OTAF",2,"Rel-16","C4","2019-09-19","2020-03-12",1,"CP-192257",null,"Wiehe, Ulrich, Nokia ","Ulrich.Wiehe@nokia.com ","; 6/12/19: 0%->65; 26/3/20: 65%->100","23.122; 29.503 ; 29.510 ",85,43,null,null,"2019-09-13","2020-03-26"]
[3128,830026,"Integration of ONAP and 3GPP 5G management framework","ONAP3GPP",1,"Rel-16","S5","2019-03-07","2020-03-12",1,"SP-190139",null,"SMITH David K., AT&T ","DS9930@att.com","31/5/19: 0%->10; 13/9/19: 10%->25; 13/9/19: FCD:05/03/2020->03/20; 26/3/20: 25%->100","28.540; 28.622; 28.623; 28.532",83,42,null,null,"2019-03-14","2020-03-26"]
[3133,860023,"5G management capabilities ","5GMNC",1,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191195",null,"CORNILY, Jean-Michel, ORANGE ","jeanmichel.cornily@orange.com ","; 26/3/20: 0%->100",28.532,86,44,null,null,"2019-12-06","2020-03-26"]
[3136,860002,"Nsoraf Service Based Interface ","NSORAF",1,"Rel-16","C4","2019-12-06","2020-03-12",1,"CP-193017",null,"EL MOATAMID, Abdessamad, Orange ","abdessamad.elmoatamid@orange.com. ","; 6/12/19: 0%->5; 26/3/20: 5%->85; 2/7/20: 85%->100","29.503; 29.510 ",86,44,null,null,"2019-12-06","2020-07-02"]
[3139,890045,"UE Conformance Test Aspects - B1C Signal in BDS Positioning System Support for LTE and NR ","B1C_BDS_pos_UEConTest",1,"Rel-16","R5","2020-09-17","2021-09-08",1,"RP-201777",null,"CATT ",null,"tested: REL-16 TEI16 CR set (R2-2000238, R2-2002121, R2-2000240) of RP-200357 and (R4-2008551, R4-2008540) of RP-201055 ; 8/4/21: 0%->71; 2/7/21: FCD:Thu 17/06/->09/21; 29/9/21: 71%->100",null,89,45,null,null,"2020-09-25","2021-09-29"]
[3142,770050,"(Small) Technical Enhancements and Improvements for Rel-16","TEI16",1,"Rel-16",null,"2017-09-11","2020-06-30",0,null,null,null,null,null,null,77,41,null,null,"2015-06-15","2015-06-15"]
[3147,800029,"Stopped - Study on system architecture for next generation real time communication services","FS_NG_RTC",1,"Rel-16","S2","2018-06-06","2019-03-14",1,"SP-180508",null,"Yi Jiang ","jiangyi at chinamobile dot com","03/22: stopped at 0% (\"deprioritised\"in SA2 language)","New",80,41,84,null,"2018-06-06","2022-03-22"]
[3150,780001,"Study on User Plane Protocol in 5GC","FS_UPPS",1,"Rel-16","C4","2017-12-15","2019-06-14",1,"CP-182052",null,"Satoru Matsushima, SoftBank Corp","satoru.matsushima@g.softbank.co.jp","16/3/18: 0%->5¦2/10/18: WID:CP-173160->CP-182052¦2/10/18: FCD:09/18->06/19¦14/3/19: 20%->70; 31/5/19: 70%->90; 14/1/20: 90%->100",29.891999999999999,78,40,null,null,"2017-12-15","2020-01-14"]
[3151,790012,"Stopped - Study on Application Awareness Interworking between LTE and NR","FS_AAI_LTE_NR",1,"Rel-16","S2","2018-03-15","2019-03-14",1,"SP-180122",null,"Biao Long, China Telecom","longb.gd@chinatelecom.cn","7/6/18: 0%->30¦6/8/18: 23.727 added; 03/22: stopped at 30% (\"deprioritised\"in SA2 language)","new; 23.727",79,40,84,null,"2018-03-15","2022-03-22"]
[3155,801001,"Study on radiated metrics and test methodology for the verification of multi-antenna reception performance of NR UEs","FS_NR_MIMO_OTA_test",1,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201069",null,"CAICT",null,"related REL-15 SI FS_NR_test_methods; 23/1/20: 0%->45; 23/1/20: WID:RP-181402->RP-182305; 28/7/20: WID:RP-182305->RP-201069; 28/7/20: 45%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3160,760053,"Study on Long Term Key Update Procedures","FS_LTKUP",1,"Rel-16","S3","2017-06-05","2018-12-14",1,"SP-170413",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","11/9/17: 0%->10¦15/12/17: 10%->70¦15/12/17: FCD:12/17->03/18¦16/3/18: 70%->90¦16/3/18: FCD:03/18->06/18¦7/6/18: FCD:06/18->12/18. 10/9/18: moved from Rel-15 as per SP-180687¦7/12/18: 90%->100","Internal TR",76,39,null,null,"2017-06-03","2018-12-07"]
[3163,830006,"Study on UEs Supporting Handset Mode with Non-Traditional Earpieces","FS_HaNTE",1,"Rel-16","S4","2019-03-07","2019-09-05",1,"SP-190041",null,"Schevciw, Andre, Qualcomm Incorporated","aschevci@qti.qualcomm.com ","31/5/19: 0%->10; 13/9/19: 10%->100","New",83,42,null,null,"2019-03-14","2019-09-13"]
[3166,0,"Release 16 other Studies","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3169,800037,"Stopped - Study on protocol enhancement for real time communication","FS_PROTIMP",1,"Rel-16","S5","2018-06-06","2020-06-12",1,"SP-180597",null,"Olaf Pollakowski, Nokia","olaf.pollakowski@nokia.com","6/8/18: 28.823 added;; 26/3/20: FCD:14/03/2019->06/20; 25/9/20: Stopped, so 0%->100","New; 28.823",80,41,84,null,"2018-06-06","2020-09-25"]
[3174,810029,"Study on management aspects of communication services","FS_CSMAN",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180923",null,"Groenendijk, Jan, Ericsson","jan<dot>Groenendijk<at>ericsson<dot>com.","7/12/18: 0%->40¦14/3/19: 40%->70; 31/5/19: 70%->75; 13/9/19: 75%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[3177,820004,"Study on ambient noise test methodology for evaluation of acoustic UE performance ","FS_ANTeM",1,"Rel-16","S4","2018-12-06","2019-12-12",1,"SP-180986",null,"Jan Reimes, HEAD acoustics GmbH","jan.reimes@head-acoustics.de ","12/3/19: 0%->10; 31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->70; 25/3/20: 70%->100",null,82,42,null,null,"2018-12-07","2020-03-25"]
[3178,800027,"Stopped - Study on supporting Flexible Local Area Data Network","FS_FLADN",1,"Rel-16","S2","2018-06-06","2019-03-14",1,"SP-180506",null,"LG Electronics, ","hyuns.kim@lge.com","10/9/18: FCD:12/18->03/19¦6/6/19: stopped at 0% as per SP-190395","New",80,41,84,null,"2018-06-06","2018-09-10"]
[3182,0,"Release 15 Features on 5G","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3185,720005,"   (Stage 1 of 5G) New Services and Markets Technology Enablers","SMARTER",2,"Rel-15","S1","2016-06-09","2017-03-15",1,"SP-160364",null,"Li, Alice","alice.li@vodafone.com","Resulting from FS_SMARTER¦19/9/16: 0%->55¦6/10/16: 22.261 added¦1/12/16: FCD:09/16->03/20¦1/12/16: 55%->75¦2/3/17: 75%->90¦7/6/17: 90%->100",22.260999999999999,72,37,null,null,"2016-06-09","2017-06-07"]
[3191,770042,"         Study on 5G Network selection","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 10%->55¦15/12/17: 55%->80¦16/3/18: 80%->100",null,77,39,null,null,"2017-03-03","2018-03-16"]
[3193,770044,"         Study on 5G Session management","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 35%->75¦15/12/17: 75%->100",null,77,39,null,null,"2017-03-03","2017-12-15"]
[3196,770047,"         Study on 5G System core network impact on services, network functions and capabilities","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 20%->65¦15/12/17: 65%->85¦16/3/18: 85%->100",null,77,39,null,null,"2017-03-03","2018-03-16"]
[3200,780010,"         5G Mobility management","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->25¦16/3/18: 25%->70¦7/6/18: 70%->95¦10/9/18: 95%->100",null,77,39,null,null,"2017-03-03","2018-09-10"]
[3204,780014,"         5G System core network impact on services, network functions and capabilities","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->10¦16/3/18: 10%->70¦7/6/18: 70%->90¦10/9/18: 90%->100",null,77,39,null,null,"2017-03-03","2018-09-10"]
[3205,780015,"         5G Network slicing","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->10¦16/3/18: 10%->60¦7/6/18: 60%->100",null,77,39,null,null,"2017-03-03","2018-06-07"]
[3209,870080,"      (IETF) Improved Extensible Authentication Protocol Method for 3GPP Mobile Network Authentication and Key Agreement (EAP-AKA') (draft-ietf-emu-rfc5448bis)","5GS_Ph1-CT",3,"Rel-15","C4-IETF","2017-03-03","2017-12-14",1,null,null,null,null,"20/6/22: Compl:80%->100%",null,87,44,null,null,"2017-03-03","2022-06-20"]
[3212,800081,"   UE Conformance Test Aspects – 5G System Non-3GPP Access","5GS_Ph1-CT_n3GPPA-UEConTest",2,"Rel-15","R5","2018-06-15","2019-03-15",1,"RP-181032",null,"Motorola",null,"tested: non-3GPP Access part of REL-15 WI 5GS_Ph1-CT (note: 3GPP Access part of 5GS_Ph1-CT is already covered in REL-15 WI 5GS_NR_LTE-UEConTest);; 26/3/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-03-26"]
[3218,780035,"   Data Charging in 5G System Architecture Phase 1","5GS_Ph1-DCH",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170952",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","16/3/18: 0%->10¦7/6/18: 10%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100",32.24,78,40,null,null,"2017-12-15","2018-09-10"]
[3220,800040,"   Charging for IMS over 5G System Architecture Phase 1","5GS_Ph1_IMSCH",2,"Rel-15","S5","2018-05-07","2018-06-15",1,"SP-180391",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","7/6/18: 0%->100","32.240; 32.260; 32.299; 32.298",80,41,null,null,"2018-06-06","2018-06-07"]
[3224,750036,"   SA3 aspects of EDCE5","EDCE5",2,"Rel-15","S3","2017-03-02","2017-09-14",1,"SP-170233",null,"Adrian Escott, Qualcomm Incorporated",null,"7/6/17: 0%->60¦11/9/17: 60%->70¦15/12/17: 70%->100",null,75,38,null,null,"2017-03-02","2017-12-15"]
[3227,760069,"      CT3 aspects of EDCE5","EDCE5-CT",3,"Rel-15","C3","2017-06-05","2017-12-14",1,"CP-173038",null,"Jesús de Gregorio, Ericsson ","jesus.de.gregorio@ericsson.com",null,"29.212; 29.213; 29.214; 29.215; 29.201",76,39,null,null,"2017-06-05","NA"]
[3231,750167,"   Core part: New Radio Access Technology","NR_newRAT-Core",2,"Rel-15","R1","2017-03-15","2018-12-14",1,"RP-190213","RP-181466","NTT DOCOMO",null,"follow-up WI of REL-14 SI FS_NR_newRAT¦19/6/17: Compl:0%->22%19/6/17: WID: RP-170855->RP-171485¦30/6/17 & 12/6/17: impacted specs added19/9/17: Compl:22%->50%19/9/17: WID: RP-171485->RP-172115¦15/12/17: added: 38.818¦37.865-01-01¦37.834-01-01¦37 .; 2 ","37.340;37.834-01-01;37.863-05-01;37.864-41-21;37.865-01-01;38.101;38.104;38.12?;38.201/2;38.211/2;38.213to215;38.300;38.304to307;38.321to323;38.331;38.401;38.410to414;38.455;38.470to475;38.815;38.817-01-02;38.818; 38.113; 29.413; 37.864-11-22; 38.415; 38.",75,38,null,null,"2017-03-21","2019-06-26"]
[3232,750267,"   Perf. part: New Radio Access Technology","NR_newRAT-Perf",2,"Rel-15","R4","2017-03-15","2019-06-14",1,"RP-191971",null,"NTT DOCOMO",null,"follow-up WI of REL-14 SI FS_NR_newRAT completed at RAN #75¦19/6/17: WID: RP-170855->RP-171485¦12/7/17: 38.133 added;¦12/7/17: 38.141 added;¦19/9/17: WID: RP-171485->RP-172115¦15/12/17: 38.101-4 added¦8/1/18: WID: RP-172115->RP-172834¦27/3/18: W ; 8/ ","38.133; 38.141; 38.101-4; 38.171",75,38,null,null,"2017-03-21","2020-01-14"]
[3236,760087,"UE Conformance Test Aspects - 5G system with NR and LTE","5GS_NR_LTE-UEConTest",1,"Rel-15","R5","2017-06-15","2021-12-14",0.87,"RP-211228",null,"Ericsson",null,"¦19/9/17: Compl:0%->2%¦15/12/17: impacted specs add¦15/12/17: 38.508-2 added;¦ ;; 8/10/19: WID:RP-181206->RP-192123; 8/10/19: 34.229-5 added;; 24/4/20: FCD:14/12/2018->12/20; 24/4/20: 15%->69; 8/10/20: 69%->79; 8/10/20: FCD:15/12/2020->12/20; 7/4/21: W ","38.507-1; 38.533; 38.522; 38.521-1-2-3; 38.508; 38.509; 38.903; 38.905; 38.523-1-2-3; ; 38.508-2; 34.229-5",76,39,null,null,"2017-06-16","2021-07-02"]
[3239,720003,"   Study on Enhancement of 3GPP support for V2X services","FS_eV2X",2,"Rel-15","S1","2016-06-09","2016-12-15",1,"SP-160370",null,"LG Electronics, SungDuck Chun","sungduck.chun@lge.com","19/9/16: 30%->70¦6/10/16: 22.886 added¦1/12/16: 70%->95¦2/3/17: 95%->100",22.885999999999999,72,37,null,null,"2016-06-09","2017-03-02"]
[3245,750262,"   Perf. Part: V2X phase 2 based on LTE","LTE_eV2X-Perf",2,"Rel-15","R4","2017-03-15","2018-12-14",1,"RP-182549",null,"Huawei",null,"follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #7519/6/17: WID: RP-170798->RP-17106919/9/17: WID: RP-171069->RP-171740¦27/6/18: Compl:0%->5%¦16/1/19: 5%->100¦16/1/19: WID:RP-171740->RP-182549",null,75,38,null,null,"2017-03-21","2019-01-16"]
[3247,0,"Release 15 Features on Ultra/Highly Reliable Low Latency Communication","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3251,750261,"   Perf. part: Highly Reliable Low Latency Communication for LTE","LTE_HRLLC-Perf",2,"Rel-15","R4","2017-03-15","2018-12-15",0,"RP-181259",null,"Ericsson",null,"¦19/6/17: WID: RP-170796->RP-171489¦8/1/18: WID: RP-171489->RP-172845¦27/6/18: WID: RP-172845->RP-181259",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3254,720058,"Study on MC Communication Interworking between LTE and non-LTE Systems","FS_MCCI",1,"Rel-15","S6","2016-06-13","2017-06-12",1,"SP-160881",null,"Monnes, Peter (Harris Corp.)",null,"28/7/16: 23.782 added¦19/9/16: WID:SP-160341->SP-160527¦19/9/16: 0%->20¦1/12/16: WID:SP-160527->SP-160881¦1/12/16: 20%->22¦9/12/16: FCD:12/16->06/17, Rel-14->Rel-15¦3/3/17: 22%->50¦7/6/17: 50%->90¦11/9/17: 90%->100","New 23.782",72,37,null,null,"2016-06-13","2017-09-11"]
[3258,750021,"Enhancements to MCPTT functional architecture and information flows ","enhMCPTT",1,"Rel-15",null,"2017-03-03","2018-06-15",1,"SP-170248",null,"Dom Lazara, Motorola Solutions","dom.lazara@motorolasolutions.com","21/3/17: impacted TS/TR added¦7/6/17: 0%->25","23.280 + 23.379",75,38,null,null,"2017-03-03","2017-06-07"]
[3259,770008,"   Stage 2 of enhMCPTT","enhMCPTT",2,"Rel-15","S6","2017-03-03","2017-12-14",1,"SP-170248",null,"Dom Lazara, Motorola Solutions","dom.lazara@motorolasolutions.com","21/3/17: impacted TS/TR added¦7/6/17: 0%->25¦11/9/17: 25%->45¦15/12/17: 45%->100","23.280 + 23.379",75,38,null,null,"2017-03-03","2017-12-15"]
[3263,770011,"   Stage 3 of eMCData","eMCData-CT",2,"Rel-15","C1","2017-09-08","2018-06-15",1,"CP-172146",null,"HASON, Baruh","Baruh.Hason@motorolasolutions.com","20/3/18: 0%->30¦7/6/18: 30%->85¦10/12/18: 85%->100","24.282; 24.582; 24.481; 24.483; 24.484",77,39,null,null,"2017-03-03","2018-12-10"]
[3267,770014,"      CT1 aspects of eMCVideo","eMCVideo-CT",3,"Rel-15","C1","2017-09-08","2018-06-15",1,"CP-181084",null,"WEI, Haitao","weihaitao@huawei.com","20/3/18: 0%->25¦7/6/18: 25%->100¦12/6/18: 100%->99¦10/9/18: 99%->100","24.281; 24.581; 24.481; 24.483; 24.484",77,39,null,null,"2017-06-03","2018-09-10"]
[3270,760067,"MC Security Enhancements","eMCSec",1,"Rel-15","S3","2017-06-05","2018-06-15",1,"SP-170415",null,"Haigh, Peter, NCSC",null,"15/12/17: 0%->80¦15/12/17: FCD:12/17->03/18¦21/12/17: FCD:03/18->05/18. Exception in SP-171056¦16/3/18: 80%->90¦16/3/18: FCD:05/18->06/18¦7/6/18: 90%->100",33.18,76,39,null,null,"2017-06-07","2018-06-07"]
[3272,800043,"   Stage 2 for MBMS_Mcservices","MBMS_Mcservices",2,"Rel-15","S6","2017-03-03","2017-12-15",1,"SP-170686",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","21/3/17: impacted TS/TR added¦7/6/17: 0%->45¦8/9/17: WID:SP-170075->SP-170686¦8/9/17: FCD:09/17->12/17¦11/9/17: 45%->70¦15/12/17: 70%->95¦16/3/18: 95%->100","23.280 + 23.281 + 23.282 + 23.379",75,38,null,null,"2017-03-03","2018-03-16"]
[3278,730050,"Battery Efficient Security for very low Throughput MTC Devices","BEST_MTC_Sec",1,"Rel-15","S3","2016-09-19","2018-03-15",1,"SP-160569",null,"Evans, Tim, VODAFONE Group Plc.",null,"6/10/16: 33.163 added 6/3/17: FCD:12/16->09/17¦6/3/17: 0%->20. Moved from Rel-14.¦7/6/17: 20%->95¦15/12/17: FCD:09/17->03/18¦16/3/18: 95%->100","33.401; 43.020; 33.220; 33.163",73,37,null,null,"2016-09-19","2018-03-16"]
[3281,750159,"   Core part: Even further enhanced MTC for LTE","LTE_eMTC4-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",1,"RP-172811","RP-181213","Ericsson",null,"WI LTE_feMTC-Core got a 3 months exception granted by RAN #75 to complete in REL-14¦note: RAN #75 approved WID RP-170732 with working agreement¦19/6/17: Compl:0%- 19/9/ 8/1 2 ;¦16/1/19: 97%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[3285,750166,"   Core part: Further NB-IoT enhancements","NB_IOTenh2-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.95,"RP-182389","RP-180851","Huawei",null,"follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76¦note: RAN #75 approved WID RP-170852 with working agreement;1 8/1/12 ;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3286,750266,"   Perf. part: Further NB-IoT enhancements","NB_IOTenh2-Perf",2,"Rel-15","R4","2017-03-15","2018-12-14",1,"RP-182389",null,"Huawei",null,"follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76¦note: RAN #75 approved WID RP-170852 with working agreement¦8/1 ;¦26/3/19: 30%->100",null,75,38,null,null,"2017-03-21","2019-03-26"]
[{"$f":"A3290+1","v":3290},740003,"   Stage 1 of ProSe_WLAN_DD","ProSe_WLAN_DD",2,"Rel-15","S1","2016-11-15","2016-12-15",1,"SP-160957",null,"Intel Corporation; Ana Lucia Pinheiro","ana.lucia.a.pinheiro@intel.com","1/12/16: 0%->100",22.277999999999999,74,38,null,null,"2016-12-01","2016-12-01"]
[3294,760028,"      CT4 aspects of ProSe_WLAN_DD","ProSe_WLAN_DD_Stage3",3,"Rel-15","C4","2017-06-02","2017-12-06",1,"CP-173084",null,"Intel, Vivek Gupta ","vivek.g.gupta@intel.com","15/12/17: 0%->100","29.345; 29.230; 23.008",76,39,null,null,"2017-06-02","2017-12-15"]
[3297,720082,"   Study on Complementary Features for Voice services over WLAN","FS_VoWLAN",2,"Rel-15","S2","2016-06-13","2017-03-15",1,"SP-160506",null,"Nokia (Nicolas Drevon","nicolas.drevon@nokia.com","28/7/16: 23.751 added¦19/9/16: 0%->10., 7/12/16: moved from Rel-14, according to SP-160806¦6/3/17: 10%->80¦7/6/17: 80%->100",23.751000000000001,72,37,null,null,"2016-06-17","2017-06-07"]
[3299,760022,"   CT aspects of VoWLAN","VoWLAN-CT",2,"Rel-15","ct","2017-06-02","2018-06-14",1,"CP-181083",null,"Jennifer Liu (Nokia)","Jennifer.Liu at nokia.com","7/6/18: WID:CP-171101->CP-181083",null,76,39,null,null,"2017-06-02","2018-06-07"]
[3305,770030,"Study on 3GPP codecs for VR audio","FS_CODVRA",1,"Rel-15","S4","2017-09-08","2017-12-15",1,"SP-170617",null,"Toftgård, Tomas, Ericsson","tomas.toftgard@ericsson.com ","15/12/17: 0%->100¦15/12/17: FCD:09/17->12/17",26.917999999999999,77,39,null,null,"2017-09-08","2017-12-15"]
[3308,770025,"Virtual Reality Profiles for Streaming Media","VRStream",1,"Rel-15","S4","2017-09-08","2018-09-14",1,"SP-180893",null,"Thomas Stockhammer, Qualcomm Incorporated","tsto@qti.qualcomm.com","15/12/17: 26.118 added;¦15/12/17: 0%->25¦16/3/18: 25%->40¦7/6/18: 40%->60¦7/6/18: FCD:06/18->09/18¦10/9/18: 60%->100¦2/10/18: WID:SP-170612->SP-180893","26.118; 26.818; 26.247; 26.346; 26.234",77,39,null,null,"2017-09-08","2018-10-02"]
[3312,790018,"Charging aspects of WLAN access in EPC","WAEPC_CH",1,"Rel-15","S5","2018-03-15","2018-06-15",1,"SP-180078",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","7/6/18: 0%->100","32.251; 32.260; 32.299; 32.298",79,40,null,null,"2018-03-15","2018-06-07"]
[3313,790020,"FEC and ROHC Activation for GCSE over MBMS","FRASE",1,"Rel-15","S4","2018-03-15","2018-09-14",1,"SP-180206",null,"Bouazizi, Imed, Samsung Electronics Co., Ltd","i.bouazizi@samsung.com.","7/6/18: 0%->30¦7/6/18: FCD:06/18->09/18¦10/9/18: 30%->100","26.346; new",79,40,null,null,"2018-03-15","2018-09-10"]
[3316,790026,"   CT1 aspects of bSRVCC_MT","bSRVCC_MT",2,"Rel-15","C1","2018-03-15","2018-06-14",1,"CP-180153",null,"Song Yue (China Mobile)","songyue (at) chinamobile (dot) com","16/3/18: 0%->80¦7/6/18: 80%->100","24.237; 24.008",79,40,null,null,"2018-03-16","2018-06-07"]
[3321,790037,"      CT1 aspects of INOBEAR","INOBEAR-CT",3,"Rel-15","C1","2018-03-16","2018-06-15",1,"CP-180098",null,"Samsung, Lalith Kumar ","lalith.kumar@samsung.com","7/6/18: 0%->100","24.301; 24.007",79,40,null,null,"2017-12-15","2018-06-07"]
[3324,780170,"   Core part: Increased number of E-UTRAN data bearers","INOBEARRAN-Core",2,"Rel-15","R2","2017-12-15","2018-09-14",0.99,"RP-180569",null,"Samsung",null,"27/3/18: WID: RP-172835->RP-180569¦27/6/18: Compl:0%->99%¦27/6/18:",null,78,40,null,null,"2018-01-08","2018-06-27"]
[3327,750017,"   Study on security aspects of enhancements to ProSe UE-to-Network Relay","FS_REAR_Sec",2,"Rel-15","S3","2017-03-02","2018-06-15",1,"SP-170270",null,null,"lihe2@huawei.com","7/6/17: 0%->15¦11/9/17: 15%->50¦15/12/17: 50%->79¦16/3/18: 79%->99¦16/3/18: FCD:03/18->06/18¦7/6/18: 99%->100",null,75,38,null,null,"2017-03-02","2018-06-07"]
[3330,780026,"   Stage 2 of eVoLP","eVoLP",2,"Rel-15","S2","2017-10-12","2017-12-15",1,"SP-170935",null,"Xiaobo Wu, Huawei","wuxiaobo@ huawei.com",null,"23.401; 23.203",78,40,null,null,"2017-12-15","NA"]
[3335,740006,"      S2 aspects of FS_eVoLP","FS_eVoLP",3,"Rel-15","S2","2016-12-01","2017-09-14",1,"SP-160833",null,"Xiaobo Wu ",null,"1/12/16: 0%->5¦6/3/17: 5%->50¦7/6/17: 50%->60¦11/9/17: 60%->100¦15/12/17: rapporteur changed",23.759,74,38,null,null,"2016-12-01","2017-12-15"]
[3339,770006,"   Stage 1 of USOS","USOS",2,"Rel-15","S1","2016-02-01","2016-03-01",1,"SP-160117","SP-170526","Edward Hall, Qualcomm Incorporated","edhall@qti.qualcomm.com",null,"22.101; 22.115",71,36,null,null,"2016-03-01","2016-03-01"]
[3340,770036,"   Stage 2 of USOS","USOS",2,"Rel-15","S2","2017-09-08","2017-12-15",1,"SP-170740",null,"Haris Zisimopoulos ","harisz@qti.qualcomm.com","15/12/17: 0%->100","23.401; 23.203",77,39,null,null,"2017-09-08","2017-12-15"]
[3343,720004,"   Study on Future Railway Mobile Communication System","FS_FRMCS",2,"Rel-15","S1","2016-06-09","2017-06-15",1,"SP-170166",null,"Merkel, Juergen","Merkel, Juergen - Nokia Networks","19/9/16: 0%->25¦6/10/16: 22.989 added¦1/12/16: 25%->40¦1/12/16: WID:SP-160371->SP-160903¦9/12/16: FCD:12/16->3/201. WID was in SP-160903¦2/3/17: 40%->80¦2/3/17: FCD:03/17->06/17¦7/6/17: 80%->100",22.989000000000001,72,37,null,null,"2016-06-09","2017-06-07"]
[3348,790032,"      CT1 aspects of MONASTERY","MONASTERY",3,"Rel-15","C1","2018-03-16","2018-06-15",1,"CP-182202",null,"Leis, Peter (Nokia) ","peter(dot)leis(at)nokia(dot)com ","16/3/18: 0%->40¦7/6/18: 40%->85¦10/9/18: 85%->100","24.379; 24.380; 24.481; 24.483; 24.484",79,40,null,null,"2018-03-16","2018-09-10"]
[3351,790013,"   Security Architecture of MONASTERY","MONASTERY_SEC",2,"Rel-15","S3","2018-01-11","2018-03-16",1,"SP-180052",null,"Woodward, Tim, Motorola Solutions",null,"16/3/18: 0%->100",33.18,79,40,null,null,"2018-03-15","2018-03-16"]
[{"$f":"A3354+1","v":3354},760031,"   Stage 3 of PS Data Off Phase 2 ","PS_DATA_OFF2-CT",2,"Rel-15","ct","2017-06-02","2018-06-14",1,"CP-181082",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","18/12/17: WID:CP-171104->CP-173162¦7/6/18: WID:CP-173162->CP-181082",null,76,39,null,null,"2017-06-02","2018-06-07"]
[3357,760034,"      CT6 aspects of PS Data Off Phase 2 ","PS_DATA_OFF2-CT",3,"Rel-15","C6","2017-06-02","2018-06-14",1,"CP-181082",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/6/18: 0%->100","31.102; 31.103; 31.111",76,39,null,null,"2017-06-02","2018-06-07"]
[3362,780007,"      CT4 aspects of NAPS","NAPS-CT",3,"Rel-15","C4","2017-06-02","2018-06-14",1,"CP-173112",null,"Yan, Yali, Huawei, ","yanyali@huawei.com","7/6/18: 95%->100",null,78,40,null,null,"2017-06-02","2018-06-07"]
[3363,770032,"   Security aspects of NAPS","NAPS-Sec",2,"Rel-15","S3","2017-09-08","2018-03-16",1,"SP-170635",null,"Zhao, Xuwen, Huawei","zhaoxuwen@huawei.com ","15/12/17: 0%->60¦16/3/18: 60%->100",33.186999999999998,77,39,null,null,"2017-09-08","2018-03-16"]
[3366,750031,"   Study on CAPIF","FS_CAPIF",2,"Rel-15","S6","2017-03-10","2017-09-14",1,"SP-170405",null,"Suresh Chitturi, Samsung","s.chitturi@samsung.com","21/3/17: added impacted TR¦7/6/17: 0%->35¦8/6/17: WID:SP-170279->SP-170405¦11/9/17: 35%->70¦15/12/17: 70%->100","new 23.722",75,38,null,null,"2017-03-10","2017-12-15"]
[3370,760066,"Management and orchestration of 5G networks and network slicing ","NETSLICE",1,"Rel-15","S5","2016-06-13","2018-09-14",1,"SP-180816",null,"Jan Groenendijk, Ericsson","jan<dot>groenendijk<at>ericsson<dot>com","21/12/17: WID:SP-170586->SP-170960. Name changed from \"Management of Network Slicing in Mobile Networks, Concepts, Use cases and Requirements\"¦27/3/18: 32.159 added;¦6/8/18: 32.159 added;¦8/8/18: WID:SP-170960->SP 180124¦2/10/18: WID:SP 180124->SP- ","32.101; 32.103; new; 32.159; 32.159",76,39,null,null,"2017-06-05","2018-10-02"]
[3374,760065,"   Provisioning of network slicing for 5G networks and services","NETSLICE-PRO_NS",2,"Rel-15","S5","2017-06-05","2018-09-14",1,"SP-180818",null,"Zhang Kai, Huawei","kai.zhangkai@huawei.com","15/12/17: 0%->15¦21/12/17: WID:SP-170580->SP-170955¦16/3/18: 15%->40¦27/3/18: 28.532 added;¦7/6/18: 40%->80¦7/6/18: FCD:06/18->09/18¦10/9/18: 80%->100¦2/10/18: WID:SP-170955->SP-180818",28.530999999999999,76,39,null,null,"2017-06-05","2018-10-02"]
[3379,810009,"   CT aspects of 5G Trace management ","NETSLICE-5GTRACE-CT",2,"Rel-15","ct","2018-09-06","2018-09-06",1,"CP-182051",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,81,41,null,null,"2018-09-06","NA"]
[3381,810043,"      CT4 aspects of 5G Trace management ","NETSLICE-5GTRACE-CT",3,"Rel-15","C4","2018-09-06","2018-09-06",1,"CP-182051",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com","10/9/18: 0%->100","29.502; 29.503; 29.505; 29.509; 29.518; 29.540; 29.571; 29.244; 29.274",81,41,null,null,"2018-09-06","2018-09-10"]
[3384,780017,"   Study on Policy and Charging for Volume Based Charging","FS_PC_VBC",2,"Rel-15","C3","2016-12-01","2017-12-15",1,"CP-172135",null,"Huang, Zhenning, China Mobile","huangzhenning <at> chinamobile <dot> com","6/3/17: 0%->30¦21/3/17: 29.827 added;¦5/6/17: 30%->60¦8/9/17: WID:CP-160822->CP-172058¦11/9/17: FCD:06/17->12/17",29.827000000000002,74,38,null,null,"2016-12-01","2017-09-11"]
[3389,760037,"Framework for Live Uplink Streaming ","FLUS",1,"Rel-15","S4","2017-06-05","2018-06-14",1,"SP-170824",null,"Park, Kyungmo, SK Telecom","kyungmo.park@sk.com","30/6/17: 26.238 added;¦11/9/17: 0%->10¦15/12/17: 10%->85¦15/12/17: FCD:12/17->06/18¦21/12/17: WID:SP-170576->SP-170824¦16/3/18: 85%->90¦7/6/18: 90%->100","New TS; 26.238",76,39,null,null,"2017-06-03","2018-06-07"]
[3390,770034,"Self-Organizing Networks (SON) for Active Antenna System (AAS) deployment management","OAM_SON_AAS",1,"Rel-15","S5","2017-09-08","2018-06-15",1,"SP-170658",null,"Nokia (Weixing Wang)","weixing.wang@nokia-sbell.com","15/12/17: 0%->80¦10/9/18: 80%->100","28.627; 28.628; 28.629; 28.658; 28.659",77,39,null,null,"2017-09-08","2018-09-10"]
[3393,780036,"Management Enhancement for EPC CUPS ","ME_CUPS",1,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170954",null,"Huawei (ZHU, Lei","lei.zhu@huawei.com","ASN.1-type of WID, hence later than St3, indpt of CUPS Rel-14¦16/3/18: 0%->5¦7/6/18: 5%->60¦10/9/18: 60%->100","32.426; 32.455; 28.658; 28.707; 28.708; 28.709",78,40,null,null,"2017-12-15","2018-09-10"]
[3397,760013,"   CT aspects of eCNAM","eCNAM-CT",2,"Rel-15","ct","2017-06-02","2018-03-14",1,"CP-171181",null,"Mowafy, Hala. Ericsson","hala.mowafy@ericsson.com",null,null,76,39,null,null,"2017-06-02","NA"]
[3401,760016,"Stage-3 SAE Protocol Development - Phase 6","SAES6",1,"Rel-15","C1","2017-06-02","2018-06-18",1,"CP-171100",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com",null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368",76,39,null,null,"2016-03-02","NA"]
[3406,720075,"Security Assurance Specification for PGW network product class","SCAS_PGW",1,"Rel-15","S3","2016-06-17","2017-12-12",1,"SP-160481",null,"Peng Jin, China Mobile","pengjin@chinamobile.com","28/7/16: 33.250 added¦19/9/16: 0%->10¦6/10/16: 33.216 added¦1/12/16: 10%->40. 06/03/17: moved from Rel-14.¦6/3/17: 40%->80¦7/6/17: FCD:06/17->12/17¦7/6/17: 80%->95¦11/9/17: 95%->100","33.250; 33.216",72,37,null,null,"2016-06-17","2017-09-11"]
[3409,760009,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc9",2,"Rel-15","C1","2017-06-02","2018-06-13",1,"CP-171098",null,"Dr. Belling, Thomas, Nokia","Thomas.Belling@nokia.com","14/9/17: 0%->40¦15/12/17: 40%->60¦16/3/18: 60%->80¦7/6/18: 80%->100","23.218; 24.229; 24.930",76,39,null,null,"2014-12-04","2018-06-07"]
[3412,780048,"      (IETF) P-Visited-Network header updated (was: draft-jesske-update-p-visited-network )","IMSProtoc9",3,"Rel-15","C1-IETF","2017-06-02","2018-06-15",1,null,null,"Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de","27/6/18: 0%->100",null,78,40,null,null,"2017-12-18","2018-06-27"]
[3415,750014,"Lawful Interception Rel-15","LI15",1,"Rel-15",null,"2017-03-02","2019-03-12",1,"SP-170839",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","21/12/17: WID:SP-170039->SP-170839¦16/3/18: 10%->20",null,75,38,null,null,"2016-07-27","2018-03-16"]
[3417,750013,"   Normative work on Lawful Interception Rel-15","LI15",2,"Rel-15","S3LI","2017-03-02","2019-03-12",1,"SP-170839",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","12/7/17: 0%->5¦15/12/17: 5%->10¦10/9/18: 17%->40¦7/12/18: FCD:12/18->03/19¦7/12/18: 40%->75¦20/3/19: 75%->80; 31/5/19: 80%->100",null,75,38,null,null,"2016-07-27","2019-05-31"]
[3420,760055,"Control and monitoring of Power, Energy and Environmental (PEE) parameters in Radio Access Networks (RAN)","PEE_CMON",1,"Rel-15","S5","2017-06-05","2018-03-15",1,"SP-170479",null,"Jean-Michel CORNILY, ORANGE",null,"30/6/17: 28.306 added;¦30/6/17: 28.305 added;¦30/6/17: 28.304 added;¦11/9/17: 0%->20¦15/12/17: 20%->80¦16/3/18: 80%->100","New TSs; 52.402; 32.405; 32.425; 32.101; 32.103; 28.306; 28.305; 28.304",76,39,null,null,"2017-06-03","2018-03-16"]
[3424,760057,"Charging for enhancement to Flexible Mobile Service Steering (eFMSS) ","eFMSS_CH",1,"Rel-15","S5","2017-06-05","2017-12-14",1,"SP-170482",null,"Long,Biao, China Telecom","longb.gd@chinatelecom.cn. ","11/9/17: 0%->70¦15/12/17: 70%->100","32.251; 32.298; 32.299",76,39,null,null,"2017-06-03","2017-12-15"]
[3428,730057,"   Study on a RESTful HTTP-based Solution Set","FS_OAM_RESTFUL",2,"Rel-15","S5","2016-09-19","2017-12-12",1,"SP-160613",null,"Nokia: Pollakowski, Olaf","olaf.pollakowski@nokia.com","6/10/16: 32.866 added¦1/12/16: 0%->5¦7/6/17: 5%->45¦7/6/17: FCD:06/17->12/17¦11/9/17: 45%->80¦15/12/17: 80%->100",32.866,73,37,null,null,"2016-09-19","2017-12-15"]
[3433,790028,"Enhancements to Call spoofing functionality ","eSPECTRE",1,"Rel-15","C1","2018-03-15","2019-03-07",1,"CP-180096",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com",null,null,79,41,null,null,"2018-03-16","NA"]
[3436,870073,"   (IETF) PASSporT Extension for Diverted Calls (draft-ietf-stir-passport-divert) ","eSPECTRE",2,"Rel-15","C1-IETF","2019-03-07","2019-03-07",1,null,null,null,null,"9/4/21: RFC 8946 added;","RFC 8946",87,44,null,null,"2020-04-23","2021-04-09"]
[3439,800102,"   (IETF) The Transport Layer Security (TLS) Protocol Version 1.3 (draft-ietf-tls-tls13)","TEI15",2,"Rel-15","S3-IETF","2017-03-17","2018-06-15",1,null,null,null,null,"26/6/19: 25%->100; 9/4/21: RFC 8446 added;","RFC 8446",80,41,null,null,"2018-06-27","2021-04-09"]
[3442,770067,"UL data compression in LTE ","LTE_UDC",1,"Rel-15","R2","2000-01-03","2019-03-15",0.99,"RP-172076",null,"CATT",null,null,null,77,39,null,null,"2017-09-19","NA"]
[3444,800080,"   UE Conformance Test Aspects - UL Data Compression in LTE","LTE_UDC-UEConTest",2,"Rel-15","R5","2018-06-15","2019-03-15",1,"RP-190311",null,"CATT",null,"tested: REL-15 WI LTE_UDC-Core¦26/3/19: WID:RP-180918->RP-190311¦26/3/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-03-26"]
[3447,770268,"   Perf. part:LTE Advanced inter-band CA (4DL/4UL) of Band 41C and Band 42C","LTE_CA_4DL4UL_B41_B41_B42_B42-Perf",2,"Rel-15","R4","2017-09-15","2018-03-15",1,"RP-180151",null,"KDDI",null,"¦27/3/18: Compl:0%->100%;",null,77,39,null,null,"2017-09-19","2018-03-27"]
[3451,780066,"   UE Conformance Test aspects - LTE bands with UE category M1 and/or NB1 in Rel-15","LTE_bands_R15_M1_NB1-UEConTest",2,"Rel-15","R5","2017-12-15","2018-06-15",1,"RP-172713",null,"Ericsson",null,"tested: REL-15 WI LTE_bands_R15_M1_NB1-Core27/3/ ;",null,78,40,null,null,"2018-01-08","2018-06-27"]
[3455,770271,"   Perf. part: Extended-Band12 new E-UTRA Band","Ext_B12_LTE-Perf",2,"Rel-15","R4","2017-09-15","2018-03-15",1,"RP-180159",null,"Ericsson",null,"¦8/1/18: WID: RP-172111->RP-17262527/3/18: Compl:0%->100%",null,77,39,null,null,"2017-09-19","2018-03-27"]
[3458,710173,"   Stopped - Core part: Signalling reduction to enable light connection for LTE","LTE_LIGHT_CON-Core",2,"Rel-15","R2","2016-03-15","2018-03-15",1,"RP-171459",null,"Huawei",null,"no Perf. part¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/12/16->Wed 15/03/17¦1/7/16: WID: RP-160540->RP-16093726/9/16: Compl:10%->30%¦20/12/16: Compl:30%->75%¦20/12/16: Stat Rep: --> 21/3/17: Compl:75%->79% 21/3/17: CD:W ¦27/6/",null,71,36,80,null,"2016-03-22","2018-06-27"]
[3460,740045,"   Stopped - Stage 3 of LTE_LIGHT_CON","LTE_LIGHT_CON-CT",2,"Rel-15","ct","2016-12-01","2017-03-14",1,"CP-160703",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,74,38,80,null,"2016-12-01","NA"]
[3466,710274,"   Perf. part: Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS)","AASenh_BS_LTE_UTRA-Perf",2,"Rel-15","R4","2016-03-15","2018-09-14",0.5,"RP-181297",null,"Huawei",null,"1/7/16: WID: RP-160548->RP-1609401/7/16: Release: Rel-15->Rel-14¦26/9/16: WID: RP-160940->RP-161668 20/12/16: Stat Rep: -->¦21/3/17: Compl:0%->10%;",null,71,36,null,null,"2016-03-22","2018-06-27"]
[3469,720291,"   Perf. part: Shortened TTI and processing time for LTE","LTE_sTTIandPT-Perf",2,"Rel-15","R4","2016-09-14","2018-09-14",1,"RP-171468",null,"Ericsson",null,"¦26/9/16: WID: RP-161299->RP-161922¦20/12/16: WID: RP-161922->RP-16201421/3/17: WID: RP-162014->RP-170113¦19/6/17: CD:Thu 15/03/18->Fri 15/06/1827/3/18: Compl:0%->33%¦27/6/18: Compl:33%->60%¦26/3/19: 60%->100",null,72,37,null,null,"2016-07-01","2019-03-26"]
[3471,740072,"450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe","LTE450_Europe_PPDR",1,"Rel-15",null,"2016-12-15","2018-03-15",1,"RP-162514",null,"Airbus",null,"21/3/17: 36.748 added;",36.747999999999998,74,38,null,null,"2016-12-20","2017-03-21"]
[3474,770065,"   UE Conformance Test Aspects - 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe (Band 72)","LTE450_Europe_PPDR-UEConTest",2,"Rel-15","R5","2017-09-15","2018-03-15",1,"RP-180528",null,"Airbus",null,"¦8/1/18: Compl:0%->77%¦27/3/18: Compl:77%->100%;",null,77,39,null,null,"2017-09-19","2018-03-27"]
[3478,770066,"   UE Conformance Test Aspects - E-UTRA 700MHz in Europe for Broadband-PPDR","LTE700_Europe_PPDR-UEConTest",2,"Rel-15","R5","2017-09-15","2018-03-15",1,"RP-180529",null,"Airbus",null,"¦8/1/18: Compl:0%->64%27/3/18: Compl:64%->100%;",null,77,39,null,null,"2017-09-19","2018-03-27"]
[{"$f":"A3482+1","v":3482},780062,"   UE Conformance Test Aspects - FDD operating band in the L-band for LTE","LTE_FDD_L_band-UEConTest",2,"Rel-15","R5","2017-12-15","2018-09-14",1,"RP-180145",null,"NTT DOCOMO",null,"tested: REL-15 WI LTE_FDD_L_Band-Core27/3/18: Compl: ;; 11/10/20: 60%->100",null,78,40,null,null,"2018-01-08","2020-10-11"]
[3485,740276,"   Perf. part: LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20","LTE_SDL_1500ext-Perf",2,"Rel-15","R4","2017-03-17","2017-09-15",1,"RP-171389",null,"Qualcomm",null,"¦19/6/17: CD:Thu 15/06/17->Fri 15/09/17 19/9/17: Compl:0%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[3487,740177,"   Core part: Add UE Power Class 2 to band 41 intra-band contiguous LTE CA","LTE_CA_C_B41_PC2-Core",2,"Rel-15","R4","2016-12-15","2017-12-15",1,"RP-172295",null,"Sprint",null,"21/3/17: Compl:0%->5%¦19/6/17: Compl:5%->50%¦19/9/17: Compl:50%->90%¦8/1/18: Compl:90%->100%;",null,74,38,null,null,"2016-12-20","2018-01-08"]
[3493,740280,"   Perf. part: TDD operating band in the L-band for LTE","LTE_TDD_L_Band-Perf",2,"Rel-15","R4","2017-03-17","2017-09-15",1,"RP-170304",null,"Huawei",null,"21/3/17: WID: RP-162557->RP-170304¦19/6/17: CD:Thu 15/06/17->Fri 15/09/17¦19/9/17: Compl:0%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[3496,750260,"   Perf. part: Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE","feCOMP_LTE-Perf",2,"Rel-15","R4","2017-03-15","2018-06-15",1,"RP-180584",null,"Intel",null,"follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #7519/6/17: WID: RP-170750->RP-171031¦8/1/18: Compl:0%->65%¦8/1/18: CD:Thu 15/03/18->Fri 15/06/1827/3/18: Compl:65%->80%27/3/ ¦27/6/18: Compl:80%->100%",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3500,750064,"Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL","LTE_1024QAM_DL",1,"Rel-15","R1","2016-09-14","2018-12-14",0.99,"RP-171067",null,"Huawei",null,"14/9/17: WID:RP-170838->RP-171067",null,75,38,null,null,"2017-03-21","2017-09-14"]
[3501,750164,"   Core part: Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL","LTE_1024QAM_DL-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.99,"RP-171740","RP-180854","Huawei",null,"¦19/6/17: Compl:0%->20%¦19/6/17: CD:Sat 15/12/18->Thu 15/03/18 19/6/17: FCD:03/18->06/18¦12/7/17: 36.783 added;19/9/17: Compl:20%->40%¦8/1/18: Compl:40%->85%27/3/18: Compl:85%->99%",36.783000000000001,75,38,null,null,"2017-03-21","2018-06-27"]
[3505,750265,"   Perf. part: Enhancements to LTE operation in unlicensed spectrum","LTE_unlic-Perf",2,"Rel-15","R4","2017-12-14","2018-12-14",1,"RP-180402",null,"Nokia",null,"19/6/17: CD:Thu 15/03/18->Sat 15/12/18¦8/1/18: WID: RP-170848->RP-17284127/3/18: WID: RP-172841->RP-180402¦16/1/19: 0%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[3509,750170,"   Core part:Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN","LTE_QMC_Streaming-Core",2,"Rel-15","R2","2017-03-15","2018-09-14",0.99,"RP-170956","RP-172192","China Unicom",null,"compare REL-14 WI UMTS_QMC_Streaming-Core¦19/6/17: Compl:0%->25%¦19/6/17: WID: RP- 19/9/17: Compl:25%->45%¦8/1/18: Compl:45%->99%¦ ¦27/6/18: CD:Fri 15/06/18->Sat 15/09/18",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3512,750171,"   Core part: Enhancing LTE CA Utilization","LTE_euCA-Core",2,"Rel-15","R2","2017-03-15","2018-09-14",0.9,"RP-180561","RP-181069","Nokia",null,"19/9/17: Compl:0%->22%¦8/1/18: Compl:22%->40%¦16/3/18: FCD:12/17->06/1827/3/18: Compl:40%->60%27/3/18: WID: RP-170805->RP-180561¦27/6/18: Compl:60%->90%;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3514,820066,"   UE Conformance Test Aspects - Enhancing LTE CA Utilization","LTE_euCA-UEConTest",2,"Rel-15","R5","2018-12-15","2021-09-08",1,"RP-182619",null,"Nokia",null,"tested: REL-15 WI LTE_euCA-Core; 8/10/20: 0%->35; 8/10/20: FCD:15/12/2019->12/20; 8/4/21: 0%->56; 8/4/21: FCD:12/12/2020->09/20; 2/7/21: 0%->82; 29/9/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-09-29"]
[3520,750174,"   Core part: US 600 MHz Band for LTE","LTE600_US-Core",2,"Rel-15","R4","2017-03-15","2017-09-15",1,"RP-171142",null,"Ericsson",null,"¦19/6/17: Compl:0%->95%¦19 12/7/17: 36.755 added;19/9/17: Compl:95%->100%",36.755000000000003,75,38,null,null,"2017-03-21","2017-09-19"]
[3521,750274,"   Perf. part: US 600 MHz Band for LTE","LTE600_US-Perf",2,"Rel-15","R4","2017-03-15","2017-09-15",1,"RP-171142",null,"Ericsson",null,"¦19/6/17: Compl:0%->95%¦19 19/9/17: Compl:95%->100%",null,75,38,null,null,"2017-03-21","2017-09-19"]
[3527,760197,"   Core part: Introduction new band support for 4Rx antenna ports for LTE for REL-15","LTE_4Rx_AP_DL_bands_R15-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180073",null,"Huawei",null,"19/9/17: Compl:0%->99%¦8/1/18: WID: RP-171131->RP-17234727/3/18: Compl:99%->90% ¦27/6/18: Compl:90%->100%",null,76,39,null,null,"2017-06-16","2018-06-27"]
[3528,760297,"   Perf. part: Introduction new band support for 4Rx antenna ports for LTE for REL-15","LTE_4Rx_AP_DL_bands_R15-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180073",null,"Huawei",null,"¦8/1/18: WID: RP-171131->RP-172347¦27/3/18: WID: RP-172347->RP-180073¦27/6/18: Compl:0%->100%",null,76,39,null,null,"2017-06-16","2018-06-27"]
[3532,760199,"   Core part: LTE Advanced high power TDD UE (power class 2) for Rel-15","LTE_TDD_HPUE_R15-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171755",null,"Huawei",null,"19/9/17: Compl:0%->10%¦ 15/12/17: 36.760 added;¦8/1/18: Compl:10%->40%27/3/18: Compl:40%->99%¦27/6/18: Comp",36.76,76,39,null,null,"2017-06-16","2018-06-27"]
[3536,761200,"   Perf. part: New LTE band for 3.3-3.4 GHz for Africa","LTE_TDD_3300_Africa-Perf",2,"Rel-15","R4","2017-06-15","2018-03-15",1,"RP-180247",null,"Huawei",null,"¦19/9/17: WID: RP-171506->RP-171759¦27/3/18: Compl:0%->100%;",null,76,39,null,null,"2017-06-16","2018-03-27"]
[3539,761201,"   Perf. part: UE requirements for network-based CRS interference mitigation for LTE","LTE_NW_CRS_IM-Perf",2,"Rel-15","R4","2017-06-15","2018-12-14",1,"RP-181315",null,"Ericsson",null,"¦27/6/18: WID: RP-171408->RP-181315¦16/1/19: 0%->100",null,76,39,null,null,"2017-06-16","2019-01-16"]
[3543,780069,"Enhanced LTE Support for Aerial Vehicles","LTE_Aerial",1,"Rel-15","R2","2017-03-15","2019-06-19",0.99,"RP-172826",null,"Ericsson",null,"follow-up WI of REL-15 SI FS_LTE_Aerial¦no Perf. part",null,78,40,null,null,"2018-01-08","2018-01-08"]
[3545,780169,"   Core part: Enhanced LTE Support for Aerial Vehicles","LTE_Aerial-Core",2,"Rel-15","R2","2017-12-15","2018-09-14",0.99,"RP-181310","RP-181045","Ericsson",null,"follow-up WI of REL-15 SI FS_LTE_Aerial¦no Perf. part¦27/3/18: Compl:0%->15%¦27/6/18: Compl:15%->99%;",null,78,40,null,null,"2018-01-08","2018-06-27"]
[3548,780171,"   Core part: Separation of CP and UP for Split Option 2 of NR","NR_CPUP_Split-Core",2,"Rel-15","R3","2017-12-15","2018-06-15",1,"RP-180326","RP-181149","Ericsson",null,"follow-up WI of REL-15 SI FS_NR_CPUP_Split¦introduction of E1 interface. 30/1/18: acronym updated27/3/18: Compl:0%->30%27/3/18: WID: RP-172831->RP-180326¦27/6/18: Compl:30%->100%¦27/6/18: Stat Rep: ->RP-181149",null,78,40,null,null,"2018-01-08","2018-06-27"]
[3551,780272,"   Perf. part: UE requirements for LTE DL 8Rx antenna ports","LTE_8Rx_AP_DL-Perf",2,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-180960",null,"Huawei",null,"follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL¦27/6/18: Compl:0%->30%¦26/3/19: 30%->100",null,78,40,null,null,"2018-01-08","2019-03-26"]
[3554,810063,"   UE Conformance Test Aspects - ProSe Support for Band 72 in LTE","LTE450_B72_Europe_ProSe-UEConTest",2,"Rel-15","R5","2018-09-14","2018-12-14",1,"RP-181630",null,"Airbus",null,"16/1/19: 0%->100",null,81,41,null,null,"2018-09-25","2019-01-16"]
[3559,761202,"   Perf. part: Performance requirements of interference cancellation receiver for LTE BS","LTE_IC_BS-Perf",2,"Rel-15","R4","2017-06-15","2017-09-15",1,"RP-171411",null,"China Telecom",null,"¦19/9/17: Compl:0%->100%",null,76,39,null,null,"2017-06-16","2017-09-19"]
[3563,760190,"   Core part: LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R15_intra-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180800",null,"Ericsson",null,"12/7/17: 36.715-00-00 added;¦19/9/17: Compl:0%->25% 8/1/18: Compl:25%->70%;27/3/18: Compl:70%->67%¦ ¦27/6/18: Compl:67%->100%;","36.715-00-00",76,39,null,null,"2017-06-16","2018-06-27"]
[3566,760191,"   Core part:LTE Advanced inter-band CA Rel-15 for 2DL/1UL","LTE_CA_R15_2DL1UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-181013",null,"Qualcomm",null,"12/7/17: 36.715-02-01 added;19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->30%¦27/3/18: Compl:30%->40%¦ ¦27/6/18: Compl:40%->100%;","36.715-02-01",76,39,null,null,"2017-06-16","2018-06-27"]
[3570,760292,"   Perf. part:LTE Advanced inter-band CA Rel-15 for 3DL/1UL","LTE_CA_R15_3DL1UL-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180955",null,"Huawei",null,"¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->65%¦ ¦27/6/18: Compl:65%->100%;",null,76,39,null,null,"2017-06-16","2018-06-27"]
[3572,760193,"   Core part:LTE Advanced inter-band CA Rel-15 for 4DL/1UL","LTE_CA_R15_4DL1UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180801",null,"Ericsson",null,"12/7/17: 36.715-04-01 added;¦19/9/17: Compl:0%->54% 8/1/18: Compl:54%->65%;27/3/18: Compl:65%->63% ¦27/6/18: Compl:63%->100%;","36.715-04-01",76,39,null,null,"2017-06-16","2018-06-27"]
[3575,760194,"   Core part:LTE Advanced inter-band CA Rel-15 for 5DL/1UL","LTE_CA_R15_5DL1UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180743",null,"Nokia",null,"12/7/17: 36.715-05-01 added;19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->50%;27/3/18: Compl:50%->75% ¦27/6/18: Compl:75%->100%;","36.715-05-01",76,39,null,null,"2017-06-16","2018-06-27"]
[3578,760195,"   Core part:LTE Advanced inter-band CA Rel-15 for 2DL/2UL","LTE_CA_R15_2DL2UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180957",null,"Huawei",null,"12/7/17: 36.715-02-02 added;¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->60%¦27/6/18: Compl:60%","36.715-02-02",76,39,null,null,"2017-06-16","2018-06-27"]
[3581,760196,"   Core part:LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5","LTE_CA_R15_xDL2UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180770",null,"LG Electronics",null,"12/7/17: 36.715-00-02 added;¦19/9/17: Compl:0%->20% 8/1/18: Compl:20%->50%¦27/3/18: Compl:50%->80%¦ ¦27/6/18: ","36.715-00-02",76,39,null,null,"2017-06-16","2018-06-27"]
[3586,630011,"   Stopped - Test part: LTE UE TRP and TRS and UTRA Hand Phantom","LTE_UTRA_TRP_TRS-UEConTest",2,"Rel-15","R5","2014-03-15","2017-12-15",0.78,"RP-150070",null,"ZTE","TAYLOR Carolyn (carolyn.tayl@zte.com.cn)","Stat Rep: RP-141132->RP-141848¦Rel 12->Rel13 1st Apr 15: Compl:15%->20% 1st Apr 15: CD:Mon 15/06/15->Wed 15/06/16 1st Apr 15: WID: RP-140090->RP-150070 1st Apr 15: Stat Rep: RP-141848->RP-150069 03/07/15: Compl:20%->25% 03/07/15: Stat Rep: RP-150069->","New 37.544 ",63,32,80,null,"2014-03-04","2018-01-08"]
[3589,790253,"   Perf. part: Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_fenh-Perf",2,"Rel-15","R6","2018-03-15","2018-09-14",1,"RP-180541",null,"Nokia",null,"follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh¦27/6/18: Compl:0%->80%;¦10/9/18: 80%->100",null,79,40,null,null,"2018-03-27","2018-09-10"]
[3594,790155,"   Core part: Addition of Power Class 1 UE to bands B31/B72 for LTE","LTE_PC1_B31_B72-Core",2,"Rel-15","R4","2018-03-15","2018-06-15",1,"RP-180688",null,"Airbus",null,"to add Power Class 1 (+31dBm) for UE operating in Europe @ 450MHz in frequency bands that are suitable for BB-PPDR operation, i.e. band 31 and band 72;27/6/18: moved from Rel-16",null,79,40,null,null,"2018-03-27","2018-06-27"]
[3597,0,"Release 15 Studies on 5G","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3599,750043,"Study on CU-DU lower layer split for New Radio","FS_NR_CU_DU_LLS",1,"Rel-15","R3","2017-03-15","2018-06-15",1,"RP-180684",null,"NTT DOCOMO",null,"CU = central unit, DU = distributed unit¦results will be captured in existing TR 38.801¦19/9/17: Compl:0%->30%¦19/9/17: WID: RP-170818->RP-171717¦15/12/17: 38.816 added;¦8/1/18: Compl:30%->95%¦8/1/18: CD:Fr ¦27/6/18",38.816000000000003,75,38,null,null,"2017-03-21","2018-06-27"]
[3602,760080,"Study on separation of CP and UP for split option 2 of NR","FS_NR_CPUP_Split",1,"Rel-15","R3","2017-06-15","2017-12-15",1,"RP-171905",null,"Ericsson",null,"19/9/17: Compl:0%->45%19/9/17: WID: RP-171421->RP-171905¦15/12/17: 38.806 added;¦8/1/18: Compl:45%->100%",38.805999999999997,76,39,null,null,"2017-06-16","2018-01-08"]
[3605,730070,"Study on interference cancellation receiver for LTE BS","FS_LTE_IC_BS",1,"Rel-15","R4","2016-09-15","2017-06-15",1,"RP-161485",null,"China Telecom",null,"6/10/16: 36.766 added¦20/12/16: Compl:0%->35% 21/3/17: Compl:35%->65%¦19/6/17: Compl:65%->100%",36.765999999999998,73,37,null,null,"2016-09-26","2017-06-19"]
[3608,0,"Other Release 15 Studies","-",1,"Rel-15",null,"2017-09-08","2018-03-16",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3613,760042,"Study on FEC for MC Services","FS_FEC_MCS",1,"Rel-15","S4","2017-06-05","2018-03-15",1,"SP-170337",null,"Lambrou, John - Motorola Solutions ","john (dot) lambrou (at) motorolasolutions (dot) com","11/9/17: 0%->15¦15/12/17: 15%->60¦15/12/17: FCD:12/17->03/18¦16/3/18: 60%->100",26.881,76,39,null,null,"2017-06-03","2018-03-16"]
[3616,720041,"Study on Technical Requirements for a new secure platform for 3GPP applications","FS_NG_SP",1,"Rel-15","C6","2016-06-13","2017-09-12",1,"CP-160371",null,"Heiko Kruse","heiko.kruse@safrangroup.com","16/9/16: 0%->15. ¦5/6/17: 15%->70. 5/6/17: moved to Rel-15 (talks with P. Jolivet)¦5/6/17: FCD:12/16->09/20¦15/12/17: 70%->100",31.800999999999998,72,37,null,null,"2016-06-13","2017-12-15"]
[3621,720025,"Study on User Services Enhancements in 3GPP for TV Services","FS_USE_3GPP_4_TV",1,"Rel-15","S4","2016-06-13","2017-09-12",1,"SP-160273",null,"Thomas Stockhammer, Qualcomm Incorporated","tsto@qti.qualcomm.com","19/9/16: 0%->30¦6/10/16: 26.917 added¦1/12/16: 30%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: 60%->75¦6/3/17: FCD:03/17->06/17¦21/3/17: Moved from Rel-14 (not completed on time)¦7/6/17: 75%->80¦7/6/17: FCD:06/17->09/17¦11/9/17: 80%->100","26.9xx; 26.917",72,37,null,null,"2016-06-11","2017-09-11"]
[3624,700048,"Study on OAM aspects of SON for AAS-based deployments","FS_OAM_SON_AAS",1,"Rel-15","S5","2015-11-02","2017-06-09",1,"SP-150677",null,"Nokia Networks (Yizhi Yao)","Yizhi.yao@nokia.com","13/6/16: 0%->40¦19/9/16: FCD:09/16->12/16¦19/9/16: 40%->60¦1/12/16: FCD:12/16->03/17¦1/12/16: 60%->70¦6/3/17: FCD:03/17->06/17¦21/3/17: moved from rel-14¦7/6/17: 70%->100","(new)",70,36,null,null,"2015-12-07","2017-06-07"]
[3627,730053,"Study on forward compatibility for 3GPP Diameter Charging Applications","FS_FWDCA",1,"Rel-15","S5","2016-09-19","2017-06-15",1,"SP-160608",null,"Nokia, Maryse <dot> Gardella <at> Nokia <dot> com","Nokia, Maryse <dot> Gardella <at> Nokia <dot> com","6/10/16: 32.870 added¦1/12/16: 0%->10¦21/3/17: moved from rel-14¦11/9/17: 10%->40¦15/12/17: 40%->100",32.869999999999997,73,37,null,null,"2016-09-19","2017-12-15"]
[3630,720047,"Study on Management and Orchestration Architecture of Next Generation Network and Service","FS_NGNS_MOA",1,"Rel-15","S5","2016-06-13","2017-12-12",1,"SP-160400",null,"Huawei Technologies, Zou Lan","zoulan@huawei.com","28/7/16: 28.800 added¦19/9/16: 0%->10¦6/3/17: FCD:03/17->06/17¦21/3/17: moved from rel-14¦7/6/17: FCD:06/17->12/17¦7/6/17: 10%->25¦11/9/17: 25%->30¦15/12/17: 30%->100","xy.abc; 28.800",72,37,null,null,"2016-06-13","2017-12-15"]
[3632,650036,"Stopped - Study on IMS Enhanced Spoofed Call Prevention and Detection","FS_ESCAPADES",1,"Rel-15","S3","2014-09-19","2017-12-15",1,"SP-140611","-","Sprint","Gregory.schumacher@sprint.com","Dec.14: TR number added. 3/3/15: 0->5%¦June2015: Compl:5%->25¦9/12/15: 25%->30¦21/3/17: moved from Rel-13¦21/3/17: FCD:09/15->12/17¦7/6/17: Stopped (30%->100%)",33.832000000000001,64,33,80,null,"2014-09-04","2017-06-07"]
[3636,760064,"Study on system and functional aspects of Energy Efficiency in 5G networks ","FS_EE_5G",1,"Rel-15","S5","2017-06-05","2018-12-14",1,"SP-170489",null,"CORNILY, Jean-Michel, ORANGE","jeanmichel.cornily@orange.com","30/6/17: 32.872 added;¦11/9/17: 0%->5¦15/12/17: 32.972 added;¦15/12/17: 5%->40¦16/3/18: 40%->60¦7/6/18: 60%->65¦7/6/18: FCD:06/18->12/18¦10/9/18: 65%->85¦7/12/18: 85%->100","new; 32.872; 32.972",76,39,null,null,"2017-06-05","2018-12-07"]
[3639,700027,"Mission Critical Improvements","MCImp",1,"Rel-14",null,"2015-04-14","2019-12-13",1,null,null,null,null,"Umbrella Feature",null,70,36,null,null,"2015-12-07","2015-12-11"]
[3643,740023,"      Stage 3 of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT-CT",3,"Rel-14","ct","2016-12-01","2017-06-14",1,"CP-160824",null,"FREDERICKS, Bob","bobfredericks@motorolasolutions.com ",null,null,74,38,null,null,"2016-12-01","NA"]
[3648,700028,"   Mission Critical Services Common Requirements ","MCImp-MCCoRe",2,"Rel-14","S1","2015-12-07","2016-06-15",1,"SP-150822","SP-170407","Andrew Thiessen","andrew (at) its (dot) bldrdoc (dot) gov","2/3/16: FCD: 03/16->06/16. ES in SP-160104¦0->75%¦9/6/16: 75%->100","New 22.280",70,36,null,null,"2015-12-07","2016-06-09"]
[3651,670006,"      Study on Mission Critical Video over LTE","FS_MCVideo",3,"Rel-14","S1","2015-04-14","2015-12-15",1,"SP-150048",null,"Villebrun, Emmanuelle (French MoI)","emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","1/4/15:TR number added¦June2015: Compl:0%->50¦07/09/15: 50%->70¦7/12/15: 70%->100","New 22.879",67,34,null,null,"2015-03-04","2015-12-07"]
[3654,750018,"      MCVideo codecs and media handling","MCImp-MCVideo",3,"Rel-14","S4","2017-01-11","2017-03-16",1,"SP-170244",null,"John Lambrou (Motorola Solutions)","john (dot) lambrou (at) motorolasolutions (dot) com","6/3/17: 0%->100",26.280999999999999,75,38,null,null,"2017-03-03","2017-03-06"]
[3657,740035,"         CT3 aspects 3 of MCVideo","MCImp-MCVIDEO-CT",4,"Rel-14","C3","2016-12-01","2017-03-15",1,"CP-160827",null,"PATEL, Milan","milan.patel@huawei.com ","5/6/17: 0%->100","29.165; 29.213; 29.214",74,38,null,null,"2016-12-01","2017-06-05"]
[3659,740037,"         CT6 aspects 3 of MCVideo","MCImp-MCVIDEO-CT",4,"Rel-14","C6","2016-12-01","2017-06-14",1,"CP-160827",null,"PATEL, Milan","milan.patel@huawei.com ","5/6/17: 0%->100. No work identified for CT6.","31.102; 31.103",74,38,null,null,"2016-12-01","2017-06-05"]
[3663,720052,"      Stage 2 for MCData","MCImp-MCData",3,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160492",null,"David Freeman (UK Home Office)","david@dnf-consulting.co.uk ","28/7/16: 23.282 added¦19/9/16: 0%->10¦1/12/16: 10%->95¦3/3/17: 95%->100",23.282,72,37,null,null,"2016-06-13","2017-03-03"]
[3666,740030,"         CT3 aspects of MCData","MCImp-MCDATA-CT",4,"Rel-14","C3","2016-12-01","2017-03-15",1,"CP-160826",null,"HASON, Baruh","baruh.hason@motorolasolutions.com ","5/6/17: 0%->100","29.165; 29.213; 29.214",74,38,null,null,"2016-12-01","2017-06-05"]
[3670,790052,"   UE Conformance Test Aspects - Mission Critical Improvements","MCImp-UEConTest",2,"Rel-14","R5","2018-03-15","2019-12-13",1,"RP-180527",null,"NIST",null,"tested: REL-14 WI MCImp (SA/CT WI: Mission Critical Improvements)¦to provide conformance test specifications for the Rel-14 core requirements for improvements to Mission Critical Services (MCPTT, MCVideo and MCData).;; 25/9/20: 5%->100",null,79,40,null,null,"2018-03-27","2020-09-25"]
[{"$f":"A3674+1","v":3674},730011,"   CT4 aspects of MCPTTProtoc1","MCPTTProtoc1",2,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160581",null,"Ricky Kaura","ricky.kaura@samsung.com","6/3/17: 0%->100","23.003; 23.008; 29.283",73,37,null,null,"2016-09-16","2017-03-06"]
[3675,730012,"   CT6 aspects of MCPTTProtoc1","MCPTTProtoc1",2,"Rel-14","C6","2016-09-16","2017-03-15",1,"CP-160581",null,"Ricky Kaura","ricky.kaura@samsung.com","5/6/17: 0%->100. No more work identified.",31.102,73,37,null,null,"2016-09-16","2017-06-05"]
[3681,720090,"   RAN aspects of LTE-based V2X Services","LTE_V2X",2,"Rel-14",null,"2016-06-15","2018-12-14",1,"RP-161298",null,"LG Electronics",null,"follow-up WI of REL-14 SI FS_LTE_V2X",null,72,37,null,null,"2016-07-08","2016-06-22"]
[3682,720190,"      Core part: LTE-based V2X Services","LTE_V2X-Core",3,"Rel-14","R1","2016-06-15","2017-03-15",1,"RP-162519","RP-170237","LG Electronics",null,"follow-up WI of REL-14 SI FS_LTE_V2X26/9/16: Compl:0%->15%26/9/16: WID: RP-161298->RP-161894¦6/10/16: 36.786 added¦6/10/16: added¦20/12/16: Compl:15%->75% 21/3/17: Compl:75%->100%","36.786; ",72,37,null,null,"2016-07-01","2017-03-21"]
[3688,730029,"      CT4 aspects of V2X Services","V2X-CT",3,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160584",null,"Taehun Kim","taehun78.kim@lge.com","6/10/16: 29.388 added¦6/10/16: 29.389 added¦2/12/16: 0%->80¦6/3/17: 80%->100","23.003; 23.007; 23.008; 29.272; 29.388; 29.389",73,37,null,null,"2016-09-16","2017-03-06"]
[3690,700019,"   Study on LTE support for V2X services","FS_V2XLTE",2,"Rel-14",null,"2015-02-09","2016-06-17",1,"SP-150051",null,"Ki-Dong Lee (LG electronics)","kidong.lee@lge.com","1/4/15:TR number added¦June2015: Compl:25%->50¦07/09/15: 50%->75","New 22.885",67,34,null,null,"2015-03-04","2015-09-07"]
[3693,760072,"      Study on Security of LTE support for V2X services","FS_V2XARC_S3",3,"Rel-14","S3","2015-09-07","2016-06-17",1,"SP-150852",null,null,null,"Introduced at 100% completion, as per SA3 report to SA#76",33.884999999999998,70,36,null,null,"2015-12-07","2016-09-19"]
[3697,700261,"   Perf. part: Support for V2V services based on LTE sidelink","LTE_SL_V2V-Perf",2,"Rel-14","R4","2015-12-15","2017-06-15",1,"RP-161603",null,"LG Electronics",null,"22/3/16: WID: RP-152293->RP-1606491/7/16: WID: RP-160649->RP-16127226/9/16: WID: RP-161272->RP-161603¦20/12/16: Compl:0%->50% 21/3/17: Compl:50%->80% 21/3/17: CD:Wed 15/03/17->Thu 15/06/1719/6/17: Compl:80%->100%",null,70,36,null,null,"2016-01-01","2017-06-19"]
[3701,710024,"   Non-IP for Cellular IoT for EC-EGPRS ","NonIP_GPRS",2,"Rel-14","S2","2016-03-02","2016-06-15",1,"SP-160196",null,"Hans Ronneke, Ericsson","hans . Ronneke (a) ericsson . Com","9/6/16: 0%->50¦19/9/16: 50%->100","23.060; 23.682; 23.401?",71,36,null,null,"2016-03-02","2016-09-19"]
[3702,710025,"   CT aspects for Non-IP for Cellular Internet of Things for EC-EGPRS ","NonIP_GPRS-CT",2,"Rel-14",null,"2016-03-02","2016-09-15",1,"CP-160293",null,"Orange, Youssef CHADLI","youssef.chadli@orange.com","11/6/16: WID:CP-160161->CP-160293",null,71,36,null,null,"2016-03-02","2016-06-11"]
[3706,720092,"Further enhanced MTC for LTE","LTE_feMTC",1,"Rel-14",null,"2016-06-15","2018-09-14",1,"RP-161321",null,"Ericsson",null,null,null,72,37,null,null,"2016-07-08","2016-06-22"]
[3709,770063,"   UE Conformance Test Aspects - Further enhanced MTC for LTE","LTE_feMTC-UEConTest",2,"Rel-14","R5","2017-09-15","2018-09-14",1,"RP-192886",null,"Ericsson",null,"¦8/1/18: Compl:0%->6%¦27/3/18: Compl:6%->21%¦ ¦2¦26/3/19: WID:RP-180414->RP-190514; 26/6/19: WID:RP-190514->RP-190935; 14/1/20: WID:RP-190935->RP-192886; 26/3/20: 26%->100",null,77,39,null,null,"2017-09-19","2020-03-26"]
[3715,730359,"Extended architecture support for Cellular Internet of Things","CIoT_Ext",1,"Rel-14",null,"2016-06-17","2017-03-14",1,"SP-160732",null,"Intel : Puneet Jain","puneet.jain@intel.com",null,"23.401; 23.682; 23.060",73,37,null,null,"2016-09-19","2016-09-19"]
[3717,730059,"   Stage 2 of Extended architecture support for Cellular Internet of Things","CIoT_Ext",2,"Rel-14","S2","2016-09-15","2016-12-16",1,"SP-160830",null,"Intel : Puneet Jain","puneet.jain@intel.com","1/12/16: 0%->100¦1/12/16: WID:SP-160732->SP-160830","23.401; 23.682; 23.060; 23.271",73,37,null,null,"2016-09-19","2016-12-01"]
[3720,740040,"      CT4 aspects of extended architecture enhancements for Cellular Internet of Things","CIoT_Ext-CT",3,"Rel-14","C4","2016-12-01","2017-03-14",1,"CP-160701",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","6/3/17: 0%->90¦5/6/17: 90%->100","23.008; 29.272; 29.002; 29.336; 29.128; 29.171; 29.172; 29.173",74,38,null,null,"2016-12-01","2017-06-05"]
[3724,730083,"New band support for Rel-14 Narrowband Internet of Things (NB-IOT)","NB_IOT_R14_bands",1,"Rel-14","R4","2016-09-15","2017-09-15",1,"RP-161890",null,"Ericsson",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[3728,720006,"Enhancements of Dedicated Core Networks selection mechanism","eDecor",1,"Rel-14",null,"2015-09-17","2017-12-15",1,"SP-160310","SP-170537","Roland Gustafsson","Roland.Gustafsson@ericsson.com","7/12/15: 0%->70¦7/3/16: 70%->80¦9/6/16: 80%->95",23.710999999999999,69,35,null,null,"2015-09-17","2016-06-09"]
[3731,730013,"   CT aspects of eDecor","eDecor-CT",2,"Rel-14","ct","2016-09-16","2016-12-15",1,"CP-160475",null,"Mikael Wass","Mikael.wass@ericsson.com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[3733,730015,"      CT4 aspects of eDecor","eDecor-CT",3,"Rel-14","C4","2016-09-16","2016-12-15",1,"CP-160475",null,"Mikael Wass","Mikael.wass@ericsson.com","2/12/16: 0%->10¦6/3/17: 10%->100","29.303; 23.003; 23.008",73,37,null,null,"2016-09-16","2017-03-06"]
[3736,740167,"      Core part: RAN aspects of eDECOR for UMTS and LTE","eDECOR-UTRA_LTE-Core",3,"Rel-14","R3","2016-12-15","2017-03-15",1,"RP-162543","RP-170547","Ericsson",null,"21/3/17: Compl:0%->100%21/3/17: Stat Rep: ->RP-170547",null,74,38,null,null,"2016-12-20","2017-03-21"]
[3742,0,"Release 14 on WLAN","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3744,700039,"   Stage 2 of EWE","EWE",2,"Rel-14","S2","2015-11-02","2016-06-17",1,"SP-150624",null,"Alcatel-Lucent, Nicolas Drevon","Nicolas.Drevon@alcatel-lucent.com","7/3/16: 45%->60¦9/6/16: 60%->100","23.002; 23.402",70,36,null,null,"2015-12-07","2016-06-09"]
[3747,720033,"      CT4 aspects of EWE","EWE-CT",3,"Rel-14","C4","2016-06-13","2016-09-15",1,"CP-160244",null,"Nokia, Bruno Landais","bruno.landais@nokia.com","2/12/16: 0%->100",29.273,72,37,null,null,"2016-06-13","2016-12-02"]
[3751,730045,"      CT1 aspects of ERP","ERP-CT",3,"Rel-14","C1","2016-09-16","2017-03-16",1,"CP-160413",null,"Orange, Julien Bournelle","Julien.bournelle@orange.com","2/12/16: 0%->80¦6/3/17: 80%->95¦5/6/17: 95%->100",24.302,73,37,null,null,"2016-09-16","2017-06-05"]
[3755,720018,"   Support of Emergency services over WLAN - phase 2","SEW2",2,"Rel-14","S2","2016-06-13","2016-09-15",1,"SP-160307",null,"Nicolas Drevon","nicolas.drevon@nokia.com","11/6/16: 0%->45¦19/9/16: 45%->100","23.402; 23.167",72,37,null,null,"2015-04-01","2016-09-19"]
[3758,730019,"      CT4 aspects of SEW2","SEW2-CT",3,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160694",null,"Jennifer Liu","jennifer.liu@nokia.com","2/12/16: 0%->100","23.003; 29.272; 29.273; 29.274; 29.328",73,37,null,null,"2016-09-16","2016-12-02"]
[3760,720076,"T-ADS supporting WLAN Access","TADS_WLAN",1,"Rel-14","S2","2016-03-15","2016-09-15",1,"SP-160488","SP-170519","Jiang Yi","jiangyi (at) chinamobile (dot) com","19/9/16: 0%->100","23.292; 23.221; 23.402",72,37,null,null,"2016-06-17","2016-09-19"]
[3763,0,"Release 14 on IMS","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3766,700021,"   Stage 2 of Evolution to and Interworking with eCall in IMS","EIEI",2,"Rel-14","S2","2015-12-11","2016-06-10",1,"SP-150623",null,"Haris Zisimopoulos, Qualcomm Incorporated","harisz@qti.qualcomm.com","7/3/16: 0%->20¦9/6/16: 20%->100. FCD: 03/16->06/16","23.167; 23.401",68,35,null,null,"2015-12-07","2016-06-09"]
[3769,720068,"      (IETF) Next-Generation Pan-European eCall (draft-ietf-ecrit-ecall)","EIEI-CT",3,"Rel-14","C1-IETF","2016-03-02","2016-09-15",1,"CP-160053",null,null,null,"18/12/17: 30%->100; 9/4/21: RFC 8147 added;","draft-ietf-ecrit-ecall; RFC 8147",72,37,null,null,"2016-03-02","2021-04-09"]
[3774,720034,"   CT aspects for PWDIMS","PWDIMS-CT",2,"Rel-14","ct","2016-06-13","2016-12-15",1,"CP-160295",null,"Axell, Jörgen",null,null,null,72,37,null,null,"2016-06-11","NA"]
[3778,630107,"   CT1 part of IMS Signalling Activated Trace","ISAT",2,"Rel-14","C1","2014-03-10","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150728¦5/6/17: 0%->100","24.229; 24.323",63,32,null,null,"2014-01-29","2017-06-05"]
[3782,630207,"   CT3 part of IMS Signalling Activated Trace","ISAT",2,"Rel-14","C3","2014-03-10","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637¦5/6/17: 0%->100",29.164999999999999,63,32,null,null,"2014-01-29","2017-06-05"]
[3785,740017,"User Controlled Spoofed Call Treatment","SPECTRE",1,"Rel-14",null,"2016-08-23","2018-06-15",1,"SP-160898",null,"Greg Schumacher, Sprint",null,"1/12/16: moved from Rel-15 to Rel-14¦1/12/16: WID:SP-160729->SP-160898",null,73,37,null,null,"2016-09-19","2016-12-01"]
[3787,740018,"   Stage 3 of User Controlled Spoofed Call Treatment","SPECTRE-CT",2,"Rel-14","C1","2016-12-01","2017-03-14",1,"CP-160696",null,"Dolly, Martin","md3135@att.com","2/12/16: 0%->25¦6/3/17: 25%->100","24.229; 29.165",74,38,null,null,"2016-09-19","2017-03-06"]
[3790,700032,"Enhancement for TV service","EnTV",1,"Rel-14",null,"2015-04-14","2017-06-09",1,"SP-150756","SP-170532","Zhiming Li","Lizhiming@huawei.com","2/3/16: 0%->100",22.100999999999999,70,36,null,null,"2015-12-07","2016-03-02"]
[3793,710046,"      Study on System Architecture Enhancements to eMBMS for TV Video Service","FS_AE_enTV",3,"Rel-14","S2","2016-03-11","2016-09-15",1,"SP-160225",null,"Miguel Griot, Qualcomm","mgriot@qti.qualcomm.com","9/6/16: 0%->70¦28/7/16: 23.746 added¦19/9/16: 70%->100",23.745999999999999,71,36,null,null,"2016-03-11","2016-09-19"]
[3796,740060,"   Codec aspects for eMBMS Delivery of Media and TV Services","AE_enTV-S4",2,"Rel-14","S4","2016-12-08","2017-06-09",1,"SP-160956",null,"Imed Bouazizi","i.bouazizi@samsung.com","6/3/17: 0%->20¦6/3/17: FCD:03/17->06/17¦7/6/17: 20%->100","26.347; 26.346",74,38,null,null,"2016-12-08","2017-06-07"]
[3801,740053,"      CT6 aspects of system architecture enhancements for TV service ","AE_enTV-CT",3,"Rel-14","C6","2016-12-01","2017-03-14",1,"CP-160816",null,"Catovic, Amer","amerc@qti.qualcomm.com","7/3/17: 0%->100",31.102,74,38,null,null,"2016-12-01","2017-03-07"]
[3805,730031,"SIP Reason header extension","REAS_EXT",1,"Rel-14","ct","2016-09-16","2018-06-14",1,"CP-160481","CP-171175","Mohali, Marianne","marianne.mohali@orange.com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[3809,690034,"Enhancements to User Location Reporting Support","eULRS",1,"Rel-14","S1","2015-09-09","2015-12-18",1,"SP-150540",null,null,null,"2/3/16: 0%->100",null,68,35,null,null,"2015-09-09","2016-03-02"]
[3812,730042,"   CT4 aspects of Diameter Load Control Mechanism","DLoCMe",2,"Rel-14","C4","2016-09-16","2016-12-15",1,"CP-160645",null,"Nokia, Ulrich Wiehe","ulrich.wiehe@nokia.com","2/12/16: 0%->100","29.153; 29.154; 29.212; 29.214; 29.215; 29.217; 29.219; 29.213",73,37,null,null,"2016-09-16","2016-12-02"]
[3813,740058,"   (IETF) Diameter Load Information Conveyance (draft-ietf-dime-load) --> RFC 8583","DLoCMe",2,"Rel-14","C4-IETF","2016-12-02","2017-03-15",1,"CP-160645",null,null,null,"2/12/16: 0%->90",null,74,38,null,null,"2016-12-02","2016-12-02"]
[3818,740056,"      CT4 aspects of Diameter Base Protocol Specification Update","DBPU",3,"Rel-14","C4","2016-12-01","2017-03-14",1,"CP-160823",null,"Huawei, Peter Schmitt","Peter.Schmitt@huawei.com","2/12/16: 0%->10¦6/3/17: 10%->100","29.109; 29.128; 29.172; 29.173; 29.228; 29.229; 29.272; 29.273; 29.283; 29.328; 29.329; 29.336; 29.337; 29.338; 29.343; 29.344; 29.345",74,38,null,null,"2016-12-01","2017-03-06"]
[3821,720029,"   Overall aspects of MMCMH_Enh","MMCMH_Enh",2,"Rel-14","S4","2016-06-13","2017-03-10",1,"SP-160596",null,"Nikolai Leung","nleung@qti.qualcomm.com","19/9/16: WID:SP-160272->SP-160785¦19/9/16: 0%->50¦1/12/16: 50%->80¦1/12/16: FCD:12/16->03/17¦6/3/17: 80%->100","26.114; 26.980",72,37,null,null,"2016-06-11","2017-03-06"]
[3823,720065,"      CT1 aspects of MMCMH_Enh","MMCMH_Enh-CT",3,"Rel-14","C1","2016-03-02","2017-03-15",1,"CP-160369",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Name changed from \"CT1 aspects of MTSI Extension on Multi-stream\". Acronym changed from \"MMCMH-CT\"¦13/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17¦13/6/16: WID:CP-160250->CP-160369¦2/12/16: 0%->95¦6/3/17: 95%->100",24.228999999999999,72,37,null,null,"2016-03-02","2017-03-06"]
[3828,710002,"Stopped - CT aspects of (or \"Enhancements of\") MTSI Extension on Multi-stream","MMCMH-CT",1,"Rel-14","ct","2016-03-02","2016-09-15",1,"CP-160117",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Deleted, \"replaced\" by MMCMH_Enh-CT",null,71,36,"CP-72",null,"2016-03-02","2016-06-13"]
[3832,720008,"Control and User Plane Separation of EPC nodes","CUPS",1,"Rel-14",null,"2015-09-17","2017-03-15",1,"SP-160316","SP-170520","Huawei, Mirko Schramm","mirko.schramm@huawei.com","7/12/15: 0%->20¦7/3/16: 20%->40¦9/6/16: 40%->100¦28/7/16: 23.214 added;","23.714; 23.214",69,35,null,null,"2015-09-17","2016-07-28"]
[3836,730039,"      CT3 aspects for CUPS","CUPS-CT",3,"Rel-14","C3","2016-09-16","2017-03-15",1,"CP-160579",null,"Huawei, Peter Schmitt","peter.schmitt@huawei.com","8/6/17: 0%->100","29.212; 29.213",73,37,null,null,"2016-09-16","2017-06-08"]
[3839,680035,"   Management of mobile networks that include virtualized network functions","OAM14-MAMO_VNF",2,"Rel-14","S5","2015-06-15","2017-12-12",1,"SP-150362",null,"Jinglei Liu, China Mobile","liujinglei@chinamobile.com","June2015: WID:SP-150308->SP-150362",null,68,35,null,null,"2015-06-15","2015-06-18"]
[3840,680036,"      Management concept, architecture and requirements for mobile networks that include virtualized network functions","OAM14-MAMO_VNF-MCAR",3,"Rel-14","S5","2015-06-15","2016-12-15",1,"SP-160023",null,"Jinglei Liu, China Mobile (liujinglei@chinamobile.com)","liujinglei@chinamobile.com","June2015: WID:SP-150309->SP-150363. Aug2015: FCD: Mar 2016¦07/09/15: 0%->20. 15/09/15: FCD: Mar 16->Dec 16, moved to Rel-14¦7/12/15: 20%->40¦7/3/16: 40%->50¦7/3/16: WID:SP-150363->SP-160023 ( FCD: Dec16->Sep16)¦13/6/16: 50%->70¦19/9/16: FCD:09/16","28.xyz; 32.101",68,35,null,null,"2015-06-15","2017-03-22"]
[3845,710009,"   Filtering of PM measurements and data volume","OAM14-FILMEAS",2,"Rel-14","S5","2016-03-01","2016-12-01",1,"SP-160610",null,"Ericsson: Robert Petersen","robert.petersen@ericsson.com","13/6/16: 0%->15¦19/9/16: WID:SP-160022->SP-160610¦19/9/16: 15%->60¦1/12/16: 60%->95¦6/3/17: 95%->100","New 32.817; 32.425; 32.412; 32.416; 32.130",71,36,null,null,"2016-03-01","2017-03-06"]
[3848,680050,"Development of super-wideband and fullband P.835","DESUDAPS",1,"Rel-14","S4","2015-06-16","2017-06-15",1,"SP-150215","SP-170346","Scott Isabelle (Knowles, Inc.)","sisabelle@audience.com","06/15: FCD corrected to Dec.15¦Aug2015: 0%->5¦07/09/15: 5%->20, FCD: 12/15->06.16¦7/12/15: 20%->40, MOVED TO REL-14¦7/3/16: 40%->50. 15/4/16: 6/16->12/16¦11/6/16: 50%->60¦19/9/16: 60%->70, fcd: 12/16->06/17¦1/12/16: 70%->75¦6/3/17: 75%->80¦7/6","26.131; 26.132",68,35,null,null,"2015-06-18","2017-06-07"]
[3851,680002,"Control of Applications when Third party Servers encounter difficulties","CATS",1,"Rel-14","S1","2015-05-11","2015-09-16",1,"SP-150273","SP-170338","Eriko Yoshida, KDDI","er-yoshida (at) kddi (dot) com","07/09/15: 0%->100",22.010999999999999,68,35,null,null,"2015-06-09","2015-09-07"]
[3854,720079,"   Study on Stage 2 of PS Data off function","FS_PS_DATA_OFF",2,"Rel-14","S2","2016-06-17","2016-12-15",1,"SP-160318",null,"Orange, david <dot> cailliere <at> orange <dot> com","david <dot> cailliere <at> orange <dot> com","28/7/16: 23.702 added¦19/9/16: 0%->60¦1/12/16: FCD:09/16->12/16¦1/12/16: 60%->100",23.702000000000002,72,37,null,null,"2016-06-17","2016-12-01"]
[3859,740044,"      CT6 aspects of PS Data Off","PS_DATA_OFF-CT",3,"Rel-14","C6","2016-12-01","2017-03-14",1,"CP-160702",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/3/17: 0%->100","31.102; 31.103; 31.111",74,38,null,null,"2016-12-01","2017-03-07"]
[3862,710004,"Paging Policy Enhancements and Procedure","PPEPO_LTE",1,"Rel-14","S1","2016-02-01","2016-03-01",1,"SP-160113","SP-170549","China Unicom, Zhuoyun Zhang","zhangzy910@chinaunicom.cn",null,22.100999999999999,71,36,null,null,"2016-03-01","2016-03-01"]
[3863,720077,"Enhancement to Flexible Mobile Service Steering ","eFMSS",1,"Rel-14",null,"2015-05-11","2016-09-15",1,"SP-160115",null,"China Mobile, Lu Lu","lulu@chinamobile.com",null,"22.115; 22.101",72,37,null,null,"2016-03-01","2016-03-01"]
[3867,710010,"Media Handling Extensions of IMS-based Telepresence","IMS_TELEP_EXT",1,"Rel-14",null,"2016-03-01","2016-12-01",1,"SP-160081","SP-170515","Ozgur Oyman, Intel","ozgur.oyman@intel.com","11/6/16: 0%->10",26.222999999999999,71,36,null,null,"2016-03-01","2016-06-11"]
[3872,800105,"      (IETF) CLUE Protocol data channel (draft-ietf-clue-datachannel)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",1,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8850 added;","RFC 8850",80,41,null,null,"2018-06-27","2021-04-09"]
[3875,800108,"      (IETF) Protocol for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-protocol)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",1,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8847 added;","RFC 8847",80,41,null,null,"2018-06-27","2021-04-09"]
[3878,800111,"      (IETF) SDP-based Data Channel Negotiation (draft-ietf-mmusic-data-channel-sdpneg)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",1,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8864 added;","RFC 8864",80,41,null,null,"2018-06-27","2021-04-09"]
[3881,710048,"S8 Home Routing Architecture for VoLTE","V8",1,"Rel-14",null,"2015-06-18","2017-06-09",1,"SP-160315","SP-170522",null,null,"Umbrella, created by MCC to group SA2 and SA3 activities",null,71,36,null,null,"2016-03-11","2016-03-11"]
[3886,730024,"      CT1 Aspects of V8","V8-CT",3,"Rel-14","C1","2016-09-16","2016-12-15",1,"CP-160479",null,"Tsuyoshi Takakura (NTT DOCOMO)","tsuyoshi.takakura.ey@s1.nttdocomo.com","2/12/16: 40%->100",24.228999999999999,73,37,null,null,"2016-09-16","2016-12-02"]
[3889,720020,"Improvements of awareness of user location change","AULC",1,"Rel-14",null,"2015-09-17","2017-06-09",1,"SP-160308","SP-170524","Yang Xu","xuyang49@chinaunicom.cn",null,null,72,37,null,null,"2015-09-17","2016-06-09"]
[3890,690050,"   Study on improvement of awareness of user location change","FS_AULC",2,"Rel-14","S2","2015-09-17","2016-06-17",1,"SP-150517",null,"Yang Xu","xuyang49@chinaunicom.cn","7/12/15: 0%->40¦7/3/16: 40%->70¦9/6/16: 70%->100",23.71,69,35,null,null,"2015-09-17","2016-06-09"]
[3894,730036,"      CT4 Aspect of AULC","AULC-CT",3,"Rel-14","C4","2016-09-16","2016-12-15",1,"CP-160466",null,"Huawei, Wu Yizhuang","wuyizhuang@huawei.com","2/12/16: 0%->95¦6/3/17: 95%->100",29.274000000000001,73,37,null,null,"2016-09-16","2017-03-06"]
[3897,700040,"   Study on Service Domain Centralization","FS_SeDoC",2,"Rel-14","S2","2015-11-02","2016-09-15",1,"SP-160306",null,"Chris Joul (T-Mobile USA)","chris (dot) joul (at) t (dash) mobile (dot) com","Comes back from previous release¦28/1/16: 23.719 added¦7/3/16: 0%->30¦7/3/16: WID:SP-150626->SP-1601679/6/16: 30%->70¦11/6/16: WID:SP-160167->SP-160306. FCD: 06/16->09/16¦1/12/16: 70%->100",23.719000000000001,70,36,null,null,"2015-12-07","2016-12-01"]
[3903,730038,"      CT3 Aspects of SDCI","SDCI-CT",3,"Rel-14","C3","2016-09-16","2016-12-15",1,"CP-160580",null,"China Unicom, Xu, Yang","xuyang49@chinaunicom.cn","6/10/16: 29.250 added¦2/12/16: 10%->30¦6/3/17: 30%->80¦5/6/17: 80%->100","29.212; 29.213; 29.214; 29.201; 29.250",73,37,null,null,"2016-09-16","2017-06-05"]
[3905,710018,"   SAES5 CS Fallback in EPS","SAES5-CSFB",2,"Rel-14","C1","2016-03-02","2017-03-15",1,"CP-160052",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com","11/6/16: 0%->5¦16/9/16: 5%->20¦2/12/16: 20%->70¦6/3/17: 70%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118",71,36,null,null,"2016-03-02","2017-03-06"]
[3908,720012,"Group based enhancements in the network capability exposure functions","GENCEF",1,"Rel-14","S2","2015-11-02","2016-12-16",1,"SP-160311","SP-170517","Samsung, Sung Hwan Won","sunghwan.won@samsung.com",null,null,70,36,null,null,"2015-12-07","2016-06-09"]
[3912,700044,"   Study on Robust Call Setup for VoLTE subscriber in LTE","FS_RobVoLTE",2,"Rel-14","S2","2015-11-02","2016-06-10",1,"SP-150632",null,"Xiaobo Wu, Huawei","wuxiaobo@ huawei.com","28/1/16: 23.750 added¦7/3/16: 0%->20¦9/6/16: 20%->100","23.8xx; 23.750",70,36,null,null,"2015-12-07","2016-06-09"]
[3916,730178,"      Core part: Voice and Video Enhancement for LTE","LTE_VoLTE_ViLTE_enh-Core",3,"Rel-14","R2","2016-09-15","2017-03-15",1,"RP-161856","RP-170323","CMCC",null,"¦20/12/16: Compl:0%->80%¦21/3/17: Compl:80%->100%¦21/3/17: Stat Rep: ->RP-170323",null,73,37,null,null,"2016-09-26","2017-03-21"]
[3917,760089,"      UE Conformance Test Aspects –Voice and Video Enhancement for LTE","LTE_VoLTE_ViLTE_enh-UEConTest",3,"Rel-14","R5","2017-06-15","2018-09-14",1,"RP-171385",null,"CATT",null,"¦19/9/17: Compl:0%->20%¦8/1/18: Compl:20%->60%¦ 27/3/18: Compl:60 ;; 11/10/20: 95%->100",null,76,39,null,null,"2017-06-16","2020-10-11"]
[3921,720038,"   CT1 aspects of IOC_UE_conf","IOC_UE_conf",2,"Rel-14","C1","2016-06-13","2017-03-15",1,"CP-160828",null,"Sedlacek, Ivo","ivo.sedlacek@ericsson.com","11/6/16: 0%->10¦16/9/16: 10%->20¦17/10/16: WID:CP-160296->CP-160374¦2/12/16: 20%->75¦6/3/17: 75%->100","24.167; 24.229; 24.301; 24.302; 24.312; 24.341; 24.368; 24.607; 24.623; 24.275",72,37,null,null,"2016-06-11","2017-03-06"]
[3924,710012,"Rel-14 Charging","CH14",1,"Rel-14","S5","2016-03-01","2017-06-09",1,"SP-160021",null,null,null,"Umbrella Feature",null,71,36,null,null,"2016-03-01","2016-03-01"]
[{"$f":"A3930+1","v":3930},740059,"   CT Aspects of Determination of Completeness of Charging Information in IMS","CH14-DCCII-CT",2,"Rel-14","ct","2016-12-01","2017-03-14",1,"CP-160697","CP-171048","Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de",null,null,74,38,null,null,"2016-12-01","2017-03-21"]
[3932,740021,"      CT3 Aspects of Determination of Completeness of Charging Information in IMS","CH14-DCCII-CT",3,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160697",null,"Michael KREIPL, Deutsche Telekom","michael(dot)kreipl(at)telekom(dot)de","8/6/17: 0%->100",29.164999999999999,74,38,null,null,"2016-12-01","2017-06-08"]
[3936,730075,"   UE Conformance Test Aspects - Enhanced LAA for LTE","LTE_eLAA-UEConTest",2,"Rel-14","R5","2016-09-15","2018-09-14",1,"RP-171577",null,"Intel",null,"¦21/3/17: Compl:0%->5% ;19/6/17: Compl:5%->6%¦19/9/17: Compl 8/1/18: C2 ;; 11/10/20: 85%->100",null,73,37,null,null,"2016-09-26","2020-10-11"]
[3939,700063,"DTX/DRX enhancements in CELL_FACH","FACH_DTXDRX",1,"Rel-14","R2","2015-12-15","2016-12-15",1,"RP-152286",null,"Huawei",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3943,700277,"   Perf. part: AWS-3/4 Band for LTE","LTE_AWS_3_4-Perf",2,"Rel-14","R4","2015-12-15","2016-06-15",1,"RP-160783",null,"Dish Network",null,"1/7/16: Compl:0%->100%1/7/16: CD:Thu 15/09/16->Wed 15/06",null,70,36,null,null,"2016-01-01","2016-07-01"]
[3944,730072,"   UE Conformance Test Aspects – AWS-3/4 Band for LTE (Band 70)","LTE_AWS_3_4-UEConTest",2,"Rel-14","R5","2016-09-15","2016-12-15",1,"RP-162009",null,"Dish Network",null,"¦20/12/16: Compl:0%->100%¦",null,73,37,null,null,"2016-09-26","2016-12-20"]
[3948,740173,"   Core part: Addition of 1.4 and 3 MHz Channel Bandwidth to E-UTRA operating band 65 for CGC (Complementary Ground Component) operations in Region 1","LTE_1980_2170_REG1_addBWs-Core",2,"Rel-14","R4","2016-12-15","2017-03-15",1,"RP-170235",null,"Hughes Network Systems",null,"¦21/3/17: Compl:0%->100% ¦2",null,74,38,null,null,"2016-12-20","2017-03-21"]
[3951,700179,"   Core part: LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1","LTE_FDD_2600_CA_B3-Core",2,"Rel-14","R4","2015-12-15","2016-06-15",1,"RP-161200",null,"Orange",null,"28/1/16: 36.858 added;22/3/16: Compl:0%->40%22/3/16: WID: RP-152253->RP-160378¦1/7/16: Compl:40%->100%;",36.857999999999997,70,36,null,null,"2016-01-01","2016-07-01"]
[3957,700081,"Performance enhancements for high speed scenario in LTE","LTE_high_speed",1,"Rel-14","R4","2015-12-15","2018-09-14",1,"RP-152263",null,"NTT DOCOMO",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3959,700282,"   Perf. part: Performance enhancements for high speed scenario in LTE","LTE_high_speed-Perf",2,"Rel-14","R4","2015-12-15","2017-06-15",1,"RP-171039",null,"NTT DOCOMO",null,"22/3/16: WID: RP-152263->RP-1601721/7/16: Compl:0%->20%¦26/9/16: Compl:20%->25%¦20/12/16: Compl:25%->35% ¦21/3/17: Compl:35%->70%¦19/6/17: Compl:70%->100%¦19/6/17: WID: RP-160172->RP-171039",null,70,36,null,null,"2016-01-01","2017-06-19"]
[3963,710272,"   Perf. part: Further Indoor Positioning Enhancements for UTRA and LTE","UTRA_LTE_iPos_enh2-Perf",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-162026",null,"Huawei",null,"26/9/16: CD:Wed 15/03/17->Thu 15/06/1726/9/16: WID: RP-160538->RP-161850¦20/12/16: Compl:0%->30%¦20/12/16: WI21/3/17: Compl:30%->50%19/6/17: Compl:50%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[3966,710176,"   Core part: Radiated performance requirements for the verification of multi-antenna reception of UEs in LTE","LTE_MIMO_OTA-Core",2,"Rel-14","R4","2016-03-15","2017-09-15",1,"RP-170278",null,"Intel",null,"follow-up WI of REL-13 WI UTRA_LTE_MIMO_OTA-Core¦no Perf. part1/7/16: Compl:0%->10%1/7/16: WID: RP-160603->RP-16091426/9/16: Compl:10%->15%¦20/12/16: Compl:15%->25%¦20/12/16: WID: RP-160914->RP-162306;21/3/17: Compl:25%->33%;1 ;",null,71,36,null,null,"2016-03-22","2017-09-19"]
[3970,710277,"   Perf. part: Enhancements on Full-Dimension (FD) MIMO for LTE","LTE_eFDMIMO-Perf",2,"Rel-14","R4","2016-03-15","2017-12-15",1,"RP-160623",null,"Samsung",null,"¦20/12/16: Stat Rep: -->¦19/6/17: Compl:0%->50%19/9/17: Compl:50%->70%19/9/17: CD:Fri 15/09/17->Fri 15/12/17¦8/1/18: Compl:70%->100%",null,71,36,null,null,"2016-03-22","2018-01-08"]
[3971,830085,"   UE Conformance Test Aspects - Enhancements on Full-Dimension (FD) MIMO for LTE","LTE_eFDMIMO-UEConTest",2,"Rel-14","R5","2019-03-01","2022-06-22",1,"RP-190650","RP-221217","Mikael ZIRÉN","Mikael.ziren@ericsson.com","08/10/20: UID corrected (was 830185); 8/10/20: 0%->5; 8/10/20: FCD:13/09/2019->12/20; 8/4/21: FCD:11/12/2020->06/21; 2/7/21: 5%->5; 2/7/21: FCD:Fri 11/06/->12/21; 20/6/22: FCD:15/12/2021->22/06/2022; Compl:5%->100%; Stat Rep: ->RP-221217; Rapporteur: Eric",null,83,42,null,null,"2019-03-26","2022-06-20"]
[3975,710079,"Uplink Capacity Enhancements for LTE","LTE_UL_CAP_enh",1,"Rel-14","R1","2016-03-15","2018-12-14",1,"RP-160664",null,"Ericsson",null,null,null,71,36,null,null,"2016-03-22","2016-03-22"]
[3978,780063,"   UE Conformance Test Aspects - Uplink capacity enhancements for LTE","LTE_UL_CAP_enh-UEConTest",2,"Rel-14","R5","2017-12-15","2018-12-14",1,"RP-172639",null,"Ericsson",null,"tested: REL-14 WI LTE_UL_CAP_enh-Core¦related to UL 256 QAM27/3 ;¦26/3/19: 35%->100",null,78,40,null,null,"2018-01-08","2019-03-26"]
[3982,710081,"eMBMS enhancements for LTE","MBMS_LTE_enh2",1,"Rel-14","R1","2016-03-15","2017-09-15",1,"RP-160675","RP-171628","Ericsson",null,null,null,71,36,null,null,"2016-03-22","2016-03-22"]
[3984,710281,"   Perf. part: eMBMS enhancements for LTE","MBMS_LTE_enh2-Perf",2,"Rel-14","R4","2016-03-15","2017-09-15",1,"RP-170199",null,"Ericsson",null,"¦1/7/16: CD:Wed 15/06/16->Fri 15/09/17¦1/7/16: WID: RP-160675->RP-161297¦20/12/16: WID: RP-161297->RP-162231¦20/12/16: Stat Rep: --> ¦21/3/17: WID: RP-162231->RP-17019919/6/17: Compl:0%->70%¦19/9/17: Compl:70%->100%",null,71,36,null,null,"2016-03-22","2017-09-19"]
[3990,710184,"   Core part: Downlink Multiuser Superposition Transmission for LTE","LTE_MUST-Core",2,"Rel-14","R1","2016-03-15","2016-12-15",1,"RP-161019","RP-162504","MediaTek",null,"¦1/7/16: Compl:0%->40%¦1/7/16: WID: RP-160680->RP-16101926/9/16: Compl:40%->60%¦20/12/16: Compl:60%->100%¦20/12/16: Stat Rep: -->RP-162504",null,71,36,null,null,"2016-03-22","2016-12-20"]
[3993,720070,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc8",2,"Rel-14","C1","2016-06-14","2017-03-15",1,"CP-160294",null,"Alcatel-Lucent","Keith Drage","Mar.15: 0->10%¦June2015: Compl:10%->30¦07/09/15: 30%->70¦7/12/15: 70%->100¦16/9/16: 0%->30¦2/12/16: 30%->75¦6/3/17: 75%->100",null,72,37,null,null,"2014-12-04","2017-03-06"]
[3997,720094,"Multi-Carrier Enhancements for UMTS","UTRA_MCe",1,"Rel-14","R2","2015-12-15","2016-12-15",1,"RP-161259",null,"Huawei, HiSilicon",null,"no Perf. part¦follow-up WI of REL-14 SI FS_UTRA_MCe",null,72,37,null,null,"2016-07-08","2016-06-22"]
[3998,700059,"   Study on Multi-Carrier Enhancements for UMTS","FS_UTRA_MCe",2,"Rel-14","R1","2015-12-15","2016-06-15",1,"RP-152290",null,"Huawei",null,"22/3/16: Compl:0%->20%¦1/7/16: Compl:20%->100%¦28/7/16: 25.707 added;",25.707000000000001,70,36,null,null,"2016-01-01","2016-07-28"]
[4002,720295,"   Perf. part: Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States","LTE_TDD_3550_CBRS_US-Perf",2,"Rel-14","R4","2016-06-15","2016-12-15",1,"RP-162007",null,"Nokia",null,"¦20/12/16: Compl:0%->100%¦",null,72,37,null,null,"2016-07-01","2016-12-20"]
[4006,720296,"   Perf. part: LTE Band 41 UE power class 2 operation","LTE_B41_UE_PC2-Perf",2,"Rel-14","R4","2016-06-15","2016-12-15",1,"RP-161221",null,"Sprint",null,"26/9/16: Compl:0%->80%¦20/12/16: Compl:80%->100%",null,72,37,null,null,"2016-07-01","2016-12-20"]
[4009,721102,"   Core part: Dedicated Core Networks for GERAN","DECOR_GERAN-Core",2,"Rel-14","R6","2016-06-15","2016-09-15",1,"RP-161029","RP-170194","Ericsson",null,"no Perf. part¦DECOR was a REL-13 SA2 feature¦26/9/16: Compl:0%->100%21/3/17: Stat Rep: ->RP-170194",null,72,37,null,null,"2016-07-01","2017-03-21"]
[4011,721103,"   Core part: Positioning Enhancements for GERAN","ePOS_GERAN-Core",2,"Rel-14","R6","2016-06-15","2017-06-15",1,"RP-171052","RP-170920","Ericsson",null,"26/9/16: Compl:0%->30%¦20/12/16: Compl:30%->50% 21/3/17: Compl:50%->80% ¦19/6/17: Compl:80%->100%;",null,72,37,null,null,"2016-07-01","2017-06-19"]
[4017,730080,"Flexible eNB-ID and Cell-ID in E-UTRAN","LTE_FNBID",1,"Rel-14","R3","2016-03-15","2017-03-15",1,"RP-161896",null,"China Telecom",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[4020,730084,"4 receiver (4Rx) antenna ports with Carrier Aggregation (CA) for LTE downlink (DL)","LTE_4Rx_AP_DL_CA",1,"Rel-14","R4","2016-09-15","2018-09-14",1,"RP-161897",null,"Ericsson",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[4024,740171,"      Core part: Introduction of new band support for 4Rx antenna ports for LTE","LTE_4Rx_AP_DL_bands-Core",3,"Rel-14","R4","2016-12-15","2017-06-15",1,"RP-170307",null,"Huawei",null,"¦21/3/17: Compl:0%->80% ¦2119/6/17: Compl:80%->100%",null,74,38,null,null,"2016-12-20","2017-06-19"]
[4025,750058,"      UE Conformance Test Aspects - 4 Rx antenna ports with CA for LTE DL","LTE_4Rx_AP_DL_CA-UEConTest",3,"Rel-14","R5","2017-03-15","2018-09-14",1,"RP-170704",null,"Ericsson",null,"tested: REL-14 LTE_4Rx_AP_DL_CA-Core¦19/6/17: C 1 8/1/18: C 27/3/ ;¦26/3/19: 90%->100",null,75,38,null,null,"2017-03-21","2019-03-26"]
[4028,730285,"   Perf. part: Requirements for a new UE category with single receiver based on Category 1 for LTE","LTE_UE_cat_1RX-Perf",2,"Rel-14","R4","2016-09-15","2017-09-15",1,"RP-171149",null,"Qualcomm",null,"¦20/12/16: Compl:0%->20%¦20/12/16: CD:Thu 15/06/17->Fri 15/09/17 21/3/17: Compl:20%->70% ¦21/3/17: WID: RP-162570->RP-17079119/6/17: Compl:70%->100%;",null,73,37,null,null,"2016-09-26","2017-06-19"]
[4033,710183,"   Core part: LTE Measurement Gap Enhancement","LTE_meas_gap_enh-Core",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-160912","RP-171330","Intel",null,"¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/06/17->Wed 15/03/17¦1/7/16: WID: RP-160678->RP-160912¦26/9/16: Compl:10%->25%26/9/16: R¦20/12/16: Compl:25%->60% 21/3/17: Compl:60%->95% 19/6/17: Compl:95%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[4036,730282,"   Perf. part: Enhanced CRS and SU-MIMO Interference Mitigation Performance Requirements for LTE","LTE_eCRSIM_eSUMIMO-Perf",2,"Rel-14","R4","2016-09-15","2017-09-15",1,"RP-162303",null,"Intel",null,"6/10/16: 36.176 added¦20/12/16: Compl:0%->30%21/3/17: Compl:30%->50% ¦21/3/17: Release: Rel-15->Rel-14¦19/6/17: Compl:50%->85%19/9/17: Compl:85%->100%",36.176000000000002,73,37,null,null,"2016-09-26","2017-09-19"]
[4039,780052,"   (IETF) SDP Offer/Answer Clarifications for RTP/RTCP Multiplexing [RFC 5761 (was draft-ietf-avtcore-5761-update)]","TEI14_IETF",2,"Rel-14","CT1-IETF","2017-03-15","2017-09-15",1,null,null,null,null,null,null,78,40,null,null,"2017-12-18","NA"]
[4042,870068,"   (IETF) Negotiating Media Multiplexing Using the Session Description Protocol (SDP) (draft-ietf-mmusic-sdp-bundle-negotiation) ","TEI14_IETF",2,"Rel-14","C1-IETF","2020-03-23","2020-04-23",1,null,null,null,null,"9/4/21: RFC 8843 added;","RFC 8843",87,44,null,null,"2020-04-23","2021-04-09"]
[4047,620362,"   TR on Security Assurance scheme for 3GPP network products","SCAS-SA3TR",2,"Rel-14","S3","2013-12-09","2016-12-15",1,"SP-150716","-","NTT DOCOMO","Alf Zugenmaier (alf.zugenmaier@hm.edu)","This TR contains results of the second WID objective. Dec.14: 75->85%¦June2015: Compl:85%->90¦7/12/15: 90%->92¦10/12/15: WID:SP-130718->SP-150716¦19/9/16: 92%->98. FCD set to 12.16 (was 03/16)¦6/10/16: 33.216 added¦1/12/16: 81%->100","New 33.916; 33.216",62,32,null,null,"2013-11-22","2016-12-01"]
[4051,709998,"Rel-14 LTE Carrier Aggregation","LTE_CA_Rel14",1,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"-","-","-","-","Acronym changed from \"LTE_CA_Rel-13\" to \"LTE_CA_Rel13\"",null,58,30,null,null,"2012-12-14","2015-01-15"]
[4052,690086,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12","LTE_CA_B4_B5_B12_B12",2,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151521","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","NA"]
[4055,690087,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12","LTE_CA_B4_B4_B12_B12",2,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151522","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","NA"]
[4060,690288,"      Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12","LTE_CA_B2_B4_B12_B12-Perf",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151523","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[4063,700169,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 5DL/1UL","LTE_CA_R14_5DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-170143",null,"Nokia Networks",null,"28/1/16: 36.714-05-01 added¦22/3/16: Compl:0%->15%¦22/3/16: WID: RP-151671->RP-1606151/7/16: Compl:15%->40%¦26/9/16: Compl:40%->60%¦20/12/16: Compl ¦21/3/17","36.714-05-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[4066,700170,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL","LTE_CA_R14_2DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.8,"RP-170123",null,"Qualcomm",null,"28/1/16: 36.714-02-01 added¦22/3/16: Compl:0%->20%¦22/3/16: WID: RP-152196->RP-160616¦1/7/16: Compl:20%->30%¦1/7/16: WI26/9/16: Compl:30%->50%¦20/12/16: Com 21/3/17: ","36.714-02-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[4069,700171,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL","LTE_CA_R14_2DL2UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-170312",null,"Huawei",null,"28/1/16: 36.714-02-02 added;22/3/16: Compl:0%->20%22/3/16: WID: RP-152237->RP-160192¦1/7/16: Compl:20%->40%¦26/9/16: Compl:40%->60%¦20/12/16: C ¦21/3/17:","36.714-02-02","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[4074,700073,"   LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5","LTE_CA_R14_xDL2UL",2,"Rel-14","R4","2015-12-15","2017-06-15",0.48,"RP-152246",null,"LG Electronics",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[4075,700173,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for xDL/2UL with x=3,4,5","LTE_CA_R14_xDL2UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-170128",null,"LG Electronics",null,"28/1/16: 36.714-00-02 added¦22/3/16: Compl:0%->10%¦22/3/16: WID: RP-152246->RP-160148¦1/7/16: Compl:10%->40%¦26/9/16: Compl:40%->70%¦20/¦21/3/17: ","36.714-00-02","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[4078,700174,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL","LTE_CA_R14_4DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-170189",null,"Ericsson",null,"28/1/16: 36.714-04-01 added;22/3/16: Compl:0%->30%22/3/16: WID: RP-152249->RP-1606141/7/16: Compl:30%->38%¦26/9/16: Compl:38%->74%¦20/12/16: Compl:74%->9521/3/1","36.714-04-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[4082,700275,"      Perf. part: LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R14_intra-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0.82,"RP-170188",null,"Ericsson",null,"¦22/3/16: WID: RP-152250->RP-1606131/7/16: Compl:0%->50%1/7/16: WID: RP-160613->RP-16082226/9/16: WID: RP-160822->RP-161473¦20/12/16: Compl:50%->64% 21/3/17: Compl:64%->",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[4086,720098,"   UE Conformance Test Aspects – Rel-14 CA configurations","LTE_CA_R14-UEConTest",2,"Rel-14","R5","2016-06-15","2021-09-21",1,"RP-160754","RP-211865","Ericsson",null,"testing REL-14 CA basket WIs: LTE_CA_R14_intra-Core, LTE_CA_R14_2DL1UL-Core, LTE_CA_R14_3DL1UL-Core, LTE_CA_R14_4DL1UL-Core, LTE_CA_R14_5DL1UL-Core, LTE_CA_R14_2DL2UL-Core, LTE_CA_R14_xDL2UL-Core, LTE_CA_R14_3DL3UL-Core ;; 8/10/20: 20%->38; 8/10/20: F ",null,72,37,null,null,"2016-07-01","2021-09-13"]
[4091,610032,"Study on need for Multiple Access Point Names","FS_MAPN",1,"Rel-14","S1","2013-09-12","2015-06-19",1,"SP-130416",null,"Giesecke & Devrient","Ilario.macchi@gi-de.com","SP#65 moved to Rel-14. Completion 12/14=>03/15. Triggered by S1-133134 LS on GSMA Connected Living Programme Request for APN Storage in the SIM. Dec.14: 50->70%, CD: 03/15->06/15. Mar.15: 90%¦June2015: Compl:90%->100",22.802,61,31,null,null,"2013-08-26","2015-06-15"]
[4093,630018,"Study on service aspects for dealing with User Control over spoofed calls","FS_UC_SPOOF",1,"Rel-14","S1","2014-03-07","2015-03-20",1,"SP-140074",null,"Sprint","Gregory.schumacher@sprint.com","SP#65 moved to Rel-14. Linked to SA3 Rel-11 TR 33.838 PUCI and Rel-12 ongoing study TR 33.831 (FS_SPOOF). Dec.14: 70->90, CD: 12/14->03/15. Mar.15: 100%",22.898,63,32,null,null,"2014-02-05","2015-03-04"]
[4096,670011,"Study on Paging Policy Enhancements and Procedure Optimizations in LTE","FS_PPEPO_LTE",1,"Rel-14","S1","2015-04-14","2015-12-15",1,"SP-150053",null,"Zhuoyun Zhang (China Unicom)","zhangzy910@chinaunicom.cn","1/4/15:TR number added¦June2015: Compl:0%->40¦07/09/15: 40%->60¦7/12/15: 60%->100","New 22.838",67,34,null,null,"2015-03-04","2015-12-07"]
[4101,700036,"Study on UICC power optimization for MTC","FS_UICC_MTC_OPT",1,"Rel-14","C6","2016-06-15","2016-12-15",1,"CP-150875",null,"Berionne, Michele","micheleb [at] qti [dot] qualcomm [dot] com","7/3/16: 0%->100¦5/6/17: 71%->100",31.97,70,36,null,null,"2015-12-07","2017-06-05"]
[4102,710013,"Study on Server and Network Assisted DASH for 3GPP","FS_SAND",1,"Rel-14","S4","2016-03-01","2016-12-15",1,"SP-160083",null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","11/6/16: 0%->10¦19/9/16: 10%->60¦1/12/16: 60%->100","TR26.957 ",71,36,null,null,"2016-03-01","2016-12-01"]
[4105,710058,"Study on HSPA and LTE Joint Operation","FS_UTRA_LTE_JOP",1,"Rel-14","R3","2016-03-15","2016-12-15",1,"RP-160571",null,"China Unicom",null,"¦1/7/16: Compl:0%->30%¦26/9/16: Compl:30%->80%¦ 20/12/16: Compl:80%->100%¦","New 37.805",71,36,null,null,"2016-03-22","2016-12-20"]
[4109,670015,"Study on Determination of Completeness of Charging Information in IMS","FS_DCCHII",1,"Rel-14","S5","2015-03-05","2016-03-11",1,"SP-150106",null,"Jesske, Roland","r.jesske@telekom.de","11/03/15: WID changed from FS_DCCII to FS_DCCHII as per SA5 chair request¦June2015: Compl:0%->7¦07/09/15: 7%->15¦7/12/15: 15%->60, FCD: 09/15->03/16¦7/3/16: 60%->100. 22/3/16: Rel-13->Rel-14","32.xyz",67,34,null,null,"2015-03-05","2016-03-22"]
[4113,720088,"Study on global application of LTE Band 11 and of LTE Band 21 UEs","FS_LTE_B11_B21_global",1,"Rel-14","R4","2016-06-15","2016-12-15",1,"RP-161220",null,"SoftBank",null,"26/9/16: Compl:0%->30%¦6/10/16: 36.745 added¦20/12/16: Compl:30%->100%",36.744999999999997,72,37,null,null,"2016-07-01","2016-12-20"]
[4118,700023,"   FS_SMARTER – massive Internet of Things","FS_SMARTER-mIoT",2,"Rel-14","S1","2015-11-02","2016-06-10",1,"SP-150817",null,"Adrian Neal (Vodafone)","adrian.neal@vodafone.com","2/3/16: 35%->65¦9/6/16: 65%->100","New 22.861",70,36,null,null,"2015-12-07","2016-06-09"]
[4121,700026,"   FS_SMARTER – Network Operation","FS_SMARTER-NEO",2,"Rel-14","S1","2015-11-02","2016-06-10",1,"SP-150820",null,"Lu Lu","lulu@chinamobile.com","2/3/16: 30%->60¦19/9/16: 60%->100","New 22.864",70,36,null,null,"2015-12-07","2016-09-19"]
[4124,0,"--- RELEASE 13 ---","-",1,"Rel-13","SP,RP,CP,GP","2013-12-11","2014-11-25",1,"-","-",null,null,"-","-",null,null,null,null,"2013-03-04","2013-03-04"]
[4127,670030,"   SA2 Study on Architecture Enhancements at the EPS and IMS Level to Support MCPTT","MCPTT",2,"Rel-13","S2","2015-03-13","2015-06-17",1,"SP-150356",null,"Randy Bloomfield (randy@its.bldrdoc.gov)","Randy Bloomfield (randy@its.bldrdoc.gov)","Mar 2015: WID: SP-140879->SP-150164.¦June2015: Compl:0%->30, WID updated¦07/09/15: 30%->100, \"To be confirmed\" deleted, since SA2 has completed it.",null,67,34,null,null,"2015-03-13","2015-09-07"]
[4129,670022,"   Study on media, codecs and MBMS enhancements for MCPTT","MCPTT",2,"Rel-13","S4","2014-12-12","2016-03-11",1,"SP-150356",null,"Zhiming Li (lizhiming@huawei.com)","Zhiming Li (lizhiming@huawei.com)","Mar 2015: WID: SP-140879->SP-150164. Name clarified. 5/5/15: TR number added¦June2015: Compl:0%->5, WID updated¦Aug2015: 5%->15¦07/09/15: 15%->40¦7/12/15: 40%->80, FCD: 12/15->03/16¦7/3/16: 80%->85; 26/6/20: 85%->100","New 26.879",67,34,null,null,"2015-03-05","2020-06-26"]
[4132,660053,"   Security of MCPTT","MCPTT",2,"Rel-13","S3","2014-12-12","2016-03-11",1,"SP-150356",null,"Peter Haigh (peter.haigh at cesg.gsi.gov.uk)","Peter Haigh (peter.haigh at cesg.gsi.gov.uk)","Mar 2015: WID: SP-140879->SP-150164. Name clarified. FCD: 03/2016->12/2015¦June2015: Compl:5%->15, WID updated. 7/9/15: TS number added¦7/12/15: 15%->60. FCD -> 03/16, ES in SP-150729¦7/3/16: 60%->85¦1/12/16: 85%->98¦6/3/17: 98%->100",33.179000000000002,66,34,null,null,"2014-12-12","2017-03-06"]
[4136,690096,"         Call Control – On Network","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->50¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 50%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.379000000000001,69,35,null,null,"2015-09-29","2016-12-05"]
[4140,691000,"         Broadcast – Call Control and Floor Control","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->50¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 50%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817","24.379; 24.380",69,35,null,null,"2015-09-29","2016-12-05"]
[4145,690028,"      CT3 aspects for MCPTT protocol aspects","MCPTT-CT",3,"Rel-13","C3","2015-09-07","2016-03-11",1,"CP-160817",null,"Alcatel-Lucent, Keith Drage","keith.drage@alcatel-lucent.com","7/12/15: 0%->70¦7/12/15: WID:CP-150587->CP-150863. FCD -> 03/16, ES in CP-150643¦7/3/16: 70%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",29.164999999999999,69,35,null,null,"2015-09-07","2016-12-05"]
[4148,710034,"      (IETF) IANA Registration of New SIP Resource- Priority Namespace for MCPTT","MCPTT-CT",3,"Rel-13","C1-IETF","2016-02-10","2016-06-30",1,"CP-160817",null,"Ericsson","christer.holmberg@ericsson.com","5/12/16: WID:CP-160160->CP-160817","draft-holmberg-dispatch-mcptt-rp-namespace",71,36,null,null,"2016-03-07","2016-12-05"]
[4151,740070,"   UE Conformance Test Aspects - Support for Mission Critical Push To Talk over LTE (MCPTT)","MCPTT-ConTest",2,"Rel-13","R5","2016-12-15","2018-06-15",1,"RP-180132",null,"US Department of Commerce",null,"6/1/17: acronym changed from \"MCPTT-UEConTest\" ¦21/3/17: Compl:0%->5%¦21/3/17: 36.579-5 added;","36.579-5",74,38,null,null,"2016-12-20","2018-06-27"]
[4154,660054,"   Deleted (duplicated): SA6 aspects for MCPTT","MCPTT",2,"Rel-13","S6","2014-12-12","2015-12-11",1,"SP-150356",null,"David Cypher (david.cypher at nist.gov)","David Cypher (david.cypher at nist.gov)","Mar 2015: WID: SP-140879->SP-150164. Name clarified. 6/15: WID updated. 31 July: deleted since duplicates 640143 and 670031 (only 640143 is kept)",null,66,34,"SP-69",null,"2014-12-12","2015-06-18"]
[4156,670090,"   TR on Profiling and Extensions of MBMS","MEPRO",2,"Rel-13","S4","2015-03-05","2015-12-11",1,"SP-150439",null,"Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson","i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com","8/4/15: line added¦June2015: Compl:0%->10¦Aug2015: 10%->15¦07/09/15: 15%->40¦14/09/15: WID:SP-150099->SP-150439¦7/12/15: 40%->100","new 26.852",67,34,null,null,"2015-04-08","2015-12-07"]
[4159,680047,"   Stage 1 fo Isolated E-UTRAN Operation for Public Safety","IOPS",2,"Rel-13","S1","2014-03-07","2014-09-17",1,"SP-150463","S1-143304","General Dynamics","paul.piggin@gd-broadband.com","SP#65 completed. TS 22.346v100 for 1-step Approval. Triggered by Rel-13 TR 22.897 (FS_IOPS)¦14/09/15: WID:SP 150358->SP-150463","New 22.346",63,32,null,null,"2014-02-05","2015-09-14"]
[4163,700038,"      CT6 aspects for IOPS","IOPS-CT",3,"Rel-13","C6","2015-11-02","2016-03-11",1,"CP-150876",null,"Heiko Kruse, Morpho Cards GmbH","heiko.kruse@mrpho.com","ES in CP-150837¦7/3/16: 0%->100",31.102,70,36,null,null,"2015-12-07","2016-03-07"]
[4167,650055,"   Stage 1 for Flexible Mobile Service Steering","FMSS-ST1",2,"Rel-13","S1","2014-09-15","2014-09-17",1,"SP-140638","S1-143310","China Mobile","Lu Lu (lulu@chinamobile.com)","SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS). Dec.14: moved from Feature to S1 BB",22.100999999999999,65,33,null,null,"2013-11-26","2014-12-03"]
[4170,690024,"   CT3 Aspect of Flexible Mobile Service Steering","FMSS-CT",2,"Rel-13","C3","2015-09-09","2016-03-11",1,"CP-150799",null,"ZTE,Zhou Xiaoyun","zhou.xiaoyun@zte.com.cn","07/09/15: 0%->20¦14/09/15: WID:CP-150488->CP-150577¦7/12/15: 20%->90¦7/12/15: WID:CP-150577->CP-150799. FCD -> 03/16. ES in CP-150646¦7/3/16: 90%->100","29.abc; 29.212; 29.213",69,35,null,null,"2015-09-09","2016-03-07"]
[4172,640052,"Application specific Congestion control for Data Communication","ACDC",1,"Rel-13","S1,C1","2014-06-18","2016-03-11",1,"SP-140234","S1-143305","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#65 completed. Triggered by Rel-13 Study TR 22.806",22.010999999999999,64,33,null,null,"2014-05-27","2014-08-29"]
[4178,670159,"      Core part: RAN aspects of Application specific Congestion control for Data Communication","ACDC-RAN-Core",3,"Rel-13","R2","2015-03-16","2015-12-15",1,"RP-150662","RP-151275","LG Electronics",null,"03/07/15: Compl:0%->25% 03/07/15: WID: RP-150512->RP-150662 03/07/15: Stat Rep: ->RP-150661 29/09/15: Compl:25%->70% 29/09/15: Stat Rep: RP-150661->RP-151275¦1/1/16: Compl:70%->100%",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4181,580057,"   TR on Stage 2 for User Plane Congestion management","UPCON-SA2TR",2,"Rel-13","S2","2012-12-12","2015-03-18",1,"SP-140631","-","Allot","Alla Goldner (agoldner@allot.com)","SP#65 updated WID SP-140153=>SP-140631. TR 23.705v100 for Information. Dec.14: 87->98%. Mar15: 100%","new 23.705",58,30,null,null,"2012-11-13","2015-03-05"]
[4183,630019,"   BB1: RAN Downlink Traffic Differentiation, Congestion Detection and Reporting","UPCON-DOTCON",2,"Rel-13","S2","2014-03-07","2015-03-13",1,"SP-140631","-","Allot","Alla Goldner (agoldner@allot.com)","SP#65 updated WID SP-140153=>SP-140631. IncludES in CP-150RAN Congestion Detection: , RAN Traffic Differentiation, RAN Congestion Reporting, CN Congestion Mitigation mechanisms, Dynamic Policy Control","-",63,32,null,null,"2014-03-04","2014-09-16"]
[{"$f":"A4186+1","v":4186},650107,"         CT3 part of CT aspects of User Plane Congestion Management for BB1","UPCON-DOTCON-CT",4,"Rel-13","C3","2014-03-18","2015-03-13",1,"CP-150365","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","Dec.14: 0->60¦WID: CP-140734->CP-140929. Mar.15: 60->95%¦June2015: Compl:95%->100. WID: CP-140929-> CP-150365.","29.201; 29.212; 29.213; 29.214; 29.215; 29.219; New 29.217 (PCC over Np)",65,33,null,null,"2014-07-29","2015-06-15"]
[4190,650028,"Media Handling Aspects of IMS-based Telepresence","IMS_TELEP_S4",1,"Rel-13",null,"2014-09-09","2017-03-15",1,"SP-140483","-","Intel","ozgur.oyman@intel.com","Can be seen as an \"enhancement\" of Rel-12 IMS-based Telepresence (IMS_TELEP) UID_530042. Mar. 15: 20%","-",65,33,null,null,"2014-09-05","2015-03-05"]
[4194,710036,"   (IETF) Mapping RTP streams to CLUE media captures (draft-ietf-clue-rtp-mapping)","IMS_TELEP_S4",2,"Rel-13","S4-IETF","2015-12-10","2017-03-15",1,null,null,"Intel","ozgur.oyman@intel.com","23/4/20: 60%->90; 9/4/21: RFC 8849 added;","26.22; RFC 8849",71,36,null,null,"2016-03-07","2021-04-09"]
[4197,600045,"RAN Sharing Enhancements","RSE",1,"Rel-13","S1,R3","2013-06-19","2015-12-15",1,"SP-130330","-","NEC","joerg.swetina@neclab.eu","Triggered by Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE)","-",60,31,null,null,"2013-06-03","2013-11-26"]
[4199,650021,"   RAN aspects of RAN Sharing Enhancements for LTE","RSE-RAN_LTE",2,"Rel-13","R3","2014-09-12","2015-12-15",1,"RP-141671","-","NEC","Siva.Vakeesar@emea.nec.com","Triggered by TR 36.856 Study on RAN aspects of RAN Sharing Enhancements for LTE (FS_RSE-RAN_LTE) & SA1 22.101 Stage 1","LTE",65,33,null,null,"2014-06-16","2014-10-05"]
[4205,650122,"   TR on Security for Enhancements to WEBRTC interoperability","eWebRTCi",2,"Rel-13","S3","2014-09-17","2015-09-30",1,"SP-140630","-","Ericsson","vesa.lehtovirta@ericsson.com","SP#65 updated WID SP-14028=>SP-140630 (added SA3 part). Dec.14: 0->20%, TR number added. 3/3/15: 30%.¦June2015: Compl:30%->75¦11/12/15: 54%->100¦11/12/15: 100%->100","New 33.872 ",65,33,null,null,"2014-09-04","2015-12-11"]
[4208,690012,"   Stage 3 for Enhancements to WebRTC interoperability","eWebRTCi-CT",2,"Rel-13","ct","2015-09-07","2016-06-16",1,"CP-150767",null,"China Mobile, Song Yue","songyue@chinamobile.com","7/12/15: WID:CP-150498->CP-150790->CP-150767",null,69,35,null,null,"2015-09-07","2015-12-07"]
[4212,710039,"      (IETF) SDP-based Data Channel Negotiation (draft-ietf-mmusic-data-channel-sdpneg)","eWebRTCi-CT",3,"Rel-13","C1-IETF,SA4-IETF","2015-12-08","2016-03-11",1,null,null,"Ericsson","christer.holmberg@ericsson.com","7/3/16: Introduced by IETF updates; 23/4/20: 75%->90; 9/4/21: RFC 8864 added;","24.371; 24.229; RFC 8864",71,36,null,null,"2016-03-07","2021-04-09"]
[4213,710040,"      (IETF) MSRP over Data Channels (draft-ietf-mmusic-msrp-usage-data-channel)","eWebRTCi-CT",3,"Rel-13","C1-IETF","2015-12-08","2016-03-11",1,null,null,"Ericsson","christer.holmberg@ericsson.com","7/3/16: Introduced by IETF updates","24.371; 24.229; 26.223",71,36,null,null,"2016-03-07","2016-03-07"]
[4217,630016,"Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks","CSPS_Coord",1,"Rel-13","S2","2014-03-07","2016-05-12",1,"SP-140168","-","Ericsson","roland.gustafsson@ericsson.com","Provide improvements to the solutions for CS/PS coordination in TS 23.251 to ensure that CS/PS coordination can be achieved for all mobility scenarios","Stage 2",63,32,null,null,"2014-02-05","2014-03-04"]
[4221,640040,"Enhancements to Proximity-based Services","eProSe",1,"Rel-13","S1,S2,S3","2013-03-18","2016-03-11",1,"SP-140386","-","Qualcomm","Eddy Hall (edhall@qti.qualcomm.com)","-","Stage 1/2",64,33,null,null,"2014-05-27","2014-09-05"]
[4224,640141,"   TR on Stage 2 for Enhancements to Proximity-based Services - Extensions","eProSe-Ext-SA2TR",2,"Rel-13","S2","2014-06-18","2015-03-13",1,"SP-150028","-","Qualcomm","Haris Zisimopoulos (harisz@qti.qualcomm.com)","SP#65 updated WID SP-140385=>SP-140573 (added SA3 part). Acronym corrected: eProSe-Ex-SA2TRt->eProSe-Ext-SA2TR. Mar15: 60% Mar15: WID: SP-140573 ->SP-150028¦June2015: Compl:60%->90¦07/09/15: 90%->95¦07/09/15: 95%->100","New 23.713",64,33,null,null,"2014-06-17","2015-09-07"]
[4226,680006,"   CT aspects of enhancements to Proximity-based","eProSe-Ext-CT",2,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150370",null,"Lena Chaponniere","lguellec@qti.qualcomm.com",null,"23.122; 24.301; 24.333; 24.334",68,35,null,null,"2015-06-15","2015-06-15"]
[4232,729999,"   Note: Charging Aspects done in Rel-14 under CH14-Prose (UID 720049)","eProSe",2,"Rel-13","S5","2015-06-17","2015-06-17",1,null,null,null,null,null,null,72,37,null,null,"2016-06-13","2016-12-01"]
[4233,640045,"voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD",1,"Rel-13","S1,S2,C4,C1,C3","2014-06-16","2014-12-12",1,"SP-140394","-","Alcatel-Lucent","(betsy.covell@alcatel-lucent.com)","-","Stage 1/2",64,33,null,null,"2014-05-29","2014-06-11"]
[4239,650303,"      CT3 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD-CT",3,"Rel-13","C3","2014-09-16","2014-12-09",1,"CP-140491","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","Mar.15: 0->100%",29.061,65,33,null,null,"2014-07-29","2015-03-04"]
[4240,640047,"IP Flow Mobility support for S2a and S2b Interfaces","NBIFOM",1,"Rel-13","S2","2014-06-18","2016-06-15",1,"SP-150250","-","Tricci So, ZTE","tso@zte.com.cn","06/15: WID: SP-140279->SP-150250","Stage 2",64,33,null,null,"2014-05-30","2015-06-18"]
[4244,680019,"   CT aspects of IP Flow Mobility support for S2a and S2b Interfaces ","NBIFOM-CT",2,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150874",null,"Xingyue(Joy) Zhou, ZTECorporation","zhou.xingyue@zte.com.cn","14/09/15: WID:CP-150285->CP-150497¦7/12/15: WID:CP-150497->CP-150791->874",24.161000000000001,68,35,null,null,"2015-06-15","2015-12-07"]
[4248,640053,"Double Resource Reuse for Multiple Media Sessions","DRuMS",1,"Rel-13","S2","2014-03-14","2015-03-13",1,"SP-140393","-","Ericsson","George.Foti@ericsson.com","-","Stage 2",64,33,null,null,"2014-05-30","2014-06-11"]
[4251,660047,"      CT1 aspects of Double Resource Reuse for Multiple Media Sessions","DRuMS-CT",3,"Rel-13","C1","2014-12-03","2015-03-13",1,"CP-140926",null,"Ericsson",null,"5/5/15: C3 corrected in C1¦June2015: Compl:65%->90¦07/09/15: 90%->100","24.229; 24.615; 24.610; 24.605",66,34,null,null,"2014-12-09","2015-09-07"]
[4255,640058,"Video enhancements by Region-Of-Interest information signalling","ROI",1,"Rel-13","S4","2014-06-18","2015-12-16",1,"SP-140219","-","Intel","ozgur.oyman@intel.com","Dec.14: 5->20%. Mar.15: 40%¦07/09/15: 43%->100",26.114000000000001,64,33,null,null,"2014-06-06","2015-09-07"]
[4257,680017,"   CT Aspects of Video Enhancements by Region-Of-Interest information signalling","ROI-CT",2,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150425",null,"Vivek Gupta, Intel","vivek.g.gupta@intel.com","14/09/15: WID:CP-150241->CP-150425",null,68,35,null,null,"2015-06-15","2015-09-14"]
[4260,680034,"      CT4 Aspects of Video Enhancements by Region-Of-Interest information signalling","ROI-CT",3,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150425",null,"Vivek Gupta, Intel","vivek.g.gupta@intel.com","07/09/15: 100%->5¦14/09/15: WID:CP-150241->CP-150425¦7/12/15: 5%->100","23.334; 29.334; 29.238",68,35,null,null,"2015-06-15","2015-12-07"]
[4263,650226,"   Specification on TV video profile","TVProf-SA4",2,"Rel-13","S4","2014-09-09","2016-03-11",1,"SP-140481","-","Orange","gilles.teniou@orange.com","Dec.14: 0->5%¦June2015: Compl:15%->30¦Aug2015: 30%->45¦07/09/15: 45%->70¦7/12/15: 70%->85, FCD: 12/15->03/16. ES in SP-150650¦7/3/16: 85%->100","26.234; 26.244; 26.346; 26.247; New 26.xyz; ES in SP-150650",65,33,null,null,"2014-09-05","2016-03-07"]
[4266,650030,"Support of EVS in 3G Circuit-Switched networks","EVSoCS",1,"Rel-13","S4,C4,C1,C3,R1,R2,R3","2014-09-09","2016-03-11",1,"SP-140485","-","Qualcomm","Imre Varga (ivarga@qti.qualcomm.com)","Provide CS support of EVS to enhance voice quality in CS services over UTRAN (3G WCDMA). Dec.14: 0->5%¦28/1/16: 26.454 added¦28/1/16: 26.453 added;","26.103; 28.062; New 26.454; New 26.453",65,33,null,null,"2014-09-05","2016-01-28"]
[4271,670019,"      CT4 aspects of EVS in 3G Circuit-Switched Networks","EVSoCS-CT",3,"Rel-13","C4","2015-03-04","2016-03-11",1,"CP-150200",null,"Qualcomm, Lena Chaponniere","lguellec@qti.qualcomm.com","June2015: Compl:0%->95. FCD -> 03/16, ES in CP-150618¦7/3/16: 95%->100","23.153; 23.334; 29.002; 29.231; 29.232; 29.332; 29.334",67,34,null,null,"2015-03-04","2016-03-07"]
[4275,650032,"QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3)","QOSE2EMTSI",1,"Rel-13","S4,C3,C1,C4","2013-03-06","2016-03-11",1,"SP-140601","-","Ericsson","tomas.frankkila@ericsson.com","SP#65 updated WID SP-130670=>SP-140601 (moved work from Rel-12 incl. new TR to Rel-13). Co-ordinate with SA2, CT1/3/4, IETF MMUSIC. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040","-",59,30,null,null,"2013-02-20","2014-09-20"]
[4278,660043,"   CT Aspects of QoS End-to-End MTSI Extensions","QOSE2EMTSI-CT",2,"Rel-13","C3,C1,C4","2014-11-05","2016-03-11",1,"CP-140925",null,"Ericsson",null,null,null,66,34,null,null,"2014-12-09","2014-12-09"]
[4282,660050,"MTSI Extension on Multi-stream Multiparty","MMCMH",1,"Rel-13",null,"2014-12-12","2016-03-07",1,"SP-150660",null,"Tomas Frankkila, Ericsson LM","tomas.frankkila@ericsson.com","Mar. 15: 0->10%. WID: SP-140738->SP-150097¦June2015: Compl:10%->30¦Aug2015: 30%->50, FCD: sep->Dec 2015¦07/09/15: 50%->60¦7/12/15: 60%->100¦10/12/15: WID:SP-150097->SP-150660. Might be moved to Rel-14 (see note in UID710002)","26.114; New 26.980",66,34,null,null,"2014-12-12","2015-12-10"]
[4284,710043,"   (IETF) RTP Stream Pause and Resume (RFC 7728)","MMCMH",2,"Rel-13","S4-IETF","2015-12-07","2016-03-07",1,"SP-150660",null,"Ericsson","tomas.frankkila@ericsson.com","02/2016: published as RFC 7728","(IETF) RTP Stream Pause and Resume (RFC 7728)",71,36,null,null,"2014-12-12","2016-03-07"]
[4287,660151,"   TR on Video Telephony Robustness Improvements","VTRI_EXT",2,"Rel-13","S4","2014-12-12","2015-09-11",1,"SP-140739",null,"Muhammed Coban, Qualcomm Incorporated","mcoban@qti.qualcomm.com","3/3/15: created to distinguish TR and TS tasks¦June2015: Compl:10%->40¦Aug2015: 40%->95¦07/09/15: 95%->100","26.922 (new); 26.114",66,34,null,null,"2015-03-03","2015-09-07"]
[4290,660052,"Acoustic Test methods and Performance Objectives for Speakerphone Performance in Noisy Environments","ATeMPO_SPINE",1,"Rel-13","S4","2014-12-12","2016-03-11",1,"SP-140740",null,"Andre Schevciw, Qualcomm Incorporated; Scott Isabelle, Audience Inc.","aschevci@qti.qualcomm.com; sisabelle@audience.com","June2015: Compl:0%->10. Aug: FCD: Jun->Sep15¦07/09/15: 10%->30, FCD:09/15->12/15¦7/12/15: 40%->80, FCD: 12/15->03/16. ES in SP-150642¦7/3/16: 80%->100","26.131; 26.132",66,34,null,null,"2014-12-12","2016-03-07"]
[4293,560034,"   Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations","OAM-NGMN_OPE",2,"Rel-13","S5","2012-06-20","2015-03-18",1,"SP-140538","-","Huawei","christian.toche@huawei.com","SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13. Source of external requirements: NGMN Top OPE Recommendations 1.0","-",56,29,null,null,"2012-05-14","2014-09-01"]
[4298,560136,"      WLAN Network Resource Model for Type-2 interface","WLAN-OAM-SA5",3,"Rel-13","S5","2012-06-27","2015-06-17",1,"SP-140535","-","Intel","joey.chou@intel.com","SP#65 updated WID SP-130042=>SP-140535. Completion 09/14=>06/15. Moved to Rel-13. Dec.14: 10->20¦June2015: Compl:20%->70¦07/09/15: 70%->80¦7/12/15: 80%->100","new (28.680; 28.682); 28.681",56,29,null,null,"2012-06-12","2015-12-07"]
[4301,660055,"   Multi-Broadcast Single Frequency Network (MBSFN) Minimization of Drive Tests (MDT) enhancement","MBSFN_MDT",2,"Rel-13","S5","2014-12-12","2014-12-12",1,"SP-140786",null,"Padma Sudarsan (Alcatel-Lucent) ","padma.sudarsan<AT>alcatel-lucent<DOT>com","Mar 15: 0->15%¦June2015: Compl:15%->100","32.421; 32.422; 32.423; 32.441; 32.442; 32.446",66,34,null,null,"2014-12-12","2015-06-15"]
[4306,660056,"   ULI and release causes for charging enhancement for VoLTE","ULRELC-CH",2,"Rel-13","S5","2014-12-12","2015-12-07",1,"SP-140785",null,"Alcatel-Lucent, Maryse Gardella","Alcatel-Lucent, Maryse <dot> Gardella <at> Alcatel-Lucent <dot> com","Acronym changed to ULRELC-CH. Mar15: 0->5%. CD: 12/14->09/15. 06/15: 20%¦07/09/15: 20%->40¦7/12/15: 40%->100, FCD: 09/15->12/15","32.251; 32.260; 32.299; 32.298; ",66,34,null,null,"2014-12-12","2015-12-07"]
[4309,680038,"   Enhanced S2a Mobility Over Trusted WLAN access to EPC - Charging ","eSaMOG-CH",2,"Rel-13","S5","2015-06-15","2015-09-17",1,"SP-150344",null,"Alcatel-Lucent, Maryse <dot> Gardella <at> Alcatel-Lucent <dot> com",null,"07/09/15: 0%->30¦7/12/15: 30%->100","32.240; 32.251; 32.299; 32.298",68,35,null,null,"2015-06-14","2015-12-07"]
[4311,610105,"   CT4 part of Support of RTP / RTCP multiplexing (signalling) in IMS","RTCP_MUX",2,"Rel-13","C4","2013-09-09","2015-12-11",1,"CP-130436","-","Alcatel-Lucent","Albrecht.Schwarz@alcatel-lucent.com","CP#65 moved to Rel-13. Completion 09/14=>12/15. Dec.14: 10->100","23.334; 29.334",61,31,null,null,"2013-08-10","2014-12-04"]
[{"$f":"A4314+1","v":4314},550017,"LTE in the 1670-1675 MHz Band for US (on hold till 12/2014)","LTE_FDD_1670_US",1,"Rel-13","R4,R2,R3","2012-03-05","2015-06-09",0.08,"RP-121397","-","LightSquared","masoud.olfat@lightsquared.com","RP#65 FS_LTE_FDD_1670_US is extended to 12/14 and this WI (LTE_FDD_1670_US) is on hold till 12/14","LTE",55,28,null,null,"2012-02-23","2014-09-09"]
[4317,640019,"Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE","COMP_LTE_IeNB_sig",1,"Rel-13","R3","2014-06-18","2015-09-15",1,"RP-141032","-","Samsung","sunghwan.won@samsung.com","Triggered by TR 36.874 Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul (UID_600015)","LTE",64,33,null,null,"2014-06-16","2014-06-23"]
[4320,640136,"   Core part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)","LTE_1980_2170_REG1-Core",2,"Rel-13","R4","2014-06-17","2015-12-15",1,"RP-151732","RP-151299","DISH Network","johny.kim@dish.com, mariam.sorond@dish.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:5%->15%¦Stat Rep: RP-141627->RP-141795 1st Apr 15: Compl:15%->35% 1st Apr 15: WID: RP-141710->RP-150424 1st Apr 15: Stat Rep: RP-141795->RP-150106 03/07/15: Compl:35%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03","36.101; 36.104; 36.133; 36.141; 36.307; generic 36.853 (3 Band CA with 1UL); New 36.862 (Technical Report for 2 GHz Band in Region 1)",64,33,null,null,"2014-06-16","2016-01-01"]
[4325,660001,"Usage Monitoring Control PCC Extension","eUMONC",1,"Rel-13","S2","2014-12-03","2015-06-16",1,"SP-140709",null,"CTBRI",null,null,null,66,34,null,null,"2014-12-03","2014-12-03"]
[4328,660030,"Enhanced P-CSCF discovery using signalling for access to EPC via WLAN","ePCSCF_WLAN",1,"Rel-13","C1","2014-10-06","2015-03-13",1,"CP-140813",null,"Ericsson",null,null,null,66,34,null,null,"2014-12-04","2014-12-09"]
[4333,660040,"   CT4 aspects of P-CSCF Restoration Enhancements with WLAN","PCSCF_RES_WLAN",2,"Rel-13","C4","2014-12-03","2015-12-11",1,"CP-150275",null,"Jean-Jacques Trottin, Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com ","Dec.14: 0->5%. Mar.15: 5->100%. 2/4/15: acronym changed to PCSCF_RES_WLAN¦June2015: Compl:100%->75. June 2015: WID: CP-140995-> CP-150275¦07/09/15: 75%->85¦7/12/15: 85%->100","New 29.8xy; 23.380; 29.273; 29.274; 29.275; 23.008",66,34,null,null,"2014-12-09","2015-12-07"]
[4336,680040,"   CT4 aspects of Mobile Equipment Identity signalling over WLAN","MEI_WLAN",2,"Rel-13","C4","2015-06-15","2015-09-17",1,"CP-150236",null,"Bruno Landais, Alcatel-Lucent","bruno.landais@alcatel-lucent.com","07/09/15: 0%->90¦7/12/15: 90%->100","29.273; 29.274; 29.275; 23.008",68,35,null,null,"2015-06-15","2015-12-07"]
[4339,670037,"   SAE Protocol Development (Stage 3) - Phase 4","SAES4",2,"Rel-13","C1","2014-12-03","2015-12-11",1,"CP-140814",null,"interdigital",null,"WP Structure created 24/03/15 to avoid confusion in Acronyms. 5/5/15: acronym changed from \"SAES4-CT1\"¦June2015: Compl:0%->30¦07/09/15: 30%->70¦7/12/15: 70%->100",null,66,34,null,null,"2015-03-24","2015-12-07"]
[4342,660034,"Interworking solution for Called IN number and original called IN number ISUP parameters ","INNB_IW",1,"Rel-13","C1,C3","2014-12-03","2015-03-13",1,"CP-140928",null,"Orange",null,null,null,66,34,null,null,"2014-12-04","2014-12-09"]
[4344,660036,"   (IETF) CT1 part of Interworking solution for Called IN number and original called IN number ISUP parameters","INNB_IW",2,"Rel-13","C1-IETF","2014-12-03","2015-03-10",1,"CP-140928",null,"Orange",null,"Mar15: resp WG:C1->C1-IETF. WID changed from INNB_IW-CT1","draft-mohali-dispatch-cause-for-service-number",66,34,null,null,"2014-12-04","2015-03-18"]
[4347,660015,"   CT1 aspects of Warning Status Report in EPS","WSR_EPS",2,"Rel-13","C1","2014-12-03","2015-09-14",1,"CP-150792",null,"one2many",null,"2/4/15: acronym changed to WSR_EP. 5/5/15: acronym changed from \"WSR_EP\"¦07/09/15: 0%->25¦7/12/15: 25%->100¦7/12/15: WID:CP-140998->CP-150792","New 23.712",66,34,null,null,"2014-12-04","2015-12-07"]
[4351,670096,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc7",2,"Rel-13","C1","2014-12-03","2015-12-11",1,"CP-140815",null,"Alcatel-Lucent","Keith Drage","Mar.15: 0->10%¦June2015: Compl:10%->30¦07/09/15: 30%->70¦7/12/15: 70%->100",null,66,34,null,null,"2014-12-04","2015-12-07"]
[4355,670020,"H.248 Aspects of WebRTC Data Channel on IMS Access Gateway","WebRTCH248DC",1,"Rel-13","C4","2015-03-04","2016-03-11",1,"CP-150185",null,"China Mobile, Xiaoning Du","duxiaoning@chinamobile.com",null,23.334,67,34,null,null,"2015-03-04","2015-03-09"]
[4360,680042,"   CT3 aspects of Controlling IMS Media Plane with SDP Capability","SDPCN_IMS",2,"Rel-13","C3","2015-06-15","2016-03-11",1,"CP-150238",null,"Weiwei(Tommy) Yang, Huawei. ES in 640","tommy@huawei.com","7/12/15: 0%->90. FCD->03/16. ES in CP-150614¦7/3/16: 90%->100","29.162; 29.163; 29.292; 29.235",68,35,null,null,"2015-06-15","2016-03-07"]
[4363,660012,"   Stage 1 for Co-ordinated packet data network gateway (P-GW) change for SIPTO","CSIPTO-ST1",2,"Rel-13","S1","2014-06-18","2014-09-16",1,"SP-140509","S1-143306","Intel","Eric.siow@intel.com","SP#65 completed. Updated WID SP-140235=>SP-140509. Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO). Dec.14: former S1-only feature split",22.100999999999999,64,33,null,null,"2014-05-27","2014-12-03"]
[4366,640251,"   Deleted - Stage 2 for Enhanced CS Fallback (CSFB)","eCSFB",2,"Rel-13","S2","2015-03-13","2015-03-13",1,"SP-140579","-","China Unicom","Yang Xu (xuyang49@chinaunicom.cn)","SP#65 updated ID SP-140285=>SP-140579 (added SA3 part)",23.271999999999998,64,33,"SP-69",null,"2014-06-11","2014-06-11"]
[4369,650125,"   TR for SRVCC Enhancements for Transcoding Avoidance","SETA-SA2TR",2,"Rel-13","S2","2014-09-19","2015-03-13",1,"SP-140436","-","Ericsson","George.Foti@ericsson.com","Dec.14: 0->70%¦14/09/15: 70%->100. Stopped without conclusion, no intention to continue the study nor to do any mormative work.","New 23.7xy",65,33,null,null,"2014-08-05","2015-09-14"]
[4371,590030,"Base Station (BS) RF requirements for Active Antenna System (AAS)","AAS_BS_LTE_UTRA",1,"Rel-13","R4","2013-03-04","2016-09-15",1,"RP-130373","-","Huawei","ronnie.zhang@huawei.com","Triggered by Rel-12 TR 37.840 Study of RF and EMC Requirements for Active Antenna Array System BS (FS_AAS_BS_LTE_UTRA)","UTRA; LTE; GERAN",59,30,null,null,"2013-02-26","2014-09-15"]
[4375,660174,"   Core part: Enhanced LTE Device to Device Proximity Services","LTE_eD2D_Prox-Core",2,"Rel-13","R2,R1,R3","2015-08-14","2016-03-15",1,"RP-150441","RP-151337","Qualcomm Incorporated, Shailesh Patil","patil@qti.qualcomm.com ","Rapporteur details and involved WGs updated 1st Apr 15: WID: RP-142311->RP-150441 1st Apr 15: Stat Rep: ->RP-150095 03/07/15: Compl:0%->32% 03/07/15: Stat Rep: RP-150095->RP-150795 29/09/15: Compl:32%->55% 29/09/15: Stat Rep: RP-150795->RP-151337¦",null,66,34,null,null,"2015-01-12","2016-03-22"]
[{"$f":"A4378+1","v":4378},660176,"   Core part: Radiated requirements for the verification of multi-antenna reception performance of UEs","UTRA_LTE_MIMO_OTA-Core",2,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-160344","RP-151573","Intel","Intel","1st Apr 15: Compl:0%->5% 1st Apr 15: WID: RP-142221->RP-150261 1st Apr 15: Stat Rep: ->RP-150260 03/07/15: Compl:5%->15% 03/07/15: Stat Rep: RP-150260->RP-150746 29/09/15: Compl:15%->25% 29/09/15: WID: RP-150261->RP-151574 29/09/15: Stat Rep: RP-15074",null,66,34,null,null,"2015-01-12","2016-03-22"]
[4382,660078,"Performance requirements of MMSE-IRC receiver for LTE BS","LTE_MMSE_IRC_BS",1,"Rel-13","R4","2014-12-15","2016-06-15",1,"RP-142223",null,"China Telecom","China Telecom",null,null,66,34,null,null,"2015-01-15","2015-01-15"]
[4386,670055,"Dual Connectivity enhancements for LTE","LTE_dualC_enh",1,"Rel-13","R2","2015-03-16","2016-06-15",1,"RP-150490",null,"NTT DOCOMO",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4387,670155,"   Core part: Dual Connectivity enhancements for LTE","LTE_dualC_enh-Core",2,"Rel-13","R2","2015-03-16","2015-12-15",1,"RP-151739","RP-151330","NTT DOCOMO",null,"03/07/15: Compl:0%->25% 03/07/15: Stat Rep: ->RP-150744 29/09/15: Compl:25%->55% 29/09/15: Stat Rep: RP-150744->RP-151330 1/1/16: Compl:55%->100%",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4393,670158,"   Core part: LTE-WLAN Radio Level Integration and Interworking Enhancement","LTE_WLAN_radio-Core",2,"Rel-13","R2","2015-03-16","2016-03-15",1,"RP-160521","RP-151563","Intel",null,"03/07/15: Compl:0%->30% 03/07/15: WID: RP-150510->RP-151114 03/07/15: Stat Rep: ->RP-151081, 07/08/15: impacted TSs added 29/09/15: Compl:30%->35% 29/09/15: Stat Rep: RP-151081->RP-151563;","36.461; 36.462; 36.463; 36.464; 36.465; 36.622; 36.623; 36.624; 36.625; 36.360",67,34,null,null,"2015-04-01","2016-03-22"]
[4394,670258,"   Perf. part: LTE-WLAN Radio Level Integration and Interworking Enhancement","LTE_WLAN_radio-Perf",2,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-160521","RP-151563","Intel",null,"03/07/15: WID: RP-150510->RP-151114 03/07/15: Stat Rep: ->RP-151081 29/09/15: Stat Rep: RP-151081->RP-1515631/1/16: Compl:0%->10% ¦22/3/16: Compl:10%->100%¦",null,67,34,null,null,"2015-04-01","2016-03-22"]
[4400,670261,"   Perf. part: LTE DL 4 Rx antenna ports","LTE_4Rx_AP_DL-Perf",2,"Rel-13","R4","2000-01-03","2016-09-15",1,"RP-161237","RP-151265","Ericsson",null,"03/07/15: Compl:0%->15% 03/07/15: CD:Mon 02/10/00->Wed 15/06/16 03/07/15: Stat Rep: ->RP-150803 29/09/15: Compl:15%->35% 29/09/15: Stat Rep: RP-150803->RP-15126522/3/16: Compl:60%-;26/9/16: Compl:90%->100%",null,67,34,null,null,"2015-04-01","2016-09-26"]
[4402,670062,"AWS-Extension Band for LTE","LTE_AWS_EXT",1,"Rel-13","R4","2015-03-16","2016-09-15",1,"RP-150428",null,"Ericsson",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4405,700068,"   UE Conformance Test Aspects - AWS-Extension Band for LTE (Band 66)","LTE_AWS_EXT-UEConTest",2,"Rel-13","R5","2015-12-15","2016-09-15",1,"RP-161524",null,"Ericsson",null,"¦22/3/16: Compl:0%->10%1/7/16: Compl:10%->65%26/9/16: Comp",null,70,36,null,null,"2016-01-01","2016-09-26"]
[4409,670064,"Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5_BWset",1,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150425",null,"Samsung",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4413,670154,"   Core part: Multiflow Enhancements for UTRA","HSDPA_MFTX_enh-Core",2,"Rel-13","R2","2015-03-16","2015-09-15",1,"RP-151021","RP-151302","Nokia","alexander.sayenko@nokia.com","03/07/15: Compl:0%->80% 03/07/15: WID: RP-150288->RP-151021 03/07/15: Stat Rep: ->RP-150827 29/09/15: Compl:80%->100% 29/09/15: Stat Rep: RP-150827->RP-151302",null,67,34,null,null,"2015-05-05","2015-09-29"]
[4414,680044,"Message interworking during PS to CS SRVCC ","mSRVCC",1,"Rel-13","C1","2015-06-15","2015-09-16",1,"CP-150401",null,"Ivo Sedlacek, Ericsson","ivo.sedlacek@ericsson.com",null,null,68,35,null,null,"2015-06-15","2015-06-15"]
[4418,680051,"   Stage 2 of Support of Emergency services over WLAN - phase 1","SEW1",2,"Rel-13","S2","2015-06-18","2015-09-16",1,"SP-150253",null,"Laurent thiebaut","Laurent.thiebaut@alcatel-lucent.com ","07/09/15: 0%->100","23.402; 23.167; 23.271; 23.203; 23.228",68,35,null,null,"2015-06-18","2015-09-07"]
[4421,690025,"      CT3 aspects of Support of Emergency services over WLAN – phase 1","SEW1-CT",3,"Rel-13","C3","2015-09-07","2015-12-11",1,"CP-150571",null,"Alcatel-Lucent, Jennifer Liu (CT1)","jennifer.liu@alcatel-lucent.com","7/12/15: 0%->100","29.212; 29.214",69,35,null,null,"2015-09-07","2015-12-07"]
[4427,700006,"   CT aspects of MBMS Enhancements","MBMS_enh-CT",2,"Rel-13","C3","2015-11-09","2015-12-07",1,"CP-150798",null,"Nokia Networks, Thomas Belling",null,null,null,70,36,null,null,"2015-12-07","NA"]
[4429,700007,"      CT4 aspects of MBMS enhancements","MBMS_enh-CT",3,"Rel-13","C4","2015-11-09","2015-12-07",1,"CP-150798",null,"Nokia Networks, Thomas Belling",null,null,"29.274; 23.008; 29.230",70,36,null,null,"2015-12-07","2015-12-07"]
[4432,690026,"   CT3 aspects for EPC Signalling Improvements for race scenarios","EPC_SIG_RACE",2,"Rel-13","C3","2015-09-07","2016-03-11",1,"CP-150424",null,"Huawei, Peter Schmitt","Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM","7/12/15: FCD -> 03/16, ES in CP-150861¦8/12/15: 0%->100","29.212; 29.213",69,35,null,null,"2015-09-07","2015-12-08"]
[4436,700010,"   CT4 aspects of DiaPri","DiaPri",2,"Rel-13","C4","2015-11-02","2016-03-11",1,"CP-150613",null,"Alcatel-Lucent, Jean-Jacques Trottin","jean-jacques.trottin@alcatel-lucent.com","ES in CP-150622¦7/3/16: 70%->100","29.228; 29.229; 29.272; 29.273; 29.328; 29.329; 29.336; 29.337; 29.338; 29.344; 29.345",70,36,null,null,"2015-12-07","2016-03-07"]
[4440,680259,"   Perf. part: Downlink TPC Enhancements for UMTS","UTRA_EDL_TPC-Perf",2,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151880","RP-151564","Huawei",null,"follow-up WI of REL-13 SI FS_UTRA_EDL¦TPC = Transmit Power Control 29/09/15: Stat Rep: -->RP-151564¦1/1/16: Compl:0%->80%¦1/1/16: WID: RP-151044->RP-151880",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4443,680260,"   Perf. part: Licensed-Assisted Access using LTE","LTE_LAA-Perf",2,"Rel-13","R4","2015-06-15","2016-12-15",1,"RP-151045",null,"Ericsson",null,"follow-up WI of REL-13 SI FS_LTE_LAA 29/09/15: Stat Rep: -->RP-15139022/3/16: Compl:0%->33%¦1/7/16: Compl:3¦26/9/16: Compl:50%->90%¦20/12/16: Compl:90%->100%¦20/12/16: Stat Rep: RP-151390->",null,68,35,null,null,"2015-07-03","2016-12-20"]
[4445,680061,"Elevation Beamforming/Full-Dimension (FD) MIMO for LTE","LTE_EBF_FDMIMO",1,"Rel-13","R1","2015-06-15","2018-12-14",0.99,"RP-151085","-","Samsung",null,"follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4448,770062,"   UE Conformance Test Aspects - Elevation Beamforming/Full-Dimension MIMO for LTE","LTE_EBF_FDMIMO-UEConTest",2,"Rel-13","R5","2017-09-15","2018-12-14",1,"RP-172651",null,"Ericsson",null,"¦8/1/18: Compl:0%->5%¦27/3/18: Compl:5%->10%¦27/6/18: CD:Fri 15/06/18-; 26/3/20: 10%->100",null,77,39,null,null,"2017-09-19","2020-03-26"]
[4454,710069,"   UE Conformance Test Aspects - Support of single-cell point-to-multipoint transmission in LTE","LTE_SC_PTM-UEConTest",2,"Rel-13","R5","2016-03-15","2016-09-15",1,"RP-161681","-","Huawei",null,"testing REL-13 LTE_SC_PTM-Core1/7/16: Compl:0%->40%26/9/16",null,71,36,null,null,"2016-03-22","2016-09-26"]
[4456,680165,"   Core part: Extension of Dual Connectivity in E-UTRAN","LTE_dualC_ext-Core",2,"Rel-13","R3","2015-06-15","2015-12-15",1,"RP-151798","RP-151214","Samsung",null,"no Perf. part¦follow-up WI of REL-13 SI FS_LTE_dualC_ext¦29/09/15: Compl:0%->30% 29/09/15: Stat Rep: -->RP-151214¦1/1/16: Compl:3",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4459,680071,"Interference mitigation for downlink control channels of LTE","LTE_IM_DLCCH",1,"Rel-13","R4","2015-06-15","2018-09-14",1,"RP-151107","-","Intel",null,"only Perf. part, no Core part;",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4463,690162,"   Core part: Network-Assisted Interference Cancellation and Suppression for UMTS","UTRA_NAICS-Core",2,"Rel-13","R1","2015-09-15","2015-12-15",1,"RP-151879","-","Huawei",null,"no Perf. part¦follow-up WI REL-13 RAN1 SI FS_UTRA_NAICS ¦1/1/16: Compl:0%->100% ¦1/1/16: WID: RP-151577->RP-151879",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4467,670042,"   Study on further Enhancements of Minimization of Drive Tests for E-UTRAN","FS_LTE_eMDT2",2,"Rel-13","R2","2015-03-16","2015-09-15",1,"RP-150472","RP-151181","CMCC",null,"03/07/15: Compl:0%->70% 03/07/15: Stat Rep: -->RP-150806 29/09/15: Compl:70%->100% 29/09/15: Stat Rep: RP-150806->RP-151181",36.880000000000003,67,34,null,null,"2015-04-01","2015-09-29"]
[4470,690066,"LTE-WLAN RAN Level Integration supporting legacy WLAN ","LTE_WLAN_radio_legacy",1,"Rel-13","R2","2015-09-15","2016-03-15",1,"RP-151615","-","Alcatel-Lucent",null,"no Perf. part¦compare REL-13 WI LTE_WLAN_radio",null,69,35,null,null,"2015-09-29","NA"]
[4472,690067,"Indoor Positioning enhancements for UTRA and LTE","UTRA_LTE_iPos_enh",1,"Rel-13","R2","2015-09-15","2017-03-15",1,"RP-151624","-","NextNav",null,"follow-up WI of REL-13 SI FS_UTRA_LTE_iPos_enh",null,69,35,null,null,"2015-09-29","NA"]
[4475,700011,"   CT aspects of Indoor Positionning","UTRA_LTE_iPos_enh-CT",2,"Rel-13","C4","2015-10-12","2015-12-07",1,"CP-150612",null,"Ericsson, Jesús de Gregorio","jesus.de.gregorio@ericsson.com",null,"29.171; 29.172; 29.230; 29.002",70,36,null,null,"2015-12-07","NA"]
[4478,680063,"Power saving enhancements for UMTS","UTRA_SDATA_POWSAV",1,"Rel-13","R2","2015-06-15","2016-03-15",1,"RP-151092","-","Ericsson",null,"no Perf. part¦follow-up WI of SI FS_UTRA_SDATA",null,68,35,null,null,"2015-07-03","2015-07-03"]
[4481,680073,"700MHz E-UTRA FDD Band for Arab Region","LTE_FDD_700_ARAB",1,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151042","-","Etisalat",null,"REL-independent from REL-9",null,68,35,null,null,"2015-07-03","2015-07-03"]
[4486,680275,"   Perf. part: European 700 Supplemental Downlink band (738-758 MHz) in E-UTRA and LTE Carrier Aggregation (2DL/1UL) with Band 20","LTE_CA_700EU_B20-Perf",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151228","RP-151232","TeliaSonera",null,"introduction of new DL only band and 2DL/1UL CA with it 29/09/15: WID: RP-150861->RP-151228 29/09/15: Stat Rep: -->RP-151232 29/09/15: Release: Rel-14->Rel-13 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4490,700016,"   Stage 2 of CIoT","CIoT",2,"Rel-13","S2","2015-10-05","2015-10-05",1,"SP-150844",null,"Intel, Puneet Jain","puneet.jain@intel.com","7/3/16: 0%->95","23.401; 23.682; 23.251",70,36,null,null,"2015-12-07","2016-03-07"]
[4494,700051,"      CT3 aspects of CIoT","CIoT-CT",3,"Rel-13","C3","2015-12-07","2016-06-15",1,"CP-160292",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","7/3/16: 0%->90¦11/6/16: WID:CP-150795->CP-160292¦13/6/16: 90%->100","29.061; 29.212",70,36,null,null,"2015-12-07","2016-06-13"]
[4497,720042,"   Charging Aspects of CIoT","CIoT-CH",2,"Rel-13","S5","2016-05-12","2016-06-13",1,"SP-160395",null,"Gardella, Maryse (Nokia)","Gardella, Maryse (Nokia)","32.25x¦13/6/16: 0%->100","32.25x; 32.240; 32.251; 32.274; 32.299; 32.298; 32.297",72,37,null,null,"2016-06-13","2016-06-13"]
[4499,690163,"      Core part: Narrowband Internet of Things (IOT)","NB_IOT-Core",3,"Rel-13","R1","2015-09-15","2016-06-15",1,"RP-160933","-","Vodafone",null,"no Perf. part¦note: WI only stays in REL-13 because of PCG decision1/1/16: Compl:0%->25% 22/3/16: Compl:25%->75%;1/7/16: Com",36.802,69,35,null,null,"2015-09-29","2016-07-01"]
[4502,710065,"   UE Conformance Test Aspects - Narrowband Internet of Things (NB-IOT)","NB_IOT-UEConTest",2,"Rel-13","R5","2016-03-15","2017-12-15",1,"RP-160047",null,"CMCC",null,"testing REL-13 NB_IOT-Core1/7/16: Compl:0%->5%¦26/9¦20/12/1¦21/3/17: Compl: ;",null,71,36,null,null,"2016-03-22","2018-01-08"]
[4505,700004,"   Test for CIoT_EC_GSM","CIoT_EC_GSM_GERAN3new",2,"Rel-13","G3","2015-11-11","2016-05-12",0,"GP-151149",null,"Sierra Wireless S.A","Marteen.Sunberg@Ericsson.com","7/12/15: created GERAN. 2/3/16: G1,G2->G3, Acronym: CIoT_EC_GSM-Test->CIoT_EC_GSM_GERAN3new",null,70,36,null,null,"2015-09-07","2016-03-02"]
[4508,690005,"Extended DRX cycle for Power Consumption","eDRX",1,"Rel-13","S2,R2,G2","2014-12-03","2016-09-15",0.93,"SP-150369",null,"Miguel Griot","mgriot@qti.qualcomm.com","June2015: WID:SP-150254->SP-150369","23.401; 23.060; 23.682; 23.271; 23.272",68,35,null,null,"2015-06-18","2015-06-18"]
[4513,690030,"      CT3 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C3","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","14/09/15: WID:CP-150499->CP-150541. FCD ->03/16. ES in CP-150723¦8/12/15: 0%->100","29.338; 23.007; 29.274; 29.060; 29.172",69,35,null,null,"2015-09-07","2015-12-08"]
[4517,670157,"      Core part: RAN enhancements for extended DRX in LTE","LTE_extDRX-Core",3,"Rel-13","R2","2015-03-16","2016-03-15",1,"RP-151339","RP-151338","Qualcomm",null,"03/07/15: Compl:0%->15% 03/07/15: Stat Rep: ->RP-150798 29/09/15: Compl:15%->35% 29/09/15: WID: RP-150493->RP-151339 29/09/15: Stat Rep: RP-150798->RP-151338 ¦22/3/16: Compl:95%->100%",null,67,34,null,null,"2015-04-01","2016-03-22"]
[4521,700002,"      MS test: Extended DRX (eDRX) for GSM","eDRX_GSM_GERAN3new",3,"Rel-13","G3","2015-12-07","2016-05-12",0.15,"GP-151148",null,"Sierra Wireless S.A","John.Diachina@Ericsson.com","7/12/15: created by GERAN. 2/3/16: G1,G2->G3. Acronym: eDRX_GSM-Test -> eDRX_GSM_GERAN3new (to conform to WID)¦0->15%",null,70,36,null,null,"2015-08-12","2016-03-02"]
[4524,680005,"   Optimizations to Support High Latency Communications","HLcom",2,"Rel-13","S2","2015-03-05","2015-06-15",1,"SP-150252",null,"Ericsson, Hans Rönneke","hans.ronneke(at)ericsson.com","June 2015: created by MCC as a result of the split of the one-line Feature into a several-lines Feature (now Stage 2 and Stage 3 aspects)¦June2015: Compl:0%->100. WID: SP-150030->SP-150252","23.401; 23.060; 23.682",67,34,null,null,"2015-06-15","2015-06-18"]
[4525,680015,"   CT aspects of Optimizations to Support High Latency","HLcom-CT",2,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150399",null,"Yong Yang, Ericsson","frank.yong.yang@ericsson.com","07/09/15: 0%->80¦7/12/15: 80%->100","29.274; 29.060; 29.281; 23.008; 29.272; 29.230; 29.002; 29.336; 29.xyz",68,35,null,null,"2015-06-15","2015-12-07"]
[4530,690045,"EGPRS Access Security Enhancements in relation to Cellular IoT","EASE_EC_GSM",1,"Rel-13","S3","2015-09-16","2016-03-11",1,"SP-150462",null,"Vesa Torvinen, Ericsson",null,"7/12/15: 0%->5¦28/1/16: 33.420 added¦7/3/16: 5%->80¦11/6/16: 80%->98¦19/9/16: 98%->99¦21/3/17: 99%->100->99%¦7/6/17: 99%->100","New 33.420",69,35,null,null,"2015-09-16","2017-06-07"]
[4533,640250,"   Stage 2 for Group based Enhancements","GROUPE",2,"Rel-13","S2","2014-06-23","2015-06-17",1,"SP-140706","-","Huawei","ZhangWanqiang@huawei.com","Mar15: 0->20%¦June2015: Compl:20%->100","23.682; TBD",64,33,null,null,"2014-05-30","2015-06-15"]
[4535,640450,"   Security for Group based Enhancements","GROUPE",2,"Rel-13","S3","2014-06-23","2015-09-16",1,"SP-140706","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","-¦11/12/15: 0%->100",33.186999999999998,64,33,null,null,"2014-05-30","2015-12-11"]
[4540,640049,"Monitoring Enhancements","MONTE",1,"Rel-13","S2,S3","2014-06-18","2016-03-11",1,"SP-140705","-","Intel","puneet.jain@intel.com","Linked to Rel-13 Feature Architecture Enhancements for Service Exposure (AESE). Although service requirements (TS 22.368 clause 7.2.8) are motivated by MTC, the solution may apply to normal UEs¦5/10/15: 32.278 added;",32.277999999999999,64,33,null,null,"2014-05-30","2015-10-05"]
[4544,640449,"   Security for Monitoring Enhancements","MONTE",2,"Rel-13","S3","2014-06-23","2015-09-16",1,"SP-140705","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","-¦11/12/15: 0%->100",33.186999999999998,64,33,null,null,"2014-05-30","2015-12-11"]
[4548,680026,"      CT3 aspects of Monitoring Enhancements","MONTE-CT",3,"Rel-13","C3","2015-06-15","2015-12-16",1,"CP-150422",null,"Peter Schmitt, Huawei","peter.schmitt@huawei.com","07/09/15: 0%->100¦14/09/15: WID:CP-150396->CP-150422","29.214; 29.213; 29.201",68,35,null,null,"2015-06-15","2015-09-14"]
[4551,640146,"   TR for Dedicated Core Networks","DECOR",2,"Rel-13","S2","2014-06-18","2014-12-12",1,"SP-150249","-","NTT DOCOMO","Daisuke Fujishima (fujishimad@nttdocomo.co.jp)","Dec.14: 30->100%. 06/15: WID: SP-140707-> SP-150249","New 23.707",64,33,null,null,"2014-05-30","2015-06-18"]
[4552,640246,"   Stage 2 for Dedicated Core Networks","DECOR",2,"Rel-13","S2","2014-06-23","2015-03-18",1,"SP-150249","-","NTT DOCOMO","Daisuke Fujishima (fujishimad@nttdocomo.co.jp)","Mar15: 0->70%¦June2015: Compl:70%->100, WID: SP-140707-> SP-150249","23.060; 23.401; 23.236",64,33,null,null,"2014-05-30","2015-06-18"]
[4557,680166,"      Core part: Dedicated Core Networks","DECOR-UTRA_LTE-Core",3,"Rel-13","R3","2015-06-15","2015-12-15",1,"RP-151048","RP-151290","Ericsson",null,"no Perf. part¦note: DECOR is a REL-13 SA2 WI¦29/09/15: Compl:0%->30% 29/09/15: Stat Rep: -->RP-1512901/1/16: Compl:30%->100%",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4560,610230,"   Stage 1 for Service Exposure and Enablement Support","SEES",2,"Rel-13","S1","2013-09-12","2014-09-17",1,"SP-130505","S1-143301","KPN","toon.norp@tno.nl","SP#65 completed","22.101; 22.115; 22.368; TBD",61,31,null,null,"2013-08-26","2014-08-28"]
[4563,640248,"   Stage 2 for Architecture Enhancements for Service capability Exposure","AESE",2,"Rel-13","S2","2014-06-23","2015-06-17",1,"SP-140704","-","Intel, Puneet Jain","puneet.jain@intel.com","-¦June2015: Compl:0%->100","23.682; 33.187",64,33,null,null,"2014-05-30","2015-06-15"]
[4566,680001,"   CT aspects of Architecture Enhancements for Service capability Exposure","AESE-CT",2,"Rel-13","C3","2015-06-15","2016-03-11",1,"CP-150576",null,"Yizhuang Wu, Huawei ","wuyizhuang@huawei.com","14/09/15: WID:CP-150402->CP-150487->CP-150576",null,68,35,null,null,"2015-06-15","2015-09-14"]
[4571,690180,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12","LTE_CA_B4_B4_B5_B12-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151208","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[4574,690181,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5","LTE_CA_B2_B4_B4_B5-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151210","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[4575,690281,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5","LTE_CA_B2_B4_B4_B5-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151210","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[4579,620032,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) for Band 3, Band 8 and Band 27","LTE_CA_B3_B8_B27",2,"Rel-13","R4","2013-12-09","2015-12-15",0.25,"RP-131754","-","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-09"]
[4584,630233,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22","LTE_CA_B7_B22-Perf",3,"Rel-13","R4","2014-03-11","2015-06-15",1,"RP-140094","RP-150536","Orange, Ericsson","erika.tejedor@ericsson.com","CD:Thu 11/12/14->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: RP-141084->RP-141732 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-141732->RP-150536","36.141; 36.307",63,32,null,null,"2014-03-10","2015-06-18"]
[4587,640222,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12","LTE_CA_B2_B2_B12-Perf",3,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-141232","RP-150536","U.S. Cellular","sebastian.thalanany@uscellular.com","CD:Thu 18/06/15->Mon 15/06/15¦Compl:0%->10%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; 36.133; 36.141; 36.307",64,33,null,null,"2014-06-16","2015-06-18"]
[4590,640225,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8","LTE_CA_B3_B3_B8-Perf",3,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-150874","RP-150536","CHTTL","Po-Han Hsieh (pohanhsieh@cht.com.tw)","¦WID: RP-142043->RP-141832¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-141832->RP-150874 03/07/15: Stat Rep: RP-150013->RP-150536",36.307000000000002,64,33,null,null,"2014-06-16","2015-06-18"]
[4593,640232,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42","LTE_CA_B41_B42_B42-Perf",3,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-140974","RP-150536","Huawei","leo.liuye@huawei.com","CD:Thu 11/12/14->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:0%->60% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:60%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141; 36.307",64,33,null,null,"2014-06-16","2015-06-18"]
[4598,650138,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28","LTE_CA_B2_B28-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141145","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->50%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4601,650139,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28","LTE_CA_B4_B28-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141146","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->35%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:35%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4602,650239,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28","LTE_CA_B4_B28-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141146","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141; 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4606,650041,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 40","LTE_CA_B1_B40",2,"Rel-13","R4","2014-09-15","2015-12-15",1,"RP-141312","-","KT","ilwhan.kim@kt.com","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4609,650042,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 40","LTE_CA_B3_B40",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141674","-","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4615,650044,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31","LTE_CA_B3_B31",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141337","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4617,650244,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31","LTE_CA_B3_B31-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150318","RP-150536","Huawei","Liu Liehai (liuliehai@huawei.com)","CD:Thu 12/03/15->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141337->RP-150318 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-150013->RP-15","36.141; 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4620,650245,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40","LTE_CA_B5_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150285","RP-150536","SK Telecom","haesung.park@sk.com","¦WID: RP-142043->RP-141888¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->80% 1st Apr 15: WID: RP-141888->RP-150285 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141; 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4624,650049,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41","LTE_CA_B8_B41_B41",2,"Rel-13","R4","2014-09-12","2015-06-15",1,"RP-141290","-","China Mobile","PAN, Qun (panqun@chinamobile.com)","Inter-band CA 3DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4628,650151,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40","LTE_CA_B38_B40_B40-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141655","RP-150536","Samsung","xutao.zhou@samsung.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->70% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:70%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; 36.133; New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4629,650251,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40","LTE_CA_B38_B40_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141655","RP-150536","Samsung","xutao.zhou@samsung.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->70% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:70%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141; 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4633,660072,"   LTE Carrier Aggregation Enhancement Beyond 5 Carriers","LTE_CA_enh_b5C",2,"Rel-13",null,"2014-12-15","2018-09-14",1,"RP-142286",null,"Nokia Networks","Nokia","FCD: 06/16->12/15, Rel-14?->Rel-13",null,66,34,null,null,"2015-01-12","2015-01-15"]
[4636,730074,"      UE Conformance Test Aspects - LTE Carrier Aggregation Enhancement Beyond 5 Carriers: PUCCH on Scell","LTE_CA_enh_b5C_PUCCH-UEConTest",3,"Rel-13","R5","2016-09-15","2018-09-14",1,"RP-192558",null,"Huawei",null,"¦20/12/16: Compl:0%->5%19/6/17: Compl:5%->8%¦19/9/17: Compl:8%->15%¦8/1/18: 27/3/18; 14/1/20: WID:RP-171764->RP-192558; 14/1/20: 20%->100",null,73,37,null,null,"2016-09-26","2020-01-14"]
[4642,660281,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 25 and Band 26","LTE_CA_B25_B26-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150115","RP-150536","Sprint","Sprint","1st Apr 15: Compl:0%->95% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142020->RP-150115 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4644,660182,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 41","LTE_CA_B3_B41-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151446","RP-151131","China Telecom","China Telecom","1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-142239->RP-151446 29/09/15: Stat Rep: RP-150536->RP-151131¦29/09/1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4647,660183,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 3","LTE_CA_B1_B3_B3-Core",3,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141777","RP-151131","China Unicom","China Unicom","1st Apr 15: Compl:0%->50% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4651,660284,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 28","LTE_CA_B1_B19_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150639","RP-151131","NTT DOCOMO","NTT DOCOMO","03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141791->RP-150639 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4655,660086,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 40 and Band 40","LTE_CA_B7_B40_B40",2,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141802",null,"ZTE","ZTE",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4656,660186,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 40 and Band 40","LTE_CA_B7_B40_B40-Core",3,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150614","RP-151131","ZTE","ZTE","1st Apr 15: Compl:0%->40% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->75% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141802->RP-150614 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:75%->100% 29/09/15: Stat Rep: RP-",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4660,660287,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 28","LTE_CA_B1_B8_B28-Perf",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-150447","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-141826->RP-150447 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4663,660288,"      Perf. Part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7_BWset-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141881","RP-150536","Ericsson","Ericsson","Acronym changed from LTE_CA_B3_B7_B7-Perf 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4669,660290,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 40","LTE_CA_B1_B3_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151258","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141946->RP-151258 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4671,660191,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 40","LTE_CA_B1_B8_B40-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151259","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141947->RP-151259 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4675,660292,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 40","LTE_CA_B3_B8_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151261","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->90% 29/09/15: WID: RP-141949->RP-151261 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4678,660293,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL) of Band 3, Band 7 and Band 8","LTE_CA_B3_B7_B8-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142013","RP-150536","Ericsson","Ericsson","1st Apr 15: Compl:0%->99% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4682,660095,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 28","LTE_CA_B3_B8_B28",2,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-142193",null,"Softbank Mobile","Softbank Mobile",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4683,660195,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 28","LTE_CA_B3_B8_B28-Core",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-142193","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4687,660296,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 42 and Band 42","LTE_CA_B8_B42_B42-Perf",3,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-142194","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131;",null,66,34,null,null,"2015-01-12","2016-03-22"]
[4690,660297,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 40 and Band 40","LTE_CA_B28_B40_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150676","RP-151131","Huawei","Huawei","1st Apr 15: WID: RP-142206->RP-150233 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: WID: RP-150233->RP-150676 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4694,660099,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 7 and Band 28","LTE_CA_B1_B7_B28",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142208",null,"Huawei","Huawei",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4696,660299,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 7 and Band 28","LTE_CA_B1_B7_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150234","RP-150536","Huawei","Huawei","1st Apr 15: WID: RP-142208->RP-150234 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4702,661201,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 5","LTE_CA_B3_B3_B5-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142238","RP-150536","Intel","Intel","03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4705,661202,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 28","LTE_CA_B3_B7_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142244","RP-150536","Ericsson","Ericsson","1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4709,661004,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30","LTE_CA_B2_B2_B5_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142199",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4710,661104,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30","LTE_CA_B2_B2_B5_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150448","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: WID: RP-142199->RP-150448 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4714,661205,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30","LTE_CA_B2_B2_B29_B30-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150450","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142200->RP-150450 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4718,661007,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30","LTE_CA_B2_B4_B5_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142202",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4721,661008,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30","LTE_CA_B2_B4_B29_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142203",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4723,661208,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30","LTE_CA_B2_B4_B29_B30-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150453","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142203->RP-150453 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4729,661210,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 in REL-13","LTE_CA_2UL_R13-A1-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150678","RP-151131","Huawei","Huawei","1st Apr 15: Compl:0%->40% 1st Apr 15: WID: RP-141935->RP-150411 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->60% 03/07/15: WID: RP-150411->RP-150678 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: Stat Rep: RP-150",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4732,661211,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 in REL-13","LTE_CA_2UL_R13-A2-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150408","RP-151131","Qualcomm","Qualcomm","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-141975->RP-150408 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4736,661013,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 4 DL","LTE_CA_NC_B41_4DL",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142022",null,"Alcatel-Lucent","Alcatel-Lucent",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4737,661113,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 4 DL","LTE_CA_NC_B41_4DL-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142022","RP-151131","Alcatel-Lucent","Alcatel-Lucent","1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Tue 15/03/16->Tue 15/12/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->50% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4740,670165,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 42","LTE_CA_B1_B3_B42-Core",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150641","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150121->RP-150641 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4745,670067,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 21 and Band 42","LTE_CA_B1_B21_B42",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150123",null,"NTT DOCOMO, INC.",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4748,670068,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 19 and Band 42","LTE_CA_B3_B19_B42",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150124",null,"NTT DOCOMO, INC.",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4751,670069,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 21 and Band 42","LTE_CA_B19_B21_B42",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150125",null,"NTT DOCOMO, INC.",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4754,670070,"   Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7_BWset",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150429",null,"Rogers Communications",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4759,670271,"      Perf. part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12_BWset-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150430","RP-151131","Rogers Communications",null,"03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4763,670073,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 7","LTE_CA_B2_B4_B7",2,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150432",null,"Rogers Communications",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4764,670173,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 7","LTE_CA_B2_B4_B7-Core",3,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150432","RP-151131","Rogers Communications",null,"03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-1511311/1/16:22/3/16: Compl:0%->100%",null,67,34,null,null,"2015-04-01","2016-03-22"]
[4767,670174,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 20 and Band 38","LTE_CA_B7_B20_B38-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150433","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->30% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4772,670076,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12","LTE_CA_B2_B2_B4_B12",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150074",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4775,670077,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4","LTE_CA_B2_B2_B4_B4",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150075",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4778,670078,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40","LTE_CA_B1_B3_B5_B40",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150434",null,"SK Telecom",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4781,670079,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8","LTE_CA_B1_B3_B7_B8",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150435",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4786,670280,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29","LTE_CA_B2_B4_B5_B29-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150436","RP-151131","Huawei",null,"03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->95% 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4787,670081,"   LTE Advanced dual uplink inter-band Carrier Aggregation FDD-TDD","LTE_CA_2UL_FDD_TDD",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150064",null,"KDDI",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4790,670082,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A4","LTE_CA_2UL_R13-A4",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150410",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4794,670183,"      Core part:LTE Advanced 3DL/2UL inter-band Carrier Aggregation","LTE_CA_3DL_2UL-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-151230","RP-151131","Nokia Corporation",null,"03/07/15: Compl:0%->25% 03/07/15: CD:Tue 15/03/16->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: WID: RP-150479->RP-151230 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4798,670284,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 3DL","LTE_CA_NC_B42_3DL-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150246","RP-150536","Huawei",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4803,670186,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 4DL","LTE_CA_C_B42_4DL-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150438","RP-151131","CATT",null,"03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4805,680077,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 11","LTE_CA_B1_B8_B11",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150609","-","Softbank Mobile",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4808,680078,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 20 and Band 32","LTE_CA_B3_B20_B32",2,"Rel-13","R4","2015-06-15","2016-03-15",0.9,"RP-150864","-","Ericsson",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4813,680279,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 42 and Band 42","LTE_CA_B7_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151012","RP-151131","Huawei",null,"29/09/15: Compl:0%->70% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4814,680080,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 20, Band 42 and Band 42","LTE_CA_B20_B42_B42",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-151013","-","Huawei",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4817,680081,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 38","LTE_CA_B3_B7_B38",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151014","-","Nokia Networks",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4821,680182,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 41 and Band 41","LTE_CA_B28_B41_B41-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151111","RP-151131","KDDI",null,"29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4825,680283,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 42 and Band 42","LTE_CA_B28_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151158","RP-151131","KDDI",null,"29/09/15: WID: RP-151112->RP-151158 29/09/15: Stat Rep: -->RP-151131¦",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4830,680186,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42","LTE_CA_B1_B3_B19_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150632","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4832,680087,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42","LTE_CA_B1_B3_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150633","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4836,680188,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 42 and Band 42","LTE_CA_B1_B19_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150634","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4839,680189,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 19, Band 42 and Band 42","LTE_CA_B3_B19_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150635","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4841,680090,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42","LTE_CA_B1_B19_B21_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150636","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4844,680091,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42","LTE_CA_B1_B21_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150637","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4848,680192,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42","LTE_CA_B19_B21_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150638","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4852,680293,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 12","LTE_CA_B2_B4_B5_B12-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150728","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4857,680195,"      Core part:LTE Advanced 4-Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12","LTE_CA_B2_B2_B12_B12-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150732","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4860,680196,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30","LTE_CA_B4_B4_B5_B30-Core",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151015","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4863,680197,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 30","LTE_CA_B4_B4_B12_B30-Core",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151016","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4866,680198,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 29 and Band 30","LTE_CA_B4_B4_B29_B30-Core",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151017","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 ¦22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4868,681000,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12","LTE_CA_B2_B2_B5_B12",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151018","-","U.S. Cellular",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4871,681001,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12","LTE_CA_B2_B5_B12_B12",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151019","-","U.S. Cellular",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4875,681102,"      Core part:LTE Advanced 3DL/2UL mixed intra- and inter-band Carrier Aggregation","LTE_CA_3DL_2UL_inter_intra-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP151576","RP-151131","Nokia Networks",null,"covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE¦pure intra-band CA combinations are also covered by this WI¦note: There is already a REL-13 WI LTE_CA_3DL_2UL ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4879,681203,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 5","LTE_CA_C_B5-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151035","RP-151131","Intel",null,"29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4882,681204,"      Perf. part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4","LTE_CA_NC_B4_BWset-Perf",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-151034","RP-151131","Nokia Networks",null,"LTE_CA_NC_B4 was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4884,681105,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 5","LTE_CA_NC_B5-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151036","RP-151131","Intel",null,"29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[{"$f":"A4890+1","v":4890},680174,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12","LTE_CA_B2_B12_BWset-Core",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150585","RP-151131","Nokia Networks",null,"LTE_CA_B2_B12 was completed as REL-12 WI 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4893,680176,"      Core part: Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset2-Core",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150947","RP-151131","Nokia Networks",null,"LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4895,680072,"   Introduction of 1447-1467MHz Band for TD-LTE in China","LTE_TDD_1447MHz_China",2,"Rel-13","R4","2015-06-15","2016-09-15",1,"RP-151037","-","Huawei",null,"Aug 15: TR numb added",null,68,35,null,null,"2015-08-12","2015-08-12"]
[4898,710068,"      UE Conformance Test Aspects - Introduction of 1447-1467MHz Band for TD-LTE in China","LTE_TDD_1447MHz_China-UEConTest",3,"Rel-13","R5","2016-03-15","2016-09-15",1,"RP-161679","-","Huawei",null,"testing REL-13 LTE_TDD_1447MHz_China-Core¦1/7/16: C¦",null,71,36,null,null,"2016-03-22","2016-09-26"]
[4902,690073,"   LTE Advanced inter-band Carrier Aggregation for Band 5 and Band 38","LTE_CA_B5_B38",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151367","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4906,690174,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 11 and Band 18","LTE_CA_B1_B11_B18-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151156","-","KDDI",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4909,690175,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 5, Band 40, and Band 40","LTE_CA_B5_B40_B40-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151200","-","ZTE",null,"1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4911,690076,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 41 and Band 42","LTE_CA_B3_B41_B42",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151365","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4917,690078,"   LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 41, Band 41 and Band 41","LTE_CA_B39_B41_B41_B41",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151175","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4920,690079,"   LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 39, Band 41 and Band 41","LTE_CA_B39_B39_B41_B41",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151176","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4924,690182,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 8 and Band 40","LTE_CA_B1_B3_B8_B40-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151262","-","KT",null,"¦1/1",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4925,690282,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 8 and Band 40","LTE_CA_B1_B3_B8_B40-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151262","-","KT",null,1,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4929,690084,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40","LTE_CA_B28_B40_B40_B40",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151364","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4933,690185,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28","LTE_CA_B3_B7_B7_B28-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151511","-","Telstra",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4936,690189,"      Core part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 19, Band 42 and Band 42","LTE_CA_B1_B3_B19_B42_B42-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151159","-","NTT DOCOMO",null,null,"36.857-13",69,35,null,null,"2015-09-29","2016-01-01"]
[4938,690090,"   LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42","LTE_CA_B1_B19_B21_B42_B42",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151160","-","NTT DOCOMO",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4944,690092,"   LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 3, Band 3, Band 7, Band 7 and Band 28","LTE_CA_B3_B3_B7_B7_B28",2,"Rel-13","R4","2015-09-15","2016-03-15",1,"RP-151513","-","Telstra",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4947,690093,"   LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 41 and Band 41","LTE_CA_3DL3UL_B39_B41_B41",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151402","-","CATT",null,"TDD case",null,69,35,null,null,"2015-09-29","NA"]
[4951,690194,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 39 and Band 41","LTE_CA_3DL3UL_B39_B39_B41-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151403","-","CATT",null,"TDD case",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4952,690294,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 39 and Band 41","LTE_CA_3DL3UL_B39_B39_B41-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151403","-","CATT",null,"TDD case",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4956,700065,"   UE Conformance Test Aspects - Rel-13 LTE CA configurations","LTE_CA_Rel13-UEConTest",2,"Rel-13","R5","2015-12-15","2018-12-14",1,"RP-161553",null,"Ericsson",null,"¦22/3/16: Compl:0%->5%;1/7/16: Compl:5%->22%26/9/16: Compl:22%->¦2 21/3/17: Compl:39% ;; 14/1/20: 62%->100",null,70,36,null,null,"2016-01-01","2020-01-14"]
[4960,690007,"(Small) Security Enhancements and Improvements for Rel-13","SEC13",1,"Rel-13","S3","2006-12-12","2015-12-21",1,"-","PCG-31","-","-","-","-",61,31,null,null,"2015-01-12","2013-09-14"]
[4963,640001,"Study on Cellular system support for ultra Low Complexity and low throughput Internet of Things","FS_IoT_LC",1,"Rel-13","G1,G2","2014-05-30","2015-08-28",1,"GP-150354","-","Vodafone","chris.pudney@vodafone.com","GP#62 approved WID. Dec.14: 15->40%¦June2015: Compl:40%->75¦07/09/15: 75%->100¦14/09/15: WID:GP-140421->GP-150354","45.8xy",66,33,null,null,"2014-05-30","2015-09-14"]
[4967,570034,"Study on Application specific Congestion control for Data Communication","FS_ACDC",1,"Rel-13","S1","2012-09-17","2014-09-17",1,"SP-130415","S1-143305","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#65 completed. SP#64 TR 22.806v200 for Approval. ACDC is applicable to UTRAN and E-UTRAN. Possible overlap with RAN2 TR 36.848 Study on smart congestion mitigation in E-UTRAN (prioritising MMTEL voice over other traffic during congestion)",22.806000000000001,57,29,null,null,"2012-08-31","2014-08-29"]
[4969,0,"Release 13 other Studies","-",1,"Rel-13","SP,R2","2013-09-12","2015-12-25",1,"-","-","-","-","-","-",null,null,null,null,"2013-03-04","2013-03-04"]
[4972,670095,"Study on Security Aspects of Isolated E-UTRAN Operation for Public Safety","FS_IOPS_Sec",1,"Rel-13","S3","2015-03-12","2015-09-18",1,"SP-150074",null,"Paul Piggin, General Dynamics UK","paul.piggin@gd-broadband.com","TR added¦June2015: Compl:0%->30¦7/12/15: 30%->100","New 33.897",67,34,null,null,"2015-04-02","2015-12-07"]
[4975,620070,"Study on Enhanced Calling Information Presentation","FS_ECIP",1,"Rel-13","S1","2013-12-13","2014-09-17",1,"SP-130598","S1-143311","China Mobile","LI Xiaofan (lixiaofan@chinamobile.com","SP#65 completed. TR 22.810v200 for Approval. Linked to Multimedia Telephony Service for IMS (UID_7038), Customized Alerting Tone (CAT) UID_370028, Customized Ringing Signal (CRS) UID_380067",22.81,62,32,null,null,"2013-11-26","2014-08-28"]
[4978,520335,"   Deleted - SA1 part of Study on Usage Monitoring Control PCC Enhancement","-",2,"-","S1","2011-06-08","2012-06-20",1,"SP-120554","-","ZTE","Li.Mian@zte.com.cn","SP#56 completed",23.858000000000001,52,27,"SP-58","PCG-31","2011-05-19","2013-09-09"]
[4983,610045,"Study on Enhancements of OAM aspects of Distributed Mobility Load Balancing (MLB) SON function","FS_D_MLB_SON_OAM",1,"Rel-13","S5","2014-09-15","2016-06-13",1,"SP-130430","-","Cisco","Vladimir Yanover (vyanover@cisco.com)","SP#64 completion 06/14=>12/14. Dec.14: 20->25%, CD: 12/14->06/15¦June2015: Compl:25%->30¦7/12/15: 30%->45¦7/3/16: 45%->50¦13/6/16: 50%->100",32.86,61,31,null,null,"2013-09-09","2016-06-13"]
[4987,590010,"Study on Review of dedicated 3GPP UICC features","FS_Red_UCe",1,"Rel-13","C6","2013-03-13","2015-12-16",1,"CP-130168","-","BlackBerry","Adrian Buckley (abuckley@blackberry.com)","CP#65 TR 31.901v100 for Information. Moved to Rel-13. Completion 09/14=>12/15. Waiting for feedback from external organizations (PTCRB/PVG). Dec.14: 65->100%",31.901,59,30,null,null,"2013-02-20","2014-12-03"]
[4990,640017,"Study on MIMO OTA antenna test function for LTE","FS_LTE_MIMO_OTA_ATF",1,"Rel-13","R4","2013-03-18","2014-12-15",1,"RP-141325","RP-142045","Keysight","Moray_Rumney@keysight.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:60%->100%¦Stat Rep: RP-141124->RP-142045","36.509; new 37.978",64,33,null,null,"2014-06-16","2015-01-12"]
[4994,620045,"Study on Multi-RAT joint coordination","FS_MultiRAT_JC",1,"Rel-13","R4","2013-12-06","2015-06-15",1,"RP-150417","RP-150807","China Mobile","Kimba Dit Adamou, Boubacar (jinba@chinamobile.com)","¦WID: RP-142043->RP-132086¦Stat Rep: RP-141301->RP-141838 1st Apr 15: Compl:55%->85% 1st Apr 15: WID: RP-132086->RP-150417 1st Apr 15: Stat Rep: RP-141838->RP-150187 03/07/15: Compl:85%->100% 03/07/15: Stat Rep: RP-150187->RP-150807","UTRA; LTE 37.870",62,32,null,null,"2013-11-27","2015-06-18"]
[4996,640018,"Study on Indoor Positioning Enhancements for UTRA and LTE","FS_UTRA_LTE_iPos_enh",1,"Rel-13","R1,R4","2014-06-18","2015-09-15",1,"RP-141102","RP-151178","NextNav","Vogedes Jerome (jvogedes@NextNav.com)","CD:Thu 17/09/15->Tue 15/09/15¦Compl:0%->8%¦Stat Rep: RP-141101->RP-141818 1st Apr 15: Compl:8%->30% 1st Apr 15: Stat Rep: RP-141818->RP-150080 03/07/15: Compl:30%->75% 03/07/15: Stat Rep: RP-150080->RP-150595 29/09/15: Compl:75%->100% 29/09/15: Stat ","UTRA; LTE 37.857",64,33,null,null,"2014-06-16","2015-09-29"]
[4999,650016,"Study on Licensed-Assisted Access using LTE","FS_LTE_LAA",1,"Rel-13","R1,R2,R4","2014-09-16","2015-06-15",1,"RP-141817","RP-150624","Ericsson, Huawei","havish.koorapaty@ericsson.com, david.mazzarese@huawei.com","3/3/15: WID: RP-141817¦Stat Rep: -->RP-141816. Impacted TR number added. 1st Apr 15: Compl:30%->40% 1st Apr 15: Stat Rep: RP-141816->RP-150414 03/07/15: Compl:40%->100% 03/07/15: Stat Rep: RP-150414->RP-150624",36.889000000000003,65,33,null,null,"2014-09-15","2015-06-18"]
[5002,660063,"Study on possible additional configuration for LTE TDD","FS_LTE_TDD_add_config",1,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150652","RP-151283","NTT DOCOMO, Hideaki Takahashi","NTT DOCOMO","TR 36.825 rapporteur: CATT. TR number added. 1st Apr 15: Compl:0%->5% 1st Apr 15: Stat Rep: ->RP-150151 03/07/15: Compl:5%->35% 03/07/15: WID: RP-142248->RP-150652 03/07/15: Stat Rep: RP-150151->RP-150805 29/09/15: Compl:35%->100% 29/09/15: Stat Rep: R",36.825000000000003,66,34,null,null,"2015-01-12","2015-09-29"]
[5005,660066,"Study on Support of single-cell point-to-multipoint transmission in LTE","FS_LTE_SC_PTM",1,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-150177","RP-150695","Jeff GAO","gaoyongqiang@huawei.com","deleted 660062 (duplicated). 29/1: TR number added 1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142205->RP-150177 1st Apr 15: Stat Rep: ->RP-150176 03/07/15: Compl:25%->100% 03/07/15: Stat Rep: RP-150176->RP-150695",36.89,66,34,null,null,"2015-01-12","2015-06-18"]
[5010,660071,"Study on performance enhancements for high speed scenario in LTE","FS_LTE_high_speed",1,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150159","RP-151313","NTTDoCoMo","NTTDoCoMo","TR Rapporteur is Huawei 1st Apr 15: Compl:0%->5% 1st Apr 15: WID: RP-142307->RP-150159 1st Apr 15: Stat Rep: ->RP-150517 03/07/15: Compl:5%->40% 03/07/15: Stat Rep: RP-150517->RP-150793 29/09/15: Compl:40%->80% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 2",null,66,34,null,null,"2015-01-12","2016-01-01"]
[5013,670043,"Study on Downlink Multiuser Superposition Transmission for LTE","FS_LTE_MUST",1,"Rel-13","R1","2015-03-16","2015-12-15",1,"RP-151100","RP-151345","Mediatek",null,"TR added 03/07/15: Compl:0%->30% 03/07/15: WID: RP-150496->RP-151100 03/07/15: Stat Rep: -->RP-150857 29/09/15: Compl:30%->50% 29/09/15: Stat Rep: RP-150857->RP-151345",36.859000000000002,67,34,null,null,"2015-04-01","2016-01-01"]
[{"$f":"A5018+1","v":5018},680018,"Study on S6a/S6d Shared Data Update","FS_eSDU",1,"Rel-13","C4","2015-06-15","2015-12-11",1,"CP-150400",null,"Ulrich Wiehe, Nokia Networks","ulrich.wiehe@nokia.com","07/09/15: 0%->20¦7/12/15: 20%->100","New 29.813",68,35,null,null,"2015-06-15","2015-12-07"]
[5021,690003,"Study on Impacts of the Diameter Base Protocol Specification Update","FS_DBPU",1,"Rel-13","C4","2015-09-07","2015-12-18",1,"CP-150575",null,"Huawei, Peter Schmitt",null,"7/3/16: 0%->79¦13/6/16: 79%->99¦2/12/16: 99%->100","29.274; 29.060; 23.003; 29.272; 29.002; 29.305; 23.008; 29.230; 29.303; 23.007; 24.301; 24.008",69,35,null,null,"2015-09-07","2016-12-02"]
[5023,720087,"Study on multi-node testing for LAA","FS_LTE_LAA_multinode_test",1,"Rel-13","R4","2016-06-15","2017-06-15",1,"RP-162144",null,"Huawei",null,"coexistence testing for REL-13 WI LTE_LAA26/9/16: Compl:0%->10%26/9/16: WID: RP-161197->RP-161672¦20/12/16: Compl:10%->30%¦20/12/16: CD:Thu 15/12/16->Wed 15/03/17¦20/12/16: WID: RP-161672->RP-162144¦21/3/17: CD:Wed 15/03/17->Thu 15/06/17;",null,72,37,null,null,"2016-07-01","2017-06-19"]
[5026,0,"Stage 1 - ONLY Features","-",1,"Rel-12","SP,CP","2011-09-27","2014-03-05",1,"-","-","-","-","-","-",58,30,null,null,"2012-12-14","2012-12-14"]
[5029,500031,"Interworking between Mobile Operators using the Evolved Packet System and Data Application Providers","MOSAP",1,"Rel-12","S1,S2","2010-12-16","2013-12-11",1,"SP-120427","-","Cisco","Vojislav Vucetic (vvucetic@cisco.com)","SP#58 Stage 2 stopped (TR only, no normative work done)","Stage 1",50,26,null,null,"2010-11-29","2012-11-22"]
[5032,520026,"   Deleted - Stage 2 for MOSAP","MOSAP-SA2Del",2,"Rel-12","S2","2011-06-14","2012-12-12",1,"SP-120427","-","Intel","chang.hong.shan@intel.com","SP#58 stopped (no normative work done)","TBD",52,27,"SP-58","PCG-30","2011-05-26","2012-11-22"]
[5037,550024,"Advanced IP Interconnection of Services (IPXS) for national interconnect","IPXSNAT",1,"Rel-12","S1","2012-03-06","2012-09-12",1,"SP-120428","-","KPN","toon.norp@tno.nl","SP#57 Stage 1 completed. Linked to Rel-11 Feature Advanced IP Interconnection of Services (IPXS) UID_470051.","Stage 1",55,28,null,null,"2012-02-22","2012-08-07"]
[5040,550125,"   Stage 1 for Integration of Single Sign-On (SSO) frameworks with 3GPP networks","SSO_Int-SA1",2,"Rel-12","S1","2012-03-08","2012-09-12",1,"SP-120184","-","InterDigital","christopher.wallace@interdigital.com","SP#57 completed",22.100999999999999,55,28,null,null,"2012-02-22","2012-08-07"]
[5045,580060,"Sequential Flexible Alerting","SEQ_FA",1,"Rel-12","S1","2012-12-10","2012-12-12",1,"SP-120895","-","Orange","bruno.tossou@orange-ftgroup.com","SP#58 approved WID & Stage 1 completed. Currently Flexible Alerting (FA) group members are simultaneously alerted by the incoming call. Add the possibility to alert FA group members sequentially. 22/01: acronym modified","Stage 1",58,30,null,null,"2012-11-16","2015-01-22"]
[5048,580161,"   Stage 1 for Language and Modality Information for communications","LangInfo-SA1",2,"Rel-12","S1","2012-12-11","2013-03-06",1,"SP-130108","-","Orange","philippe.lottin@orange.com","SP#59 completed. Updated WID SP-120937=>SP-130108",22.228000000000002,58,30,null,null,"2012-11-16","2013-02-19"]
[5051,590041,"Deleted - Application and Service Access Control","ASAC",1,"Rel-12","S1","2013-03-06","2013-06-19",1,"SP-130124","-","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#60 stopped and Rel-13 FS_ACDC continues. Triggered by TR 22.806 Study on Application specific Congestion control for Data Communication (FS_ACDC) UID_570034","Stage 1",59,30,"SP-60","PCG-31","2013-02-19","2013-02-19"]
[5054,590142,"   Stage 1 for Prevention of Mobile-Originating signalling and/or data traffic of UE in Connected mode","PMOC-SA1",2,"Rel-12","S1","2013-03-04","2013-03-06",1,"SP-130111","-","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#59 completed",22.010999999999999,59,30,null,null,"2013-02-19","2013-02-19"]
[5056,500028,"LIPA Mobility and SIPTO at the Local Network","LIMONET",1,"Rel-12","S2,C4,C1,R3","2010-10-15","2014-03-06",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","CP#63 completed. SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility). Linked to UID_450035 Local IP Access and Selected IP Traffic Offload (LIPA_SIPTO)","Stage 2/3",50,26,null,null,"2010-11-26","2013-02-27"]
[5059,501328,"      Stage 2 for SIPTO at the Local Network","LIMONET-SIPTO-SA2",3,"Rel-12","S2","2010-10-22","2013-06-19",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","SP#60 completed","23.060; 23.401",50,26,null,null,"2010-11-26","2013-06-06"]
[5063,590020,"   RAN aspects for SIPTO at the Local Network","LIMONET-RAN",2,"Rel-12","R3","2013-03-04","2014-03-06",1,"RP-130372","-","Huawei","zheng.zhou@huawei.com","-","UTRA; LTE",59,30,null,null,"2013-02-26","2013-02-26"]
[5067,530016,"      Deleted - Stage 3 CN aspects of LIPA Mobility","LIMONET-LIPA-del2",3,"Rel-12","C1,C4","2011-09-24","2012-12-12",1,"CP-110820","-","Huawei","christian.herrero@huawei.com","SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility)","Stage 3",53,27,"SP-58","PCG-30","2011-08-27","2012-06-06"]
[5072,510249,"   Stage 2 for Operator Policies for IP Interface Selection","OPIIS",2,"Rel-12","S2","2011-04-04","2013-03-06",1,"SP-120738","-","LG Electronics","taehyeon.kim@lge.com","SP#59 completed (23.402 CR#152: Introduction of Inter-APN Routing Policies)",23.402000000000001,51,26,null,null,"2011-02-21","2013-02-27"]
[5075,520129,"   TR on Stage 2 for SMS submit and delivery without MSISDN in IMS","SMSMI-SA2TR",2,"Rel-12","S2","2011-06-08","2012-12-12",1,"SP-120321","-","Nokia Siemens Networks","curt.wong@nsn.com","SP#58 completed","new 23.863",52,27,null,null,"2011-05-26","2012-11-22"]
[5078,590113,"      CT1 part of Stage 3 for SMS submit and delivery without MSISDN in IMS","SMSMI-CT",3,"Rel-12","C1","2013-03-01","2013-12-06",1,"CP-130090","-","NSN","peter.leis@nsn.com","CP#62 completed","23.040; 24.341",59,30,null,null,"2013-02-16","2013-11-18"]
[5081,530142,"   Stage 1 for IMS-based Telepresence","IMS_TELEP",2,"Rel-12","S1","2011-09-22","2012-06-20",1,"SP-110588","-","Orange","bruno.tossou@orange-ftgroup.com","SP#56 completed. 2/4/15: acronym changed to IMS_TELEP",22.228000000000002,53,27,null,null,"2011-07-19","2015-04-02"]
[5083,580002,"      TR on CT part of IMS Telepresence (Stage 2/3)","IMS_TELEP",3,"Rel-12","C1","2012-12-07","2014-06-13",1,"CP-140624","-","Huawei","Weiwei(Tommy) Yang (tommy@huawei.com)","CP#64 completed. 2/4/15: acronym changed to IMS_TELEP","New 24.803",58,30,null,null,"2012-11-19","2015-04-02"]
[5087,641003,"      (IETF) CLUE Protocol data channel (draft-ietf-clue-datachannel) ","IMS_TELEP",3,"Rel-12","C1-IETF","2010-03-22","2014-12-05",1,"CP-140624","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-datachannel); 9/4/21: RFC 8850 added;","draft-ietf-clue-datachannel; RFC 8850",64,33,null,null,"2014-06-06","2021-04-09"]
[5090,580004,"      CT3 part of IMS Telepresence (Stage 3)","IMS_TELEP",3,"Rel-12","C3","2012-12-07","2014-09-11",1,"CP-140624","-","Huawei","Weiwei(Tommy) Yang (tommy@huawei.com)","CP#65 completed. 2/4/15: acronym changed to IMS_TELEP",29.164999999999999,58,30,null,null,"2012-11-19","2015-04-02"]
[5094,590037,"   TR on Architecture enhancements to support Group Communication System Enablers for LTE","GCSE_LTE",2,"Rel-12","S2","2013-03-07","2014-03-07",1,"SP-140433","-","Nokia Networks","rainer.liebhart@nsn.com ","SP#63 completed. TR 23.768v200 for Approval","New 23.768",59,30,null,null,"2013-02-21","2014-09-07"]
[5098,640010,"   CT aspects of Group Communication System Enablers for LTE","GCSE_LTE-CT",2,"Rel-12","C3,C4,C1","2014-06-13","2014-12-09",1,"CP-140559","-","Nokia Networks","thomas.belling@nsn.com","CP#65 updated WID CP-140452=>C3-143199 (added CT1 part)","Stage 3",64,33,null,null,"2014-06-10","2014-09-06"]
[5099,640110,"      CT3 part of Group Communication System Enablers for LTE","GCSE_LTE-CT",3,"Rel-12","C3","2014-06-13","2014-09-11",1,"CP-140559","-","Nokia Networks","thomas.belling@nsn.com","CP#65 completed. TS 29.468v200 for Approval","29.212; 29.213; 29.214; 29.274; New 29.468",64,33,null,null,"2014-06-10","2014-09-06"]
[5105,560021,"   Stage 1 for Support for Interworking with M2M Service Enablement","MTCe-SIMSE",2,"Rel-12","S1","2012-06-18","2013-03-06",1,"SP-120436","-","KPN","toon.norp@tno.nl","SP#59 completed. Define requirements for interworking with M2M service enablement layer specified by ETSI TC M2M in TS 102 689 ( specification for Service Enablement layer)",22.367999999999999,56,29,null,null,"2012-05-14","2013-02-19"]
[5106,570030,"   Stage 1 for Machine-Type and other mobile data applications Communications – Service Requirement Maintenance","MTCe-SRM",2,"Rel-12","S1","2012-09-13","2013-03-06",1,"SP-130105","-","KPN","toon.norp@tno.nl","SP#59 completed. Updated WID SP-120541=>SP-130105","22.101; 22.368",57,29,null,null,"2012-08-06","2013-02-19"]
[5112,630001,"      Stage 3 for BB1: Small Data and Device Triggering Enhancements","MTCe-SDDTE-CT",3,"Rel-12","C4,C3","2014-03-05","2014-09-11",1,"CP-140489","-","Huawei","peter.schmitt@huawei.com","CP#65 updated WID CP-140272=>CP-140489","Stage 3",63,32,null,null,"2014-01-29","2014-07-29"]
[5114,630201,"         CT3 part of Stage 3 for BB1: Small Data and Device Triggering Enhancement","MTCe-SDDTE-CT",4,"Rel-12","C3","2014-03-05","2014-06-13",1,"CP-140489","-","Huawei","peter.schmitt@huawei.com","CP#64 completed",29.367999999999999,63,32,null,null,"2014-01-29","2014-07-29"]
[5117,561622,"      TR on Stage 2 BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP",3,"Rel-12","S2","2012-06-18","2013-12-11",1,"SP-120442","-","Ericsson","peter.hedman@ericsson.com ","SP#62 completed. TR 23.887v200 for Approval","New 23.887",56,29,null,null,"2012-04-13","2013-11-28"]
[5121,620207,"         Deleted - CT4 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP-CT4",4,"Rel-12","C4","2013-12-09","2014-09-11",1,"CP-130714","-","Ericsson","mikael.wass@ericsson.com","CP#65 stopped (no inpact on CT4)","29.274; 29.060; 23.008",62,32,"CP-65","PCG-33","2013-11-18","2014-05-25"]
[5125,700005,"      Testing of Support of Power Saving Mode in GERAN","MTCe-UEPCOP_GERAN3new",3,"Rel-12","G3","2015-11-11","2016-05-12",0.1,"GP-151186",null,"Ericsson","sajal.kumar.das@ericsson.com","7/12/15: created.02/3/16: acronym: MTCe-UEPCOP-GERAN_test->MTCe-UEPCOP_GERAN3new¦2/3/16: 0%->10",null,70,36,null,null,"2014-08-29","2016-03-02"]
[5126,560422,"   Deleted - BB4: Group based MTC feature (GROUP)","MTCe-GROUP",2,"Rel-12","S2","2012-06-20","2012-12-12",1,"SP-120267","-","KPN","Annemieke Kips","SP#58 stopped (at 25% completion)",23.681999999999999,56,29,"SP-58","PCG-30","2012-04-13","2012-12-14"]
[5132,670048,"   UE Conformance Test Aspects - Low cost & enhanced coverage MTC UE for LTE","LC_MTC_LTE-UEConTest",2,"Rel-12","R5","2015-03-16","2016-12-15",1,"RP-160069",null,"Ericsson",null,"03/07/15: Compl:0%->13% 03/07/15: WID: RP-150135->RP-150838 03/07/15: Stat Rep: ->RP-150833 29/09/15: Compl:13%->25% 29/09/15: Stat Rep: RP-150833->RP-151165 ¦1/1/16: Compl:25%->70% ¦1/1/16: CD:Tue 15/12/15->Tue 15/03/16 ",null,67,34,null,null,"2015-04-01","2016-12-20"]
[5133,560024,"Policy and Charging Control for supporting fixed broadband access networks","P4C",1,"Rel-12","S2,S1,S5,C3,C1,C4","2012-06-20","2014-12-12",1,"SP-120443","-","Huawei","marco.spini@huawei.com","Linked to BBF, IETF work. SP#58 stopped BB3 to BB6. Split BB1 and BB2 into TR and Stage 2 work","Stage 1/2/3",56,29,null,null,"2012-04-13","2013-01-08"]
[5139,610112,"         CT3 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks","P4C-F-CT3",4,"Rel-12","C3","2013-09-06","2014-06-13",1,"CP-130776","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","CP#64 completed","29.212; 29.213; 29.215; 29.219",61,31,null,null,"2013-08-12","2014-04-16"]
[5141,620010,"         CT4 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks","P4C-F-CT3",4,"Rel-12","C4","2013-12-06","2014-06-13",1,"CP-130776","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","CP#64 completed",29.273,62,32,null,null,"2013-11-19","2014-04-16"]
[5144,560224,"   BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI)","P4C-TI",2,"Rel-12","S2","2012-06-20","2013-06-19",1,"SP-120444","-","Alcatel-Lucent","konstantin.livanos@alcatel-lucent.com","-","-",56,29,null,null,"2012-06-04","2013-01-08"]
[5148,560424,"   Deleted - BB4: Policy and Charging Control for EPC routed traffic over fixed broadband access networks of 3GPP UEs connected via H(e)NB in convergent scenarios (P4C-HeNB)","P4C-HeNB",2,"Rel-12","S2","2012-06-21","2012-12-12",1,"SP-120278","-","NEC","Stefan.Schmid@neclab.eu","SP#58 stopped (at 0% completion)","23.139; 23.203; new 23.896",56,29,"SP-58","PCG-30","2012-06-04","2013-01-08"]
[5152,560325,"   Stage 1 for IMS Business Trunking for IP-PBX in Static Mode of Operation","BusTI-SA1",2,"Rel-12","S1","2011-09-28","2012-09-12",1,"SP-120862","-","Deutsche Telekom","kurt.bischinger@t-mobile.at","SP#57 completed. 22.228CR#0171 ",22.228000000000002,56,29,null,null,"2012-05-11","2012-12-10"]
[5155,610007,"   CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3)","BusTI-CT",2,"Rel-12","C1,C3","2013-09-06","2014-12-09",1,"CP-140197","-","Deutsche Telekom","michael.kreipl@telekom.de","-","Stage 3",61,31,null,null,"2013-08-10","2014-03-03"]
[5157,610207,"      CT3 part of CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3)","BusTI-CT",3,"Rel-12","C3","2013-09-06","2014-06-11",1,"CP-140197","-","Deutsche Telekom","michael.kreipl@telekom.de","CP#64 completed",29.164999999999999,61,31,null,null,"2013-08-10","2014-04-16"]
[5160,560226,"   Stage 2 for WLAN Network Selection for 3GPP Terminals","WLAN_NS-SA2",2,"Rel-12","S2","2012-06-22","2013-12-11",1,"SP-120847","-","Intel","vivek.g.gupta@intel.com","SP#62 completed","23.402; 23.865",56,29,null,null,"2012-11-22","2013-11-28"]
[5166,600016,"   Deleted - CT aspects of IMS registration control","IMS_RegCon-CT",2,"Rel-12","C1,C4","2013-06-19","2013-12-11",1,"CP-130217","-","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","SP#62 no CT/Stage 3 work is needed (stopped at 0% completion)","Stage 2/3",60,31,"SP-62","PCG-32","2013-05-28","2013-12-10"]
[5168,600216,"      Deleted - CT4 aspects of CT aspects of IMS registration control (Stage 3)","IMS_RegCon-CT4",3,"Rel-12","C4","2013-06-19","2013-12-11",1,"CP-130217","-","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","SP#62 no CT/Stage 3 work is needed (stopped at 0% completion)","29.228; 29.229; 23.008",60,31,"SP-62","PCG-32","2013-05-28","2013-12-10"]
[5171,580259,"   TR on Stage 2 for Proximity-based Services","ProSe-SA2TR",2,"Rel-12","S2","2012-12-13","2014-03-07",1,"SP-140574","-","Qualcomm","Haris Zisimopoulos (harisz@qti.qualcomm.com)","SP#63 completed. TR 23.703v200 for Approval","New 23.703",58,30,null,null,"2012-11-16","2014-09-15"]
[5175,640039,"   Charging Aspects of Proximity-based Services","ProSe-CH",2,"Rel-12","S5","2014-06-19","2015-03-13",1,"SP-140401","SP-140543","Qualcomm","Cheng Hong (hongc@qti.qualcomm.com)","SP#65 exception in SP-140543. Mar15: 85->100%","Stage 2/3",64,33,null,null,"2014-06-06","2015-03-05"]
[5179,630106,"      CT1 part of CT aspects of Proximity-based Services","ProSe-CT",3,"Rel-12","C1","2014-03-05","2014-12-09",1,"CP-140290","CP-140615","Qualcomm","Lena Chaponniere (lguellec@qti.qualcomm.com)","CP#65 completion 09/14=>12/14. Exception in CP-140615. TS 24.333/4v200 for Approval. Dec.14: 90->100%","24.301; 23.122; New TSs (24.333; 24.334)",63,32,null,null,"2014-01-29","2014-12-04"]
[5182,630406,"      CT6 part of CT aspects of Proximity-based Services","ProSe-CT",3,"Rel-12","C6","2014-03-06","2014-12-09",1,"CP-140290","CP-140695","Qualcomm","Lena Chaponniere (lguellec@qti.qualcomm.com)","CP#65 completion 09/14=>12/14. Exception in CP-140695. Dec.14: 60->100%",31.102,63,32,null,null,"2014-01-29","2014-12-03"]
[5184,630130,"      Core part: LTE Device to Device Proximity Services","LTE_D2D_Prox-Core",3,"Rel-12","R1,R2,R4","2014-03-15","2015-03-13",1,"RP-142043","RP-150094","Qualcomm","Shailesh Patil (patil@qti.qualcomm.com)","¦CD:Sat 15/03/14->Sun 15/03/15Compl:0%->95%¦CD:Fri 13/03/15->Sun 15/03/15¦Stat Rep: RP-141244->RP-141894 1st Apr 15: Compl:95%->100% 1st Apr 15: Stat Rep: RP-141894->RP-150094","36.101; 36.133; 36.211; 36.212; 36.213; 36.214; 36.300; 36.304; 36.306; 36.321; 36.322; 36.323; 36.331; 36.413; 36.423; New 36.877",63,32,null,null,"2014-03-10","2015-04-01"]
[5187,580062,"Web Real Time Communication access to IMS","IMS_WebRTC",1,"Rel-12","S1,S2,S3","2012-12-14","2019-03-07",1,"SP-130707","-","China Mobile","lulu@chinamobile.com","IETF RTCWEB and W3C WEBRTC groups are specifying a browser-based client to support communication services. Interoperability for WebRTC clients to access 3GPP IMS is needed.","Stage 1/2",58,30,null,null,"2012-11-16","2013-09-09"]
[5190,600041,"   Stage 2 for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S2","2013-06-19","2014-03-07",1,"SP-130707","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#63 completed",23.228000000000002,60,31,null,null,"2013-06-06","2014-02-04"]
[5193,620067,"   TR on Security for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S3","2013-12-11","2014-09-17",1,"SP-130707","-","Ericsson","oscar.ohlsson@ericsson.com","SP#65 completed. TR 33.871v200 for Approval","New 33.871",62,32,null,null,"2013-12-05","2014-09-04"]
[5198,630103,"      CT1 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS","IMS_WebRTC-CT1",3,"Rel-12","C1","2014-03-05","2014-12-09",1,"CP-140192","CP-140621","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","CP#65 TS 24.371v100 for Information. Completion 09/14=>12/14. Exception in CP-140621. Dec.14: 70->90%. 3/3/15: 100% cpltd.","24.229; New 24.371",63,32,null,null,"2014-01-29","2015-03-03"]
[5202,870067,"       (IETF) Third-Party Token-based Authentication and Authorization for Session Initiation Protocol (SIP) (draft-ietf-sipcore-sip-token-authnz)","IMS_WebRTC-yusef",3,"Rel-12","C1-IETF","2014-09-12","2014-12-05",1,null,null,null,null,"9/4/21: RFC 8898 added;","RFC 8898",87,44,null,null,"2014-09-02","2021-04-09"]
[5206,580163,"   Stage 2 for Usage Monitoring Control PCC enhancement","UMONC",2,"Rel-12","S2","2012-12-13","2013-03-06",1,"SP-120928","-","ZTE","bi.yifeng@zte.com.cn ","SP#59 completed. 23.203 CR#0782 (Time Based Usage Monitoring), CR#0784 (Usage Monitoring via Online Charging System)",23.202999999999999,58,30,null,null,"2012-11-18","2013-02-27"]
[5209,590139,"   Stage 2 for Application Based Charging","ABC-SA2",2,"Rel-12","S2","2013-03-07","2013-06-19",1,"SP-130328","-","Allot","Alla Goldner (agoldner@allot.com)","SP#60 completed",23.202999999999999,59,30,null,null,"2013-02-21","2013-07-25"]
[5211,600049,"   CT3 aspects of Application Based Charging (Stage 3)","ABC-CT3",2,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130353","-","Allot","Alla Goldner (agoldner@allot.com)","CP#62 completed","29.212; 29.213; 29.214; 29.215; 29.219",60,31,null,null,"2013-05-29","2013-10-21"]
[5214,610009,"   Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC","eSaMOG-St3",2,"Rel-12","C1,C4","2013-09-09","2014-12-09",1,"CP-130715","-","ZTE","Joy Zhou (zhou.xingyue@zte.com.cn)","CP#62 updated WID CP-130580=>CP-130715","Stage 3",61,31,null,null,"2013-08-10","2013-11-28"]
[5217,610039,"Optimized Offloading to WLAN in 3GPP-RAT Mobility","WORM",1,"Rel-12","S2,C1","2013-09-12","2014-06-13",1,"SP-130392","-","BlackBerry","Steve Barrett (sbarrett@blackberry.com)","Linked to TR 23.890 Study on Optimized Offloading to WLAN in 3GPP-RAT mobility (FS_WORM), SAE for support for non-3GPP accesses, Multi-Access PDN Connectivity (MAPCON), IP Flow Mobility and Seamless WLAN Offload (IFOM), CS Fallback in EPS (SAES-CSFB)","Stage 2/3",61,31,null,null,"2013-07-25","2013-09-09"]
[5220,610040,"Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN",1,"Rel-12","S2,C3,C1,C4","2013-09-12","2014-09-11",1,"SP-130393","-","Alcatel-Lucent","Laurent.thiebaut@alcatel-lucent.com","Rel-11 Network Provided Location Information for IMS (NWK-PL2IMS) covers the case where UE is served by a 3GPP RAN. This WI covers the case where the UE is served by a TWAN","Stage 2/3",61,31,null,null,"2013-07-25","2013-09-09"]
[5225,620308,"      CT4 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN-CT",3,"Rel-12","C4","2013-12-06","2014-09-11",1,"CP-130810","-","China Telecom","Xia Xu (xiaxu@ctbri.com.cn)","CP#65 completed","29.273; 29.274; 29.275; 29.328; 29.329",62,32,null,null,"2013-11-19","2014-07-28"]
[5229,630004,"   CT aspects of Core Network Overload – User Location Information reporting improvements","CNO_ULI-CT",2,"Rel-12","C3,C4","2014-03-05","2014-09-11",1,"CP-140093","-","Alcatel-Lucent","horst.brinkmann@alcatel-lucent.com","Specify Stage 3 procedures to support the ULI signalling optimizations","Stage 3",63,32,null,null,"2014-01-29","2014-01-29"]
[5233,510054,"Security aspects of Public Warning System","PWS_Sec",1,"Rel-12","S3,S1","2011-03-23","2014-09-17",1,"SP-140299","-","ST-Ericsson","john.mattsson@ericsson.com","-","-",51,26,null,null,"2012-06-02","2014-06-09"]
[5236,511354,"   Deleted - SA3 part for Security aspects of Public Warning System","PWS_Sec-del1",2,"Rel-12","S3","2011-03-30","2014-06-18",1,"SP-140299","-","ST-Ericsson","john.mattsson@ericsson.com","SP#64 stopped","New 33.269",51,26,"SP-64","PCG-33","2012-06-02","2014-06-09"]
[5237,510154,"   Deleted - Stage 1 for Security aspects of Public Warning System","PWS_Sec-del2",2,"Rel-12","S1","2011-03-23","2012-06-20",1,"SP-120434","-","ST-Ericsson","john.mattsson@ericsson.com","Completed in Rel-9 under PWS. SP#55 stopped, Stage 1 requirements removed from Rel-9 onwards (SP-120172). AP 55/1: SA1 to align Stage 1 PWS security for Rel-12. SA1 new WID PWS Security UID_560029. ",22.268000000000001,51,26,"SP-56","PCG-29","2012-06-02","2012-06-26"]
[5242,560030,"Extended IMS media plane security features","eMEDIASEC",1,"Rel-12","S3,C4,C1,C3,IETF","2012-06-20","2014-12-09",1,"SP-120447","-","Vodafone","Aguibou.Barry@vodafone.com","Triggered by Rel-11 TR 33.829 Study on Extended IMS media plane security features (FS_eMEDIASEC)","Stage 2/3",56,29,null,null,"2012-06-02","2013-02-19"]
[5244,611003,"   (IETF) SA3 part of Extended IMS media plane security features (RFC 7345)","eMEDIASECSA3IETF",2,"Rel-12","S3-IETF","2012-06-20","2014-09-12",1,"SP-120447","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","SP#65 completed","RFC 7345 (was draft-ietf-mmusic-udptl-dtls)",61,31,null,null,"2013-09-23","2014-09-02"]
[5247,580006,"      CT4 part of CT aspects of Extended IMS media plane security features","eMEDIASEC-CT",3,"Rel-12","C4","2012-12-19","2014-12-09",1,"CP-130597","CP-140479","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#65 completion 09/14=>12/14. Exception in CP-140479. Dec.14: 90->100. 2/4/15: acronym changed to eMEDIASEC-CT","23.334; 29.334; 29.238; 23.333; 29.333",58,30,null,null,"2012-11-14","2015-04-02"]
[5252,580008,"      CT3 part of CT aspects of Extended IMS media plane security features","eMEDIASEC-CT",3,"Rel-12","C3","2012-12-19","2014-12-09",1,"CP-130597","CP-140569","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#65 completion 06/14=>12/14. Level 100%=>80%. Exception in CP-140569. CP#64 completed. Dec.14: 80->100. 2/4/15: acronym changed to eMEDIASEC-CT",29.161999999999999,58,30,null,null,"2012-11-14","2015-04-02"]
[5256,600050,"   CT aspects of Tunneling of UE Services over Restrictive Access Networks (Stage 3)","TURAN-CT",2,"Rel-12","C1","2013-06-14","2014-06-13",1,"CP-130716","-","Huawei","Haitao Wei (weihaitao@huawei.com)","CP#64 completed. Stage 3 for 2 new SA3 solutions for firewall traversal: 1) UE access to PLMN IP-based services via restrictive non-3GPP Ans, 2) UE access to IMS services via restrictive ANs","24.229; 24.302; New 24.322",60,31,null,null,"2013-05-28","2014-05-26"]
[5260,470032,"   Stage 2/3 for Codec for Enhanced Voice Services","EVS_codec-SA4",2,"Rel-12","S4","2010-03-25","2014-12-12",1,"SP-140151","SP-140467","Huawei","lei.miao@huawei.com","SP#65 completion 09/14=>12/14. Exception in SP-140467. TS 26.441v200 for Approval. TSs 26.442/44/45/46/47/48/49/50/51v100 for 1-step Approval. Ongoing TS 26.443 EVS Codec ANSI C code (floating point). Dec.14: 90->95","26.114; New (26.441; 26.442; 26.443; 26.444; 26.445; 26.446; 26.447; 26.448; 26.449; 26.450; 26.451)",47,24,null,null,"2010-03-10","2015-06-26"]
[5263,650105,"      CT4 part of CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",3,"Rel-12","C4","2014-09-16","2014-12-09",1,"CP-140800","CP-140478","Nokia Networks","Jan.Kall@nsn.com","CP#65 exception in CP-140478. Dec.14: 0->100¦WID: CP-140492-> CP-140800","23.334; 29.232; 29.238; 29.332; 29.333; 29.334",65,33,null,null,"2014-07-29","2014-12-09"]
[5264,650205,"      CT1 part of CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",3,"Rel-12","C1","2014-09-16","2014-12-09",1,"CP-140800","CP-140618","Nokia Networks","Jan.Kall@nsn.com","CP#65 exception in CP-140618. Dec.14: 0->100%¦WID: CP-140492-> CP-140800",24.228999999999999,65,33,null,null,"2014-07-29","2014-12-09"]
[5269,600006,"   CT aspects of Coordination of Video Orientation","CVO-CT",2,"Rel-12","C4,C1,C3","2013-06-14","2013-12-06",1,"CP-130393","-","Ericsson","nevenka.biondic@ericsson.com","Complete CVO support (both, basic 2 bit orientation and additional option for extra 6 bit granularity) within CN protocols/procedures for IMS nodes, e.g. IMS ALG/AGW,IBCF/TrGW,MRFC/MRFP & add support of CVO-related SDP attributes to be negotiated by UE","Stage 2/3",60,31,null,null,"2013-05-28","2013-11-19"]
[5272,600306,"      CT3 part of CT aspects of Coordination of Video Orientation","CVO-CT",3,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130393","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed","29.162; 29.163",60,31,null,null,"2013-05-28","2013-11-18"]
[5275,570233,"   High Efficiency Video Coding in 3GPP services PSS, MBMS, DASH, MMS, MTSI, IMS Messaging and Presence","HEVC-SA4",2,"Rel-12","S4","2012-09-17","2014-06-18",1,"SP-130569","-","Qualcomm","Ye-Kui Wang (yekuiw@qti.qualcomm.com)","SP#64 completed","26.114; 26.140; 26.141; 26.234; 26.244; 26.247; 26.346",57,29,null,null,"2012-08-30","2014-04-16"]
[5278,580066,"IMS-based Streaming and Download Delivery Enhancements","IMS_SDE",1,"Rel-12","S4","2012-12-12","2014-03-07",1,"SP-120767","-","Intel","ozgur.oyman@intel.com","Provide an extension of IMS based PSS and MBMS user services","-",58,30,null,null,"2012-11-12","2013-04-19"]
[5283,580267,"   Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - UE Delay aspects","ART_LTE-UED",2,"Rel-12","S4","2012-12-12","2014-09-17",1,"SP-120770","-","AT&T, Orange","luisa.marchetto@att.com, stephane.ragot@orange.com","SP#65 completed","26.131; 26.132",58,30,null,null,"2012-11-12","2014-08-13"]
[5286,590343,"   TR on Enhanced MBMS Operation","MI-EMOTR",2,"Rel-12","S4","2013-03-06","2014-12-12",1,"SP-140212","SP-140471","Huawei","Zhiming Li (lizhiming@huawei.com)","SP#65 completion 09/14=>12/14. Exception in SP-140471. SP#63 TR 26.848v100 for Information. Dec.14: 85->100. ","New 26.848",59,30,null,null,"2013-02-20","2015-03-05"]
[5287,590143,"   Enhanced MBMS Operation","MI-EMO",2,"Rel-12","S4","2013-03-06","2014-12-12",1,"SP-140212","SP-140471","Huawei","Zhiming Li (lizhiming@huawei.com)","SP#65 completion 09/14=>12/14. Exception in SP-140471. Dec.14: 85->100","26.247; 26.346",59,30,null,null,"2013-02-20","2015-03-05"]
[5291,670098,"   S4 aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI",2,"Rel-12","S4","2013-03-06","2014-09-16",1,"SP-140600","-","Ericsson","tomas.frankkila@ericsson.com","SP#65 completed. Updated WID SP-130670=>SP-140594. Reduced Scope & Objectives. Moved work on new TR 26.924, etc. to Rel-13. Co-ordinate with CT1/3/4. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040",26.114000000000001,59,30,null,null,"2013-02-20","2014-09-09"]
[5296,620066,"Video Coding Enhancements in IMS Messaging and Presence","VCEIMP",1,"Rel-12","S4","2013-12-11","2014-03-07",1,"SP-130579","-","Ericsson","frederic.gabin@ericsson.com","SP#63 completed. Linked to Rel-6 Media Codecs and Formats for IMS Messaging and Presence (PRESNC-COFIMP) UID_34025. Work item which gave rise to TS 26.141",26.140999999999998,62,32,null,null,"2013-11-29","2014-01-29"]
[5299,560131,"   Rel-12 Self-Organizing Networks (SON) - OAM aspects","OAM12-SON",2,"Rel-12","S5","2011-09-21","2013-12-11",1,"-","-","-","-","OAM12-SON is an umbrella BB also for SON related TEI12 type of changes that are not part of any other dedicated feature/WI","-",56,29,null,null,"2012-04-18","2012-11-19"]
[5302,560135,"      Converged Management Model Alignment (Phase 2)","OAM-MODAL",3,"Rel-12","S5","2012-06-20","2014-09-17",1,"SP-140322","-","NSN","olaf.pollakowski@nsn.com","SP#65 completed. TR 28.280v100 for 1-step Approval","32.156; new 28.820",56,29,null,null,"2012-05-14","2014-08-25"]
[5305,530150,"      Performance measurements part Network Management for 3GPP Interworking WLAN","OAM-IWLAN-SA5P",3,"Rel-12","S5","2011-09-22","2014-09-17",1,"SP-140542","-","China Mobile","Chengang@chinamobile.com, lijian@chinamobile.com","SP#65 completed. TS 28.402v100 for 1-step Approval, withdraw New TS 28.401 (CN and non-3GPP access i/w PMs). Moved PMs for EPC and non-3GPP access i/w from 28.401=>28.402","new 28.401; withdrawn new 28.402",53,27,null,null,"2011-08-27","2014-09-10"]
[5310,580054,"   Deleted - Rel-12 Performance Management","OAM12-PM",2,"Rel-12","S5","2013-06-21","2014-09-16",1,"-","-","-","-","OAM12-PM is an umbrella BB also for PM related TEI12 type of changes that are not part of any other dedicated feature/WI","-",58,30,"SP-69",null,"2012-11-15","2014-08-19"]
[5313,620257,"      OAM aspects of Network Sharing - Impacts on existing specifications","OAM-SHARE-SA5imp",3,"Rel-12","S5","2013-12-12","2014-12-12",1,"SP-130607","SP-140545","Orange","jeanmichel.cornily@orange.com","SP#65 completion 09/14=>12/14. Exception in SP-140545. Dec.14: 60->100","28.401.28.621/2/3.28.651/2/3.28.654/5/6.28.657/8/9.28.701/2/3.28.731/2/3.28.734/5/6.32.101/2.32.111-1/2/3/6.32.121/2/6.32.155.32.171/2/6.32.300/1/2/6.32.311/2/6.32.321/2/6.32.331/2/6.32.341/2/6.32.351/352/6.32.361/2/6.32.381/2/6.32.405/6/7/8/9/10/11/12/41",62,32,null,null,"2013-11-28","2014-12-04"]
[5314,570037,"Rel-12 Charging","CH12",1,"Rel-12","S5","2012-12-12","2014-06-18",1,"-","-","-","-","CH12 is an umbrella Feature for changes that are not part of any other dedicated feature/WI","-",57,29,null,null,"2012-09-19","2012-09-19"]
[5318,620058,"   Charging for IMS centralized service (ICS) control (Stage 2/3)","CHICS",2,"Rel-12","S5","2013-12-11","2014-06-18",1,"SP-130610","-","NSN","Gerald.Goermer@nsn.com","SP#64 completed. Align SA5 Charging specifications with Rel-8 Feature IMS Centralized Service control (ICSRA) and subsequent enhancements under TEIx (SA2 23.292 ICSRA Stage 2, CT3 29.292, CT1 24.607, 24.611)","32.250; 32.298",62,32,null,null,"2013-12-06","2014-06-10"]
[5321,531004,"   (IETF) CT1 part of IMS Emergency PSAP Callback (RFC 7090)","EMC_PC",2,"Rel-12","C1-IETF","2011-09-21","2014-06-13",1,"CP-130218","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#64 completed. 2/4/15: acronym changed to EMC_PC","RFC 7090 (was draft-ietf-ecrit-psap-callback",53,27,null,null,"2011-08-28","2015-04-02"]
[5327,580011,"   CT4 part of Reporting Enhancements in Warning Message Delivery (Stage 2/3)","REP_WMD-CT4",2,"Rel-12","C4","2012-12-10","2014-06-13",1,"CP-130480","-","one2many","peter.sanders@one2many.eu","CP#64 completed","23.007; 29.168",58,30,null,null,"2012-11-19","2014-05-25"]
[5329,590121,"      Core part: PWS - Reset/Failure/Restart in Warning Message Delivery in LTE","REP_WMD-RFR_PWS-Core",3,"Rel-12","R3","2013-03-04","2014-06-13",1,"RP-130398","RP-140637","one2many, Huawei","peter.sanders@one2many.eu, Dai Mingzeng (daimingzeng@huawei.com)","RP#64 completed",36.412999999999997,59,30,null,null,"2013-02-26","2014-03-04"]
[5332,600008,"   CT3 part of Single Radio Voice Call Continuity (SRVCC) before ringing","bSRVCC",2,"Rel-12","C3","2013-06-12","2013-06-14",1,"CP-130219","-","NTT DOCOMO","keisuke.sasada.kx@nttdocomo.com","CP#60 completedbSRVCC",29.164999999999999,60,31,null,null,"2013-05-28","2015-04-02"]
[5336,601002,"   (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-holmberg-sipcore-received-realm)","IMSProtoc6",2,"Rel-12","C1-IETF","2013-05-21","2014-12-09",1,"CP-120905","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6¦21/3/17: 50%->100","draft-holmberg-sipcore-received-realm",60,31,null,null,"2013-06-10","2017-03-21"]
[5340,611001,"   (IETF) CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-holmberg-sipcore-received-realm)","IMSProtoc6",2,"Rel-12","C3-IETF","2013-09-06","2014-12-05",1,"CP-120905","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6¦21/3/17: 50%->100","draft-holmberg-sipcore-received-realm",61,31,null,null,"2013-08-23","2017-03-21"]
[5341,580016,"SAE Protocol Development - Phase 3","SAES3",1,"Rel-12","C1","2012-12-07","2014-09-11",1,"CP-120704","-","InterDigital","behrouz.aghili@interdigital.com ","Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005","Stage 2/3",58,30,null,null,"2012-11-19","2013-02-16"]
[5345,580020,"IM-SSF Application Server Service Data Descriptions (Stage 2/3)","IMS_SSFDD",1,"Rel-12","C4,C1","2012-12-07","2013-06-14",1,"CP-120756","-","Huawei","susan.shishufeng@huawei.com","CP#60 completed","Stage 2/3",58,30,null,null,"2012-11-19","2013-05-29"]
[5348,580023,"Diameter based interface between SGSN and SMS central functions (Stage 2/3)","Dia_SGSN_SMS",1,"Rel-12","C4,C1","2012-12-10","2013-12-06",1,"CP-130437","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#62 completed","Stage 2/3",58,30,null,null,"2012-11-20","2013-11-18"]
[5354,590112,"   CT4 part of eMBMS restoration procedures","eMBMS_Rest",2,"Rel-12","C4","2013-03-01","2013-12-06",1,"CP-140271","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#62 completed","23.007; 23.008; 29.274",59,30,null,null,"2013-03-07","2013-11-18"]
[5356,590014,"Dual Radio VCC enhancements (Stage 2/3)","eDRVCC",1,"Rel-12","C1,C3.S2","2012-09-19","2013-12-06",1,"CP-130091","-","Ericsson","Jan.Holm@ericsson.com","CP#62 completed. Stage 2 in Rel-12 TEI12 TS 23.237 CR#0431, CR#0440, CR#0441, CR#0453 (pre-alerting). Stage 3 linked to Rel-8 Feature IMS Service Continuity (IMS-Cont) UID_390056 (Stage 2 in TS 23.237). 2/4/15: acronym changed to eDRVCC","Stage 2/3",59,30,null,null,"2013-02-16","2013-11-18"]
[5359,590314,"      CT1 part of Stage 3 for Dual Radio VCC enhancements","eDRVCC",3,"Rel-12","C1","2013-03-01","2013-12-06",1,"CP-130091","-","Ericsson","Jan.Holm@ericsson.com","CP#62 completed. 2/4/15: acronym changed to eDRVCC","24.237; 24.292",59,30,null,null,"2013-02-16","2015-04-02"]
[5363,600209,"   CT1 part of CT Aspects of Signalling of Image Size","SIS_CT",2,"Rel-12","C1","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed",24.228999999999999,60,31,null,null,"2013-05-28","2013-11-19"]
[5367,610004,"Proxy Call Session Control Function (P-CSCF) restoration enhancements (Stage 2/3)","PCSCF_RES",1,"Rel-12","C4,C3,C1","2013-04-03","2014-12-09",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 updated WID CP-140443=>CP-140490. Based TR 29.806, solutions B and D are selected for standardization. Dec.14: 95->100","Stage 2/3",61,31,null,null,"2013-08-10","2014-12-04"]
[5368,610104,"   TR on Proxy Call Session Control Function (P-CSCF) restoration enhancements","PCSCF_RES",2,"Rel-12","C4","2013-09-06","2014-09-11",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 completed. TR 29.806v200 for Approval","New 29.806",61,31,null,null,"2013-08-10","2014-09-06"]
[5372,650002,"      CT3 part of Common for HSS & PCRF solutions","PCSCF_RES",3,"Rel-12","C3","2013-05-03","2014-12-09",1,"CP-140490","CP-140687","Huawei","susan.shishufeng@huawei.com","CP#65 updated WID CP-140443=>CP-140490 (added CT3 part). Exception in CP-140687","29.061; 29.165",65,33,null,null,"2013-08-10","2014-06-03"]
[5375,640114,"      CT1 part of HSS based solution","PCSCF_RES",3,"Rel-12","C1","2013-04-03","2014-12-09",1,"CP-140490","CP-140605","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 completion 09/14=>12/14. Exception in CP-140605. Dec.14: 65->100%",24.228999999999999,64,33,null,null,"2013-08-10","2014-12-04"]
[5381,610208,"   CT3 part of Updating IMS to conform to RFC 6665","UP6665",2,"Rel-12","C3","2013-09-09","2013-12-06",1,"CP-130717","-","BlackBerry","Andrew Allen (aallen@blackberry.com)","CP#62 completed","29.163; 29.165",61,31,null,null,"2013-07-25","2013-11-19"]
[5383,670034,"   (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-ietf-sipcore-refer-explicit-subscription)","UP6665",2,"Rel-12","C1-IETF","2015-03-13","2015-03-13",1,"CP-130717",null,"BlackBerry","Andrew Allen (aallen@blackberry.com)","Added as per CT chair indications on 12th March 2015, no WID, no end date¦14/09/15: 50%->100; 9/4/21: RFC 7614 added;","draft-ietf-sipcore-refer-explicit-subscription; RFC 7614",67,34,null,null,"2015-03-13","2021-04-09"]
[5387,620204,"   CT3 part of IMS Operator Determined Call Barring enhancements","eIODB",2,"Rel-12","C3","2013-12-09","2014-09-11",1,"CP-130711","-","Ericsson","Jorgen.Axell@ericsson.com","CP#65 completed",29.164999999999999,62,32,null,null,"2013-11-18","2014-08-01"]
[5390,630102,"   CT4 part of ICE impacts on IMS H.248 profiles (Stage 2/3)","ICEH248",2,"Rel-12","C4","2014-03-05","2014-09-11",1,"CP-140266","-","NSN","Jan.Kall@nsn.com","CP#65 completed","23.333; 23.334; 29.232; 29.238; 29.332; 29.333; 29.334",63,32,null,null,"2014-01-29","2014-07-28"]
[5394,630205,"   CT1 part of Transfer of ETSI business trunking specifications","IMS_Corp2",2,"Rel-12","C1","2014-03-05","2014-12-09",1,"SP-140170","CP-140619","Alcatel-Lucent","keith.drage@alcatel-lucent.com, Youssef Chadli","CP#65 TS 24.525v200 for Approval. TR 24.969v100 for Information. Completion 09/14=>12/14. Exception in CP-140619. Dec.14: 90->100","New TSs [24.523 (182 023); 24.524 (182 024); 24.525 (182 025)]; New 24.969 (183 069)",63,32,null,null,"2014-01-29","2014-12-04"]
[5395,630008,"Support of ALT-C attribute","ALTC",1,"Rel-12","C4,C1,C3","2014-03-10","2014-12-09",1,"CP-140191","-","Orange","lionel.morand@orange.com","SA2 TS 23.228 requires UEs supporting IPv4, IPv6 or both IPv4 and IPv6 IP address formats shall be supported by IMS. Specify procedures to support altc SDP attribute within IMS for terminating communications destined to an enterprise network.","-",63,32,null,null,"2014-01-29","2014-03-03"]
[5399,640003,"Diameter Overload Control Mechanisms","DOCME",1,"Rel-12","C4,IETF","2014-06-13","2014-12-09",1,"CP-140273","-","Orange","lionel.morand@orange.com","Triggered by TR 29.809 Study on Diameter overload control mechanism (FS_DOCME)","-",64,33,null,null,"2014-05-25","2014-06-16"]
[{"$f":"A5402+1","v":5402},640004,"Impacts of RFC7044 for introduction of the new History-Info header field","HISTORY_CT",1,"Rel-12","C1,C3","2014-06-13","2014-12-09",1,"CP-140285","-","Deutsche Telekom","Roland Jesske (r.jesske@telekom.de)","IETF updated RFC4244 for History-Info header field to RFC7044. IETF introduced new features which could be useful for 3GPP use cases.","-",64,33,null,null,"2014-04-07","2014-04-07"]
[5406,640107,"   CT1 part of Indication of NNI Routeing scenarios in SIP requests","NNI_RS",2,"Rel-12","C1","2014-06-13","2014-12-09",1,"CP-140288","CP-140613","Ericsson","Jan.Holm@ericsson.com","CP#65 completion 09/14=>12/14. Exception in CP-140613. Dec.14: 95->100",24.228999999999999,64,33,null,null,"2014-04-07","2014-12-04"]
[5408,640207,"   CT3 part of Indication of NNI Routeing scenarios in SIP requests","NNI_RS",2,"Rel-12","C3","2014-06-13","2014-09-11",1,"CP-140288","-","Ericsson","Jan.Holm@ericsson.com","CP#65 completed","29.079; 29.165",64,33,null,null,"2014-04-07","2014-07-31"]
[5414,650004,"Network Initiated USSD Simulation Services in IMS","USSI-NET",1,"Rel-12","C1","2014-09-12","2014-12-09",1,"CP-140625","CP-140610","AT&T","Martin Dolly (md3135@att.com)","CP#65 exception in CP-140610. Dec.14: 75->100",24.39,65,33,null,null,"2014-07-28","2014-12-04"]
[5417,610016,"   Test part: Introduction of ER-GSM band for GSM-R","RT_ERGSM",2,"Rel-12","G3new","2013-09-02","2014-02-28",1,"GP-130889","-","Kapsch Carriercom, Sierra Wireless","thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com)","GP#61 completed","51.010; 51.021",59,31,null,null,"2013-09-04","2014-03-07"]
[5421,570202,"   CT part: Downlink Multi Carrier GERAN","DMCG",2,"Rel-12","C1","2012-09-10","2014-09-11",1,"GP-140190","-","Ericsson","paul.schliwa-bertling@ericsson.com","CP#65 completed",24.007999999999999,55,29,null,null,"2012-09-03","2014-07-28"]
[5422,570302,"   Test part: Downlink Multi Carrier GERAN","DMCG-MStest",2,"Rel-12","G3new","2012-09-10","2015-03-13",0.8,"GP-120930","-","ST-Ericsson","hakan.e.grunditz@stericsson.com","GP#63 completion 08/14=>11/14. Dec.14: 35->80%, CD:11/14->03/15","51.010-1; 51.010-2",55,29,null,null,"2012-09-03","2014-12-03"]
[5426,590233,"   MSRD for VAMOS - MS Conformance Test","MSRD_VAMOS-Test",2,"Rel-12","G3new","2013-03-06","2014-11-21",1,"GP-130849","GP-140579","Nokia Networks, Microsoft","Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft)","GP#63 completion 08/14=>11/14. Exception in GP-140579. Dec.14: 85->100","51.010-1; 51.010-2",57,30,null,null,"2013-03-04","2014-12-03"]
[5429,620214,"   GERAN2 part of New Training Sequence Codes (TSC) for GERAN","NewToN",2,"Rel-12","G2","2013-11-22","2014-11-19",0.8,"GP-131139","GP-140542","Ericsson","Mårten Sundberg","GP#63 completion 08/14=>11/14. Exception in GP-140542. ","44.018; 44.060",60,32,null,null,"2013-11-22","2014-05-30"]
[5433,570021,"Further enhancements to H(e)NB mobility - Part 3 (Stage 2/3)","EHNB_enh3",1,"Rel-12","R3,R2","2012-09-12","2013-12-06",1,"RP-130741","-","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","Triggered by FS_EHNB_enh (TR 37.803)","UTRA; LTE",57,29,null,null,"2012-09-03","2013-06-07"]
[5435,590019,"Support for BeiDou Navigation Satellite System (BDS) for UTRA and LTE","LCS_BDS",1,"Rel-12","R2,R3,R4,R5","2013-03-04","2015-06-15",1,"RP-130416","-","CATR","Ying Du (duying1@catr.cn)","BeiDou = Chinese Navigation Satellite System. Location Services (LCS) TS 22.071 Stage 1, TS 23.271 Stage 2","UTRA; LTE",59,30,null,null,"2013-02-26","2013-03-05"]
[5441,620011,"Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN","LCS_BDS_GERAN",1,"Rel-12","G2,G1,G3new","2013-11-22","2015-03-13",0.93,"GP-140211","-","ZTE","Wang Xinhui (wangxinhui@zte.com.cn)","GP#60 approved WID. Based on the same framework used in Rel-8 Support for Additional Navigation Satellite Systems (ANSS) for LCS UID_38001","GERAN",60,32,null,null,"2013-11-22","2014-03-01"]
[5444,630009,"   Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN3new","LCS_BDS_GERAN-GERAN3new",2,"Rel-12","G3new","2014-03-01","2015-03-13",0.8,"GP-140244",null,"CATR","Zhou DaiWei, China Academy of Telecommunication Research, zhoudaiwei@catr.cn","Dec.14: 25->80%, CD: 11/14->03/15","51010-1; 51.010-2; 51.010-7",61,32,null,null,"2014-03-01","2014-08-29"]
[5448,600219,"   Deleted - Perf. part: New Base Station specification structure","BSspec_struc-Perf",2,"Rel-12","R4","2013-06-20","2013-12-06",1,"RP-130851","RP-131514","Ericsson","johan.skold@ericsson.com","RP#62 stopped (at 0% completion)","25.113; 25.141; 25.142; 36.113; 36.141; 37.113; 37.141; 37.810; New 37.xyz (New RF test specification; New 37.xyw (ew EMC specification)",60,31,"RP-62","PCG-32","2013-06-17","2013-11-29"]
[5449,600021,"L-band for Supplemental Downlink in E-UTRA and UTRA","LTE_UTRA_SDL_BandL",1,"Rel-12","R4,R2,R3","2013-06-17","2015-12-15",1,"RP-140092","-","Orange","olfa.benhaddada@orange.com","ECC(12)052 CEPT decision to harmonize 1452-1492 MHz (L-band) for mobile communications Supplemental Downlink (SDL) => standardize L-band and corresponding E-UTRA and UTRA requirements for SDL operation in Region 1","UTRA; LTE",60,31,null,null,"2013-06-17","2013-12-07"]
[5452,670047,"   UE Conformance Test Aspects - L-band for Supplemental Downlink in E-UTRA and UTRA","LTE_UTRA_SDL_BandL-UEConTest",2,"Rel-12","R5","2015-03-16","2015-12-15",1,"RP-150835","RP-151163","Ericsson",null,"03/07/15: Compl:0%->85% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-150134->RP-150835 03/07/15: Stat Rep: ->RP-150830 29/09/15: Compl:85%->90% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150830->RP-151163¦1/1/16",null,67,34,null,null,"2015-04-01","2016-01-01"]
[5457,610015,"   GERAN aspects for LTE-HRPD inter-RAT SON, RAN Information Management (RIM) - Stage 3","LTE_HRPD_SON-RIM",2,"Rel-12","G2","2013-08-26","2013-08-30",1,"GP-130817","-","Alcatel-Lucent","marguerite.woch@alcatel-lucent.com","GP#59 WID approved & Completed",48.018000000000001,59,31,null,null,"2013-08-11","2013-10-01"]
[5460,620242,"   Perf. part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA","LTE_UTRA_IncMon-Perf",2,"Rel-12","R4","2013-12-15","2015-06-15",1,"RP-132061","RP-150596","Ericsson","christopher.callender@ericsson.com","¦CD:Fri 12/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141600->RP-141787 1st Apr 15: Compl:5%->40% 1st Apr 15: Stat Rep: RP-141787->RP-150063 03/07/15: Compl:40%->100% 03/07/15: Stat Rep: RP-150063->RP-150596","25.133; 36.133",62,32,null,null,"2013-12-07","2015-06-18"]
[5463,620148,"   Core part: WLAN/3GPP Radio Interworking","UTRA_LTE_WLAN_interw-Core",2,"Rel-12","R2","2013-12-06","2014-09-12",1,"RP-140981","RP-141310","Intel","sasha.sirotkin@intel.com","SP#65 completed","25.304; 25.306; 25.331; 36.304; 36.306; 36.331",62,32,null,null,"2013-12-09","2014-09-09"]
[{"$f":"A5466+1","v":5466},640106,"      CT1 part of CT aspects of WLAN/3GPP Radio Interworking (Stage 3)","UTRA_LTE_WLAN_interw-CT",3,"Rel-12","C1","2014-09-09","2014-12-09",1,"CP-140623","CP-140720","Alcatel-Lucent","jennifer.liu@alcatel-lucent.com","CP#65 completion 09/14=>12/14. Exception in CP-140720. 78%->95%. 12/12: 95->78%. 3/3/15: 100% cpltd.","24.008; 24.301; 24.302; 24.312",64,33,null,null,"2014-04-07","2015-03-03"]
[5471,530125,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 7","LTE_CA_B1_B7-Core",3,"Rel-12","R4","2011-09-19","2014-09-12",1,"RP-141487","RP-141084","Ericsson","christian.bergljung@ericsson.com ","RP#65 completed. Updated WID RP-132042=>RP-141487","36.101; 36.104; new generic 36.851",53,27,null,null,"2011-09-15","2014-09-20"]
[5475,530229,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25-Perf",3,"Rel-12","R4","2011-09-19","2013-06-14",1,"RP-130179","RP-130759","Sprint","George.Cummings@sprint.com","RP#60 completed","36.141; 36.307",53,27,null,null,"2011-09-15","2013-06-10"]
[5476,550010,"   Deleted -LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL","LTE_CA_B3_B5_2UL",2,"Rel-12","R4","2012-03-05","2013-03-01",1,"RP-120867","-","SK Telecom","Seungpyo Hong","Inter-band 2UL","LTE",55,28,"RP-59","PCG-30","2012-02-23","2013-07-29"]
[5479,670049,"   UE Conformance Test Aspects - Further Rel-12 configurations for LTE Advanced Carrier Aggregation with 2UL","LTE_CA_Rel12_2UL-UEConTest",2,"Rel-12","R5","2015-03-16","2016-12-15",1,"RP-160071",null,"Ericsson","NA","03/07/15: Compl:0%->29% 03/07/15: Stat Rep: ->RP-150834 29/09/15: Compl:29%->55% 29/09/15: Stat Rep: RP-150834->RP-151166 1/1/16: Compl:55%->70% 1/1/16: CD:Tue 15/12/15->Tue 15/03/16 1/1/16: WID: RP-1¦",null,67,34,null,null,"2015-04-01","2016-12-20"]
[5484,560115,"      Deleted - Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 1","LTE_CA_C_B1-Core",3,"Rel-12","R4","2012-06-18","2013-06-14",1,"RP-120826","RP-130549","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#60 stopped at 10% completion (rationale in RP-130670)","36.101; 36.104; 36.133; 36.141; 36.307; new 36.835",56,29,"RP-60","PCG-31","2012-06-13","2013-06-05"]
[5487,560116,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4","LTE_CA_NC_B4-Core",3,"Rel-12","R4","2012-06-18","2013-09-06",1,"RP-131135","RP-131039","T-Mobile USA","nelson.ueng@t-mobile.com","RP#61 completed. Updated WID RP-130842=>RP-131135","36.101; 36.104; 36.133; new 36.833-2-04",56,29,null,null,"2012-06-13","2013-08-28"]
[5490,560117,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4","LTE_CA_B2_B4-Core",3,"Rel-12","R4","2012-06-18","2013-09-06",1,"RP-130175","RP-131007","T-Mobile USA","nelson.ueng@t-mobile.com","RP#61 completed","36.101; 36.104; 36.133; new generic 36.851",56,29,null,null,"2012-06-13","2013-08-28"]
[5493,570112,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29","LTE_CA_B23_B29-Core",3,"Rel-12","R4","2012-09-12","2013-06-14",1,"RP-130170","RP-130535","DISH Network","mariam.sorond@dish.com, johny.kim@dish.com","RP#60 completed","36.101; 36.104; 36.133; new generic 36.851",57,29,null,null,"2012-09-03","2013-06-04"]
[5498,570014,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19","LTE_CA_B3_B19",2,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130198","-","NTT DOCOMO","Kei ANDO","Inter-band 1 UL","LTE",57,29,null,null,"2012-09-03","2012-09-07"]
[5499,570114,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19","LTE_CA_B3_B19-Core",3,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130198","RP-130525","NTT DOCOMO","Kei ANDO","RP#60 completed","36.101; 36.104; 36.133; new generic 36.851",57,29,null,null,"2012-09-03","2013-06-08"]
[5502,570115,"      Deleted - Core part:LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39","LTE_CA_B38_B39-Core",3,"Rel-12","R4","2012-09-11","2012-12-07",1,"RP-121178","RP-121624","China Mobile","Pan Qun (panqun@chinamobile.com)","RP#58 stopped at 10% completion following regulatory decisions (see instead new WI LTE_CA_B39_B41)","36.101; 36.104; 36.307; new generic 36.851",57,29,"RP-58","PCG-30","2012-09-03","2012-12-11"]
[5506,570216,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 3","LTE_CA_C_B3-Perf",3,"Rel-12","R4","2012-09-11","2013-09-06",1,"RP-131184","RP-131030","China Unicom","Fei CUI (cuifei1@chinaunicom.cn)","RP#61 completed","36.141; 36.307",57,29,null,null,"2012-09-03","2013-09-04"]
[5510,570026,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 28","LTE_CA_B3_B28",2,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130189","-","eAccess","FukumotoShiro@eaccess.net","Inter-band 1 UL","LTE",57,29,null,null,"2012-09-03","2012-09-07"]
[5515,580232,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26","LTE_CA_B1_B26-Perf",3,"Rel-12","R4","2012-12-07","2013-09-06",1,"RP-130668","RP-131006","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#61 completed","36.141; 36.307",58,30,null,null,"2012-12-10","2013-08-28"]
[5517,580133,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41","LTE_CA_B39_B41-Core",3,"Rel-12","R4","2012-12-10","2014-03-06",1,"RP-130292","RP-140428","China Mobile","Pan Qun (panqun@chinamobile.com)","RP#63 completed. Replaces the Stopped WI - LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39 (LTE_CA_B38_B39) UID_570015","36.101; 36.104; 36.307; new generic 36.851",58,30,null,null,"2012-12-10","2014-03-05"]
[5520,580134,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12","LTE_CA_B2_B12-Core",3,"Rel-12","R4","2012-12-10","2014-09-12",1,"RP-140474","RP-141084","US Cellular","sebastian.thalanany@uscellular.com ","RP#65 completed","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.851",58,30,null,null,"2012-12-10","2014-09-08"]
[5525,580036,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 27","LTE_CA_C_B27",2,"Rel-12","R4","2012-12-10","2014-06-13",1,"RP-131679","-","NII Holdings","bill.shvodian@nii.com","Intra-band contig. CA 2DL/1UL","LTE",58,30,null,null,"2012-12-10","2013-12-19"]
[5526,580136,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 27","LTE_CA_C_B27-Core",3,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-131679","RP-131567","NII Holdings","bill.shvodian@nii.com","RP#62 completed","36.101; 36.104; new 36.833-1-27",58,30,null,null,"2012-12-10","2013-12-06"]
[5529,590122,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 13","LTE_CA_B2_B13-Core",3,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130196","RP-130523","Ericsson","christian.bergljung@ericsson.com ","RP#60 completed","36.101; 36.104; 36.133; new generic 36.851",59,30,null,null,"2013-02-26","2013-02-26"]
[5533,590224,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21","LTE_CA_B19_B21-Perf",3,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130197","RP-130534","NTT DOCOMO","Kei ANDO","RP#60 completed","36.141; 36.307",59,30,null,null,"2013-02-26","2013-06-08"]
[5537,590029,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A1","LTE_CA_2UL-A1",2,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-140475","-","Huawei","Liu Ye (leo.liuye@huawei.com)","Inter-band CA 2UL","LTE",59,30,null,null,"2013-02-26","2014-09-09"]
[5542,590228,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2","LTE_CA_2UL-A2-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-130327","RP-141732","Qualcomm","Gene Fong (gfong@qti.qualcomm.com)","¦Stat Rep: RP-141084->RP-141732","36.141; 36.307",59,30,null,null,"2013-02-26","2015-01-12"]
[5544,590123,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A3","LTE_CA_2UL-A3-Core",3,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-140853","RP-141732","Ericsson","christian.bergljung@ericsson.com ","¦Stat Rep: RP-141084->RP-141732","36.101; 36.104; 36.133; New generic 36.860",59,30,null,null,"2013-02-26","2015-01-12"]
[5548,590231,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4","LTE_CA_2UL-A4-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-141967","RP-141732","Nokia","petri.j.vasenkari@nokia.com","¦WID: RP-142043->RP-141967¦Stat Rep: RP-141084->RP-141732","36.141; 36.307",59,30,null,null,"2013-02-26","2015-01-12"]
[5551,590226,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A5","LTE_CA_2UL-A5-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-141195","RP-141732","NTT DOCOMO","kei.andou.ye@nttdocomo.com","¦Stat Rep: RP-141084->RP-141732","36.141; 36.307",59,30,null,null,"2013-02-26","2015-01-12"]
[5553,590127,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 39","LTE_CA_C_B39-Core",3,"Rel-12","R4","2013-03-04","2014-03-06",1,"RP-131171","RP-140428","China Mobile","Li Nan (linan@chinamobile.com)","RP#63 completed","36.101; 36.104; 36.133; New 36.833-1-39 [instead of 36.845]",59,30,null,null,"2013-02-26","2014-03-05"]
[5556,600122,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation: framework requirements for 2UL","LTE_CA_NC_2UL-Core",3,"Rel-12","R4","2013-06-18","2014-12-15",1,"RP-141962","RP-141732","Nokia","petri.j.vasenkari@nokia.com","¦WID: RP-142043->RP-141962¦Stat Rep: RP-141084->RP-141732","36.101; 36.104; 36.133; 36.306; 36.331; New 36.833-4",60,31,null,null,"2013-06-17","2015-01-12"]
[5560,600024,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL","LTE_CA_NC_B4_2UL",2,"Rel-12","R4","2013-06-19","2014-12-15",1,"RP-131136","-","T-Mobile USA","nelson.ueng@t-mobile.com","Intra-band non-contig. CA 2DL","LTE",60,31,null,null,"2013-06-17","2014-09-09"]
[5564,600125,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 23","LTE_CA_C_B23-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131265","RP-131565","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","RP#62 completed","36.101; 36.104; 36.133; new 36.833-1-23 [instead of 36.864]",60,31,null,null,"2013-06-17","2013-12-02"]
[5569,600028,"   LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25","LTE_CA_B12_B25",2,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131159","-","US Cellular","sebastian.thalanany@uscellular.com ","Inter-band 1UL/2DL","LTE",60,31,null,null,"2013-06-05","2013-06-17"]
[5572,600029,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set","LTE_CA_B1_B18_BWset",2,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130669","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band 1UL/2DL","LTE",60,31,null,null,"2013-06-05","2013-06-17"]
[5575,600030,"   LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5","LTE_CA_B2_B5",2,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130675","-","AT&T","marc.grant@att.com","Inter-band 2DL","LTE",60,31,null,null,"2013-06-05","2013-06-17"]
[5578,600031,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 30","LTE_CA_B2_B5_B30",2,"Rel-12","R4","2013-06-18","2014-09-12",1,"RP-131696","-","AT&T","marc.grant@att.com","Inter-band 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-08"]
[5580,600231,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 30","LTE_CA_B2_B5_B30-Perf",3,"Rel-12","R4","2013-06-18","2014-09-12",1,"RP-131696","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101; 36.104; 36.133; 36.141; 36.307",60,31,null,null,"2013-06-17","2014-09-08"]
[5583,600232,"      Deleted - Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 17 and Band 30","LTE_CA_B2_B17_B30-Perf",3,"Rel-12","R4","2013-06-19","2013-12-06",1,"RP-131130","RP-131591","AT&T","marc.grant@att.com","RP#62 stopped (25% complete) following RP-131652 discussion","36.101; 36.104; 36.133; 36.141; 36.307",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[5587,600034,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 30","LTE_CA_B4_B5_B30",2,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141213","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-08"]
[5591,600135,"      Deleted - Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 17 and Band 30","LTE_CA_B4_B17_B30-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131133","RP-131598","AT&T","marc.grant@att.com","RP#62 stopped (25% complete) following RP-131653 discussion","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.853 (3 Band CA with 1UL)",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[{"$f":"A5594+1","v":5594},600136,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 29 and Band 30","LTE_CA_B4_B29_B30-Core",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141215","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131699=>RP- 141215","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-08"]
[5596,600037,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 13","LTE_CA_B2_B4_B13",2,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141434","-","Verizon","zheng.zhao@verizonwireless.com","Inter-band CA 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-21"]
[5602,600039,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 13","LTE_CA_B4_B4_B13",2,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141433","-","Verizon","zheng.zhao@verizonwireless.com","Inter-band CA 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-21"]
[5605,610017,"   LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28","LTE_CA_B7_B28",2,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131307","-","Huawei","Liehai Liu (liuliehai@huawei.com)","Inter-band 1UL/2DL","LTE",61,31,null,null,"2013-09-07","2013-12-02"]
[5607,610217,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28","LTE_CA_B7_B28-Perf",3,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131307","RP-131546","Huawei","Liehai Liu (liuliehai@huawei.com)","RP#62 completed",36.140999999999998,61,31,null,null,"2013-09-07","2013-12-02"]
[5610,610218,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25","LTE_CA_B5_B25-Perf",3,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131343","RP-131705","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#62 completed","36.141; 36.307",61,31,null,null,"2013-09-07","2013-12-02"]
[5614,610020,"   LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 11","LTE_CA_B8_B11",2,"Rel-12","R4","2013-09-09","2014-09-12",1,"RP-131355","-","SoftBank Mobile","kenichi.kihara@g.softbank.co.jp","Inter-band CA 2DL","LTE",61,31,null,null,"2013-09-07","2014-09-08"]
[5618,610121,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7-Core",3,"Rel-12","R4","2013-09-09","2013-12-02",1,"RP-131365","RP-131541","LG Uplus","Yeonsang KOO (yskoo@lguplus.co.kr)","RP#62 completed","36.101; 36.104; 36.133; new generic 36.851",61,31,null,null,"2013-09-07","2013-12-02"]
[5621,610122,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL","LTE_CA_C_B41_3DL-Core",3,"Rel-12","R4","2013-09-09","2014-09-12",1,"RP-140100","RP-141084","Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","RP#65 completed","36.101; 36.104; 36.133; 36.307; New 36.833-5-41",61,31,null,null,"2013-09-07","2014-09-08"]
[5623,610023,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2","LTE_CA_NC_B2",2,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-131366","-","Ericsson","imadur.rahman@ericsson.com","Intra-band non-contig. CA 2DL","LTE",61,31,null,null,"2013-09-07","2013-09-07"]
[5629,620019,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28","LTE_CA_B1_B28",2,"Rel-12","R4","2013-12-09","2014-12-15",1,"RP-132028","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band CA 2DL","LTE",62,32,null,null,"2013-12-07","2014-09-09"]
[5632,620020,"   LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 - Additional bandwidth combination set","LTE_CA_B2_B4_BWset",2,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-131656","-","T-Mobile USA","nelson.ueng@t-mobile.com","Inter-band 2DL","LTE",62,32,null,null,"2013-12-07","2014-03-04"]
[5636,620121,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27","LTE_CA_B4_B27-Core",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140142","RP-140569","NII Holdings","bill.shvodian@nii.com","RP#64 completed","36.101; 36.104; 36.133; new generic 36.851",62,32,null,null,"2013-12-07","2014-06-20"]
[5637,620221,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27","LTE_CA_B4_B27-Perf",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140142","RP-140569","NII Holdings","bill.shvodian@nii.com","RP#64 completed","36.141; 36.307",62,32,null,null,"2013-12-07","2014-06-20"]
[5641,620072,"   LTE Advanced inter-band Carrier Aggregation in Band 8 and Band 20 - Additional channel bandwidth","LTE_CA_B8_B20_BW",2,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-132118","RP-140428","Vodafone","luis.anaya@vodafone.com","Inter-band 2DL","LTE",62,32,null,null,"2013-12-09","2014-03-05"]
[5645,620124,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8","LTE_CA_B1_B3_B8-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141654","RP-141084","KT","Ilwhan Kim (ilwhan.kim@kt.com)","RP#65 completed. Updated WID RP-131753=>RP-141654","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-22"]
[5648,620125,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 5 and Band 7","LTE_CA_B1_B5_B7-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141462","RP-141084","LG Uplus","Yeonsang KOO (yskoo@lguplus.co.kr)","RP#65 completed. Updated WID RP-140209=>RP-141462","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-22"]
[5650,620026,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 5","LTE_CA_B2_B4_B5",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140186","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5656,620028,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 12","LTE_CA_B2_B5_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140190","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5659,620029,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 12","LTE_CA_B2_B12_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-131654","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5663,620130,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30","LTE_CA_B2_B12_B30-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141211","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131652=>RP-141211.","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[5664,620230,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30","LTE_CA_B2_B12_B30-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141211","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101; 36.104; 36.133; 36.141; 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[5668,620033,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 5 and Band 12","LTE_CA_B4_B5_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140191","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5672,620134,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 12","LTE_CA_B4_B12_B12-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-131655","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[5675,620135,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30","LTE_CA_B4_B12_B30-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141214","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131653=>RP-141214","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[5679,620237,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 42","LTE_CA_C_B42-Perf",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140728","RP-140569","CATT","Yuexia Song (songyuexia@catt.cn)","RP#64 completed. TR 36.833-1-42v100 for 1-step Approval. Updated WID RP-132029=>RP-140728","36.141; 36.307",62,32,null,null,"2013-12-07","2014-06-12"]
[5681,620136,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations","LTE_CA_C_B7_BW-Core",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-131810","RP-140569","Orange","Olfa BEN HADDADA","RP#64 completed","36.101; 36.307",62,32,null,null,"2013-12-07","2014-06-20"]
[5684,620138,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL","LTE_CA_NC_B41_3DL-Core",3,"Rel-12","R4","2013-12-09","2014-09-11",1,"RP-140101","RP-141084","Sprint, Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","RP#65 completed","36.101; 36.104; 36.133; 36.307; new 36.833-6-xy",62,32,null,null,"2013-12-07","2014-09-08"]
[5687,620139,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42","LTE_CA_NC_B42-Core",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140671","RP-140569","Huawei","Liu Liehai (liuliehai@huawei.com)","RP#64 completed. Updated WID RP-140404=>RP-140671. TR 36.833-2-42v100 for 1-step Approval","36.101; 36.104; 36.133; new 36.833-2-42",62,32,null,null,"2013-12-07","2014-06-12"]
[5690,620150,"      Core part:LTE Advanced 3 Band Carrier Aggregation(3DL/1UL) for Band 1, Band 3 and Band 5","LTE_CA_B1_B3_B5-Core",3,"Rel-12","R4","2013-12-06","2014-09-12",1,"RP-141454","RP-141084","SK Telecom","haesung.park@sk.com","RP#65 completed. Updated WID RP-132121=>RP-141454","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-09","2014-09-21"]
[5695,620052,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 7 and Band 20","LTE_CA_B1_B7_B20",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141223","-","Vodafone","luis.anaya@vodafone.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-09","2014-09-21"]
[5699,620153,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20","LTE_CA_B7_B8_B20-Core",3,"Rel-12","R4","2013-12-09","2014-12-15",1,"RP-132080","RP-141732","Vodafone","luis.anaya@vodafone.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:85%->100%¦Stat Rep: RP-141084->RP-141732","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL); 36.851 (2 Band CA with 1UL)",62,32,null,null,"2013-12-09","2015-01-12"]
[5702,630122,"      Core part: Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29","LTE_DL_FDD700_B29_BWset-Core",3,"Rel-12","R4","2014-03-03","2014-03-06",1,"RP-140084","RP-140428","AT&T","marc.grant@att.com","RP#63 approved WI (no Perf. Part) & completed. Rel-10 and Rel-11 versions of 36.307 affected","36.101; 36.307",63,32,null,null,"2014-03-10","2014-03-12"]
[5706,630124,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 20","LTE_CA_B7_B20_BWset-Core",3,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140448","RP-140569","NSN","iwajlo.angelow@nsn.com","RP#64 completed","36.101; 36.851",63,32,null,null,"2014-03-10","2014-06-20"]
[5708,630125,"      Core part: Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation to support 3DL fallback","LTE_CA_3DL_FB_BW-Core",3,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140454","RP-140569","Qualcomm","Fong Gene (gfong@qti.qualcomm.com)","RP#64 completed, Additional BW combinations added for 6 Wis: 3 open Rel-12 Wis (B1_B5_B7, B2_B29_B30, B4_B29_B30) and 3 completed Rel-11 Wis (B3_B5, B4_B5, B4_B12)","36.101; 36.307",63,32,null,null,"2014-03-10","2014-06-20"]
[5711,630226,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7-Perf",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141196","RP-141084","Nokia Networks","iwajlo.angelow@nsn.com","RP#65 completed. Updated WID RP-140095=>RP-141196. Mar15: acronym reverted from LTE_CA_B3_B7_B7-Perf_","36.141; 36.307",63,32,null,null,"2014-03-10","2015-03-10"]
[5714,630227,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21","LTE_CA_B1_B19_B21-Perf",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141193","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed. Updated WID RP-140106=>RP-141193","36.141; 36.307",63,32,null,null,"2014-03-10","2014-09-21"]
[5717,630228,"      Perf. part: LTE-Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 7","LTE_CA_B3_B3_B7-Perf",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141126","RP-141084","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#65 completed. Updated RP-140390=>RP-141126","36.141; 36.307",63,32,null,null,"2014-03-10","2014-09-08"]
[{"$f":"A5722+1","v":5722},630135,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset-Core",3,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-141235","RP-141084","T-Mobile USA","nelson.ueng@t-mobile.com","RP#65 completed. Updated WID RP-140987=>RP-141235 (removed Perf. Part)","36.101; generic 36.850",63,32,null,null,"2014-03-10","2014-09-21"]
[5725,630136,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42","LTE_CA_B41_B42-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-140450","RP-141084","Huawei","leo.liuye@huawei.com","RP#65 completed","36.101; 36.104; 36.851",63,32,null,null,"2014-03-10","2014-09-08"]
[5730,630038,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4, and Band 4","LTE_CA_B2_B4_B4",2,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141236","-","T-Mobile USA","nelson.ueng@T-Mobile.com","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-21"]
[5733,630045,"   Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25_BWset",2,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-140452","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Intra-band non-contig. CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-08"]
[5735,630245,"      Perf. part: Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25_BWset-Perf",3,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-140452","RP-141084","Huawei","Liu Liehai (liuliehai@huawei.com)","RP#65 completed",36.307000000000002,63,32,null,null,"2014-03-10","2014-09-08"]
[5738,640021,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5","LTE_CA_B2_B5_BWset",2,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140642","-","AT&T","marc.grant@att.com","2DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5741,640027,"   E-UTRA UE demodulation/Channel State Information (CSI) performance requirements for multiple Carrier Aggregation configurations","LTE_CA_Mult",2,"Rel-12","R4","2014-06-16","2015-03-13",1,"RP-141304","-","China Mobile","Zhang Xiaoran (zhangxiaoran@chinamobile.com)","LTE","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5744,640128,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19","LTE_CA_B1_B3_B19-Core",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141004","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed","36.101; 36.104; 36.133; generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2014-09-08"]
[5749,640030,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42","LTE_CA_B3_B42_B42",2,"Rel-12","R4","2014-06-16","2015-03-13",1,"RP-141005","-","NTT DOCOMO","ANDO Kei (kei.andou.ye@nttdocomo.com)","3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5752,640031,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42","LTE_CA_B1_B42_B42",2,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141006","-","NTT DOCOMO","ANDO Kei (kei.andou.ye@nttdocomo.com)","Inter-band CA 3DL","LTE",64,33,null,null,"2014-06-16","2014-09-08"]
[5757,650054,"      Perf. part: Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL_BW-Perf",3,"Rel-12","R4","2014-09-08","2014-09-12",1,"RP-141127","RP-141084","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#65 updated WID RP-140950=>RP-141127 (added Perf. Part). Completed.",36.307000000000002,65,33,null,null,"2014-09-21","2014-10-05"]
[5760,650210,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 18 and Band 28","LTE_CA_B18_B28-Perf",3,"Rel-12","R4","2014-09-10","2014-09-12",1,"RP-141611","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","-","36.141; 36.307",65,33,null,null,"2014-03-10","2014-09-10"]
[5763,630234,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13","LTE_CA_B5_B13-Perf",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140169","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.133; 36.141; 36.307",63,32,null,null,"2014-03-10","2015-01-12"]
[5766,630239,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5","LTE_CA_B2_B2_B5-Perf",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140165","RP-141732","Intel","peiling.zhang@intel.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.133; 36.141; 36.307",63,32,null,null,"2014-03-10","2015-01-12"]
[5768,630140,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5","LTE_CA_B4_B4_B5-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140166","RP-141732","Intel","peiling.zhang@intel.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:90%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.104; 36.133; generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[5771,630141,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13","LTE_CA_B2_B5_B13-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140167","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:50%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.104; 36.133; generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[5775,630242,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13","LTE_CA_B4_B5_B13-Perf",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140168","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.133; 36.141; 36.307",63,32,null,null,"2014-03-10","2015-01-12"]
[5779,630044,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28","LTE_CA_B1_B18_B28",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-141610","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5784,640223,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140661","RP-141732","Rogers Wireless","pavlo.nebesny@rci.rogers.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.133; 36.141",64,33,null,null,"2014-06-16","2015-01-12"]
[5787,640224,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140662","RP-141732","Rogers Wireless","pavlo.nebesny@rci.rogers.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.133; 36.141",64,33,null,null,"2014-06-16","2015-01-12"]
[5790,640226,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41","LTE_CA_B39_B41_B41-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142301","RP-141732","China Mobile","PAN Qun (panqun@chinamobile.com)","¦WID: RP-140708->RP-142301¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.141; 36.307",64,33,null,null,"2014-06-16","2015-01-12"]
[5793,640233,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41","LTE_CA_B1_B41_B41-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142297","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","Compl:100%->0%¦WID: RP-142043->RP-142297¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.141; 36.307",64,33,null,null,"2014-06-16","2015-01-12"]
[5795,640134,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41","LTE_CA_B26_B41_B41-Core",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142298","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","¦WID: RP-142043->RP-142298¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.104; 36.133; generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2015-01-12"]
[5799,650246,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41","LTE_CA_B25_B41_B41-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-142018","RP-141732","Alcatel-Lucent","Ng, Man Hung (man-hung.ng@alcatel-lucent.com)","¦WID: RP-142043->RP-142018¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12",36.140999999999998,65,33,null,null,"2014-06-16","2015-01-12"]
[5802,650248,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 39 and Band 41","LTE_CA_B39_B39_B41-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-142302","RP-141732","China Mobile","PAN, Qun (panqun@chinamobile.com)","¦WID: RP-141288->RP-142302¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.141; 36.307",65,33,null,null,"2014-06-16","2015-01-12"]
[5806,650052,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29","LTE_CA_B2_B4_B29",2,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141668","-","Huawei","SHAN Huiping (shanhuiping@huawei.com)","Inter-band CA 3DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[5810,650011,"UE Conformance Test Aspects – Further Rel-12 configurations for LTE Advanced Carrier Aggregation with 3DL","LTE_CA_Rel12_3DL-UEConTest",1,"Rel-12","R5","2014-09-15","2016-03-15",1,"RP-151821","RP-151464","Microsoft","jussi.kuusisto@microsoft.com","¦Stat Rep: -->RP-141775 1st Apr 15: Compl:6%->12% 1st Apr 15: CD:Tue 15/09/15->Tue 15/12/15 1st Apr 15: WID: RP-142231->RP-150079 1st Apr 15: Stat Rep: RP-141775->RP-150078 03/07/15: Compl:12%->35% 03/07/15: WID: RP-150079->RP-150594 03/07/15: Stat Re","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-1; 36.523-2; 36.523-3; 37.571-1; 37.571-3; 37.571-5",65,33,null,null,"2014-09-09","2016-03-22"]
[5811,510033,"Deleted - Carrier based HetNet ICIC for LTE","LTE_CA_HetNet_ICIC",1,"Rel-12","R3,R1,R2","2011-03-18","2013-06-14",1,"RP-121198","-","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#60 stopped. RP#58 on hold til June 2013","LTE",51,26,"RP-60","PCG-31","2011-03-14","2013-06-12"]
[5817,570019,"Introduction of LTE 450 MHz band in Brazil","LTE450_Brazil",1,"Rel-12","R4,R5","2012-09-11","2013-12-06",1,"RP-121414","-","Huawei","Liehai Liu (liuliehai@huawei.com)","-","LTE",57,29,null,null,"2012-09-03","2012-09-07"]
[5818,570119,"   Core part: Introduction of LTE 450 MHz band in Brazil","LTE450_Brazil-Core",2,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-121414","RP-130567","Huawei","Liehai Liu (liuliehai@huawei.com)","RP#60 completed. TR 36.840 v100 for 1-step Approval","36.101; 36.104; 36.113; 36.124; 36.133; 37.104; 37.113; 36.307; new 36.840",57,29,null,null,"2012-09-03","2013-06-05"]
[5824,670045,"   UE Conformance Test Aspects - Further DL MIMO Enhancement for LTE-Advanced","LTE_eDL_MIMO_enh-UEConTest",2,"Rel-12","R5","2015-03-16","2016-03-15",1,"RP-150071","RP-151189","ZTE",null,"03/07/15: Compl:0%->10% 03/07/15: Stat Rep: ->RP-150606 29/09/15: Compl:10%->70% 29/09/15: Stat Rep: RP-150606->RP-1511891/1/16: Compl:70%->75%",null,67,34,null,null,"2015-04-01","2016-03-22"]
[5826,570125,"   Deleted - Core part: New Carrier Type for LTE","LTE_NCT-Core",2,"Rel-12","R1,R2,R4","2012-09-11","2013-09-06",1,"RP-122028","RP-130984","Ericsson","daniel.n.larsson@ericsson.com","RP#61 stopped at 20% completion","36.101; 36.104; 36.133; 36.211; 36.212; 36.213; 36.321; 36.331",57,29,"RP-61","PCG-31","2012-09-03","2013-09-10"]
[5829,580127,"   Core part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation","LTE_TDD_eIMTA-Core",2,"Rel-12","R1,R2,R3,R4","2012-12-07","2014-06-13",1,"RP-121772","RP-140724","CATT","Zukang Shen (shenzukang@catt.cn)","RP#64 completed","36.101; 36.104; 36.133; 36.211; 36.212; 36.213; 36.214; 36.300; 36.321; 36.331; 36.413; 36.423",58,30,null,null,"2012-09-03","2014-07-06"]
[5833,580129,"   Core part: HetNet Mobility enhancements for LTE","HetNet_eMOB_LTE-Core",2,"Rel-12","R2,R4","2012-04-13","2014-09-12",1,"RP-122007","RP-141413","Alcatel-Lucent","sudeep.palat@alcatel-lucent.com","SP#65 completed","36.133; 36.304; 36.331",58,30,null,null,"2012-12-10","2014-09-09"]
[5837,580231,"   Perf. part: 8 Rx Antennas for LTE UL","LTE_UL_8Rx-Perf",2,"Rel-12","R4","2012-12-10","2013-12-06",1,"RP-121709","RP-131523","China Telecom","Shan Yang (yangshan@ctbri.com.cn)","RP#62 completed","36.104; 36.141",58,30,null,null,"2012-09-03","2013-11-29"]
[5838,600013,"LTE TDD-FDD joint operation including Carrier Aggregation","LTE_CA_TDD_FDD",1,"Rel-12","R1,R2,R4","2013-04-12","2014-12-15",1,"RP-140465","-","Nokia","lars.e.lindh@nokia.com","-","LTE",60,31,null,null,"2013-06-17","2014-03-13"]
[5844,650012,"   Test part: LTE Coverage Enhancements","Cov_Enh_LTE-UEConTest",2,"Rel-12","R5","2014-09-15","2015-06-15",1,"RP-141150","RP-150631","China Telecom","YANG Shan (yangshan@ctbri.com.cn)","¦Stat Rep: -->RP-141834 03/07/15: Compl:5%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: RP-141834->RP-150631","36.508; 36.523-1; 36.523-2; 36.523-3",65,33,null,null,"2014-09-09","2015-06-18"]
[5845,610024,"Further MBMS operations support for E-UTRAN","MBMS_LTE_OS",1,"Rel-12","R2,R1,R3,R4","2013-09-15","2014-12-15",1,"RP-140282","-","Verizon","yeesin.chan@verizonwireless.com","Solutions for Minimization of Drive Tests (MDT), in order to reduce the need for manual drive testing for MBMS.","LTE",61,31,null,null,"2013-09-07","2014-09-09"]
[5851,631000,"   SA2 part of Dual connectivity for LTE","LTE_SC_enh_dualC-S2",2,"Rel-12","S2","2014-03-19","2014-09-17",1,"-","-","-","-","SP#64 Three CRs agreed in SP-140262 (23.251CR0099, 23.401CR2658&CR2707). Dec.14:99->100%","23.251; 23.401",63,32,null,null,"2014-06-19","2014-12-03"]
[5853,680070,"   UE Conformance Test Aspects - Dual connectivity for LTE","LTE_SC_enh_dualC-UEConTest",2,"Rel-12","R5","2015-06-15","2017-09-15",1,"RP-150840",null,"Ericsson",null,"tested Core part: LTE_SC_enh_dualC-Core 29/09/15: Compl:0%->3% 29/09/15: Stat Rep: -->RP-1511671/1/16: Compl:3%->15%1/1/16: CD:Tue 15/03/16->Wed 15/06/16¦ ;",null,68,35,null,null,"2015-07-03","2017-09-19"]
[5856,620241,"   Perf. part: E-UTRA Small cell enhancements - Physical layer aspects","LTE_SC_enh_L1-Perf",2,"Rel-12","R4","2013-12-15","2015-06-15",1,"RP-141459","RP-150690","Huawei","Elean FAN (fanxiaoan@huawei.com)","¦CD:Wed 18/03/15->Sun 15/03/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141632->RP-141899 1st Apr 15: Compl:40%->80% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141899->RP-150173 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-","36.101; 36.104; 36.133; 36.141",62,32,null,null,"2013-12-09","2015-06-18"]
[5860,630031,"Smart Congestion Mitigation in E-UTRAN","SCM_LTE",1,"Rel-12","R2,S1,C1","2014-03-05","2015-09-15",1,"RP-140434","-","LG Electronics","youngdae.lee@lge.com","follow-up of TR 36.848 FS_SCM_LTE","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[5864,670051,"   UE Conformance Test Aspects - Smart Congestion Mitigation in E-UTRAN","SCM_LTE-UEConTest",2,"Rel-12","R5","2015-03-16","2015-09-15",1,"RP-150797","RP-151445","NTT DOCOMO",null,"03/07/15: Compl:0%->60% 03/07/15: WID: RP-150202->RP-150797 03/07/15: Stat Rep: ->RP-150794 29/09/15: Compl:60%->100% 29/09/15: Stat Rep: RP-150794->RP-151445",null,67,34,null,null,"2015-04-01","2015-09-29"]
[5867,630046,"Network-Assisted Interference Cancellation and Suppression for LTE","LTE_NAICS",1,"Rel-12","R1,R2,R4,R3","2014-03-11","2017-03-15",1,"RP-141634","-","MediaTek","Craig.Burnet@mediatek.com","follow-up of TR 36.866 FS_LTE_NAICS","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5869,630246,"   Perf. part: Network-Assisted Interference Cancellation and Suppression for LTE","LTE_NAICS-Perf",2,"Rel-12","R4","2014-03-11","2015-09-15",1,"RP-151297","RP-151296","MediaTek","Craig.Burnet@mediatek.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->25%¦Stat Rep: RP-141621->RP-141866 1st Apr 15: Compl:25%->50% 1st Apr 15: Stat Rep: RP-141866->RP-150179 03/07/15: Compl:50%->85% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150179->RP-150862",36.100999999999999,63,32,null,null,"2014-03-10","2015-09-29"]
[5872,630147,"   Perf. part: Performance requirements of interference cancellation and suppression receiver for SU-MIMO","LTE_SUMIMO_RX-Perf",2,"Rel-12","R4","2014-03-06","2015-03-13",1,"RP-140520","RP-150229","Huawei","Qian Cheng (Q.Cheng@Huawei.com)","CD:Fri 13/03/15->Sun 15/03/15¦Compl:50%->80%¦Stat Rep: RP-141255->RP-141906 1st Apr 15: Compl:80%->100% 1st Apr 15: Stat Rep: RP-141906->RP-150229",36.100999999999999,63,32,null,null,"2014-03-10","2015-04-01"]
[5878,600117,"   Core part: HNB Positioning for UTRA","UTRA_HNB_Pos-Core",2,"Rel-12","R3","2013-06-18","2013-12-06",1,"RP-132037","RP-131974","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#62 closed at 85% completion. Not completed work on HNB positioning / No consensus (may be TEI12, if contribution and support). Updated WID RP-130868=>RP-132037 (HNB positiong was not addressed in this WI, however it was NOT remoded from the WID)","25.305; 25.467; new 25.470",60,31,null,null,"2013-06-17","2013-12-09"]
[5880,610125,"   Core part: Dedicated Channel (DCH) enhancements for UMTS","UTRA_DCHenh-Core",2,"Rel-12","R1,R2,R3,R4","2013-11-18","2014-09-12",1,"RP-140771","RP-141137","Qualcomm","arjunb@qti.qualcomm.com","RP#65 completed","25.101; 25.104; 25.133; 25.211; 25.212; 25.213; 25.214; 25.215; 25.306; 25.308; 25.321; 25.331; 25.423; 25.433",61,31,null,null,"2013-09-07","2014-09-09"]
[5883,610026,"UMTS Mobility enhancements for heterogeneous networks","UTRA_HetNet_mob",1,"Rel-12","R2,R3,R4","2013-07-23","2014-06-13",1,"RP-132039","-","Huawei","Xudong Yang (yangxudong@huawei.com)","Triggered by Rel-12 TR 25.800 Study on UMTS heterogeneous networks (FS_UTRA_hetnet) UID_570024. Stage 2/3","UTRA",61,31,null,null,"2013-09-07","2013-09-07"]
[5887,620154,"   Core part: Heterogeneous Networks enhancements","UTRA_HetNet_enh-Core",2,"Rel-12","R1","2013-12-06","2014-09-12",1,"RP-141701","RP-141702","Huawei","carmela.cozzo@huawei.com","RP#65 completed. Updated WID RP-140463=>RP-141701","25.101; 25.211; 25.212; 25.213; 25.214; 25.300; 25.302; 25.306; 25.308; 25.319; 25.331; 25.423; 25.433",62,32,null,null,"2013-12-09","2014-09-15"]
[5891,620255,"   Perf. part: Enhanced Broadcast of System Information","UTRA_SIBenh-Perf",2,"Rel-12","R4","2013-12-15","2014-12-15",1,"RP-140131","RP-142080","Ericsson","martin.van.der.zee@ericsson.com","¦Stat Rep: RP-141230->RP-142080","25.101; 25.104; 25.133; 25.141",62,32,null,null,"2013-12-09","2015-01-12"]
[5894,620249,"   Perf. part: Further Enhanced Uplink (EUL) enhancements","EDCH_enh-Perf",2,"Rel-12","R4","2013-12-15","2015-03-13",1,"RP-140127","RP-150062","Ericsson","mark.curran@ericsson.com","¦CD:Wed 18/03/15->Sun 15/03/15¦Stat Rep: RP-141684->RP-141860 1st Apr 15: Compl:75%->100% 1st Apr 15: Stat Rep: RP-141860->RP-150062","25.101; 25.104; 25.133; 25.141",62,32,null,null,"2013-12-09","2015-04-01"]
[5896,660032,"(IETF) (Small) Technical Enhancements and Improvements for Rel-12 (draft-ietf-insipid-session-id)","TEI12_IETF",1,"Rel-12","C1-IETF","2014-06-13","2014-12-09",1,"CP-140815",null,"Alcatel-Lucent",null,"Mar15: In WGLC¦21/3/17: 50%->100; 9/4/21: RFC 7989 added;","draft-ietf-insipid-session-id; RFC 7989",66,34,null,null,"2014-12-04","2021-04-09"]
[5899,470020,"Study on Alternatives to E.164 for Machine-Type Communications","FS_AMTC",1,"Rel-12","S1","2010-03-25","2012-03-07",1,"SP-100198","-","T-Mobile USA","gary.jones@T-Mobile.com","SP#55 completed. Determine an alternative to E.164 for identifying individual devices and route messages between those devices",22.988,47,24,null,null,"2010-03-23","2012-02-22"]
[5902,500035,"Study on Continuity of Data Sessions to Local Networks","FS_CSN",1,"Rel-12","S1","2010-12-16","2011-12-14",1,"SP-100885","-","NEC","joerg.swetina@neclab.eu","SP#54 completed. Linked to SA1 Rel-11 Feature UID_490030 SIPTO Service Continuity of IP Data Session (SIPTO_SC)",22.896000000000001,50,26,null,null,"2010-11-25","2011-11-29"]
[5905,540027,"Study on User Plane Congestion management","FS_UPCON",1,"Rel-12","S1","2011-12-14","2012-09-12",1,"SP-110819","-","KDDI","John Visser (jvisser@rogers.com)","SP#57 completed. Linked to SAPP (Service Awareness and Privacy Policies), FS_UMONC (Study on Usage Monitoring Control Enhancement), QoS_SSL (QoS Control Based on Subscriber Spending Limits)",22.805,54,28,null,null,"2011-11-29","2012-08-07"]
[5910,490234,"   SA2 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2)","FS_IMS_P2P_CDS",2,"Rel-12","S2","2010-09-23","2012-06-20",1,"SP-120622","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#56 completed. TR 23.844v100 for Information and Approval",23.844000000000001,49,25,null,null,"2010-09-15","2012-06-14"]
[{"$f":"A5914+1","v":5914},490236,"   Study on Core Network Overload solutions (Phase 2)","FS_CNO",2,"Rel-12","S2","2010-09-23","2013-12-11",1,"SP-120490","-","Huawei","Mirko.Schramm@huawei.com","SP#62 completed",23.843,49,25,null,null,"2010-08-31","2013-11-28"]
[5918,560038,"Study on Application Based Charging","FS_ABC",1,"Rel-12","S2","2012-06-18","2013-03-06",1,"SP-120271","-","Allot","Alla Goldner (agoldner@allot.com)","SP#59 completed. Linked to Rel-11 Feature UID_500032 Service Awareness and Privacy Policies (SAPP)",23.8,56,29,null,null,"2012-06-04","2013-02-27"]
[5921,410243,"   SA2 part of Study on Multi Access PDN connectivity and IP flow Mobility","FS_MAPIM",2,"Rel-12","S2","2008-09-18","2012-12-12",1,"SP-110452","-","Qualcomm","Gerardo Giaretta (gerardog@qualcomm.com)","SP#43 TR 23.861v100 for Information. SP#56 Rel-9 TR 23.861v130 renamed & progressed under new Study FS_NBIFOM. SP#58 completed the FS_MAPIM part of TR 23.861 (TR continued under FS_NBIFOM).",23.861000000000001,41,21,null,null,"2008-09-15","2013-01-16"]
[5923,480043,"Study on Extended IMS Media Plane Security features","FS_eMEDIASEC",1,"Rel-12","S3","2010-06-10","2013-03-06",1,"SP-100256","-","Vodafone","Aguibou.Barry@vodafone.com","SP#59 completed. Continuation of Rel-9 Feature UID_430036 IMS Media Plane Security (MEDIASEC). Study solutions and extensions to features and functionality described in TR 33.828 and TS 33.328",33.829000000000001,48,25,null,null,"2010-05-05","2013-02-19"]
[5926,570035,"Study on Security Assurance Methodology for 3GPP Network Elements","FS_SECAM",1,"Rel-12","S3","2012-09-13","2014-06-18",1,"SP-120654","-","Orange","loic.habermacher@orange.com","SP#64 completed. Spin-off Rel-13 Feature SCAS. Study methodologies for specifying product security assurance and hardening requirements on 3GPP network elements (with associated test cases when feasible)",33.805,57,29,null,null,"2012-08-31","2014-05-21"]
[5929,470050,"Study on version handling","FS_OAM_VH",1,"Rel-12","S5","2010-03-25","2012-12-12",1,"SP-100082","-","Ericsson","thomas.tovinger@ericsson.com","SP#58 completed",32.83,47,24,null,null,"2010-02-12","2012-11-21"]
[5932,560032,"Study on Enhanced Network Management (NM) centralized Coverage and Capacity Optimization","FS_SON_NM_CCO",1,"Rel-12","S5","2011-09-21","2014-09-17",1,"SP-140028","-","Ericsson","robert.petersen@ericsson.com","SP#65 completed. TR 32.836v200 for Approval. SP#63 split of Rel-12 SP-130045 WID (Enhanced NM Centralized Coverage and Capacity Optimization) into a Rel-12 Study (SP-140028) and a Rel-13 Normative WID (SP-140060)",32.835999999999999,56,29,null,null,"2012-04-18","2014-08-25"]
[5937,590011,"Study on XML based access of AF to the PCRF","FS_XML_AF_PCRF",1,"Rel-12","C3","2013-03-01","2013-12-04",1,"CP-130167","-","Alcatel-Lucent","horst.brinkman@alcatel-lucent.com","CP#64 completed. Investigate introducing an XML-based protocol (e.g. SOAP, Restful HTTP, etc.) between AF and PCRF for non-IMS applications",29.817,59,30,null,null,"2013-02-16","2014-06-19"]
[5941,460001,"Study on GERAN improvements for Machine-Type Communications","FS_NIMTC_GERAN",1,"Rel-12","G1,G2","2010-05-24","2012-11-23",1,"GP-092418","-","Ericsson","paul.schliwa-bertling@ericsson.com","GP#56 completed. GP#44 approved WID",43.868000000000002,44,24,null,null,"2009-11-20","2012-11-23"]
[5945,530052,"Study on Provision of low-cost MTC UEs based on LTE","FS_LC_MTC_LTE",1,"Rel-12","R1,R2,R4","2011-09-19","2013-06-14",1,"RP-121441","RP-130583","Vodafone","prakash.bhat@vodafone.com","RP#60 completed","LTE 36.888",53,27,null,null,"2011-09-19","2013-06-07"]
[5948,580041,"Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects","FS_LTE_SC_enh_L1",1,"Rel-12","R1,R2,R4","2012-09-11","2013-09-06",1,"RP-122032","RP-131618","Huawei","Elean Fan (fanxiaoan@huawei.com)","RP#62 completed. RP#61 TR 36.872v100 for 1-step approval. Triggered by Rel-12 TR 36.932 Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN UID_570023","LTE 36.872",58,30,null,null,"2012-12-10","2013-12-03"]
[5949,580044,"Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Higher-layer aspects","FS_LTE_SC_enh_hilayer",1,"Rel-12","R2,R3","2012-12-10","2013-12-06",1,"RP-122033","RP-131619","NTT DOCOMO","Hideaki Takahashi (h-takahashi@nttdocomo.co.jp)","RP#62 completed. Triggered by Rel-12 TR 36.932 Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN UID_570023","LTE 36.842",58,30,null,null,"2012-12-10","2013-12-03"]
[5954,590017,"Study on Cell-specific Reference Signals (CRS) Interference Mitigation for homogenous deployments for LTE","FS_LTE_CRSIC",1,"Rel-12","R4","2013-03-04","2013-12-06",1,"RP-131840","RP-131623","Ericsson","shaohua.li@ericsson.com","RP#62 completed. Updated WID RP-130393=>RP-131840","LTE 36.863",59,30,null,null,"2013-02-26","2013-12-19"]
[5956,600015,"Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul ","FS_COMP_LTE_nibackhaul",1,"Rel-12","R1","2013-06-18","2013-12-06",1,"RP-130847","RP-131626","Samsung","Hyojin Lee (hyojin257.lee@samsung.com)","RP#62 completed. Extension of Rel-11 CoMP Operation for LTE – Downlink UID_530332)","LTE 36.874",60,31,null,null,"2013-06-17","2013-12-03"]
[5959,620044,"Study on RAN aspects of RAN Sharing Enhancements for LTE","FS_RSE-RAN_LTE",1,"Rel-12","R3","2013-12-06","2014-06-13",1,"RP-132116","RP-140746","NEC","Siva.Vakeesar@emea.nec.com","RP#64 completed. TR 36.856v100 for 1-step approval. Triggered by SA1 Re-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) and Rel-13 Feature RSE (TS 22.101 Stage 1)","LTE 36.856",62,32,null,null,"2013-11-27","2014-06-12"]
[5964,580047,"Study on RAN Enhancements for UMTS/HSPA and LTE Interworking","FS_HSPA_LTE_interworking",1,"Rel-12","R3","2012-12-10","2013-12-06",1,"RP-122036","RP-131612","China Unicom","Meng Zhang (zhangmeng68@chinaunicom.cn)","RP#62 completed. TR 37.852v100 for Information & Approval","UTRA; LTE 37.852",58,30,null,null,"2012-12-10","2013-12-03"]
[5968,590032,"Study on RAN aspects of Machine Type and other mobile data applications Communications enhancements","FS_MTCe_RAN",1,"Rel-12","R2","2013-03-01","2013-09-06",1,"RP-130396","RP-131081","ZTE","sergio.parolari@zteitaly.com","RP#61 completed","UTRA; LTE 37.869",59,30,null,null,"2013-02-26","2013-08-30"]
[5972,580040,"Study on Dedicated Channel (DCH) enhancements for UMTS","FS_UTRA_DCHenh",1,"Rel-12","R1","2012-12-10","2013-09-06",1,"RP-130216","RP-131073","Qualcomm","Arjun Bharadwaj (arjunb@qti.qualcomm.com)","RP#61 completed","UTRA 25.702",58,30,null,null,"2012-12-10","2013-06-07"]
[5975,610027,"Study on Enhanced Broadcast of System Information","FS_UTRA_SIBenh",1,"Rel-12","R2,R1","2013-09-09","2013-12-06",1,"RP-131386","RP-131610","Ericsson","martin.van.der.zee@ericsson.com","RP#62 completed. TR 25.704v100 for Information & Approval. Study need to add capacity to present SI Broadcast mechanism unchanged since R99","UTRA 25.704",61,31,null,null,"2013-09-07","2013-12-03"]
[5976,0,"--- RELEASE 11 ---","-",1,"Rel-11","SP,CP,GP,RP","2013-06-02","2014-09-16",1,"-","-","-","-","-","-","-","-",null,null,"2006-05-31","2014-02-18"]
[5981,530104,"      CT1 part of Stage 3 for Advanced IP Interconnection of Services","IPXS",3,"Rel-11","C1","2011-09-16","2012-09-12",1,"CP-110646","-","Ericsson","christer.holmberg@ericsson.com","CP#58 completed",24.228999999999999,53,27,null,null,"2011-08-29","2012-11-19"]
[5984,480130,"   Stage 1 for SIMTC","SIMTC",2,"Rel-11","S1","2010-06-10","2011-09-21",1,"SP-120848","-","KPN","toon.norp@tno.nl","SP#53 completed. SP#57 added MTC definitions in 21.905","22.368; 21.905 (MTC definitions)",48,25,null,null,"2010-05-28","2012-11-12"]
[5987,520121,"      Deleted - MTC Feature Control (described in TS 22.368, clause 7.1.1 and 23.888, clause 5.7)","SIMTC-Reach",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","-",52,27,"SP-54","PCG-28","2011-05-26","2012-11-12"]
[5990,520421,"      Identifiers – especially removal of MSISDN dependencies in the architecture","SIMTC-Reach",3,"Rel-11","S2","2011-06-09","2012-06-20",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#56 completed","New 23.682",52,27,null,null,"2011-05-26","2012-11-12"]
[5995,530206,"      CT3 part of Stage 3 BB1: Reachability Aspects of SIMTC","SIMTC-ReachCSPS",3,"Rel-11","C3","2011-09-19","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","22/01: acronym modified","29.061; New 29.368",53,27,null,null,"2011-08-29","2015-01-22"]
[5998,530005,"   Stage 2/3 for CS aspects for SIMTC ","SIMTC-CS",2,"Rel-11","C4,C1,C6","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 completed. Updated WID CP-120418=>CP-120617","Stage 2/3",53,27,null,null,"2011-08-29","2012-08-13"]
[5999,530105,"      Deleted - Stage 2 CS aspects for SIMTC ","SIMTC-CS",3,"Rel-11","C4","2011-09-16","2012-09-06",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 stopped",23.012,53,27,"CP-57","PCG-29","2011-08-29","2012-08-13"]
[6003,560002,"   Stage 2/3 for SMS in MME architecture option and related PS-only service subscription","SIMTC-PS_Only",2,"Rel-11","C1,C4","2012-06-15","2012-12-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#58 completed","Stage 2/3",56,29,null,null,"2012-04-23","2012-11-17"]
[6008,530209,"      Stage 3 (CS+PS) Extended Access Barring for UTRAN and E-UTRAN","SIMTC-RAN_OC",3,"Rel-11","C1,C6","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 completed. Updated WID CP-120418=>CP-120617","Stage 3",53,27,null,null,"2011-08-29","2012-08-24"]
[6011,610014,"   Test part: System Improvements for Machine-Type Communications","SIMTC-UEConTest",2,"Rel-11","R5","2013-09-09","2014-03-06",1,"RP-140077","RP-140075","Ericsson","calle.hagenfeldt@ericsson.com","RP#63 completed. Updated WID RP-131341=>RP-140077 (added affected TS 36.508). Testing for core part: SIMTC-Reach, SIMTC-CS, SIMTC-PS_Only, SIMTC-RAN_OC","34.123-1; 34.123-2; 34.123-3; 36.508; 36.523-1; 36.523-2; 36.523-3",61,31,null,null,"2013-09-03","2014-03-03"]
[6014,520122,"      Deleted - Effectively maintain connectivity for a large number of MTC Devices (TS 22.368, 7.1.1)","SIMTC-Sig",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[6017,530207,"         Deleted - CT1 part of Stage 3 Signalling Optimizations of SIMTC","SIMTC-Sig",4,"Rel-11","C1","2011-09-16","2011-12-09",1,"CP-110756","-","Ericsson","mikael.wass@ericsson.com","-","23.122; 24.008; 24.301; 24.368",53,27,"CP-55","PCG-28","2011-08-29","2011-11-28"]
[6022,520323,"      Deleted - MTC Monitoring (TS 22.368, 7.2.8)","SIMTC-CN_Pow",3,"Rel-11","S2","2011-06-08","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[6025,530208,"         Deleted - CT6 part of Stage 3 CN-based requirements and Power Considerations of SIMTC","SIMTC-CN_Pow",4,"Rel-11","C6","2011-09-16","2011-12-09",1,"CP-110756","-","ST Ericsson","Andrzej Winiarski","-","31.101; 31.102",53,27,"CP-55","PCG-28","2011-08-29","2011-11-28"]
[6026,490028,"   Deleted - TR on Security aspects of Machine-Type Communications","-",2,"Rel-11","S3","2009-12-10","2012-06-20",1,"SP-120848","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","Was Rel-10 UID_460023 (Security for NIMTC). SP#56 stopped (activity transferred to Rel-12 Feature MTCe under UID_560722). ","New 33.868",49,25,"SP-56","PCG-29","2010-09-18","2012-11-12"]
[6030,480330,"   Deleted - Stage 2 on SA2 part for System Improvements to Machine-Type Communications","SIMTC",2,"Rel-11","S2","2010-06-10","2011-06-08",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#52 stopped","TBD",48,25,"SP-52","PCG-27","2010-05-28","2012-11-12"]
[6033,480131,"   Stage 1 for USSD simulation service in IMS","USSI",2,"Rel-11","S1","2010-06-10","2010-06-10",1,"SP-100408","-","Deutsche Telekom","kurt.bischinger@t-mobile.at","SP#48 completed. Specify a CS domain USSD like service over IMS (see GSM Mobile User Initiated USSD)",22.172999999999998,48,25,null,null,"2010-06-06","2011-08-24"]
[6039,510043,"   Stage 2 for QoS Control Based on Subscriber Spending Limits","QoS_SSL",2,"Rel-11","S2","2011-03-23","2011-09-21",1,"SP-110519","-","Huawei","Xu Xia (xiatony@huawei.com)","SP#53 completed",23.202999999999999,51,26,null,null,"2011-03-10","2011-08-12"]
[6041,520004,"   CT3 aspects of QoS Control Based on Subscriber Spending Limits (Stage 3)","QoS_SSL-CT3",2,"Rel-11","C3","2011-06-03","2012-06-15",1,"CP-120203","-","Huawei","QiaoWeihua@huawei.com","CP#56 completed","29.212; 29.213; 29.214; 29.215; new 29.219",52,27,null,null,"2011-05-18","2012-04-20"]
[6044,490232,"   Stage 1 for Optimized Service Charging and Allocation of Resources in IMS whilst Roaming","OSCAR",2,"Rel-11","S1","2010-09-23","2011-09-21",1,"SP-110347","-","Vodafone","mona.mustapha@vodafone.com","SP#53 completed","22.115; 22.173; 22.228",49,25,null,null,"2010-08-31","2012-03-05"]
[6048,530221,"   Stage 3 for Inclusion of Media Resource Broker","MRB",2,"Rel-11","C1,C3,IETF","2011-09-16","2013-06-14",1,"CP-120277","-","AT&T","Martin Dolly (md3135@att.com)","CP#60 completed","-",53,27,null,null,"2011-08-25","2012-06-06"]
[6052,500030,"Non Voice Emergency Services","NOVES",1,"Rel-11","S1,S2","2010-12-16","2012-03-07",1,"SP-100884","-","Qualcomm","dwilliams@qualcomm.com","SP#55 Stage 2 completed. Triggered by SA1 Rel-11 TR 22.871 Study on Non Voice Emergency Services (FS_NOVES)","-",50,26,null,null,"2010-11-29","2012-03-16"]
[6053,500130,"   Stage 1 for Non Voice Emergency Services","NOVES",2,"Rel-11","S1","2010-12-16","2011-09-21",1,"SP-100884","-","Qualcomm","dwilliams@qualcomm.com","SP#53 completed",22.100999999999999,50,26,null,null,"2010-11-29","2011-08-24"]
[6057,530010,"   Stage 2/3 for Support for 3GPP Voice Interworking with Enterprise IP-PBX","VINE-CT1",2,"Rel-11","C1","2011-09-20","2013-03-01",1,"CP-110641","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","CP#59 completed","23.218; 24.229",53,27,null,null,"2011-08-25","2013-02-16"]
[6060,530011,"   Core Network aspects of Anonymous Call Rejection in the CS domain","ACR_CS-CN",2,"Rel-11","C4,C3","2011-09-14","2011-12-02",1,"CP-110587","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#54 completed","Stage 2/3",53,27,null,null,"2011-08-27","2011-08-27"]
[6066,470023,"   Stage 2 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI",2,"Rel-11","S2","2010-03-26","2012-06-20",1,"SP-120539","-","Ericsson","stefan.rommer@ericsson.com","SP#56 completed","23.203; new 23.139",47,24,null,null,"2009-12-06","2012-06-09"]
[6068,530012,"   Stage 3 BB I - Core Network impacts: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI_BBI-CT",2,"Rel-11","C1,C3,C4","2011-09-16","2012-12-07",1,"CP-120419","-","Ericsson","Zu.Qiang@Ericsson.com","CP#58 completed","Stage 3",53,27,null,null,"2011-08-29","2012-11-17"]
[6071,551002,"      Deleted - (IETF) on Stage 3 BB I for BBAI; Home (e)Node B – Security Gateway Interface","BBAI_BBI-CT",3,"Rel-11","C4-IETF","2012-03-02","2012-06-15",1,"CP-120419","-","Lionel Morand","-","Draft removed from 3GPP documentation","draft-so-ipsecme-ikev2-cpext",55,28,"CP-56","PCG-29","2012-03-05","2012-06-14"]
[6075,490026,"   Stage 1 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB","BBAI_BBII-CTofldS1",2,"Rel-11","S1","2010-09-23","2011-09-21",1,"SP-120419","-","Ericsson","Olle.Eriksson@ericsson.com","SP#53 completed. 22/01: acronym modified",22.277999999999999,49,25,null,null,"2010-09-01","2015-01-22"]
[6079,530213,"      CT1 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB","BBAI_BBII-CT",3,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#57 completed","new 24.320",53,27,null,null,"2011-08-29","2012-08-14"]
[6080,530313,"      CT3 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB","BBAI_BBII-CT",3,"Rel-11","C3","2011-09-16","2012-09-07",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#57 completed","29.212; 29.213; 29.215",53,27,null,null,"2011-08-29","2012-08-13"]
[6084,530014,"   Deleted - Stage 3 BB III - Core Network impacts: BBF convergence and network based mobility ","-",2,"Rel-11","C3,C1,C4","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","Stage 3",53,27,"CP-55","PCG-28","2011-08-29","2012-03-06"]
[6087,530314,"      Deleted - CT3 part of Stage 3 BB III: BBF convergence and network based mobility","-",3,"Rel-11","C3","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","29.212; 29.213; 29.215",53,27,"CP-55","PCG-28","2011-08-29","2012-02-20"]
[6093,500126,"   Stage 2 for Single Radio Video Call Continuity for 3G-CS","vSRVCC",2,"Rel-11","S2","2010-10-15","2011-09-21",1,"SP-100704","-","Samsung","xiaowan.ke@samsung.com","SP#53 completed. Triggered by Feasibility Study on video call handover capability in TR 23.886 UID_470048 Study on Single Radio Video Call Continuity for 3G-CS (FS_vSRVCC)","23.203; 23.216; 23.237",50,26,null,null,"2010-11-26","2012-06-18"]
[6095,520105,"      CT1 aspects of Single Radio Video Call Continuity for 3G-CS","vSRVCC-CT",3,"Rel-11","C1","2011-06-03","2012-06-15",1,"CP-120278","-","NEC","gottfried.punz@neclab.eu","CP#56 completed","24.008; 24.237; 24.301",52,27,null,null,"2011-05-18","2012-06-06"]
[6098,480038,"Network-provided Location information for IMS (NETLOC)","NWK-PL2IMS",1,"Rel-11","S2,S1,S5,C3,C4,C1","2010-06-10","2013-03-01",1,"SP-110631","-","T-Mobile","michele.zarri@t-mobile.co.uk ","Covers the case where UE is served by a 3GPP RAN. Architecture making Cell/PLMN ID (UE is camped on) available to IMS nodes when the operator needs to record this information either to fulfil legal obligations or for charging.","-",48,25,null,null,"2010-06-06","2012-11-13"]
[6102,490029,"   Charging for Network-provided Location information for IMS","NWK-PL2IMS_CH",2,"Rel-11","S5","2010-09-23","2012-09-12",1,"SP-110700","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#57 completed","Stage 2 (32.240; 32.260); Stage 3 (32.298; 32.299)",49,25,null,null,"2010-09-03","2012-09-05"]
[{"$f":"A6106+1","v":6106},550308,"      CT1 part of CT aspects of Network-provided Location information for IMS","NWK-PL2IMS-CT",3,"Rel-11","C1","2012-03-02","2013-03-01",1,"CP-120845","-","Huawei","Qiao Weihua (qiaoweihua@huawei.com)","CP#57 completed. 3/3: Acronym changed from \"NWK-PL2IMS_CT\"","24.229; 24.292",55,28,null,null,"2012-02-22","2015-03-03"]
[6107,500032,"Service Awareness and Privacy Policies","SAPP",1,"Rel-11","S2,S1,C3","2010-10-12","2011-12-02",1,"SP-100882","-","Allot","Alla Goldner (agoldner@allot.com)","CP#54 completed. Triggered by the SA1,SA2 Rel-10 TR 23.813 Study on Policy solutions and enhancements (FS_PP) UID_440047","-",50,26,null,null,"2010-11-26","2011-08-12"]
[6111,500033,"VPLMN Autonomous CSG Roaming","VCSG",1,"Rel-11","S2,C4","2010-10-15","2011-12-14",1,"SP-100706","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","CP#56 completed. Linked to Rel-10 UID_450053 Enhanced Home NodeB / eNodeB (EHNB). Implements Rel-9 requirements for CSG support in SA1 TS 22.220","-",50,26,null,null,"2010-11-26","2012-08-13"]
[6114,510048,"Data Identification in Access Network Discovery and Selection Function (ANDSF)","DIDA",1,"Rel-11","S2,C1","2011-03-23","2012-12-07",1,"SP-110084","-","Qualcomm","Gerardo Giaretta (gerardo@qualcomm.com)","SP#58 completed. Linked to Rel-10 IFOM (IP Flow Mobility and seamless WLAN offload) UID_450041. Defines IP flow mobility, seamless and non seamless WLAN offload and respective ANDSF extensions","Stage 2/3",51,26,null,null,"2011-02-21","2012-11-19"]
[6118,510050,"LOcation-Based Selection of gaTEways foR WLAN","LOBSTER",1,"Rel-11","S2,C4","2011-03-23","2012-06-15",1,"SP-110752","-","ZTE","zhu.chunhui@zte.com.cn","CP#56 completed. Related to UID_350027 SAE for support for non-3GPP accesses (SAES-SA-FP_n3GPP). Enhancements to ePDG and PDN GW selection functions for S2b and S2c based on UE location","-",51,26,null,null,"2011-03-18","2012-06-01"]
[6120,540010,"   CT aspects of LOcation-Based Selection of gaTEways foR WLAN","LOBSTER-CT",2,"Rel-11","C4","2011-12-02","2012-06-15",1,"CP-120252","-","ZTE","zhou.xingyue@zte.com.cn","Stage 3. CP#56 completed","Stage 3",54,28,null,null,"2011-11-23","2012-09-24"]
[6126,530301,"      CT1 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-CT",3,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-110726","-","Ericsson","ivo.sedlacek@ericsson.com","CP#57 completed","23.009; 24.008; 24.229; 24.237; 24.292; 24.301",53,27,null,null,"2011-08-25","2012-08-14"]
[6129,530601,"   GERAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (Stage 3)","rSRVCC-GERAN",2,"Rel-11","G2","2011-09-12","2013-06-28",1,"GP-111290","-","ZTE","li.jing4@zte.com.cn","GP#60 completed. GP#51 approved WID","44.018; 48.008",51,27,null,null,"2011-08-25","2013-09-04"]
[6133,530046,"S2a Mobility based On GTP and WLAN access to EPC","SaMOG_WLAN",1,"Rel-11","S2,C4,C1,C3,IETF","2011-09-22","2014-03-05",1,"SP-110642","-","ZTE","Chunhui Zhu (zhu.chunhui@zte.com.cn)","Triggered by Rel-11 TR 23.852 FS_SaMOG UID_510061, Rel-8 UID_350027 SAE for support for non-3GPP accesses (defines PMIP-S2a)","Stage 2/3",53,27,null,null,"2011-08-12","2014-02-19"]
[6134,530146,"   Stage 2 for S2a Mobility based On GTP and WLAN access to EPC","SaMOG_WLAN",2,"Rel-11","S2","2011-09-22","2012-03-07",1,"SP-110642","-","ZTE","zhu.chunhui@zte.com.cn","SP#55 completed","23.002; 23.203; 23.402",53,27,null,null,"2011-08-12","2012-02-20"]
[6138,540211,"      Deleted - CT1 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC","SaMOG_WLAN-CN",3,"Rel-11","C1","2011-12-02","2012-06-15",1,"CP-110802","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#56 stopped (no CT1 impact)",24.302,54,28,"CP-56","PCG-29","2011-10-26","2012-06-01"]
[6141,540129,"   Stage 2 for Roaming Architecture for Voice over IMS with Local Breakout","RAVEL",2,"Rel-11","S2","2011-11-28","2011-12-14",1,"SP-110885","-","Deutsche Telekom","michele.zarri@telekom.com","SP#54 completed","23.002; 23.228",54,28,null,null,"2011-10-25","2011-11-28"]
[6145,550204,"      CT3 part of CT aspects of Roaming Architecture for Voice over IMS with Local Breakout","RAVEL-CT",3,"Rel-11","C3","2012-03-02","2012-12-07",1,"CP-120088","-","Deutsche Telekom","reinhard.lauster@)t-mobile.at","CP#58 completed","29.165; 29.162; 29.079",55,28,null,null,"2012-02-20","2012-11-20"]
[6147,560127,"   Stage 2 for IMS Overload Control","IOC",2,"Rel-11","S2","2012-06-18","2012-09-12",1,"SP-120273","-","Orange, China Mobile","antoine.mouquet@orange-ftgroup.com, YU Qing","SP#57 completed. Moved Rel-12=>Rel-11 as CT finished Stage 3. ",23.228000000000002,56,29,null,null,"2012-05-11","2012-07-24"]
[6153,571003,"      (IETF) CT part of Stage 3 for IMS Overload Control (RFC 7200)","IOC",3,"Rel-11","C1-IETF,C3-IETF","2013-07-29","2014-06-13",1,"CP-120561","-","Keith Drage","Keith Drage","CP#64 completed","RFC 7200 (was draft-ietf-soc-load-control-event-package)",57,29,null,null,"2012-08-13","2014-06-06"]
[6156,440055,"ZUC EEA3 and EIA3 (new Encryption & Integrity EPS security Algorithms)","EEA3_EIA3",1,"Rel-11","S3,R5","2009-06-04","2012-09-07",1,"SP-090457","-","CATR","Yuan Qi (yuanqi@catr.cn)","RP#57 completed testing","-",44,23,null,null,"2009-05-18","2012-09-04"]
[6160,510053,"H(e)NB security features for UE mobility scenarios (Stage 2)","HNB_mob_Sec",1,"Rel-11","S3","2011-03-23","2012-03-07",1,"SP-110025","-","Huawei","Marcus Wong (mwong@huawei.com)","SP#55 completed. Add HeNB Security extensions to Extended H(e)NB Features (EHNBF) UID_450053",33.32,51,26,null,null,"2011-02-14","2012-02-20"]
[6161,540012,"Generic Bootstrapping Architecture (GBA) extensions for re-use of SIP Digest credentials","GBA-ext",1,"Rel-11","S3,C4,C1","2011-12-02","2012-09-07",1,"SP-110884","-","Nokia","Silke.Holtmanns@nokia.com","Stage 2/3. CP#57 completed","-",54,28,null,null,"2011-11-28","2012-08-14"]
[6164,540312,"      CT4 part of Stage 3 for GBA extensions for re-use of SIP Digest credentials","GBA-ext-St3",3,"Rel-11","C4","2011-12-02","2012-09-07",1,"CP-110804","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#57 completed",29.109000000000002,54,28,null,null,"2011-11-23","2012-08-14"]
[6169,530248,"   Download Delivery Enhancements for MBMS","EMM-DDE",2,"Rel-11","S4","2011-09-21","2012-12-12",1,"SP-120025","-","Qualcomm","Nikolai Leung (nleung@qualcomm.com)","SP#58 completed","26.346; new 26.951=>26.851",53,27,null,null,"2011-09-07","2012-12-11"]
[6172,510051,"Rel-11 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM11",1,"Rel-11","S5","2011-03-23","2013-03-06",1,"-","-","-","-","OAM11 is an umbrella Feature also for OAM&P related TEI11 type of changes that are not part of any other dedicated feature/WI","-",51,26,null,null,"2011-02-22","2011-02-22"]
[6175,510251,"   Rel-11 Performance Management","OAM11-PM",2,"Rel-11","S5","2011-03-23","2012-12-12",1,"-","-","-","-","-","-",51,26,null,null,"2011-02-22","2012-11-19"]
[6178,520034,"      CN performance measurements enhancement","OAM-ePM-CN",3,"Rel-11","S5","2011-06-08","2012-09-12",1,"SP-110275","-","China Mobile","Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com), Li Jian (lijian@chinamobile.com)","SP#57 completed","32.406; 32.407; 32.426",52,27,null,null,"2011-05-19","2012-08-31"]
[6183,540031,"      Inter-RAT Energy Saving Management","OAM-IRAT-ESM",3,"Rel-11","S5","2011-12-07","2012-12-12",1,"SP-110701","-","Nokia Siemens Networks, Huawei","clemens.suerbaum@nsn.com, xiahaitao@huawei.com","SP#58 completed. Triggered by Rel-11 TR 32.834 (Study on OAM aspects of inter-RAT Energy Saving) UID_510045. Needs coordination with RAN WGs","32.405; 32.551; 32.522; 32.526; 32.642; 32.646; 32.762; 32.766",54,28,null,null,"2011-11-22","2012-11-19"]
[6187,550019,"   Unification of Charging session from SIP AS and SRVCC functions in IMS","UCHIMS_AS-SRVCC",2,"Rel-11","S5","2012-03-07","2012-12-12",1,"SP-120042","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","Stage 2/3. SP#58 completed","32.260; 32.275; 32.298; 32.299",55,28,null,null,"2012-02-22","2012-12-05"]
[6188,510029,"Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment","IOI_IMS_CH",1,"Rel-11","S5,S1,C1","2010-10-27","2012-06-15",1,"SP-110132","-","Deutsche Telekom","matthias.seibel@telekom.de","Stage 2/3. CP#56 completed. Stage 1 in SA1 22.115","-",51,26,null,null,"2011-02-22","2012-06-01"]
[6191,520006,"   Stage 3 for Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment","IOI_IMS_CH",2,"Rel-11","C1","2011-06-07","2012-06-15",1,"CP-110440","-","Deutsche Telekom","martin.huelsemann@telekom.de]","CP#56 completed",24.228999999999999,52,27,null,null,"2011-05-23","2012-06-01"]
[6196,510004,"Definition of the UICC Application for Hosting Party Module","HPM_UICC",1,"Rel-11","C6","2011-03-18","2012-06-15",1,"CP-110289","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#56 completed","31.102; New 31.104",51,26,null,null,"2011-03-03","2012-09-25"]
[6199,520108,"   CT4 part of enhanced Nodes Restoration for EPC","eNR_EPC",2,"Rel-11","C4","2011-06-03","2012-12-07",1,"CP-120449","-","ZTE","lu.fei1@zte.com.cn","CP#58 completed","23.007; 23.008; 23.018; 29.274; 29.275",52,27,null,null,"2011-05-18","2012-11-20"]
[6202,570009,"   CT3 part of enhanced Nodes Restoration for EPC","eNR_EPC",2,"Rel-11","C3","2012-09-10","2012-12-07",1,"CP-120449","-","ZTE","lu.fei1@zte.com.cn","CP#58 completed",29.212,57,29,null,null,"2012-08-13","2012-11-20"]
[6205,520209,"   CT1 part of Reference Location Information (Stage 3)","RLI",2,"Rel-11","C1","2011-06-03","2011-09-16",1,"CP-110386","-","Huawei","susan.shishufeng@Huawei.com","CP#53 completed",24.228999999999999,52,27,null,null,"2011-05-18","2011-06-01"]
[6210,611002,"   (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (RFC 7135)","IMSProtoc5",2,"Rel-11","C1-IETF","2013-09-06","2014-06-13",1,"CP-110437","-","Roland Jesske","Roland Jesske","CP#64 completed","RFC 7135 (was draft-polk-local-emergency-rph-namespace)",61,31,null,null,"2013-08-23","2014-06-06"]
[6213,530003,"Service Identification for RRC Improvements in GERAN (Stage 2/3)","SIRIG",1,"Rel-11","S2,C4,C3,G2","2011-09-19","2012-09-07",1,"CP-120033","-","China Mobile","zhanghao@chinamobile.com","TSG#57, GP#55 completed. CT defined a generic solution (not only for GERAN)","GERAN",51,27,null,null,"2011-09-06","2012-09-06"]
[6214,560008,"   Stage 2 for Service Identification for RRC Improvements in GERAN","SIRIG",2,"Rel-11","S2","2012-06-18","2012-09-07",1,"-","-","-","-","SP#57 completed","23.060; 23.251",56,29,null,null,"2012-06-18","2012-08-31"]
[6218,530103,"   GERAN2 part of Service Identification for RRC Improvements in GERAN","SIRIG",2,"Rel-11","G2","2011-09-19","2012-08-31",1,"GP-111876","-","China Mobile, Huawei","Juan Deng, Yang Zhao","GP#55 completed. GP#51 approved WID",48.018000000000001,51,27,null,null,"2011-09-06","2012-08-31"]
[6222,530020,"GCSMSC and GCR Redundancy for VGCS/VBS (Stage 2/3)","RT_VGCS_Red",1,"Rel-11","C1","2011-09-19","2012-09-07",1,"CP-120279","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#57 completed. Stage 2/3 adding a CN internal functionality, not affecting Voice Group Call Service (VGCS)/VBS as perceived by service subscriber. Hence, no Stage 1 impact for VGCS/VBS (42.068, 42.069)","Stage 2/3",53,27,null,null,"2011-08-27","2012-08-14"]
[6227,540117,"   CT4 part of Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority","eMPS_Gateway",2,"Rel-11","C4","2011-12-02","2012-09-07",1,"CP-110806","-","Telcordia","Viqar Shaikh","CP#57 completed","23.333; 23.334; 29.232; 29.238; 29.332; 29.333; 29.334",54,28,null,null,"2011-10-26","2012-08-13"]
[6229,550007,"Inter-IMS Network to Network Interface (II-NNI) enhancements: SIP timers applicability (Stage 3)","NNI_timers",1,"Rel-11","C3","2012-03-02","2012-09-07",1,"CP-120082","-","Telecom Italia","antonio.ascolese@telecomitalia.it","CP#57 completed",29.164999999999999,55,28,null,null,"2012-02-22","2012-08-13"]
[6232,560007,"Generic IMS User Group Over Sh","GenUG_Sh",1,"Rel-11","C4","2012-06-15","2012-09-07",1,"CP-120254","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#57 completed",29.364000000000001,56,29,null,null,"2012-06-02","2012-08-13"]
[6237,570111,"   CT3 part of Enhanced T.38 FAX support","MMTel_T.38_FAX",2,"Rel-11","C3","2012-09-07","2012-12-07",1,"CP-120673","-","NEC","Naoaki Suzuki (n-suzuki@en.jp.nec.com)","CP#58 completed",29.163,57,29,null,null,"2012-08-13","2012-11-20"]
[6238,570211,"   CT1 part of Enhanced T.38 FAX support","MMTel_T.38_FAX",2,"Rel-11","C1","2012-09-07","2012-12-07",1,"CP-120673","-","NEC","Naoaki Suzuki (n-suzuki@en.jp.nec.com)","CP#58 completed",24.228999999999999,57,29,null,null,"2012-08-13","2012-11-19"]
[6241,540116,"   Deleted - TR Study on enhancement of protocols for SMS service over SGs","PROTOC_SMS_SGs",2,"Rel-11","C4","2011-12-02","2012-06-15",1,"CP-120034","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#56 stopped (abandonned new TR 29.818)","new 29.818",54,28,"CP-56","PCG-29","2011-10-26","2012-06-19"]
[6245,510101,"   GERAN part of Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",2,"Rel-11","G2","2011-03-04","2013-05-17",1,"GP-121090","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","GP#58 completed. GP#49 approved WID","44.018; 44.060; 45.002; 45.008; 48.008; 48.018",49,26,null,null,"2011-03-04","2013-05-17"]
[6249,560004,"      CT4 part of CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",3,"Rel-11","C4","2012-06-13","2012-09-07",1,"CP-120563","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","CP#57 completed",23.003,54,29,null,null,"2012-06-02","2012-11-19"]
[6254,550023,"Domain Specific Access Control in GERAN","GDSAC",1,"Rel-11","G2","2012-03-05","2012-08-31",1,"GP-120452","-","Vodafone","chris.pudney@vodafone.com","GP#55 completed. GP#53 approved WID. Work is dependent upon Full_MOCN-GERAN (UID_510001)","GERAN 44.018",53,28,null,null,"2012-04-18","2012-08-31"]
[6256,500120,"   Core part: Extending 850 MHz Upper Band (814 – 849 MHz)","e850_UB-Core",2,"Rel-11","R4,R2,R3","2010-12-10","2012-03-02",1,"RP-111396","RP-120075","Sprint","John.J.Humbert@Sprint.com","RP#55 completed","25.101; 25.104; 25.113; 25.133; 25.141; 25.461; 25.466; 36.101; 36.104; 36.113; 36.124; 36.133; 36.141; 36.307; 36.331; 37.104; 37.113; 37.141",50,26,null,null,"2010-12-10","2012-02-23"]
[6260,530130,"   Core part: Further Self Optimizing Networks (SON) enhancements","SONenh2_LTE_UTRA-Core",2,"Rel-11","R3,R2","2011-09-19","2012-12-07",1,"RP-120314","RP-121557","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#58 completed","25.331; 25.401; 25.410; 25.413; 25.423; 25.433; 36.300; 36.331; 36.413; 36.423",53,27,null,null,"2011-09-15","2012-11-27"]
[6263,590001,"   Test part: Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN","eMDT_UMTSLTE-UEConTest",2,"Rel-11","R5","2013-03-04","2013-12-06",1,"RP-130172","RP-131447","NTT DoCoMo","masahiro.tamaoki.eu@nttdocomo.com","RP#62 completed","34.108; 34.109; 34.123-1; 34.123-2; 34.123-3; 36.508; 36.509; 36.523-1; 36.523-2; 36.523-3",59,30,null,null,"2013-01-29","2013-08-13"]
[6265,530136,"   Core part: Network Energy Saving for E-UTRAN","Netw_Energy_LTE-Core",2,"Rel-11","R3","2011-09-19","2012-09-07",1,"RP-120620","RP-121016","China Mobile","yangning@chinamobile.com","RP#57 completed. Inter-RAT aspect can affect UTRA and GERAN as well","25.413; 36.300; 36.413; 36.423",53,27,null,null,"2011-09-15","2012-09-06"]
[6268,530137,"   Core part: E-UTRA medium range and MSR medium range/local area BS class requirements","medBS_class_LTE_MSR-Core",2,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-111383","RP-121558","Ericsson","johan.skold@ericsson.com","RP#58 completed. TR 37.809 v200 for Approval","25.104; 36.104; 37.104; new 37.809",53,27,null,null,"2011-09-15","2012-12-05"]
[6272,550115,"   Core part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station","MB_MSR_RF-Core",2,"Rel-11","R4,G1","2012-02-06","2012-12-07",1,"RP-120857","RP-121985","Huawei","Liu Ye (leo.liuye@huawei.com)","RP#58 completed","25.104; 25.105; 36.104; 37.104; new 37.812",55,28,null,null,"2012-02-23","2012-12-05"]
[6276,560014,"Further enhancements to H(e)NB mobility - Part 2","EHNB_enh2",1,"Rel-11","R3,R2","2012-06-19","2012-12-07",1,"RP-121712","-","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","Stage 2/3. Legacy UE Handling (X2-GW, 20% complete, moved to Rel-12 UID_580030). Triggered by FS_EHNB_enh (UTRA, LTE TR 37.803 under AI 12.3.2)","UTRA; LTE",56,29,null,null,"2012-06-13","2012-11-27"]
[6281,480026,"Service continuity improvements for MBMS for LTE","MBMS_LTE_SC",1,"Rel-11","R2,R3,R5","2010-06-04","2014-03-06",1,"RP-120258","-","Huawei","David.Lecompte@huawei.com ","-","LTE",48,25,null,null,"2010-06-04","2012-07-13"]
[6284,510021,"Further Enhanced Non CA-based ICIC for LTE","eICIC_enh_LTE",1,"Rel-11","R1,R2,R3,R4,R5","2011-03-22","2014-12-15",1,"RP-120860","-","China Mobile","ShenXiaodong@chinamobile.com","-","LTE",51,26,null,null,"2011-03-14","2012-12-05"]
[6287,600001,"   Test part: Further Enhanced Non CA-based ICIC for LTE","eICIC_enh_LTE-UEConTest",2,"Rel-11","R5","2013-06-15","2014-12-15",1,"RP-130649","RP-141847","ZTE","Carolyn Taylor (carolyn.tayl@zte.com.cn)","¦Stat Rep: RP-141131->RP-141847","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-1; 36.523-2; 36.523-3",60,31,null,null,"2013-05-22","2015-01-12"]
[6290,510228,"   Perf. part: New Band LTE Downlink FDD 716-728 MHz (Band 29), Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29","LTE_DL_FDD700-Perf",2,"Rel-11","R4","2011-03-29","2012-12-07",1,"RP-110435","RP-121605","AT&T","marc.grant@att.com ","RP#58 completed","36.101; 36.104; 36.133; 36.141; 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[6292,510131,"   Core part: LTE RAN Enhancements for Diverse Data Applications","LTE_eDDA-Core",2,"Rel-11","R2","2011-03-18","2012-12-07",1,"RP-120256","RP-121571","BlackBerry","Gordon Young (gyoung@rim.com)","RP#58 completed","36.300; 36.321; 36.331; new 36.822",51,26,null,null,"2011-03-14","2012-11-29"]
[6295,510132,"   Core part: LTE E850 - Lower Band for Region 2 (non-US), Band 27","LTE_e850_LB-Core",2,"Rel-11","R1,R2,R4","2011-06-15","2012-09-07",1,"RP-120602","RP-120570","NII Holdings","bill.shvodian@nii.com","RP#56 completed","25.101; 25.104; 25.461; 25.466; 36.101; 36.104; 36.113; 36.124; 36.307; 37.104; 37.113",51,26,null,null,"2011-03-14","2012-06-09"]
[6299,520117,"   Core part: LTE for 700 MHz Digital Dividend","LTE_APAC700-Core",2,"Rel-11","R4,R2,R3","2011-06-07","2012-06-15",1,"RP-110875","RP-120572","Ericsson","olav.queseth@ericsson.com","RP#56 completed. TR 36.820 v100 for Information and Approval","25.461; 25.466; 36.101; 36.104; 36.113; 36.124; 36.133; 36.307; 37.104; 37.113; new 36.820",52,27,null,null,"2011-06-02","2012-06-09"]
[6303,520119,"   Core part: Relays for LTE (part 2)","LTE_Relay2-Core",2,"Rel-11","R4","2011-06-07","2012-09-07",1,"RP-110914","RP-121008","Ericsson","christian.hoymann@ericsson.com ","RP#57 completed. TS 36.116, TR 36.826 v100 for Information & Approval. RP#52 Core part not completed in Rel-10","36.133; new RAN4 (36.116; 36.826)",52,27,null,null,"2011-06-03","2012-09-04"]
[6306,530131,"   Core part: Signalling and Procedure for Interference Avoidance for in-device coexistence","SPIA_IDC_LTE-Core",2,"Rel-11","R2,R4","2011-09-19","2012-12-07",1,"RP-111355","RP-121573","China Mobile","Zhenping HU","RP#58 completed","36.133; 36.300; 36.306; 36.321; 36.331",53,27,null,null,"2011-09-15","2012-11-27"]
[6308,530032,"Coordinated Multi-Point Operation for LTE","COMP_LTE",1,"Rel-11","R1,R2,R3,R4,R5","2011-09-19","2014-12-15",1,"RP-111365","-","Huawei, Samsung","Juho Lee (juho95.lee@samsung.com), david.mazzarese@huawei.com","Stage 3. Triggered by Rel-11 TR 36.819 Study on Coordinated Multi-Point Operation for LTE (FS_CoMP_LTE)","LTE",53,27,null,null,"2011-09-15","2011-09-15"]
[6314,540025,"Enhanced downlink control channel(s) for LTE Advanced","LTE_enh_dl_ctrl",1,"Rel-11","R1,R2,R4,R5","2011-12-09","2014-09-12",1,"RP-120871","-","Alcatel-Lucent","sigen.ye@alcatel-lucent.com","Stage 3. RP#58 Core completed. Triggered by UID_510037 Rel-11 TR 36.871 Study on further Downlink MIMO enhancements for LTE-Advanced (FS_LTE_eDL_MIMO_enh)","LTE",54,28,null,null,"2011-12-07","2012-11-28"]
[6317,590005,"   Test part: Enhanced downlink control channel(s) for LTE Advanced","LTE_enh_dl_ctrl-UEConTest",2,"Rel-11","R5","2013-03-04","2014-09-12",1,"RP-130304","RP-141256","Huawei","Xu Kai (xk.xukai@huawei.com)","RP#65 completed","36.508; 36.521-1; 36.521-2; 36.523-1; 36.523-2; 36.523-3",59,30,null,null,"2013-01-29","2014-09-09"]
[6319,550112,"   Core part: Public Safety Broadband High Power UE for Band 14 for Region 2","LTE_B14_PSBB_HPUE-Core",2,"Rel-11","R4","2012-03-05","2012-12-07",1,"RP-120362","RP-121581","Motorola Solutions","xiaowei.jin@motorolasolutions.com","RP#58 completed. TR 36.837 v100 for Information and Approval","36.101; new 36.837",55,28,null,null,"2012-02-23","2012-12-05"]
[6322,550113,"   Perf. part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection","LTE_Interf_Rej-Perf",2,"Rel-11","R4","2012-03-05","2012-12-07",1,"RP-120382","RP-121582","Renesas Mobile","Timo Roman","RP#58 completed",36.100999999999999,55,28,null,null,"2012-02-23","2012-11-27"]
[6326,590007,"   Test part: Additional special subframe configuration for LTE TDD","LTE_TDD_add_subframe-UEConTest",2,"Rel-11","R5","2013-03-04","2013-06-14",1,"RP-130305","RP-130475","Huawei","Li Xiang (tricia.li@huawei.com)","RP#60 completed","36.508; 36.523-1; 36.523-2; 36.523-3",59,30,null,null,"2013-02-26","2013-06-04"]
[6330,510230,"      Perf. part: LTE Carrier Aggregation Enhancements","LTE_CA_enh-Perf",3,"Rel-11","R4","2011-03-15","2014-12-12",1,"RP-121999","RP-141969","Nokia","lars.e.lindh@nokia.com","¦Stat Rep: RP-141377->RP-141969","36.101; 36.104; 36.133; 36.141",51,26,null,null,"2011-03-14","2015-01-12"]
[6333,580258,"   Rel-11 inter-band Carrier Aggregation","-",2,"Rel-11","R4","2010-12-10","2012-12-07",1,"-","-","-","-","LTE_CA_Rel-11","LTE",58,30,null,null,"2012-11-30","2012-11-30"]
[6335,480123,"         Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 7","LTE_CA_B3_B7-Core",4,"Rel-11","R4","2010-12-10","2012-09-07",1,"RP-120830","RP-121022","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.307; new generic 36.850",48,25,null,null,"2010-06-04","2012-09-04"]
[6341,500118,"         Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 13","LTE_CA_B4_B13-Core",4,"Rel-11","R4","2010-12-10","2012-09-07",1,"RP-120905","RP-121026","Ericsson","christian.bergljung@ericsson.com ","RP#57 completed","36.101; 36.104; 36.133; 36.307; new generic 36.850",50,26,null,null,"2010-12-10","2012-09-04"]
[6344,510122,"         Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12-Core",4,"Rel-11","R4,R2","2011-03-22","2012-12-07",1,"RP-120877","RP-121592","Leap Wireless","Bill Chandler (bchandler@cricketcommunications.com)","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.307; new generic 36.850",51,26,null,null,"2011-03-14","2012-11-27"]
[6348,510223,"         Perf. part: LTE Advanced Carrier Aggregation of Band 5 and Band 12","LTE_CA_B5_B12-Perf",4,"Rel-11","R4","2011-03-25","2012-12-07",1,"RP-120221","RP-121597","US Cellular","sebastian.thalanany@uscellular.com ","RP#58 completed","36.101; 36.104; 36.133; 36.307",51,26,null,null,"2011-03-14","2012-11-27"]
[6349,510024,"      LTE Advanced Carrier Aggregation of Band 7 and Band 20","LTE_CA_B7_B20",3,"Rel-11","R4","2011-03-22","2012-09-07",1,"RP-120889","-","Huawei","Steven Chen","Stage 3. RP#57 completed","LTE",51,26,null,null,"2011-03-14","2012-09-04"]
[6353,510125,"         Core part: LTE Advanced Carrier Aggregation of Band 2 and Band 17","LTE_CA_B2_B17-Core",4,"Rel-11","R4","2011-03-23","2012-09-07",1,"RP-110432","RP-121034","AT&T","marc.grant@att.com ","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.850",51,26,null,null,"2011-03-14","2012-09-04"]
[6357,510226,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 5","LTE_CA_B4_B5-Perf",4,"Rel-11","R4","2011-03-25","2012-12-07",1,"RP-110433","RP-121589","AT&T","marc.grant@att.com ","RP#58 completed","36.101; 36.104; 36.133; 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[6360,510227,"         Perf. part: LTE Advanced Carrier Aggregation of Band 5 and Band 17","LTE_CA_B5_B17-Perf",4,"Rel-11","R4","2011-03-25","2012-12-07",1,"RP-110434","RP-121599","AT&T","marc.grant@att.com ","RP#58 completed","36.101; 36.104; 36.133; 36.141; 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[{"$f":"A6362+1","v":6362},530123,"         Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 20","LTE_CA_B3_B20-Core",4,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-120887","RP-121046","Vodafone","tim.frost@vodafone.com","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.133; 36.307; new generic 36.850",53,27,null,null,"2011-09-15","2012-09-04"]
[6368,530126,"         Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5-Core",4,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-120899","RP-121042","SK Telecom","Haesung Park","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.133; 36.307; new generic 36.850",53,27,null,null,"2011-09-15","2012-09-04"]
[6371,530127,"         Core part: LTE Advanced Carrier Aggregation of Band 4 and Band 7","LTE_CA_B4_B7-Core",4,"Rel-11","R4","2011-09-19","2012-12-07",1,"RP-121152","RP-121590","Rogers Wireless","takwing.wan@rci.rogers.com","RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.133; 36.141; 36.307; 37.104; new generic 36.850",53,27,null,null,"2011-09-15","2012-11-27"]
[6375,540220,"         Perf. part: LTE Advanced Carrier Aggregation of Band 11 and Band 18","LTE_CA_B11_B18-Perf",4,"Rel-11","R4","2011-12-15","2012-12-07",1,"RP-120898","RP-121603","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#58 completed",36.133000000000003,54,28,null,null,"2011-12-07","2012-12-04"]
[6376,540021,"      LTE Advanced Carrier Aggregation of Band 1 and Band 18","LTE_CA_B1_B18",3,"Rel-11","R4,R2","2011-12-09","2012-09-07",1,"RP-120892","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Stage 3. RP#57 completed","LTE",54,28,null,null,"2011-12-07","2012-09-04"]
[6380,540122,"         Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 19","LTE_CA_B1_B19-Core",4,"Rel-11","R4,R2","2012-03-05","2012-09-07",1,"RP-120866","RP-120552","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","RP#56 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.133; 36.307; new generic 36.850",54,28,null,null,"2011-12-07","2012-06-15"]
[6384,540223,"         Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 21","LTE_CA_B1_B21-Perf",4,"Rel-11","R4","2011-12-13","2012-12-07",1,"RP-121173","RP-121055","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","RP#57 completed","36.133; 36.141",54,28,null,null,"2011-12-07","2012-09-04"]
[6387,550218,"         Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 8","LTE_CA_B3_B8-Perf",4,"Rel-11","R4","2012-03-06","2012-12-07",1,"RP-121162","RP-121587","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#58 completed","36.133; 36.141",55,28,null,null,"2012-02-23","2012-11-27"]
[6391,520215,"         Perf. part: LTE Advanced Carrier Aggregation in Band 38","LTE_CA_B38-Perf",4,"Rel-11","R4","2011-06-08","2012-09-07",1,"RP-110862","RP-121061","Huawei","ronnie.zhang@huawei.com","RP#57 completed","36.101; 36.104; 36.133; 36.141; 36.307; 37.104; 37.141",52,27,null,null,"2011-06-02","2012-09-04"]
[6393,520116,"         Core part: LTE Advanced Carrier Aggregation in Band 41","LTE_CA_B41-Core",4,"Rel-11","R4","2011-06-07","2012-03-02",1,"RP-120249","RP-120126","Clearwire","michael.hart@clearwire.com","RP#55 completed. Updated WID RP-110673=>RP-120249. TR 36.827 v100 for Information + Approval","36.101; 36.104; 36.133; 36.141; 36.307; 37.104; new 36.833-1-41 [instead of 36.827]",52,27,null,null,"2011-06-02","2012-02-23"]
[6398,450016,"UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test","UEAnt_FSTest",1,"Rel-11","R4,R5","2009-09-18","2016-09-15",1,"RP-111381","-","CATR","Guo Lin (guolin@emcite.com)","-","UTRA",45,23,null,null,"2009-09-15","2011-09-17"]
[6399,450116,"   Core part: UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test","UEAnt_FSTest-Core",2,"Rel-11","R4","2009-09-18","2011-12-09",1,"RP-111381","RP-111456","CATR","Guo Lin (guolin@emcite.com)","RP#54 completed","25.144; 25.914; 34.114",45,23,null,null,"2009-09-15","2011-11-29"]
[6402,500119,"   Core part: Eight carrier HSDPA","8C_HSDPA-Core",2,"Rel-11","R1,R2,R3,R4","2010-09-15","2012-06-15",1,"RP-101419","RP-120971","Ericsson","johan.hultell@ericsson.com","RP#57 completed","25.101; 25.104; 25.133; 25.211; 25.212; 25.213; 25.214; 25.215; 25.308; 25.331; 25.423; 25.433; 26.306",50,26,null,null,"2010-12-10","2012-09-04"]
[6407,500022,"Uplink Transmit Diversity for HSPA","HSPA_UL_TxDiv",1,"Rel-11","R1,R4,R2,R3,R5","2010-12-10","2014-06-13",1,"RP-120367","-","Huawei","zongjie.wang@huawei.com","Stage 2/3","UTRA",50,26,null,null,"2010-12-10","2012-02-28"]
[6411,500422,"   Perf. part: Uplink Transmit Diversity for HSPA - Open Loop","HSPA_UL_TxDiv-OL-Perf",2,"Rel-11","R4","2010-12-14","2012-12-07",1,"RP-120367","RP-121545","Huawei","zongjie.wang@huawei.com","RP#58 completed","25.101; 25.133",50,26,null,null,"2010-12-10","2012-11-28"]
[6414,510118,"   Core part: Introduction of New Configuration for 4C-HSDPA","4C_HSDPA_Config-Core",2,"Rel-11","R4,R2","2011-03-22","2011-12-09",1,"RP-110308","RP-111463","Telus Communications","jorge.delrio@telus.com ","RP#54 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101; 25.104; 25.141; 25.317 replaced by new 25.327",51,26,null,null,"2011-03-14","2011-12-07"]
[6418,510219,"   Perf. part: Non-contiguous 4C-HSDPA operation","NC_4C_HSDPA-Perf",2,"Rel-11","R4","2011-03-23","2013-03-01",1,"RP-110416","RP-130049","Ericsson","muhammad.kazmi@ericsson.com","RP#59 completed","25.101; 25.104; 25.133; 25.141",51,26,null,null,"2011-03-14","2013-02-27"]
[6420,510120,"   Core part: Further Enhancements to CELL_FACH","Cell_FACH_enh-Core",2,"Rel-11","R2,R1,R3,R4","2011-03-18","2012-12-07",1,"RP-111321","RP-121547","Qualcomm","Ravi Agarwal","RP#58 completed","25.101; 25.104; 25.133; 25.211; 25.212; 25.213; 25.214; 25.306; 25.308; 25.319; 25.321; 25.331; 25.423; 25.433",51,26,null,null,"2011-03-14","2012-11-27"]
[6423,530034,"HSDPA Multiflow Data Transmission","HSDPA_MFTX",1,"Rel-11","R2,R1,R3,R4,R5","2011-09-19","2015-03-13",1,"RP-111375","-","Nokia Siemens Networks","Alexander Sayenko","Stage 2,3","UTRA",53,27,null,null,"2011-09-15","2011-09-15"]
[{"$f":"A6426+1","v":6426},620016,"   Test part: HSDPA Multiflow Data Transmission","HSDPA_MFTX-UEConTest",2,"Rel-11","R5","2013-12-15","2015-03-13",1,"RP-131692","RP-150126","Qualcomm","Shubhang Vora (svora@qti.qualcomm.com)","¦Stat Rep: RP-141136->RP-141961 1st Apr 15: Compl:90%->100% 1st Apr 15: Stat Rep: RP-141961->RP-150126","34.108; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",62,32,null,null,"2013-11-25","2015-04-01"]
[6429,530235,"   Perf. part: Four Branch MIMO transmission for HSDPA","4Tx_HSDPA-Perf",2,"Rel-11","R4","2011-09-21","2013-12-06",1,"RP-111393","RP-131460","Ericsson","johan.hultell@ericsson.com","RP#62 completed","25.101; 25.104; 25.133; 25.141",53,27,null,null,"2011-09-15","2013-11-29"]
[6434,540124,"   Core part: HSDPA Dual-Band Multi-Carrier combinations","HSDPA_DB_MC-Core",2,"Rel-11","R4,R2","2011-12-09","2012-09-07",1,"RP-111746","RP-120987","Ericsson","muhammad.kazmi@ericsson.com","RP#57 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101; 25.104; 25.141; 25.317 replaced by new 25.327",54,28,null,null,"2011-12-07","2012-09-04"]
[6437,480004,"(Small) Technical Enhancements and Improvements for Rel-11","TEI11",1,"Rel-11","SP,CP,RP,GP","2010-06-18","2012-09-20",1,"-","-","-","-","SP#50 EU-Alert is introduced under Public Warning System in parallel with the already existing ETWS and CMAS. SA1 22.268 CR#9r1 adds EU-ALERT specific requirements & CT1 23.041 CRs#","-",48,25,null,null,"2009-06-02","2010-12-13"]
[6442,460024,"Study on Non Voice Emergency Services","FS_NOVES",1,"Rel-11","S1","2009-12-10","2011-09-21",1,"SP-090897","-","Qualcomm","dwilliams@qualcomm.com","SP#53 completed. Spin-off Feature UID_500030 Non Voice Emergency Services (NOVES) ",22.870999999999999,46,24,null,null,"2009-12-06","2011-08-24"]
[6445,410041,"Study on IMS Evolution","FS_eIMS",1,"Rel-11","S2","2008-09-18","2011-12-14",1,"SP-100360","-","China Mobile","Li Gang (ligangyf@chinamobile.com), Yu Qing (yuqing@chinamobile.com)","SP#54 completed",23.812000000000001,41,21,null,null,"2008-09-15","2011-11-28"]
[6447,440048,"Study on IPv6 Migration","FS_IP6M",1,"Rel-11","S2","2009-06-04","2011-06-08",1,"SP-090362","-","China Mobile","Li Lianyuan (lilianyuan@chinamobile.com), Liu Hong (liuhongyfw@chinamobile.com)","SP#52 completed",23.975000000000001,44,23,null,null,"2009-05-31","2011-05-26"]
[6450,380084,"Study on UTRAN key management enhancements","FS_UKM",1,"Rel-11","S3","2007-12-20","2012-03-07",1,"SP-090283","-","Ericsson","karl.norrman@ericsson.com","SP#55 completed",33.859000000000002,38,21,null,null,"2007-12-20","2012-11-20"]
[6453,480047,"Study on Management of Converged Networks","FS_ManCon",1,"Rel-11","S5","2010-06-10","2012-09-12",1,"SP-100377","-","Nokia Siemens Networks","Jörg Schmidt (J.Schmidt@nsn.com)","SP#57 completed. TR 32.833v200 for Approval",32.832999999999998,48,25,null,null,"2010-05-26","2012-08-30"]
[6456,480015,"Study on impacts on UE-Core Network signalling from Energy Saving","FS_UE-CN_ES",1,"Rel-11","C1","2010-06-04","2011-06-03",1,"CP-100330","-","NEC","gottfried.punz@nw.neclab.eu ","CP#52 completed. Linked to SA5 UID_430044 (FS_OAM-ESM) & UID_470037 (OAM-ES), RAN3 UID_470015 (FS_Energy_LTE), RAN1 UID_460016 (FS_Energy_UMTS)",24.826000000000001,48,25,null,null,"2010-05-29","2011-05-23"]
[6461,510034,"Study on HetNet mobility enhancements for LTE","FS_HetNet_eMOB_LTE",1,"Rel-11","R2,R1,R3,R4","2011-03-18","2012-09-07",1,"RP-110709","RP-121085","Alcatel-Lucent","sudeep.palat@alcatel-lucent.com","RP#57 completed. TR 36.839 v100 for Information & Approval","LTE 36.839",51,26,null,null,"2011-03-21","2012-09-03"]
[6464,530053,"Study on LTE Coverage Enhancements","FS_Cov_Enh_LTE",1,"Rel-11","R1,R2","2011-09-19","2012-06-15",1,"RP-120225","RP-120589","China Telecom","Peng Chen (chenpeng@ctbri.com.cn)","RP#56 completed. TR 36.824 v200 for Approval","LTE 36.824",53,27,null,null,"2011-09-19","2012-06-09"]
[6469,450015,"Study on RAN improvements for Machine-Type Communications","FS_NIMTC_RAN",1,"Rel-11","R2,R1,R3,R4","2009-09-18","2011-09-16",1,"RP-100330","RP-111052","Huawei","Jeff Gao (gaoyq@huawei.com)","RP#53 completed. TR 37.868v100 for Approval (No WID change: RAN overload only). Triggered by TR 22.868 Study on Facilitating Machine to Machine Communication in GSM and UMTS (M2M) UID_7027 and Rel-10 NIMTC UID_410030","UTRA; LTE 37.868",45,23,null,null,"2009-09-15","2011-09-06"]
[6472,510038,"Study on Interference analysis between 800~900 MHz bands","FS_B800_B900_Interf_LTE",1,"Rel-11","R4","2011-03-23","2012-06-15",1,"RP-111752","RP-120586","LG Uplus","Koo Yeon Sang (yskoo@lguplus.co.kr)","RP#56 completed. Impacts TR 37.804 Study on UMTS/LTE in 900 MHz band (Japan, Korea) UID_520018 ","UTRA; LTE impac37.804",51,26,null,null,"2011-03-21","2012-06-06"]
[6475,500015,"Study on HSDPA Multipoint Transmission","FS_HSDPA_MP_TX",1,"Rel-11","R1,R2,R3","2010-12-10","2011-09-16",1,"RP-101439","RP-111049","Nokia Siemens Networks","karri.ranta-aho@nsn.com ","RP#53 completed","UTRA 25.872",50,26,null,null,"2010-12-08","2011-09-09"]
[6478,510035,"Deleted - Study on Enhanced Uplink Transmission for LTE","FS_eUL_TX_LTE",1,"Rel-11","R1","2011-03-22","2012-06-15",1,"RP-120259","RP-120585","Huawei","Yongxing Zhou","RP#56 stopped. RP-120856 discussion: most content moved to Rel-11 Coordinated Multi-Point Operation for LTE – Uplink (COMP_LTE_UL) and RAN1 has no time to look at it","LTE 36.8xy",51,26,"RP-56","PCG-29","2011-03-21","2012-06-18"]
[6480,390073,"Enhancements for Multimedia Priority Service","eMPS",1,"Rel-10","S1,S2,C4,C3,C1","2006-03-13","2011-03-18",1,"SP-080051","-","Telcordia","jgarraha@telcordia.com","CP#51 completed. SP#49 moved Stage 1 from Rel-9 & Completed Stage 2. SP#40 Stage 1 completed. Continuation of Rel-8 Feature PRIOR (UID_340044)","-",39,21,null,null,"2003-03-28","2011-03-01"]
[6483,460329,"      Stage 2 on eMPS for CSFB","ePRIOR-St2",3,"Rel-10","S2","2009-12-10","2010-09-23",1,"SP-100647","-","Telcordia, NTT DoCoMo","Vijay Varma, Katsutoshi Nishida","22/01: acronym modified","23.002; 23.203; 23.221; 23.228; 23.272; 23.401",46,24,null,null,"2009-12-06","2015-01-22"]
[6487,490008,"   Stage 3 on enhancements for Multimedia Priority Service","eMPS-CN",2,"Rel-10","C4,C3,C1","2010-09-17","2011-03-18",1,"CP-100878","-","Ericsson","Philip.hodges@ericsson.com","CP#51 completed","Stage 3",49,25,null,null,"2010-09-01","2010-12-09"]
[6491,410030,"Network Improvements for Machine-Type Communications","NIMTC",1,"Rel-10","S1,S2,S5,C1,C4,C6,G2,R2,R3,R5,G3new","2008-09-18","2013-11-22",1,"SP-100863","-","KPN","toon.norp@tno.nl","Triggered by Rel-8 UID_7027 Study on Facilitating Machine to Machine Communication in GSM and UMTS (FS_M2M) TR 22.868","-",41,21,null,null,"2008-09-15","2011-02-28"]
[6496,510040,"   Charging for Network Improvements for Machine-Type Communication","NIMTC-CH",2,"Rel-10","S5","2011-03-21","2011-03-23",1,"SP-110136","-","Ericsson","patrik.teppo@@ericsson.com","SP#51 completed","32.251; 32.298; 32.299",51,26,null,null,"2011-02-22","2011-03-22"]
[6499,480205,"      Deleted - CT3 part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",3,"Rel-10","C3","2010-06-04","2011-06-03",1,"CP-110442","-","Ericsson","mikael.wass@ericsson.com","CP#52 stopped (SA2 decided to move impact from CT3 to CT4). Updated WID CP-110147=>CP-110442 (no CT3 impact)","29.212; 29.213; 29.215",48,25,"CP-52","PCG-27","2010-05-26","2011-06-01"]
[6502,490003,"   GERAN part of Network Improvements for Machine-Type Communications (Stage 3)","NIMTC",2,"Rel-10","G2","2010-09-03","2011-09-02",1,"GP-101647","-","Vodafone, Ericsson","leo.patanapongpibul@vodafone.com, john.diachina@ericsson.com","GP#51 completed. GP#47 approved WID","44.018; 44.060",47,25,null,null,"2010-09-05","2011-09-05"]
[6505,570004,"   UE Conformance Test Aspects - Network Improvements for Machine-Type Communications","NIMTC-UEConTest",2,"Rel-10","R5","2012-09-11","2013-06-14",1,"RP-121124","RP-130465","Ericsson","calle.hagenfeldt@ericsson.com","RP#60 completed. Testing for CT1 part of Stage 3 UID_480105, RAN mechanisms to avoid CN overload due to MTC UID_490024","34.123-1; 34.123-2; 34.123-3; 36.523-1; 36.523-2; 36.523-3 ",57,29,null,null,"2012-09-05","2013-06-03"]
[6507,430135,"   Stage 2 for Multi Access PDN Connectivity","MAPCON",2,"Rel-10","S2","2009-03-13","2010-09-23",1,"SP-090659","-","Telecom Italia","ivano.guardini@telecomitalia.it","SP#49 completed. Triggered by TR 23.861 UID_410043 FS_MAPIM. Stage 1 in Rel-9 22.278 (6.2 - IP session control)","23.237; 23.401; 23.402",43,22,null,null,"2010-10-25","2010-10-25"]
[6510,500204,"      CT1 aspects of Multi Access PDN Connectivity","MAPCON-St3",3,"Rel-10","C1","2010-12-10","2011-03-18",1,"CP-100709","-","ZTE","Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn)","CP#51 completed","24.302; 24.312",50,26,null,null,"2010-10-25","2011-02-28"]
[6514,450029,"   Stage 2 - IMS Inter-UE Transfer enhancements","IMS_SC_eIDT",2,"Rel-10","S2","2009-09-24","2010-09-23",1,"SP-100167","-","Huawei","Lee Valerius (lvalerius@huawei.com)","SP#49 completed","23.237; 23.292; new 23.831",45,23,null,null,"2009-09-21","2010-09-06"]
[6518,450031,"   Stage 1 for CPM-SMS","CPM-SMS",2,"Rel-10","S1","2009-09-24","2010-03-25",1,"SP-090615","-","China Mobile","Qing Huang","SP#47 completed. External requirements (Stage 1 in OMA-RD-CPM-V1_0-20090310-C)",22.34,45,23,null,null,"2009-09-08","2010-03-09"]
[6522,450034,"   Stage 1 for Completion of Communications on Not Logged-in","CCNL",2,"Rel-10","S1","2009-09-24","2009-09-24",1,"SP-090493","-","Deutsche Telekom","Kurt Bischinger","SP#45 completed","22.173 CR#0056r1",45,23,null,null,"2009-09-08","2010-10-01"]
[6523,470002,"   CT1 part of Stage 3 for Completion of Communications on Not Logged-in","CCNL",2,"Rel-10","C1","2010-03-19","2011-03-18",1,"CP-100335","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#51 completed","24.173; 24.642",47,24,null,null,"2010-03-17","2011-02-14"]
[6529,450040,"   OAM&P for Local IP Access and Selected Internet IP Traffic Offload","LIPA_SIPTO",2,"Rel-10","S5","2009-09-24","2011-03-23",1,"SP-110131","-","Huawei, China Mobile","Zou Lan (zlan@huawei.com), Chen Gang (chengang@chinamobile.com)","SP#51 completed. Updated WID SP-100696=>SP-110131","32.581; 32.582; 32.584; 32.591; 32.592; 32.642; 32.646; 32.772; 32.782",45,23,null,null,"2009-09-08","2011-03-17"]
[6530,460039,"   Charging for Local IP Access and Selected Internet IP Traffic Offload","LIPA_SIPTO",2,"Rel-10","S5","2009-12-10","2011-03-23",1,"SP-110131","-","Huawei, China Mobile","shan.mingjun@huawei.com, Ai Chen (chenai@chinamobile.com)","SP#51 completed. Updated WID SP-100696=>SP-110131",32.250999999999998,46,24,null,null,"2009-09-08","2011-03-17"]
[6536,450038,"   Stage 2/3 for SIPTO for macro networks","SIPTO",2,"Rel-10","S2,C4,C1","2009-09-24","2011-03-18",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","-","-",45,23,null,null,"2009-09-08","2010-12-01"]
[6538,480007,"      Stage 3 for SIPTO for macro networks","SIPTO",3,"Rel-10","C4,C1","2010-06-04","2011-03-18",1,"CP-110091","-","Huawei","Caixia Qi (qcxmay@huawei.com)","CP#51 completed. Updated WID CP-100419=>CP-110091","-",48,25,null,null,"2010-05-26","2011-03-08"]
[6541,450041,"IP Flow Mobility and seamless WLAN offload","IFOM",1,"Rel-10","S2,S1,S5,C1,C3","2009-09-24","2011-03-23",1,"SP-100089","-","Qualcomm","Gerardo Giaretta (gerardo@qualcomm.com)","SP#51 completed. Triggered by Rel-10 TR 23.861 (UID_410043 Study on Multi Access PDN connectivity and IP flow mobility - MAPIM)","-",45,23,null,null,"2009-09-08","2011-03-10"]
[6545,480009,"   Stage 3 for IP Flow Mobility and seamless WLAN offload","IFOM-CT",2,"Rel-10","C1,C3","2010-06-04","2011-03-18",1,"CP-100715","-","Qualcomm","Patrick Stupar (pstupar@qualcomm.com)","CP#51 completed","Stage 3",48,25,null,null,"2010-05-26","2010-12-09"]
[6549,450045,"   TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",2,"Rel-10","S2,S4","2010-01-07","2010-09-23",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#48 completed","new 23.860",45,23,null,null,"2009-09-08","2010-05-26"]
[6550,450145,"   SA4 review of TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",2,"Rel-10","S4","2009-09-24","2010-12-15",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#50 completed","new 23.860",45,23,null,null,"2009-09-08","2010-12-01"]
[6556,490207,"      CT3 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA-CN",3,"Rel-10","C3","2010-09-17","2011-06-03",1,"CP-100702","-","Ericsson","philip.hodges@ericsson.com","CP#52 completed","29.162; 29.163; 29.213; 29.235; 29.292",49,25,null,null,"2010-09-01","2011-05-17"]
[6557,490307,"      CT1 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA-CN",3,"Rel-10","C1","2010-09-17","2011-06-03",1,"CP-100702","-","Ericsson","philip.hodges@ericsson.com","CP#52 completed",24.228999999999999,49,25,null,null,"2010-09-01","2011-05-23"]
[6563,460128,"   Stage 2 for Optimal Media Routing","OMR",2,"Rel-10","S2","2010-03-25","2010-03-25",1,"SP-090803","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com","SP#47 completed",23.228000000000002,46,24,null,null,"2009-12-06","2010-02-26"]
[6565,480110,"      CT3 part of Stage 3 for Optimal Media Routeing","OMR",3,"Rel-10","C3","2010-06-04","2011-06-03",1,"CP-110134","-","Alcatel-Lucent","jim.calme@alcatel-lucent.com","CP#52 completed","29.162; 29.163; 29.165; 29.235; new 29.079",48,25,null,null,"2010-05-26","2011-05-17"]
[6568,500013,"   Charging for Optimal Media Routing","OMR",2,"Rel-10","S5","2010-12-16","2011-06-08",1,"SP-100772","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#52 completed. Stage 3: Linked to CT3 TS 29.079 OMR within the IMS¦Stage 3 (UID_480110)","32.260; 32.298; 32.299",50,26,null,null,"2010-11-27","2011-05-16"]
[6572,500005,"   Stage 3 for IMS Emergency Session Enhancements","IESE",2,"Rel-10","C1","2010-12-10","2011-06-03",1,"CP-100880","-","Deutsche Telekom","reinhard.lauster@t-mobile.at ","CP#52 completed",24.228999999999999,50,26,null,null,"2010-10-25","2011-05-23"]
[6576,490109,"      CT4 part of Stage 3 for S2b Mobility based on GTP","SMOG-St3",3,"Rel-10","C4","2010-09-17","2011-03-18",1,"CP-100644","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#51 completed","23.003; 23.007; 23.008; 29.273; 29.274; 29.281; 29.303",49,25,null,null,"2010-09-01","2011-03-18"]
[6579,500006,"Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases","PEST",1,"Rel-10","S2,C3","2010-10-12","2011-03-18",1,"SP-110196","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","CP#51 completed. SP#50 Stage 2 completed. Triggered by the SA1,SA2 Rel-10 TR 23.813 Study on Policy solutions and enhancements (FS_PP) UID_440047. Provides Video Call seamless service continuity for 3G/LTE terminal user","-",50,26,null,null,"2010-11-26","2011-03-19"]
[6581,500206,"   CT3 aspects of Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases","PEST-CT3",2,"Rel-10","C3","2010-12-10","2011-03-18",1,"CP-100860","-","ZTE","zhou.xiaoyun@zte.com.cn","CP#51 completed","29.212; 29.213; 29.214; 29.215",50,26,null,null,"2010-11-26","2011-03-01"]
[6584,470229,"   LI for CRS (Customized Ringing Signal)","LI10",2,"Rel-10","S3","2010-03-25","2011-06-08",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#52 completed","33.106; 33.107; 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[6590,470829,"   LI for LCLS (Local Call Local Switch)","LI10",2,"Rel-10","S3","2010-03-25","2011-03-23",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#51 completed","33.106; 33.107; 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[6592,470034,"HTTP-based Streaming and Download Services","HTTP_SDS",1,"Rel-10","S4,IETF","2010-03-25","2011-09-21",1,"SP-100032","-","Qualcomm","Thomas Stockhammer (c_tstock@qualcomm.com)","SP#52 completed. Work to enhance UID_430038 Rel-9 PSS and MBMS extensions","-",47,24,null,null,"2010-03-10","2011-05-26"]
[6595,480040,"PSS and MBMS enhancements","MBS_Enh",1,"Rel-10","S4","2010-06-10","2011-03-23",1,"SP-100305","-","Ericsson","Markus.Kampmann@ericsson.com","SP#51 completed. Linked to Rel-9 Feature UID_430038 PSS and MBMS extensions (PMA-MBS_Ext). ","26.234; 26.346",48,25,null,null,"2010-05-28","2011-03-02"]
[6599,460032,"   Rel-10 Network Infrastructure Management","OAM10-NIM",2,"Rel-10","S5","2009-12-10","2011-09-21",1,"-","-","-","-","umbrella BB","-",46,24,null,null,"2009-12-01","2009-12-12"]
[6603,480042,"      IRP Overview, Profiles & Usage Guide","OAM-NIM-IRP_OPU",3,"Rel-10","S5","2010-06-10","2011-06-08",1,"SP-110277","-","Nokia Siemens Networks","Jörg Schmidt (J.Schmidt@NSN.com)","SP#52 completed. Updated WID SP-100777=>SP-110277","new 32.103",48,25,null,null,"2010-05-26","2011-06-06"]
[6606,460034,"   Rel-10 Self-Organizing Networks (SON) - OAM aspects","OAM10-SON",2,"Rel-10","S5","2009-12-10","2011-06-08",1,"-","-","-","-","umbrella BB","-",46,24,null,null,"2009-12-01","2009-12-12"]
[6608,460036,"      SON Self-healing management","LTE-SON-OAM_SH",3,"Rel-10","S5","2009-12-10","2011-03-23",1,"SP-110150","-","ZTE","zhu.weihong@zte.com.cn","SP#51 completed. WID updated SP-100776=>SP-110150. Work moved to Rel-10 after split of the Rel-9 UID_390007 SON self-optimization (removed Self-Healing handling)","32.522; 32.526; 32.762; 32.766; new 32.541",46,24,null,null,"2009-12-01","2011-03-22"]
[6611,470039,"   Rel-10 Performance Management","-",2,"Rel-10","S5,C4","2010-03-25","2011-06-08",1,"-","-","-","-","umbrella BB","-",47,24,null,null,"2010-02-12","2010-02-12"]
[6614,470042,"      Management of UE based network performance measurements","OAM-PM-UE",3,"Rel-10","S5,C4","2010-03-25","2011-06-08",1,"SP-100612","-","Huawei, Nokia Siemens Networks, Ericsson","Zou Lan (zlan@huawei.com), gyula.bodog@nsn.com, ulf.hubinette@ericsson.com","SP#52 completed. Stage 2/3. Linked to UID_460003 Minimization of drive tests for E-UTRAN and UTRAN (MDT_UMTSLTE)","-",47,24,null,null,"2010-02-12","2011-03-22"]
[6617,470043,"      3G HNB and LTE HeNB Subsystem performance measurements","OAM-PM-HeNS",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100081","-","China Mobile","Chen Gang (chengang@chinamobile.com)","SP#51 completed","32.582; 32.592; new (32.452; 32.453)",47,24,null,null,"2010-03-08","2011-03-09"]
[6622,490010,"   CT1 part - AoC enhancements (Stage 3)","eAoC",2,"Rel-10","C1","2010-09-17","2011-06-03",1,"CP-100645","-","Deutsche Telekom","reinhard.lauster@t-mobile.at","CP#52 completed. SA1 Stage 1 in 22.115, 22.173, 22.024. Add mobile-specific CAI format and volume charging elements. Extensions to existing AoC XML",24.646999999999998,49,25,null,null,"2010-09-07","2011-05-23"]
[6626,480114,"   Further improvements of II-NNI Stage 3","II-NNI2",2,"Rel-10","C3","2010-06-04","2011-03-18",1,"CP-100326","-","Orange","beata.dobrowolska@orange-ftgroup.com","CP#51 completed",29.164999999999999,48,25,null,null,"2012-04-20","2012-04-20"]
[6630,490011,"AT Commands for USIM Application Toolkit (USAT)","AT_UICC",1,"Rel-10","C1","2010-09-17","2011-03-18",1,"CP-100646","-","ST-Ericsson","magnus.mk.karlsson@stericsson.com ","CP#51 completed",27.007000000000001,49,25,null,null,"2010-05-29","2011-02-14"]
[6633,500007,"Introduction of Smart Card Web Server launch functionality","SCWS_L",1,"Rel-10","C6","2010-12-10","2011-03-18",1,"CP-100883","-","Telecom Italia","davide.pratone@telecomitalia.it","CP#51 completed. Define a solution which allows enabling to launch Smart Card Web Server servicES in CP-150an easy and simple manner",31.102,50,26,null,null,"2010-11-28","2011-03-03"]
[6635,500010,"Single Radio Voice Call Continuity (SRVCC) enhancements (Stage 3)","eSRVCC",1,"Rel-10","C1,C4,IETF","2010-12-10","2012-12-07",1,"CP-100881","-","China Mobile","Jiang Y (jiangyi@chinamobile.com)","Triggered by SA2 TR 23.856 Study on Single Radio Voice Call Continuity enhancements (FS_eSRVCC) UID_440049","-",50,26,null,null,"2010-10-25","2013-02-21"]
[6638,521003,"   (IETF) CT1 part of Stage 3 for SRVCC enhancements (RFC 6809)","eSRVCC",2,"Rel-10","C1-IETF","2010-12-10","2012-12-07",1,"CP-100881","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#58 completed","RFC 6809 (was draft-ietf-sipcore-proxy-feature)",52,27,null,null,"2011-06-20","2013-02-21"]
[6641,570005,"   Conformance test aspects SRVCC in alerting phase","aSRVCC-UEConTest",2,"Rel-10","R5","2012-09-11","2013-03-01",1,"RP-121700","RP-130042","NTT DoCoMo","Takao.Shimizu.rp@nttdocomo.com","RP#59 completed","36.523-1; 36.523-2; 36.523-3; 34.229-1; 34.229-2; 34.229-3",57,29,null,null,"2012-09-05","2013-02-27"]
[6644,500212,"   CT3 part of PCRF failure and restoration","PCRF_FR",2,"Rel-10","C3","2010-12-10","2011-03-18",1,"CP-100703","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","CP#51 completed","Stage 3 29.212; 29.213; 29.214; 29.215",50,26,null,null,"2010-10-25","2011-03-01"]
[6649,510009,"Mobile Terminating Roaming Forwarding with pre-paging","MTRF",1,"Rel-10","C4","2011-03-16","2011-06-03",1,"CP-110093","-","Ericsson","philip.hodges@ericsson.com","CP#52 completed. Provides Stage 2/3 alternative solution to Mobile Terminating Roaming Retry to solve roaming events during paging, in particular to support CSFB. Hence, no new Stage 1 requirements exist","Stage 2/3: 23.012; 23.018; 23.116; 29.002",51,26,null,null,"2011-02-22","2011-03-08"]
[6653,550006,"Deleted - Testing for Terminal support of Rel-10 USIM, ISIM and USAT features","USIM_R10_Test",1,"Rel-10","C6","2012-03-05","2013-12-03",1,"CP-120396","-","Gemalto","Denis.Praca@gemalto.com","CP#62 stopped (at 70% completion 06/13). Testing for New featurES in CP-150Rel-10 specifications for USIM, ISIM applications and USIM Application Toolkit (USAT) in TS 31.102, 31.103, 31.111","31.121; 31.124; New 31.ABC (Conformance Testing of specific features)",55,28,"CP-62","PCG-32","2012-02-22","2013-06-06"]
[6657,440023,"   Deleted - CT3 aspects of Local Call Local Switch","LCLS-CN",2,"Rel-10","C3","2009-05-29","2010-09-16",1,"CP-090812","-","Vodafone","David.Hutton@vodafone.com","CP#49 stopped. Result of study TR 23.889: no CT3 specification impact","-",44,23,"CP-49","PCG-25","2009-05-13","2010-09-01"]
[6660,480002,"Tightened Link Level Performance Requirements for Single Antenna MS","TIGHTER",1,"Rel-10","G1,G2,C1,G3new","2010-09-03","2013-03-01",1,"GP-101083","-","Renesas Mobile","carsten.juncker@renesasmobile.com","GP#46 approved WID","GERAN",46,25,null,null,"2010-05-27","2013-03-16"]
[6661,480102,"   CT1 part for TIGHTER","TIGHTER",2,"Rel-10","C1","2010-09-03","2011-06-03",1,"GP-101083","-","Renesas Mobile","marko.niemi@renesasmobile.com","CP#52 completed",24.007999999999999,46,25,null,null,"2010-05-27","2011-05-23"]
[6666,490201,"   CT1 part of Stage 3 for Support of Multi-Operator Core Network by GERAN","MOCN-GERAN",2,"Rel-10","C1","2010-05-21","2010-12-10",1,"GP-101443","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","CP#50 completed","24.008 CR#1644",47,25,null,null,"2010-05-27","2011-03-04"]
[6668,490002,"Enhancements of Iur-g interface","eIurg",1,"Rel-10","G2,R3","2010-09-03","2011-06-03",1,"GP-101758","-","China Mobile, ZTE","Ms Juan Deng (dengjuan@chinamobile.com), Xinhui Wang (wangxinhui@zte.com.cn)","GP#47 approved WID","GERAN.UTRA",47,25,null,null,"2010-09-05","2011-05-26"]
[6671,380077,"1.28 Mcps TDD Repeater","RANimp-Repeaters1.28TDD",1,"Rel-10","R4","2007-12-04","2010-03-19",1,"RP-071003","RP-100039","RITT","qinyan@chinattl.com","RP#47 completed","UTRA 25.113; New 25.116; 25.153 (testing)",38,21,null,null,"2007-12-17","2010-03-09"]
[6676,470012,"Multi-User Multiple-Input and Multiple-Output (MU-MIMO) for 1.28Mcps TDD","MUMIMO_LCR_TDD",1,"Rel-10","R1,R2,R3,R4","2010-03-19","2011-06-03",1,"RP-100347","-","CATT","Yanping Xing (xingyanping@datangmobile.cn)","RP#52 completed","UTRA",47,24,null,null,"2010-03-19","2010-03-23"]
[6680,450127,"   AGNSS Minimum Performance Specification Development","AGNSSPerf_UTRAN",2,"Rel-10","R4","2009-09-18","2010-12-10",1,"RP-100363","RP-101078","Thales","Michel.monnerat@thalesaleniaspace.com","RP#50 completed","new 25.172",45,23,null,null,"2009-09-15","2010-12-08"]
[6684,460015,"Four carrier HSDPA","4C_HSDPA",1,"Rel-10","R1,R2,R3,R4,R5","2009-12-04","2013-09-06",1,"RP-100991","-","Qualcomm","Arjun Bharadwaj (arjunb@qualcomm.com)","RP#53 completed","UTRA",46,24,null,null,"2009-11-30","2011-09-12"]
[6687,540006,"   Test part: Four carrier HSDPA","4C_HSDPA-UEConTest",2,"Rel-10","R5","2011-12-02","2013-09-06",1,"RP-111565","RP-130940","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#61 completed","34.108; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",54,28,null,null,"2011-11-24","2013-08-29"]
[6688,470013,"Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver","2ant_UE_LCR_TDD",1,"Rel-10","R4","2010-03-19","2011-06-03",1,"RP-100168","-","TD Tech","dafei.wang@td-tech.com","Stage 3. RP#52 completed","UTRA",47,24,null,null,"2010-03-19","2011-06-01"]
[6693,530039,"   Test part: Automatic Neighbour Relation (ANR) for UTRAN","ANR_UTRAN-UEConTest",2,"Rel-10","R5","2011-09-19","2012-12-07",1,"RP-120599","RP-121529","Ericsson","leif.mattisson@ericsson.com","RP#58 completed","34.108; 34.123-1; 34.123-2; 34.123-3",53,27,null,null,"2011-09-09","2012-11-28"]
[6695,480121,"   Core part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA","DB_DC_HSDPA-Core",2,"Rel-10","R4,R2","2010-06-04","2011-06-03",1,"RP-100657","RP-110523","AT&T","Vince Spatafora (vs5785@att.com)","RP#52 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101; 25.104; 25.141; 25.317 replaced by new 25.327",48,25,null,null,"2010-06-03","2011-05-24"]
[6699,480122,"   Perf. part: MIMO operation with non-MIMO coexistence in HSDPA","MIMO_HSDPA-Perf",2,"Rel-10","R4","2010-06-04","2011-06-03",1,"RP-100993","RP-110525","Qualcomm","Heechoon Lee","RP#52 completed","25.101; 25.141",48,25,null,null,"2010-06-03","2011-05-27"]
[6702,460007,"Carrier Aggregation for LTE","LTE_CA",1,"Rel-10","R1,R2,R3,R4,R5","2009-12-04","2012-12-07",1,"RP-100661","-","Nokia","Asbjorn.grovlen@nokia.com","-","LTE",46,24,null,null,"2009-11-30","2011-03-14"]
[6707,460108,"   Core part: Enhanced Downlink Multiple Antenna Transmission for LTE","LTE_eDL_MIMO-Core",2,"Rel-10","R1,R2,R4","2009-12-04","2011-03-18",1,"RP-100196","RP-110067","NTT DoCoMo","Hidekazu Taoka (taoka@nttdocomo.com)","RP#51 completed. RP#56 new RAN4 TR 36.807 v200 for Approval","36.101; 36.104; 36.133; 36.201; 36.211; 36.212; 36.213; 36.300; 36.306; 36.321; 36.331; new RAN4 36.807",46,24,null,null,"2009-11-30","2012-06-07"]
[6710,460009,"Uplink Multiple Antenna Transmission for LTE","LTE_UL_MIMO",1,"Rel-10","R1,R2,R4,R5","2000-01-03","2013-03-01",1,"RP-100959","-","Huawei","Mattias.wennstrom@huawei.com","-","LTE",46,24,null,null,"2009-11-30","2011-09-12"]
[6711,460109,"   Core part: UL multiple antenna transmission for LTE","LTE_UL_MIMO-Core",2,"Rel-10","R1,R2,R4","2000-01-03","2001-06-29",1,"RP-100959","RP-110537","Huawei","Mattias.wennstrom@huawei.com","RP#52 completed. TR 36.817 v110 for Approval. RP#56 new TR 36.807 v200 for Approval","36.101; 36.104; 36.133; 36.201; 36.211; 36.212; 36.213; 36.300; 36.306; 36.321; 36.331; new RAN4 (36.807; 36.817)",46,24,null,null,"2009-11-30","2012-06-07"]
[6715,460113,"   Core part: Relays for LTE","LTE_Relay-Core",2,"Rel-10","R1,R2,R4","2009-12-04","2011-06-03",1,"RP-110911","RP-110540","Ericsson","christian.hoymann@ericsson.com","RP#52 completed. Updated WID RP-101417=>RP-101911 (contains only Core part completed in Rel-10). Open RAN4 Core & Perf parts moved to new Rel-11","36.201; 36.211; 36.212; 36.213; 36.300; 36.321; 36.323; 36.331; New RAN1 36.216",46,24,null,null,"2009-11-30","2012-06-14"]
[6720,500138,"      Security for LTE Relay Nodes (Stage 2)","LTE_Relay-Sec",3,"Rel-10","S3","2010-12-16","2011-03-22",1,"SP-100733","-","Qualcomm","Adrian Escott (aescott@qualcomm.com)","SP#51 completed (impacting Stage 3 in CT and RAN)","33.401 (CR#0437.0438); CT1 24.301; CT4 (29.272; 29.274); CT6 31.102; RAN2 (36.331; 36.323); RAN3 36.413",50,26,null,null,"2010-11-25","2011-02-14"]
[6723,470007,"Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE","eICIC_LTE",1,"Rel-10","R1,R2,R3,R4,R5","2010-03-19","2014-06-13",1,"RP-100383","-","China Mobile","Xiaodong XU (xuxiaodong@chinamobile.com)","RP#56 completed","LTE",47,24,null,null,"2010-03-19","2011-03-14"]
[6726,550001,"   Test part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE","eICIC_LTE-UEConTest",2,"Rel-10","R5","2012-03-05","2014-06-13",1,"RP-120217","RP-140766","Qualcomm","Anjali Mishra (ajha@qualcomm.com)","RP#64 completed","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-1; 36.523-2; 36.523-3",55,28,null,null,"2012-02-23","2014-06-10"]
[6729,470208,"   Perf. part: LTE TDD in 2600MHz for US","LTE_TDD_2600_US-Perf",2,"Rel-10","R4","2010-03-19","2010-09-17",1,"RP-101003","RP-100783","Clearwire","michael.hart@clearwire.com","RP#49 completed","36.101; 36.104; 36.133; 36.141; 36.307; 37.104; 37.141; new 36.812",47,24,null,null,"2010-03-19","2010-09-16"]
[6734,520012,"   Test part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America","S_Band_LTE_ATC_MSS-UEConTest",2,"Rel-10","R5","2011-06-07","2011-12-09",1,"RP-110623","RP-111444","DBSD","Mariam.Sorond@ico.com","RP#54 completed","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-1; 36.523-2; 36.523-3",52,27,null,null,"2011-05-23","2011-11-29"]
[6737,470210,"   Perf. part: Adding L-Band (Band 24) LTE for ATC of MSS in North America","L_Band_LTE_ATC_MSS-Perf",2,"Rel-10","R4","2010-03-19","2011-06-03",1,"RP-101284","RP-110548","LightSquared","Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com","RP#52 completed","34.121-1; 36.101; 36.104; 36.113; 36.124; 36.133; 36.141; 36.307; 36.521-1; 36.813",47,24,null,null,"2010-03-19","2011-05-24"]
[6738,510015,"   Test part: Adding L-Band (Band 24) LTE for ATC of MSS in North America","L_Band_LTE_ATC_MSS-UEConTest",2,"Rel-10","R5","2011-03-18","2011-09-16",1,"RP-110777","RP-110980","LightSquared","masoud.olfat@lightsquared.com","RP#53 completed","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-2",51,26,null,null,"2011-03-10","2011-09-06"]
[6742,480127,"   Core part: Further enhancements to MBMS for LTE","MBMS_LTE_enh-Core",2,"Rel-10","R2,R3","2010-06-04","2011-03-18",1,"RP-101244","RP-110083","Huawei","Ms Zhao Junhui (zhaojh@huawei.com)","RP#51 completed","25.446; 36.300; 36.321; 36.322; 36.323; 36.331; 36.440; 36.441; 36.442; 36.443; 36.444; 36.445",48,25,null,null,"2010-06-04","2011-03-14"]
[6745,380073,"   Core part: UMTS/LTE 3500 MHz","RInImp8-UMTSLTE3500",2,"Rel-10","R4,R2,R3","2007-11-30","2011-09-16",1,"RP-091380","RP-110987","Ericsson","johan.skold@ericsson.com","RP#53 completed. TR 37.801v200 for Approval","25.101; 25.104; 25.113; 25.133; 25.141; 25.307; 25.307; 25.331; 25.461; 25.463; 34.124; 36.101; 36.104; 36.113; 36.141; 36.331; new 37.801",38,21,null,null,"2007-12-17","2011-09-09"]
[6751,470005,"HNB and HeNB Mobility Enhancements","HNB_HENB_mob_enh",1,"Rel-10","R3,R2,R5","2010-03-19","2012-12-07",1,"RP-110183","-","Alcatel-Lucent","Martin,Warner@alcatel-lucent.com","-","UTRA; LTE",47,24,null,null,"2010-03-19","2011-04-08"]
[6753,550002,"   Test part: HeNB Mobility Enhancements","HNB_HENB_mob_enh-UEConTest_LTE",2,"Rel-10","R5","2012-03-05","2012-12-07",1,"RP-120218","RP-121533","Qualcomm","Anjali Mishra (ajha@qualcom.com)","RP#58 completed","34.108; 34.123-1; 34.123-2; 34.123-3; 36.508; 36.523-1; 36.523-2; 36.523-3",55,28,null,null,"2012-02-23","2012-09-04"]
[6756,480224,"   Perf. part: Expanded 1900 MHz Band for UTRA and LTE","E1900-Perf",2,"Rel-10","R4,R2","2010-06-04","2011-06-03",1,"RP-100676","RP-110530","Sprint","nick.j.baustert@sprint.com","RP#52 completed","25.101; 25.104; 25.113; 25.133; 25.141; 25.461; 25.466; 36.101; 36.104; 36.113; 36.124; 36.133; 36.141; 36.307; 36.331; new 36.818",48,25,null,null,"2010-06-04","2011-05-24"]
[6760,480225,"   Perf. part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments","MSR_NC-Perf",2,"Rel-10","R4","2010-06-04","2011-09-16",1,"RP-101402","RP-110988","Ericsson","johan.skold@ericsson.com","RP#53 completed","25.141; 36.141; 37.141; 37.802",48,25,null,null,"2010-06-04","2011-09-12"]
[6764,440044,"(Small) Technical Enhancements and Improvements for Rel-10","TEI10",1,"Rel-10","SP,CP,RP,GP","2009-06-04","2011-03-23",1,"-","-","-","-","-","-",44,23,null,null,"2009-06-02","2011-03-07"]
[6765,521004,"(IETF) (Small) Technical Enhancements and Improvements for Rel-10 (draft-atarius-dispatch-meid-urn) --> RFC8464","TEI10_IETF",1,"Rel-10","C1-IETF","2009-06-04","2014-12-04",1,"-","-","Andrew Allen","Andrew Allen","Not completed internet-draft, waiting for draft-montemurro to complete; 26/6/19: 75%->100; 23/4/20: 100%->100","draft-atarius-dispatch-meid-urn",52,27,null,null,"2011-06-20","2020-04-23"]
[6769,370030,"   Deleted - Stage 1 for RED","RED",2,"Rel-10","S1","2007-03-12","2007-03-15",1,"SP-070133","-","NTT DoCoMo","takakurat@s1.nttdocomo.co.jp","SP#35 completed. SP#46 work stopped/abandoned","22.101 CR#0207",37,19,"SP-46","PCG-24","2007-03-29","2009-12-07"]
[6772,380162,"   Deleted - Stage 1 for N3GtoNSP","N3GtoNSP",2,"Rel-10","S1","2007-12-07","2009-09-24",1,"SP-070874","-","Telefónica O2","chris.friel@O2.com","SP#45 work stopped/abandoned",22.010999999999999,38,21,"SP-45","PCG-23","2007-12-13","2009-09-21"]
[6778,460010,"Deleted - Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements","FW_CPE_RF",1,"Rel-10","R4,R5","2009-12-04","2011-06-03",1,"RP-091432","-","Verizon Wireless","zheng.zhao@verizonwireless.com","RP#52 work stopped (lack of contributions). Add new power classES in CP-150E-UTRAN UL to allow CPE type applications to be operated at higher max output power","LTE",46,24,"RP-52","PCG-27","2009-11-30","2011-05-27"]
[6780,460210,"   Deleted - Test part: Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements","FW_CPE_RF-UEConTest",2,"Rel-10","R5","2009-12-04","2011-06-03",1,"RP-091432","RP-110504","Verizon Wireless","zheng.zhao@verizonwireless.com","RP#52 work stopped (lack of contributions)","36.521-1",46,24,"RP-52","PCG-27","2009-11-30","2011-05-27"]
[6783,470006,"Deleted - Enhanced Interference Management for Home NodeBs","HNB_IM",1,"Rel-10","R3","2010-03-19","2010-09-17",1,"RP-100392","RP-100754","Qualcomm","Andrei Radulescu (aradules@qualcomm.com)","RP#49 stopped (no further standardization needed). Ensure that Enhanced Interference Management methods identified in Rel-9 for HNBs do not fail in deployments with a large penetration of CSG-aware UEs","UTRA",47,24,"RP-49","PCG-25","2010-03-19","2010-09-09"]
[6787,370047,"   Use cases definition and service and system requirements","FS_EV_EPS-S1",2,"Rel-10","S1","2007-09-03","2008-12-11",1,"SP-070698","-","France Telecom","philippe.lottin@orange.com","SP#47 completed. TR 22.813-100 for Approval",22.812999999999999,37,19,null,null,"2007-10-04","2010-08-31"]
[6791,410040,"Study on LCS support in SAE for non-3GPP accesses","FS_LCS_n3GPP",1,"Rel-10","S1","2008-09-18","2010-03-25",1,"SP-080648","-","SK Telecom","jinhan.song@sktelecom.com ","SP#47 completed",22.814,41,21,null,null,"2008-09-15","2010-08-11"]
[6792,430030,"Study on Haptic Services","FS_Haptics",1,"Rel-10","S1","2009-03-12","2010-03-25",1,"SP-090664","-","SK Telecom","jinhan.song@sktelecom.com ","SP#47 completed. Covers Mobile/Fixed/Cordless/etc terminals. Haptic (human-machine tactile communication) extend service offering & richness of user experience beyond current visual & auditory senses",22.986999999999998,43,22,null,null,"2009-02-12","2010-08-11"]
[6796,470048,"Study on Single Radio Video Call Continuity for 3G-CS","FS_vSRVCC",1,"Rel-10","S2","2010-03-25","2010-09-23",1,"SP-100168","-","Samsung","Haris Zisimopoulos (haris.z@samsung.com)","SP#49 completed. TR 23.886v100 for Approval. Related to Rel-8 UID_350030 Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC). Study how to provide Video Call seamless service continuity for 3G/LTE terminal user",23.885999999999999,47,24,null,null,"2010-03-10","2010-09-15"]
[6799,480044,"Study on Improved Video Coding Support","FS_IVCS",1,"Rel-10","S4","2010-06-10","2011-03-23",1,"SP-100304","-","Nokia, ETRI","imed.bouazizi@nokia.com, jaihyung@etri.re.kr","SP#51 completed. Extends Rel-9 Improved Video Support for PSS and MBMS (UID_430039)",26.904,48,25,null,null,"2010-05-28","2011-02-18"]
[6805,480045,"Study on Alarm Correlation and Alarm Root Cause Analysis","FS_AC_ARCA",1,"Rel-10","S5","2010-06-10","2011-03-23",1,"SP-100775","-","Ericsson","edwin.tse@ericsson.com","SP#51 completed",32.832000000000001,48,25,null,null,"2010-05-26","2011-03-09"]
[6807,450013,"Study on Policy and Charging Rules Function (PCRF) failure and restoration","FS_PCRF-FR",1,"Rel-10","C3","2009-08-18","2010-09-17",1,"CP-090861","-","NEC","gottfried.punz@nw.neclab.eu ","CP#49 completed",29.815999999999999,45,23,null,null,"2009-09-08","2010-09-17"]
[{"$f":"A6810+1","v":6810},450014,"Study on Uplink Tx Diversity for HSPA","FS_UL-TxDiv-HSPA",1,"Rel-10","R4","2009-08-18","2010-06-04",1,"RP-090987","RP-100499","Qualcomm","Heechoon Lee (heechoon@qualcomm.com)","RP#48 completed","UTRA 25.863",45,23,null,null,"2009-09-15","2010-06-01"]
[6814,400037,"Deleted - Study on Unauthenticated PS Emergency Calls","FS_UAPSEC",1,"Rel-10","S1","2008-06-05","2010-03-25",1,"SP-080320","-","Nokia Siemens Networks","Juergen.Merkel@nsn.com","SP#47 work stopped/abandoned",22.984000000000002,40,21,"SP-47","PCG-24","2007-12-13","2010-03-09"]
[6818,0,"--- RELEASE 9 ---","-",1,"Rel-9","CP,GP,RP,SP","2000-01-01","2000-01-01",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[6819,400035,"Enhanced Home NodeB / eNodeB","EHNB",1,"Rel-9","S1,S2,S3,S5,C1,C6,R2,R3,R4,R5,GP","2008-06-05","2011-12-09",1,"SP-090214","-","T-Mobile","michael.kurz@t-mobile.at ","RP#54 Testing completed","UTRA; LTE",40,21,null,null,"2007-12-13","2011-11-29"]
[6823,450003,"   CT1 aspects - Support of Home NB and Home eNB enhancements","EHNB-CT1",2,"Rel-9","C1","2009-09-18","2010-12-10",1,"CP-090741","-","Qualcomm","Ramachandran Subramanian (rsubrama@qualcomm.com)","CP#50 completed (Roaming aspects for manual CSG selection, Support of temporary users and CSG membership changes, Support of user controlled and operator controlled lists)","23.122; 24.008; 24.285; 24.301",45,23,null,null,"2009-07-09","2010-11-25"]
[6826,430012,"   3G HNB and LTE HeNB OAM&P Type 1 Interface","HNB_eHNB-OAM_Type1",2,"Rel-9","S5","2009-03-12","2010-03-25",1,"SP-090208","-","Huawei","Zou Lan (zlan@huawei.com)","SP#47 completed","32.581; 32.582; 32.583; 32.584; New (32.591; 32.592; 32.593; 32.594)",43,22,null,null,"2009-03-09","2010-03-08"]
[6830,430025,"   Home NB and Home eNB enhancements - RAN3 aspects","EHNB-RAN3",2,"Rel-9","R3","2009-03-06","2009-12-04",1,"RP-090349","RP-091050","Alcatel-Lucent","Martin Warner (mw15@alcatel-lucent.com)","RP#46 completed (based on high priority items specified in RP-090995)","25.413; 25.467; 25.467; 25.468; 25.469; 25.469; 36.401; 36.413; New 25.444",43,22,null,null,"2009-03-10","2009-11-27"]
[6832,490020,"   Conformance Test Aspects – Home NB enhancements for FDD","EHNB-UTRA_FDD_UEConTest",2,"Rel-9","R5","2010-09-17","2011-12-09",1,"RP-111315","RP-111679","Huawei","trica_li@huawei.com","UTRA. RP#54 completed. Testing for UID_430026 Support of Home NB and Home eNB enhancements RAN2 aspects (25.304, 25.331, 25.367)","34.108; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",49,25,null,null,"2010-09-09","2011-12-07"]
[6838,410014,"   CT1 aspects of VAS4SMS Interface and Signalling Flow","VAS4SMS",2,"Rel-9","C1","2008-09-09","2009-12-04",1,"CP-090813","-","China Mobile","Wu Bin (wubin@chinamobile.com)","CP#46 completed",23.04,41,21,null,null,"2008-09-11","2009-12-02"]
[6841,380067,"Customized Ringing Signal","CRS",1,"Rel-9","S1,C1","2007-12-06","2009-12-03",1,"SP-080502","-","SK Telecom, China Mobile","Donghee Shim (SK Telecom), Jianping Zheng (China Mobile)","CP#48 completed","-",38,21,null,null,"2007-12-13","2010-05-28"]
[6845,380058,"   Stage 1 for Public Warning System","PWS",2,"Rel-9","S1","2007-12-06","2008-12-11",1,"SP-070876","-","T-Mobile","Mark.Younge@t-mobile.com","SP#42 completed",22.268000000000001,38,21,null,null,"2007-12-13","2008-12-05"]
[6846,440029,"   Stage 3 for Public Warning System","PWS-St3",2,"Rel-9","C1,C4","2009-05-29","2009-12-04",1,"CP-090437","-","Qualcomm","Ramachandran Subramanian (rsubrama@qualcomm.com)","RP#46 completed","-",44,23,null,null,"2009-05-13","2009-12-03"]
[6850,540005,"   Conformance Test Aspects – Public Warning System (PWS) – RAN aspects for LTE","PWS-RAN_UEConTest",2,"Rel-9","R5","2011-12-02","2012-12-07",1,"RP-111564","RP-121525","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#58 completed","36.508; 36.523-1; 36.523-2; 36.523-3",54,28,null,null,"2011-11-24","2012-12-04"]
[6853,430002,"   Stage 2 for Support of Personal Area Networks and Enhancements to Personal Network Management","PAN_EPNM",2,"Rel-9","C1","2009-03-06","2009-12-04",1,"CP-090435","-","Huawei","Lili Yang (kadyyang@huawei.com)","CP#46 completed",23.259,43,22,null,null,"2009-03-05","2009-11-16"]
[6857,430031,"   Multimedia Telephony (MMTel) Service and Supplementary Services - Online Charging and completion for Offline Charging (all supplementary services)","eMMTel-SS-CH",2,"Rel-9","S5","2009-03-12","2010-03-25",1,"SP-090196","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#47 completed","32.275; 32.298; 32.299",43,22,null,null,"2009-02-26","2010-03-08"]
[6859,440032,"   Stage 3 - Enhancements for Completion of Communications Supplementary service","eMMTel-CC",2,"Rel-9","C1","2009-05-30","2009-12-04",1,"CP-090490","-","France Telecom","Youssef.chadli@orange-ftgroup.com","CP#46 completed",24.641999999999999,44,23,null,null,"2009-05-13","2009-11-16"]
[6865,440060,"   User Data Convergence (UDC) Modelling and Management","UDC-MMAN",2,"Rel-9","S5","2009-06-04","2010-06-10",1,"SP-090309","-","T-Mobile, China Mobile, Ericsson","istvan.aba@t-mobile.at, lansizhong@chinamobile.com, miguel.a.garcia@ericsson.com","SP#48 completed","-",44,23,null,null,"2009-05-18","2010-05-26"]
[6868,410032,"IMS Services Centralization and Continuity","IMS_SCC",1,"Rel-9","S1,S2,C1","2008-09-18","2010-03-19",1,"SP-080633","-","NEC","joerg.swetina@neclab.eu","CP#47 completed","-",41,21,null,null,"2008-09-15","2010-03-04"]
[6872,440034,"      Stage 3 for IMS Service Continuity Enhancements: Service, Policy, Interactions and Inter UE Transfer","IMS_SCC-SPI",3,"Rel-9","C1","2009-05-29","2010-03-19",1,"CP-090440","-","Qualcomm","Roozbeh Atarius (ratarius@qualcomm.com)","CP#47 completed","24.216; 24.229; 24.237",44,23,null,null,"2009-05-13","2010-03-02"]
[6873,410135,"   Stage 2/3 for IMS Centralized Services","IMS_SCC-ICS",2,"Rel-9","S2,C1","2008-09-18","2010-03-19",1,"SP-080634","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","-","-",41,21,null,null,"2008-09-15","2009-06-02"]
[6876,430004,"   Stage 3 - IMS Centralized Services support via I1 interface","IMS_SCC-ICS_I1",2,"Rel-9","C1","2009-03-06","2010-03-19",1,"CP-090640","-","Huawei","Lili Yang(kadyyang@huawei.com)","CP#47 completed","24.237; 24.292; new 24.294",43,22,null,null,"2009-03-05","2010-03-02"]
[6881,380064,"Support for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS",1,"Rel-9","S1,S2,S3,C1,C3,C4,R2,R3,R5,IETF","2000-01-03","2014-06-13",1,"SP-080844","-","Alcatel-Lucent","Deborah Barclay","RP#56 completed testing. CP#47 completed. SP#48 completed","GERAN; LTE",38,21,null,null,"2007-10-02","2012-06-05"]
[6884,420022,"   Security aspects for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS-Sec",2,"Rel-9","S3","2008-12-12","2010-06-10",1,"SP-080844","-","Alcatel-Lucent","Deborah Barclay","SP#48 completed","33.401; 33.402",42,22,null,null,"2008-12-09","2010-05-05"]
[6887,480029,"      Conformance Test Aspects - CT1 aspects for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS_UEConTest",3,"Rel-9","R5","2010-06-04","2012-06-15",1,"RP-100567","RP-120445","Samsung","stoyan.baev@partner.samsung.com","RP#56 completed","34.108; 34.123-1; 34.123-2; 34.123-3; 34.229-1; 34.229-2; 34.229-3; 36.508; 36.523-1; 36.523-2; 36.523-3",48,25,null,null,"2010-06-04","2012-06-05"]
[6890,420041,"   Support for IMS Emergency Calls over LTE","IMS_EMER_LTE",2,"Rel-9","R2,R3","2000-01-03","2000-10-16",1,"RP-081140","RP-090698","Alcatel-Lucent","Sudeep Palat (spalat@alcatel-lucent.com) ","RP#45 completed","36.331; 36.413",42,22,null,null,"2009-02-18","2012-05-09"]
[6895,440027,"         CT1 aspects of SRVCC support for IMS Emergency Calls","IMS_EMER_GPRS_EPS-SRVCC",4,"Rel-9","C1","2009-05-29","2009-12-04",1,"CP-090882","-","China Mobile","jiangyi@chinamobile.com","CP#46 completed","24.229; 24.237",44,23,null,null,"2009-05-13","2009-12-02"]
[6899,430006,"LCS for LTE and EPS","LCS_LTE_EPS",1,"Rel-9","S2,C1,C4,R2,R1,R3,R4,R5","2008-06-05","2012-03-02",1,"-","-","-","-","-","LTE",43,22,null,null,"2009-02-18","2010-03-16"]
[6900,400038,"   LCS Control Plane Solution for EPS","LCS_EPS-CPS",2,"Rel-9","S2,C4,C1","2008-06-05","2010-03-19",1,"SP-080445","-","Polaris Wireless","Robert Gross (rgross@polariswireless.com)","Triggered by abandoned Study UID_380068 (FS_LCS_EPS). Linked to Feature UID_380064 Support for IMS Emergency Calls over GPRS and EPS","-",40,21,null,null,"2007-12-13","2008-11-22"]
[6903,440120,"      CT1 aspects of Control Plane LCS in the EPC","LCS_EPS-CPS",3,"Rel-9","C1","2009-05-29","2010-03-19",1,"CP-090811","-","Polaris Wireless","Robert Gross (rgross@polariswireless.com)","CP#47 completed",24.300999999999998,44,23,null,null,"2009-05-13","2010-03-02"]
[6908,420023,"   Security for MBMS support in EPS","MBMS_EPS",2,"Rel-9","S3","2008-12-11","2009-12-10",1,"SP-080737","-","China Mobile","Liu Hong (liuhongyfw@chinamobile.com)","SP#46 completed",33.246000000000002,42,22,null,null,"2008-12-09","2009-12-09"]
[6911,440026,"   CT3 aspects of MBMS support in EPS (Stage 3)","MBMS_EPS",2,"Rel-9","C3","2009-05-29","2009-12-04",1,"CP-090330","-","ZTE, China Mobile","zhou.xiaoyun@zte.com.cn, wangjingyf@chinamobile.com","CP#46 completed",29.061,44,23,null,null,"2009-05-13","2009-11-25"]
[6914,420024,"Access Network Discovery and Selection Function enhancements","eANDSF",1,"Rel-9","S2,C1","2008-12-11","2010-03-19",1,"SP-080887","-","Motorola","Apostolis Salkintzis (salki@motorola.com)","CP#47 completed. No new Rel-9 use cases defined. Implement service requirements not covered in Rel-8","22.278; SA3 33.402 CR#0055",42,22,null,null,"2008-12-05","2010-03-04"]
[6917,430034,"Multiple PDN Connection to the Same APN for PMIP-based Interfaces","MUPSAP",1,"Rel-9","S2,C4,C1","2009-03-13","2010-03-19",1,"SP-090098","-","Samsung","erik.guttman@partner.samsung.com","CP#47 completed. Continues Rel-8 SAES Stage 2 UID_320005. Stage 1 in 22.278 (EPS Service requirements)","-",43,22,null,null,"2009-03-05","2010-03-04"]
[6922,450050,"   SA2 system aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",2,"Rel-9","S2","2009-06-04","2009-09-24",1,"SP-090653","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#45 completed (CR adding support for Explicit Congestion Notification)","23.401 CR#1103r3",45,23,null,null,"2009-05-28","2009-09-21"]
[6925,521005,"   (IETF) SA4 system aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",2,"Rel-9","S4-IETF","2009-06-04","2012-09-12",1,"SP-090653","-","Lionel Morand","-","SP#57 completed","RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp)",52,27,null,null,"2011-06-20","2012-09-03"]
[6926,521006,"   (IETF) CT aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",2,"Rel-9","C1-IETF,C3-IETF,C4-IETF","2007-05-07","2012-09-07",1,"SP-090653","-","Lionel Morand","-","CP#57 completed","RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp)",52,27,null,null,"2011-06-20","2012-09-03"]
[6930,410029,"   SA3 work on PUCI","PUCI",2,"Rel-9","S3","2008-09-18","2009-12-10",1,"SP-080482","-","NEC","Anand R. Prasad (anand@bq.jp.nec.com)","SP#46 completed. No normative work done in Rel-9","New 33.937",41,21,null,null,"2008-09-15","2009-12-07"]
[6934,870075,"   (IETF) Security Considerations for WebRTC (draft-ietf-rtcweb-security)","MEDIASEC",2,"Rel-9","S3-IETF","2002-03-01","2012-09-14",1,null,null,null,null,"9/4/21: RFC 8826 added;","RFC 8826",87,44,null,null,"2011-06-20","2021-04-09"]
[6939,440053,"GBAPush enhancements (Generic push layer)","eGBAPush",1,"Rel-9","S3","2008-03-12","2010-03-25",1,"SP-090282","-","Ericsson","Rolf Blom","SP#43 umbrella to host 33.224, moved from Rel-8 to Rel-9. SP#47 completed","New 33.224",44,23,null,null,"2009-02-11","2009-09-21"]
[6941,440054,"Extended Identity Management","GBA-IdM",1,"Rel-9","S3","2009-06-04","2009-12-10",1,"SP-090284","-","Nokia","Silke.Holtmanns@nokia.com","SP#46 completed. Stage 1 not identified (GBA Liberty Interworking has been outlined and GBA–OpenID interworking is analogous)","New 33.924; CT4 29.109 (added service code)",44,23,null,null,"2009-05-18","2010-02-23"]
[6944,521008,"   (IETF) SA3 part of Network Domain Security (NDS) enhancements to support backhaul security","NDS_Backhaul",2,"Rel-9","S3-IETF","2009-06-04","2012-12-07",1,"SP-090286","-","Bengt Sahlin","-","CP#58 completed","RFC 6712 (was draft-ietf-pkix-cmp-transport-protocols)",52,27,null,null,"2011-06-20","2012-11-24"]
[6949,440457,"   CT4 part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","C4","2009-06-04","2009-12-10",1,"SP-090287","-","Ericsson","Karl Norrman","CP#46 completed. Kc128 enhancements are carried as UMTS keys => no impact on CT4 29.002, 29.060","-",44,23,null,null,"2009-05-18","2009-11-16"]
[6950,440557,"   GERAN2 part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","G2","2009-06-04","2009-09-04",1,"GP-091212","-","Ericsson","Karl Norrman","GP#43 WID approved + completed","44.018.48.008.48.018.48.058",44,23,null,null,"2009-05-18","2010-01-06"]
[6953,420027,"Timed Graphics","TG",1,"Rel-9","S4","2008-12-11","2010-03-25",1,"SP-080683","-","Ericsson","clinton.priddle@ericsson.com","SP#47 completed. Provide graphics in parallel to a video stream (without requiring an umbrella scene descriptor such as 3GPP DIMS in TS 26.142)","26.114; 26.140; 26.234; 26.244; 26.245; 26.346; New 26.430",42,22,null,null,"2008-11-23","2010-02-01"]
[6957,430039,"   Improved Video Support for PSS and MBMS","PMA-IVS",2,"Rel-9","S4","2009-03-12","2010-03-25",1,"SP-090263","-","Nokia","imed.bouazizi@nokia.com","SP#47 completed","26.234; 26.244; 26.346; new 26.903",43,22,null,null,"2009-02-02","2010-03-08"]
[6961,420029,"Rel-9 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM9",1,"Rel-9","S5","2008-02-22","2010-06-10",1,"-","-","-","-","OAM9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI",30.818999999999999,42,22,null,null,"2008-11-25","2010-02-09"]
[6966,420032,"   Rel-9 Performance Management","OAM9-PM",2,"Rel-9","S5","2009-03-12","2010-06-10",1,"-","-","-","-","SP#42 umbrella BB created to host OAM WIs","-",42,22,null,null,"2008-11-25","2008-12-01"]
[6968,430041,"      Enhancement of E-UTRAN Performance Measurements","-",3,"Rel-9","S5","2009-03-12","2010-06-10",1,"SP-090053","-","Motorola, Huawei","Yizhi Yao (yzyao@motorola.com),Lan Zou (zlan@huawei.com)","SP#48 completed",32.424999999999997,43,22,null,null,"2009-02-23","2010-05-26"]
[6972,440067,"      Automatic Radio Network Configuration Data Preparation","-",3,"Rel-9","S5","2009-06-04","2010-06-10",1,"SP-090869","-","Nokia Siemens Networks","clemens.suerbaum@nsn.com","SP#48 completed","32.501; 32.502; 32.503; 32.505; new 32.507",44,23,null,null,"2009-05-18","2010-05-26"]
[6975,440068,"Rel-9 Charging Management small Enhancements","CH9",1,"Rel-9","S5","2009-06-04","2010-03-25",1,"-","-","-","-","CH9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI",30.818999999999999,44,23,null,null,"2009-05-19","2010-03-08"]
[6977,400109,"   CT3 aspects of CS-IBCF and CS-TrGW definition in 3GPP specifications","CS-IBCF",2,"Rel-9","C3","2008-05-30","2010-03-19",1,"CP-090073","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","CP#47 completed",29.234999999999999,40,21,null,null,"2007-09-05","2010-03-02"]
[6980,410108,"   CT4 part of IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3","IMS_IBCF",2,"Rel-9","C4","2008-09-12","2009-12-04",1,"CP-090019","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.fr","CP#46 completed","new 29.238",41,21,null,null,"2007-09-05","2009-11-16"]
[6984,420017,"   Stage 3 for Enhancements of IMS Customized Alerting Tone (CAT) Service","eCAT-SS",2,"Rel-9","C1","2008-12-05","2010-06-04",1,"CP-080796","-","China Mobile","Jiang Yi","CP#48 completed",24.181999999999999,42,22,null,null,"2008-12-04","2010-05-28"]
[6988,460022,"   CT3 aspects of Completion of IMS Restoration Procedures","eIMS_RP",2,"Rel-9","C3","2009-05-29","2010-03-19",1,"CP-091050","-","Ericsson","Emiliano Merino (emiliano.merino@ericsson.com)","CP#47 completed","29.061; 29.212; 29.213; 29.214; 29.215",46,24,null,null,"2009-05-13","2010-03-02"]
[6993,440070,"Operational description of the Inter-IMS Network to Network Interface (II-NNI)","II-NNI",1,"Rel-9","C3,IETF","2009-05-29","2014-12-09",1,"CP-090331","-","Orange","sebastien.daudet@orange-ftgroup.com","-","-",44,23,null,null,"2009-05-29","2013-02-28"]
[6995,561004,"   (IETF) Operational description of the Inter-IMS Network to Network Interface (RFC 7329)","II-NNI",2,"Rel-9","C3-IETF","2012-04-20","2014-09-12",1,"CP-090331","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","CP#65 complete","RFC 7329 (was draft-kaplan-insipid-session-id)",56,29,null,null,"2012-04-20","2014-09-03"]
[6999,561008,"   (IETF) Operational description of the Inter-IMS Network to Network Interface","II-NNI",2,"Rel-9","C3-IETF","2012-04-20","2014-12-09",1,"CP-090331","-","Keith Drage","Keith Drage","In RFC Editors Queue. Dec.14: 75->90. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui-isdni). June 15: RFC 7434 (was draft-ietf-cuss-sip-uui-isdn)","RFC 7434",56,29,null,null,"2012-04-20","2014-12-04"]
[{"$f":"A7002+1","v":7002},450005,"Definition of Ml interface for Control Plane LCS (Stage 3)","EMC2",1,"Rel-9","C1","2009-09-18","2010-03-19",1,"CP-090746","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#47 completed [Stage 3 for Rel-7 Emergency Calls (EMC1)]. Related to Rel-9 UID_400038 LCS Control Plane Solution for EPS. Stage 2 in Rel-9 UID_400038 (23.271), UID_410037 (23.167)",24.228999999999999,45,23,null,null,"2009-09-17","2010-03-02"]
[7004,460004,"3GPP IMS Conferencing Management Object (MO)","IMS_ConfMO",1,"Rel-9","C1","2009-12-03","2009-12-04",1,"-","-","-","-","CP#46 completed. Linked to Rel-6 UID_11051 (IMS Management objects) under the Feature UID_32021 (IMS Phase 2). MO compatible with OMA DM v1.2 & upwards and defined using OMA DM Device Description Framework (OMA-ERELD _DM-V1_2)","New 24.166",46,24,null,null,"2009-12-08","2010-02-09"]
[7007,410017,"   LCR TDD UE OTA Performance Requirements","RInImp9-RFLCROTA",2,"Rel-9","R4","2008-09-12","2009-05-29",1,"RP-080744","RP-090389","RITT","Wu Xiang (wuxiang@chinattl.com)","RP#44 completed technical work (RAN4 internal TR abandoned)","UTRA (no 25.8xy produced)",41,21,null,null,"2008-09-11","2009-09-09"]
[7011,420010,"   Extended UMTS/LTE 800 MHz","RInImp9-UMTSLTE800",2,"Rel-9","R4,R2,R3","2008-12-05","2008-12-05",1,"RP-080884","RP-090687","NTT DoCoMo","Shingo Suwa (suwas@nttdocomo.co.jp)","RP#45 completed","UTRA; LTE 25.101; 25.104; 25.113; 25.133; 34.124; 36.101; 36.104; 36.113; 36.124; 36.133; 36.141; 25.306; 25.307; 25.331; 36.331; 25.461; 25.466; new 36.800",42,22,null,null,"2008-12-04","2009-10-07"]
[7015,440006,"Rel-9 Improvements of the Radio Interface - UE Conformance Testing","-",1,"Rel-9","R5","2009-05-19","2010-09-17",1,"-","-","-","-","-","UTRA; LTE",44,23,null,null,"2009-05-18","2009-05-28"]
[7018,440012,"   TDD UE Over The Air (Antenna) conformance testing methodology","UEAnt_TDDTest",2,"Rel-9","R5","2009-05-30","2009-09-18",1,"RP-090621","RP-090727","CATR","Qu Yan (quyan@emcite.com)","RP#45 completed. Finalized TDD UE test methodology based on R4 TR 25.914 (UE and MS antenna performance evaluation method) and TS 25.144 Over the Air (Antenna) minimum performance requirements for the speech mode (terminal close to head)","UTRA 34.114",44,23,null,null,"2009-05-20","2009-09-10"]
[7020,450018,"Conformance Test Aspects – SMS over IMS in E-UTRAN","SMSoverIMS_UEConTest",1,"Rel-9","R5","2009-09-18","2010-03-19",1,"RP-090959","RP-100072","Alcatel-Lucent","Nidal Khrais (khrais@alcatel-lucent.com)","RP#47 completed","LTE 34.229-1; 34.229-2; 34.229-3",45,23,null,null,"2009-09-15","2010-03-16"]
[7026,440014,"   Cell Portion for 1.28 Mcps TDD","CP_LCRTDD",2,"Rel-9","R3,R1,R4","2009-03-06","2010-09-08",1,"RP-090659","RP-091041","CATT","Ying Zhang (zhangying2@datangmobile.cn)","RP#46 completed","25.102; 25.105; 25.123; 25.225; 25.423; 25.433",44,23,null,null,"2009-05-28","2009-11-26"]
[7029,510014,"   Conformance Test Aspects – Dual-Cell HSUPA","RANimp-DC_HSUPA_UEConTest",2,"Rel-9","R5","2011-03-18","2012-12-07",1,"RP-110116","RP-121524","Ericsson","leif.mattisson@ericsson.com","RP#58 completed. Testing for Rel-9 UID_430014 Dual-Cell HSUPA","UTRA 34.108; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",51,26,null,null,"2011-03-10","2012-11-28"]
[7031,420007,"LTE improvements","LTEimp",1,"Rel-9","R1,R2,R4,R5","2009-03-06","2011-06-03",1,"-","-","-","-","-","LTE",42,22,null,null,"2008-12-02","2009-01-21"]
[7034,490018,"   UE Conformance Test Aspects – Enhanced Dual-layer transmission for LTE TDD","LTEimp-eDL_UEConTest",2,"Rel-9","R5","2010-09-17","2011-06-03",1,"RP-100868","RP-110509","China Mobile","Shanpeng Xiao (xiaoshanpeng@chinamobile.com)","RP#52 completed. Testing for UID_430029 (Enhanced Dual-Layer transmission for LTE)","36.508; 36.521-1; 36.521-2",49,25,null,null,"2010-09-09","2011-05-18"]
[7038,38004,"   AGNSS Testing Procedures","AGNSSPTP-MStest",2,"Rel-9","G3new","2008-05-16","2011-05-20",1,"GP-092343","-","Thales","Michel.monnerat@thalesaleniaspace.com","GP#50 completed","51.010-1; new 51.010-7",38,20,null,null,"2008-05-19","2011-05-21"]
[7042,420005,"   VAMOS Radio Performance Requirements","VAMOS",2,"Rel-9","GP,G1,G2","2008-11-24","2011-05-20",1,"GP-081966","-","Nokia Siemens Networks, China Mobile","juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com","GP#50 completed. GP#40 WID approved",45.005000000000003,40,22,null,null,"2008-11-23","2011-05-21"]
[7045,440002,"Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre (BSC-CBC)","CEBRO",1,"Rel-9","GP,C1","2009-05-15","2010-03-19",1,"GP-091022","-","Ericsson","claes-goran.persson@ericsson.com","CP#47 completed. GP#45 completed. GP#42 WID approved","-",42,23,null,null,"2009-05-18","2010-03-05"]
[7047,440202,"   CT1 part of Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre","CEBRO",2,"Rel-9","C1","2009-05-15","2010-03-19",1,"GP-091022","-","Ericsson","claes-goran.persson@ericsson.com","CP#47 completed",23.041,42,23,null,null,"2009-05-18","2010-03-02"]
[7053,380071,"Deleted - Harmonization of Gq'/Rx for Common IMS","IMS_Comm_GqRx_Harm",1,"Rel-9","S2","2008-01-14","2009-03-12",1,"SP-070822","-","Alcatel-Lucent","geoffrey.cristallo@alcatel-lucent.be","SP#43 stopped. LS_out to TISPAN informs about stopping this activity ","23.822; 23.203",38,21,"SP-43","PCG-22","2007-10-02","2009-03-24"]
[7056,380086,"Deleted - Definition of 3GPP UICC services over the new high-speed interface","UICCHS",1,"Rel-9","C6","2010-03-19","2010-03-19",1,"CP-070837","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#47 work stopped/abandoned","31.xyz",38,21,"CP-47","PCG-24","2008-01-31","2009-11-25"]
[7060,390042,"   Deleted - SAE for generic support for non-3GPP accesses","SAES_Ph2",2,"Rel-9","S2","2007-06-25","2008-06-09",1,"-","-","-","-","SP#39 SAE functionality moved to Rel-9. BUT no agreed WID","-",39,21,"SP-39","PCG-21","2007-03-29","2009-03-24"]
[7061,390043,"      Deleted - Single Radio Aspects of SAE for Optimized Handover with WiMAX","SAES_Ph2",3,"Rel-9","S2","2007-06-25","2008-06-09",1,"-","-","-","-","SP#39 SAE functionality moved to Rel-9. BUT no agreed WID","-",39,21,"SP-39","PCG-21","2007-04-26","2009-03-24"]
[7065,350052,"Study on CS Domain Services over EPS access","FS_CSoPS",1,"Rel-9","S2","2007-04-25","2009-03-12",1,"SP-080800","-","T-Mobile","Karl-Heinz.Nenner@T-Mobile.net","SP#43 completed. Linked to Combinational Services UID_31064, Services Alignment and Migration (ServAl) UID_330017 and 3GPP System Architecture Evolution (SAES) UID_3208",23.879000000000001,35,18,null,null,"2007-03-29","2010-08-09"]
[7069,360006,"Study on System Maintenance over Itf-N","FS_OAM-Maint-Itf-N",1,"Rel-9","S5","2007-06-07","2009-09-24",1,"SP-070306","-","ZTE","Shuqiang Huang (huangsq@zte.com.cn)","SP#45 completed",32.822000000000003,36,19,null,null,"2007-05-28","2009-09-07"]
[7072,400029,"Study on Service Oriented Architecture (SOA) for IRP","FS_OAM_SOA_IRP",1,"Rel-9","S5","2008-06-05","2009-06-04",1,"SP-080281","-","Ericsson","edwin.tse@ericsson.com","SP#44 completed. Spin-off implementation WI UID_440064 Service Oriented Architecture (SOA) for IRP",32.823999999999998,40,21,null,null,"2007-05-28","2009-06-02"]
[7074,390031,"Study on LTE-Advanced","FS_RAN_LTEA",1,"Rel-9","R1,R2,R3,R4","2008-03-21","2010-03-19",1,"RP-091360","RP-100080","NTT DoCoMo","Tetsushi Abe","RP#47 completed","36.913 ; New 36.814; 36.912; R2 36.806 (Relay architectures for E-UTRA); R4 36.815 (LTE-Advanced feasibility studies in RAN4)",39,21,null,null,"2007-12-17","2010-03-16"]
[7080,320026,"Deleted - Study on Protection against SMS and MMS spam","FS_CPSMal",1,"Rel-9","S3","2006-06-08","2009-09-24",1,"SP-060446","-","Orange","eric.gauthier@orange.ch","SP#45 work stopped/abandoned","33.9xx",32,17,"SP-45","PCG-23","2006-06-23","2009-09-21"]
[7083,320022,"   Requirements for evolution of the 3GPP system architecture ","AIPN-SAE",2,"Rel-8","S1","2006-06-08","2007-12-12",1,"SP-080132","-","T-Mobile","michael.kurz@t-mobile.at ","SP#38 completed","22.011; 22.246; New 22.278",32,17,null,null,"2006-06-23","2010-07-28"]
[7087,340051,"      Stage 3 (CT1) for SAE impact on services, network functions and capabilities","SAES",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.229; 27.007; New 24.305",34,18,null,null,"2006-07-19","2010-07-28"]
[7088,340054,"      Stage 3 SAE impact on existing capabilities","SAES",3,"Rel-8","C3","2007-02-05","2008-12-05",1,"CP-080772","-","Huawei","Wei Weihua (weiwh@huawei.com)","CP#42 completed",29.061,34,18,null,null,"2006-07-19","2010-07-28"]
[7092,340022,"      Stage 3 PCC within SAE","SAES-St3-PCC",3,"Rel-8","C3","2007-02-05","2009-05-29",1,"CP-080576","-","Ericsson ","j.javier.pastor@ericsson.com","CP#44 completed","29.212; 29.213; 29.214; New 29.215",34,18,null,null,"2006-07-19","2010-07-28"]
[7096,340060,"      CT4 Stage 3 for protocol between EPCs","SAES-LTE",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.274; 29.275",34,18,null,null,"2006-07-19","2010-07-28"]
[7099,340055,"         CT4 Stage 3 for GTP v2 protocol","SAES-SA-FP_LTE-GTP",4,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed",29.274000000000001,34,18,null,null,"2006-07-19","2010-07-28"]
[7103,410004,"         Mobile IPv4 (MIPv4) based Mobility protocols","SAES-SA-FP_LTE-IETF",4,"Rel-8","C4","2007-02-05","2008-12-05",1,"CP-090247","-","Motorola","Lewis Milton","CP#42 completed",29.279,41,21,null,null,"2006-07-19","2010-07-28"]
[7105,340050,"      Stage 3 for Session management, bearer control and QoS aspects","SAES-LTE",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.007; 24.301",34,18,null,null,"2006-07-19","2010-07-28"]
[7110,370008,"      Stage 2 for Interoperation between LTE and 2G/3G","EPSto2_3G",3,"Rel-8","S2","2007-02-05","2008-09-18",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","SP#41 completed","23.401; 23.402",37,19,null,null,"2007-09-19","2010-07-28"]
[7111,380031,"      Stage 3 for Inter-system mobility between E-UTRAN and 2G/3G","SAES-SA-FP_3GPP",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.008; 24.301",38,21,null,null,"2007-11-19","2010-07-28"]
[7114,340056,"      Stage 3 for EPC - GPRS ","SAES-SA-FP_3GPP",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.274; 29.275; 29.281",34,18,null,null,"2006-07-19","2010-07-28"]
[7119,340061,"      Stage 3 for MME - SGSN signalling free protocol","SAES-SA-FP_3GPP",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.272; 29.274",34,18,null,null,"2006-07-19","2010-07-28"]
[7123,360022,"      Stage 3 for Mobility management based on DSMIPv6","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2008-12-05",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#42 completed",24.303000000000001,36,19,null,null,"2007-09-12","2010-07-28"]
[7126,390009,"      Stage 3 for Mobility management based on MIP v4","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2008-12-05",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#42 completed",24.303999999999998,39,21,null,null,"2008-03-03","2010-07-28"]
[{"$f":"A7130+1","v":7130},370010,"      Stage 3 security aspects for DSMIPv6 Access","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2008-12-05",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#42 completed",24.303000000000001,37,19,null,null,"2006-07-19","2010-07-28"]
[7132,360021,"      Stage 3 for Access to the EPC via non-3GPP access networks","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.302; 24.312",36,19,null,null,"2007-09-12","2010-07-28"]
[7135,521013,"      (IETF) Stage 3 for Interfaces EPC - non-3GPP IP access ","SAES-SA-FP_n3GPP",3,"Rel-8","C4-IETF","2007-02-05","2012-06-15",1,"CP-090247","-","Lionel Morand","-","CP#56 completed","RFC 6611 (was draft-ietf-mip6-bootstrapping-integrated)",52,27,null,null,"2011-06-20","2012-04-20"]
[7138,360018,"      Deleted (already covered) SAES-SA-FP_n3GPP Optimized Handover with CDMA","SAES-SA-FP_n3GPP-OptCDMA",3,"Rel-8","S2","2007-06-25","2007-06-25",1,"-","-","Nokia Siemens Networks","-","SP#37 stopped","-",36,19,"SP-37",null,"2007-04-26","2009-03-24"]
[7141,410005,"      Stage 3 for SRVCC in EPS","SAES-SRVCC",3,"Rel-8","C1","2008-05-30","2009-03-06",1,"CP-080793","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","23.009; 24.008; New 24.301",41,21,null,null,"2008-09-03","2010-07-28"]
[7146,400001,"      Stage 2 for CS Fallback in EPS","SAES-CSFB",3,"Rel-8","S2","2008-03-12","2008-06-05",1,"SP-080097","-","T-Mobile, Vodafone","sabine.demel@t-mobile.at, chris.pudney@vodafone.com","SP#40 completed","New (23.272; 23.401)",40,21,null,null,"2007-03-29","2010-07-28"]
[7149,390039,"   System enhancements for the use of IMS services in local breakout","SAES-IMS_LBO",2,"Rel-8","S2","2008-03-12","2008-06-05",1,"SP-080090","-","Telecom Italia","mario.madella@telecomitalia.it","SP#40 completed","23.228; 23.221; 23.203",39,21,null,null,"2007-10-02","2010-07-28"]
[7154,400104,"   Domain Name System Procedures for Evolved Packet System (DEPS)","SAES-DEPS",2,"Rel-8","C4","2008-05-30","2009-03-06",1,"CP-080280","-","TeliaSonera","jouni.korhonen@teliasonera.com","CP#43 completed","23.003; New 29.303",40,21,null,null,"2006-07-19","2010-07-28"]
[7157,390121,"      Core specification for CT6 aspects of SAE","SAES",3,"Rel-8","C6","2008-03-07","2009-05-29",1,"CP-080164","-","Nokia","Rune Lindholm","CP#44 completed (specified Network Measurement Results collection via USAT)","31.102; 31.111",39,21,null,null,"2008-03-12","2010-07-28"]
[7159,490015,"      Test interworking of IP Multimedia Services Identity Module (ISIM) terminals with IP Multimedia Subsystem (IMS)","SAES-ISIM_IMS_Test",3,"Rel-8","C6","2010-09-17","2011-06-03",1,"CP-100602","-","Comprion","Udo Willenbrink (uwillenbrink@comprion.com )","CP#52 completed. Linked to R5 UID_1273 Provisioning of IP-based multimedia services (24.229, 31.103), R8 UID_390021 CT6 aspects of SAE, UID_420018 Test interworking of LTE Terminals with the USIM, R UID_450018 Testing SMS over IMS in E-UTRAN (34.229).","31.121; 31.124; New 31.134",49,25,null,null,"2010-09-06","2011-05-18"]
[7162,390020,"   Deleted - Issues for CT4 TR 29.803","SAES",2,"Rel-8","C4","2007-01-04","2008-09-12",1,"CP-080068","-","Huawei","-","CP#41 Work stopped and continued in Normative specifications",29.803000000000001,39,21,"CP-41","PCG-21","2006-07-19","2009-03-24"]
[7165,340019,"   Deleted - CT aspects of SAES","SAES-St3",2,"Rel-8","C3,C1,C4","2007-09-04","2008-03-14",1,"CP-060674","-","-","-","SP#37 stopped","-",34,18,"SP-37",null,"2006-07-19","2009-03-24"]
[7168,350020,"      Deleted - CT3 aspects of SAES","SAES",3,"Rel-8","C3","2007-09-04","2007-09-04",1,"CP-060675","-","-","-","SP#37 stopped","-",35,18,"SP-37",null,"2006-07-19","2009-03-24"]
[7173,320030,"   Deleted - Stage 2 of architecture for the 3GPP System Architecture Evolution","SAES-St2",2,"Rel-8","S2","2007-10-02","2007-10-02",1,"SP-060926","-","Vodafone","chris.pudney@vodafone.com","SP#34 stopped. Replaced by UIDs 340018 and 340037. (SP#34 report discussion of SP-060917.)","23.002; 23.060; 23.107; 23.203; 23.228; 23.234; 23.246; 23.271; 23.279",32,17,"SP-34",null,"2006-07-19","2009-03-24"]
[7176,370025,"IMS Centralized Service control","ICSRA",1,"Rel-8","S1,S2,C1,C3,C4,IETF","2005-11-01","2014-12-09",1,"SP-070924","-","AT&T","Randolph Wohlert (rwohlert@tri.sbc.com)","CP#46 completed","-",37,19,null,null,"2007-10-02","2009-12-02"]
[7181,521014,"      (IETF) CT1 aspects - Stage 3 for ICSRA (draft-ietf-salud-alert-info-urns)","ICSRA",3,"Rel-8","C1-IETF","2008-05-30","2014-12-09",1,"CP-091046","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100; 9/4/21: RFC 7462 added;","draft-ietf-salud-alert-info-urns; RFC 7462",52,27,null,null,"2011-06-20","2021-04-09"]
[7184,521017,"      (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 7006)","ICSRA",3,"Rel-8","C1-IETF","2008-06-03","2013-12-06",1,"CP-091046","-","Andrew Allen","-","CP#62 completed","RFC7006 (was draft-ietf-mmusic-sdp-miscellaneous-caps)",52,27,null,null,"2011-06-20","2013-11-27"]
[7187,521018,"      (IETF) CT4 aspects - Stage 3 for ICSRA (RFC 7254)","ICSRA",3,"Rel-8","C4-IETF","2005-11-01","2014-06-13",1,"CP-091046","-","Andrew Allen","-","CP#64 complete","RFC 7254 (was draft-montemurro-gsma-imei-urn)",52,27,null,null,"2011-06-20","2014-06-06"]
[7190,370060,"   General aspects of IMS Sup Services","IMSSS-Gal",2,"Rel-8","S1,C1,C3,C4","2007-09-03","2009-03-06",1,"SP-070691","-","Ericsson","Susana Sabater","CP#43 completed","-",37,19,null,null,"2007-11-19","2007-11-19"]
[7192,380001,"      Documentation of TISPAN R1 and R2 in CT1","REDOC_TIS-C1",3,"Rel-8","C1","2007-11-28","2008-09-12",1,"CP-080213","-","Nokia Siemens Networks","peter.leis@nsn.com","CP#41 completed","24.141; 24.147; 24.173; 24.229; 24.247; 24.341; 24.604; 24.605; 24.606; 24.607; 24.608; 24.610; 24.611; 24.616; 24.623; 24.628; 24.629; 24.647; 24.654",38,21,null,null,"2007-11-28","2008-08-01"]
[7195,370062,"   IMS Multimedia Telephony Service","IMS-MMTel",2,"Rel-8","S1,S5","2007-09-10","2009-03-12",1,"-","-","-","-","SP#43 completed","-",37,19,null,null,"2007-11-19","2007-11-19"]
[7199,380007,"      CT1 part of Stage 3 CCBS_CCNR","CCBS_CCNR",3,"Rel-8","C1","2007-05-02","2009-03-06",1,"CP-080215","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#43 completed","24.642; 24.229; 24.173",38,21,null,null,"2007-11-14","2012-01-11"]
[7203,390059,"      Stage 1 FA","FA",3,"Rel-8","S1","2008-01-30","2008-06-05",1,"-","-","Telecom Italia","-","SP#40 completed ",22.172999999999998,39,21,null,null,"2008-03-03","2008-09-18"]
[7208,380011,"      CT3 part of Stage 3 CW-IMS","CW_IMS",3,"Rel-8","C3","2007-11-30","2008-12-04",1,"CP-080214","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#42 completed",29.163,38,21,null,null,"2007-11-14","2008-11-21"]
[7211,380042,"      Advice of Charge (AoC) support in IMS Charging","CH8_IMS",3,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-070739","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#43 completed","32.240; 32.260; 32.296; 32.298; 32.299; new 32.280",38,21,null,null,"2005-06-17","2009-02-23"]
[7214,390051,"   Stage 2 CIMS_3GPP2","CIMS_3GPP2",2,"Rel-8","S2","2008-03-12","2008-06-05",1,"SP-080220","-","Nortel","Amar Deol (deola@nortelnetworks.com)","SP#40 completed. Acronym changed from \"CIMS_3GPP2, IMS_Common\"","23.002; 23.141; 23.203; 23.167; 23.228",39,21,null,null,"2008-03-03","2015-03-24"]
[7217,390013,"      Stage 3 CIMS_3GPP2 (CT1)","REDOC_3GPP2",3,"Rel-8","C1","2008-03-07","2008-12-05",1,"CP-080795","-","Alcatel-Lucent","orsic@alcatel-lucent.com","CP#42 completed","23.218; 24.141; 24.147; 24.173; 24.229; 24.238; 24.247; 24.604; 24.605; 24.606; 24.607; 24.608; 24.610; 24.611; 24.629; 24.930",39,21,null,null,"2008-03-03","2008-12-04"]
[7219,390027,"      Stage 3 CIMS_3GPP2 (CT4)","REDOC_3GPP2",3,"Rel-8","C4","2008-03-07","2008-12-11",1,"CP-080795","-","Alcatel-Lucent","orsic@alcatel-lucent.com","CP#42 completed","29.228; 29.229; 29.328; 29.329",39,21,null,null,"2008-03-03","2009-03-26"]
[7222,350009,"      Architecture aspects of PktCbl-Deploy","PktCbl-Deploy",3,"Rel-8","S2","2007-02-05","2007-12-06",1,"SP-070105","-","Cablelabs","Bernie McKibben (b.mckibben@cablelabs.com)","SP#38 completed",23.228000000000002,35,18,null,null,"2007-03-29","2008-05-27"]
[7226,350013,"      CT1,CT3 aspects of PktCbl-Interwork","PktCbl-Intw",3,"Rel-8","C1,C3","2007-03-26","2008-03-14",1,"CP-070575","-","Cablelabs","D.Hancock@CableLabs.com","CP#39 completed",24.228999999999999,35,18,null,null,"2007-03-29","2008-03-03"]
[7230,380029,"      CT3 aspects of PktCbl-Sec","PktCbl-Sec",3,"Rel-8","C3","2007-03-26","2007-11-30",1,"CP-070124","-","Cablelabs","D.Hancock@CableLabs.com","CP#38 completed",29.163,38,21,null,null,"2007-03-29","2008-03-07"]
[7234,360014,"   SA2 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","S2","2007-06-22","2008-09-18",1,"SP-080095","-","Orange","Delphin Barankanira","no Stage 2 impacts",23.228000000000002,36,19,null,null,"2007-06-22","2010-07-29"]
[7235,390022,"   CT1 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","C1","2008-03-07","2010-03-19",1,"CP-080220","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#47 completed","24.229; 24.503",39,21,null,null,"2008-03-07","2010-03-03"]
[7241,380043,"   Documentation of TISPAN NGN R1 and R2 in 3GPP SA2","IMS_Comm_Doc",2,"Rel-8","S2","2008-01-14","2008-06-05",1,"SP-070823","-","Nokia Siemens Networks","jozsef.varga@nsn.com","SP#40 completed","23.228; 23.204; 23.167",38,21,null,null,"2007-10-02","2008-05-27"]
[7242,380044,"   Maintenance of TISPAN release 2 common IMS","IMS_Comm_Mtce8",2,"Rel-8","S2","2007-07-02","2007-12-06",1,"SP-070916","-","Telecom Italia","antonio.ascolese@telecomitalia.it","SP#38 completed","23.506; 23.507.23.517; 23.521",38,21,null,null,"2007-10-02","2010-07-29"]
[7248,360017,"   Stage 2 for IMS-Sec","IMS-Sec",2,"Rel-8","S3","2007-03-01","2008-12-11",1,"SP-070496","-","Ericsson","Bengt.Sahlin@ericsson.com","SP#42 completed. SP#46 withdrawn draft 33.178-100 and 33.978 from Rel-8 onwards","33.203; 33.141; 33.803",36,19,null,null,"2007-11-21","2009-04-06"]
[7250,390154,"   CT4 part of Stage 3 for IMS-Sec","IMS-Sec",2,"Rel-8","C4","2007-06-07","2009-03-06",1,"-","-","Ericsson","-","CP#43 completed","-",39,21,null,null,"2007-11-21","2009-02-20"]
[7253,34046,"IMS initiated and controlled PSS and MBMS User Service","IMS_PSS_MBMS_US",1,"Rel-8","S4,S3,IETF","2008-03-12","2011-09-21",1,"SP-080201","-","FT, Ericsson","olle.franceschi@ericsson.com","SP#39 WID approved","-",34,18,null,null,"2008-03-18","2011-06-30"]
[7257,7013,"   Stage 1 and 2 defined in earlier Releases","MIW-IMS",2,"Rel-8","S2","2005-09-23","2005-11-30",1,"-","-","Vodafone","nico.gabriele@vodafone.com","SP#31 Moved from FS section Feb 2006","-",70,36,null,null,"2006-02-16","2010-07-30"]
[7261,360029,"IMS Stage 3 IETF Protocol Alignment - phase 2","IMSProtoc2",1,"Rel-8","C1,IETF","2007-06-22","2014-12-09",1,"CP-080794","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#43 completed","-",36,19,null,null,"2007-09-05","2009-02-20"]
[7262,360129,"   CT1 aspects of IMS Stage 3 IETF Protocol Alignment - phase 2","IMSProtoc2",2,"Rel-8","C1","2007-06-22","2009-03-06",1,"CP-080794","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#43 completed","23.218; 24.229; 24.930",36,19,null,null,"2007-09-05","2009-02-20"]
[7268,521026,"   (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui)","UUSIW",2,"Rel-8","C1-IETF,C3-IETF","2007-11-30","2014-12-09",1,"CP-070782","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui). June 2015: RFC 7433 (was draft-ietf-cuss-sip-uui)","RFC 7433",52,27,null,null,"2011-06-20","2015-03-10"]
[7269,551001,"   (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui-isdn)","UUSIW",2,"Rel-8","C1-IETF,C3-IETF","2011-03-17","2014-12-09",1,"CP-070782","-","Keith Drage","Keith Drage (drage@alcatel-lucent.com)","In RFC Editors Queue. Dec.14: 75->90. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui-isdn). June 2015: RFC 7434 (was draft-ietf-cuss-sip-uui-isdn)","RFC 7434",55,28,null,null,"2012-03-03","2015-03-10"]
[7275,380035,"AS/MRFC Stage 2 and 3","MRFC_TS",1,"Rel-8","C1,IETF","2007-11-14","2012-06-15",1,"CP-070784","-","Hewlett-Packard","mark.syrett@hp.com","Triggered by Study UID_7048 (MRFC)","-",38,21,null,null,"2007-11-14","2010-07-30"]
[7277,380235,"   AS/MRFC Stage 3","MRFC_TS",2,"Rel-8","C1","2007-11-14","2008-12-05",1,"CP-070784","-","Hewlett-Packard","mark.syrett@hp.com","CP#42 completed","24.229; 24.147; 24.247",38,21,null,null,"2007-11-14","2012-01-10"]
[7280,400026,"   IMS Restoration Procedures (CT4)","IMS_RP",2,"Rel-8","C4","2008-05-30","2009-03-06",1,"CP-080447","-","Ericsson","german.blanco@ericsson.com","CP#43 completed","23.380; 29.228; 29.229; 29.230; 23.008",40,21,null,null,"2007-03-29","2010-07-30"]
[7284,390024,"   Stage 1 for I-WLAN NSP","IWLANNSP",2,"Rel-8","S1","2007-06-14","2007-06-14",1,"SP-060932","-","Telefónica O2","chris.friel@O2.com","SP#36 completed",22.234000000000002,39,21,null,null,"2005-11-04","2008-03-25"]
[7288,380045,"   Stage 2 for Mobility between 3GPP-WLAN Interworking and 3GPP Systems","IWLAN_Mob",2,"Rel-8","S2","2007-09-14","2008-06-05",1,"SP-070701","-","Orange","xiaobao.chen@orange-ftgroup.com","SP#40 completed","new 23.327",38,21,null,null,"2007-11-21","2010-07-30"]
[7291,7042,"Enhancements for Voice Group Call Service (VGCS) Applications (EVA)","EVA",1,"Rel-8","S1,C1,C4,G2","2006-03-15","2009-09-18",1,"SP-070904","-","Nortel","Amar Deol (deola@nortelnetworks.com)","CP#45 completed","-",70,36,null,null,"2006-03-21","2010-07-30"]
[7293,370019,"   VGCS/VBS and GPRS Interactions","EVA",2,"Rel-8","S1","2007-09-03","2008-03-21",1,"SP-070653","-","Huawei","Ling Liu","SP#39 completed","42.068; 42.069",37,19,null,null,"2007-10-02","2008-05-16"]
[7296,52148,"   GERAN2 aspects of EVA","EVA",2,"Rel-8","G2","2006-06-30","2008-02-22",1,"GP-071855","-","Nortel","frank.billenkamp@nortel.com","GP#37 completed","44.018; 48.008",null,null,null,null,"2006-07-05","2008-05-16"]
[7302,350002,"      Deleted - CT4 aspects of Stage 3 PNM","PNM",3,"Rel-8","C4","2007-03-26","2008-12-05",1,"CP-080065","-","Vodafone","yang.lu@vodafone.com","CP#42 no impact on CT4 specs","-",null,null,"CP-42",null,"2007-03-29","2010-07-30"]
[7304,350049,"   Deleted - Actual Requirements of PNM","PNM",2,"Rel-8","C1","2007-03-26","2007-03-26",1,"-","-","Ericsson","-","SP#37 stopped","-",null,null,"SP-37",null,"2007-05-04","2009-03-24"]
[7307,400014,"   Transfer of data during an emergency call","EData",2,"Rel-8","C1","2008-05-30","2009-03-06",1,"CP-080316","-","T-Mobile","Dieter Jacobsohn","CP#43 completed",24.007999999999999,40,21,null,null,"2006-10-06","2010-08-02"]
[7311,380060,"IP Interconnection of Services ","IPinterc",1,"Rel-8","S1,S2,S5,C3","2006-08-16","2009-03-06",1,"SP-080565","-","Telefónica O2","chris.friel@O2.com","SP#43 completed","-",38,21,null,null,"2007-12-13","2010-08-02"]
[7315,360011,"      IMS inter-operator service interconnection interface","FBI2-IOPSI",3,"Rel-8","C3","2007-06-01","2009-03-06",1,"CP-080578","-","Telecom Italia","antonio.ascolese@telecomitalia.it","CP#43 completed","29.865; 29.165",null,null,null,null,"2007-06-20","2010-08-02"]
[7318,7006,"      Deleted (never approved) - Stage 2 of FBI for TISPAN R2 - Rel 8","FBI2-TISP2-s2",3,"Rel-8","S2","2007-11-30","2007-11-30",1,"-","-","Nokia Siemens Networks","-","SP#36 stopped","-",null,null,"SP-36",null,"2006-02-16","2009-03-24"]
[7320,410002,"   Stage 1 for SIP_Nc (covered by Feature IPinterc)","SIP_Nc",2,"Rel-8","S1","2007-12-06","2008-03-12",1,"SP-070871","-","Telefónica O2","chris.friel@O2.com","22/07/08 Created. Stage 1 for SIP_Nc (covered by SA1 Feature UID_380060 Ipinterc)","22.101; 22.228",41,21,null,null,"2007-12-13","2008-03-20"]
[7323,360028,"   Interworking between the 3GPP CS domain with SIP-I as signalling protocol and other networks","SIP_Nc-St3C3",2,"Rel-8","C3","2007-09-14","2009-03-06",1,"CP-080282","-","Nokia Siemens Networks","Thomas.Belling@nsn.com","CP#43 completed. CP#42 target 12/08=>03/09","29.235; 23.172; 23.202; 29.007; 29.163; 29.414",null,null,null,null,"2007-09-05","2009-02-19"]
[7326,380056,"   SA2 aspects of ETWS","ETWS",2,"Rel-8","S2","2008-01-14","2008-09-18",1,"SP-070815","-","NTT DoCoMo","tanakai@nttdocomo.co.jp","SP#41 completed","23.828; 23.401",38,21,null,null,"2007-12-13","2008-09-14"]
[7329,430045,"   ETWS primary notification message definition in GERAN","ETWS",2,"Rel-8","G2","2009-03-12","2009-05-15",1,"SP-090154","-","Ericsson","claes-goran.persson@ericsson.com","SP#44 completed with CT1 help (GERAN2 LS_in SP-090154)","44.018; 44.060",43,22,null,null,"2009-03-10","2009-05-30"]
[7334,330006,"Local Charging Zone Requirements","LCZR",1,"Rel-8","S1","2006-09-28","2008-03-12",1,"SP-060482","-","China Mobile","liuhongyfw@chinamobile.com","SP#39 Stage 1 completed",22.114999999999998,null,null,null,null,"2006-10-06","2008-03-25"]
[7338,390014,"   IMS CAT Supplementary Service","CAT-SS",2,"Rel-8","C1,C3","2008-03-12","2009-09-18",1,"CP-080496","-","Nortel","milanpa@nortel.com","-","-",39,21,null,null,"2008-03-03","2008-11-21"]
[7342,410110,"      CT4 part of CAT Service in 3GPP CS domain","CAT-3G_CS",3,"Rel-8","C4","2008-09-12","2009-03-06",1,"CP-080445","-","China Mobile","zhaoyuyi@chinamobile.com","CP#43 completed. Triggered by Study UID_360031 (TR 29.882) ","23.205; 23.231; 29.002",41,21,null,null,"2008-09-11","2012-01-11"]
[7345,350047,"   Stage 1 for MESSIW","MESSIW",2,"Rel-8","S1","2007-03-26","2007-03-26",1,"SP-070816","-","Huawei","ling.liu@huawei.com","SP#35 completed","22.105; 22.340",null,null,null,null,"2005-11-04","2008-03-22"]
[7347,400016,"   CT3 part of Stage 3 for MESSIW","MESSIW",2,"Rel-8","C3","2008-05-30","2009-03-06",1,"CP-080773","-","Huawei","xupeili@huawei.com","CP#43 completed",29.311,40,21,null,null,"2006-07-19","2009-02-19"]
[7350,320023,"   Service Requirements for PRIOR","PRIOR_EMR",2,"Rel-8","S1","2006-06-08","2007-12-06",1,"SP-060780","-","Telcordia","jgarraha@telcordia.com","SP#38 completed","New 22.153",32,null,null,null,"2003-03-28","2008-06-03"]
[7353,370020,"   Deleted - Stage 3 for PRIOR","PRIOR-EMR",2,"Rel-8","C3","2007-09-21","2009-05-29",1,"CP-070576","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#44 stopped (Reason: No Rel-8 solution expected (LS sent to SA2, but not prioritized in SA2)","29.212; 29.213; 29.214; 29.163",37,null,"CP-44","PCG-23","2007-09-25","2009-05-29"]
[7356,370034,"   OSA Stage 1 - NGN Service Requirement","OSA8-IMSReq",2,"Rel-8","S1","2007-09-03","2008-03-14",1,"SP-070692","-","Orange","Song Dong","SP#40 maintenance & new OSA work moved to OMA",22.126999999999999,37,null,null,null,"2007-10-02","2010-08-02"]
[7361,370015,"      Parlay-X Terminal status web service","OSA8-IMS",3,"Rel-8","C5","2007-10-25","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.199-08",37,null,null,null,"2007-09-13","2009-01-19"]
[7364,380048,"      Deleted - Privacy on Subscriber Identity (Liberty Alliance, OASIS) (22.127 CR 0085 S1-071835)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[7369,380053,"      Deleted - API usage accounting (22.127 CR 0090 S1-071792)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[7372,390067,"      Framework Enterprise Operator (Service Subscription function)","OSA8-IMS",3,"Rel-8","C5","2008-01-10","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.198-03",39,21,null,null,"2008-03-26","2009-01-19"]
[7373,390068,"      Mobility Emergency Location","OSA8-IMS",3,"Rel-8","C5","2008-01-10","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.198-06",39,21,null,null,"2008-03-26","2009-01-19"]
[7378,380017,"   Stage 3 for PPACR (CT1)","PPACR-CT1",2,"Rel-8","C1","2007-11-14","2008-12-05",1,"CP-070783","-","NTT DoCoMo","-","CP#42 completed","24.008; 23.122; 24.301",38,21,null,null,"2007-11-14","2008-11-21"]
[7380,380063,"Charging for multi-phases services","CHRGMPH",1,"Rel-8","S1","2007-12-06","2008-03-12",0.99,"SP-080053","-","Telecom Italia","Marco.DeLuca1@telecomitalia.it","SP#39 Stage 1 completed",22.114999999999998,38,21,null,null,"2007-12-13","2008-12-10"]
[7383,380066,"   Stage 1 for Home NodeB / eNodeB","HomeNB-S1",2,"Rel-8","S1","2007-12-06","2008-03-12",1,"SP-070952","-","Vodafone","John Watson","SP#39 completed","22.011; 22.115",38,21,null,null,"2007-12-13","2008-07-24"]
[7388,400053,"   Support of UTRA HNB","HNB-supp",2,"Rel-8","R2","2008-05-30","2009-03-06",1,"RP-080752","RP-090040","Huawei","Yang Xudong (yangxudong@huawei.com)","RP#43 completed","25.304; 25.306; 25.331; new 25.367",40,21,null,null,"2008-06-03","2009-02-27"]
[7392,430022,"UTRA HNB – UE Conformance Testing","HNB-UEConTest",1,"Rel-8","R5","2009-03-06","2010-06-04",1,"-","-","-","-","RP#48 FDD completed. Testing for Feature UID_390033 UTRA HNB","-",43,22,null,null,"2009-02-27","2010-06-01"]
[7396,390146,"   SA3 part of GBAPush (33.223)","GBAPush",2,"Rel-8","S3","2008-03-12","2008-12-05",1,"SP-080133","-","Ericsson","Rolf Blom","SP#42 completed 33.223 as Rel-8. TS 33.224 moved to Rel-9 under new UID_420039",33.222999999999999,39,21,null,null,"2008-03-22","2009-03-09"]
[7399,34045,"Requirements and Test methods for Wideband Terminals","RETEM_WB_T",1,"Rel-8","S4","2008-03-12","2008-12-11",1,"SP-080004","-","FT, Ericsson","stephane.ragot@orange-ftgroup.com, wanqing.shi@sonyericsson.com","SP#42 completed. SP#39 WID approved. ","26.131; 26.132",null,null,null,null,"2008-03-18","2008-11-21"]
[7400,34043,"Extending PSS and MBMS User Services for optimized Mobile TV","PSS_MBMS_OMTV",1,"Rel-8","S4","2007-12-06","2008-12-11",1,"SP-070757","-","Ericsson","thorsten.lohmar@ericsson.com","SP#42 completed. SP#38 WID approved. ","26.234; 26.346; 26.946",null,null,null,null,"2007-12-09","2008-11-21"]
[7405,400019,"   Deleted - CT1 part of Enhancement of interworking between MTSI and CS networks","MTSI_eMHI",2,"Rel-8","C1","2008-05-30","2008-12-12",1,"CP-080774","-","Huawei","Tingfang Tang (tagna_online@huawei.com)","CP#42 stopped (No CT1-impact). WID updated CP-080422=>CP-080774","-",40,21,"CP-42",null,"2007-12-09","2010-08-02"]
[7407,340064,"   Rel-8 Network Infrastructure Management","OAM8-NIM",2,"Rel-8","S5","2007-06-07","2009-12-04",1,"-","-","-","-","-","-",34,null,null,null,"2007-07-13","2009-03-24"]
[7411,390016,"      Alignment with eTOM and M.3060 architectural concepts","OAM8-NIM",3,"Rel-8","S5","2008-02-22","2008-12-11",1,"SP-080068","-","TeliaSonera","tommy.berggren@teliasonera.com","SP#42 completed","32.101/2; 32-series",39,21,null,null,"2007-09-15","2008-11-25"]
[7414,370002,"      Deleted - End point modelling for reference point","OAM8-NIM",3,"Rel-8","S5","2007-09-17","2008-12-11",1,"SP-070618","-","Motorola","Yizhi Yao (yzyao@motorola.com)","SP#41 Work stopped. Contributions related to E-UTRAN/EPC to be submitted to UID_380036 E-UTRAN NRM IRP/ UID_380037 EPC NRM IRP","32.152; 32.62/3/4x; 32.73x",37,null,"SP-41","PCG-21","2007-09-15","2009-03-24"]
[7419,340066,"   Rel-8 Trace Management","OAM8-Trace",2,"Rel-8","C1,C4,IETF","2008-03-07","2012-12-07",1,"-","-","-","-","-","-",34,null,null,null,"2007-06-22","2008-12-10"]
[7422,531003,"      Deleted - (IETF) Service Level Tracing in IMS (draft-dawes-sipping-debug-event)","OAM8-Trace",3,"Rel-8","C1-IETF","2008-03-07","2011-12-09",1,"CP-080315","-","Peter Dawes","peter.dawes@vodafone.com","CP#54 Draft removed from 3GPP documentation, covered by draft-dawes-sipping-debug; 9/4/21: 100%->100","draft-dawes-sipping-debug-event",53,27,null,null,"2011-07-29","2021-04-09"]
[7423,400022,"      CT4 part of Service Level Tracing in IMS","OAM8-Trace",3,"Rel-8","C4","2008-03-07","2008-12-05",1,"CP-080315","-","Vodafone","peter.dawes@vodafone.com","CP#42 completed","29.228; 29.229",40,21,null,null,"2008-03-17","2010-08-02"]
[7427,350038,"   Online charging correlation","CH8",2,"Rel-8","S5","2006-03-16","2007-12-14",1,"SP-070077","-","Orange","Chahine, Rony ","SP#38 completed",32.295999999999999,null,null,null,null,"2008-03-17","2008-03-17"]
[7432,380025,"   Stage 2 for eMp","eMp",2,"Rel-8","C4","2007-11-30","2008-12-05",1,"CP-080725","-","Huawei","Chencheng@huawei.com","CP#42 completed",23.332999999999998,38,21,null,null,"2007-11-19","2010-08-02"]
[7435,320015,"   Requirements for Contact Manager","eUPHBOOK-St1",2,"Rel-8","C6","2006-06-22","2007-12-21",1,"CP-080382","-","Gemalto","Jacques.seif@gemalto.com","CP#38 completed",21.111000000000001,null,null,null,null,"2006-01-24","2008-05-29"]
[7438,320016,"   Deleted - Implementation of eUPHBOOK","eUPHBOOK-St23",2,"Rel-8","C6","2007-06-21","2007-06-21",1,"CP-060355","-","Giesecke & Devrient","Claus Dietze","SP#33 stopped",31.102,null,null,"SP-33",null,"2006-01-24","2009-03-24"]
[7441,330019,"   LTE – Radio Interface Layer 2 and 3 Protocol Aspect","LTE-L23",2,"Rel-8","R2","2006-09-25","2008-12-05",1,"RP-080747","RP-080741","Nokia Siemens Networks","benoist.sebire@nokia.com","RP#42 completed","36.302; 36.304; 36.306; 36.314; 36.321; 36.322; 36.323; 36.331; 25.302; 25.304; 25.331",null,null,null,null,"2006-03-21","2009-12-18"]
[7446,370001,"      Subscriber and Equipment Trace for E-UTRAN and EPC","E-UTRAN-OAM",3,"Rel-8","S5","2007-09-17","2009-03-12",1,"SP-070617","-","Ericsson","robert.petersen@ericsson.com ","SP#43 completed","32.421; 2.422; 32.423; 2.441; 32.442; 32.443; 32.445",37,null,null,null,"2007-09-15","2010-07-29"]
[7449,390003,"      Key Performance Indicators (KPIs) for E-UTRAN","E-UTRAN-OAM",3,"Rel-8","S5","2008-02-22","2009-03-12",1,"SP-080063","-","Ericsson ","ulf.hubinette@ericsson.com ","SP#43 completed","new (32.450; 32.451)",39,21,null,null,"2005-06-17","2009-02-23"]
[{"$f":"A7450+1","v":7450},390004,"   Self-Organizing Networks (SON)","LTE_SON-OAM",2,"Rel-8","S5","2008-02-22","2008-12-11",1,"SP-080275","-","Vodafone","GOMPAKIS, Panagiotis","SP#42 completed (WT UID_390007 moved to Rel-9)","-",39,21,null,null,"2005-06-17","2008-12-01"]
[7454,25029,"Rel-8 LTE – Terminal Conformance Test Specification","LTE-UEConTest",1,"Rel-8","R5","2007-06-01","2009-12-04",1,"-","-","-","-","Testing for Feature UID_20068 (LTE)","-",null,null,null,null,"2006-03-21","2008-06-01"]
[7457,350040,"Rel-8 Improvements of the Radio Interface","RInImp8",1,"Rel-8","RP","2007-03-05","2009-03-06",1,"-","-","-","-","-","-",null,null,null,null,"2005-01-04","2009-03-24"]
[7463,370032,"   CS Voice Service over HSPA","RInImp8-CsHspa",2,"Rel-8","R2","2007-07-19","2008-03-07",1,"RP-070765","RP-080042","Nokia Siemens Networks","woonhee.hwang@nsn.com","RP#39 completed","25.323; 25.331; 25.322",37,null,null,null,"2007-10-02","2010-08-02"]
[7465,350036,"   Deleted - UMTS 2300 MHz FDD/TDD","RInImp8-UMTS2300",2,"Rel-8","R4","2007-03-05","2008-09-12",1,"RP-070128","RP-080515","AT&T","Marc Grant","RP#41 stopped","25.101; 25.104; 25.133; 25.141; 25.331; 25.942; 25.306; 25.307; 34.121",null,null,"RP-41","PCG-21","2004-09-27","2010-08-02"]
[7468,400055,"   Conformance Test Aspects – Performance requirements for 15 code reception with 16QAM/QPSK (FDD)","RInImp8-UEConTest_Hsdpa15codes",2,"Rel-8","R5","2008-03-07","2008-12-05",1,"RP-080311","RP-080818","Ericsson","Mikael.Ziren@Ericsson.com","RP#42 completed","34.121-1; 34.121-2",40,21,null,null,"2008-06-03","2008-12-09"]
[7472,370037,"   Enhanced Uplink for CELL_FACH State in FDD","RANimp-UplinkEnhState",2,"Rel-8","R2","2007-09-14","2008-12-05",1,"RP-070677","RP-080804","Nokia Siemens Networks","markus.wimmer@nsn.com","RP#42 completed. Linked to UID_370036 Improved L2 for uplink","25.309; 25.211; 25.214; 25.321; 25.331; 25.423; 25.433",37,null,null,null,"2007-10-02","2010-08-03"]
[7476,380075,"   64QAM for 1.28 Mcps TDD HSDPA","RANimp-64Qam1.28TDD",2,"Rel-8","R1","2007-12-04","2008-12-05",1,"RP-070924","RP-080806","ZTE","zfmail@zte.com.cn","RP#42 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","25.102; 25.105; 25.123; 25.142; 25.201; 25.221; 25.222; 25.223; 25.224; 25.306; 25.308; 25.321; 25.331; 25.423; 25.433",38,21,null,null,"2007-12-17","2010-08-03"]
[7477,380076,"   Enhanced CELL_FACH state in 1.28 Mcps TDD","RANimp-EnhState1.28TDD",2,"Rel-8","R2","2007-12-04","2008-12-05",1,"RP-071038","RP-080807","ZTE","zhang.yincheng@zte.com.cn","RP#42 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","25.123; 25.221; 25.222; 25.224; 25.301; 25.302; 25.304; 25.306; 25.308; 25.319; 25.321; 25.331; 25.401; 25.423; 25.425; 25.433; 25.435",38,21,null,null,"2007-12-17","2010-08-03"]
[7481,400050,"   MIMO for 1.28 Mcps TDD. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","RANimp-MIMOLCR",2,"Rel-8","R1,R4","2008-01-24","2009-05-29",1,"RP-080485","RP-090313","CATT","wangke@datangmobile.cn","RP#43 completed","25.201; 25.221; 25.222; 25.223; 25.224; 25.306; 25.308; 25.321; 25.331; 25.423; 25.433; 25.102; 25.105; 25.142",40,21,null,null,"2008-03-17","2010-08-03"]
[7484,410020,"   Conformance Test Aspects – Combination of 64QAM and MIMO for HSDPA (FDD)","RANimp-UEConTest_64QamMimoHsdpa",2,"Rel-8","R5","2008-09-12","2009-12-04",1,"RP-080759","RP-091058","Ericsson","leif.mattisson@ericsson.com","RP#46 completed. Testing for UID_360013","34.108; 34.121-1; 34.121-2; 34.123-1; 34.123-2",41,21,null,null,"2008-06-03","2010-08-03"]
[7490,430028,"   Conformance Test Aspects – Receiver Type3i","RANimp-UEConTest_ReceiverType3i",2,"Rel-8","R5","2009-03-06","2009-12-04",1,"RP-090010","RP-091066","Qualcomm","Ashok Kumar Narayanaswamy (anarayan@qualcomm.com)","RP#46 completed. Testing for Receiver Type3i in 25.101 UE radio Tx and Rx FDD","34.108; 34.121-1; 34.121-2",43,22,null,null,"2009-03-10","2010-08-03"]
[7492,450024,"   Conformance Test Aspects – Continuous Connectivity for packet data users for 1.28 Mcps TDD","RANimp-UEConTest_CPCLCRTDD",2,"Rel-8","R5","2009-09-18","2010-09-17",1,"RP-090751","RP-100739","ZTE","huang.he4@zte.com.cn","RP#49 completed. Testing for UID_390028","34.108; 34.123-1; 34.123-2; 34.123-3",45,23,null,null,"2009-09-15","2010-09-09"]
[7495,360008,"3.84 Mcps TDD MBMS over a Single Frequency Network (MBSFN) Integrated Mobile Broadcast","MBSFN-DOB",1,"Rel-8","R1","2007-06-04","2008-12-05",1,"RP-081124","RP-080218","Ericsson","Lars.Lindbom@ericsson.com","RP#42 completed. WID updated RP-070493=>RP-081124 (changed WI title \"MBSFN Downlink Optimized Broadcast (DOB) 3.84 Mcps TDD\" => \"3.84Mcps TDD MBSFN Integrated Mobile Broadcast\"). ","25.102; 25.105; 25.123; 25.201; 25.221; 25.222; 25.223; 25.224; 25.304; 25.306; 25.331; 25.346; 25.402; 25.433",null,null,null,null,"2007-06-21","2008-12-09"]
[7499,52583,"   G2 part of GERAN support for GERAN - 3G Long Term Evolution interworking","GELTE",2,"Rel-8","G2","2006-09-08","2009-02-20",1,"GP-061757","-","Nokia, Nokia Siemens Networks","sergio.parolari@nsn.com, vlora.rexhepi@nokia.com","GP#41 completed","44.018; 44.060; 48.008; 48.018",null,null,null,null,"2006-09-13","2010-09-09"]
[7503,50587,"GAN Enhancements","GANENH",1,"Rel-8","GP","2007-05-15","2009-09-04",1,"GP-071484","-","T-Mobile","mohammed.versi@t-mobile.com","GP#37 completed. GP#43 completed Testing","-",null,null,null,null,"2007-09-06","2009-09-28"]
[7504,50588,"   Update to GAN specifications","GANENH-SPEC",2,"Rel-8","GP","2007-08-31","2008-02-22",1,"GP-071560","-","T-Mobile","mohammed.versi@t-mobile.com","GP#37 completed","43.318; 44.318",null,null,null,null,"2007-09-06","2008-05-19"]
[7508,400042,"   Media Requirements for CS over IP based User Plane","AoIP-CSoIP",2,"Rel-8","S4","2007-12-05","2008-12-11",1,"SP-080444","-","China Mobile, Ericsson","Karl.Hellwig@Ericsson.com","SP#42 completed","26.102; 26.103; 26.202",40,21,null,null,"2007-12-09","2008-11-21"]
[7511,400124,"      CT1 part of Core Network Impacts for A-Interface User Plane over IP","AoIP-CN",3,"Rel-8","C1","2008-05-30","2008-12-05",1,"CP-080722","-","Ericsson","philip.hodges@ericsson.com","CP#42 completed. Updated WID CP-080278=>CP-080722",23.009,40,21,null,null,"2007-09-19","2012-01-11"]
[7517,400051,"   RAN2 part of Support for Additional Navigation Satellite Systems (ANSS) for LCS","RANimp-ANSS",2,"Rel-8","R2","2008-05-30","2008-12-05",1,"RP-080346","RP-080813","Qualcomm","Etienne Chaponniere (echaponn@qualcomm.com)","RP#42 WI closed at 95%. Considers Rel-9 performance requirements","25.305; 25.306; 25.331; 25.413; 25.423; 25.433; 25.453",40,21,null,null,"2008-03-17","2008-12-04"]
[7519,53090,"   MS conformance testing for the Latency Reductions feature","CTLATRED-MStest",2,"Rel-8","G3new","2008-02-22","2010-03-05",1,"GP-080368","-","Ericsson","hakan.e.grunditz@ericsson.com","GP#45 completed",51.01,null,21,null,null,"2008-02-26","2010-03-05"]
[7522,320001,"(Small) Technical Enhancements and Improvements for Rel-8","TEI8",1,"Rel-8","SP,CP,RP,GP","2007-01-01","2008-12-11",1,"-","-","-","-","SP#42 completed","-",null,null,null,null,"2005-11-04","2009-02-20"]
[7526,31068,"   Deleted - Stage 1","AIPN",2,"Rel-8","S1","2004-06-28","2006-03-15",1,"SP-050181","-","NTT DoCoMo","c.masyu@nttdocomo.co.jp","22.258 withdrawn, superseded by 22.278 (UID 320022). SP#38 stopped",22.257999999999999,null,null,"SP-38",null,"2004-08-30","2009-03-24"]
[7530,370055,"Deleted - IMS Enhancements Rel-8","IMS8",1,"Rel-8","S1","2007-09-03","2007-12-14",1,"-","-","Telecom Italia","-","SP#38 stopped","-",37,null,"SP-38",null,"2007-10-30","2009-03-24"]
[7531,400023,"Deleted - Contact Manager Conformance Test specifications","eUPHBOOK-Test",1,"Rel-8","C6","2008-06-02","2010-03-19",1,"CP-080430","-","Comprion, Gemalto","Udo Willenbrink, Jacques Seif","CP#47 work stopped/abandoned","-",40,21,"CP-47","PCG-24","2006-01-24","2010-03-09"]
[7535,0,"Release 8 Studies","-",1,"Rel-8","CP,GP,RP,SP","2005-10-07","2005-10-07",1,"-","-","-","-","-","-",null,null,null,null,"2004-09-08","2010-02-09"]
[7538,31089,"Study on Network Composition","FS_NetComp",1,"Rel-8","S1","2005-12-07","2007-12-12",1,"SP-060478","-","Nokia Siemens Networks","joerg.swetina@neclab.eu","SP#38 completed",22.98,null,null,null,null,"2005-12-12","2008-03-24"]
[7542,340033,"Study on Non-3GPP access Network Selection Principles (NSP)","FS_N3GtoNSP",1,"Rel-8","S1","2006-12-06","2008-06-05",1,"SP-080318","-","Telefónica O2","chris.friel@O2.com","SP#38 completed. Spin-off New Feature UID_380062 (N3GTONSP). SP#40 WID updated SP-060930=>SP-080318. TR re-approved with new # 22.812=>22.912",22.911999999999999,34,null,null,null,"2006-10-06","2008-06-03"]
[7544,340035,"Study on Service continuity between mobile and WLAN networks","FS_SMLSWLAN",1,"Rel-8","S1","2006-12-06","2007-12-06",1,"SP-060936","-","NEC","joerg.swetina@neclab.eu","SP#38 completed",22.937000000000001,34,null,null,null,"2006-10-06","2010-08-31"]
[7550,320028,"Study on Stage 2 aspects of IMS Service Brokering","FS_ISB_ST2",1,"Rel-8","S2","2006-06-19","2008-09-18",1,"SP-060443","-","Telcordia","raquel@research.telcordia.com","SP#41 completed. No spin-off activity proposed. [Note: IMS Service Brokering enhancements UID_31088 moved back from R8 to R7 to give a home to 22228CR0036_(Rel-7)_S1-051232. Hence, Rel-7 ISB has Stage 1 only (and is misaligned with Rel-7 Stages 2/3.]",23.81,null,null,null,null,"2006-07-17","2008-09-14"]
[7553,380034,"Study on centralized IMS service control","FS_ICS",1,"Rel-8","S2,S1","2006-10-23","2008-03-12",1,"SP-070494","-","Ericsson","peter.bleckert@ericsson.com","SP#39 completed","-",38,21,null,null,"2007-10-31","2008-03-20"]
[7557,380085,"Study on Home (e)NodeB Security","FS_HNB_Sec",1,"Rel-8","S3","2007-12-20","2009-03-12",1,"SP-070783","-","Huawei","yangyanmei@huawei.com","SP#43 completed. Linked to RAN4 Study on 3G Home NodeB/eNodeB (UID_350039) and to SA5 Study on Self-Organizing Networks (SON) related OAM interfaces for Home NodeB (UID_360007)",33.82,38,21,null,null,"2007-12-20","2009-03-11"]
[7558,360015,"Study on Transferring of emergency call data – in-band modem solution","eCALLIBMS",1,"Rel-8","S4","2006-12-07","2007-12-12",1,"SP-060935","-","Airbiquity","lhong@airbiquity.com","SP#38 completed. Spin-off WID UID_34042 (eCall_Phase2)",26.966999999999999,null,null,null,null,"2006-12-10","2008-05-16"]
[7562,340036,"Study on Management for LTE and SAE","FS_OAM_LTE_SAE",1,"Rel-8","S5","2006-12-07","2008-12-11",1,"SP-060753","-","Ericsson","robert.petersen@ericsson.com ","SP#42 completed",32.816000000000003,34,null,null,null,"2006-12-15","2008-11-25"]
[7565,350018,"Study on IMS Restoration Procedures","FS_IMS_RP",1,"Rel-8","C4","2007-03-26","2008-05-30",1,"CP-070031","-","Ericsson","german.blanco@ericsson.com","CP#40 completed. Spin-off WID UID_400012 (IMS_RP)",23.82,null,null,null,null,"2007-03-29","2008-05-29"]
[7569,370041,"Study on Scope of future HSPA Evolution for 1.28 Mcps TDD","FS_RAN-LCRTDDHSPAEvo",1,"Rel-8","R1","2007-09-14","2008-05-30",1,"RP-070748","RP-080290","RITT","Xu Fei","RP#40 completed",25.824000000000002,37,null,null,null,"2007-06-21","2008-06-12"]
[7571,360016,"Study on Improved network controlled mobility between LTE and 3GPP2/mobile WiMAX radio technologies","FS_RAN-LTEmob",1,"Rel-8","R4","2007-06-04","2007-12-03",1,"RP-070511","RP-070827","Motorola","hao.bi@Motorola.com","RP#38 completed",36.938000000000002,null,null,null,null,"2007-06-21","2008-06-26"]
[7577,370044,"Deleted - equals 340035 -FS on Service continuity between mobile and WLAN networks","FSSCMobToW",1,"Rel-8","S1","2007-09-03","2007-12-14",1,"SP-070557","-","BT","mike.meyerstein@bt.com","SP#39 stopped",22.937000000000001,37,null,"SP-39","PCG-21","2007-10-02","2009-03-24"]
[7580,390032,"Deleted - Study on Dual-Cell HSDPA operation","FS_RAN-DCHS",1,"Rel-8","R1","2007-08-15","2009-03-06",1,"RP-080228","RP-090066","Qualcomm","Josef Blanz","RP#43 stopped (draft TR 25.825 v100 withdrawn). Conclusions in RP-090318 (RAN1 findings of the UTRA Multi-Carrier Evolution study). RP#42 New WI approved on Dual-Cell HSDPA operation on adjacent carriers (UID_400052)","withdrawn 25.825 v100",39,21,"RP-43","PCG-22","2007-12-17","2009-03-17"]
[7584,32107,"   Stage 1,2 of ServID","ServID",2,"Rel-7","S1,S2","2005-11-11","2006-05-31",1,"SP-060293","-","Ericsson","stephen.terrill@ericsson.com","-","22.228; 23.228; 23.203",null,null,null,null,"2005-07-01","2008-07-01"]
[7585,320010,"   Stage 3 of ServID","ServID",2,"Rel-7","C1","2006-03-31","2007-03-15",1,"CP-060259","-","Ericsson","christer.holmberg@ericsson.com","CP#32 approved WID","23.218; 24.229",null,null,null,null,"2006-03-20","2008-07-01"]
[7588,7009,"   Deleted - TR on GRUU","GRUU",2,"Rel-7","S2","2005-11-14","2006-09-14",1,"SP-050633","-","Research In Motion","Adrian Buckley (abuckley@rim.com)","Abandoned","-",null,null,"SP-32",null,"2006-02-16","2008-07-01"]
[7593,7037,"   Stage 3 of MTSI","MTSI",2,"Rel-7","C1","2006-03-10","2007-06-14",1,"CP-060257","-","Ericsson","christer.holmberg@ericsson.com","-",24.172999999999998,null,null,null,null,"2006-03-22","2008-06-25"]
[7596,690071,"   UE Conformance Test Aspects – Multimedia Telephony Services for IMS (MTSI) over WLAN","MTSI_WLAN-UEConTest",2,"Rel-7","R5","2015-09-15","2016-12-15",1,"RP-151770",null,"Ericsson",null,"tested: REL-7 WI MTSI¦1/1/16: Compl:0%->5%1/1/16: WID: RP-151334->RP-15177022/3/16: Compl:5%->10% ",null,69,35,null,null,"2015-09-29","2016-12-20"]
[7599,377001,"TISPAN requirements for Multimedia Telephony with PSTN/ISDN simulation services","TMMTEL7",1,"Rel-7","S1","2007-09-18","2007-12-06",1,"SP-070568","-","-","-","-","22.273 (EI 181 002 maintenance)",37,null,null,null,"2008-01-10","2008-01-10"]
[7602,387003,"   SA2 aspects of MCIMSTR1","MCIMSTR1-S2",2,"Rel-7","S2","2007-09-18","2007-12-06",1,"SP-070915","-","Ericsson","Raymond Forbes","-","23.406; 23.417; 23.508.23.509; 23.511",38,21,null,null,"2008-01-10","2008-07-21"]
[7607,32046,"   Study on Stage 2 for IMS-level solution","EMC1",2,"Rel-7","S2","2003-02-26","2005-09-16",1,"SP-050604","-","Siemens","Rainer Liebhart","-",23.867000000000001,null,null,null,null,"2003-03-27","2005-12-22"]
[7611,1653,"   Emergency Call Enhancements for IP& PS Based Calls – stage 3","EMC1",2,"Rel-7","C1,C4,IETF","2006-01-09","2011-12-09",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","-","-",null,null,null,null,"2000-08-08","2005-12-22"]
[7612,1315,"      CT1 IMS aspects to support IMS Emergency sessions","EMC1",3,"Rel-7","C1","2006-01-09","2007-06-15",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","-",24.228999999999999,null,null,null,null,"2000-04-19","2007-09-12"]
[7615,13031,"      Deleted - CT3 PS domain aspects to support IMS Emergency sessions","EMC1",3,"Rel-7","C3","2006-05-08","2006-09-15",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","Cancelled for Rel-7 and there is no corresponding Rel-8 WI",29.061,null,null,"CP-33",null,"2000-08-08","2008-07-01"]
[7620,31062,"WLAN-UMTS Interworking Phase 2","WLAN2",1,"Rel-7","S1,S2","2004-01-05","2005-06-07",1,"SP-030712","-","Telenor","frederic.paint@telenor.com","Created at SP#27 because of WLAN items belonging to Rel-7. Acronym changed from \"WLAN2, WLAN-SC\"","33.234 (SP-36 SA3 CRs approved)",null,null,null,null,"2005-03-09","2015-03-24"]
[7623,32110,"WLAN Interworking – Private Network access from WLAN 3GPP IP Access","WLANPNA",1,"Rel-7","S2,C1,C3,C4","2005-10-10","2006-09-26",1,"SP-050489","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","-","-",null,null,null,null,"2003-03-28","2005-10-07"]
[7626,11064,"      CT1 aspets for WLAN-PNA","WLANPNA-st3",3,"Rel-7","C1","2006-02-01","2006-09-26",1,"CP-060256","-","NEC","-","Approved at CP#29",24.234000000000002,null,null,null,null,"2005-12-22","2006-05-31"]
[7629,32092,"Enhancements to support QoS provisioning over 3GPP/WLAN Interworking","WLANQOS",1,"Rel-7","S2,C4,C1","2005-03-14","2007-03-09",1,"SP-050682","-","Samsung","-","Moved from FS section Feb 06. SP-30 updated WID","-",null,null,null,null,"2005-06-07","2008-07-18"]
[7634,32079,"Location Services enhancements","LCS3",1,"Rel-7","S1,S2,GP,C4,R2","2004-06-28","2007-12-17",1,"SP-040682","-","-","-","-","-",null,null,null,null,"2002-06-21","2008-07-02"]
[7637,14025,"   CT4 aspects for LCS UEPos-LBS","LCS3-UEPos-LBS",2,"Rel-7","C4","2006-01-02","2006-12-01",1,"CP-050240","-","SiRF","brodilitz@sirf.com","-","24.030; 24.080; 29.002",null,null,null,null,"2005-06-20","2008-07-02"]
[7638,20042,"   UE positioning - Velocity","LCS3-UEPos-Velocity",2,"Rel-7","R2","2005-03-15","2006-09-15",1,"RP-050300","RP-060459","SiRF","BRodilitz@SiRF.com","-","25.305; 25.331; 25.410; 25.413; 25.453",null,null,null,null,"2005-06-20","2008-07-02"]
[{"$f":"A7642+1","v":7642},32108,"      Deleted - Study of work on an LCS architecture for I-WLAN.","LCS3-IWLAN-FSs2",3,"Rel-7","S2","2006-06-26","2007-03-02",1,"SP-060291","-","LG Electronics","dhshim@lge.com ; phede@lge.com","SP#41 TR withdrawn. All work transferred to specs",23.837,null,null,"SP-35",null,"2006-02-16","2008-07-02"]
[7646,340041,"   Stage 1 of MBMSE","MBMSE",2,"Rel-7","S1","2005-07-11","2005-12-08",1,"SP-050389","-","China Mobile","liuhongyfw@chinamobile.com","-","22.146; 22.246; 22.228",34,null,null,null,"2005-06-20","2008-04-15"]
[7651,400058,"MBMS - UE Conformance Testing","MBMSE_UEConTest",1,"Rel-7","R5","2007-06-01","2009-12-04",1,"-","-","-","-","Linked to Rel-7 Feature UID_31084 (MBMSE)","-",40,21,null,null,"2008-03-11","2009-04-01"]
[7653,400059,"   Conformance Test Aspects – MBMS LCR TDD Physical Layer Enhancement","MBMSE-RANPhysLCRTDD_UEConTest",2,"Rel-7","R5","2008-05-30","2009-09-18",1,"RP-080318","RP-090715","CATT","chenxiaozhong@datangmobile.cn","RP#45 completed","34.108; 34.123-1",40,21,null,null,"2008-06-03","2009-09-11"]
[7656,31051,"Advanced Global Navigation Satellite System (AGNSS) concept","LCS3-AGNSS",1,"Rel-7","S1,S2,GP,R2","2004-06-28","2007-08-31",1,"SP-040681","-","Alcatel","Michel.monnerat@thalesaleniaspace.com","-","-",null,null,null,null,"2004-08-30","2008-06-25"]
[7661,31048,"Unstructured Supplementary Service Data (USSD) message delivery and transfer to USIM","USSD-USIM",1,"Rel-7","S1,C6","2004-03-05","2005-08-12",1,"SP-040104","-","Axalto","Christophe Dubois (cdubois@axalto.com)","-","-",null,null,null,null,"2004-06-08","2008-09-10"]
[7664,31063,"Combinational Services ","CSICS",1,"Rel-7","S1,S2,C1,S4","2005-01-17","2006-03-06",1,"SP-050228","-","TeliaSonera","Robert.Frank@teliasonera.com","-","-",null,null,null,null,"2004-12-17","2008-07-02"]
[7665,31064,"   Stage 1 for CSICS","CSICS",2,"Rel-7","S1","2005-01-17","2005-06-09",1,"SP-050228","-","TeliaSonera","Robert.Frank@teliasonera.com","-",22.279,null,null,null,null,"2005-02-28","2008-07-02"]
[7669,31065,"CAMEL Trunk Triggers","TTCAMEL",1,"Rel-7","S1,C4","2004-12-17","2005-12-05",1,"SP-040743","-","Nortel","Amar Deol (deola@nortelnetworks.com)","-","-",null,null,null,null,"2004-12-17","2008-07-18"]
[7673,320027,"   Stage 1 for ISB","ISB-s1",2,"Rel-7","S1","2005-12-07","2006-03-13",1,"SP-050830","-","Telcordia","jbakker@telcordia.com","No Rel-8 changes",22.228000000000002,null,null,null,null,"2005-11-04","2008-03-25"]
[7678,14022,"      CT4 aspects of EVGCS","EVGCS",3,"Rel-7","C4","2004-08-27","2006-03-10",1,"CP-050528","-","Siemens","robert.zaus@nsn.com","-",29.001999999999999,null,null,null,null,"2005-09-14","2007-03-08"]
[7680,11055,"Improvements of VGCS for parallel use of services","IVGCS",1,"Rel-7","S1","2005-03-15","2007-03-15",1,"SP-070167","-","-","-","Voice Group Call Service","-",null,null,null,null,"2005-03-02","2007-03-26"]
[7684,11063,"      CT1 aspects of IVGCS","IVGCS",3,"Rel-7","C1","2005-12-01","2007-03-15",1,"CP-070118","-","T-Mobile","-","-","43.068; 44.068",null,null,null,null,"2005-09-14","2007-09-12"]
[7687,31172,"   OSA Service Broker","OSA7-SB",2,"Rel-7","S1,C5","2005-03-15","2006-12-01",1,"SP-050183","-","AePONA","eamonn.murray@aepona.com","-","-",null,null,null,null,"2005-03-22","2006-02-16"]
[7689,43011,"      Stage 2 OSA API Service Brokering","OSA7",3,"Rel-7","C5","2006-04-28","2006-12-01",1,"CP-070200","-","AePONA","damian.oneill@aepona.com","-",23.198,null,null,null,null,"2005-03-22","2012-07-26"]
[7692,7018,"      Parlay X Message Broadcast Web Service","OSA7",3,"Rel-7","C5","2006-04-28","2006-12-01",1,"CP-070200","-","ETRI","-","-","29.199-15; 23.198",null,null,null,null,"2006-03-01","2012-07-26"]
[7696,340002,"      Parlay-X Multimedia Streaming Session Management Web Service","OSA7",3,"Rel-7","C5","2006-10-26","2007-03-09",1,"CP-070200","-","Telenor","-","-","29.199-19; 23.198",34,null,null,null,"2006-10-26","2012-07-26"]
[7700,32088,"   Stage 1 of SDoUE","SDoUE-CR",2,"Rel-7","S1","2005-01-24","2006-12-08",1,"SP-050182","-","Motorola","-","Moved from FS section Feb 06",22.010999999999999,null,null,null,null,"2004-08-30","2008-07-17"]
[7705,320013,"   Procedural aspects of NSP","NSP-CR",2,"Rel-7","C1","2006-06-02","2007-06-15",1,"CP-060357","-","Motorola","Andrew Howell","-","23.122; 24.008; 31.102",null,null,null,null,"2006-06-21","2007-05-04"]
[7707,32064,"Access Class Barring and Overload Protection","ACBOP",1,"Rel-7","S2,C1","2004-03-15","2006-09-08",1,"SP-040338","-","Vodafone","chris.pudney@vodafone.com","-",23.898,null,null,null,null,"2004-04-14","2008-07-15"]
[7711,20009,"   Deleted - Extra ACBOP information in RAN","ACBOP",2,"Rel-7","RP","2004-03-15","2004-03-15",1,"-","-","-","-","-",25.331,null,null,"RP-25",null,"2004-04-14","2004-10-13"]
[7714,7001,"   TISPAN Rel 1 related aspects","FBI-TIS1",2,"Rel-7","S2,S3,C1,C3,C4,IETF","2003-11-05","2011-12-09",1,"-","-","-","-","-","-",null,null,null,null,"2006-02-16","2006-02-16"]
[7716,11050,"      Protocol impact of FBI for TISPAN R1","-",3,"Rel-7","S3,C1,C3,C4,IETF","2003-11-05","2011-12-09",1,"NP-040618","-","Siemens","peter.leis@nsn.com","-","-",null,null,null,null,"2004-09-03","2006-02-16"]
[7719,13025,"         CT3 aspects of FBI for TISPAN R1","-",4,"Rel-7","C3","2003-11-05","2006-12-08",1,"NP-040618","-","Siemens","peter.leis@nsn.com","-","29.163; 29.209",null,null,null,null,"2004-09-03","2006-10-12"]
[7723,7003,"      Stage 1,2 of FBI for PacketCable","-",3,"Rel-7","S2","2006-02-01","2006-12-15",1,"SP-060145","-","CableLabs","Bernie McKibben (b.mckibben@cablelabs.com)","-","22.228; 23.228",null,null,null,null,"2006-02-16","2006-09-19"]
[7727,32094,"   FS on SMSIP","-",2,"Rel-7","S2","2004-10-14","2005-06-13",1,"SP-060658","-","Huawei","zhangwenlin@huawei.com","SP#33 updated WID",23.803999999999998,null,null,null,null,"2005-06-07","2008-07-15"]
[7730,310002,"      CT1 aspects for SMSIP","-",3,"Rel-7","C1","2005-06-08","2007-06-14",1,"CP-060697","-","Nokia","jari.jansson@nokia.com","CP#34 updated WID","23.040; 24.229",null,null,null,null,"2006-04-13","2008-07-15"]
[7732,32082,"Evolution of Policy Control and Charging","PCC",1,"Rel-7","S2,S5,C3,C1","2004-10-14","2007-11-30",1,"SP-060217","-","Nokia","balazs.bertenyi@nsn.com","SP-29 approved WID. SP-31 updated WID adding SA5 charging. 23.125 will be discontinued from Rel-7.","-",null,null,null,null,"2004-10-14","2008-07-18"]
[7738,13030,"   Rx reference point for PCC CT3 aspects","PCC-Rx",2,"Rel-7","C3,C1","2005-12-02","2007-11-30",1,"CP-060435","-","Ericsson","j.javier.pastor@ericsson.com","WID approved at CP#30, Revised at CP#31, Revised at CP#33","-",null,null,null,null,"2005-12-13","2008-07-18"]
[7741,32091,"Voice Call Continuity between CS and IMS (incl. I-WLAN)","VCC",1,"Rel-7","S2,S1,S5,C1,C4","2004-12-31","2007-06-15",1,"SP-060292","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","WID approved SP#27¦updated SP#28¦updated SP#32","-",null,null,null,null,"2005-06-07","2008-07-21"]
[7743,31085,"   Stage 1 for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",2,"Rel-7","S1","2005-03-17","2005-09-28",1,"SP-060292","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","-",22.100999999999999,null,null,null,null,"2005-09-19","2008-07-21"]
[7746,11058,"   Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",2,"Rel-7","C1,C4","2006-02-01","2007-06-15",1,"CP-070186","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","-","-",null,null,null,null,"2005-10-04","2008-07-21"]
[7750,7046,"One Tunnel solution for optimization of Packet Data Traffic","OPTUNEL",1,"Rel-7","S2","2006-03-27","2007-10-31",1,"SP-060819","-","Nokia","antti.j.pasanen@nokia.com","-","-",null,null,null,null,"2006-03-22","2008-07-15"]
[7754,320029,"CSI Terminating Session handling","CSItermS",1,"Rel-7","S2,C1","2006-06-08","2007-06-15",1,"SP-060437","-","Samsung","Osok Song","Triggered by the abandoned Study UID_32117 ","-",null,null,null,null,"2006-07-19","2008-07-17"]
[7757,340011,"   Deleted - duplicated with UID 340015 -Stage 3 CSI Terminating Session handling","-",2,"Rel-7","C1","2007-03-09","2007-03-09",1,"CP-060647","-","Samsung","chenho.chin@samsung.com","CP-34 approved WID ","24.229; 24.179; 24.279",34,null,"CP-34",null,"2006-12-18","2008-07-17"]
[7759,33023,"Trust Requirements for Open Platforms in 3GPP","TrustOP",1,"Rel-7","S3","2005-01-03","2006-11-30",1,"SP-040863","-","Nokia","Silke.Holtmanns@nokia.com","WID approved SP#26. ",33.905000000000001,null,null,null,null,"2005-03-24","2008-07-16"]
[7765,732031,"   HTTPS connection between a UICC and a NAF","SEC7-HSUN",2,"Rel-7","S3,C1","2005-09-12","2005-09-12",1,"SP-050573","-","Gemalto","JSeif@axalto.com, mireille.pauliac@gemplus.com","-","33.918; 33.222; 24.109",null,null,null,null,"2005-11-04","2008-07-16"]
[7768,32034,"   SS7 TCAP security Gateway","SEC7-NDS-TCAPsec",2,"Rel-7","S3,C4","2005-09-12","2006-08-14",1,"SP-050579","-","Siemens","marc.blommaert.ext@nsn.com","-","-",null,null,null,null,"2005-11-04","2008-07-16"]
[7772,7043,"Interoperability between VGCS/VBS and A/Gb flexibility","VGCSFlex",1,"Rel-7","C1,C4","2006-03-22","2007-03-09",1,"CP-060102","-","Siemens","robert.zaus@nsn.com","Voice Group Call Service","-",null,null,null,null,"2006-03-22","2008-07-21"]
[7773,7044,"   CT1 aspects of VGCSFlex","-",2,"Rel-7","C1","2006-03-22","2006-10-30",1,"CP-060102","-","Siemens","robert.zaus@nsn.com","-","43.068; 43.069",null,null,null,null,"2006-03-22","2008-07-21"]
[7776,13022,"DIAMETER on the PDG Wi interface","DIAMWi",1,"Rel-7","C3","2004-09-10","2006-12-08",1,"CP-060432","-","Vodafone","Nico.Gabriele@vodafone.com","-",29.161000000000001,null,null,null,null,"2005-01-18","2008-07-15"]
[7781,13026,"   Deleted - CT3 aspects of Mp","-",2,"Rel-7","C3","2006-09-22","2006-09-22",1,"-","-","Ericsson","philip.hodges@ericsson.com","CP#34: CT3 not involved in Mp interface definition",29.161999999999999,null,null,"CP-33",null,"2003-01-13","2008-07-15"]
[7784,340016,"Routeing of MT-SMS via the HPLMN","SMSviaH",1,"Rel-7","C4,C1","2006-12-01","2007-03-09",1,"CP-070032","-","Vodafone","Nick.Russell@vodafone.com","WID approved in CP#34","23.040; 29.002",34,null,null,null,"2005-10-07","2007-09-12"]
[7786,743009,"ISIM API for Java Card","APIJAVA",1,"Rel-7","C6","2005-03-14","2007-07-27",1,"CP-050145","-","Sun","Sebastian Hans","-","31.103; 102 241",74,38,null,null,"2005-11-04","2007-09-12"]
[7792,34035,"Optimizations for Multimedia Telephony over IMS","OMTIMS",1,"Rel-7","S4","2005-09-28","2005-09-29",1,"SP-060226","-","Ericsson","olle.franceschi@ericsson.com","Aug2015: 99%->100","26.235; 26.236",null,null,null,null,"2005-10-04","2015-08-12"]
[7795,34039,"Packet Switched Streaming Enhancements","PSSe",1,"Rel-7","S4","2006-06-08","2007-06-07",1,"SP-060361","-","Ericsson","olle.franceschi@ericsson.com","-","26.234; 26.244",null,null,null,null,"2006-01-24","2007-05-29"]
[7799,35046,"      Co-operative Element Management interface (CO-OP) (Study + Implementation)","-",3,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050304","-","Motorola","-","-","32.806; 32.814; 32.101",null,null,null,null,"2005-06-17","2007-03-29"]
[7800,35047,"      Network Management (NM) Itf-N performance criteria","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050305","-","China Mobile","-","-",32.811,null,null,null,null,"2005-06-17","2007-06-22"]
[7804,35052,"      Partial suspension of Itf-N during maintenance/testing (Study + Implementation)","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050310","-","Siemens","-","-","32.381/2/3/5",null,null,null,null,"2005-06-17","2007-06-22"]
[7808,35071,"      Repeater Network Resource Model (NRM) definition","-",3,"Rel-7","S5","2006-02-13","2006-12-07",1,"SP-050731","-","China Mobile","-","-","32.721/2/3/5",null,null,null,null,"2005-11-24","2007-03-29"]
[7811,35043,"   Rel-7 Performance Management","OAM7-PM",2,"Rel-7","S5","2005-09-02","2007-06-14",1,"-","-","-","-","-","-",null,null,null,null,"2005-06-17","2007-03-29"]
[7815,35060,"      ATM bearer network Performance measurements","-",3,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050318","-","ZTE","-","-","No impact on 32.404; 32.405; 32.406; 32.407 ",null,null,null,null,"2005-06-17","2007-03-29"]
[7817,35073,"      HSDPA performance measurements","-",3,"Rel-7","S5","2006-02-13","2007-06-14",1,"SP-060379","-","China Mobile","-","-",32.405000000000001,null,null,null,null,"2005-11-24","2007-06-22"]
[7822,11046,"      Deleted - SIP enhancements for trace","-",3,"Rel-7","C1","2007-06-15","2007-06-15",1,"-","-","-","-","combined with UID 11067","-",null,null,"CP-32",null,"2004-03-01","2006-11-29"]
[7823,35070,"      Deleted - duplicated with UID 35063 - IRP for Subscriber and Equipment Trace Management","-",3,"Rel-7","S5","2005-09-02","2006-12-15",1,"SP-050629","-","Nokia","-","-","32.421.32.422.32.423; 3 new 32.4x1.2.3",null,null,"SP-33",null,"2005-03-02","2007-03-29"]
[7826,330004,"   Align 3GPP Charging with OMA PoC Enabler Release 2.0","CH7-PoC",2,"Rel-7","S5","2006-09-28","2007-06-14",1,"SP-060546","-","Siemens","Gerald.Goermer@nsn.com","09/2006 SP#33 WID approved","32.240; 32.272; 32.299; 32.298",null,null,null,null,"2006-10-09","2007-06-22"]
[7831,24008,"   MIMO - RF Radio Transmission/Reception, System Performance Requirements and Conformance Testing","MIMO-RF",2,"Rel-7","R4","2003-12-12","2007-09-17",1,"RP-030192","RP-070531","Alcatel-Lucent","ngm@Alcatel-Lucent.com","Completed Sep 2007¦SR in RP-070531","-",null,null,null,null,"2003-03-27","2008-06-24"]
[7835,20060,"   Extended UMTS 1.7/2.1 GHz","RInImp-UMTS1721Ext",2,"Rel-7","R4","2006-03-15","2006-12-15",1,"RP-060180","RP-060681","Ericsson","johan.skold@ericsson.com","RP#34 completed. Introduction of Band X (Extended UMTS 1.7/2.1 GHz) in 25.307","25.806; 25.101; 25.104; 25.133; 24.141; 25.331; 25.306; 25.307; 25.423; 25.461; 25.463; 34.121",null,null,null,null,"2006-03-21","2010-07-27"]
[7838,20025,"   UMTS 2.6 GHz TDD","RInImp-UMTS2600TDD",2,"Rel-7","R4","2004-12-15","2005-12-14",1,"RP-040553","RP-050661","IPWireless","Shin Horng Wong (shwong@ipwireless.com)","RP#30 completed","25.102; 25.105; 25.113; 25.123; 25.142; 25.331; 25.942; 25.306; 25.307; 34.122; 34.124",null,null,null,null,"2005-01-04","2010-07-27"]
[7842,20045,"   Improved Performance Requirements for HSDPA UE based on Rx Diversity (type 1) & LMMSE equalizer (type 2)","RInImp-HSPerf-Type3",2,"Rel-7","R4","2005-03-15","2005-03-15",1,"RP-050362","RP-060015","Cingular","Marc Grant","RP#27 completed",25.100999999999999,null,null,null,null,"2005-06-20","2010-07-27"]
[7844,20048,"      Additional minimum UE performance requirement for DL physical channels in support of DCH/HS-DSCH operation based on type 1 enhanced receiver (RX-Diversity)","RInImp-RxDiv-DCH",3,"Rel-7","R4","2005-09-15","2006-06-14",1,"RP-060185","RP-060235","Cingular","Marc Grant","RP#32 completed",25.100999999999999,null,null,null,null,"2005-10-05","2010-07-27"]
[7847,20049,"   Deleted Improved support of gaming over HSDPA/EDCH","RInImp-Gaming",2,"Rel-7","R2","2005-12-15","2006-12-15",1,"-","RP-060680","Cingular","Don Zelmer (dz1069@att.com)","RP#34 stopped. SR in RP-060680","-",null,null,"RP-34",null,"2005-12-15","2010-07-27"]
[7850,25007,"   UE Conformance Test for UMTS 2600 MHz","RInImp-UMTS2600_Test",2,"Rel-7","R5","2005-11-11","2006-06-02",1,"-","-","Nokia","Aleksi.Heino@nokia.com","RP#32 completed","34.108; 34.121",null,null,null,null,"2002-02-28","2006-03-21"]
[7853,25020,"   UE antenna Over The Air (OTA) conformance testing","RInImp-UEAnt_Test",2,"Rel-7","R5","2006-09-20","2008-09-12",1,"RP-060486","RP-080535","Nokia","Aleksi.Heino@nokia.com","RP#41 completed (GERAN aspects might need to be included later)",34.113999999999997,null,null,null,null,"2006-09-20","2008-09-14"]
[7858,20029,"Rel-7 RAN improvements","-",1,"Rel-7","RP,S5","2004-12-15","2007-06-15",1,"-","-","-","-","Generic feature","-",null,null,null,null,"2005-01-04","2008-06-25"]
[7861,20132,"   Improved support of IMS Realtime Services using HSDPA/HSUPA","RANimp-IMSRealTime",2,"Rel-7","R2","2005-03-15","2005-12-14",1,"RP-050160","RP-050667","Cingular","Don Zelmer (dz1069@att.com)","RP#30 completed","-",null,null,null,null,"2005-03-15","2010-07-27"]
[7866,330009,"   Enhanced CELL_FACH State in FDD","RANimp-EnhState",2,"Rel-7","R2","2006-09-25","2007-06-04",1,"RP-070245","RP-070286","Nokia","juho.pirskanen@nokia.com","RP#36 completed","25.308; 25.304; 25.306; 25.321; 25.331; 25.433; 25.435; 25.423; 25.425.",null,null,null,null,"2006-10-06","2010-07-27"]
[7869,340040,"   Introduction of 16QAM in HSUPA (FDD)","RANimp-16QamUplink",2,"Rel-7","R1","2006-12-15","2007-06-04",1,"RP-060844","RP-070288","Nokia","Karri.Ranta-aho@nsn.com","RP#36 completed","25.319; 25.101; 25.104; 25.133; 25.141; 25.211; 25.212; 25.213; 25.214; 25.306; 25.321; 25.331; 25.423; 25.433",null,null,null,null,"2006-10-06","2010-07-27"]
[7871,20166,"      RAN3 part of Interface to control Tower Mounted Amplifiers (TMAs)","-",3,"Rel-7","R3","2006-06-02","2007-03-16",1,"RP-060418","RP-070140","Vodafone","alexej.kulakov@vodafone.com","RP#35 completed","-",null,null,null,null,"2006-06-21","2010-07-27"]
[7874,25021,"   Conformance Test Aspects - 3.84 Mcps and 7.68 Mcps TDD Enhanced Uplink","RANimp-UEConTest_EDCHTDH",2,"Rel-7","R5","2006-09-20","2008-09-12",1,"RP-060484","RP-080536","IPWireless","tspeight@ipwireless.com","RP#41 completed","34.108; 34.122; 34.123-1; 34.123-2; 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[7877,25033,"   Conformance Test Aspects – Improved L2 support for high data rates","RANimp-UEConTest_L2DataRates",2,"Rel-7","R5","2007-03-09","2008-05-30",1,"RP-070020","RP-080256","Ericsson","leif.mattisson@ericsson.com","RP#40 completed","34.108; 34.123-1; 34.123-2; 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[7880,20014,"7.68 Mcps TDD option","VHCRTDD",1,"Rel-7","R1,R2,R3,R4,R5","2004-09-15","2007-09-14",1,"RP-060119","RP-060684","IPwireless","Martin Beale (mbeale@ipwireless.com)","RP#31 completed","-",null,null,null,null,"2004-09-27","2010-07-27"]
[7885,20019,"   VHCRTDD: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing","VHCRTDD-RF",2,"Rel-7","R4","2004-09-15","2006-06-15",1,"RP-060119","RP-060684","IPwireless","Shin Horng Wong (shwong@ipwireless.com)","RP#32 completed","25.102; 25.105; 25.123; 25.133; 25.142",null,null,null,null,"2004-09-27","2010-07-27"]
[7888,20036,"   EDCHTDD: Stage 2","EDCHTDD-Stage2",2,"Rel-7","R2","2005-03-15","2006-06-15",1,"-","RP-060462","IPwireless","nanderson@ipwireless.com","RP#33 completed","-",null,null,null,null,"2005-03-15","2010-07-27"]
[7893,20055,"1.28 Mcps TDD Enhanced Uplink","LCRTDD-EDCH",1,"Rel-7","R1,R2,R3,R4,R5","2006-03-15","2008-09-12",1,"RP-060202","RP-070296","CATT","Haijing Hu","RP#35 completed","-",null,null,null,null,"2006-03-21","2010-07-27"]
[7896,20058,"   1.28 Mcps TDD Enhanced Uplink: UTRAN Iub/Iur Protocol Aspects","LCRTDD-EDCH-IubIur",2,"Rel-7","R3","2006-03-15","2007-03-15",1,"-","RP-070038","CATT","Yincheng Zhang","RP#35 completed","25.401; 25.420; 25.423; 25.425; 25.427; 25.430; 25.433; 25.435",null,null,null,null,"2006-03-21","2010-07-27"]
[7899,490016,"Conformance Test Aspects – Multiple Band and Multiple Frequency operation for LCR TDD","LCRTDD_MB_MF_UEConTest",1,"Rel-7","R5","2010-09-17","2011-09-16",1,"RP-100805","RP-110968","CATR","Ms Jun Chen (chenjun@catr.cn)","RP#53 completed. Core specification was introduced via Rel-7 CR under TEI7 (RP#37 RP-070650) and via 2 Rel-8 work items: RInImp9-UMTS1880TDD and RInImp8-UMTS2300TDD.","UTRA 34.108; 34.123-1; 34.123-2; 34.123-3",49,25,null,null,"2010-09-08","2011-09-06"]
[7902,51138,"   Inclusion of the 698 – 746 MHz band into GERAN core specifications","GSM710-core",2,"Rel-7","G1","2005-01-03","2005-06-30",1,"-","-","-","-","Completed","24.008; 43.022; 44.018; 44.118; 45; 001; 45.005; ",null,null,null,null,"2005-09-12","2005-09-15"]
[7904,53084,"      G1 aspects of GSM710","-",3,"Rel-7","G1","2005-08-31","2006-06-30",1,"-","-","-","-","-",51.021000000000001,null,null,null,null,"2005-09-12","2006-07-20"]
[7907,52143,"   Minimise the transfer delay between the SGSN and the MS","SCSAGB-MTD",2,"Rel-7","GP","2005-04-08","2007-08-31",1,"GP-061501","-","Ericsson","gunnar.hedby@ericsson.com","-","-",null,null,null,null,"2006-05-03","2008-01-10"]
[7911,52139,"   Deleted- Modifications to FLO","SCSAGB-FLO",2,"Rel-7","G2","2006-07-17","2006-07-17",1,"GP-051165","-","Ericsson","gunnar.hedby@ericsson.com","-","-",null,null,"SP-32",null,"2005-04-21","2006-03-09"]
[7915,53082,"   Changes to BTS testing specification","TGSM810-BTStest",2,"Rel-7","G1","2005-04-08","2005-11-11",1,"GP-050948","-","Huawei","chende@huawei.com","-",51021,null,null,null,null,"2005-04-21","2005-12-22"]
[7920,50569,"Mobile Station Receive Diversity (DARP Phase II)","MSRD2",1,"Rel-7","GP","2005-11-11","2007-11-16",1,"GP-061491","-","Nokia","kent.pedersen@nokia.com","GP#36 completed","-",null,null,null,null,"2005-11-21","2008-05-19"]
[7923,50573,"   Test Scenarios for Mobile Station Receive Diversity, DARP Phase II ","MSRD2-TestSc",2,"Rel-7","GP","2005-11-11","2007-02-16",1,"GP-060117","-","Nokia","kent.pedersen@nokia.com","GP#33 completed",45.005000000000003,null,null,null,null,"2005-11-21","2007-03-08"]
[7926,51139,"   Downlink Dual Carrier Stage 2","GDCDL-Stage2",2,"Rel-7","G1","2006-01-20","2006-06-30",1,"GP-060484","-","Nokia Siemens Networks","leonardo.provvedi@roke.co.uk","GP#30 completed","43.055; 43.064",null,null,null,null,"2006-01-24","2009-04-01"]
[7929,50580,"Support of SIGTRAN in GERAN","GSIGT",1,"Rel-7","GP","2006-01-20","2006-06-30",1,"GP-060450","-","Ericsson","peter.ostrup@ericsson.com","GP#30 completed","48.001; 48.006; 43.059; 49.031",null,null,null,null,"2006-01-24","2009-04-02"]
[7931,52145,"   Improved Ack/Nack reporting","LATRED-ACKNAR",2,"Rel-7","G2","2006-06-30","2007-08-31",1,"GP-061520","-","Ericsson","Hakan.Persson@Ericsson.com","GP#35 completed","45.001; 45.002; 45.003; 45.005; 45.010; 43.055; 43.064; 44.060; 51.010-1; 51.021",null,null,null,null,"2006-07-05","2008-12-15"]
[7934,50584,"Higher Uplink performance for GERAN Evolution ","HUGE",1,"Rel-7","GP","2006-09-08","2011-05-20",1,"GP-071083","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#39 completed","-",null,null,null,null,"2006-09-13","2010-07-26"]
[7938,51142,"   Performance requirements for HUGE","HUGE-Perfreq",2,"Rel-7","G1","2006-09-08","2008-08-29",1,"GP-061905","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#39 completed",45.005000000000003,null,null,null,null,"2006-09-13","2008-12-15"]
[7942,51144,"   Stage 2 for REDHOT","REDHOT-Stage2",2,"Rel-7","G1","2006-11-17","2007-08-31",1,"GP-062489","-","Ericsson, Nokia Siemens Networks, Marvell","stefan.g.eriksson@ericsson.com","GP#35 completed","43.055; 43.064",null,null,null,null,"2006-11-20","2008-12-15"]
[7946,60110,"(Small) Technical Enhancements and Improvements for Rel-7","TEI7",1,"Rel-7","SP,CP,RP,GP","2007-03-26","2007-03-26",1,"-","-","-","-","-","-",null,null,null,null,"2005-11-04","2006-04-20"]
[7947,25030,"Test - (Small) Technical Enhancements and Improvements for Rel-7","TEI7_Test",1,"Rel-7","R5","2006-06-02","2007-11-28",1,"-","-","-","-","-","-",null,null,null,null,"2010-05-26","2010-05-26"]
[7953,11035,"   Deleted - Stage 3 for IMS Local services","-",2,"Rel-7","C1","2006-01-06","2006-01-06",1,"-","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","-","-",null,null,"SP-25",null,"2003-01-13","2004-09-09"]
[7954,32078,"Deleted - IMS Phase 3","-",1,"Rel-7","S2","2006-01-06","2006-01-06",1,"-","-","-","-","-","-",null,null,"SP-25",null,"2004-09-08","2004-09-09"]
[7960,31050,"Study on Behaviour of Multi system UEs","BMSU",1,"Rel-7","S1","2004-06-28","2005-12-15",1,"SP-050502","-","Qualcomm","dwilliams@qualcomm.com","-",22.936,null,null,null,null,"2004-08-30","2008-06-27"]
[7961,31055,"Study on Combining CS calls and IMS sessions","IRTSD-CS_IMS",1,"Rel-7","S1","2004-06-28","2005-03-17",1,"SP-040467","-","TeliaSonera","robert.frank@teliasonera.com","-",22.978999999999999,null,null,null,null,"2004-08-30","2010-07-27"]
[7965,31041,"Study on Multimedia Priority Service","PRIOR-MM",1,"Rel-7","S1","2003-03-28","2006-06-30",1,"SP-060329","-","Telcordia","James Garrahan (jgarraha@telcordia.com)","Spin-off Feature PRIOR UID_340044",22.952999999999999,null,null,null,null,"2003-03-28","2010-08-31"]
[7969,35067,"Study on Itf-N Implementation Conformance Statement (ICS) template","OAM7-NIM-ICS",1,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050609","-","China Mobile","Li Yewen (liyewen@chinamobile.com)","SP#35 completed",32.811999999999998,null,null,null,null,"2005-09-16","2007-03-29"]
[7973,7025,"Feasibility Study on the TCAPsec Gateway concept","FS_SEC7-TCAP",1,"Rel-7","C4","2005-10-28","2006-03-10",1,"CP-050687","-","Siemens","Ulrich.wiehe@gksag.de","TR 29.800 content moved to TS 29.204 under implementation WI UID_310005 TCAPsec Gateway",29.8,null,null,null,null,"2005-10-07","2008-07-01"]
[7974,7050,"Study on using M2PA in 3GPP network ","FS-M2PA",1,"Rel-7","C4","2006-03-22","2007-06-08",1,"CP-060698","-","China Mobile","zhaoyuyi@chinamobile.com","-",29.800999999999998,null,null,null,null,"2006-03-22","2008-07-01"]
[7980,20041,"Study on UTRA Tower Mounted Amplifier (FDD)","RANFS-TMA",1,"Rel-7","R4","2005-06-15","2006-03-14",1,"RP-050387","RP-060035","Ericsson","Klas.Sjerling@ericsson.com","RP#31 (Mar 2006) completed. SR in RP-060035",25.818000000000001,null,null,null,null,"2005-06-20","2010-07-27"]
[7981,20044,"Study on Continuous connectivity for packet data users","RANFS-cont-packet",1,"Rel-7","R1","2005-03-15","2005-09-14",1,"RP-050391","RP-050427","Siemens","joerg.gustrau@siemens.com","RP#29 (Sep 2006) completed. SR in RP-050427","none",null,null,null,null,"2005-06-20","2008-06-23"]
[7987,50568,"Study on Future GERAN Evolution","FGE",1,"Rel-7","GP","2005-04-08","2007-02-16",1,"GP-051052","-","Nokia","eddie.riddington@nokia.com","GP#33 completed",45.911999999999999,null,null,null,null,"2005-04-21","2007-03-08"]
[7989,31054,"Deleted - Study on IMS with real time services deployment","IRTSD",1,"Rel-7","S1","2004-06-28","2005-09-12",1,"SP-040465","-","-","-","-","-",null,null,"SP-30",null,"2004-08-30","2008-06-27"]
[7992,732028,"Deleted - IMS security extensions (covered by UID33027)","IMS-SE",1,"Rel-7","S3","2005-12-08","2005-12-08",1,"SP-050395","-","Ericsson","Bengt.Sahlin@ericsson.com","-","-",null,null,"SP-30",null,"2005-06-20","2005-12-22"]
[7996,32076,"Deleted - Study on Stage 2 (IMS services using CS bearers)","IRTSD-IMSCS",1,"Rel-7","S2","2004-06-28","2005-09-12",1,"SP-040479","-","Nortel","Mark Watson","SP-30: S2 has no intention for TR completion",23.899000000000001,null,null,"SP-30",null,"2004-08-30","2008-06-26"]
[8000,32117,"Deleted - Study on Terminating Session handling","CSIterm",1,"Rel-7","S2","2006-01-09","2006-12-29",1,"SP-050811","-","Samsung","-","SP#32 Jun 2006 Study abandoned => spin-off Implementation work UID_320029",23.818999999999999,null,null,"SP-32",null,"2005-12-20","2008-06-30"]
[8003,360009,"Deleted - Study on Interference Cancellation for UTRA FDD UE (covered by UID 20053)","RANFS-InterfCanc",1,"Rel-7","R4","2007-03-28","2007-03-28",1,"-","-","-","-","Deleted. Same as FS on Further Improved Performance Requirements for UMTS/HSDPA UE (FDD)","-",null,null,"SP-38",null,"2007-06-21","2008-01-10"]
[8005,0,"--- RELEASE 6 ---","-",1,"Rel-6","NP,GP,RP,SP,TP","2002-06-28","2005-12-30",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[8008,24006,"   Improving Receiver Performance Requirements for the FDD UE","RInImp-UERecPerf",2,"Rel-6","R4","2002-03-08","2003-09-19",1,"-","-","Intel","shimon.moshavi@INTEL.COM","-",25.100999999999999,null,null,null,null,"2003-10-02","2004-07-08"]
[8014,25010,"   Conformance Test Aspects – UMTS 1.7/2.1 GHz Band","RInImp-UMTS1721_Test",2,"Rel-6","R5","2006-03-10","2006-12-01",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","TS34.121, TS34.108",null,null,null,null,"2006-03-21","2010-06-16"]
[8016,20011,"      Improved Minimum Performance Requirements for HSDPA UE categories 7 and 8","RInImp-HSPerf-10code",3,"Rel-6","R4","2004-09-15","2006-06-09",1,"-","-","Nokia","jussi.numminen@nokia.com","Approved at RP#25 as RP-040375",25.100999999999999,null,null,null,null,"2004-09-27","2006-01-13"]
[8019,25002,"      Testing of Performance of Receiver diversity for HSDPA","RInImp-HSPerf-RxDiv_Test",3,"Rel-6","R5","2003-09-19","2006-03-16",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2004-09-27","2010-06-16"]
[8023,21000,"   FS on Improvement of inter-frequency and inter-system measurements for 1.28 Mcps TDD","RInImp-IfIsMLCR",2,"Rel-6","R1","2001-12-14","2003-09-19",1,"-","-","Samsung","Li Xiao Qiang (xqli@samsung.co.kr)","-",25.888000000000002,null,null,null,null,"2003-10-02","2004-07-08"]
[8027,24011,"   FS on Low Output Powers for general purpose FDD BSs","RInImp-FSLoPw",2,"Rel-6","R3","2003-06-13","2004-03-12",1,"-","-","Telefónica","Ana Burgos (burgos_a@tsm.es)","-",25.806999999999999,null,null,null,null,"2003-10-02","2004-07-08"]
[8030,23006,"   Deleted - FS on the evolution of the UTRAN architecture","RANimp-FSEvo",2,"Rel-6","R3","2002-09-09","2004-12-14",1,"-","-","Nokia","woonhee.hwang@nsn.com, Antti.Toskala@nokia.com","Study Closed, work will continue within the FS on evolved UTRA and UTRAN","-",null,null,"RP-26",null,"2002-09-16","2005-01-13"]
[8032,20004,"   FDD Enhanced Uplink - Stage 2","EDCH-Stage2",2,"Rel-6","R2","2004-03-15","2004-12-14",1,"-","-","-","-","-",25.309000000000001,null,null,null,null,"2004-03-21","2005-01-13"]
[8035,20007,"   FDD Enhanced Uplink - UTRAN Iub/Iur Protocol Aspects","EDCH-IurIub",2,"Rel-6","R3","2004-03-15","2005-03-14",1,"-","-","Nortel","Saso Stojanovski","-","25.401, 25.420, 25.423, 25.430, 25.433",null,null,null,null,"2004-03-18","2005-03-25"]
[8038,9,"Rel-6 RAN improvements","-",1,"Rel-6","RP,S5","2002-09-09","2005-03-14",1,"-","-","-","-","Generic feature","-",null,null,null,null,"2000-03-31","2004-07-08"]
[8041,21009,"      optimization of channelisation code utilisation for 3.84 Mcps TDD","RANimp-RABSE-CodOptTDD",3,"Rel-6","R1","2004-03-15","2005-03-14",1,"-","-","IPWireless","Nicholas Anderson","WIDS modified in RP#26, RP-040551","-",null,null,null,null,"2004-03-18","2006-01-13"]
[8046,23012,"   Rel-6 RRM optimization for Iur and Iub","RANimp-RRMopt-UEMsD",2,"Rel-6","R3","2003-09-19","2004-03-12",1,"-","-","Ericsson","Gert-Jan.van.Lieshout@eln.ericsson.se","-","-",null,null,null,null,"2003-03-27","2004-07-08"]
[8050,35023,"      OAM&P impacts","RANimp-TiltAnt-OAM",3,"Rel-6","S5","2004-02-27","2004-09-16",1,"S5-048270","-","Vodafone","Adrian.Neal@vodafone.com","SP#25 09/2004 completed","32.804, 32.64x",null,null,null,null,"2004-03-30","2006-01-13"]
[8054,32051,"      Stage 2 for Improvement on Le interface","-",3,"Rel-6","S2","2002-06-17","2003-09-22",1,"SP-030127","-","Nokia","Jan Kåll","-","23.002,23.271",null,null,null,null,"2003-03-27","2012-05-21"]
[8057,32047,"      Stage 2 for Enhanced support for anonymity and user privacy","-",3,"Rel-6","S2","2002-07-08","2003-06-27",1,"SP-030127","-","Nokia","Jan Kåll","-","23.002,23.271",null,null,null,null,"2003-03-27","2012-05-21"]
[8059,32025,"   Enhanced inter-GMLC interface","-",2,"Rel-6","S2,OMA","2002-06-24","2004-12-15",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2001-09-19","2012-05-21"]
[8062,32012,"   Location Services support for IMS public identities","-",2,"Rel-6","S2,OMA","2003-02-24","2004-12-15",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2002-01-24","2012-05-21"]
[8065,32026,"   New area event for location service triggering reports","-",2,"Rel-6","S2,N4,OMA","2002-06-03","2004-12-15",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2002-06-21","2012-05-21"]
[8068,32057,"      Stage 3 for New area event for location service triggering reports - impacts MLP, RLP and PCP","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[8073,2457,"      Deleted - UE positioning enhancements - other methods","LCS2-UEpos-enh",3,"Rel-6","R2","2003-09-26","2003-09-26",1,"-","-","Siemens","Meik.Kottkamp@siemens.com","RP#24 Work stopped","-",null,null,"RP-24",null,"2004-10-19","2012-05-21"]
[8076,2026,"   Enhanced HE control of security (including positive authentication reporting)","-",2,"Rel-6","S3","2001-01-03","2003-09-25",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","SP#9 approved WID S3-000490 (Enhanced home control of security by HE)",33.101999999999997,null,null,null,null,"2000-09-22","2011-08-08"]
[8081,33019,"   Key Management of group keys for Voice Group Call Services","SECGKYV",2,"Rel-6","S3","2003-09-26","2004-11-26",1,"SP-030491","-","Vodafone","benno.tietz@vodafone.com","-","42.068, 43.068, 44.068, 42.069, 43.069, 44.069, 31.102, 24.008, 48.008, 42.009, 43.020, New TSs (55.236, 55.205) MILENAGE algorithms ",null,null,null,null,"2003-10-14","2005-01-13"]
[8084,14014,"   Enhancements to the Cx and Sh interfaces","IMS2-CCR",2,"Rel-6","N4","2003-06-06","2004-08-31",1,"NP-030229","-","-","-","Shared public user identities need to be solved. If email approval CR is accepted. Work 100% done.","-",null,null,null,null,"2003-06-09","2005-03-25"]
[8085,25009,"   Conformance Test Aspects – IMS Call Control Rel-6 enhancements","IMS2_CCR_Test",2,"Rel-6","R5","2006-03-10","2007-09-14",1,"-","-","Ericsson","Jacob.John@motorola.com, Leif.Mattisson@ericsson.com","-","34.229-1, 34.229-2, 34.229-3, 34.108",null,null,null,null,"2006-03-21","2010-06-16"]
[{"$f":"A8090+1","v":8090},11037,"   IMS Conferencing","-",2,"Rel-6","N1","2002-11-04","2004-12-08",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-13","2003-01-13"]
[8092,32038,"      Stage 3 for IMS Conferencing","-",3,"Rel-6","N1","2002-12-13","2004-12-08",1,"NP-040494","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","Depends on CN decision on IETF dependenciES in CP-150Rel-6. Higher figure if CPCP is dropped (-> LS to CN plenary)","-",null,null,null,null,"2003-02-28","2005-03-25"]
[8095,31034,"      Stage 1 22.340","IMSM-TS",3,"Rel-6","S1","2002-11-11","2002-12-11",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-",22.34,null,null,null,null,"2003-01-13","2010-09-07"]
[8100,11040,"   Additional SIP Capabilities support not covered by Rel-5","-",2,"Rel-6","N1","2002-11-11","2005-06-17",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-13","2003-01-13"]
[8104,11041,"   Review additional SIP Capabilities against IMS","-",2,"Rel-6","N1","2002-12-13","2004-09-08",1,"NP-040494","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","-","-",null,null,null,null,"2003-01-13","2005-03-25"]
[8108,11044,"      Interworking for IPv6 to IPv4 (SIP / SDP aspects)","-",3,"Rel-6","N1","2004-05-11","2004-09-08",1,"-","-","-","-","-","-",null,null,null,null,"2004-03-01","2004-09-08"]
[8111,14001,"   Mn interface (IM-MGW to MGCF) enhancements (CN4 Part)","IMS-CCR-Mn",2,"Rel-6","N4","2001-08-07","2004-09-01",1,"-","-","-","-","TISPAN issue is open","-",null,null,null,null,"2001-10-08","2005-03-09"]
[8112,31036,"   Study of subscriber and operators relationship in IMS and related ISIM requirements for Rel 6”","-",2,"Rel-6","S1","2002-11-15","2002-12-12",1,"-","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2003-01-13","2003-07-04"]
[8117,32027,"   Deleted - Stage 2 of IMS Phase 2","-",2,"Rel-6","S2","2003-09-19","2003-09-19",1,"SP-020544","-","-","-","-","-",null,null,"SP-21",null,"2004-10-19","2004-10-21"]
[8119,32068,"   Feasibility Study on 3GPP Enablers for services like Push to Talk over Cellular (PoC)","-",2,"Rel-6","S2","2003-09-08","2004-11-30",1,"SP-030384","-","Ericsson","Shabnam Sultana","-",23.978999999999999,null,null,null,null,"2003-10-15","2004-12-06"]
[8123,32062,"Study on Interworking aspects and migration scenarios for IPv4 based IMS Implementations","IPv4IMS",1,"Rel-6","S2","2003-09-08","2004-06-25",1,"SP-040327","-","Siemens","Alexander Milinski","-",23.981000000000002,null,null,null,null,"2003-10-15","2009-11-18"]
[8126,32061,"   Stage 2 for commonality","-",2,"Rel-6","S2","2002-09-16","2003-09-19",1,"SP-020543","-","Nokia","balazs.bertenyi@nsn.com","-",23.864000000000001,null,null,null,null,"2003-09-15","2004-07-08"]
[8131,42009,"Rel-6 Multimedia Messaging (MMS) enhancements","MMS6",1,"Rel-6","T2,S1,S4,S5,OMA","2002-08-15","2005-12-07",1,"TP-030175","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","-",null,null,null,null,"2002-09-26","2004-12-06"]
[8134,42011,"   Technical realization of MMS6","-",2,"Rel-6","T2","2002-09-06","2004-12-10",1,"-","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-",23.14,null,null,null,null,"2002-09-26","2004-12-06"]
[8135,42012,"   OMA dependencies","-",2,"Rel-6","OMA","2003-08-15","2005-04-29",1,"-","-","-","-","-","OMA specs",null,null,null,null,"2002-09-26","2005-03-25"]
[8139,42015,"   Deleted - FS Multiple MMS Relay/Server Architecture","-",2,"Rel-6","T2","2004-12-10","2004-12-10",1,"TP-030301","-","Telefónica Móviles","Juan Gorospe (gorospe_j@tsm.es)","originally it was intended to create a FS TR but most likely the work will become an Annex of 23.140","probably Annex to 23.140",null,null,"TP-26",null,"2003-12-01","2004-09-08"]
[8144,2499,"Presence Capability","PRESNC",1,"Rel-6","S1,S2,S3,S4,N1,N3,N4,OMA","2001-03-19","2005-12-07",1,"SP-010064","-","Motorola","Mark Cataldo","merged \"Presence Service Enhancements\" (UID31028, PRES1) to this feature as no answer was provided on why Presence and Presence Encmts had same target completion date","-",null,null,null,null,"2001-03-30","2004-09-08"]
[8146,2502,"   Stage 2 for Presence Capability","-",2,"Rel-6","S2","2001-09-12","2002-09-20",1,"SP-010517","-","Nokia","balazs.bertenyi@nsn.com","-","23.002, 24.229, New 23.141",null,null,null,null,"2001-03-30","2011-08-09"]
[8150,2504,"   Security aspects of Presence Capability","-",2,"Rel-6","S3","2002-08-26","2002-12-12",1,"SP-020514","-","Ericsson","krister.boman@erv.ericsson.se","SP#17 approved WID S3-020429","-",null,null,null,null,"2001-03-30","2011-08-09"]
[8153,50057,"   Feasibility study on A/Gb enhancements","AGbEnFS-FS",2,"Rel-6","G2","2002-08-30","2002-11-08",1,"GP-022565","-","Vodafone","jose-luis.carrizo@vodafone.co.uk","-","None",null,null,null,null,"2002-05-23","2009-11-18"]
[8158,50082,"      Standardisation effort","-",3,"Rel-6","GP","2002-08-30","2002-11-08",1,"-","-","-","-","-","None",null,null,null,null,"2002-09-26","2009-11-18"]
[8161,50064,"   Realisation of a Flexible Layer One","FLOGER-Real",2,"Rel-6","GP","2000-01-03","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-07-08"]
[8162,50065,"      Technical Report on Realisation of a Flexible Layer One","-",3,"Rel-6","GP","2002-04-19","2004-02-06",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[8166,51005,"      Performance Requirements in 45.005 for Realisation of a Flexible Layer One","-",3,"Rel-6","G1","2000-01-03","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[8169,52072,"   Signalling and protocol support for a Flexible Layer One","FLOGER-SigPro",2,"Rel-6","G2","2002-04-19","2004-06-25",1,"GP-021020","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-12-06"]
[8175,55078,"      Deleted at TSG #27 - MS Test in 51.010","-",3,"Rel-6","G4,G5","2004-02-06","2004-02-06",1,"-","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,"GP-22",null,"2002-05-23","2005-03-09"]
[8177,53080,"      Deleted at TGS #27 - BTS Test in 51.021 - DELETE","-",3,"Rel-6","G3new","2004-02-06","2004-02-06",1,"-","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,"GP-22",null,"2002-09-26","2005-03-09"]
[8180,2545,"   Stage 1 for Multimedia Broadcast and Multicast Service","-",2,"Rel-6","S1","2001-05-11","2002-04-01",1,"-","-","-","-","-","22.146, 22.101",null,null,null,null,"2001-03-30","2012-07-26"]
[8184,11030,"   Support of the MBMS in CN protocols","-",2,"Rel-6","N1","2002-06-18","2004-12-08",1,"NP-040493","-","-","-","-","-",null,null,null,null,"2002-06-21","2012-07-26"]
[8188,31045,"   MBMS User Services","-",2,"Rel-6","S1,S4","2003-05-13","2006-03-16",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-30","2012-07-26"]
[8189,31044,"      Stage 1 for MBMS User Services","-",3,"Rel-6","S1","2003-05-13","2004-04-01",1,"-","-","-","-","-",22.245999999999999,null,null,null,null,"2001-03-30","2012-07-26"]
[8193,20020,"      UE Performance Requirements for MBMS","MBMS-RAN-RF",3,"Rel-6","R4","2004-09-15","2005-09-14",1,"RP-040370","-","Ericsson","Torgny.Palenius@ericsson.com","RP#25 approved WID RP-040370","25.101, 25.133",null,null,null,null,"2004-09-27","2012-07-26"]
[8196,25022,"      Conformance Test Aspects - MBMS for 3.84 Mcps and 7.68 Mcps TDD","MBMS-UEConTest_TDH",3,"Rel-6","R5,T1","2006-09-20","2007-12-07",1,"-","-","IPWireless","Timothy Speight (tspeight@ipwireless.com)","-","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-09-21","2012-07-26"]
[8202,52085,"      MBMS Re-synchronisation at cell change","-",3,"Rel-6","G2","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[8204,50099,"      Simultaneous support of MBMS and non-MBMS services","-",3,"Rel-6","GP","2001-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2012-07-26"]
[8207,50088,"      MBMS channel allocations procedures to multiple MSs","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[8211,50092,"      MBMS Security aspects","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[8215,31007,"   Speech Enabled Services Based on Distributed Speech Recognition (DSR)","DSR",2,"Rel-6","S1","2001-10-08","2002-03-15",1,"SP-010581","-","Qualcomm","Dwilliams@qualcomm.com","-","22.977, 22.941, 23.207, 22.243",null,null,null,null,"2001-10-09","2004-03-12"]
[8216,32999,"   TR on Architectural impacts","-",2,"Rel-6","S2","2003-05-12","2004-03-02",1,"-","-","-","-","-",23.876999999999999,null,null,null,null,"2001-11-29","2004-07-08"]
[8220,31008,"Generic User Profile Rel-6","GUP",1,"Rel-6","S1,S3,N4","2001-10-08","2005-03-03",1,"SP-040515","-","-","-","-","-",null,null,null,null,"2001-10-09","2003-03-28"]
[8223,42002,"   Stage 2 - Data Description Method","-",2,"Rel-6","N4","2002-12-05","2005-03-03",1,"TP-020275","-","T-Mobile","kurt.bischinger@t-mobile.at","TR approved in CN#26",23.241,null,null,null,null,"2001-10-09","2005-03-09"]
[8229,60006,"   Stage 3 for Digital Rights Management","-",2,"Rel-6","OMA","2004-01-01","2004-05-28",1,"-","-","-","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2004-06-08","2005-03-25"]
[8231,31037,"   Deleted - Monitoring of Stages 2 and 3 progress (actual work to be done by OMA)","-",2,"Rel-6","S1","2003-03-21","2003-03-21",1,"-","-","-","-","Replaced by UID 60005 and 60006","-",null,null,"SP-19",null,"2003-01-15","2004-09-08"]
[8234,31035,"   Stage 1 for WLAN-UMTS Interworking Rel-6","WLAN-TS",2,"Rel-6","S1","2003-01-06","2004-06-11",1,"SP-030712","-","Telenor","frederic.paint@telenor.com","-","22.101, 22.105",null,null,null,null,"2003-01-13","2004-06-08"]
[8238,13019,"   Stage 3 - CN3 aspects (Wi Interface for Scenario 3)","-",2,"Rel-6","N3","2003-05-23","2004-09-30",1,"-","-","-","-","-",29.161000000000001,null,null,null,null,"2004-06-08","2005-03-09"]
[8242,43010,"   USIM enhancements for WLAN Interworking","-",2,"Rel-6","T3","2003-09-05","2005-03-04",1,"TP-030185","-","Axalto","Jabellan@axalto.com","-",31.102,null,null,null,null,"2004-12-06","2011-09-01"]
[8243,31015,"Priority Service","PRIOR1",1,"Rel-6","S1","2002-05-30","2003-09-26",1,"SP-010523","-","Telcordia","James Garrahan (jgarraha@telcordia.com)","-","-",null,null,null,null,"2002-02-27","2010-08-31"]
[8247,31018,"Network Sharing ","NTShar",1,"Rel-6","S1,S2,N1,R2,R5","2003-01-20","2006-03-10",1,"SP-010739","-","T-Mobile","michele.zarri@t-mobile.co.uk ","-","-",null,null,null,null,"2002-02-27","2009-11-10"]
[8250,32044,"   Stage 2 for Network Sharing ","-",2,"Rel-6","S2","2003-02-27","2004-07-30",1,"SP-030123","-","T-Mobile","michele.zarri@t-mobile.co.uk ","-","23.002, 23.060, 23.221, 23.236, new 23.251, 23.851",null,null,null,null,"2003-03-27","2009-11-10"]
[8254,32016,"QoS Improvements","QoS1",1,"Rel-6","S2,N3","2002-07-15","2004-12-08",1,"SP-010719","-","Nokia","-","-","23.107, 23.207, 23.221",null,null,null,null,"2002-01-24","2002-01-24"]
[8256,32059,"   Definition of the Gq interface","-",2,"Rel-6","S2","2003-07-01","2004-04-23",1,"SP-030306","-","-","Janne Rinne","-",23.207000000000001,null,null,null,null,"2003-07-23","2004-07-08"]
[8261,14504,"   Stage 3 for Subscriber certificates","-",2,"Rel-6","N4,T3","2003-09-19","2004-11-30",1,"NP-030399","-","Nokia","Lauri Laitinen","Finished in CN4#26","23.003, 23.008, 29.109, 29.230, T3 31.102, 31.103, 31.111",null,null,null,null,"2003-10-15","2009-11-10"]
[8265,31040,"   Scope of the Open Service Access Release 6","-",2,"Rel-6","S1","2003-03-28","2003-06-27",1,"SP-030038","-","-","-","-","-",null,null,null,null,"2003-03-28","2004-03-12"]
[8269,15029,"   TS on Presence and Availability Management (from the PRESNC WI)","-",2,"Rel-6","N5","2002-10-31","2004-03-26",1,"-","-","-","-","N5#26: Split WI into TS & TR.","29.198-14",null,null,null,null,"2003-01-13","2005-01-13"]
[8270,15032,"   OSA interfaces at different levels of abstractions (Parlay X, Web services)","-",2,"Rel-6","N5","2003-07-14","2004-09-10",1,"-","-","-","-","-",29.199000000000002,null,null,null,null,"2003-03-27","2005-01-13"]
[8274,15037,"   Deleted - TR on Presence and Availability Management (from the PRESNC WI)","-",2,"Rel-6","N5","2004-09-17","2004-09-17",1,"-","-","-","-","N5#26:TR Completion 09/04¦consistent with CN1 delayed Rel-6 completion.","-",null,null,"NP-24",null,"2004-10-20","2004-10-21"]
[8277,51102,"      Changes to core specs","-",3,"Rel-6","G1","2002-11-15","2002-12-20",1,"GP-022073","-","Nokia","Torben Themsen","-","-",null,null,null,null,"2002-07-31","2003-02-13"]
[8281,51131,"   Identification of requirements for streaming","-",2,"Rel-6","G1","2003-06-27","2003-08-29",1,"GP-022564","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2002-09-26","2003-09-16"]
[8283,51132,"   Performance study of cell change mechanisms","-",2,"Rel-6","G1","2000-01-03","2003-08-29",1,"GP-022562","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2002-09-26","2003-09-16"]
[8289,52134,"      Inter-system NACC","-",3,"Rel-6","G2","2003-06-27","2003-11-21",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[8292,54131,"   Deleted - MS conformance testing for Seamless support of streaming services in A/Gb mode","-",2,"Rel-6","G3new","2003-12-19","2004-01-30",1,"GP-023424","-","Vodafone","José Luis Carrizo Martínez","Marked as stopped 10/2009","-",null,null,"GP-27",null,"2002-09-26","2009-10-13"]
[8296,31030,"Study on Privacy Capability","PrivCap",1,"Rel-6","S1","2003-11-10","2004-03-03",1,"SP-020579","-","Lucent","Michael Boote (mboote@alcatel-lucent.com)","-",22.949000000000002,null,null,null,null,"2002-11-08","2010-08-31"]
[8297,35010,"Rel-6 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM6",1,"Rel-6","S5","2002-09-12","2005-03-11",1,"SP-040766","-","-","-","SP#26: Updated WID SP-040766 was SP-020445. Completion delayed 12/04->03/05 due to OAM-Trace in CN1/4.","-",null,null,null,null,"2002-11-08","2005-01-13"]
[8300,35014,"   Network Infrastructure Management ","-",2,"Rel-6","S5","2002-09-12","2004-12-16",1,"SP-040789","-","Ericsson","thomas.tovinger@ericsson.com","SP#26 12/2004 completed","32.150/1/2, 32.805, 32.111-5, 32.313/4, 32.331/2/3/4/5, 32.341/2/3/4, 32.351/2/3/4, 32.361/2/3/4, 32.371/2/3/4, 32.804, 32.675, 32.690, 32.695, 32.71/2/3/4/5, 32.741/2/3/4/5",null,null,null,null,"2002-11-08","2011-02-21"]
[8305,35016,"Rel-6 Charging Management","CH",1,"Rel-6","S5,S2,N3","2002-11-21","2005-06-09",1,"SP-040773","-","T-Mobile","karl-heinz.nenner@t-mobile.de","SP#28 Target 09/2005 for WLAN Charging 32.252","-",null,null,null,null,"2003-01-13","2006-01-13"]
[8308,35025,"   CDR parameter description","-",2,"Rel-6","S5","2003-03-21","2005-06-09",1,"-","-","-","-","SP#28 06/2005 completed",32.298000000000002,null,null,null,null,"2004-10-29","2006-01-13"]
[8311,35028,"   OCS: Applications and interfaces","-",2,"Rel-6","S5","2003-03-21","2004-12-16",1,"-","-","-","-","SP#26 12/2004 completed",32.295999999999999,null,null,null,null,"2004-10-29","2006-01-13"]
[8314,35030,"      PS domain charging","-",3,"Rel-6","S5","2003-03-21","2004-09-16",1,"-","-","-","-","SP#25 09/2004 completed",32.250999999999998,null,null,null,null,"2004-10-29","2006-01-13"]
[8319,32070,"      Study on providing policy control with FBC","-",3,"Rel-6","S2","2004-02-02","2004-07-30",1,"-","-","-","-","-","-",null,null,null,null,"2004-05-20","2004-10-21"]
[8323,1802,"   UICC API","USAT1-API",2,"Rel-6","T3","2002-03-20","2005-03-10",1,"-","-","-","-","8/3/2001: test spec is based on R99 core spec, so deleted from Workplan","-",null,null,null,null,"2000-09-14","2001-03-12"]
[8324,43001,"      Rel-6 Java API Test specification","-",3,"Rel-6","T3","2002-03-20","2002-06-10",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","-","-",null,null,null,null,"2002-05-30","2010-02-09"]
[8327,43003,"      Deleted - Java API Test specification (TS 43.019 Rel-5)","-",3,"Rel-6","T3","2002-05-30","2003-06-09",1,"TP-020122","-","Microelectrónica Española","Mario Pérez ","MOVED to Rel-5 WP","-",null,null,"TP-20",null,"2002-09-26","2010-02-09"]
[8332,43009,"      USIM application toolkit Conformance Test Specification for Mobile Equipments ","-",3,"Rel-6","T3","2003-12-05","2005-03-04",1,"TP-030259","-","Gemplus","Eric.laffont@gemplus.com","-",31.123999999999999,null,null,null,null,"2004-12-06","2005-06-02"]
[8335,34024,"   Stage 3 for Packet Switched Streaming Services Rel-6","PSSrel6-Stage3",2,"Rel-6","S4","2002-12-13","2005-12-07",1,"SP-020685","-","Ericsson","olle.franceschi@ericsson.com","TR tbc by Sept. 05","26.233, 26.234, 26.244, 26.245, 26.246, 26.401, 26.402, 26.403, 26.404, 26.405, 26.406, 26.410, 26.411, 26.412, 26.273, 26.290, 26.304, 26.412, 26.274, 26.936",null,null,null,null,"2003-03-27","2009-11-13"]
[8338,34028,"3G-324M Improvements","3G-324MI",1,"Rel-6","S4","2004-03-16","2004-12-16",1,"SP-040067","-","Ericsson","bo.burman@ericsson.com","-","26.111, 26.911",null,null,null,null,"2004-03-02","2004-12-06"]
[8341,12007,"   Stages 2 and 3 for Enhancement of dialled service for CAMEL","-",2,"Rel-6","N2,N4","2003-03-28","2003-12-31",1,"NP-030153","-","Samsung","Richard Brook","-","23.008, 23.016, 23.018, 23.078, 29.002, 29.078",null,null,null,null,"2003-03-27","2009-11-13"]
[{"$f":"A8346+1","v":8346},50603,"      Multiple TBF Stage 2 (43.064) CRs","-",3,"Rel-6","GP,G2","2002-04-05","2003-08-29",1,"-","-","-","-","-","-",null,null,null,null,"2003-07-31","2003-09-16"]
[8349,50096,"Alignment between the test-regimes for GERAN capable MS","ALTERE",1,"Rel-6","G3new","2003-08-29","2005-09-02",0.99,"GP-032236","-","Ericsson","anthony.toubassi@sonyericsson.com ","-","-",null,null,null,null,"2003-09-16","2006-01-13"]
[8350,50097,"   Determine the controversial test cases in the different test regimes and align them with 3GPP GERAN test specifications. Such test cases to be added to TS 51.010.","ALTERE-TC",2,"Rel-6","G3new","2003-08-29","2005-09-02",1,"-","-","-","-","-","-",null,null,null,null,"2003-09-16","2006-01-13"]
[8354,50102,"   DARP test scenarios","DARP-TS",2,"Rel-6","GP","2003-11-21","2004-08-27",1,"GP-041967","-","Nokia","tommy.bysted@nokia.com","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[8358,50106,"   DARP for GPRS and EGPRS MCS1-MCS4","DARP-GPRSE",2,"Rel-6","GP","2004-02-06","2004-11-12",1,"GP-041969","-","Nokia","tommy.bysted@nokia.com","-","-",null,null,null,null,"2003-12-01","2005-03-09"]
[8363,50109,"Reduction of PS service interruption in Dual Transfer Mode","PSintDTM",1,"Rel-6","G2","2003-11-21","2005-06-24",1,"GP-032548","-","Siemens","toby.proctor@roke.co.uk","-","-",null,null,null,null,"2003-12-01","2006-01-13"]
[8365,50111,"   Performance Study of Current Procedures","PSintDTM-Perf",2,"Rel-6","G2","2003-11-21","2004-04-23",1,"GP-032550","-","Siemens","toby.proctor@roke.co.uk","-","-",null,null,null,null,"2003-12-01","2006-01-13"]
[8368,50114,"   Deleted - BTS Conformance testing - Reduction of PS service interruption in DTM","PSintDTM-ConfBTS",2,"Rel-6","G3new","2005-06-24","2005-06-24",1,"-","-","-","-","-","-",null,null,"GP-25",null,"2003-12-01","2006-01-13"]
[8373,32072,"   Deleted - Stage 2 description on Redial","-",2,"Rel-6","S2","2004-05-03","2004-12-16",1,"SP-040331","-","Vodafone","chris.pudney@vodafone.com","-","-",null,null,"SP-26",null,"2004-05-20","2005-03-09"]
[8376,13017,"   Deleted - CS_VSS - CN3 Part","-",2,"Rel-6","N3","2004-10-14","2004-10-14",1,"SP-040331","-","Vodafone","-","-","-",null,null,"TP-26",null,"2004-10-20","2004-10-21"]
[8377,13024,"Reorganisation of CS Data Specifications","CSData",1,"Rel-6","N3","2004-11-19","2004-12-08",1,"NP-040563","-","Siemens","Thomas.Belling@nsn.com","Created at TSG#27 as 100 % complete","23.910, 29.007, New 23.202",null,null,null,null,"2005-03-02","2005-03-09"]
[8381,50555,"   GAAI – Stage 3","GAAI-Stage3",2,"Rel-6","GP","2004-08-27","2005-04-08",1,"-","-","-","-","-",44.317999999999998,null,null,null,null,"2004-10-15","2006-01-13"]
[8385,50561,"   PS handover for Support of PS Handover for GERAN A/Gb mode","SPSHAGB-PSHO",2,"Rel-6","GP,G2","2003-11-03","2005-08-24",1,"GP-051162","-","Ericsson","gunnar.hedby@ericsson.com","Replaces SCSAGB-PSH","-",null,null,null,null,"2005-04-20","2006-01-13"]
[8390,25019,"Test - (Small) Technical Enhancements and Improvements for Rel-6","TEI6_Test",1,"Rel-6","R5,T1","2006-06-02","2008-05-06",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 4 conformance testing","34.108,34.121-1/2,34.122,34.123-1/2/3",null,null,null,null,"2006-09-21","2008-05-06"]
[8392,50563,"Deleted EVGCS - Enhancements of VGCS in public networks for communication of public authority officials","-",1,"Rel-6","GP,G2","2005-08-25","2005-09-02",1,"GP-041837","-","Siemens","kenneth.isaacs@roke.co.uk","GP#26 moved to Rel-7 as UID_11045 Enhancements of VGCS in public networks for communication of public authority officials","44.018, 44.068, 48.008",null,null,"GP-26",null,"2005-04-20","2005-04-21"]
[8396,50503,"   Deleted - Radio Channel Support","SCSAGB-RCS",2,"Rel-6","GP","2003-11-21","2003-11-21",1,"GP-030446","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","Not started","-",null,null,"GP-17",null,"2003-02-13","2010-03-02"]
[8399,50506,"   Deleted SCSAGB-FLO - Modifications to FLO","-",2,"Rel-6","GP","2003-11-21","2003-11-21",1,"GP-030449","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","Not started","-",null,null,"RP-29",null,"2003-02-13","2010-03-02"]
[8401,0,"--- RELEASE 5 ---","-",1,"Rel-5","NP,GP,RP,SP,TP","2000-01-03","2001-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[8404,2476,"High Speed Downlink Packet Access","HSDPA",1,"Rel-5","R2,R5","2001-04-02","2007-03-09",1,"-","-","Motorola","Ravi Kuchibhotla","-","-",null,null,null,null,"2001-03-20","2001-12-10"]
[8408,2480,"   RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing","HSDPA-RF",2,"Rel-5","R4","2001-04-09","2003-06-06",1,"RP-010262","-","Motorola","Howard Benn","-","-",null,null,null,null,"2001-03-20","2003-03-27"]
[8412,1471,"   Base station classification for TDD","RInImp-BSClass",2,"Rel-5","R4","2000-08-14","2002-06-14",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2000-04-26","2001-10-03"]
[8417,1221,"   FS on USTS","RInImp-USTS",2,"Rel-5","R1","2000-08-14","2001-12-21",1,"-","-","SK Telecom","D. Kim","-","-",null,null,null,null,"2000-04-26","2002-02-28"]
[8419,2494,"   FS on the re-introduction of the downlink SIR measurement","RInImp-SIR",2,"Rel-5","R4","2001-03-12","2001-12-14",1,"-","-","Ericsson","Torgny.Palenius@ericsson.com","-","-",null,null,null,null,"2001-03-27","2001-11-29"]
[8423,2211,"      Deleted - Testing Hybrid ARQ II/III","-",3,"Rel-5","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-02-28"]
[8426,23000,"      Iur common transport channel efficiency optimization","RANimp-RRMopt-ctc",3,"Rel-5","R3","2001-03-16","2002-03-29",1,"-","-","Ericsson","Shahrokh Amirijoo","-","-",null,null,null,null,"2001-09-19","2002-03-21"]
[8428,23002,"      FS Introduction of direct transport bearers between SRNC and Node-B","RAN-imp-RRMopt-DTB",3,"Rel-5","R3","2001-06-15","2002-06-04",1,"-","-","Ericsson","Risto Sepponen","FS was closed and introduction of WI not agreed at RAN #16 ","-",null,null,null,null,"2001-09-19","2002-11-08"]
[8431,23003,"   FS SRNS Relocation Procedure Enhancement","RANimp-SRNS",2,"Rel-5","R3","2001-06-15","2002-09-03",1,"-","-","Nokia","Olivier Guyot","-","-",null,null,null,null,"2001-09-19","2002-11-08"]
[8435,25005,"   Testing of ROHC performance","RANimp-RABSE5_Test",2,"Rel-5","R5","2005-09-09","2007-03-09",1,"-","-","Nokia","jarkko.hellsten@nokia.com","-","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2002-02-28","2010-06-16"]
[8439,2102,"   Deleted - Conformance Test Aspects - RAN Improvements","-",2,"Rel-5","T1","2002-01-01","2004-03-01",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-23",null,"2000-11-01","2000-04-01"]
[8442,23004,"UTRAN Sharing in Connected Mode","NETSHARE",1,"Rel-5","R3","2001-12-03","2002-09-03",1,"-","-","Ericsson ","Martin Israelsson","Formerly 'Shared Network support in connected mode', renamed at RAN #16.","-",null,null,null,null,"2002-03-21","2002-11-08"]
[8444,1274,"   Call control and roaming to support IMS in UMTS","IMS-CCR",2,"Rel-5","S2,R5","2000-01-03","2006-12-01",1,"SP-010339","-","Lucent","Liz Daniel","-","-",null,null,null,null,"2000-04-09","2002-01-24"]
[8450,1278,"         IMS stage 3","-",4,"Rel-5","N1","2000-10-02","2002-03-22",1,"-","-","-","-",24.228999999999999,24.228999999999999,null,null,null,null,"2000-04-19","2003-03-14"]
[8453,10004,"      Main IETF dependencies","-",3,"Rel-5","NP","2000-01-03","2002-06-14",1,"-","-","Lucent","-","-","-",null,null,null,null,"2002-01-25","2003-03-28"]
[8455,2523,"         IETF: RFC 3262 (Reliability of provisional responses)","-",4,"Rel-5","N1","2000-11-24","2002-03-22",1,"-","-","Lucent","-","-","-",null,null,null,null,"2002-03-25","2003-03-14"]
[8458,2525,"         IETF: RFC 3313 (SIP extensions for media authorization)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-05-06","2003-03-14"]
[8462,11004,"         IETF: RFC 3267 (AMR and AMR WB RTP and SDP)","-",4,"Rel-5","N1","2000-11-24","2002-03-22",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[8466,11024,"         IETF: RFC editor Queue (Various 3GPP Private Extensions)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2002-06-21","2003-03-14"]
[8469,1292,"            Impact on HSS ","-",5,"Rel-5","N4","2000-11-15","2002-03-22",1,"-","-","-","-","Covered by 29.228 & 29228","-",null,null,null,null,"2000-04-19","2002-05-30"]
[8471,2531,"            IMS Framework Report (work stopped)","IMS-FrWk",5,"Rel-5","S1","2001-04-17","2002-06-14",1,"-","-","SBC","Randolph Wohlert (rwohlert@tri.sbc.com)","-",22.940999999999999,null,null,null,null,"2001-05-28","2003-07-25"]
[8477,35007,"   Charging and OAM&P for IMS","IMS-OAM",2,"Rel-5","S5","2000-12-25","2002-06-12",1,"SP-010461","-","-","-","-","32-series",null,null,null,null,"2000-04-19","2002-06-21"]
[8480,34020,"      Transport protocols","-",3,"Rel-5","S4","2002-03-12","2002-03-12",1,"-","-","Nokia","P. Ojala","-",26.236000000000001,null,null,null,null,"2002-03-25","2002-03-25"]
[8484,32003,"   SIP message compression","-",2,"Rel-5","S2","2001-09-24","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2002-03-25"]
[8485,32004,"      Stage 2 for SIP message compression","-",3,"Rel-5","S2","2001-09-24","2001-10-26",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2001-11-24"]
[8488,1286,"      Cx interface (HSS to CSCF)","-",3,"Rel-5","N4","2001-03-14","2002-06-07",1,"NP-010626","-","-","-","-","-",null,null,null,null,"2000-04-19","2002-05-30"]
[8493,13001,"      Go interface (GGSN to PCF)","-",3,"Rel-5","N3","2001-03-14","2002-06-07",1,"-","-","-","-","[DAB - 23/05/03] - 100 % complete","-",null,null,null,null,"2001-10-08","2003-07-25"]
[8496,14998,"      Si interface (HSS to IM-SSF)","-",3,"Rel-5","N4","2002-01-16","2002-08-30",1,"-","-","-","-","SA16: Part of Rel5 only if completed in September 02. Marked as closed 12/2008 (was marked 72% complete)","-",null,null,null,null,"2002-03-25","2002-05-30"]
[8498,11027,"      Mi interface (CSCF to BGCF)","-",3,"Rel-5","N1","2001-03-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-11","2003-03-14"]
[8504,12002,"      Stage3 work 'CAP'","-",3,"Rel-5","N2","2002-01-07","2002-09-06",1,"-","-","-","-","DAB 12.12.01 split into cn4 and cn2 parts","-",null,null,null,null,"2002-01-24","2003-01-13"]
[8507,14004,"      Deleted - SDM issues for CAMEL control of IMS","-",3,"Rel-5","N4","2002-02-14","2002-06-07",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"NP-17",null,"2001-10-08","2008-12-12"]
[8511,35006,"      Charging management for IMS (off-line & on-line)","-",3,"Rel-5","S5","2001-11-19","2002-09-12",1,"-","-","-","-","-",32.225000000000001,null,null,null,null,"2001-10-08","2002-11-08"]
[8512,34012,"      Billing, accounting and call detail record aspects","-",3,"Rel-5","S5","2001-09-27","2002-09-12",1,"SP-010631","-","T-Mobile","Karl-Heinz.Nenner@T-MOBILE.DE","-",32.225000000000001,null,null,null,null,"2001-10-09","2002-11-08"]
[8516,1844,"   Conformance Test Aspects - Provisioning of IMS","IMS-TEST",2,"Rel-5","T1","2002-03-18","2002-12-27",1,"-","-","-","-","The task is a BB, individual work items were considered but are constrained by lack of supporting companies. Marked as stopped 12/2008","-",null,null,null,null,"2000-09-14","2008-12-12"]
[8520,34001,"Extended Transparent End-to-End PS Streaming Service","PSS-E",1,"Rel-5","S4","2002-01-03","2003-03-17",1,"SP-010392","-","Ericsson","olle.franceschi@ericsson.com","-","26.233, 26.234",null,null,null,null,"2001-06-28","2002-02-28"]
[8523,34003,"   Stage 2 (version Rel-5 of TS 26.234)","-",2,"Rel-5","S4","2002-01-03","2002-03-14",1,"SP-010392","-","-","-","2nd resp SA2",26.234000000000002,null,null,null,null,"2001-06-28","2002-03-25"]
[8527,1429,"   OSA APIs for Multimedia Call Control","OSA1-CSCF",2,"Rel-5","S2","2000-07-11","2002-06-07",1,"-","-","-","-","For Rel5 even if completed by March","-",null,null,null,null,"2000-04-19","2002-01-24"]
[8529,15002,"      Stages 2 and 3 for Multimedia Call Control","-",3,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-04",null,null,null,null,"2002-02-28","2002-06-21"]
[8534,1419,"   OSA Security","OSA1-SEC",2,"Rel-5","S3","2000-07-11","2002-12-20",1,"SP-000302","-","Ericsson","colin.blanchard@bt.com","SP#8 approved WID",33.101999999999997,null,null,null,null,"2000-04-19","2011-08-08"]
[8535,2121,"      Stage 1 for OSA Security","-",3,"Rel-5","S1","2000-07-11","2001-11-09",1,"-","-","Siemens","Manfred.leitgeb@siemens.at","-",22.126999999999999,null,null,null,null,"2000-11-22","2002-02-28"]
[{"$f":"A8538+1","v":8538},1423,"      OSA changes required from supporting platforms, e.g. gsmSCF, HLR ","-",3,"Rel-5","S3","2000-09-11","2000-12-14",1,"SP-000302","-","BT, Ericsson","colin.blanchard@bt.com","SP#8 approved WID",33.101999999999997,null,null,null,null,"2000-04-19","2011-08-08"]
[8543,15005,"   Policy Management - Stage 3","-",2,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-13",null,null,null,null,"2002-02-28","2002-09-26"]
[8547,2124,"      Stage 2 for LCS - OSA interfaces","-",3,"Rel-5","S2","2000-12-11","2000-12-11",1,"-","-","Ericsson","Christophe GOURRAUD","az 24/05/01: Rel4 completion 90->100%.",23.126999999999999,null,null,null,null,"2000-11-22","2001-06-06"]
[8550,1433,"   Retrieval of Terminal capabilities","OSA2-TC",2,"Rel-5","S2","2000-07-11","2002-12-13",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2003-07-25"]
[8554,1638,"CAMEL phase 4","CAMEL4",1,"Rel-5","S1","2000-04-17","2002-09-06",1,"NP-020486","-","Nokia","keijo.palviainen@nokia.com","-","-",null,null,null,null,"2000-08-08","2002-02-28"]
[8556,2012,"   Call Party Handling","CAMEL4-CPH",2,"Rel-5","N2","2000-07-10","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-15","2002-05-30"]
[8561,2460,"   Notification of GPRS mobility management to CSE","CAMEL4-NMM",2,"Rel-5","N2","2001-03-02","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-13","2002-05-30"]
[8562,2458,"   Provision of location information of called subscriber","CAMEL4-LOCB",2,"Rel-5","N2","2001-03-02","2002-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-13","2002-02-28"]
[8565,2516,"   GPRS Any Time Interrogation","CAMEL4-ATI",2,"Rel-5","N2","2001-07-09","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-05-29","2002-05-30"]
[8570,1625,"Wideband Telephony Service - AMR","AMRWB",1,"Rel-5","S4","2000-01-01","2003-12-19",1,"SP-99354","-","Siemens","Imre.Varga@mch.siemens.de","-","-",null,null,null,null,"2000-08-08","2003-03-27"]
[8573,32007,"      Stage 2 for Wideband Telephony Service - AMR","-",3,"Rel-5","S4","2000-01-03","2000-04-17",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-05","2002-02-28"]
[8578,14005,"      N4 work for Wideband Telephony Service - AMR","-",3,"Rel-5","N4","2002-02-13","2002-06-07",1,"N4-010538","-","-","-","CN4#11 30/11/01: No inputs to CN4 at this meeting","-",null,null,null,null,"2000-08-08","2002-05-30"]
[8581,74,"         Codec selection tests","-",4,"Rel-5","S4","2000-06-01","2000-10-20",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2002-02-28"]
[8583,34007,"         TFO AMR-WB","AMRWB-TFO",4,"Rel-5","S4","2001-12-18","2002-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-09-26"]
[8586,34009,"         Interworking with fixed broadband networks","-",4,"Rel-5","S4","2001-09-27","2002-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-02-28"]
[8589,1855,"      Conformance tests (CRs to 34 series) ","-",3,"Rel-5","T1","2000-01-01","2000-04-12",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2003-01-13"]
[8592,1629,"            Test specification for Terminal Acoustic Characteristics","-",5,"Rel-5","S4","2000-02-01","2000-04-12",1,"-","-","-","-","-",26.132000000000001,null,null,null,null,"2000-08-08","2001-03-20"]
[8597,2267,"      Signalling for Iu","-",3,"Rel-5","GP","2000-01-03","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8600,2269,"   Deleted - GERAN MS conformance test for AMR-WB","-",2,"Rel-5","GP","2000-01-03","2003-12-19",1,"GP-000454","-","-","-","Not started 02/2003. Marked as stopped 12/2008","-",null,null,"SP-69",null,"2001-02-01","2008-12-12"]
[8605,1536,"Rel-5 Location Services enhancements","LCS1",1,"Rel-5","S2,S1,S3,S5,N4,R2,R3,GP","2000-04-03","2003-06-27",1,"SP-010518","-","Nokia","Jan Kall",". Acronym changed from \"LCS1, Rel-5\"","-",null,null,null,null,"2000-07-28","2015-03-24"]
[8608,2125,"      Open SMLC-SRNC Interface within the UTRAN to support A-GPS Positioning","LCS-INTF",3,"Rel-5","R2","2001-01-15","2001-10-12",1,"RP-010414","-","Qualcomm","Kirk Burroughs","RP#13 completed","-",null,null,null,null,"2000-11-27","2002-01-24"]
[8611,1538,"      Stage 2 for Event based and Periodic LCS","-",3,"Rel-5","S2","2000-11-06","2001-01-26",1,"-","-","-","-","Marked as closed 12/2008 (was marked 51% complete)","-",null,null,null,null,"2000-07-28","2008-12-12"]
[8614,2437,"      GERAN LCS Stage 2 (first release)","-",3,"Rel-5","GP,S2,G1,G2","2000-04-03","2002-02-08",1,"GP-011925","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2012-05-21"]
[8616,2440,"      L3 protocol support for LCS","-",3,"Rel-5","GP","2000-04-03","2001-06-01",1,"GP-011925","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2012-05-21"]
[8619,2443,"      GERAN LCS Stage 2","-",3,"Rel-5","S2,G1,G2","2000-04-03","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8623,2447,"      RRC protocol support for LCS","-",3,"Rel-5","G1,G2,R2,R3","2001-08-20","2001-11-30",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8627,55069,"      LCS MS test case work plan (Release 98/99/4)","-",3,"Rel-5","G4,G5","2002-06-03","2003-06-27",1,"GP-000458","-","-","-","Marked as closed 12/2008 (was marked 60% complete)","-",null,null,null,null,"2002-05-23","2012-05-21"]
[8632,544,"   LCS interoperation stage 2 aspects","-",2,"Rel-5","S2","2000-08-28","2002-06-28",1,"-","-","-","-","Marked as closed 12/2008 (was marked 17% complete)","-",null,null,null,null,"2000-04-19","2008-12-12"]
[8635,1183,"   FS on LCS support in the IMS","-",2,"Rel-5","S1","2001-02-12","2002-01-18",1,"-","-","-","-","Marked as closed 12/2008 (was marked 75% complete)","-",null,null,null,null,"2000-04-19","2008-12-12"]
[8638,32011,"   Specification for the Le interface","LCS1-Le",2,"Rel-5","S2","2002-01-14","2002-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2002-01-24","2012-05-21"]
[8641,1576,"   Rel-5 Network Domain Security (SEC1-NDS)","-",2,"Rel-5","S3","2000-02-21","2002-06-28",1,"SP-000420","-","Telenor","Geir-myrdahl.koien@telenor.com","SP#9 approved WID SP-000420 (S3-000606 Network domain security). S3#17: All due in Rel5. (WI Update at S3#18). Replaced by NDS-IP and NDS-MAP. TO BE DELETED OR MOVED TO HISTORY FILE","New 33.200 (exisalso for Rel-4)",null,null,null,null,"2000-04-18","2011-08-08"]
[8643,1577,"      Deleted - Control plane protection in core network (e.g., GTP, CAP, MAP/IP, provided by IPsec) ","-",3,"Rel-5","S3","2000-05-12","2002-06-07",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"SP-16",null,"2000-04-18","2008-12-12"]
[8646,1580,"      Deleted - User plane protection in core network (e.g., provided by IPsec)","-",3,"Rel-5","S3","2000-02-21","2002-06-28",1,"-","-","-","-","TO BE DELETED. Marked as stopped 12/2008","-",null,null,"SP-16",null,"2000-04-18","2008-12-12"]
[8650,2244,"   Overall System Architecture for Intra Domain Connection of RAN Nodes to Multiple CN Nodes","-",2,"Rel-5","S2","2001-01-03","2001-09-21",1,"-","-","-","-","-","-",null,null,null,null,"2000-12-13","2001-09-19"]
[8654,50067,"   GERAN work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes","IDCRAN-GERAN",2,"Rel-5","GP","2002-02-08","2002-06-28",1,"GP-020492","-","Ericsson","ingemar.backlund@era.ericsson.se","Accept changes Gb over IP","-",null,null,null,null,"2002-05-23","2002-09-26"]
[8658,52077,"      48.016 Use of Gb interface concepts when a network applies IDNNS","-",3,"Rel-5","G2","2002-02-08","2002-06-28",1,"-","-","-","-","Closed, accept changes for Gb over IP","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8659,52078,"      48.018 Include MSC/VLR identity in CS IMSI paging","-",3,"Rel-5","G2","2002-02-08","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8665,35002,"   Rel-5 Principles, high level Requirements and Architecture","-",2,"Rel-5","S5","2001-09-17","2002-06-28",1,"SP-010461","-","Motorola","-","-","32.101, 32.102",null,null,null,null,"2000-04-26","2002-06-21"]
[{"$f":"A8666+1","v":8666},35003,"   Rel-5 Performance Management","-",2,"Rel-5","S5","2001-09-17","2002-09-12",1,"SP-010631","-","Nortel","-","-","32.4xy, 52.402",null,null,null,null,"2000-04-26","2002-11-08"]
[8672,2396,"GERAN enhancements for streaming services 2 (usage of ECSD)","-",1,"Rel-5","GP","2000-11-06","2002-06-28",1,"GP-010430","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola, Vodafone","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8673,2398,"   Usage of ECSD Concept","-",2,"Rel-5","GP","2000-11-06","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8677,2402,"   MAC header","-",2,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8681,2415,"      Update of Evolution of Iu ps specifications ","-",3,"Rel-5","GP,R3","2001-12-03","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8685,2419,"      Update of Evolution of Iu cs specifications ","-",3,"Rel-5","GP,R3","2000-09-01","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8686,2556,"End to End QoS for PS Domain including IMS","E2EQoS",1,"Rel-5","S2,S5,N3","2000-08-28","2002-06-28",1,"SP-010343","-","Ericsson","Johnson.oyama@era.ericcson.se","Acronym changed from \"E2EQoS, Rel-5\"","-",null,null,null,null,"2001-06-08","2015-03-24"]
[8692,31000,"      Definition of service requirements for MESS5-MMS","MESS5-SR",3,"Rel-5","S1","2001-06-15","2002-03-15",1,"-","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-",22.14,null,null,null,null,"2001-07-04","2003-07-25"]
[8693,42000,"      Technical realization of MESS5-MMS","-",3,"Rel-5","T2","2001-06-15","2002-06-07",1,"-","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","stage 3 MM7 is missing",23.14,null,null,null,null,"2001-07-04","2003-03-27"]
[8699,50001,"GERAN Inter BSC NACC improvements over the Gb Interface","GERNACC",1,"Rel-5","GP","2001-09-03","2002-06-28",1,"GP-012313","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[8701,32502,"      Stage 2 - Concept","-",3,"Rel-5","N4,S2","2001-09-03","2001-10-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[8704,50002,"   Modification of Gb protocols for GERAN Inter BSC NACC over Gb Interface","GERNACC-Gbmod",2,"Rel-5","GP","2001-11-30","2002-06-28",1,"GP-012314","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[8708,50035,"   Deleted - GERAN MS Conformance test for Enhanced Power Control","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012750","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2003-02-13"]
[8712,50061,"      Concept","-",3,"Rel-5","GP","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8713,52004,"      Changes to 44.018","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8717,51028,"      Changes to 45.005","-",3,"Rel-5","G1","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8718,52005,"      Changes to 24.008","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8719,52006,"      Changes to 48.058","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8720,50039,"   Deleted - GERAN MS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012754","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2008-12-12"]
[8721,50040,"   GERAN BTS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2002-12-20",1,"GP-012755","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-01-13"]
[8722,13000,"Service Change and UDI Fallback","SCUDIF",1,"Rel-5","N3","2001-10-08","2002-06-07",1,"NP-020164","-","Ericsson","Rune.Werner.Wiik@ericsson.no","-","29.007, 27.001, 24.008",null,null,null,null,"2001-09-19","2003-07-25"]
[8723,501800,"Rel-5 USIM toolkit enhancements","USAT5",1,"Rel-5","T3,S1","2000-06-05","2003-09-26",1,"-","-","G & D","Michael Meyer","Acronym changed from USAT1, USAT1-Interpr, USAT1LocLnk","22.038, 31.111 (USAT1), 22.038, 03.19, 03.48 (USAT1LocLnk), 23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[8724,43002,"   Deleted - Test specification for USIM toolkit security mechanisms","-",2,"Rel-5","T3","2002-05-28","2003-09-26",1,"TP-020028","-","Gemplus","Sophie Viallet","Marked as stopped 12/2008","-",null,null,"TP-21",null,"2002-05-30","2003-01-13"]
[8725,1801,"   Protocol Standardisation of a SIM Toolkit Interpreter","-",2,"Rel-5","T3,T2","2000-06-05","2003-01-22",1,"TP-000116","-","G & D","Michael Meyer","28/5/2001: T3-19 proposed that since the stage 2 and 3 will not be presented to TP-12 for approval as expected, the WI will be moved to rel-5, with completion expected at TP-13.","T2 27.103",null,null,null,null,"2000-09-14","2001-05-28"]
[8726,2497,"      Stage 1 for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2000-06-05","2001-03-16",1,"-","-","-","-","5/10/2001: Stage one comepeted at TP-12.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2001-10-05"]
[8727,2496,"      Stage 2 and 3","-",3,"Rel-5","T3","2001-01-03","2002-03-08",1,"-","-","-","-","5/10/2001: TS 31.112 and 31.113 approved at TP-13. TS 31.114 to be presented to TP-14.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2002-06-04"]
[8728,2518,"      Test specification for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2001-09-03","2003-01-22",1,"TP-010111","-","Gemplus","Gérald MAUNIER","5/10/2001: Work started on test specification. Marked as closed 12/2008 (was marked 12% complete)","-",null,null,null,null,"2001-03-30","2008-12-12"]
[8729,501802,"   (U)SIM API","USAT5-API",2,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","8/3/2001: test spec is based on R99 core spec, so deleted from Workplan. Acronym changed from USAT1-API, TEI4","-",null,null,null,null,"2000-09-14","2015-03-24"]
[{"$f":"A8730+1","v":8730},504301,"      Rel-5 Java API Test specification","-",3,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","-",51.012999999999998,null,null,null,null,"2002-05-30","2002-09-26"]
[8731,30001,"(Small) Technical Enhancements and Improvements for Rel-5","TEI5",1,"Rel-5","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 5 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[8732,25018,"Test - (Small) Technical Enhancements and Improvements for Rel-5","TEI5_Test",1,"Rel-5","R5,T1","2000-01-03","2008-12-31",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 5 conformance testing. Moved in from Stoyan/testing WP.","34.108, 34.109, 34.121-1, 34.121-2, 34.122, 34.123-1, 34.123-2, 34.123-3, 34.171, 34.229-1, 34.229-2, 34.229-3",null,null,null,null,"2006-03-21","2008-05-06"]
[8733,31013,"Technical Report on UE Functionality Split","UESPLIT",1,"Rel-5","S1","2000-01-03","2000-05-01",1,"SP-010484","-","Motorola","jian.j.wu@motorola.com","-","New 22.944 ",null,null,null,null,"2001-10-11","2010-09-14"]
[8734,2520,"User Equipment Management","UEM",1,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-06-06","2002-06-21"]
[8735,35000,"   FS on User Equipment (UE) Management ","OAM-UEM",2,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-07-03","2002-06-21"]
[8736,50201,"Flow control supporting an MS with multiple data flows with different QoS over the Gb interface","FlowCon",1,"Rel-5","GP","2002-06-24","2002-08-30",1,"GP-021767","-","Ericsson","ingemar.backlund@era.ericsson.se","50101 -> 50201","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8737,50202,"   Update of stage 2 specifications","-",2,"Rel-5","GP","2002-06-24","2002-08-30",1,"-","-","-","-","50102 -> 50202","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8738,32097,"      Concept document 23.060 (changes to)","-",3,"Rel-5","S2","2002-06-28","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[8739,50203,"      Flow Control","-",3,"Rel-5","GP","2002-06-24","2002-06-28",1,"-","-","-","-","50103 -> 50203","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8740,50204,"   Modification of BSSGP protocol","-",2,"Rel-5","GP","2002-06-24","2002-06-28",1,"GP-021508","-","Ericsson","ingemar.backlund@era.ericsson.se","50104 -> 50204","-",null,null,null,null,"2002-07-31","2012-10-26"]
[8741,52095,"      Stage 3 (changes to 48.018)","-",3,"Rel-5","G2","2002-06-24","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[8742,50058,"Deleted - Multiple TBF in A/Gb mode - Phase 1 (MULTBF)","-",1,"Rel-5","GP","2002-04-19","2003-11-28",1,"GP-021263","-","Ericsson","gunnar.mildh@era.ericsson.se","GP#17 Nov 2003 Moved to Rel-6 as UID_50600 MULTBF (Only Multiple TBF Concept paper produced in Rel-5)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8743,50059,"   Deleted - Multiple TBF in A/Gb mode - Core (MULTBF-Agbmode)","-",2,"Rel-5","GP","2002-04-19","2003-08-22",1,"GP-021263","-","-","-","Marked as closed 12/2008 (was marked 26% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8744,50060,"      Deleted - Multiple TBF Concept paper","-",3,"Rel-5","GP","2002-04-19","2003-08-22",1,"-","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8745,51001,"      Deleted - Multiple TBF Stage 2 (43.064) CRs","-",3,"Rel-5","G1","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[8746,50062,"      Deleted - Multiple TBF Stage 3 (44.060) CRs","-",3,"Rel-5","G2","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[8747,50206,"   Deleted - Multiple TBF in A/Gb mode - Phase 1 – MS testing","-",2,"Rel-5","GP","2002-06-24","2003-11-28",1,"GP-022098","-","Ericsson","ingemar.backlund@era.ericsson.se","08/08: duplicate UID_50106=-> 50206. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[8748,54101,"      Deleted - MS conformance tests for Multiple TBF in A/Gb mode ","-",3,"Rel-5","G4","2002-06-24","2003-11-28",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[8749,2345,"Alignment of 3G functional split and Iu","GER3GAL",1,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021256","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2002-09-26"]
[8750,2346,"   GERAN user / control plane","GER3GAL-GUCOPL",2,"Rel-5","GP","2000-08-07","2002-08-30",1,"GP-021255","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8751,2347,"      Alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-08-07","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8752,50300,"         Enhanced power control - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2001-08-31","2001-08-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2001-09-12"]
[8753,2423,"         Stage 2 - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2000-08-07","2001-06-29",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8754,2348,"         Adoption of the UTRAN PDCP","-",4,"Rel-5","GP","2000-11-06","2001-12-21",1,"-","-","-","-","Responsible is GERAN¦RAN WG2 help may be needed.","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8755,50043,"         Development of RLC / MAC","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2003-01-13"]
[8756,50044,"         Development of GERAN RRC","-",4,"Rel-5","GP","2001-06-22","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8757,50045,"         Ciphering and integrity protection concept paper","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8758,50046,"         Multiple TBF or equivalent Concept paper","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8759,50047,"         Paging concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8760,50048,"         Dedicated Physical subchannels, includes traffic and control channels","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8761,50049,"         Iu support and broadcast concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8762,50050,"         Impact of using RLC instead of LAPDm concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8763,50051,"         Contention resolution, mobile station identity, and access concept","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8764,50052,"         PDCP concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8765,50053,"         Downlink delayed TBF release","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-09-26"]
[8766,50054,"         Add transparent RLC Concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8767,50055,"         Handover concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8768,2424,"      Physical layer alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8769,2356,"         PDTCH/TCH in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8770,2357,"         Control channels in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8771,2358,"         Receiver performance in 45.005 for PDTCH/TCH and control channels","-",4,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8772,2359,"   Iu rg interface","GER3GAL-Iurg",2,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"GP-010428","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8773,2425,"      Inter BSS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8774,2360,"         Identification of requirements for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8775,2361,"         Stage 2 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8776,2362,"         Adoption of relevant parts from Iur - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8777,2363,"         Complementation with GERAN specifics - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8778,2364,"         Stage 3 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8779,2426,"      Inter BSS-RNS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8780,2365,"         Identification of requirements for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8781,2366,"         Stage 2 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8782,2367,"         Adoption of relevant parts from Iur - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8783,2368,"         Complementation with GERAN specifics - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8784,2369,"         Stage 3 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8785,2370,"   Voice over GERAN PS and CS concept","-",2,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"GP-011252","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8786,2371,"      Architecture for A, Iu cs and Iu ps","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8787,2372,"      Transcoder position/operation","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8788,2373,"      Handover for Voice over GERAN PS and CS","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8789,2374,"      RTP payload","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8790,2375,"      Codec renegotiation concept","-",3,"Rel-5","GP,R3","2000-11-06","2002-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[8791,2376,"      LA","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[8792,2388,"   Deleted - GERAN MS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2001-06-11","2003-12-19",1,"GP-021253","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8793,2389,"      Deleted - MS test for GERAN interface evolution","-",3,"Rel-5","GP","2001-06-11","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[{"$f":"A8794+1","v":8794},2390,"   GERAN BSS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021254","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,null,null,"2001-02-01","2008-12-12"]
[8795,2391,"      Deleted - BSS test","-",3,"Rel-5","GP","2000-06-08","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8796,2330,"GERAN support for IMS","GERIMS",1,"Rel-5","GP","2000-05-01","2002-12-20",1,"GP-010420","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8797,2331,"   GERAN Header adaptation","GERIMS-HEADAPT",2,"Rel-5","GP,S2,RP","2000-05-01","2002-12-20",1,"GP-010421","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8798,2332,"      Definition of compression and removal modes for PDCP protocol","-",3,"Rel-5","GP,S2,RP","2000-07-24","2000-09-01",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8799,2333,"      Conceptual description in stage 2","-",3,"Rel-5","GP,S2,RP","2000-05-01","2001-10-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8800,2334,"      Necessary changes on stage 3 regarding header removal","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-12-20",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8801,2335,"   Deleted - GERAN Radio access bearer design for IMS","GERIMS-RABDES",2,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"GP-010422","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[8802,2422,"      Deleted - MuM control signalling for conversational multimedia services","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[8803,2431,"         Deleted - Identification of requirements for MuM control signalling for conversational multimedia services","-",4,"Rel-5","GP,S2,RP","2000-11-06","2002-02-08",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-08",null,"2001-02-13","2003-01-13"]
[8804,2337,"         Deleted - Necessary modifications due to SIP","-",4,"Rel-5","GP,S2,RP","2002-05-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-10",null,"2001-02-01","2003-01-13"]
[8805,2341,"   Deleted - GERAN MS Conformance test for support of IMS","GERIMS-MSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010424","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8806,2342,"      Deleted - MS test for support of IMS","-",3,"Rel-5","G4","2001-06-11","2002-12-20",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8807,2343,"   Deleted - GERAN BTS Conformance test for support of IMS","GERIMS-BTSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010425","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8808,54001,"MS Conformance Testing of Dual Transfer Mode","MSCTDTM",1,"Rel-5","G4,G5","2002-11-11","2003-02-07",1,"GP-023236","-","Vodafone","Dave Fox","Needed to complete DTM (R99)","-",null,null,null,null,"2003-01-13","2003-02-13"]
[8809,32033,"Handling of early Ues","LATE_UE",1,"Rel-5","S2","2000-01-03","2003-06-27",1,"SP-030125","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[8810,32031,"   Feasibility Study on Handling of early Ues","-",2,"Rel-5","S2","2002-10-07","2002-12-13",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[8811,32032,"   Stage 2 for Handling of early Ues","-",2,"Rel-5","S2","2003-01-06","2003-06-27",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-07-23"]
[8812,22001,"   FS for the Early Mobile Handling in UTRAN","FSEarlyUE",2,"Rel-5","R2","2002-09-09","2003-06-06",1,"-","-","Vodafone","alan.law@vodafone.com ","-","-",null,null,null,null,"2002-09-16","2003-07-04"]
[8813,96,"   Note: Stage 3 RAN part not shown","-",2,"Rel-5","RP","2000-01-03","2000-01-03",1,"-","-","-","-","-","-",null,null,null,null,"2000-10-09","2001-10-11"]
[8814,0,"--- RELEASE 4 ---","-",1,"Rel-4","NP,GP,RP,SP,TP","2000-01-03","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[8815,1861,"Miscellaneous UE Conformance Testing Activities","MISTST1",1,"Rel-4","T1","2001-04-02","2004-12-01",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2003-01-13"]
[8816,1862,"   Optimization of Test Time, RF Aspects (FDD)","MISTST1-OpFDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times. Marked as stopped 12/2008 (was 70% complete)",34.121000000000002,null,null,null,null,"2000-09-14","2008-12-12"]
[8817,1863,"   Optimization of Test Time, RF Aspects (TDD)","MISTST1-OpTDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times",34.122,null,null,null,null,"2000-09-14","2008-12-12"]
[8818,1907,"   Extensions to R99 Test cases","MISTST1-Ext",2,"Rel-4","T1","2001-04-02","2003-12-02",1,"TP-030052","-","-","-","Further test coverage of the R99 specification to cover supplementry services. Marked as stopped 12/2008 (was 70% complete)","34.123 p 1,2",null,null,null,null,"2000-08-24","2008-12-12"]
[8819,2564,"   Extension to R99 Test cases - TTCN","-",2,"Rel-4","T1","2002-06-28","2004-03-03",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2001-06-01","2008-12-12"]
[8820,2565,"   Creation of R99 TCs for TDD - prose","MISTST1-TDD",2,"Rel-4","T1","2001-10-01","2004-07-01",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","34.123-1",null,null,null,null,"2001-06-01","2008-12-12"]
[8821,2566,"   Deleted - Creation of R99 TCs for TDD - TTCN","-",2,"Rel-4","T1","2002-09-03","2004-12-01",1,"TP-030052","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-26",null,"2001-06-01","2008-12-12"]
[8822,1908,"   Deleted - Review all other work items for impact on new or exiting 34 series specs.","-",2,"Rel-4","T1","2002-07-02","2002-12-27",1,"-","-","-","-","Marked as stopped 12/2008","34.121,122,123,125",null,null,"TP-18",null,"2000-09-06","2008-12-12"]
[8823,1340,"Real Time Facsimile","FAX-RT",1,"Rel-4","S1","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8824,1341,"   Real Time Fax ","-",2,"Rel-4","S2","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","postponed from R99 to R00, SP-000169","-",null,null,null,null,"2000-04-09","2000-11-15"]
[8825,1808,"      Terminal capabilities, AT commands","-",3,"Rel-4","T2","2000-02-22","2000-06-23",1,"-","-","-","-","-","21.904, 27.007",null,null,null,null,"2000-09-14","2000-04-01"]
[8826,1343,"      Signalling aspects (e.g. ICM)","-",3,"Rel-4","N1","2000-02-22","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-11-15"]
[8827,1648,"      Service provision","-",3,"Rel-4","N3","2000-02-22","2000-06-23",1,"-","-","-","-","-",23.146000000000001,null,null,null,null,"2000-08-08","2000-11-15"]
[8828,1345,"      Review whether service/stage 1 aspects need to be aligned","-",3,"Rel-4","S1","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8829,1346,"      Review whether architecture/stage 2 aspects need to be aligned","-",3,"Rel-4","S2","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8830,1539,"Transparent End-to-End PS mobile streaming application","PSTREAM",1,"Rel-4","S4","2000-04-03","2001-03-21",1,"SP-000345","-","-","-","-","26.233, 26.234",null,null,null,null,"2000-07-28","2001-03-20"]
[8831,1818,"Multimedia Messaging","MMS4",1,"Rel-4","T2,S1","2000-02-22","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","Acronym changed from \"MMS, Rel-4\"","22.140, 23.140",null,null,null,null,"2000-09-14","2015-03-24"]
[8832,136,"   Definition of service requirements for Multimedia Messaging","-",2,"Rel-4","S1","2000-02-22","2000-05-31",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8833,1819,"   Review of definition of service requirements","-",2,"Rel-4","T2","2000-06-01","2001-03-14",1,"TP-000078","-","Siemens","-","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8834,1820,"   Technical Realisation ","-",2,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8835,1821,"      Review of definition of reference Achitecture model","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8836,1822,"      Fulfill Requirements of Stage 1","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","e.g. minimum set of media formats, media format conversion, personalization of MMS. ","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8837,1823,"      Definition of MMS primitives in Stage 2","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8838,1541,"Transcoder-Free Operation","TrFO",1,"Rel-4","N4,S2,N1","2000-01-03","2001-03-30",1,"-","-","-","-","Lead given to CN4 from CN","-",null,null,null,null,"2000-07-28","2002-03-25"]
[8839,112,"   Out-of-Band Transcoder Control solution","TrFO-OoBTC",2,"Rel-4","N4","2000-01-03","2001-03-30",1,"N4-000531","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","-","-",null,null,null,null,"2000-04-06","2009-07-08"]
[8840,1512,"      implementation in UTRAN","TrFO-OoBTC-UTRAN",3,"Rel-4","R3","2000-09-11","2001-03-30",1,"-","-","Siemens","Alexander Vesely","moved according to NP-000575","25.401, 25.410, 25.413, 25.415, 23.153",null,null,null,null,"2000-07-26","2001-03-20"]
[8841,896,"      Impact on architecture, Principles and Terminology","-",3,"Rel-4","S2","2000-01-03","2000-10-20",1,"-","-","-","-","e.g. study cascading TrFO/TFO/TrFO","-",null,null,null,null,"2000-04-06","2000-12-13"]
[8842,1657,"      Codec Negotiation between UE and MSC","-",3,"Rel-4","N1","2000-08-14","2001-02-02",1,"-","-","Motorola","Andrew Howell","the link to NP-000085has been deleted because refering to a R99 status sheet","24.008, 23.009, 23.108, (29.002)",null,null,null,null,"2000-08-08","2000-12-04"]
[8843,115,"      Codec Negotiation inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"-","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex + list of open issues","-",null,null,null,null,"2000-04-06","2001-03-12"]
[8844,894,"      Bearer establishment inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"NP-000127","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex.",23.152999999999999,null,null,null,null,"2000-04-06","2001-03-12"]
[8845,905,"   Speech Transcoder: Location and Control at the UMTS Core Network Border","TrFO-STLC",2,"Rel-4","S2","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8846,124,"      Transcoder at Edge ","-",3,"Rel-4","NP","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2001-03-12"]
[8847,2310,"GERAN improvements 1 (Gb over IP)","GEIMP1",1,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000433","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8848,2311,"   Gb over IP (Ip-fication of Gb)","GbIP",2,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000434","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8849,2312,"      Concept of Gb over IP (Ip-fication of Gb)","-",3,"Rel-4","GP","2000-05-09","2000-11-10",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8850,2313,"      Changes to 08.16, 08.18","-",3,"Rel-4","GP","2000-05-09","2001-03-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8851,2314,"GERAN improvements 2 (NACC)","GEIMP2",1,"Rel-4","GP","2000-11-06","2003-06-10",1,"GP-012812","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8852,2315,"   Gb enhancements","Gben",2,"Rel-4","GP","2000-11-06","2001-06-08",1,"GP-000436","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8853,2316,"      Intra BSC NACC (Network Assisted Cell Change)","-",3,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8854,2420,"         Concept","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8855,2317,"         Changes in 03.64","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8856,2318,"         Changes in 04.60","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8857,2319,"         Changes in 44.008","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[{"$f":"A8858+1","v":8858},50030,"   MS conformance test for Intra BSC NACC","GEIMP2-Msconf",2,"Rel-4","GP","2001-11-30","2003-06-10",1,"GP-012811","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-02-13"]
[8859,50299,"      Changes in 51.010","-",3,"Rel-4","G5,G4","2001-11-30","2003-06-10",1,"-","-","-","-","az 05/08: duplicated UID_50099 => 50299. Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2002-05-23","2008-05-06"]
[8860,2324,"GERAN improvements 4 (Delayed TBF)","GEIMP4",1,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8861,2325,"   Gb enhancements 2","GEIMP4-Gben2",2,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8862,2429,"      Stage 2 for Gb enhancements 2","-",3,"Rel-4","GP","2001-01-15","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-13","2002-03-01"]
[8863,2421,"      Stage 3 (changes in 44.060)","-",3,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8864,2327,"         Definition of enhanced countdown procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8865,2328,"         Definition of enhanced TBF release procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8866,2329,"         Definition of USF=FREE type polling mechanism on PDCH","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8867,1222,"Low Chip Rate TDD option","LCRTDD",1,"Rel-4","R1","2000-07-19","2003-12-02",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[8868,1223,"   Physical layer for Low Chip Rate TDD option","LCRTDD-Phys",2,"Rel-4","R1","2000-07-19","2001-03-30",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8869,1224,"   Layer 2 and layer 3 protocol aspects","LCRTDD-L23",2,"Rel-4","R2","2000-07-19","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8870,1225,"   RF radio transmission/reception, system performance requirements and conformance testing","LCRTDD-RF",2,"Rel-4","R4","2000-08-14","2001-03-30",1,"-","-","CWTS","D. Zhang","-","-",null,null,null,null,"2000-04-26","2001-03-30"]
[8871,1227,"   UE radio access capability","LCRTDD-UErac",2,"Rel-4","R2","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8872,1228,"   Iub/Iur protocol aspects - for Low Chip Rate TDD option","LCRTDD-IubIur",2,"Rel-4","R3","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[8873,2262,"   Low chiprate TDD interworking with GERAN","-",2,"Rel-4","GP","2000-09-01","2001-01-19",1,"GP-000432","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8874,2263,"      Handover and Cell Selection / Reselection to UTRA 1.28 Mcps TDD","-",3,"Rel-4","GP","2000-09-01","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8875,2103,"   Conformance Test Aspects - Low Chip Rate TDD","-",2,"Rel-4","T1","2001-09-17","2003-12-02",1,"-","-","-","-","-","-",null,null,null,null,"2000-11-01","2000-04-01"]
[8876,2217,"      Testing Layer 2 and layer 3 protocol aspects","-",3,"Rel-4","T1","2001-09-17","2003-07-02",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 60% complete)","34.123-1, 34.123-2",null,null,null,null,"2000-11-16","2003-03-14"]
[8877,2562,"      Deleted - Testing Layer 2 and layer 3 protocol aspects - TTCN","-",3,"Rel-4","T1","2002-12-03","2003-12-02",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2001-05-31","2003-03-14"]
[8878,2218,"      Testing RF Radio Transmission and Reception","-",3,"Rel-4","T1","2001-09-17","2002-06-28",1,"TP-030052","-","-","-","duration set to 6 months (was 0), finish date set","-",null,null,null,null,"2000-11-16","2003-01-13"]
[8879,1322,"Enable bearer independent CS architecture","CSSPLIT",1,"Rel-4","S2,N3,N4","2000-01-03","2002-03-01",1,"SP-000288","-","Siemens","Alexander Milinski","-","-",null,null,null,null,"2000-04-09","2011-08-06"]
[8880,1323,"   Enable bearer-independent call control","-",2,"Rel-4","N4","2000-01-03","2001-08-16",1,"N4-000512","-","Ericsson","Heinz-Peter.Keutmann@eed.ericsson.se ","DAB 12.12.01 should be 100% hence closed","-",null,null,null,null,"2000-04-09","2002-01-24"]
[8881,1516,"      Architecture and Stage 2 description","-",3,"Rel-4","S2","2000-01-03","2000-09-08",1,"-","-","-","-","R00 stage 2 at least 80 % complete in TSGS #8 21.-23.6.2000",23.001999999999999,null,null,null,null,"2000-07-28","2000-04-01"]
[8882,1325,"      Standardisation of protocols (control & user planes) over Nb interface","-",3,"Rel-4","N3","2001-01-02","2001-03-30",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[8883,1326,"      Standardisation of protocols over reference points between MSC server and Gateway MSC server","-",3,"Rel-4","N4","2000-09-25","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8884,1616,"      Standardisation of detailed stage 2 description","-",3,"Rel-4","N4","2000-07-17","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-03-12"]
[8885,1327,"      Bearer control between MSC server and MGW","-",3,"Rel-4","N4","2000-09-01","2001-08-16",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8886,1328,"         stage 3 - protocol issues","-",4,"Rel-4","N4","2000-09-01","2001-08-16",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8887,1329,"         stage 3 - parameter value issues","-",4,"Rel-4","N3","2001-01-02","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[8888,2052,"   Deleted - Conformance Test Aspects - Enable bearer independent CS architecture","CSSPLIT-TEST",2,"Rel-4","T1","2001-03-05","2002-03-01",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-15",null,"2000-10-09","2000-04-01"]
[8889,1445,"MExE enhancements Rel-4","MEXE",1,"Rel-4","T2,S3","2000-01-03","2001-12-14",1,"TP-030052","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-09-14"]
[8890,1447,"   MExE Security Analysis Activity","MEXE-SEC",2,"Rel-4","S3,T2","2000-02-22","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","SP#12 updated WID","-",null,null,null,null,"2000-04-18","2011-08-06"]
[8891,2045,"      Stage 3 for MExE Security","-",3,"Rel-4","S3","2000-07-17","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-","21.133, 33.102",null,null,null,null,"2000-10-09","2011-08-06"]
[8892,1448,"      Terminal aspects for MExE Security","-",3,"Rel-4","T2","2000-02-22","2000-12-15",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-",23.056999999999999,null,null,null,null,"2000-04-09","2001-03-13"]
[8893,1810,"   MExE Rel-4 Improvements and Investigations","MEXE-ENHANC",2,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8894,1812,"      3rd MExE classmark","-",3,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","Additional features for MExE R2000","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8895,1814,"      FS on Secure download mechanism and capabilities to support SDR concepts","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8896,1815,"      FS on Support of MP3/MPEG4 content","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8897,1631,"Tandem Free aspects for 3G and between 2G and 3G systems ","TFO",1,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify no problems for GSM terminals roaming in 3G R99","-",null,null,null,null,"2000-08-08","2001-03-30"]
[8898,1632,"   Tandem Free AMR","TFO-AMR",2,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-08-08","2001-03-30"]
[8899,130,"      Specification of Tandem Free AMR","-",3,"Rel-4","S4","2000-02-22","2001-03-23",1,"-","-","-","-","-",28.062000000000001,null,null,null,null,"2000-04-06","2001-03-20"]
[8900,907,"      Impact of Tandem Free AMR on:","-",3,"Rel-4","NP","2001-01-08","2001-06-15",1,"-","-","-","-","\"Implementation\" changed to \"Impact on:\" by A. Sultan (for better wording)","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8901,131,"         CN","-",4,"Rel-4","NP","2001-03-26","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-04-06","2001-03-30"]
[8902,132,"         GERAN","-",4,"Rel-4","GP","2001-01-08","2001-04-06",1,"-","-","-","-","End date Modified from June to March to have it in Rel4","-",null,null,null,null,"2000-04-06","2002-02-28"]
[8903,2230,"Advanced Speech Call Items enhancements_Rel-4","ASCI4",1,"Rel-4","N1","2000-12-03","2002-03-14",1,"NP-000730","-","Nortel","sonia.garapaty@nortelnetworks.com","Approved at CN#10. Acronym changed from ASCI, Rel-4","-",null,null,null,null,"2000-12-11","2015-03-24"]
[8904,2232,"   Stage 2 for Advanced Speech Call Items enhancements_Rel-4 (ASCI)","-",2,"Rel-4","N4","2000-12-03","2002-03-14",1,"-","-","Sagem","Vivien Perlic","CN4#11 30/11/02: no inputs received in CN4","23.067, 24.067",null,null,null,null,"2000-12-11","2001-12-12"]
[8905,2231,"   Stages 2 and 3 on A interface","-",2,"Rel-4","N1","2000-12-03","2001-03-23",1,"-","-","Nortel","sonia.garapaty@nortelnetworks.com","-","44.068, 44.069, 24.008",null,null,null,null,"2000-12-11","2001-05-30"]
[8906,2403,"700 MHz spectrum support","700SS",1,"Rel-4","GP","2000-01-03","2002-12-20",1,"GP-000449","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8907,2404,"   GERAN support for the 700 MHz band","-",2,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8908,2405,"      Signalling support","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8909,2406,"      Physical layer definitions - for GERAN support for the 700 MHz band","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8910,2407,"      Receiver performance and RF budget","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8911,2408,"   GERAN MS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2001-11-30",1,"GP-000451","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8912,2410,"   GERAN BTS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2002-12-20",1,"GP-000452","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8913,2463,"Operator Determined Barring for Packet Oriented Services","ODB",1,"Rel-4","NP","2000-06-01","2001-03-19",1,"NP-010089","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","Completed WI missing from the P-plan Added for tracking","-",null,null,null,null,"2001-03-20","2001-03-20"]
[8914,2546,"UMTS QoS Architecture for PS Domain","QoSPS",1,"Rel-4","S2,S5,R3,GP","2000-01-03","2002-11-27",1,"SP-010342","-","Ericsson","Ina.widegren@era.ericsson.se","-","-",null,null,null,null,"2001-06-08","2002-01-24"]
[8915,2548,"   Architecture","-",2,"Rel-4","S2","2000-06-05","2001-01-03",1,"-","-","-","-","-",23.106999999999999,null,null,null,null,"2001-06-08","2002-01-24"]
[8916,2550,"   Charging and OAM&P for QoS Management","QoSPS-OAM",2,"Rel-4","S5","2001-09-21","2002-06-28",1,"SP-010461","-","-","-","-","32-series",null,null,null,null,"2001-06-08","2002-06-21"]
[8917,1681,"   RAB Quality of Service (re)Negotiation over Iu","QoSPS-MAPEND-RABQoS",2,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-",25.413,null,null,null,null,"2000-07-26","2001-02-16"]
[8918,1991,"      RAB Quality of Service Negotiation over Iu","QoSPS-MAPEND-RABQoS-Negot",3,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8919,2456,"      RAB Quality of Service Negotiation over Iu during relocation","QoSPS-MAPEND-RABQoS-NegotReloc",3,"Rel-4","R3","2001-03-02","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-09","2001-03-12"]
[8920,1992,"      RAB Quality of Service Re-Negotiation over Iu","QoSPS-MAPEND-RABQoS-ReNegot",3,"Rel-4","R3","2000-09-25","2001-03-23",1,"-","-","Motorola","S. Irwin","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8921,1553,"   GERAN QoS Aspects - Handovers: maintenance of real-time QoS while moving between cells in the PLMN including inter-SGSN and SRNS relocation or possibly other mechanisms","GERQoS",2,"Rel-4","GP","2000-01-03","2001-11-30",1,"GP-010431","-","-","-","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[{"$f":"A8922+1","v":8922},2306,"      Handover Concept for the PS domain","-",3,"Rel-4","GP","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8923,2309,"         Stable RT handover report 25.936 including header removal","-",4,"Rel-4","GP","2000-01-03","2000-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2002-01-24"]
[8924,2307,"         Update of stage 2","-",4,"Rel-4","GP","2000-01-03","2001-02-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-01-24"]
[8925,2308,"         Update of relevant stage 3 specs -> RRC","-",4,"Rel-4","G2","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8926,50010,"   Deleted - GERAN MS Conformance test for inter-system and intra-system Packet data real-time Handover","GERQoS-Mstest",2,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"GP-012287","-","-","-","Still exist? To be clarified by GERAN4/5. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8927,50011,"      Deleted - Handover for the PS domain","-",3,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8928,50012,"         Deleted - Stable RT handover report 25.936 including header removal","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8929,50013,"         Deleted - Update of stage 2","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8930,50014,"         Deleted - Update of relevant stage 3 specs","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8931,1685,"   PS-domain handover for real-time services","QoSPS-PSdoRTS",2,"Rel-4","R3","2000-08-28","2001-03-30",1,"-","-","Nokia","atte.lansisalmi@nokia.com ","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[8932,2554,"   Deleted - RAB QoS Renegotiation at Relocation","-",2,"Rel-4","R3","2001-01-03","2001-03-23",1,"-","-","-","-","Marked as stopped 12/2008","25.851, 25.946",null,null,"RP-11",null,"2001-06-08","2008-12-12"]
[8933,1993,"(Small) Technical Enhancements and Improvements for Rel-4","TEI4",1,"Rel-4","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 4 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[8934,25017,"Test - (Small) Technical Enhancements and Improvements for Rel-4","TEI4_Test",1,"Rel-4","R5,T1","2000-01-03","2001-03-30",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 4 conformance testing. Moved in from the Stoyan/Testing WP","-",null,null,null,null,"2006-03-21","2008-05-06"]
[8935,400002,"Rel-4 Evolutions of the transport in the UTRAN","ETRAN",1,"Rel-4","RP","2000-08-21","2002-08-23",1,"-","-","Alcatel","Francois Courau","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[8936,12,"   QoS optimization for AAL2 connections over Iub and Iur interfaces","ETRAN-QoSAAL2",2,"Rel-4","R3","2000-08-21","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[8937,1995,"   Transport bearer modification procedure on Iub, Iur, and Iu","ETRAN-MigrMod",2,"Rel-4","R3","2000-10-02","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-09-26","2001-03-20"]
[8938,401834,"   Deleted - Conformance Test Aspects of Rel-4 evolutions of the transport in UTRAN","-",2,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-09-14","2009-10-13"]
[8939,2208,"      Deleted - Testing RAB support enhancements","CT-RABS?",3,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34. 121, 34.122, 34.123 p 1,2, 34.123 pt 3",null,null,"TP-17",null,"2000-11-16","2009-10-13"]
[8940,400004,"Rel-4 Evolutions of the transport in the CN","CNTRSP",1,"Rel-4","N4,N1,N2,S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[8941,859,"   IP Transport of CN protocols (e.g. CAP, MAP)","SS7IP",2,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[8942,1679,"      Stage 3 for IP Transport of CN protocols (e.g. CAP, MAP)","-",3,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[8943,2018,"         CAP","-",4,"Rel-4","N2","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[8944,2019,"         MAP","-",4,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-",29.202000000000002,null,null,null,null,"2000-08-25","2001-03-12"]
[8945,2253,"         BSSAP+","SS7IP-BSSAP+",4,"Rel-4","N1","2001-01-15","2001-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2001-03-12"]
[8946,1513,"   FS on Transport and control separation in the PS CN domain","-",2,"Rel-4","S2","2000-05-29","2001-03-23",1,"SP-000293","-","Ericsson","Juan-Antonio.Ibanez@eed.ericsson.se","-","-",null,null,null,null,"2000-07-28","2001-09-19"]
[8947,1615,"      Architectural impacts","-",3,"Rel-4","S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-02-08"]
[8948,401216,"Rel-4 Improvements of Radio Interface","-",1,"Rel-4","RP","2000-07-10","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-10-11"]
[8949,1509,"   UTRA repeater specification (master)","RInImp-REP",2,"Rel-4","R4","2000-07-10","2001-03-21",1,"-","-","Mikom, Allgon","T. Kummetz, Mikom; Alf Ahlström, Allgon","-","-",null,null,null,null,"2000-07-26","2001-03-30"]
[8950,1994,"   DSCH power control improvement in soft handover","RInImp-DSCHsho",2,"Rel-4","R1","2000-09-11","2001-03-23",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8951,1996,"   UMTS 1800","RInImp-UMTS18",2,"Rel-4","R4","2000-09-25","2001-12-14",1,"-","-","Motorola","Howard Benn","-","-",null,null,null,null,"2000-09-26","2001-11-29"]
[8952,2467,"   UMTS 1900","RInImp-UMTS19",2,"Rel-4","R4","2001-03-19","2001-12-14",1,"-","-","Motorola","Howard Benn","-",25.100999999999999,null,null,null,null,"2001-03-19","2009-07-09"]
[8953,1219,"   FS on High Speed downlink packet access","RInImp-HSDPA",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Motorola","Amitabha Ghosh (qa0047@email.mot.com)","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8954,1510,"   Deleted - FS on improved common DL channel for Cell-FACH state","RInImp-DLCFACH",2,"Rel-4","R2","2000-09-11","2001-12-28",1,"-","-","GBT","J. Kwak","Stopped at RP#14","-",null,null,"RP-14",null,"2000-04-26","2009-10-13"]
[8955,401839,"   Conformance Test Spec. Rel-4 improvements in Radio Interface","-",2,"Rel-4","T1","2001-10-08","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-10-11"]
[8956,2212,"      Deleted - Testing Improved usage of downlink resource in FDD for CCTrCHs of dedicated type","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[8957,2213,"      Deleted - Testing Terminal Power saving features","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[8958,2214,"      Deleted - Testing DSCH power control improvement in soft handover","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-02-28"]
[8959,2215,"      Testing UMTS 1800","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[8960,41000,"      Testing UMTS 1900","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[8961,2561,"      Testing UMTS 1800 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8962,41001,"      Testing UMTS 1900 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8963,400009,"Rel-4 RAN improvements","-",1,"Rel-4","RP","2000-08-14","2004-03-17",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[8964,655,"   Node B synchronization for TDD","RANimp-NBsync",2,"Rel-4","R1","2000-08-14","2001-03-23",1,"-","-","Siemens","S. Oestreich","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8965,2206,"   RAB support enhancement for Rel-4","RANimp-RABSE",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Ericsson","M. Israelsson, A. Krishnarajah","29 Nov 2000: split into ROHC and non-ROHC part¦5 Mar 2001: splitting off of ROHC for Rel-4 agreed by R2","-",null,null,null,null,"2000-12-04","2002-02-28"]
[8966,402102,"   Deleted - Conformance Test Aspects - Rel-4 RAN Improvements","-",2,"Rel-4","T1","2002-01-01","2004-03-17",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-23",null,"2000-11-01","2000-04-01"]
[8967,402222,"      Deleted - Testing Radio access bearer support enhancments","-",3,"Rel-4","T1","2002-01-01","2002-09-02",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-04-09"]
[8968,402461,"      Deleted - Testing RAB support enhancements-Robust Header Compression","RABimp-RoCH",3,"Rel-4","T1","2002-05-28","2003-09-03",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-1, -2",null,null,"TP-21",null,"2001-03-20","2003-03-14"]
[8969,41006,"      Deleted - Testing RAB support enhancements-Robust Header Compression - TTCN","-",3,"Rel-4","T1","2002-05-28","2004-03-17",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-3",null,null,"TP-23",null,"2002-09-26","2003-03-14"]
[8970,41007,"      Testing of Extended Robut Header Compression","Ext-RoHC",3,"Rel-4","T1","2002-09-18","2003-09-30",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 15% complete)","34.123-1, -2",null,null,null,null,"2002-09-26","2003-03-14"]
[8971,41008,"      Deleted - Testing of Extended Robut Header Compression - TTCN","-",3,"Rel-4","T1","2002-09-18","2003-12-16",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2002-09-26","2003-03-14"]
[8972,41009,"      Deleted - General changes to TS34.121 corresponding to release 4","RANimp-test,TEI4",3,"Rel-4","T1","2003-03-03","2004-03-03",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34.121",null,null,"TP-23",null,"2003-03-14","2003-03-14"]
[8973,401652,"Rel-4 Emergency call enhancements","EMC1-CS",1,"Rel-4","N1,S1,T1","2000-01-03","2002-05-28",1,"-","-","Ericsson","-","Acronym changed from EMC1, EMC1-CS","-",null,null,null,null,"2000-08-08","2015-03-24"]
[8974,1654,"   For CS based calls","EMC1-CS",2,"Rel-4","N1","2000-01-03","2002-05-28",1,"NP-010136","-","Ericsson","-","WI approved in TSG_10","-",null,null,null,null,"2000-08-08","2001-05-30"]
[8975,1320,"      Distinction in CS domain of emergency call types to different emergency services","-",3,"Rel-4","S1","2000-05-01","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2008-07-21"]
[8976,1999,"      Distinction in CS domain of emergency calls to different emergency types","-",3,"Rel-4","N1","2000-08-24","2000-09-22",1,"NP-010136","-","-","-","Calls to different emergency services such as ambulance, fire brigade, police, etc. can be routed to respective different emergency centres.",24.007999999999999,null,null,null,null,"2000-09-23","2008-07-21"]
[8977,402224,"      Deleted - Conformance Test Aspects - Emergency call enhancements","-",3,"Rel-4","T1","2000-01-03","2000-07-28",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"TP-08",null,"2000-11-16","2008-12-12"]
[8978,2226,"      Testing CS based emergency calls","-",3,"Rel-4","T1","2002-02-25","2002-05-28",1,"TP-030052","-","-","-","-","34.123-1",null,null,null,null,"2000-11-28","2003-01-13"]
[8979,2563,"      Testing CS based emergency calls - TTCN","-",3,"Rel-4","T1","2001-11-22","2002-05-28",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[8980,401826,"Rel-4 Terminal interfaces","TI",1,"Rel-4","T2","2000-01-03","2001-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-03-13"]
[8981,1827,"   AT commands enhancements","TI-ATC",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-13"]
[8982,1828,"      Specification of AT commands for new services","-",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","goal not completely achieved because of missing input",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-20"]
[8983,1829,"   Wide Area Data Synchronization","TI-WADS",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","AS: Rel5 changed to Rel4 according to SP#10 decision, milestone on testing added","-",null,null,null,null,"2000-09-14","2000-12-19"]
[8984,1830,"      Continues evolution of Synchronization protocol","TI-SYNC-EVOL",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-","27.903, 27.103",null,null,null,null,"2000-09-14","2001-03-20"]
[8985,1832,"   Terminal local model","TLM",2,"Rel-4","T2","2000-05-16","2001-03-15",1,"TP-000080","-","Ericsson","Olga.Tome@ECS.ERICSSON.SE","-",23.227,null,null,null,null,"2000-09-14","2001-09-14"]
[{"$f":"A8986+1","v":8986},401536,"Rel-4 Location Services enhancements","LCS4",1,"Rel-4","S2,S1,T2,N1,N4,R3,R2","2000-04-03","2001-12-28",1,"SP-010518","-","Nokia","Jan Kall","Acronym changed form LCS1","-",null,null,null,null,"2000-07-28","2015-03-24"]
[8987,2229,"   CBS interactions","LCS4-CBS",2,"Rel-4","T2","2000-04-03","2001-12-28",1,"-","-","-","-","-",23.041,null,null,null,null,"2000-09-14","2015-03-24"]
[8988,523,"   LCS support in the CS domain","LCS4-CS",2,"Rel-4","S2","2000-05-15","2001-01-19",1,"-","-","-","-","Only MAP impact foreseen so far. To be further split if needed.","-",null,null,null,null,"2000-04-19","2015-03-24"]
[8989,525,"   LCS support in the PS domain","LCS4-PS",2,"Rel-4","S2,S1,N1,N4","2000-05-01","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2015-03-24"]
[8990,1642,"      Stage 1 for LCS support in the PS domain","-",3,"Rel-4","S1","2000-07-03","2000-08-25",1,"-","-","Pacific Bell Wireless","Randolph Wohlert (rwohlert@tri.sbc.com)","To be also considered: External LCS client identity, and Privacy options when PDP-context and when no PDP-context is established",22.071000000000002,null,null,null,null,"2000-08-08","2000-04-01"]
[8991,1181,"      Stage 2 for LCS support in the PS domain","-",3,"Rel-4","S2,R2,G1","2000-05-01","2001-01-19",1,"-","-","-","-","SP#10 completed","25.305 (UTRAN part), new 23.271 (CN part by S2, 43.059 (GERAN part)",null,null,null,null,"2000-04-19","2000-12-13"]
[8992,1180,"      Stage 3 for LCS support in the PS domain","-",3,"Rel-4","N1,N4","2000-08-21","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-10-10"]
[8993,526,"         Layer 3 LCS signalling UE (MS) -SGSN (UMTS PS and and GSM-GPRS)","-",4,"Rel-4","N1","2000-08-21","2001-12-28",1,"-","-","Nokia","Janne Muhonen","-","-",null,null,null,null,"2000-04-19","2002-03-25"]
[8994,2462,"         MAP impacts of LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-20","2001-03-20"]
[8995,527,"         GTP signalling for LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[8996,401600,"   UE positioning Rel-4","LCS1-UEpos",2,"Rel-4","R3,R2","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","-","-","-","-",null,null,null,null,"2000-07-26","2002-04-09"]
[8997,1601,"      Iub/Iur interfaces for methods Rel 99","LCS1-UEpos-IubIur",3,"Rel-4","R3","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","Ericsson","Yun-Chao Hu","-","25.401, 25.420, 25.423, 25.430, 25.433, new 25.850",null,null,null,null,"2000-07-26","2001-03-20"]
[8998,1602,"      UE positioning enhancements - IPDL for TDD","LCS1-UEpos-enh",3,"Rel-4","R2","2000-08-28","2001-03-23",1,"RP-000509","RP-010045","Siemens","Armin Sitte ","5 Mar 2001: split of IPDL for TDD agreed by R2","new 25.847",null,null,null,null,"2000-07-26","2012-05-22"]
[8999,401560,"Rel-4 UICC/(U)SIM enhancements and interworking","UICC1",1,"Rel-4","T3","2000-07-24","2001-03-23",1,"-","-","-","-","Acronym changed from UICC1, Rel-4","-",null,null,null,null,"2000-04-09","2015-03-24"]
[9000,1799,"   Common PCN Handset Specification (CPHS)","UICC1-CPHS",2,"Rel-4","T3","2000-07-24","2001-03-23",1,"TP-000116","-","One2One","-","28/5/2001: CRs approved at TP-11. WI complete.",27.103000000000002,null,null,null,null,"2000-09-14","2001-05-28"]
[9001,401800,"Rel-4 (U)SIM toolkit enhancements","USAT4",1,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"-","-","Gemplus","Jean-Francois Rubon","Acronym changed from USAT1, USAT1-LocLnk, USAT1APIJAVA, USAT1SM","23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[9002,2034,"   USAT local link","USAT1-LocLnk",2,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"TP-000116","-","Gemplus","Jean-Francois Rubon","25/5/2001:CR was approved at TP-11. WI is complete","22.038, 31.111",null,null,null,null,"2000-09-27","2001-05-28"]
[9003,401571,"Rel-4 Security enhancements","SEC4",1,"Rel-4","S3,N4,N1","2000-01-03","2002-03-15",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","acronym changed from SEC1","-",null,null,null,null,"2000-04-09","2015-03-24"]
[9004,1331,"   Rel-4 Lawful Interception","SEC4-LI",2,"Rel-4","S3","2000-08-21","2001-03-23",1,"-","-","-","-","Requirements capture: S3#14 (Aug 00), Feature specification: S3#15 (Sep 00), Definition of architecture. Should be included in general LI work mentioned above.. Acronym changed from SEC1-LI",33.106999999999999,null,null,null,null,"2000-04-09","2015-03-24"]
[9005,1587,"   Evolution of GSM CS algorithms (e.g. A5/3 development and deployment)","SEC1-CSALGO1",2,"Rel-4","S3","2000-01-03","2001-01-15",1,"SP-000306","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[9006,1588,"   Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","SEC1-PSALGO1",2,"Rel-4","S3,N4,N1","2000-02-22","2000-12-22",1,"SP-000307","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[9007,1589,"      Deleted - Main aspects of Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","-",3,"Rel-4","S3","2000-02-22","2000-11-24",1,"-","-","DTI, BIS","cbrookson@iee.org","Complete TSG#09 (09/2000). S3#17: Proposed for deletion. TO BE DELETED","-",null,null,"SP-69",null,"2000-04-09","2011-08-06"]
[9008,1618,"      Impact on GTP","-",3,"Rel-4","N4","2000-03-20","2000-12-22",1,"-","-","DTI, BIS","cbrookson@iee.org","-","-",null,null,null,null,"2000-08-08","2000-12-13"]
[9009,1661,"      GEA capability indication in MS CM","SEC1-PSALGO1-GEACAP",3,"Rel-4","N1","2000-06-19","2000-12-22",1,"-","-","Vodafone Airtouch","Duncan Mills","-","-",null,null,null,null,"2000-08-08","2000-11-15"]
[9010,401583,"   Deleted - MAP application layer security","SEC1-MAPAL",2,"Rel-4","S3","2000-01-03","2002-03-15",1,"-","-","-","-","REPLACED BY NDS-MAP and NDS-IP. Completed Auto Key Management -> Rel-6. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[9011,401584,"      Deleted - Main aspects of MAP application layer security","-",3,"Rel-4","S3","2000-02-21","2001-03-29",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"SP-11",null,"2000-04-09","2002-04-09"]
[9012,402025,"      Deleted - Other stage 3 aspects","-",3,"Rel-4","N4","2000-02-22","2000-11-24",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"CP-10",null,"2000-04-09","2002-04-09"]
[9013,401594,"      Deleted - Visibility and Configurability of security","SEC1-VCS",3,"Rel-4","S3","2000-01-03","2002-03-15",1,"SP-000305","-","France Telecom","Sebastien.nguyenngoc@rd.francetelecom.com","CR approved at SA3#21 awaiting comments from CN1. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[9014,401142,"Rel-4 Charging and OAM&P","OAM4",1,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-010461","-","-","-","SP#13 approved WID","-",null,null,null,null,"2000-04-26","2002-01-24"]
[9015,2089,"   Rel-4 Principles, high level Requirements and Architecture","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-010461","-","Motorola, Telia","Michael.Truss@motorola.com, Tommy.R.Berggren@TELIA.SE","-","32.101, 32.102",null,null,null,null,"2000-04-26","2003-01-13"]
[9016,2088,"   Rel-4 Performance Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-010238","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.4xy, 52.402",null,null,null,null,"2000-04-26","2003-01-13"]
[9017,2081,"   Fault Management","-",2,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-000524","-","Lucent","-","-","32.111-1/4",null,null,null,null,"2000-04-26","2003-01-13"]
[9018,2082,"   Configuration Management","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Ericsson","thomas.tovinger@ericsson.com","-","32.106-1/8",null,null,null,null,"2000-04-26","2003-01-13"]
[9019,2083,"   Rel-4 Charging Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-000524","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.200, 32.205, 32.215, 32.235",null,null,null,null,"2000-04-26","2009-07-07"]
[9020,2071,"   UTRAN Operations and Maintenance procedures","UOAM",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Mannesmann Mobilfunk","bert.boden@d2mannesmann.de","-",32.799999999999997,null,null,null,null,"2000-10-09","2003-01-13"]
[9021,1517,"Global Text Telephony","GTT",1,"Rel-4","S1,S2,S4,T1,R5","2000-01-03","2001-03-19",1,"SP-010340","-","Ericsson ","gunnar.hellstrom@omnitor.se","SP#12 updated WID SP-000162=>SP-010340","-",null,null,null,null,"2000-07-28","2009-10-14"]
[9022,1634,"   Stage 1 for Global Text Telephony","-",2,"Rel-4","S1","2000-04-05","2000-12-22",1,"SP-010340","-","-","-","-",22.225999999999999,null,null,null,null,"2000-08-08","2012-05-09"]
[9023,1519,"   Stage 2 for Global Text Telephony","-",2,"Rel-4","S2","2000-01-03","2000-10-13",1,"SP-010340","-","-","-","-",23.225999999999999,null,null,null,null,"2000-07-28","2002-01-24"]
[9024,2234,"   Specification of Cellular Text telephone Modem","GTT-CTM",2,"Rel-4","S4","2000-09-11","2001-03-19",1,"SP-010340","-","-","-","-","-",null,null,null,null,"2000-12-13","2002-02-28"]
[9025,2238,"      General description and C-code","-",3,"Rel-4","S4","2000-09-11","2000-12-11",1,"-","-","-","-","-","26.226, 26.230",null,null,null,null,"2000-12-13","2002-02-28"]
[9026,2237,"      Minimum Performance requirements","-",3,"Rel-4","S4","2000-09-11","2001-03-19",1,"-","-","-","-","-",26.231000000000002,null,null,null,null,"2000-12-13","2002-02-28"]
[9027,1852,"   Deleted - Conformance Test Aspects - Global Text Telephony","GTT_Test",2,"Rel-4","R5,T1","2000-09-21","2000-09-21",1,"-","-","-","-","RP#45 work item abandoned/closed (it was never really started)","-",null,null,"RP-45","PCG-23","2000-09-14","2009-09-15"]
[9028,0,"--- RELEASE 99 ---","-",1,"R99","NP,SP,TP,SMG","2000-01-03","2000-12-29",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[9029,60150,"UMTS Features","-",1,"R99","S1,S2,S4,SMG,N3,N4,RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-08-11"]
[9030,60102,"   UMTS_SERVICES","UMTS_SERVICES",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[9031,60103,"   UMTS phase 1","UMTS1",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.1,null,null,null,null,"2009-07-06","2009-07-06"]
[9032,60119,"   UMTS Capabilities","UMTS_Capabil",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[9033,60164,"   Architecture of the GSM-UMTS platform","-",2,"R99","S2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","wid “Architecture overview of the GSM-UMTS System”, “Architecture the GSM-UMTS Platform” and “New Access Network to Core Network (BSS-NSS) interface”","23.002, 23.008, 23.060, 23.101, 23.110",null,null,null,null,"2009-07-16","2009-07-21"]
[9034,60165,"   UMTS Terrestrial Radio Access Network","UTRAN",2,"R99","RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.011, 22.038, 22.060, 22.078, 22.100, 22.101, 22.105, 22.115, 22.129, 23.002, 23.060, 24.007, 24.008, 25.101, 25.102, 25.104, 25.105, 25.113, 25.123, 25.133, 25.141, 25.142, 25.201, 25.211, 25.212, 25.213, 25.214, 25.215, 25.221, 25.222, 25.223, 25.224,",null,null,null,null,"2009-07-16","2009-07-21"]
[9035,60083,"   UMTS 1800, UMTS 1900","Rlnlmp19,Rlnlmp18",2,"R99","R2","1999-01-01","1999-12-31",1,"-","-","-","-","-","25.307 CR#0002, 0003 Inclusion of release independent RF related information",null,null,null,null,"2009-07-30","2010-02-09"]
[9036,60149,"   Mandatory speech codec for narrowband telephony service","Mandatory_Speech_Codec,AMR-NB,AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","Define the default speech codec for UMTS (both for FDD and TDD). Definition limited to selection of one codec among several existing ones/proposed codecs: GSM AMR, IS127 EVRC, ITU G.729 and MPEG-4 speech codec.","04.08, 05.01, 05.02, 05.03, 05.05, 05.08, 05.09, 05.09, 05.50, 08.60, 08.61, 11.21, 26.071, 26.073, 26.074, 26.090, 26.091, 26.092, 26.093, 26.094, 26.101, 26.102, 26.103, 26.104, 26.975",null,null,null,null,"2009-07-16","2009-08-11"]
[9037,60055,"   Codec for low bitrate multimedia telephony service","Low_bit_rate_codec_for_MM_Tel.,H.324M",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.104, 26.110, 26.111, 26.911, 26.912, 26.915",null,null,null,null,"2009-07-16","2009-08-11"]
[9038,60109,"   3G Audio-Visual Terminal characteristics","WI5TAC,3G-AVT,Terminal_Acoustic_Characteristics",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99129","-","-","-","-","26.131, 26.132",null,null,null,null,"2009-07-16","2009-08-11"]
[9039,60104,"   Updates_for_UMTS","Updates_for_UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.022, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9040,60124,"   UMTS","UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-08","2009-07-06"]
[9041,60151,"UMTS and GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4,R2,R3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[9042,60147,"   Multimedia Messaging Service","MMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MMS allows users to send/receive messages e.g. almost unlimited text length, images, audio and video clips and new content types. R99 only includes the concept. MMS stage 3 is not included in 23.140. Rel-4 adds detailed architecture and protocols.","22.140, 23.040, 23.140",null,null,null,null,"2009-07-16","2009-07-21"]
[9043,60121,"   Location Services","LCS",2,"R99","S1,S2,S3,SMG1,SMG2,SMG12,N1,N2,N4,R2,R3","1999-01-01","1999-12-31",1,"SP-99327","-","-","-","LCS provide ability to localize a terminal","02.07, 03.71, 04.31, 04.35, 04.71, 05.05, 08.08, 08.31, 08.71, 09.31, 22.071, 23.002, 23.003, 23.007, 23.008, 23.016, 23.018, 23.032, 23.171, 24.007, 24.008, 24.030, 24.080, 25.305, 25.306, 25.331, 25.413, 25.423, 29.002, 29.010",null,null,null,null,"2009-07-16","2011-08-06"]
[9044,60118,"   Customised Application for Mobile network Enhanced Logic Phase 3","CAMEL3",2,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"SP-99368","-","-","-","CAMEL is a network feature providing mechanisms to support services of operators which are not covered by standardised services, even when roaming outside the HPLMN.","22.101, 23.008, 23.012, 23.016, 23.018, 23.060, 23.072, 23.078, 23.079, 23.082, 23.093, 29.002, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[9045,60218,"      Global view","-",3,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.078, 23.078, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[9046,60318,"      Multiple Subscriber Profile (MSP) based on CAMEL phase 3","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","MSP is an optional service enabling mobile subscribers to have several profiles associated with a single IMSI, with each profile being a subscription option. Each profile may be used for mobile originated and mobile terminated calls.","22.097 (Advanced Addressing)",null,null,null,null,"2009-07-16","2009-07-21"]
[9047,60038,"   Short Message Service enhancements / Enhanced Messaging Service (EMS)","EMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","SMS for 3G terminals compatible with GSM SMS. Added Enhanced Messaging Service (EMS) allowing small pictures, sounds, animations to be transferred via SMS.","23.038, 23.039, 23.040, 23.042",null,null,null,null,"2009-07-16","2009-07-21"]
[9048,60122,"   Mobile Station Execution Environment","MExE",2,"R99","S1,SMG1,T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MExE provides a standardized MS execution environment and ability to negotiate its supported capabilities with a MExE SP. R99 enhances SIM MExE certificate management, security clarifications, QoS and defines two MExE classmarks WAP/Personal-Java based.","02.57, 22.057, 22.101, 23.057",null,null,null,null,"2009-07-16","2009-07-21"]
[9049,60123,"   MS_Classmark","MS_Classmark",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","MExE classmark identifies a category of MExE UE supporting MExE functionality with a minimum level of processing, memory, display, and interactive capabilities. Several MExE classmarks may be defined. ",24.007999999999999,null,null,null,null,"2009-07-08","2009-07-07"]
[{"$f":"A9050+1","v":9050},60057,"   MultiCall","Multicall",2,"R99","S1,N1,N2,N4","1999-01-01","1999-12-31",1,"NP-000348","-","-","-","Multicall allows several simultaneous CS calls with dedicated bearers of independent traffic and performance characteristics. R99 Multicall was defined as a supplementary service limited to one CS bearer to be used for speech at any time.","22.030, 22.083, 22.087, 23.008, 23.009, 23.016, 23.018, 23.108, 23.135, 24.008, 24.080, 24.135, 29.002, 29.010",null,null,null,null,"2009-07-16","2009-07-21"]
[9051,60058,"      Stage 1 for Multicall","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.030, 22.083, 22.087",null,null,null,null,"2009-07-30","2010-02-09"]
[9052,60105,"   Virtual Home Environment","VHE",2,"R99","S1,SMG1,S2","1999-01-01","1999-12-31",1,"-","-","-","-","Information exists in SP#5-8 reports & in SP-99416,SP-000095,SP 000155. OSA allows service development by operators and 3rd parties by making use of network functionality through open, standardised, secure, extensible and scalable interfaces. ","02.01, 22.105, 22.121,23.127",null,null,null,null,"2009-07-06","2009-07-06"]
[9053,60067,"   Open Service Access","OSA",2,"R99","S1,S2,N5","1999-01-01","1999-12-31",1,"-","-","-","-","Open Service Architecture became in later Releases Open Service Access. Produced by Parlay, ETSI SPAN (TISPAN), 3GPP SA1 (Stage 1), SA2 (Stage 2) and CN5 (Stage 3), resulting in a single set of standard OSA APIs for the whole development community.","22.121, 23.127, 29.198, 29.998",null,null,null,null,"2009-07-06","2009-07-06"]
[9054,60091,"   Super Charger mechanism for signalling traffic associated with mobility","Super_Charger",2,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Super Charger reduces mobility management cost by reducing the volume of location update signalling. It changes subscriber data management associated with inter-VLR and SGSN location updates. It also applies to packet services (SGSN replaces VLR and ","21.905, 23.007, 23.008, 23.012, 23.016, 23.018, 23.040, 23.060, 23.116, 23.912, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[9055,60039,"   Follow_Me service","Follow_Me",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Follow Me enables a mobile subscriber A to manipulate the Follow Me data of a party B in such a way that - under certain conditions - subsequent calls directed to party B will be forwarded to subscriber A. It is PLMN-specific and control based on USSD","21.905, 22.004, 22.030, 22.082, 22.090, 22.094, 23.090, 24.090, 22.094, 23.011, 23.015, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[9056,60093,"   Wide area network Synchronization and object exchange","SYNC",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Allows data stored in ME/USIM to be synchronized with the outside world. TS 27.103 defines protocols based upon IrMC level 4 and will evaluate new technologies (XML) for inclusion. From Rel-4 IrMC was replaced by SyncML in 27.103. ","27.103, 27.903",null,null,null,null,"2009-07-16","2009-07-06"]
[9057,60145,"   R99 Terminal Interfaces","-",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[9058,60166,"      AT commands for 3GPP","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","AT commands to control a 3G ME via an external Terminal Equipment (TE), fully compatible with GSM AT commands. R99 adds new AT commands e.g. to control Advanced Speech Call Items (ASCI) services.","27.005, 27.007",null,null,null,null,"2009-07-16","2009-07-20"]
[9059,60167,"      Physical interfaces","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Conclusion: 3GPP should not produce any technical specification for terminal interfaces other than radio interface and USIM interface. SDOs could develop own optional physical connector specification based on market requirements",27.901,null,null,null,null,"2009-07-16","2009-07-20"]
[9060,60168,"      Multiplexer","MUXMS-TE",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Multiplexing protocol allowing a number of simultaneous sessions between a MS and a terminal¦used to send any data (voice, SMS, USSD, fax etc.). 27.010 describes the protocol, but not the commands or data transported with it.",27.01,null,null,null,null,"2009-07-16","2009-07-20"]
[9061,60169,"   Bearer Services","-",2,"R99","S1,T2,N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[9062,60012,"      Circuit Switched Bearer Services","Circuit_switched_Bearer_Services",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported","22.002, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-16","2009-07-20"]
[9063,60021,"         Stage 1 for Circuit Switched Bearer Services","CS_Bearerss_in_UMTS",4,"R99","S1","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported",22.001999999999999,null,null,null,null,"2009-07-16","2009-07-20"]
[9064,60019,"         CS_Bearers","CS_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[9065,60020,"         CS_Bearerss","CS_Bearerss",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.21, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9066,60022,"         CS_Data","CS_Data",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.002, 27.003, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9067,60023,"         CS_Data_Bearers","CS_Data_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9068,60024,"         Deleted - CN3 poart of Circuit Switched Bearer Services","CSBS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.910, 27.001, 29.007",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[9069,60040,"      Frame Tunnelling Mode","FTM",3,"R99","T2,N1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","FTM is a type of async non-transparent CS bearer service (22.002). Generic term for HDLC and HDLC-related transmission protocols. Converts async non-transp data stream towards mobile side & sync data stream using X.31 flag stuffing on fixed network side.","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9070,60171,"      Access to ISPs and Intranets – Wireless/Remote access to LANs","InterworkingwithPDN(DHCP)",3,"R99","N3","1999-01-01","1999-12-31",1,"N3-99069","-","-","-","Access to an Intranet or ISP by running DHCP between the TE and a server in the Intranet/ISP domain. ",29.061,null,null,null,null,"2009-07-16","2009-07-06"]
[9071,60070,"      PHS Internet Access Forum Specification","PIAFS",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","PIAFS is one type of CS bearer data service (22.002). It refers to async CS tx protocol over ISDN 64 kbit/s unrestricted digital line. Facilitates interworking between PHS-MS and UMTS-UE & UMTS-UE and existing PIAFS TA (Terminal Adapter).","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-16","2009-07-06"]
[9072,60170,"         Personal Handyphone System Internet Access Forum Standard (PIAFS)","-",4,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","PIAFS was originally standardised by the PHS Internet Access Forum in Japan. More information can be found at: http://www.infopro.or.jp/piaf",22.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[9073,60092,"         Support_of_PIAFS_in_UMTS","Support_of_PIAFS_in_UMTS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9074,60172,"   Universal Integrated Circuit Card (UICC) and Universal Subscriber Identity Module (USIM)","UICC,USIM",2,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","For 3G, GSM 11.11 was divided into two parts: a platform comprised of basic physical, electrical and logical specification (31.101) and an application specification (31.102)","-",null,null,null,null,"2009-07-16","2009-07-21"]
[9075,60173,"      UICC / Terminal interface; Physical and logical characteristics","UICC",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines a generic Terminal/Integrated Circuit Card (ICC) interface. Is independent of 3G USIM application => platform for any IC card application. Ensures interoperability between ICC and terminal independently of manufacturer, card issuer or operator.","31.101 (Since 10/2000, ETSI EP SCP is responsible for the generic Terminal/Integrated Circuit Card (ICC) interface 102 221)",null,null,null,null,"2009-07-16","2009-07-21"]
[9076,60142,"      UICC/(U)SIM enhancements and interworking","UICC99",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from UICC1","31.102, 31.900",null,null,null,null,"2009-07-08","2015-03-24"]
[9077,60174,"      Characteristics of the USIM application","USIM",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines Universal Subscriber Identity Module (USIM) application for 3G telecom network operation & resides on UICC, an IC card specified in 31.101. UICC can be used as a multi-application card: several USIMs and/or other applications can co-exist",31.102,null,null,null,null,"2009-07-16","2009-07-21"]
[9078,60114,"      UICC Application Identifiers","AID,Application_Identifiers",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines and administers Application IDentifiers (AID) for UICC. AID is used to address an application in the card. Consists of Registered application provider ID (RID) & Proprietary application ID exception (PIX - according to ISO/IEC 7816-5).","21.111, 31.110",null,null,null,null,"2009-07-16","2009-07-21"]
[9079,60139,"      SIM Application Toolkit","SAT",3,"R99","S1,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","11.14, 22.030, 22.100, 22.101",null,null,null,null,"2009-07-08","2009-07-06"]
[9080,60141,"      USIM Application Toolkit","USAT",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines UICC - ME interface, and mandatory ME procedures for USAT. Based on GSM 11.14 (SIM Application Toolkit). Commands and procedures defined in USIM and 3G Terminal for using USAT. Service and security requirements defined in 22.100 and 22.101.",31.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[9081,60175,"      Bearer Independent Protocol for SAT applications to exchange data over the GSM network","BIP",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines at SIM-ME interface a basic protocol allowing SIM Toolkit applications to determine available bearers and to exchange data by selecting using the most appropriate bearer available (CS data, GPRS, SMS, Unstructured Supplementary Service Data (USSD)","03.48, 11.10, 11.14",null,null,null,null,"2009-07-16","2009-07-21"]
[9082,60176,"      Administrative commands and functions for IC cards","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines function and syntax of administrative commands for telecommunication IC Card used during installation, activation and de-activation of applications. Compliant to ISO/IEC 7816 series. Handed over to ETSI Project Smart Card Platform (SCP) in 2000.","ETSI 102 222",null,null,null,null,"2009-07-16","2009-07-21"]
[9083,60177,"      USIM and UICC requirements","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","High level requirements for 3GPP IC card and its interface to 3GPP terminal (USIM&UICC reqs). Service&security reqs in 322.01,22.00. USIM is a 3GPP application on an IC card. Inter-operates with 3GPP terminals and provides access to 3GPP services",21.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[9084,60140,"      SIM_API","SIM_API",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.19,null,null,null,null,"2009-07-08","2009-07-06"]
[9085,60086,"      SIM_toolkit_API","SIM_toolkit",3,"R99","SMG9,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.48, 11.11, 11.14",null,null,null,null,"2009-07-06","2009-07-06"]
[9086,60087,"      Deleted - 1.8 Volt SIM ME interface","SMIME_1.8V",3,"R99","SMG9","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI",11.18,null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[9087,60178,"   USIM/UICC Testing","-",2,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[9088,60179,"      Terminal tests for the UICC Interface","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Test spec for the interface between UICC and terminal (originally based GSM 11.10-1 clause 27). Ensures UICC - terminal interoperability independently of manufacturer, card issuer or operator. Tests for applications residing on UICC are in 31.121",31.12,null,null,null,null,"2009-07-16","2009-07-21"]
[9089,60180,"      USIM application test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Application test spec originally based on GSM 11.17. Aspects related to UICC administrative management phase are not defined. Any internal technical realisation of either UICC or terminal is only specified where these are reflected over the interface.",31.120999999999999,null,null,null,null,"2009-07-16","2009-07-21"]
[9090,60181,"      USIM conformance test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Conformance Test specification for UICC defined in 31.101 with USIM defined in 31.102.",31.122,null,null,null,null,"2009-07-16","2009-07-21"]
[9091,60182,"      SIM toolkit test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","SIM Application Toolkit (SAT) has major impact on ME design and enhances SIM/ME interface. Contains tests for SIM/ME interface optional features (no network related signalling issues involved). Doesn't form basis for any type approval or regulatory tests.","11.10-4",null,null,null,null,"2009-07-16","2009-07-21"]
[9092,60137,"   Security for UMTS and GSM Features","Security",2,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.09, 03.20, 21.133, 22.022, 23.003, 23.007, 23.008, 23.012, 23.018, 24.007, 24.008, 24.010, 24.011, 29.002, 29.060, New (33.102, 33.103, 33.105, 33.107, 35.201)",null,null,null,null,"2009-07-16","2009-07-21"]
[9093,60183,"      Fraud Information Gathering Service (for connection-orientated services)","FIGS",3,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can monitor its subscribers in VPLMN, which collects info on a defined set of monitored subscribers activities & sends it to HPLMN, which can perform service limitation control eg Operator Determined Barring (ODB) and IST to limit financial exposure","New 22.031, 23.031",null,null,null,null,"2009-07-16","2009-07-21"]
[9094,60085,"      Immediate Service Termination / SECurity Immediate Service Termination","IST,SECIST",3,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can terminate all activities of its subscriber in VPLMN, if decides (based on info via eg FIGS) that a roaming subscriber is behaving in fraudulent/suspicious way. HPLMN can terminate all subscriber activities including calls in progress.","03.35, 22.032, 23.008, 23.016, 23.035, 29.002",null,null,null,null,"2009-07-08","2009-07-21"]
[9095,60018,"      Core_Network_Security","Core_Network_Security",3,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[9096,60152,"GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[9097,60184,"   Dual Transfer Mode within GSM and GPRS","DTM",2,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","2-99-1780 (2-99-H80 from SMG2#32) WID on “BSS co-ordination of Radio Resource allocation for class A GPRS services - GSM Radio Access (R99)”","03.55, 03.64, 04.18, 04.60, 05.01, 05.02, 05.08, 08.08, 23.060, 24.007, 24.008",null,null,null,null,"2009-07-16","2009-07-21"]
[9098,60013,"      Class A Dual Transfer Mode","Class_A_Dual_Transfer_Mode_(DTM)",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.0999999999999996,null,null,null,null,"2009-07-06","2009-07-06"]
[9099,60027,"      Dual Transfer Mode","-",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.55, 03.64, 04.18, 05.01, 05.02, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[9100,60185,"   General Packet Radio Service enahancements","GPRSenhancements",2,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GPRS was introduced in Release 97. Release 99 brings a number of essential corrections e.g. on Downlink Power Control, Timing Advance procedure, Cell reselection delay time, PBCCH scheduling, PTCCH mapping, etc. ","05.02, 05.05, 05.08, 05.10, 05.50, 11.21, 23.064, 24.008, 24.060",null,null,null,null,"2009-07-16","2010-02-09"]
[9101,60132,"      General Packet Radio Service","GPRS",3,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.60, 03.22, 03.64, 04.18, 04.60, 04.64, 04.65, 05.01, 05.02, 05.05, 05.08, 05.10, 08.08, 08.18, 11.10-1, 11.21, 22.041, 22.060, 23.003, 23.007, 23.060, 23.107, 23.122, 24.007, 24.008, 27.007, 27.060, 29.002, 29.016, 29.018, 29.060, 29.061",null,null,null,null,"2009-07-07","2009-07-06"]
[9102,60133,"      GPRS2","GPRS2",3,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Introduction of EGPRS (S1) + Introduction of Reserved Service Labels in the APN (N2)","02.60, 23.003",null,null,null,null,"2009-07-09","2009-07-06"]
[9103,60134,"      GPRS Tunnelling Protocol enhancement","GTP_enhancement",3,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.003, 23.008, 29.060",null,null,null,null,"2009-07-07","2009-07-06"]
[9104,60186,"   Enhanced Data rates for GSM Evolution - Phase 1","EDGE-Phase1",2,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","EDGE is independent of the frequency bands, so it can be deployed e.g. in 900 and 1900 MHz bands. The new physical layer based on 8-PSK modulation is introduced and EGPRS and ECSD facilitate the new modulation in single and multi slot constellation.","10.59, 02.34, 02.60, 03.30, 05.10, 05.50, 11.26",null,null,null,null,"2009-07-16","2010-02-09"]
[9105,60030,"      Enhanced Data rates for GSM Evolution","EDGE",3,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","02.34, 03.10, 03.20, 03.64, 04.03, 04.04, 04.06, 04.08, 04.18, 04.21, 04.22, 04.60, 04.64, 05.01, 05.02, 05.03, 05.04, 05.05, 05.08, 05.10, 05.50, 07.01, 07.02, 07.03, 08.08, 08.20, 08.58, 08.60, 09.07, 09.18, 11.10-1, 11.11, 11.21, 11.26, 23.034, 24.008,",null,null,null,null,"2009-07-06","2009-07-06"]
[9106,60034,"      EDGE-Layer1","EDGE-Layer1",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","05.05, 05.10, 05.50",null,null,null,null,"2009-07-06","2009-07-06"]
[9107,60135,"      High Speed Circuit Switched Data","HSCSD",3,"R99","SMG1,SMG2,SMG7","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.34, 04.18, 11.10-1",null,null,null,null,"2009-07-08","2009-07-06"]
[9108,60029,"      Enhanced Circuit Switched Data - Phase 1","ECSD",3,"R99","S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","ECSD supports both transparent and non-transparent services, up to 64 kbit/s and 57.6 kbit/s respectively. See Tdoc SMG2 670/99 “ECSD Concept Evaluation” for more info","05.02, 08.58, 22.034",null,null,null,null,"2009-07-06","2009-07-06"]
[9109,60032,"      EDGE-Enhanced Circuit Switched Data","EDGE-ECSD",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.03,null,null,null,null,"2009-07-06","2009-07-06"]
[9110,60035,"      Enhanced GPRS - Phase 1","EGPRS",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.07, 03.64, 04.14, 04.18, 04.60, 05.05, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[9111,60033,"      EDGE-EGPRS","EDGE-EGPRS",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","05.03, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[9112,60069,"      Packet Flow Context (PFC) ","PFC",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",4.18,null,null,null,null,"2009-07-06","2009-07-06"]
[9113,60031,"      Support for EGPRS in ANSI-136 networks and EDGE COMPACT","EDGE-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Support for EGPRS in ANSI-136 networks” and “EDGE Compact” (for ANSI-136 networks only). COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 03.30, 03.64, 05.01, 05.02, 05.03, 05.05, 05.08, 05.10",null,null,null,null,"2009-07-06","2009-07-06"]
[{"$f":"A9114+1","v":9114},60036,"      EGPRS COMPACT","EGPRS-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","04.18, 05.02",null,null,null,null,"2009-07-06","2009-07-06"]
[9115,60136,"      COMPACT","COMPACT",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 04.18, 04.60, 05.08, 23.122, 24.008",null,null,null,null,"2009-07-08","2009-07-06"]
[9116,60047,"   GSM_400","GSM_400",2,"R99","SMG2,SMG7,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GSM in the 400 MHz bands allows to deploy GSM within frequency bands in the range 450 to 500 MHz, previously used for analogue cellular systems. See Tdoc SMG2 190/99 and 595/99 for further info.","02.17, 03.22, 03.30, 04.04, 04.18, 04.60, 05.01, 05.02, 05.05, 05.08, 05.10, 05.50, 08.18, 08.58, 11.21, 24.008, 27.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9117,60048,"   GSM_450","GSM_450",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 03.30, 05.01, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[9118,60131,"   GSM_700","GSM_700",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.05,null,null,null,null,"2009-07-06","2009-07-06"]
[9119,60041,"   Deleted - GERAN","GERAN",2,"R99","SMG2,S2","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","G2: 04.18 CR#A248 , 04.60 CR#B090 ",null,null,"SP-06",null,"2009-07-30","2010-02-09"]
[9120,60153,"GSM Features transposed to UMTS","-",1,"R99","S1,S3,T2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[9121,60187,"   Cell Broadcast Service","CBS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Applicability of the Cell Broadcast Service (as defined for GSM network) to 3G networks",23.041,null,null,null,null,"2009-07-16","2010-02-09"]
[9122,60188,"   GSM mobile number portability euro MNP / North American MNP","MNP",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","R98 MNP: mobile subscriber ability to change PLMN operator within the same country whilst retaining its original MS ISDN number (MSISDN). IMSI is changed, only MSISDN is kept. R99 adds requirements for North American Service Provider Number Portability.",22.065999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[9123,60144,"      Mobile Number Portability","-",3,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.066, 29.002",null,null,null,null,"2009-07-08","2009-07-06"]
[9124,60189,"   Automatic establishment of roaming relations","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Telecom Italia","enrico.scarrone@telecomitalia.it","framework for commercial and technical interworking between UMTS Home Environments and Serving Networks who have no direct prior commercial agreements with each other.","22.101, 22.971",null,null,null,null,"2009-07-16","2010-08-31"]
[9125,60190,"   Advanced addressing","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.101, 22.75U, 22.975",null,null,null,null,"2009-07-16","2010-02-09"]
[9126,60191,"   UMTS numbering, addressing and identities","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Also new requirements for Single and Multiple Numbering scheme was added (CR#20 and 21). Deleted the term International Mobile User Identifier (IMUI) and changed IMSI (International Mobile Station Identifier=>International Mobile Subscriber Identity.",22.100999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[9127,60192,"   Lawful Interception for GSM Features transposed to UMTS","LI",2,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines an interception system in UMTS that supports a number of regional interception regulations. Regional interception requirements shall be met in using specific (regional) mediation functions allowing only required information to be transported.","New 33.106, 33.107",null,null,null,null,"2009-07-16","2009-07-06"]
[9128,60154,"Charging","-",1,"R99","S1,S5","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[9129,60011,"   R99 Charging","Charging",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.115, 23.121",null,null,null,null,"2009-07-06","2009-07-06"]
[9130,60215,"   R99 OAM Charging Management","OAMCH,CH",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99271","-","-","-","-","32.005, 32.015",null,null,null,null,"2009-07-06","2009-08-11"]
[9131,60155,"Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM1999",1,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","-",null,null,null,null,"2009-07-06","2010-02-09"]
[9132,60073,"   OAM Principles and High-level Requirements","PR,Princs_&_Reqs_(PR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-",32.100999999999999,null,null,null,null,"2009-07-06","2009-08-11"]
[9133,60062,"   OAM Architecture","OAMAR,AR,Telecom_Management_Arch_(AR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","32.101, 32.102",null,null,null,null,"2009-07-06","2009-08-11"]
[9134,60014,"   OAM Configuration Management","OAMCM,CM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99273","-","-","-","-","32.106, 32.106-1, 32.106-2, 32.106-3, 32.106-4, 32.106-5, 32.106-6, 32.106-7, 32.106-8",null,null,null,null,"2009-07-06","2009-08-11"]
[9135,60063,"   OAM Fault Management","OAMFM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99272","-","-","-","-","32.111, 32.111-1, 32.111-2, 32.111-3, 32.111-4",null,null,null,null,"2009-07-06","2009-08-11"]
[9136,60064,"   OAM Performance Management","OAMPM,PM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99274","-","-","-","-","12.04, 32.104",null,null,null,null,"2009-07-06","2009-08-11"]
[9137,60106,"Vocabulary","Vocabulary",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",21.905000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[9138,60037,"Emergency","Emergency",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[9139,60049,"GSM General Bearer Services (GBS) and interworking scenarios support in UMTS","GSM_to_UMTS_Evol",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS shall support GSM General Bearer Services (GBS) and interworking scenarios as specified in 02.02",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[9140,60043,"GPRS_Mobile_IP_interworking","GPRS_Mobile_IP_interworking",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[9141,60046,"GSM/UMTS interworking","2G3Ginterworking",1,"R99","N1,N2,N4,R3,S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 08.18, 08.58, 09.08, 22.011, 23.003, 23.009, 23.014, 23.034, 23.122, 24.007, 24.008, 24.011, 24.080, 29.108",null,null,null,null,"2009-07-06","2009-07-06"]
[9142,60050,"Handover","Handover",1,"R99","S1,SMG2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 08.08, 08.58, 22.129, 23.009, 29.002, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[9143,60120,"2G3Ghandover","2G3Ghandover",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[9144,60088,"Service Provider Name Indication","SPANME",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Service Provider Name Indication included in R98 (02.07) was not carried into R99 (22.101), but is in the SIM/USIM specification for R99",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[9145,60026,"Data & Data_CleanUp","Data,Data_CleanUp",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.01, 02.02, 02.04, 02.34",null,null,null,null,"2009-07-06","2009-07-06"]
[9146,60125,"Unstructured Supplementary Service Data (USSD)","USSD",1,"R99","SMG1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.04, 02.90, 23.090, 29.002",null,null,null,null,"2009-07-07","2009-07-07"]
[9147,60126,"Man-Machine Interface (MMI) of the User Equipment (UE)","MMI",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Data services streamlining + Support for Anonymous Call Rejection",22.03,null,null,null,null,"2009-07-08","2009-07-07"]
[9148,60127,"Network Identity and Timezone (NITZ)","NITZ",1,"R99","SMG1,SMG3","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.42, 04.08",null,null,null,null,"2009-07-08","2009-07-07"]
[9149,60128,"Deleted - Operator Determined Barring for Packet Oriented Services","ODB_Enh.",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Remove ODB for Packet Oriented Services from R99",22.041,null,null,"SP-69",null,"2009-07-09","2009-07-07"]
[9150,60068,"Packet Flow Management","Packet_Flow_Management",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",8.18,null,null,null,null,"2009-07-06","2009-07-06"]
[9151,60044,"GPRS_Point-To-Multipoint Group call ","GPRS_PTMG",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-",2.6,null,null,null,null,"2009-07-06","2009-07-06"]
[9152,60156,"Call Forwarding","-",1,"R99","SMG1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-22","2010-02-09"]
[9153,60010,"   Call Forwarding enhancements","CF_enhancements",2,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","23.078, 23.079, 23.082, 29.002, 29.078",null,null,null,null,"2009-07-06","2009-07-06"]
[9154,60116,"   Call_Forwarding","Call_Forwarding",2,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.82, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[9155,60117,"   Call_Forwarding_Enhancements","Call_Forwarding_Enhancements",2,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.082000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[9156,60157,"Quality of Service ","-",1,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","-",null,null,null,null,"2009-07-16","2010-02-09"]
[9157,60076,"   End-to-end UMTS Quality of Service management","QoS",2,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","23.107, 23.907, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[9158,60130,"   End-to-end QoS for PS Domain including IMS","E2EQoS99",2,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from E2EQos","23.060, 23.170",null,null,null,null,"2009-07-08","2015-03-24"]
[9159,60045,"   GPRS-enhanced_QoS","GPRS-enhanced_QoS",2,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","AT-commands for Enhanced QoS Support management",27.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[9160,60077,"   QoS_enhancements","QoS_enhancements",2,"R99","N2,N1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.008, 23.016, 24.008, 29.002, 29.060",null,null,null,null,"2009-07-06","2009-07-06"]
[9161,60129,"Support of Localised Service Area","SoLSA",1,"R99","SMG2,SMG3,SMG7,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Mechanism which can be used as a platform for providing special tariffs and/or special set of service features for certain subscribers within a regionally restricted area or areas. No additional features for R99.","04.08, 04.18, 08.08, 11.10-1, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[9162,60100,"Transcoder_location","Transcoder_location",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","UE location identification: background information and associated primitives 2. Transcoder location at the core network and source depending coding belonging to the non-access stratum.",23.11,null,null,null,null,"2009-07-06","2009-07-06"]
[9163,60113,"Antenna_test_methods","Antenna_test_methods",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.3,null,null,null,null,"2009-07-06","2009-07-06"]
[9164,60107,"WBAMR / high quality speech in UMTS Phase 1 but not in R99","WBAMR",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Add requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[9165,60138,"Codec","-",1,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[9166,60015,"   Codecs for Multimedia Telephony Service","Codec_for_Multimedia_Telephony",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[9167,60415,"      Codecs for Multimedia Telephony Service","Multimedia_Codec",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9168,60515,"      Codecs for Multimedia Telephony Service","CSM",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9169,60615,"      Codecs for Multimedia Telephony Service","WI2MMC",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9170,60715,"      Codecs for Multimedia Telephony Service","Codec(s)_for_CS_MM_Tel._Serv",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9171,60815,"      Codecs for Multimedia Telephony Service","Codec(s)_for_MM_Tel_Service",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9172,60915,"      Codecs for Multimedia Telephony Service","-",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9173,60078,"   QoS for Speech and Multimedia Codec","QoS_for_Speech_&_MM_Codecs_/_AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.102, 26.912",null,null,null,null,"2009-07-06","2009-08-11"]
[9174,60099,"   Tandem Free Operation - Adaptive Multi-Rate codec types","TFOAMR",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS_AMR2 is default Codec Type in R99 dual_mode terminals",26.103000000000002,null,null,null,null,"2009-07-06","2009-08-11"]
[9175,60112,"   Noise Suppression for AMR","AMRNS",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","Combination of the AMR speech codec and the Noise Suppression function. TS 06.77 and TR 06.78 only apply to GSM. They apply to UMTS from Rel-4 onwards, when they were converted to TS 26.077 and TR 26.078.","06.77, 06.78",null,null,null,null,"2009-07-06","2009-08-11"]
[9176,60065,"   Out-of-Band Transcoder","OoBT",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Transcoder handling in the CN at inter-system handover and relocation + Introduction of UMTS AMR","23.009, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[9177,60066,"   Out-of-Band Transcoder Control ","OoBTC",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","24.008 CR#0572 in NP-020220 was approved under this WI","24.008 CR#0572 in NP-020220",null,null,null,null,"2009-07-30","2010-02-09"]
[{"$f":"A9178+1","v":9178},60143,"Advanced Speech Call Items enhancements","ASCI",1,"R99","SMG1,SMG2,SMG3,SMG7,SMG9,N1,N4,S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.30, 02.68, 03.68, 03.69, 04.18, 08.08, 11.10-1, 11.11, 23.067, 23.094, 24.008, 24.067, 27.007, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[9179,60009,"Call Control improvements","CC_Related_items",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Minor improvements to 24.007 and 24.008 to increase the number of simultaneous calls/sessions from the present 7: the TI value is increased (NP-99441).","24.007, 24.008",null,null,null,null,"2009-07-06","2009-07-23"]
[9180,60059,"Multimedia","Multimedia",1,"R99","N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.008, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9181,60089,"Sub-System Number allocation for RANAP, RNSAP","SSN_allocation",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","Sub-System Number allocation for Radio Access Network Application Part, Radio Network Subsystem Application Part",23.003,null,null,null,null,"2009-07-06","2009-07-06"]
[9182,60053,"Intranet / ISP access with DHCP end-to-end","ISPaccess",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Access to an Intranet/ISP with DHCP end to end",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[9183,60072,"Point_to_Multipoint_Services","Point_to_Multipoint_Services",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Support for the IP-Multicast protocol",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[9184,60146,"Facsimile","FAX",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.003, 22.100",null,null,null,null,"2009-07-08","2009-07-06"]
[9185,60081,"Realtime_NT_FAX_in_UMTS","Realtime_NT_FAX_in_UMTS",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Asynchronous Interface for real-time NT Fax + Introduction of Asynchronous interface for Real-time non-transparent FAX","27.001, 27.003",null,null,null,null,"2009-07-06","2009-07-06"]
[9186,60042,"Gateway Location Register (GLR) - Mobile Application Part (MAP) specification","GLR",1,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.12,null,null,null,null,"2009-07-06","2009-07-06"]
[9187,60056,"Multiple Subscriber Profile phase 2","MSP2",1,"R99","S1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.097, 23.072, 23.083, 23.084, 23.091, 23.093, 23.097",null,null,null,null,"2009-07-06","2009-07-06"]
[9188,60074,"Prepaging","Prepaging",1,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[9189,60148,"Re-definition of channel quality measure used for AMR link adaptation for Downlink Advanced Receiver Performance (DARP) MS","-",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Re-definition of channel quality measure used for AMR link adaptation for DARP MS",5.09,null,null,null,null,"2009-07-08","2009-07-06"]
[9190,60051,"Harmonized Standard","HS",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",13.21,null,null,null,null,"2009-07-06","2009-07-06"]
[9191,60090,"Streamlining of specifications","Streamlining",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[9192,60079,"R99_Service_Clean_up","R99_Service_Clean_up",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.10, 27.001, 27.002, 27.003, 27.060, 29.007, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[9193,60094,"(Small) Technical Enhancements and Improvements for R99","TEI",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[9194,60095,"   TEI_[CS_Data]","TEI_[CS_Data]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[9195,60096,"   TEI_[GPRS]","TEI_[GPRS]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[9196,25016,"R99 UE Conformance Testing","TEI_Test",1,"R99","R5,T1","1999-01-01","1999-12-31",1,"-","-","-","-","Specifies Conformance Tests for a 3G UE to be recognised as “3GPP-standard compliant”. A 3GPP-external body, GCF (Global Certification Forum), delivers certificates to prove that a UE has correctly passed tests and is then conform to the 3GPP standard.","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2009-07-06","2009-07-06"]
[9197,60084,"   Deleted - RTEI","RTEI",2,"R99","T1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","34.123-1 CR#0650, 0651, 34.123-3 CR#0148, 0149, 0150",null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[9198,60193,"   Common test environments for User Equipment (UE); Conformance testing","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","-",34.107999999999997,null,null,null,null,"2009-07-22","2009-07-22"]
[9199,60194,"   Terminal conformance specification, Radio transmission and reception (FDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in FDD mode.",34.121000000000002,null,null,null,null,"2009-07-22","2009-07-22"]
[9200,60195,"   Terminal conformance specification, Radio transmission and reception (TDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in TDD mode.",34.122,null,null,null,null,"2009-07-22","2009-07-22"]
[9201,60196,"   UE conformance specification; Part 1: Protocol conformance specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","TS 34.123, composed of three parts, actually specifies the protocol conformance testing for the 3G UE. Part 1 describes the overall test structure.","34.123-1",null,null,null,null,"2009-07-22","2009-07-22"]
[9202,60197,"   UE conformance specification; Part 2: Implementation Conformance Statement (ICS) specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 2 contains the applicability of each test case defined as the “Implementation Conformance Statement (ICS) proforma”, in compliance with the relevant requirements, and in accordance with the relevant guidance given in ISO/IEC 9646-7 and ETS 300 406. ","34.123-2",null,null,null,null,"2009-07-22","2009-07-22"]
[9203,60198,"   UE conformance specification; Part 3: Abstract test suites (ATSs)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 3 specifies the protocol conformance testing in TTCN for the 3G UE at the Uu interface. It defines the TTCN test specification and design considerations in Abstract Test Suites based on the test cases specified in prose in part 1. ","34.123-3",null,null,null,null,"2009-07-22","2009-07-22"]
[9204,60028,"Deleted - Dual Tone Multi-Frequency signalling : Support in the whole 3GPP system","DTMF",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.014 CR#0004",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[9205,60052,"Deleted - Intersystem_Change","Intersystem_Change",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","04.18 CR#A243",null,null,"SMG",null,"2009-07-30","2010-02-09"]
[9206,60054,"Deleted - Long_Forwardedto_Numbers","Long_Forwardedto_Numbers",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,"NP-06",null,"2009-07-06","2009-07-06"]
[9207,60080,"Deleted - RANimp-FSEarlyUE","RANimp-FSEarlyUE",1,"R99","R3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","25.413 CR#0520, 0538, 0565, 0563, 0541, 0540, 0539, 0547",null,null,"RP-06",null,"2009-07-30","2010-02-09"]
[9208,0,"Release 1999 Studies","-",1,"R99","S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-06-14"]
[9209,60061,"Advanced Addressing/Numbering","Numbering",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Vodafone","mona.mustapha@vodafone.com ","Study on requirements for numbering and addressing for UMTS",22.975000000000001,null,null,null,null,"2009-07-06","2010-08-31"]
[9210,60161,"Combined GSM and Mobile IP mobility handling in UMTS IP CN","-",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.922999999999998,null,null,null,null,"2009-07-23","2010-02-09"]
[9211,60101,"UE Capabilities Requirements","UCR",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure",21.904,null,null,null,null,"2009-07-06","2009-07-06"]
[9212,60158,"Electrical safety requirements and regulations","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure. TR summarizes differences between international and national standards relevant to IEC60950 and refers to regulations for conformity assessment due to different regulatory environments in different countries / regions.",34.906999999999996,null,null,null,null,"2009-07-16","2009-07-06"]
[9213,60159,"Specific Absorbtion Rate (SAR) requirements and regulations in different regions","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure.",34.924999999999997,null,null,null,null,"2009-07-16","2009-07-06"]
[9214,60160,"Multi-mode UE issues","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Consequences on roaming capabilities and service availability (e.g. handover) of multi-mode UEs while roaming in various regions with various network configurations. Case studies for each of the possible scenarios in specs","21.810, 21.910",null,null,null,null,"2009-07-16","2009-07-06"]
[9215,60162,"Provision of fax service in GSM and UMTS","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","Ericsson","peter.bleckert@ericsson.com","CP#27: Moved to C1 on closure of T2¦see TP-050062. CP#28: C1->C3",22.945,null,null,null,null,"2009-07-23","2010-02-09"]
[9216,60163,"Separating Radio Resources and Mobility Management specific parts of the MS Classmark","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","CP#27: change of WG as a result of closure of CN and T.",23.814,null,null,null,null,"2009-07-23","2010-02-09"]