## Cover sheet
3GPP TSG RAN WG5#109 | [10 empty] | R5-255649
Dallas, US, November 17-21, 2025
Agenda Item: | 7.5.2
Source: | China Telecom
Title: | UE Conformance – NR demodulation performance evolution
Work item code: | NR_demod_enh3-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to enable UE conformance testing for the Rel-18 NR demodulation performance evolution WI which includes analysing the test case impact, applicability, test environment, and updating the relevant conformance specifications. The conformance testing aspects for this WI would consist of Demod area.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 93% (+13%) | 5 | 11
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 92.9% (+13.3%) | 5 | 11
FR1 |  | 92.4% (+13.1%) | 4 | 10
FR2 |  | 96.8% (+14.2%) | 1 | 1
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2 | 100% |  |  | 100%
NR RF/RRM
RF Demod/QSI test cases | 38.521-4 | 93.3% (+9.4%) | 5 | 11 | 91.7% (+11.8%) | 4 | 10 | 100% | 1 | 1
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 90% (+65%) |  |  | 90% (+70%) |  |  | 90% (+45%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5 References
[1] RP-241298 | New WID on UE Conformance – NR demodulation performance evolution, China Telecom, Qualcomm, Samsung, 3GPP TSG RAN Meeting #104
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP for UE Conformance – NR demodulation performance evolution | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_demod_enh3-UEConTest
WP Scope: |  | The objective of this work item is to enable UE conformance testing for the Rel-18 NR demodulation performance evolution WI which includes analysing the test case impact, applicability, test environment, and updating the relevant conformance specifications. | [12 empty] | vs Area
WP Resp: |  | Wu Jingzhou |  |  | wujingzhou@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 92.4% (+13.1%) | 96.8% (+14.2%)
[14 empty] | 32 | 8
[14 empty] | 11.2 | 1.5
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 | 5.4 | Default NG-RAN RRC message and information elements contents | Common UE configuration for Demod TCs if any. |  |  |  |  | TBD
TS 38.508-2: Common ICS
|  | 38.508-2 | A.4 | ICS proforma tables | ICS for new UE capabilities for advanced receiver for MU-MIMO. New ICS for ATP declaration. | China Telecom, Qualcomm | RAN5#109 (Nov-25) | R5-247164 R5-250412 |  | 0.5 | 100% | 100% |  | 100%
NR RF/RRM
TS 38.521-4: Demod test cases for Enhanced Receiver Type 2
|  | 38.521-4 | 5.1.1.3 | Applicability of requirements for optional UE features | Applicability rule for advanced Rec for MU-MIMO. | China Telecom | RAN5#109 (Nov-25) | R5-250418 |  | 0.1 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.2.2.1.16_1 | 2Rx FDD FR1 for PDSCH with intra cell inter user interference performance – 2x2 MIMO for both NSA and SA | Existing sub-clause header to be updated to '2Rx FDD FR1 for PDSCH with intra cell inter user interference performance for baseline MMSE-IRC receiver – 2x2 MIMO for both NSA and SA' | China Telecom | RAN5#109 (Nov-25) |  | The TC title in TS38.522 should also be updated. | 0 | 100% | 100% |  | 100%
| Y | 38.521-4 | 5.2.2.1.16_2 | 2Rx FDD FR1 for PDSCH with intra cell inter user interference performance for Enhanced Receiver Type 2 – 2x2 MIMO for both NSA and SA | Test 2-1 and Test 2-2 in 5.2.2.1.16 in TS38.101-4. | China Telecom | RAN5#109 (Nov-25) | R5-250411 R5-253487 | Test applicability is FFS. | 1 | 95% | 95% |  | 95%
|  | 38.521-4 | 5.2.2.2.17_1 | 2Rx TDD FR1 for PDSCH with intra cell inter user interference performance – 2x2 MIMO for both NSA and SA | Existing sub-clause header to be updated to '2Rx TDD FR1 for PDSCH with intra cell inter user interference performance for baseline MMSE-IRC receiver – 2x2 MIMO for both NSA and SA' | SGS Wireless | RAN5#109 (Nov-25) | R5-253488 | The TC title in TS38.522 should also be updated. | 0 | 100% | 100% |  | 100%
| Y | 38.521-4 | 5.2.2.2.17_2 | 2Rx TDD FR1 for PDSCH with intra cell inter user interference performance for Enhanced Receiver Type 2 – 2x2 MIMO for both NSA and SA | Test 2-1 and Test 2-2 in 5.2.2.2.17 in TS38.101-4. | SGS Wireless | RAN5#109 (Nov-25) | R5-253488 |  | 1 | 80% | 80% |  | 80%
|  | 38.521-4 | 5.2.3.1.16_1 | 4Rx FDD FR1 for PDSCH with intra cell inter user interference performance – 2x4 MIMO for both NSA and SA | Existing sub-clause header to be updated to '4Rx FDD FR1 for PDSCH with intra cell inter user interference performance for baseline MMSE-IRC receiver – 2x2 MIMO for both NSA and SA' | China Telecom | RAN5#109 (Nov-25) | R5-253486 | The TC title in TS38.522 should also be updated. | 0 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.2.3.1.16_2 | 4Rx FDD FR1 for PDSCH with intra cell inter user interference performance – 4x4 MIMO for both NSA and SA | Existing sub-clause header to be updated to '4Rx FDD FR1 for PDSCH with intra cell inter user interference performance for baseline MMSE-IRC receiver – 4x4 MIMO for both NSA and SA' | China Telecom | RAN5#109 (Nov-25) | R5-253486 | The TC title in TS38.522 should also be updated. | 0 | 100% | 100% |  | 100%
| Y | 38.521-4 | 5.2.3.1.16_3 | 4Rx FDD FR1 for PDSCH with intra cell inter user interference performance for Enhanced Receiver Type 2 – 2x4 MIMO for both NSA and SA | Test 3-1 and Test 3-2 in 5.2.3.1.16 in TS38.101-4. | China Telecom | RAN5#109 (Nov-25) | R5-253486 |  | 1 | 90% | 90% |  | 90%
| Y | 38.521-4 | 5.2.3.1.16_4 | 4Rx FDD FR1 for PDSCH with intra cell inter user interference performance for Enhanced Receiver Type 2 – 4x4 MIMO for both NSA and SA | Test 4-1 and Test 4-2 in 5.2.3.1.16 in TS38.101-4. | China Telecom | RAN5#109 (Nov-25) | R5-253486 |  | 1 | 90% | 90% |  | 90%
|  | 38.521-4 | 5.2.3.2.17_1 | 4Rx TDD FR1 for PDSCH with intra cell inter user interference performance – 2x4 MIMO for both NSA and SA | Existing sub-clause header to be updated to '2Rx TDD FR1 for PDSCH with intra cell inter user interference performance for baseline MMSE-IRC receiver – 2x2 MIMO for both NSA and SA' | SGS Wireless | RAN5#109 (Nov-25) | R5-254211 | The TC title in TS38.522 should also be updated. | 0 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.2.3.2.17_2 | 4Rx TDD FR1 for PDSCH with intra cell inter user interference performance – 4x4 MIMO for both NSA and SA | Existing sub-clause header to be updated to '4Rx TDD FR1 for PDSCH with intra cell inter user interference performance for baseline MMSE-IRC receiver – 4x4 MIMO for both NSA and SA' | SGS Wireless | RAN5#109 (Nov-25) | R5-254211 | The TC title in TS38.522 should also be updated. | 0 | 100% | 100% |  | 100%
| Y | 38.521-4 | 5.2.3.2.17_3 | 4Rx TDD FR1 for PDSCH with intra cell inter user interference performance for Enhanced Receiver Type 2 – 2x4 MIMO for both NSA and SA | Test 3-1 and Test 3-2 in 5.2.3.2.17 in TS38.101-4. | SGS Wireless | RAN5#109 (Nov-25) | R5-254211 R5-256866 |  | 1 | 80% (+60%) | 80% (+60%) |  | 80%
| Y | 38.521-4 | 5.2.3.2.17_4 | 4Rx TDD FR1 for PDSCH with intra cell inter user interference performance for Enhanced Receiver Type 2 – 4x4 MIMO for both NSA and SA | Test 4-1 and Test 4-2 in 5.2.3.2.17 in TS38.101-4. | SGS Wireless | RAN5#109 (Nov-25) | R5-254211 R5-256866 |  | 1 | 80% (+60%) | 80% (+60%) |  | 80%
|  | 38.521-4 | A.3 | DL reference measurement channels | New RMCs for Enhanced Receiver Type 2 requirements. | China Telecom | RAN5#109 (Nov-25) |  |  | 0.1 | 100% | 100% |  | 100%
TS 38.521-4: Demod test cases for ATP requirements
|  | 38.521-4 | 5.6 | PDSCH absolute physical layer throughput requirements | New Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.6.1 | 1RX requirements | New sub-Clause (Void) |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.6.2 | 2RX requirements | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.6.2.1 | FDD | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.6.2.1.1 | PDSCH absolute physical layer throughput requirements with link adaptation | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  | 100%
| Y | 38.521-4 | 5.6.2.1.1_1 | 2Rx FDD FR1 PDSCH performance with link adaptation - 2x2 MIMO for both SA and NSA | Test 1 in 5.6.2.1.1 in TS38.101-4. | Qualcomm | RAN5#109 (Nov-25) | R5-247801 R5-250551 R5-254878 |  | 1 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.6.2.2 | TDD | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.6.2.2.1 | PDSCH absolute physical layer throughput requirements with link adaptation | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  | 100%
| Y | 38.521-4 | 5.6.2.2.1_1 | 2Rx TDD FR1 PDSCH performance with link adaptation - 2x2 MIMO for both SA and NSA | Test 1 in 5.6.2.2.1 in TS38.101-4. | Qualcomm | RAN5#109 (Nov-25) | R5-247801 R5-250551 |  | 1 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.6.3 | 4RX requirements | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.6.3.1 | FDD | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.6.3.1.1 | PDSCH absolute physical layer throughput requirements with link adaptation | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  | 100%
| Y | 38.521-4 | 5.6.3.1.1_1 | 4Rx FDD FR1 PDSCH performance with link adaptation - 2x4 MIMO for both SA and NSA | Test 1 in 5.6.3.1.1 in TS38.101-4. | Qualcomm | RAN5#109 (Nov-25) | R5-247801 R5-250551 |  | 1 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.6.3.2 | TDD | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.6.3.2.1 | PDSCH absolute physical layer throughput requirements with link adaptation | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  | 100%
| Y | 38.521-4 | 5.6.3.2.1_1 | 4Rx TDD FR1 PDSCH performance with link adaptation - 2x4 MIMO for both SA and NSA | Test 1 in 5.6.3.2.1 in TS38.101-4. | Qualcomm | RAN5#109 (Nov-25) | R5-247801 R5-250551 |  | 1 | 100% | 100% |  | 100%
|  | 38.521-4 | 7.6 | PDSCH absolute physical layer throughput requirements | New Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-4 | 7.6.1 | 1RX requirements | New sub-Clause (Void) |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-4 | 7.6.2 | 2RX requirements | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-4 | 7.6.2.1 | FDD | New sub-Clause (Void) |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-4 | 7.6.2.2 | TDD | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  |  | 100%
|  | 38.521-4 | 7.6.2.2.1 | PDSCH absolute physical layer throughput requirements with link adaptation | New sub-Clause |  | RAN5#109 (Nov-25) |  |  | 0 | 100% | 100% |  |  | 100%
| Y | 38.521-4 | 7.6.2.2.1_1 | 2Rx TDD FR2 PDSCH performance with link adaptation - 2x2 MIMO for both SA and NSA | Test 1 in 7.6.2.2.1 in TS38.101-4. | Qualcomm | RAN5#109 (Nov-25) | R5-247801 R5-251734 |  | 1 | 100% | 100% |  |  | 100%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
|  | 38.522 | 4 | Recommended test case applicability | Add ICS and test case applicability statements for the new test cases introduced for 38.521-4. | All companies | RAN5#109 (Nov-25) | R5-247817 R5-250553 R5-250410 R5-251907 R5-256926 |  | 0.5 | 90% (+57.5%) | 90% (+57.5%) |  | 90% | 90%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.