## Slide 1
3GPP Work Plan
Review at Plenary #109
Source: MCC / Work Plan Manager (A. Sultan)
Agenda item: Review of the Work Plan
Document for: Information
Review based on the latest available version of the Work Plan, available at: https://ftp.3gpp.org/Information/WORK_PLAN
Includes: - the progress on all WIDs, as indicated in the WG Chairs’ reports (CT & SA) and in the Status Report (RAN), - the new WIDs proposed by SA/CT WGs to this TSG (will be removed if not TSG-approved)
Does not include: - the company-proposed WIDs proposed/approved at this TSG, the revised WID/SID during this TSG
Warnings :
- This review is a high-level view of the 3GPP progress. It is based on the 3GPP Work Plan, a continuously updated document.
Some misalignments might temporarily appear on some individual items.
- Some WG cannot progress because of reasons beyond their control (e.g. dependencies with other groups).
These slides shall not be used to judge the “efficiency” of whatever WG.
© 3GPP 2025
SP-251175 - 3GPP TSG#109, 15 -19 September 2025, Beijing, China
Green highlight: good news
Yellow highlight: to be clarified
Cyan highlight: other highlight

## Slide 2: Content of this Work Plan review
Snapshot of all ongoing/future Releases
Ongoing Releases
  Rel-19 Timeline and Progress
  Rel-20 Timeline and Progress
  Rel-21 Timeline and Progress
Background information

## Slide 3
Releases 19 to 21 timelines
#108
Release 19
Note: All starting dates are indicative
#110
#112
#114
#116
#118
#120
#122
#124
#126
2025
2026
2028
*: +3 months for RAN4
**: - 3 months for RAN1 & + 3 months for RAN4 perf
#111
#113
#115
#119
#121
#123
#125
2027
2029
5GA Stage 1
RAN Completion**
Stage 3 (CT & SA)
ASN.1
&
Open
APIs
Stage 2
#117
#109
2024
#104
#106
#107
#105
Mar.
#103
TSGs
Mar.
Mar.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Dec.
Dec.
Dec.
Now
SA1 St.1, Content Definition (RAN & SA St.2): completed Dec. 2023
Release 20 5GA
Release 20 FS_6G
5GA Stage 2
5GA RAN Completion**
5GA Stage 3
Chart showing Normative dates
(timeline for 5GA studies not shown)
Chart showing Studies dates
(no 6G normative work in Rel-20)
FS_6G Stage 1
FS_6G RAN P
FS_6G Stage 2
or
FS_6G RAN WG**
FS_6G Stage 3
TBD
Release 21 6G
Rel-21 timeline to be decided no later than June 2026
ITU deadlines for 6G: March 2029 for technology proposal, mid-2030 for specifications
ASN.1

## Slide 4: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 5
Release 19 timeline
#101
Note: All starting dates are indicative
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop

## Slide 6: Release 19 progress overview (1/3) - SA
SA1 (Stage 1): completed and stable (14 Studies, 25 Normative items)
SA2, SA6 (Stage 2): completed (24 Studies, 72 Normative items), except for 3 items:
  Stage 2 for :
    AI/ML (UID 1040033, AIML_CN) : now 99%, was 98%
    NG_RTC_Phase 2 (UID 1040026, NG_RTC_Ph2): remaining at 99%
    Ambient-IoT (UID 1070010, AmbientIoT-ARC): now 95%, was 90%
SA3/4/5:
    Reminder: these WGs also handle Stage 3 for certain topics
    Studies: 51 studies (same at previous TSG), OCI = 100 % (against 95 % at previous TSG)
    Normative: 73 items (against 74 at previous TSG), OCI = 95 % (against 67 % at previous TSG)
    Stage 3 freeze declared at September 2025, with 3 formal exceptions (2 from SA4, one for SA5)
    Normative Items not 100% complete:
Unique_ID | Name | Acronym | WG | %
1070022 | Security Aspects of Ambient IoT Services in 5G | AmbientIoT-SEC | S3 | 95%
1050113 | Terminal Audio quality performance and Test methods for Immersive Audio Services, Phase 2 | ATIAS_Ph2 | S4 | 75%
1040021 | EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 | IVAS_Codec_Ph2 | S4 | 80%
1030002 | Video Operating Points - Harmonization and Stereo MV-HEVC | VOPS | S4 | 95%
1070057 | Stage 3 for Advanced Media Delivery | AMD_PRO-MED | S4 | 85%
1010010 | 5G Security Assurance Specification (SCAS) for the Unified Data Repository (UDR) | SCAS_5G_UDR | S3 | 80%
1020035 | Mission critical security enhancements for release 19 | MCXSec4 | S3 | 99%
  Left for Rel-19 in SA: complete the exceptions/not 100% items.

## Slide 7: Release 19 progress overview (2/3) - CT
    Studies: 5 studies (same at previous TSG), OCI = 87 % (against 80% at previous TSG)
    Normative: 137 items (against 123 at previous TSG), OCI = 93% (against 78% at previous TSG)
    CT#109: CT Rel-19 Stage 3 freeze declared at CT#109, with some exceptions
    Normative Items less than 80% complete are:
Unique_ID | Name | Acronym | WG | %
1050045 | CT1 aspects of Application enablement for AI/ML services | AIML_App | C1 | 75%
1080030 | CT1 aspects of Ambient power-enabled Internet of Things | AmbientIoT-CT | C1 | 75%
1060038 | CT1 aspects of Application enablement for XRM Services Phase 2 | XRM_Ph2_App | C1 | 75%
1080022 | CT 1aspects of Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | C1 | 30%
1090035 | CT4 aspects of Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | C4 | 0%
1080038 | CT6 aspects of Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | C6 | 0%
1070038 | CT3 aspects of Application enablement aspects for MMTel | MMTel_App | C3 | 75%
1090034 | CT1 aspects of IMS Disaster Prevention and Restoration Enhancement | IMS_RES-CT | C1 | 0%
1080035 | CT3 aspects of IMS Disaster Prevention and Restoration Enhancement | IMS_RES-CT | C3 | 70%
1080036 | CT4 aspects of IMS Disaster Prevention and Restoration Enhancement | IMS_RES-CT | C4 | 70%
1090032 | CT aspects of Lower Selection-priority for PLMN Selection | LoSePLMN-CT | C1 | 5%
1080003 | Harmonization of test case definitions for cross-RAT usability | TestHarmon_CrossRAT | C6 | 0%
  Left for Rel-19 in CT: complete the exceptions/not 100% items; complete code freeze (by Dec. 2025).

## Slide 8: Release 19 progress overview (3/3) - RAN
  Studies: 12 studies (against 11 at previous TSG), OCI = 100 % (against 96% at previous TSG)
  RAN Core: 55 items (same at previous TSG), OCI = 95 % (against 84% at previous TSG) .
  RAN#109: RAN Rel-19 Stage 3 freeze declared at RAN#109, with some exceptions. Not 100%:
  RAN4Perf: 36 items (same at previous TSG), OCI = 55 % (against 45% at previous TSG). Completion date is Dec.2025
UID | Name | Acronym | WG | %
1021093 | Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air-Core | R1 | 90%
1041135 | Introduction of Ku bands for NR NTN | NR_NTN_Ku_bands-Core | R4 | 95%
1041134 | Introduction of NR NTN bands to support the Extended L-band and the combined MSS L-band and Extended L-band ranges | NR_NTN_combinedLband-Core | R4 | 90%
1041121 | Additional NR bands for NR features in Rel-19 | NR_bands_xFeature_R19-Core | R4 | 85%
1041120 | Rel-19 NR CADC for x bands DL with y bands UL (x<7, y<3) and SUL band combinations/CA band […] | NR_CADC_SUL_R19-Core | R4 | 88%
1031078 | NR base station (BS) RF requirement evolution for FR1/FR2 and testing | NR_BS_RF_req_evo-Core | R4 | 85%
1041123 | Rel-19 High power UE (power class 1.5 or 2) for NR intra-band Carrier Aggregation (CA) or NR inter-band CA/Dual […] | HPUE_NR_CADC_SUL_R19-Core | R4 | 85%
1041124 | Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA Ues, and […] | HPUE_NR_FR1_bands_R19-Core | R4 | 88%
1041122 | Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) | HPUE_DC_LTE_NR_R19-Core | R4 | 80%
1041125 | Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-19 | LTE_NR_R19_Simult_RxTx-Core | R4 | 80%
1041119 | Rel-19 Dual connectivity (DC) of x LTE band(s), y NR band(s) (1<=x<6, 1<=y<6, x+y<=6) and single or two NR […] | DC_R19_xBLTE_yBNR-Core | R4 | 80%
1041116 | Rel-19 High power UE (power class 2) and high power operation (power class 1) for fixed-wireless/vehicle-mounted […] | HPUE_LTE_bands_R19-Core | R4 | 10%
1041115 | Rel-19 LTE-Advanced Carrier Aggregation for x bands (1<=x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R19_xBDL_yBUL-Core | R4 | 85%
1051122 | Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE | LCS_NAVIC_L1_SPS_NR_LTE-Core | R2 | 99%
  Left for Rel-19 in RAN: complete the exceptions/not 100% items; Complete Performance part (by Dec. 25).

## Slide 9: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 10: Release 20: introduction
Rel-20 has 2 components: “Rel-20_5GA” and “Rel-20_6G” (or “Rel-20_FS_6G”)
  Rel-20_5GA covers 5GA studies and normative;
  Rel-20_6G covers 6G studies only (6G normative in Rel-21)
  Up to each TSG/WG how to split their time on each component (e.g. in SA1, it was initially at 50%-50%)

## Slide 11
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
SA1 5GA WID definition
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
#113
Sep.
#114
Dec.
#115
Mar.
Jun
RAN1
RAN Completion (RAN2/3/4core)
#116
RAN4 C.def.
RAN4 Perf
RP Content def.
2025
2026
2027
5GA ASN.1 & Open APIs
Release 20 5GA timeline
Note: All starting dates are indicative
Workshops
5GA RAN & SA
RAN WG SID def.
St.2 WID def.
St.3 WID def.

## Slide 12: Release 20 5GA progress overview (1/2)
Stage 1:
  Frozen in June 2025
    including now the FRMCS_Ph6-REQ (for which there was an exception in June)
Stage 2 in SA2 and SA6:
  SID approval getting stable
  Studies: 21 studies, OCI = 36 % (not significant at previous TSG)
  Normative: 8 items so far, OCI = 18 % (not significant at previous TSG)
RAN:
  RAN WG SIDs/WIDs approved at RAN#108
    Studies: 4 studies, OCI = 10 % (not significant at previous TSG)
    Normative: 19 items so far, work just starting
  RAN4 WIDs approval has been finalized at RAN#109 (9 WIDs)

## Slide 13: Release 20 5GA progress overview (2/2)
Rel-20 5GA SA3/4/5 activities:
  Studies: 15 studies, OCI = 14 % (not significant at previous TSG)
  Normative: 9 items so far, OCI = 18 % (not significant at previous TSG)
Rel-20 5GA Stage 3 in CT (from CP-252253/2252):
  not started, to be started in Q1 2026
  Rel-20 timeline to be used about 50%-50% between 5GA topics and FS_6G topics

## Slide 14
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
Workshop 6G TSGs
CT & St. 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
Workshop SA1 on IMT-2030 use cases
#116
SA1 6G Study(ies)
SA1 6G SID def.
RP IMT-2030 disc.
RP ITU Study
RP 6G Study(ies)
RAN1 6G Study(ies)
SA2 6G Study(ies)
Stage 3 6G Study(ies)
2025
2026
2027
SA2 & RAN WGs 6G SID def.
SA3/4/5/6 6G SID def. TBD
RAN2/3/4 6G Study(ies)
Release 20 (FS) 6G timeline
or
TBD
Note: All starting dates are indicative
SA3/4/5/6 6G Study(ies)TBD
Several Dates yet to be clarified/defined for several groups
TBD
TBD
TBD
TBD

## Slide 15: Release 20 FS_6G progress overview (1/2)
Reminder: no normative work on 6G in Rel-20 (only studies)
Several groups have now started working on 6G:
Most advanced ones are:
  SA1’s TR 22.870 on FS_6G_REQ, now at 77%, targeted for March 2026
  RAN Plenary’s TR 38.914 on Study on 6G Radio, now 10% complete, targeted for June 2026
Cross-TSG topics already identified on:
  6G Requirements (RAN and SA1)
  6G Migration (RAN and SA2)
  6G Security (RAN2 and SA3)
Unique_ID | Name | Acronym | WG | %
0 | Rel-20 6G Studies | - |  | 
1050110 | Study on 6G Use Cases and Service Requirements | FS_6G_REQ | S1 | 77%
1080057 | Study on Architecture for 6G System | FS_6G_ARC | S2 | 5%
1060079 | Study on 6G Scenarios and Requirements | FS_6G_RAN_Scen_Req | RP | 10%
1080064 | Study on Modernization of Specification Format and Procedures for 6G | FS_6GSpecs | SP | 0%
1080072 | Study on 6G Radio | FS_6G_Radio | R1 | 2%
1090013 | Study on Charging Aspects of 6G System | FS_6G_CH | S5 | 0%

## Slide 16: Release 20 FS_6G progress overview (2/2)
Rel-20 FS_6G Stage 2 (SA2/SA6) activities:
  SA2: SIDs approved at TSG#108, Technical work started, target completion date to be clarified (Dec 25 or Mar 26?)
  SA6: SID targeted to be presented to TSG#110, target completion date to be set
Rel-20 FS_6G SA3/4/5 activities:
  SIDs being submitted/approved at TSG#109
  Technical work not started
  Timeline for SIDs approval and for target completion date to be set
Rel-20 FS_6G Stage 3 in CT (from CP-252253/2252):
  not started, to be started in Q4 2025
  Rel-20 timeline to be used about 50%-50% between 5GA topics and FS_6G topics

## Slide 17: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 18: Release 21
Release 21 is the release for submission to IMT-2030*, aka 6G
This implies that 3GPP (normative) work will be submitted to ITU-R before 2030
  ASN.1/OpenAPI freeze date is no earlier than March 2029
Release 21 Freezing dates and other milestones TBD:
  Previous decision: “Rel-21 timeline is to be decided no later than June 2026”
  But some groups (SA1, RAN Plenary) would have already finished their Rel-20 work by that time
Note that, as usual in 3GPP, previous Generations will in parallel continue to be maintained & enhanced in Rel-21 and after
* source: TSG#103-endorsed CT-240307/SP-240458/RP-240823

## Slide 19
Discussion on Rel-21 timeline
TSG#117
TSG#118
TSG#123
TSG#109
TSG#110
TSG#111
TSG#112
TSG#113
TSG#114
TSG#115
TSG#116
2025
2026
Dec
Mar.
Mar.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
2027
Release 21
(incl. 6G Norm.)
Now
Rel-21 Stage 1
TBD
Mar
FS_6G RAN WG
FS_6G RAN Plenary
FS_6G Stage 1
FS_6G Stage 2
or
FS_6G Stage 3
Reminder:
Release 20
FS_6G
TBD
2028
TSG#121
TSG#122
TSG#120
Dec
Mar.
Jun.
Sep.
2029
TSG#119
?
Note: All starting dates are indicative
Other Stages?
SA1 WID def.

## Slide 20: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 21: Background information (1/2): overall background information
Dedicated e-mail list for Work Plan aspects
Open to everyone interested (rapporteus, chairs, delegates, etc.) by sending the message “Subscribe 3GPP_WORKPLAN” to the address LISTSERV@LIST.ETSI.ORG
For comments/update to the Work Plan, please use the 3GPP_WORKPLAN list
Editorial comments can be sent directly to: alain.sultan@etsi.org
3GPP Work Plan
http://www.3gpp.org/ftp/Information/WORK_PLAN
Contains Release 1999 to Release 20; Master version in MS Project; Working versions in Excel
Tutorials on content, maintenance and other info on the Work Plan in subfolder /info
3GPP Releases Descriptions – R99 to Rel-18
http://www.3gpp.org/ftp/Information/WORK_PLAN/Description_Releases/
“Releases Descriptions” for Releases 8 to 13: limited to copy-paste of the WIDs.
“Releases Descriptions” for Releases 14 to 18: TR 21.9xx: “Release xx Description; Summary of Rel-xx Work Items”, written in collaboration with all the Rel-xx Features Rapporteurs
3GPP Releases Descriptions – Rel-19
To be started December 2025 (time for work to stabilise).
CALL FOR CONTRIBUTIONS TO COME FROM WORK PLAN MANAGER TO RAPPORTEURS

## Slide 22: Background information (2/2): Relationship between WGs, Stages and deadlines
Most 3GPP Working Groups handle only one Stage:
  SA1  Stage 1
  SA2  Stage 2; SA6  Stage 2
  CT WGs  Stage 3 (also Stage 2 for some specific items)
SA3, SA4 and SA5 handle several Stages for some or all their WIDs:
  SA3: handles Stages 2 and 3 for all its WIDs. Stage 2 at SA3 is one quarter after SA2/SA6’s deadline, but this date is an SA3-internal date since there is no dependency (i.e. SA3 is not expecting work from any other WGs)
  SA4: handles Stage 2 for some WIDs (for which SA4 might rely on CT WGs for Stage 3), and Stage 3 for a majority of its WIDs. Stage 2 WIDs in SA4 are clearly identified as such and have the same deadline as SA2/SA6’s date.
  SA5: handles Stages 1, 2 and 3 for all its WIDs. Stage 1 for SA5 is 4 quarters after SA1’s date. Stage 2 for SA5 is 2 quarters after SA2/SA6’s date. Stage 3 for SA5 is same date as CT WGs’ date.
  For SA3, SA4 and SA5, the completion date for all WIDs dealing with Stage 3 (fully or partially) is the same as for CT WGs.
  In this Work Plan review slides, SA3, SA4 and SA5 are reported in the “Stage 3” slides since their overall completion date is aligned with (CT’s) Stage 3. Except for SA4’s Stage 2-only WIDs but this cannot be handled by the present tools.
RAN has a slightly different process. RAN defines two dates:
  The “RAN Content Definition”, which is the same date as SA Stage 1 and SA content definition
  The “RAN Completion”, which is the same date as SA/CT’s Stage 3
  Note that there is no specific RAN-equivalent date for SA/CT’s Stage 2