## Slide 1: R19 FS_EnergySys : Status of conclusion discussion

## Slide 2: FS_EnergySys (AI #19.4)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 15% | SP-231192 | 55% | Study in progress
  Work Status
  TR 23.700-66 v.0.4.0 has total 32 solutions for three key issues (11 solutions for KI#1, 13 solutions for KI#2, 8 solutions for KI#3, roughly)
  Three key issues have multiple key technical aspects to resolve
  (4 key aspects for KI#1, 5 for KI#2, and 4 for KI#3)
  1 TU is remaining for Study Phase
Drafting session for merging conclusion proposals
  Agreed to focus on deriving solution principles rather than evaluating for solution selection, in April meeting
  Identified baseline documents to merge proposals and continue further discussions
  Agreed that issues that cannot be concluded in the meeting or need further discussion will be listed as topics for email or NWM discussion before May meeting

## Slide 3: FS_EnergySys
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 15% | SP-231192 | 55% | Study in progress
  Main Session
  Reviewed 9 new solutions (unhandled in the previous meetings)
  Reviewed revised conclusion proposals for three key issues
  Some high level principles as interim conclusion are being sought for as output of the meeting
  - KI#1: granularity of energy information, information source of energy information, etc.
  - KI#2: energy related information in UE subscription data, use of energy info for AM/SM policy decision, etc.
  - KI#3: NF selection, access/session management, and slice admission control, based on energy information
  NWDAF analytics for network energy saving and efficiency
  Next Steps
  Continue discussion on the identified issues and/or detailed aspects to derive conclusions
  Plan a pre-call before May meeting

## Slide 4: FS_EnergySys Work Plan
Total 13 TUs
  6.5 TUs for Study Phase
  6.5 TUs for Normative Work
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 1 | 1 | TR skeleton, scope, architectural assumptions, key issue discussion
SA2#160 | Nov 2023 | 1 | 1 | Continue discussion on Key Issues, start solution discussion
SA2#160AH-e | Jan 2024 | 1 | 1 | Start solution discussion, last meeting for Key Issue proposals
SA2#161 | Feb 2024 | 1.5 | 1.5 | Continue solution discussion, last meeting for new solution proposals
SA2#162 | Apr 2024 | 1 |  | Focus on solution updates, only unhandled new solution proposals from #161(if not covered by the existing solutions), start discussion on evaluation and conclusion
SA2#163 | May 2024 | 1 |  | Critical solution updates only, Complete evaluations and conclusions
 | Total | 6.5 |  |