## Tdoc cover sheet
3GPP TSG-CT WG4 Meeting #131 Sophia Antipolis, France, 13-17 October 2025 |  | C3-254033 C4-254028
Source: | vivo
Title: | Work plan for the CT aspects of AIML_CN
Agenda item: | 19.39
Document for: | Discussion

## CT3
NOTE: Text in red color means to be resolved
Contribution Plan
Meeting | Topic | Related stage 2 agreed CR # other WG tdoc(s) # | SA2 TDoc source | Impacted stage-3 TS | Volunteered company | Addressed? | Comments
KI#1 Direct AI/ML based Positioning
| Editor’s Note: The necessity and terminology of the lmfEventInd attribute are FFS. |  |  | 29.574
SA2#170 | Clarification on data collection for LMF-based AI/ML positioning | S2-2507651 | CATT, Nokia, vivo, Huawei, HiSilicon | N/A
SA2#170 | Resolution of Editors Note on user consent and LCS privacy | S2-2507585 | Ericsson, AT&T, Lenovo, Nokia, ZTE, Interdigital | N/A
SA2#170 | General maintenance of KI#1 | S2-2507490 | ZTE | N/A
SA2#170 | Removal of requirements related to case 2b | S2-2507488 | vivo | N/A |  | positioning case is not implemented in CT3 yet.
SA2#169 | LMF re-selection based on AI capability | S2-2505951 |  | N/A
SA2#169 | Typo correction in clause 6.2E.4 in TS 23.288 | S2-2505449 |  | N/A
SA2#168 | ML Model provisioning by OAM for LMF-based AI/ML Positioning | S2-2504198 | NTT DOCOMO, Ericsson, Nokia, Huawei, HiSilicon | N/A
SA2#168 | Removal of requirements related to case 2b | S2-2504200 | vivo, Xiaomi, ZTE, OPPO, Mediatek Inc., Samsung, Nokia, CATT, Ericsson, Qualcomm Incorporated, Huawei, HiSilicon, ERTI | TS 29.520 |  | positioning case is not implemented in CT3 yet.
SA2#168 | Resolve ENs on input data for LMF based AI/ML positioning | S2-2504201 | CATT, Ericsson, vivo, Huawei, HiSilicon | N/A
SA2#167 | Modifications on ML Model retrieval service | S2-2502225 | ZTE | n/a |  |  | CT3 has already supported
SA2#167 | Adding new LMF Selection Factor | S2-2502480 | China Mobile, ZTE, ETRI, Interdigital | n/a
SA2#167 | Clarification on LMF requesting ML model for LMF-based AI/ML Positioning from the NWDAF containing MTLF | S2-2502483 | CATT, ZTE, Intel, Huawei | n/a |  |  | LMF may retrieve the ML Model from ADRF has already supported in C3-250477
SA2#167 | User consent check during performance monitoring | S2-2502484 | Samsung | n/a
SA2#167 | Procedures to collect data from the UE and from NG-RAN, resolution of Editor s Note. | S2-2502485 | Ericsson, AT&T | n/a
SA2#167 | KI#1 - Further clarification on ML Model performance monitoring for AI/ML positioning | S2-2502486 | Lenovo, CATT | n/a
SA2#167 | Update UDM to support user consent of data collection for performance monitoring | S2-2502487 | Xiaomi | n/a
SA2#167 | Updates to AI/ML-based positioning general descriptions | S2-2502495 | Apple, CATT, Intel | n/a
SA2#167 | Clarification on data collection by LMF from NG-RAN for LMF-based AIML Positioning | S2-2502496 | CATT | n/a
SA2#167 | Clarification on LMF as service consumer for ML Model Training | S2-2502516 | China Mobile | n/a
SA2#167 | Clarification on model performance monitoring for LMF-based AIML Positioning | S2-2502528 | CATT, vivo, Intel, Huawei, HiSilicon, ZTE, China Telecom | n/a
SA2#167 | Updates to AI/ML-based positioning procedures | S2-2502784 | Apple, vivo, Interdigital | n/a
SA2#166 | Update to model provisioning for LMF-based AIML positioning | S2-2412441 | CATT | n/a
SA2#166 | KI#1: Using New LMF DataCollection service to collect input data for model training | S2-2412457 | Nokia | n/a
SA2#166 | Addressing the EN about model provision for AI positioning | S2-2412728 | Vivo, Qualcomm Incorporated, ChinaTelecom, OPPO, Xiaomi, Nokia, Ericsson | TS 29.520 | Ericsson | The indication of LMF-based AI/ML Positioning is not defined yet | - Related to indication of supporting model for LMF-based AI/ML Positioning, which will be decided by CT3 - positioning case information is related to EN, which is not suggested to be discussed in next meeting
SA2#166 | NWDAF collects data from LCS to train ML model for AI positioning | S2-2412930 | Vivo, Nokia | n/a
SA2#166 | Update on Data Collection by LMF procedure | S2-2412931 | Lenovo, Qualcomm, Huawei, vivo, Nokia, Xiaomi | n/a
SA2#166 | KI#1 - Addressing Editor s Note: Procedure for Data Collection for AI/ML based positioning from NG-RAN | S2-2412932 | Ericsson, Xiaomi, Nokia, Interdigital, Apple, Lenovo, CATT | 29.520 |  | positioning case,ML Model Filter Information and/or Target of ML Model Reporting,Indication of whether the ML Model identifier is updated is missing in CT3 definition | -The LMF requests the NWDAF containing MTLF to provide an ML Model for LMF-based AI/ML Positioning as described in clause 6.2A of TS 23.288 [37] with the following considerations: Optionally, Vendor ID, ML Model Filter Information (e.g. Area of Interest), Positioning case information, Target of ML Model Reporting, ML Model Target Period, Time when model is needed, Inference Input Data information and ML Model Monitoring Information. '-ML Model Filter Information and/or Target of ML Model Reporting, if the ML Model provisioning request includes multiple ML Model Filter Information and/or Target of ML Model Reporting; '-iIndication of whether the ML Model identifier is updated (e.g. retrained ML model)if model is retrained and optionally .
SA2#166 | Support AI/ML model performance monitoring by NWDAF | S2-2412941 | Xiaomi, Nokia, Ericsson, Lenovo | N/A
SA2#166AH | Modifications on ML Model retrieval service | S2-2500083 | ZTE | 29.575 |  | C3-250477
SA2#166AH | Updates to AI/ML-based positioning general descriptions | S2-2501136 | Apple | TS 29.520 | Ericsson | See S2-2412932 | -TS 29.520: If the LMF supports multiple AI/ML Models, indication of the supporting for multiple AI/ML Models, optionally with the maximum Number of ML Models and Accuracy level(s) of Interest. - TS 29.520: supported indication of whether the ML Model identifier is updated (e.g. retrained ML model)
SA2#166AH | Clarification on LMF requesting ML model for LMF-based AI/ML Positioning from the NWDAF containing MTLF | S2-2501137 | CATT | TS 29.520 TS 29.575 |  | see S2-2500083 and S2-2501136 | - Related parameters are defined in S2-2501136 - If the LMF receives ADRF (Set) ID in the ML Model Information, is mentioned in S2-2500083
SA2#166AH | Clarification on data collection by LMF for LMF-based AIML Positioning | S2-2501138 | CATT | n/a
SA2#166AH | Updates to AI/ML-based positioning procedures | S2-2501139 | Apple | n/a
SA2#166AH | NWDAF model provision for AI positioning | S2-2501140 | Vivo | TS 29.552? | Ericsson (29.552) | The indication of LMF-based AI/ML Positioning is not defined yet | - Related to indication of supporting model for LMF-based AI/ML Positioning, which will be decided by CT3 - When selecting an NWDAF for ML model provisioning, the following additional factors may be considered by the NWDAF: LMF-based AI/ML positioning indication (indicating that the NWDAF containing MTLF supports ML model training for LMF-based AI/ML positioning).
SA2#166AH | NWDAF registration and discovery for AI positioning | S2-2501141 | Vivo | TS 29.552? | Ericsson (29.552) | The indication of LMF-based AI/ML Positioning is not defined yet | - Related to indication of supporting model for LMF-based AI/ML Positioning, which will be decided by CT3 - When selecting an NWDAF for ML model provisioning, the following additional factors may be considered by the NWDAF: LMF-based AI/ML positioning indication (indicating that the NWDAF containing MTLF supports ML model training for LMF-based AI/ML positioning).
SA2#166AH | Procedures to collect data from the UE and from NG-RAN, resolution of Editor s Note. | S2-2501348 | Ericsson | N/A |  |  | - Whether to introduce a new UcPurpose should based on EN of SA2, propose to wait
SA2#165 | LMF enhancements for LMF-based AI/ML Positioning | S2-2410978 | Huawei, HiSilicon, NTT DOCOMO, Nokia | n/a
SA2#165 | ML Model based UE positioning support | S2-2410980 | NTT DOCOMO, Ericsson | n/a
SA2#165 | Support AI/ML model performance monitoring by LMF | S2-2410981 | Xiaomi, Nokia, Ericsson | n/a
SA2#165 | Support AI/ML model performance monitoring by NWDAF | S2-2410995 | Xiaomi, Nokia, Ericsson | potential impact on TS 29.552 | Ericsson, Nokia | C3-246465 (29.575) C3-246532 (29.574) C3-246583 (29.552) C2-252265 (29.575) | - May have some gengeral description in 29.552, e.g. new reference in clause 5.12
SA2#165 | Addressing the EN about model provision for AI positioning | S2-2410997 | vivo | TS 29.520 Potential impacts on TS 29.552 | Ericsson, Nokia, ZTE | The indication of LMF-based AI/ML Positioning is not defined yet | - TS 29.552: Enhancement of Nnwdaf_MLModelProvision_Subscribe to support indication that a model for LMF-based AI/ML Positioning is requested. Backward compatible issue (if any) can be discussed in CT3. - TS 29.520: Impact on Nnwdaf_MLModelProvision_Subscribe to support indication that a model for LMF-based AI/ML Positioning is requested. Backward compatible issue (if any) can be discussed in CT3 as 29.552
SA2#165 | KI#1 - Addressing Editor´s Note: Procedure for Data Collection for AI/ML based positioning from NG-RAN | S2-2411257 | Ericsson, Xiaomi, Nokia | n/a
SA2#165 | Update on Data Collection by LMF procedure | S2-2411256 | Lenovo, Qualcomm, Huawei | n/a
SA2#164 | Support for LMF to retrieve ML Model of AI/ML based positioning | S2-2409413 | Vivo, Nokia, Lenovo, ZTE, Huawei, OPPO, MediaTek Inc., Ericsson, CATT | TS 29.520 TS 29.552 | vivo, Ericsson, Nokia, Huawei | C3-245477 C3-245478 | 29.520: Enhancement on Nnwdaf_MLModelProvision and Nnwdaf_MLModelInfo to include LMF as a new consumer 29.552: Enhancement on Nnwdaf_MLModelProvision and Nnwdaf_MLModelInfo to include LMF as a new consumer (e.g. clause 5.6.1)
SA2#164 | Introduction of LMF enhancement for Direct AI/ML based Positioning | S2-2409414 | Qualcomm Incorporated, Ericsson, Nokia, ZTE, Xiaomi, vivo, OPPO, interdigital, Lenovo | potential impact | Ericsson | C3-245477 C3-245478 | -Performance monitoring procedures for NWDAF containing MTLF is FFS
SA2#164 | KI#1 - LMF enhancements for UE positioning using a ML model | S2-2409415 | Ericsson, Xiaomi, Lenovo, Vivo, NTT DOCOMO | potential impact | Ericsson | C3-245477 C3-245478
KI#2 Vertical Federated Learning (VFL)
| Editor's Note: The final list of the attributes and their presence conditions are FFS. |  |  | TS 29.520
| Editor's Note:The attributes shall be present in the response and the attributes that can be modified by the NWDAF are FFS. |  |  | TS 29.520
| Editor's Note: The full content of this data type is FFS. |  |  | TS 29.520
| Editor's note: The list of VFL inference related attributes allowed to be changed with a PATCH is FFS. |  |  | TS 29.520
| Editor's Note: Only a general description for VFL procedures will be captured in this clause. The detailed procedures will be captured in the corresponding clauses. |  |  | TS 29.552
| Editor's Note: The training procedures are FFS as the corresponding API(s) are not defined by stage-3 yet. |  |  | TS 29.552
SA2#168 | Editor s Note clean up for the VFL | S2-2504202 | OPPO, Nokia | N/A
SA2#168 | Optimization of VFL triggers | S2-2504221 | ZTE, Huawei, Hisilicon, vivo, OPPO, Nokia, Futurewei, Samsung, China Mobile, Interdigital | 29.552 29.520 |  | VFL procedures are not defined yet | - update of Training Procedure (The VFL training proceudre is not defined in CT3 yet)
SA2#168 | Update triggering Case A and some corrections and Resolving ENs for VFL | S2-2504220 | Ericsson, China Telecom, ZTE | 29.552 29.520 |  | VFL procedures are not defined yet | -update of Training Procedure (The VFL training proceudre is not defined in CT3 yet) - update of Inference Procedure (The VFL inference proceudre is not defined in CT3 yet) - 29.520: Update on Nnwdaf_MLModelProvision to support 'Indication that no ML model identifier will be made available, Indication that training is ongoing or NF ID of a VFL server' -Update of Nnwdaf_VFLTraining service, Naf_VFLTraining Service, Naf_Training Service,Nnef_Training service, Nnef_VFLTraining Service (all not defined yet)
SA2#168 | Alignment of existing mechanisms for accuracy generation impacted by VFL procedures | S2-2503972 | Huawei, HiSilicon, ZTE | N/A |  | VFL procedures are not defined yet | -VFL ML Accuracy information is the same as existing parameter Analytics Accuracy Information. Hence it should be no impact on data type. Potential clairification may be needed
SA2#168 | Parameters for vertical federated learning inference procedure | S2-2504216 | Nokia, Vivo, Huawei, Oppo, Samsung | 29.552 29.520 |  | VFL procedures are not defined yet | - update of Inference Procedure (The VFL inference proceudre is not defined in CT3 yet) - update of Nnwdaf_VFLInference, Naf_VFLInference Service, Nnef_VFLInference (all not defined yet)
SA2#168 | Updates on VFL inference | S2-2504476 | Interdigital, Samsung | 29.552 29.520 |  | VFL procedures are not defined yet | - update of Inference Procedure (The VFL inference proceudre is not defined in CT3 yet)
SA2#168 | Maintenance of VFL model training and inference with client intermediate results sharing between VFL clients | S2-2504218 | Samsung, ZTE, Nokia, OPPO, LG Electronics, Ericsson | 29.552 29.520 |  | VFL procedures are not defined yet | - Update of preparation, training and inference procedures. (not defined yet)
SA2#167 | Addressing EN in VFL training | S2-2501546 | Tejas Networks | 29.552 |  | VFL procedures are not defined yet | - should be considered when implementing Training Procedure
SA2#167 | Clarifications on intermediate training result and intermediate model training information | S2-2502261 | ZTE | 29.552 |  | VFL procedures are not defined yet | - should be considered when implementing Training Procedure
SA2#167 | Sample update during VFL training | S2-2502262 | Apple, Ericsson, Samsung, ETRI, Futurewei, ZTE | 29.552 |  | VFL procedures are not defined yet | - should be considered when implementing Training Procedure
SA2#167 | KI#2 update to VFL preparation procedure | S2-2502488 | InterDigital, Nokia, Ericsson, Futurewei, LGE, Huawei, HiSilicon, ZTE, OPPO, Samsung, Lenovo | 29.552 |  | VFL procedures are not defined yet | - should be considered when implementing Preparation procedure
SA2#167 | Adding VFL related services supported by NEF and AF | S2-2502492 | Vivo, Nokia, KDDI | n/a |  |  | CT4 has already supported
SA2#167 | Resolving ENs for VFL | S2-2502527 | Ericsson, Lenovo, InterDigital, OPPO, Nokia, ZTE, KDDI, Samsung, Vivo, CMCC, China Telecom, Huawei, HiSilicon | 29.552 |  | VFL procedures are not defined yet | - should be considered when implementing Training Procedure
SA2#167 | Resolve some ENs in the vertical federated learning inference procedure | S2-2502668 | OPPO, ZTE, Nokia, Ericsson, Samsung, China Telecom, vivo, Huawei, Hisilicon | 29.552 |  | VFL procedures are not defined yet | - should be considered when implementing inference Procedure
SA2#167 | KI#2: VFL services | S2-2502669 | Nokia, Ericsson, LG Electronics, OPPO | 29.520 29.591 29.530 (new spec) 29.522 |  | C3-252544 (29.520) C3-252545 (29.520) C3-252546 (29.520) C3-252547 (29.520) C3-252548 (29.520) C3-252549 (29.520) C3-252612 (29.522) C3-252613 (29.522) | "- TS 29.520: support of Nnwdaf_VFLTraining Service, Nnwdaf_VFLInference Service - TS 29.530: support of Naf_VFLTraining, Naf_VFLInference - TS 29.591/TS29.522: support of Nnef_VFLTraining Service, Nnef_VFLInference Service, Nnef_VFLNFDiscovery Service
SA2#167 | Enhancements for the accuracy monitoring of VFL training | S2-2502679 | vivo | 29.552 |  | VFL procedures are not defined yet | - should be considered when implementing Training Procedure
SA2#167 | KI#2 update to VFL inference procedure | S2-2502680 | InterDigital, Samsung, Nokia, LG Electronics | 29.552 |  | VFL procedures are not defined yet | - should be considered when implementing inference Procedure
SA2#167 | Support of VFL model training and inference with client intermediate results sharing between VFL clients | S2-2502681 | Samsung, Lenovo, OPPO, ZTE, Apple, Nokia, InterDigital | 29.552 |  | VFL procedures are not defined yet | - should be considered when implementing inference Procedure - should be considered when implementing Training Procedure
SA2#167 | EN removal for clarification of VFL high level description | S2-2502682 | KDDI, LG Electronics, Huawei, ETRI, Samsung, China mobile, ZTE | n/a
SA2#166 | High level description refinement of NWDAF initiated VFL training | S2-2412455 | ZTE | n/a
SA2#166 | High-level description for Vertical Federated Learning when AF is as Server. | S2-2412734 | KDDI, Ericsson, ZTE, ICS, CMCC, ETRI, Huawei, Samsung, Apple, OPPO | n/a |  |  | potential update to general 5.10.3.1
SA2#166 | KI#2 Update of VFL training and inference | S2-2412885 | Ericsson, ETRI, InterDigital, ICS, OPPO, Lenovo, Vivo, Nokia, Apple, Samsung, Futurewei, ZTE, Huawei | TS 29.552 | Ericsson | VFL procedures are not defined yet | TS 29.552: Preparation phase. The latest base of preparation phase should be referred to S2-2501347
SA2#166 | Enhancement to NRF s discovery and registration procedures to support VFL | S2-2412929 | ICS, InterDigital, Futurewei, Nokia, Ericsson, Lenovo, LG Electronics | n/a
SA2#166 | Update the general inference procedure for vertical federated learning to resolve ENs | S2-2412933 | OPPO, ZTE, Samsung, Nokia, Lenovo, Toyota, ICS, Huawei, HiSilicon, Ericsson, InterDigital, Tencent, ETRI, Vivo, Apple. | TS 29.552 | vivo (if time permits) | VFL procedures are not defined yet | TS 29.552: Inference procedure. The latest base of Inference procedure should be referred to S2-2501345
SA2#166 | Refinements for VFL feature | S2-2412934 | Vivo, ICS, LG Electronics, InterDigital, ZTE, OPPO, Nokia, Samsung, Ericsson, Huawei, Lenovo, KDDI, ETRI | TS 29.552 | vivo | VFL procedures are not defined yet | TS 29.552: Discovery and Registration procedure. The latest base of the procedure should be referred to S2-2501347
SA2#166 | General training procedure for Vertical Federated Learning between NWDAF(s) and AF(s) | S2-2413023 | China Mobile, CATT, ZTE, OPPO, China Telecom, ETRI, Huawei, HiSilicon, Nokia, Futurewei, Samsung, Ericsson, InterDigital, Apple, Lenovo, Vivo | TS 29.552 | China Mobile | VFL procedures are not defined yet | TS 29.552: Training procedure. The latest base of the procedure should be referred to S2-2501346
SA2#166AH | Adding missing parts for VFL | S2-2500195 | Vivo(rapporteur), MediaTek Inc(rapporteur) | n/a
SA2#166AH | Resolving ENs for VFL | S2-2501134 | Ericsson, Lenovo, InterDigital, [OPPO] | n/a |  |  | Just endorsed in SA2, not stable. Propose to wait.
SA2#166AH | KI#2: VFL services | S2-2501135 | Nokia, Ericsson | TS 29.520 TS 29.517 TS 29.591 TS 29.522 |  | see S2-2502669 | - TS 29.520: support of Nnwdaf_VFLTraining Service, Nnwdaf_VFLInference Service - TS 29.517: support of Naf_VFLTraining, Naf_VFLInference - TS 29.591/TS29.522: support of Nnef_VFLTraining Service, Nnef_VFLInference Service, Nnef_VFLNFDiscovery Service - The parameters may be changed and new service may be addeded in next meeting, but at least these APIs will be needed. Hence CT WG can progress on new services.
SA2#166AH | The related definitions for VFL and HFL | S2-2501142 | China Mobile, ZTE, Nokia | N/A
SA2#166AH | KI#2 update to registration and discovery procedure | S2-2501143 | InterDigital, Nokia, KDDI, OPPO, LGE, Ericsson, Samsung | TS 29.552? |  | VFL procedures are not defined yet | Registration and Discovery procedure for Vertical Federated Learning.
SA2#166AH | Clarifications on VFL general procedure | S2-2501144 | China Mobile | N/A
SA2#166AH | KI2: Addressing ENs for VFL . | S2-2501145 | Lenovo | N/A
SA2#166AH | NWDAF discovery and selection parameters | S2-2501146 | LG Electronics | n/a
SA2#166AH | KI#1 and KI#2 alignment | S2-2501147 | ZTE | n/a
SA2#166AH | Adding VFL related services supported by NEF and AF | S2-2501148 | Vivo | n/a |  |  | Requirements have already covered by other CRs
SA2#166AH | Resolve some ENs in the vertical federated learning inference procedure | S2-2501345 | OPPO, Nokia, Ericsson, Samsung | TS 29.552 | vivo (if time permits) | VFL procedures are not defined yet | TS 29.552: Inference procedure for vertical federated learning. Procedure is almost stable. A new clause is needed, but how to draft the 29.552 CR for the new clause can be further discussed.
SA2#166AH | Updates on VFL training and VFL inference to remove ENs | S2-2501346 | China Telecom, ZTE, Lenovo, Nokia, ETRI | TS 29.552 | China Mobile | VFL procedures are not defined yet | TS 29.552: Training procedure for Vertical Federated Learning. Procedure is almost stable. A new clause is needed, but how to draft the 29.552 CR for the new clause can be further discussed.
SA2#166AH | KI#2 update to VFL preparation procedure | S2-2501347 | InterDigital, Nokia | TS 29.552 | Ericsson | VFL procedures are not defined yet | TS 29.552: Preparation procedure for Vertical Federated Learning. A new clause is needed, but how to draft the 29.552 CR for the new clause can be further discussed.
SA2#165 | VFL support during the discovery of NWDAF, NEF, and AF instances | S2-2410996 | ICS, InterDigital, Futurewei, Ericsson, Nokia, Huawei, LG Electronics, KDDI, ETRI, NTT DOCOMO, MediaTek Inc., Lenovo, BT, Samsung, OPPO, ZTE, Vivo | n/a | Huawei (for clarifying FL) |  | - related how to clarify "Federated Learning"
SA2#165 | Update the general inference procedure for vertical federated learning to resolve ENs | S2-2411192 | OPPO, ZTE, Samsung, Nokia, Lenovo, Toyota, ICS, Huawei, HiSilicon, Ericsson | potential impact on TS 29.552 |  |  | - SA2 changes the place to put the text, and add some description under clause 6.2H.1. May have some similar description in stage-3. - The procedure related to inference procedure for VFL is not stable to be implemented in stage-3
SA2#165 | Refinements for VFL feature | S2-2411193 | Vivo, ICS, LG Electronics, InterDigital, ZTE, OPPO, Nokia, Samsung | TS 29.520 Potential impact on TS 29.552 | vivo | C3-246429 (29.520) C3-246468 (29.552) | - related how to clarify "Federated Learning" - TS 29.552/TS29.520: Potential update of discovery and selection of NWDAF in NRF - TS 29.522: support of "AF sends a discovery request for the VFL client(s) to the NEF and provides selection criteria" and "The NEF anonymizes NWDAF instances ID(s) and assigns temporary NWDAF ID(s) for each selected NWDAF intance as VFL client." But the related stage-2 API is not updated yet.
SA2#165 | General training procedure for Vertical Federated Learning between NWDAF(s) and AF(s) | S2-2411194 | China Mobile, CATT, ZTE, OPPO, China Telecom, ETRI, Huawei, HiSilicon, Nokia, Futurewei, Samsung | potential impact on TS 29.552 |  | C3-246467 | - TS 29.552: Training Procedure for VFL. Please note that there are plenty of ENs in the agreed CR. So the procedure is not stable for this meeting. There may some procedures that can achieve the consensus.
SA2#165 | High-level description for Vertical Federated Learning when AF is as Server. | S2-2411195 | KDDI, Ericsson, OPPO, ETRI, ICS | n/a |  |  | general functionality description for VFL server and VFL client. But stage 2 seems not stable.
SA2#164 | General inference procedure for vertical federated learning between AF and NWDAFs with AF as the VFL server | S2-2409417 | OPPO, ETRI, China Telecom, Tencent, ICS, ZTE, Samsung, Huawei, Nokia, KDDI, Ericsson, Lenovo, Interdigital, vivo, Futurewei | TS 29.552 | Ericsson, vivo | C3-250588 (only title) | - 29.552: New subclause for VFL when NWDAF as the VFL server (e.g. similar as clause 5.10.2) - Whether one general procedure or two separate procedures for NWDAF/AF as server is FFS
SA2#164 | High level feature description for VFL | S2-2409418 | Interdigital, LG Electronics, ICS, Futurewei, Huawei, ETRI, Nokia, Ericsson | TS 29.552 | Ericsson, vivo | C3-250588 (29.552) | - 29.552: New general subclause for VFL (e.g. similar as clause 5.10.1).
SA2#164 | Registration and Discovery procedure for Vertical Federated Learning among NWDAF(s) and/or AF(s) with NWDAF as the VFL server | S2-2409419 | ICS, OPPO, InterDigital, Lenovo, Vivo, NTT DOCOMO, Huawei, ZTE, LG Electronics, KDDI, Ericsson, Nokia, ETRI, MediaTek Inc., Samsung | TS 29.552 | Ericsson, Huawei | C3-245524 (29.552) C3-246469 (29.552) | - 29.552: Consumer discovery and selection of NWDAF in NRF for VFL (e.g. clause 5.8.2.3)
KI#3 NWDAF-assisted policy control and QoS enhancement
| Editor's note: whether the UE IDs need to be included is FFS. |  |  | 29.520 |  |  | The corresponding reply LS is S2-2507650 in SA2#170
| Editor's note: whether the UE IDs need to be included is FFS. |  |  | 29.520 |  |  | The corresponding reply LS is S2-2507650 in SA2#170
| Editor's note: FFS on the contents of the QosPara data type. |  |  | 29.520 |  |  | The corresponding reply LS is S2-2507650 in SA2#170
| Editor's note: Whether the used QoS profile needs to be provided is FFS. |  |  | 29.508 |  |  | The corresponding reply LS is S2-2507650 in SA2#170
SA2#170 | QoS Profile exposed by SMF event exposure | S2-2507581 | LG Electronics, Nokia | 29.508
SA2#170 | Correction on AIML_CN issues | S2-2507649 | Huawei, HiSilicon, Nokia | 29.508 29.520
SA2#168 | Enhancements on the input and output of QoS and Policy Assistance Analytics | S2-2504219 | China Mobile, ETRI, Samsung, Huawei | N/A |  |  | In agreed C3-251669, 'time window' is supported. In agreed C3-251629, QoS flow change is supported
SA2#167 | QFI Change event | S2-2502493 | NTT DOCOMO, CATT, Nokia, Samsung, ETRI | 29.508 |  | C3-251629 (29.508) | TS 29.508: support of QoS Flow change and QFI deallocation event
SA2#167 | Editorial improvement on QoS and policy assistance analytics | S2-2502520 | Samsung, Ericsson, Verizon, Oracle, China Mobile, NTT DOCOMO, Huawei, HiSilicon, ETRI | 29.520 29.552 |  | see S2-2412938 | - should be considered when implementing QoS and policy assistance analytics
SA2#166 | Support of QoS and policy assistance analytics | S2-2412938 | Samsung, China Mobile, ETRI, ICS, InterDigital Inc., MediaTek Inc, NTT DOCOMO, OPPO, SK Telecom, Tencent, Tencent Cloud, vivo, CATT, Huawei, Apple, Lenovo, Futurewei, Nokia, China Telecom | TS 29.552 TS 29.520 TS 29.513 | Huawei, Ericsson | C3-251645 (29.513) C3-251647 (29.520) C3-251648 (29.552) C3-251669 (29.520) C3-252380 (29.552) C3-252516 (29.520) C3-251628 (29.508) | TS 29.552: New subclause of QoS and Policy Assistance Analytics TS 29.520: support of New Analytics ID TS 29.508: potential New data type 'QFI allocation or QFI deallocation events' for SMF to expose to NWDAF - Please remind that the text is further updated in S2-2501149
SA2#166AH | Corrections on QoS and policy assistance analytics | S2-2501149 | Samsung, Ericsson | TS 29.552 TS 29.520 TS 29.508 | Huawei, Ericsson | see S2-2412938 | - Latest basis of S2-2412938
SA2#166AH | Support of QoS policy assistance information analytics | S2-2501150 | CATT | n/a
SA2#166AH | PCF use of QoS and policy assistance information analytic | S2-2501151 | Ericsson, Nokia, NTT DOCOMO | n/a | Ericsson | see S2-2412938 | requirement has already covered by S2-2412938
SA2#166AH | QFI Change event | S2-2501152 | NTT DOCOMO | n/a |  |  | requirement has already covered by S2-2412938
SA2#166AH | Addition of delay threshold match indication | S2-2501156 | Verizon, Oracle | n/a |  |  | potential impact: For NWDAF(Analytics = "QoS Sustainability"), support 'For a 5QI of non-GBR resource type, the output includes end-to-end delay (NOTE 2).'
KI#4 Signalling storm mitigation and prevention
| Editor's Note: It is FFS whether the SCP, the UDM, and the NRF are consumers of the Ndccf_DataManagement service. |  |  | 29.574 |  |  | waiting for SA2 reply LS
| Editor's Note: It is FFS whether the SCP, the UDM, and the NRF are consumers of the Nmfaf_3caDataManagement service. |  |  | 29.576 |  |  | waiting for SA2 reply LS
SA2#169 | KI#4: NRF Event Exposure to detect signaling storm | S2-2505749 | Oracle | N/A
SA2#169 | CR for 23.501 AIML_CN NRF services expsoure | S2-2505750 | vivo | N/A
SA2#169 | Clarification on data collection from SCP | S2-2505949 | Huawei, HiSilicon | N/A
SA2#169 | Clarifications for Signalling Storm Analytics | S2-2505752 | Lenovo | N/A
SA2#169 | NF discovery for signaling data collection related to signaling storm analytics | S2-2505445 | China Mobile | N/A
SA2#169 | Clarification on Signalling Storm Analytics | S2-2505052 | LG Electronics | n/a
SA2#169 | Update event exposure service of PCF | S2-2505950 | China Telecom
SA2#167 | KI#4: Minor Clarifications and Corrections | S2-2502232 |  | n/a
SA2#166 | New analytics for signaling storm mitigation (TS 23.501) | S2-2412725 | Vivo, SK Telecom, Huawei, HiSilicon, Nokia, Oracle, China Telecom, NTT DOCOMO, Samsung, Lenovo | N/A
SA2#166 | New analytics ID to support Signalling storm Mitigation and Prevention | S2-2412939 | SK Telecom, Samsung, Verizon, AT&T, China Mobile, ETRI, KPN N.V., LG Uplus, Rakuten Mobile, ZTE, China Telecom, Nokia, Ericsson, Lenovo, OPPO, NTT DOCOMO, Huawei, HiSilicon, KDDI, vivo, Oracle | TS 29.552 TS 29.520 TS 29.513 | China Telecom, ZTE Ericsson | C3-250450 (29.520) C3-250451 (29.520) C3-250563 (29.552) | Potential update to Signalling storm Mitigation and Prevention analytics to keep alignment TS 29.513: Signalling storm analytics for policy decision
SA2#166 | Event exposure service enhancement to support signalling storm data collection | S2-2412942 | China Telecom, Huawei, HiSilicon, Nokia, Oracle, SK Telecom, Verizon | TS 29.518 TS 29.513 TS 29.508 | Nokia, Huawei, China Telecom | C3-250563 (29.552) C3-252514 (29.508) C3-252515 (29.508) | TS 29.518: supports Total Signalling Measurements in Namf_EventExposure service TS 29.513: support collect data for NF related information from PCF TS 29.508: support collect data from SMF for Signalling Storm Analytics
SA2#166AH | Clarifying Signalling Storm Analytics | S2-2501153 | Huawei, HiSilicon, China Telecom, SK Telecom, Verizon, NTT DOCOMO | TS 29.520 | Huawei | C3-250452 (29.520) C3-250476 (29.522) | TS 29.520: support of a group of UEs or several groups of Ues in Analytics Filter Information
SA2#165 | New analytics ID to support Signalling storm Mitigation and Prevention | S2-2410976 | SK Telecom, Samsung, Verizon, AT&T, China Mobile, ETRI, KPN N.V., LG Uplus, Rakuten Mobile, ZTE, China Telecom, Nokia, Ericsson, Lenovo, OPPO, NTT DOCOMO, Huawei, HiSilicon, KDDI, vivo | TS 29.552 TS 29.520 potential impact on TS 29.508 TS 29.517 TS 29.591 | Ericsson, China Telecom, Huawei, Nokia | C3-246427 (29.517) C3-246428 (29.591) C3-246479 (29.520) C3-246480 (29.520) C3-246481 (29.522) C3-250454 (29.523) C3-250455 (29.517) C3-250456 (29.591) C3-250457 (29.575) C3-250589 (29.574) C3-251279 (29.517) C3-251280 (29.591) C3-251420 (29.522) C3-251603 (29.574) C3-251604 (29.576) C3-252513 (29.552) C3-252558 (29.520) | - TS 29.552/ TS29.520: New analytics ID for signalling storm,and procedures on Signalling Storm Mitigation and Prevention - TS 29.508: potential support Data collection from SMF. - TS 29.517/29.591: support of activation time information collection from AF

## CT4
NOTE: Text in red color means to be resolved
Contribution Plan
Meeting | Topic | Related stage 2 agreed CR # other WG tdoc(s) # | SA2 TDoc source | Impacted stage-3 TS | Volunteered company | addressed? | Comments
KI#1 Direct AI/ML based Positioning
SA2#170 | Clarification on data collection for LMF-based AI/ML positioning | S2-2507651 | CATT, Nokia, vivo, Huawei, HiSilicon | N/A
SA2#170 | Resolution of Editors Note on user consent and LCS privacy | S2-2507585 | Ericsson, AT&T, Lenovo, Nokia, ZTE, Interdigital | N/A
SA2#170 | General maintenance of KI#1 | S2-2507490 | ZTE | N/A
SA2#170 | Removal of requirements related to case 2b | S2-2507488 | vivo | N/A |  | positioning case is not implemented in CT4 yet.
SA2#169 | LMF re-selection based on AI capability | S2-2505951 |  | N/A |  |  | CT4 has already suppored the indication for LMF reselectiopn
SA2#169 | Typo correction in clause 6.2E.4 in TS 23.288 | S2-2505449 |  | n/a
SA2#168 | ML Model provisioning by OAM for LMF-based AI/ML Positioning | S2-2504198 | NTT DOCOMO, Ericsson, Nokia, Huawei, HiSilicon | N/A
SA2#168 | Removal of requirements related to case 2b | S2-2504200 | vivo, Xiaomi, ZTE, OPPO, Mediatek Inc., Samsung, Nokia, CATT, Ericsson, Qualcomm Incorporated, Huawei, HiSilicon, ERTI | 29.572 | Ericsson | C4-252312 | - TS 29.572: ‘NOTE X: The data source type only indicates NG-RAN measurement in this release.' The agreed C4-251481 should be updated to remove 'UE' from the data source type. - For TS 29.518 (Namf_EventExposure), removal of uePosCap and ueUpPosCap in AmfEventReport is needed, same for 'uePosCapRequestedInd' in AmfEvent. However, seems not stable in SA2. Suggest to wait for one meeting.
SA2#168 | Resolve ENs on input data for LMF based AI/ML positioning | S2-2504201 | CATT, Ericsson, vivo, Huawei, HiSilicon | N/A
SA2#167 | Modifications on ML Model retrieval service | S2-2502225 | ZTE | N/A
SA2#167 | Adding new LMF Selection Factor | S2-2502480 | China Mobile, ZTE, ETRI, Interdigital | 29.510 | Nokia, Ericsson | C4-251462 | Inclusion of AI/ML positioning capability for LMF re-selection only
SA2#167 | Clarification on LMF requesting ML model for LMF-based AI/ML Positioning from the NWDAF containing MTLF | S2-2502483 | CATT, ZTE, Intel, Huawei | N/A
SA2#167 | User consent check during performance monitoring | S2-2502484 | Samsung | N/A
SA2#167 | Procedures to collect data from the UE and from NG-RAN, resolution of Editor s Note. | S2-2502485 | Ericsson, AT&T | N/A |  |  | CT4 has already supported the LMF as a comsumer of Nudm_SubscriberDataManagement Service
SA2#167 | KI#1 - Further clarification on ML Model performance monitoring for AI/ML positioning | S2-2502486 | Lenovo, CATT | 29.572 | vivo, Nokia | C4-251481 C4-251487 | TS 29.572: Update to Nlmf_DataExposure Service to support Location measurement data, Ground truth data from PRU(s)/UE(s), and inference output
SA2#167 | Update UDM to support user consent of data collection for performance monitoring | S2-2502487 | Xiaomi | N/A | Huawei, Nokia | C4-250651 | CT4 has already supported the LMF as a comsumer of Nudm_SubscriberDataManagement Service
SA2#167 | Updates to AI/ML-based positioning general descriptions | S2-2502495 | Apple, CATT, Intel | 29.510 |  |  | - support of positioning case information is FFS and suggest to wait SA2 progress on it - TS 29.510: Potential clarification on "Other NWDAF discovery parameters listed in clause 5.2 of TS 23.288 [37] such as Analytics ID, FL capability type and related time period, S-NSSAI or any roaming capabilities are not included by LMF" - LMF-based AI/ML positioning indication is to be decided by CT3
SA2#167 | Clarification on data collection by LMF from NG-RAN for LMF-based AIML Positioning | S2-2502496 | CATT | N/A
SA2#167 | Clarification on LMF as service consumer for ML Model Training | S2-2502516 | China Mobile | N/A
SA2#167 | Clarification on model performance monitoring for LMF-based AIML Positioning | S2-2502528 | CATT, vivo, Intel, Huawei, HiSilicon, ZTE, China Telecom | 29.572 | Ericsson, Huawei, Nokia | C4-251481 C4-251487 | -TS29.572: support of quality threshold, ML model identifier , data source type, location estimation of PRU(s)/UE(s), cause code(?) for Nlmf_DataExposure Service -TS29.572: Support of 'The LMF may send a cause code to the NWDAF when the requested number of data samples cannot be met.' for Nlmf_DataExposure Service
SA2#167 | Updates to AI/ML-based positioning procedures | S2-2502784 | Apple, vivo, Interdigital | N/A |  |  | CT4 has already supported the LMF as a comsumer of Nudm_SubscriberDataManagement Service
SA2#166 | Update to model provisioning for LMF-based AIML positioning | S2-2412441 | CATT | N/A
SA2#166 | KI#1: Using New LMF DataCollection service to collect input data for model training | S2-2412457 | Nokia | N/A |  |  | Nlmf_DataExposure has already defined in CT4
SA2#166 | Addressing the EN about model provision for AI positioning | S2-2412728 | Vivo, Qualcomm Incorporated, ChinaTelecom, OPPO, Xiaomi, Nokia, Ericsson | 29.510 | Suggest to wait CT3 decision | The indication of LMF-based AI/ML Positioning is not defined yet
SA2#166 | NWDAF collects data from LCS to train ML model for AI positioning | S2-2412930 | Vivo, Nokia | N/A |  |  | - Related to indication of supporting model for LMF-based AI/ML Positioning, which will be decided by CT3 - positioning case information is related to EN, which is not suggested to be discussed in next meeting
SA2#166 | Update on Data Collection by LMF procedure | S2-2412931 | Lenovo, Qualcomm, Huawei, vivo, Nokia, Xiaomi | N/A |  |  | NWDAF can collect input data from LMF, i.e. Nlmf_DataExposure has already defined in CT4
SA2#166 | KI#1 - Addressing Editor s Note: Procedure for Data Collection for AI/ML based positioning from NG-RAN | S2-2412932 | Ericsson, Xiaomi, Nokia, Interdigital, Apple, Lenovo, CATT | N/A
SA2#166 | Support AI/ML model performance monitoring by NWDAF | S2-2412941 | Xiaomi, Nokia, Ericsson, Lenovo | N/A
SA2#166AH | Modifications on ML Model retrieval service | S2-2500083 | ZTE | N/A
SA2#166AH | Updates to AI/ML-based positioning general descriptions | S2-2501136 | Apple | N/A
SA2#166AH | Clarification on LMF requesting ML model for LMF-based AI/ML Positioning from the NWDAF containing MTLF | S2-2501137 | CATT | N/A
SA2#166AH | Clarification on data collection by LMF for LMF-based AIML Positioning | S2-2501138 | CATT | N/A |  |  | - Wait for SA2 further discussion: 'The LMF may query the UE for UE Positioning Capability and optionally UE User Plane Positioning Capabilities if not received in step 3.'
SA2#166AH | Updates to AI/ML-based positioning procedures | S2-2501139 | Apple | N/A |  |  | - LMF as UDM consumer is already supported - Whether to introduce a new UcPurpose should based on EN of SA2, propose to wait
SA2#166AH | NWDAF model provision for AI positioning | S2-2501140 | Vivo | TS 29.510 | Suggest to wait CT3 decision | The indication of LMF-based AI/ML Positioning is not defined yet | - Related to indication of supporting model for LMF-based AI/ML Positioning, which will be decided by CT3
SA2#166AH | NWDAF registration and discovery for AI positioning | S2-2501141 | Vivo | TS 29.510 | Suggest to wait CT3 decision | The indication of LMF-based AI/ML Positioning is not defined yet | - Related to indication of supporting model for LMF-based AI/ML Positioning, which will be decided by CT3
SA2#166AH | Procedures to collect data from the UE and from NG-RAN, resolution of Editor s Note. | S2-2501348 | Ericsson | N/A |  |  | - Whether to introduce a new UcPurpose should based on EN of SA2, propose to wait
SA2#165 | LMF enhancements for LMF-based AI/ML Positioning | S2-2410978 | Huawei, HiSilicon, NTT DOCOMO, Nokia | TS 29.572 TS 29.510 | Huawei (29.572, 29.510), Ericsson | C4-245383 C4-245534 | -TS 29.572: Introduction of Nlmf_DataExposure API - TS 29.510: Enhancement of NRF discovery service
SA2#165 | ML Model based UE positioning support | S2-2410980 | NTT DOCOMO, Ericsson | N/A |  | C4-245354 | - Clarifications has been captured by other CRs
SA2#165 | Support AI/ML model performance monitoring by LMF | S2-2410981 | Xiaomi, Nokia, Ericsson | N/A |  |  | - May have impact e.g. some gengeral description in 29.572
SA2#165 | Support AI/ML model performance monitoring by NWDAF | S2-2410995 | Xiaomi, Nokia, Ericsson | N/A
SA2#165 | Addressing the EN about model provision for AI positioning | S2-2410997 | vivo | TS 29.510 | vivo, Huawei, ZTE | The indication of LMF-based AI/ML Positioning is not defined yet | - TS 29.510: During the discovery of NWDAF containing MTLF... If the consumer is an LMF, it may include in the request an indication that supporting of ML Model training for LMF-based AI/ML Positioning is required.
SA2#165 | KI#1 - Addressing Editor´s Note: Procedure for Data Collection for AI/ML based positioning from NG-RAN | S2-2411257 | Ericsson, Xiaomi, Nokia | N/A
SA2#165 | Update on Data Collection by LMF procedure | S2-2411256 | Lenovo, Qualcomm, Huawei | TS 29.518 | vivo, Huawei, Ericsson | C4-245377 | - SA2 changes the place to put the text, and add a new requirement on considering "UE Positioning Capability" - TS 29.518: Enhancment on Namf_EventExposure to support the “Event ID = "UEs in/out area of interest" and “UE Positioning Capability”"
SA2#164 | Support for LMF to retrieve ML Model of AI/ML based positioning | S2-2409413 | Vivo, Nokia, Lenovo, ZTE, Huawei, OPPO, MediaTek Inc., Ericsson, CATT | N/A
SA2#164 | Introduction of LMF enhancement for Direct AI/ML based Positioning | S2-2409414 | Qualcomm Incorporated, Ericsson, Nokia, ZTE, Xiaomi, vivo, OPPO, interdigital, Lenovo | TS 29.503 | Ericsson | C4-244355 | - 29.503: LMF as a new comsumer of UDM for retrieving user consent - The details of discovering a NWDAF containing MTLF via NRF is FFS - Performance monitoring procedures for LMF is FFS - input data collection for ML model training is FFS
SA2#164 | KI#1 - LMF enhancements for UE positioning using a ML model | S2-2409415 | Ericsson, Xiaomi, Lenovo, Vivo, NTT DOCOMO | TS 29.503 | Ericsson | C4-244355 | - 29.503: LMF as a new comsumer of UDM for retrieving user consent, same as S2-2409414 - Namf_EventExposure_Subscriber service between LMF and AMF has already be supported (29.518)
KI#2 Vertical Federated Learning (VFL)
SA2#168 | Editor s Note clean up for the VFL | S2-2504202 | OPPO, Nokia | N/A |  |  | -TS 29.503: potential support of 'NOTE 2: For UE as samples, UEs can be registered to the network and NWDAF as a VFL server can check with whether the UEs are registered to the network.' i.e. The NWDAF can get RM status from UDM
SA2#168 | Optimization of VFL triggers | S2-2504221 | ZTE, Huawei, Hisilicon, vivo, OPPO, Nokia, Futurewei, Samsung, China Mobile, Interdigital | N/A
SA2#168 | Update triggering Case A and some corrections and Resolving ENs for VFL | S2-2504220 | Ericsson, China Telecom, ZTE | N/A
SA2#168 | Alignment of existing mechanisms for accuracy generation impacted by VFL procedures | S2-2503972 | Huawei, HiSilicon, ZTE | N/A
SA2#168 | Parameters for vertical federated learning inference procedure | S2-2504216 | Nokia, Vivo, Huawei, Oppo, Samsung | N/A
SA2#168 | Updates on VFL inference | S2-2504476 | Interdigital, Samsung | N/A
SA2#168 | Maintenance of VFL model training and inference with client intermediate results sharing between VFL clients | S2-2504218 | Samsung, ZTE, Nokia, OPPO, LG Electronics, Ericsson | 29.510 |  | C4-252296 | -TS29.510: support of 'The VFL client may also include its capability of aggregating the intermediate results of the other clients into its NF profile.' during registration to NRF
SA2#167 | Addressing EN in VFL training | S2-2501546 | Tejas Networks | n/a
SA2#167 | Clarifications on intermediate training result and intermediate model training information | S2-2502261 | ZTE | n/a
SA2#167 | Sample update during VFL training | S2-2502262 | Apple, Ericsson, Samsung, ETRI, Futurewei, ZTE | n/a
SA2#167 | KI#2 update to VFL preparation procedure | S2-2502488 | InterDigital, Nokia, Ericsson, Futurewei, LGE, Huawei, HiSilicon, ZTE, OPPO, Samsung, Lenovo | n/a
SA2#167 | Adding VFL related services supported by NEF and AF | S2-2502492 | Vivo, Nokia, KDDI | n/a
SA2#167 | Resolving ENs for VFL | S2-2502527 | Ericsson, Lenovo, InterDigital, OPPO, Nokia, ZTE, KDDI, Samsung, Vivo, CMCC, China Telecom, Huawei, HiSilicon | n/a
SA2#167 | Resolve some ENs in the vertical federated learning inference procedure | S2-2502668 | OPPO, ZTE, Nokia, Ericsson, Samsung, China Telecom, vivo, Huawei, Hisilicon | n/a
SA2#167 | KI#2: VFL services | S2-2502669 | Nokia, Ericsson, LG Electronics, OPPO | n/a
SA2#167 | Enhancements for the accuracy monitoring of VFL training | S2-2502679 | vivo | n/a
SA2#167 | KI#2 update to VFL inference procedure | S2-2502680 | InterDigital, Samsung, Nokia, LG Electronics | n/a
SA2#167 | Support of VFL model training and inference with client intermediate results sharing between VFL clients | S2-2502681 | Samsung, Lenovo, OPPO, ZTE, Apple, Nokia, InterDigital | n/a
SA2#167 | EN removal for clarification of VFL high level description | S2-2502682 | KDDI, LG Electronics, Huawei, ETRI, Samsung, China mobile, ZTE | n/a
SA2#166 | High level description refinement of NWDAF initiated VFL training | S2-2412455 | ZTE | N/A
SA2#166 | High-level description for Vertical Federated Learning when AF is as Server. | S2-2412734 | KDDI, Ericsson, ZTE, ICS, CMCC, ETRI, Huawei, Samsung, Apple, OPPO | N/A
SA2#166 | KI#2 Update of VFL training and inference | S2-2412885 | Ericsson, ETRI, InterDigital, ICS, OPPO, Lenovo, Vivo, Nokia, Apple, Samsung, Futurewei, ZTE, Huawei | N/A
SA2#166 | Enhancement to NRF s discovery and registration procedures to support VFL | S2-2412929 | ICS, InterDigital, Futurewei, Nokia, Ericsson, Lenovo, LG Electronics | TS 29.510 | vivo, Huawei | C4-250638 | latest version can be seen from S2-2501143 For NWDAF, untrusted AFs, trusted AFs: -TS 29.510: Support of Feature ID - TS 29.510: support of VFL interoperability indicator
SA2#166 | Update the general inference procedure for vertical federated learning to resolve ENs | S2-2412933 | OPPO, ZTE, Samsung, Nokia, Lenovo, Toyota, ICS, Huawei, HiSilicon, Ericsson, InterDigital, Tencent, ETRI, Vivo, Apple. | N/A
SA2#166 | Refinements for VFL feature | S2-2412934 | Vivo, ICS, LG Electronics, InterDigital, ZTE, OPPO, Nokia, Samsung, Ericsson, Huawei, Lenovo, KDDI, ETRI | N/A
SA2#166 | General training procedure for Vertical Federated Learning between NWDAF(s) and AF(s) | S2-2413023 | China Mobile, CATT, ZTE, OPPO, China Telecom, ETRI, Huawei, HiSilicon, Nokia, Futurewei, Samsung, Ericsson, InterDigital, Apple, Lenovo, Vivo | N/A
SA2#166AH | Adding missing parts for VFL | S2-2500195 | Vivo(rapporteur), MediaTek Inc(rapporteur) | N/A
SA2#166AH | Resolving ENs for VFL | S2-2501134 | Ericsson, Lenovo, InterDigital, [OPPO] | N/A
SA2#166AH | KI#2: VFL services | S2-2501135 | Nokia | N/A
SA2#166AH | The related definitions for VFL and HFL | S2-2501142 | China Mobile | N/A
SA2#166AH | KI#2 update to registration and discovery procedure | S2-2501143 | InterDigital | TS 29.510 | vivo, Huawei | C4-250638 | For NWDAF, untrusted AF, trusted AFs: -TS 29.510: Support of Feature ID. Please note that there is no standardized Feature ID. - TS 29.510: support of VFL interoperability indicator
SA2#166AH | Clarifications on VFL general procedure | S2-2501144 | China Mobile | N/A
SA2#166AH | KI2: Addressing ENs for VFL . | S2-2501145 | Lenovo | N/A
SA2#166AH | NWDAF discovery and selection parameters | S2-2501146 | LG Electronics | TS 29.510 | vivo, Huawei | C4-250638 | same as S2-2501143 For NWDAF, untrusted AFs, trusted AFs: -TS 29.510: Support of Feature ID - TS 29.510: support of VFL interoperability indicator
SA2#166AH | KI#1 and KI#2 alignment | S2-2501147 | ZTE | n/a
SA2#166AH | Adding VFL related services supported by NEF and AF | S2-2501148 | Vivo | N/A
SA2#166AH | Resolve some ENs in the vertical federated learning inference procedure | S2-2501345 | OPPO | N/A
SA2#166AH | Updates on VFL training and VFL inference to remove ENs | S2-2501346 | China Telecom | N/A
SA2#166AH | KI#2 update to VFL preparation procedure | S2-2501347 | InterDigital | N/A
SA2#165 | VFL support during the discovery of NWDAF, NEF, and AF instances | S2-2410996 | ICS, InterDigital, Futurewei, Ericsson, Nokia, Huawei, LG Electronics, KDDI, ETRI, NTT DOCOMO, MediaTek Inc., Lenovo, BT, Samsung, OPPO, ZTE, Vivo | TS 29.510 | vivo, Huawei | C4-245481 | - TS 29.510: support discovery and selection of an NWDAF that supports Vertical Federated Learning (VFL) - TS 29.510: support AF Discovery and Selection for VFL - TS 29.510: Clarify HFL, e.g. FlCapabilityType
SA2#165 | Update the general inference procedure for vertical federated learning to resolve ENs | S2-2411192 | OPPO, ZTE, Samsung, Nokia, Lenovo, Toyota, ICS, Huawei, HiSilicon, Ericsson | N/A
SA2#165 | Refinements for VFL feature | S2-2411193 | Vivo, ICS, LG Electronics, InterDigital, ZTE, OPPO, Nokia, Samsung | TS 29.510 | vivo, Huawei | C4-245481 | - TS 29.510: support discovery and selection of an NWDAF that supports Vertical Federated Learning (VFL), similar as S2-2410996
SA2#165 | General training procedure for Vertical Federated Learning between NWDAF(s) and AF(s) | S2-2411194 | China Mobile, CATT, ZTE, OPPO, China Telecom, ETRI, Huawei, HiSilicon, Nokia, Futurewei, Samsung | n/a
SA2#165 | High-level description for Vertical Federated Learning when AF is as Server. | S2-2411195 | KDDI, Ericsson, OPPO, ETRI, ICS | n/a |  |  | - support AF registration e.g. VFL capability information
SA2#164 | General inference procedure for vertical federated learning between AF and NWDAFs with AF as the VFL server | S2-2409417 | OPPO, ETRI, China Telecom, Tencent, ICS, ZTE, Samsung, Huawei, Nokia, KDDI, Ericsson, Lenovo, Interdigital, vivo, Futurewei | N/A |  |  | - an NWDAF acting as VFL server/client shall include its (VFL) capability information including (VFL) capability type during the registration in NRF, but the capability form is FFS
SA2#164 | High level feature description for VFL | S2-2409418 | Interdigital, LG Electronics, ICS, Futurewei, Huawei, ETRI, Nokia, Ericsson | N/A
SA2#164 | Registration and Discovery procedure for Vertical Federated Learning among NWDAF(s) and/or AF(s) with NWDAF as the VFL server | S2-2409419 | ICS, OPPO, InterDigital, Lenovo, Vivo, NTT DOCOMO, Huawei, ZTE, LG Electronics, KDDI, Ericsson, Nokia, ETRI, MediaTek Inc., Samsung | N/A |  |  | - Data model for Nnrf_NFDiscovery service has already supported in 29.510
KI#3 NWDAF-assisted policy control and QoS enhancement
SA2#170 | QoS Profile exposed by SMF event exposure | S2-2507581 | LG Electronics, Nokia | N/A
SA2#170 | Correction on AIML_CN issues | S2-2507649 | Huawei, HiSilicon, Nokia | N/A
SA2#168 | Enhancements on the input and output of QoS and Policy Assistance Analytics | S2-2504219 | China Mobile, ETRI, Samsung, Huawei | N/A
SA2#167 | QFI Change event | S2-2502493 | NTT DOCOMO, CATT, Nokia, Samsung, ETRI | N/A
SA2#167 | Editorial improvement on QoS and policy assistance analytics | S2-2502520 | Samsung, Ericsson, Verizon, Oracle, China Mobile, NTT DOCOMO, Huawei, HiSilicon, ETRI | N/A
SA2#167 | QoS and Policy Assistance Analytics |  |  | N/A
SA2#166 | Support of QoS and policy assistance analytics | S2-2412938 | Samsung, China Mobile, ETRI, ICS, InterDigital Inc., MediaTek Inc, NTT DOCOMO, OPPO, SK Telecom, Tencent, Tencent Cloud, vivo, CATT, Huawei, Apple, Lenovo, Futurewei, Nokia, China Telecom | N/A
SA2#166AH | Corrections on QoS and policy assistance analytics | S2-2501149 | Samsung, Ericsson | N/A
SA2#166AH | Support of QoS policy assistance information analytics | S2-2501150 | CATT | N/A
SA2#166AH | PCF use of QoS and policy assistance information analytic | S2-2501151 | Ericsson, Nokia, NTT DOCOMO | N/A
SA2#166AH | QFI Change event | S2-2501152 | NTT DOCOMO | N/A
SA2#166AH | Addition of delay threshold match indication | S2-2501156 | Verizon, Oracle | N/A
KI#4 Signalling storm mitigation and prevention
SA2#169 | KI#4: NRF Event Exposure to detect signaling storm | S2-2505749 | Oracle | TS 29.570 |  |  | related to reply LS S2-2506099
SA2#169 | CR for 23.501 AIML_CN NRF services expsoure | S2-2505750 | vivo | N/A
SA2#169 | Clarification on data collection from SCP | S2-2505949 | Huawei, HiSilicon | TS 29.570 |  |  | related to reply LS S2-2506099
SA2#169 | Clarifications for Signalling Storm Analytics | S2-2505752 | Lenovo | n/a
SA2#169 | NF discovery for signaling data collection related to signaling storm analytics | S2-2505445 | China Mobile | N/A
SA2#169 | Clarification on Signalling Storm Analytics | S2-2505052 | LG Electronics | n/a
SA2#169 | Update event exposure service of PCF | S2-2505950 | China Telecom | N/A |  |  | -In 29.523, the data type array(SnssaiDnnCombination) states: If omitted, it represents any combination. Hence it is supported to omit this combination in 29.523 - In 29.523, NWDAF has already a consumer of the API
SA2#167 | KI#4: Minor Clarifications and Corrections | S2-2502232 |  | N/A
SA2#166 | New analytics for signaling storm mitigation (TS 23.501) | S2-2412725 | Vivo, SK Telecom, Huawei, HiSilicon, Nokia, Oracle, China Telecom, NTT DOCOMO, Samsung, Lenovo | TS 29.570 (SCP) |  | related Tdoc see S2-2412942 | - 29.570 (New TS): for Nscp_EventExposure
SA2#166 | New analytics ID to support Signalling storm Mitigation and Prevention | S2-2412939 | SK Telecom, Samsung, Verizon, AT&T, China Mobile, ETRI, KPN N.V., LG Uplus, Rakuten Mobile, ZTE, China Telecom, Nokia, Ericsson, Lenovo, OPPO, NTT DOCOMO, Huawei, HiSilicon, KDDI, vivo, Oracle | N/A
SA2#166 | Event exposure service enhancement to support signalling storm data collection | S2-2412942 | China Telecom, Huawei, HiSilicon, Nokia, Oracle, SK Telecom, Verizon | TS 29.570 (SCP) TS 29.510 TS 29.518 | Huawei (29.510, skeleton of the new TS) | C4-250147 C4-250148 C4-250412 C4-250418 C4-250419 C4-250650 C4-250485 C4-250639 C4-250640 C4-251129 C4-251435 C4-251437 C4-251458 C4-251499 C4-252297 C4-252298 | - TS 29.510 has already support NF load status information, capacity and priority information of NFs and NF Services, etc as described in Table 6.x.2-2 and Table 6.x.2-5 of TS 23.288 [50]. - New TS: Nscp_EventExposure Service TS 29.518: new event Total Signalling Measurements for AMF event exposure
SA2#166AH | Clarifying Signalling Storm Analytics | S2-2501153 | Huawei, HiSilicon, China Telecom, SK Telecom, Verizon, NTT DOCOMO | N/A
SA2#166AH | Clarification and alignment on signalling storm analytics | S2-2501154 | China Telecom | N/A
SA2#165 | New analytics ID to support Signalling storm Mitigation and Prevention | S2-2410976 | SK Telecom, Samsung, Verizon, AT&T, China Mobile, ETRI, KPN N.V., LG Uplus, Rakuten Mobile, ZTE, China Telecom, Nokia, Ericsson, Lenovo, OPPO, NTT DOCOMO, Huawei, HiSilicon, KDDI, vivo | N/A

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT meeting #; tdoc(s) # | Open issues | Comments
S2-2506099 | Reply LS on Questions on stage 2 requirements for AIML_CN |  | CT4#127, C4-250591 | clarification of SCP from SA2

## Outcoming LSs
Outcoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
C4-250591 | LS on Questions on stage 2 requirements for AIML_CN | N/A | CT4#127 | Question for SA2 to clarify SCP | From CT4 to SA2, CC CT3
C4-251477 | LS on Clarification on SCP data collection | N/A | CT4#128 | Question for SA2 to clarify SCP | From CT4 to SA2
C3-251653 | LS on AIML_CN issues | N/A | CT3#140 | Question for SA2 to clarify DCCF and the MFAF consumer, and QoS Profile parameters | From CT3 to SA2, CC CT4

## CT WG Progress
Meeting | Tdoc | Title | Source | status
CT3#137 | C3-245477 | Support for LMF to retrieve ML Model of AIML based positioning | Ericsson, Huawei, Nokia, vivo | agreed
| C3-245478 | Support for LMF to retrieve ML Model of AIML based positioning | Ericsson, Nokia, vivo | agreed
| C3-245524 | Support the discovery of NWDAF for VFL | Huawei, Nokia, Ericsson | agreed
CT4#125 | C4-244355 | LMF as Consumer of User Consent Subscription Data | Ericsson, Nokia | agreed
CT3#138 | C3-246427 | Support of activation time information collection | Huawei, Ericsson, Nokia | agreed
| C3-246428 | Support of activation time information collection | Huawei, Ericsson, Nokia | agreed
| C3-246429 | Clarification for Horizontal Federated Learning | Huawei, vivo, Ericsson, Nokia | agreed
| C3-246465 | Adding LMF as LM model training and performance monitoring data source | Nokia | agreed
| C3-246467 | Procedure for Vertical Federated Learning when NWDAF is acting as VFL server | China Mobile, Ericsson, Huawei | agreed
| C3-246468 | Clarification for Horizontal Federated Learning | Huawei, vivo, China Mobile, Ericsson, Nokia | agreed
| C3-246469 | Support the discovery of NWDAF for VFL | Huawei, Nokia, Ericsson, vivo | agreed
| C3-246479 | Support of the signalling storm analytics for Nnwdaf_EventsSubscription API | Huawei, Ericsson, Nokia, vivo | agreed
| C3-246480 | Support of the signalling storm analytics for Nnwdaf_AnalyticsInfo API | Huawei, vivo, Nokia, Ericsson | agreed
| C3-246481 | Support of the signalling storm analytics for AnalyticsExposure API | Huawei | agreed
| C3-246519 | Support of signalling storm mitigation and prevention | China Telecom, vivo | agreed
| C3-246532 | Adding LMF as ML model training and performance monitoring data source | Nokia | agreed
| C3-246583 | Adding LMF as ML model training and performance monitoring data source | Nokia, Ericsson | agreed
CT4#126 | C4-245354 | Updates on the Reference model | Huawei, Nokia | agreed
| C4-245377 | Addition of Data Collection parameters in AMF for LMF data collection procedure | Nokia, Huawei, vivo, Ericsson | agreed
| C4-245383 | New LMF service | Huawei, Nokia | agreed
| C4-245481 | Supporting vertical federated learning | Huawei, vivo, Nokia, Ericsson | agreed
| C4-245534 | LMF Enhancements for LMF based AI/ML Positioning – Stage 3 aspects | Ericsson, Vivo, Nokia, Huawei | agreed
CT3#139 | C3-250177 | Adding PCF as data source | Nokia | agreed
| C3-250450 | Add service consumer for retrieving signalling storm analytics | China Telecom, Ericsson, vivo, Huawei | agreed
| C3-250451 | Updates to Signalling Storm Analytics | Ericsson | agreed
| C3-250452 | Enhancements on the signalling storm analytics | Huawei, Ericsson | agreed
| C3-250453 | LMF event model corrections | Nokia | agreed
| C3-250454 | Signalling storm information exposure | Nokia | agreed
| C3-250455 | Signalling storm information exposure | Nokia | agreed
| C3-250456 | Signalling storm information exposure | Nokia | agreed
| C3-250457 | Adding PCF as data source | Nokia | agreed
| C3-250476 | Enhancements on the signalling storm analytics | Huawei, Ericsson | agreed
| C3-250477 | Adding LMF as consumer of Nadrf_MLModelManagement_RetrievalRequest service operation | ZTE, vivo | agreed
| C3-250563 | Updates to Signalling Storm Analytics | Ericsson, China Telecom, Huawei, vivo | agreed
| C3-250588 | Clarification on VFL procedures | vivo, Ericsson, China Mobile | agreed
| C3-250589 | Adding PCF as data source | Nokia | agreed
CT4#127 | C4-250147 | Skeleton of new TS on Service Communication Proxy (SCP) Services | Huawei, vivo | agreed
| C4-250148 | Abbreviations clause of new TS on Service Communication Proxy (SCP) Services | Huawei | agreed
| C4-250343 | Corrections to Nlmf_DataExposure service | Nokia | agreed
| C4-250345 | Removal of subscriptionCorrelationId from LmfDataExposureNotification data type | Nokia | agreed
| C4-250412 | Adding SCP services | Huawei, Nokia, Ericsson | agreed
| C4-250418 | Overview for the SCP service | vivo, Nokia | agreed
| C4-250419 | PCR on Services offered by the SCP | Nokia | agreed
| C4-250443 | Alignment of MlAnalyticsInfo attributes for VFL | Nokia, vivo, Huawei | agreed
| C4-250485 | AMF Signalling Measurement Event for Storm Mitigation | Ericsson | agreed
| C4-250524 | Updates on Nlmf_DataExposure | Huawei | agreed
| C4-250617 | Defining VFL time interval | Nokia, Huawei | agreed
| C4-250638 | Support of Feature ID and VFL interoperability indicator for NWDAF, untrusted AF, and trusted Afs | vivo, Huawei, Nokia | agreed
| C4-250639 | 3GPP TS 29.abc | Huawei | agreed
| C4-250640 | PCR on API Definition of new SCP Service | Nokia | agreed
| C4-250650 | NF signalling information data model | Nokia | agreed
| C4-250651 | LMF functionalities and consumers | Nokia | agreed
CT3#140 | C3-251224 | eventFilter for APP_ACTIVE_TIME | ZTE | agreed
| C3-251225 | Clarification on cause NF for Nnwdaf_AnalyticsInfo Service | ZTE | agreed
| C3-251226 | Adding cause NF for Signalling Storm analytics | ZTE | agreed
| C3-251279 | Removal of the EN for the attribute with array data type | Huawei, Nokia | agreed
| C3-251280 | Removal of the EN for the attribute with array data type | Huawei, Nokia | agreed
| C3-251422 | Resolve EN on Signaling Storm Analytics | Ericsson | agreed
| C3-251441 | Wrong event names | Nokia | agreed
| C3-251603 | Signalling Storm analytics consumers | Nokia | agreed
| C3-251604 | Signalling Storm analytics consumers | Nokia | agreed
| C3-251629 | Support of QoS parameters reporting | Huawei, Nokia | agreed
| C3-251645 | Introduction of QoS and Policy Assistance analytics | Ericsson, Huawei | agreed
| C3-251647 | Support of QoS and Policy Assistance Analytics for Nnwdaf_AnalyticsInfo API | Huawei, Nokia, Ericsson | agreed
| C3-251648 | Procedure definition for QoS and Policy Assistance Analytics | Huawei, Ericsson | agreed
| C3-251669 | QoS and Policy Assistance Analytics in Nnwdaf_EventsSubscription API | Ericsson, Huawei, Nokia | agreed
CT4#128 | C4-251129 | Pseudo-CR on correction of definition and abbreviation clauses | Huawei, MCC | agreed
| C4-251373 | Updates on data collection by LMF | Huawei | agreed
| C4-251435 | Pseudo-CR on event exposure service description | Huawei | agreed
| C4-251437 | Pseudo-CR on removing template guideline texts | Huawei, vivo | agreed
| C4-251458 | 3GPP TS 29.570 v0.2.0 | Huawei | agreed
| C4-251462 | Support for AI/ML Positioning Capability for LMF Reselection | Nokia, Ericsson, ZTE, Huawei, vivo | agreed
| C4-251481 | Support of Performance Monitoring for LMF Based AIML Positioning | Ericsson, CEWiT, vivo, Huawei, Nokia | agreed
| C4-251487 | Abnormal Handling for LMF Data Exposure Service | Ericsson, Nokia, CEWit, vivo, Huawei | agreed
| C4-251499 | Pseudo-CR on service data types used in Subscribe service operation | Huawei, Nokia | agreed
CT3#141 | C3-252265 | Enhancements on the consumers of Nadrf_ MLModelManagement Service | Huawei | agreed
| C3-252380 | Procedure definition for QoS and Policy Assistance Analytics | Huawei, Ericsson | agreed
| C3-252513 | Add SCP as the analytics data source of NWDAF | Huawei, Ericsson | agreed
| C3-252514 | Support of UE related Context Data and NF specific Data collection | Huawei, Nokia | agreed
| C3-252515 | Support of signalling information collection for signalling storm analytics | Huawei, Nokia | agreed
| C3-252516 | QoS and Policy Assistance Analytics in Nnwdaf_EventsSubscription API | Ericsson, Huawei, Nokia | agreed
| C3-252544 | Nnwdaf_VFLInference API | Ericsson, Nokia, Huawei, vivo, Verizon | agreed
| C3-252545 | Define OpenAPI for Nnwdaf_VFLTraining API | Huawei, Nokia, Ericsson | agreed
| C3-252546 | Nnwdaf_VFLInference model definition | Ericsson, Nokia, Huawei, vivo, Verizon | agreed
| C3-252547 | Nnwdaf_VFLInference service definition | Ericsson, Nokia, Huawei, vivo, Verizon | agreed
| C3-252548 | Define resource and data model for Nnwdaf_VFLTraining API | Huawei, Nokia, Ericsson | agreed
| C3-252549 | VFLTraining API service operation descriptions | Nokia, Ericsson, Huawei, vivo | agreed
| C3-252558 | Updates to Signalling Storm Analytics | Ericsson | agreed
| C3-252612 | Support of Nnef_VFLNFDiscovery Service | vivo, Nokia, Ericsson | agreed
| C3-252613 | Support of procedure for Nnef_VFLNFDiscovery Service | vivo, Nokia, Ericsson | agreed
CT4#129 | C4-252129 | Correction on UE UP Positioning Capabilities | Ericsson | agreed
| C4-252222 | Corrections in the OpenAPI | Huawei | agreed
| C4-252295 | Support for ML model access control for LMF | Nokia | agreed
| C4-252296 | Support of VFL capability for aggregating the intermediate result | vivo, Nokia, LG Electronics, Huawei | agreed
| C4-252297 | Restructure ScpEventFilter to Support Multiple Configurations | Nokia | agreed
| C4-252298 | Spec Cleanup: Template Text Removal and Event Name Correction | Nokia, Huawei | agreed
| C4-252299 | 3GPP TS 29.570 v0.3.0. on 5G System; Service Communication Proxy (SCP) Services; Stage 3 | Huawei | agreed
| C4-252312 | Support of Performance Monitoring for LMF Based AIML Positioning | Ericsson, CEWiT, vivo, Huawei, Nokia | agreed
| C4-252445 | Enhancements to Nlmf_DataExposure API | CEWiT, Nokia, Ericsson | agreed
| C4-252446 | VFL services | Nokia, Huawei | agreed
CT3#142 | C3-253241 | Re-used data types correction | Nokia | agreed
| C3-253362 | Pseudo-CR on the new AIML AF Services TS Skeleton | Huawei | agreed
| C3-253363 | Pseudo-CR on defining the new AF services TS scope, terms and abbreviations | Huawei | agreed
| C3-253401 | Correction to SignalStormReq | Ericsson | agreed
| C3-253450 | Correction and completion of VFLNFDiscovery impacts | vivo, Ericsson | agreed
| C3-253540 | Editorial correction on Nnwdaf_VFLInference Service definition | China Mobile | agreed
| C3-253541 | Corrections to signalling storm analytics | China Telecom, Ericsson | agreed
| C3-253542 | Data and error completion for Nnwdaf_VFLInference | Ericsson, Nokia, China Mobile | agreed
| C3-253543 | VFL Training on MLModelProvision | Ericsson, Nokia | agreed
| C3-253544 | Pseudo-CR on The procedures of the Naf_Inference API | Ericsson, Nokia | agreed
| C3-253545 | Definition of Nnef_Inference | Ericsson | agreed
| C3-253546 | Pseudo-CR on defining the API definition clauses of the Naf_Training API | Huawei, Nokia | agreed
| C3-253547 | Pseudo-CR on defining the new AF services TS general clauses | Huawei | agreed
| C3-253548 | Pseudo-CR on defining the service description clauses of the Naf_Training API | Huawei, Nokia | agreed
| C3-253549 | Pseudo-CR on defining the OpenAPI of the Naf_Training API | Huawei, Nokia | agreed
| C3-253550 | Pseudo-CR on defining the API definition clauses of the Naf_VFLTraining API | Huawei | agreed
| C3-253551 | Pseudo-CR on defining the service description clauses of the Naf_VFLTraining API | Huawei | agreed
| C3-253552 | Pseudo-CR on defining the OpenAPI description of the Naf_VFLTraining API | Huawei | agreed
| C3-253553 | Support of PATCH and GET for Nnwdaf_VFLTraining API | Huawei | agreed
| C3-253554 | Resolve ENs in QoS and Policy Assistance Analytics | Ericsson, Huawei | agreed
| C3-253555 | Support of VFL preparation procedures | vivo | agreed
| C3-253556 | Support of VFL inference procedures | vivo | agreed
| C3-253636 | Naf_VFLInference Service definition | China Mobile, Ericsson, Huawei, Nokia | agreed
| C3-253637 | Naf_VFLInference Service model definition | China Mobile, Ericsson, Huawei, Nokia | agreed
| C3-253638 | Naf_VFLInference Service API definition | China Mobile, Ericsson, Huawei, Nokia | agreed
| C3-253639 | Definition of Nnef_VFLInference | Ericsson, China Mobile | agreed
| C3-253640 | Definition of Northbound Nnef_VFLInference | Ericsson, vivo, Nokia, China Mobile | agreed
| C3-253641 | Nnef_VFLInference service operation descriptions | Nokia, vivo, Ericsson | agreed
| C3-253642 | Nnef_VFLTraining service operation descriptions | Nokia, vivo | agreed
| C3-253643 | Nnef_VFLTraining data model | Nokia, vivo | agreed
| C3-253644 | Nnef_VFLTraining OpenAPI | Nokia, vivo | agreed
| C3-253650 | 3GPP TS 29.530 v0.1.0 | Huawei | agreed
| C3-253710 | Exception sheet for AIML_CN | vivo | agreed
| C3-253716 | Presentation of 3GPP TS 29.530 v0.1.0 to TSG for information | Huawei | agreed
CT4#130 | C4-253196 | Addition of OverloadControlInfo data type | Nokia | agreed
| C4-253200 | VFL services | Nokia | agreed
| C4-253458 | AIML Positioning Method | Ericsson | agreed
| C4-253459 | Resolve Editor's Notes | Ericsson, vivo | agreed
| C4-253495 | Corrections to SCP Event Exposure Data Definitions, API Versioning, and OpenAPI | Nokia | agreed
| C4-253496 | Update the NF signalling information | Nokia | agreed
| C4-253517 | SCP Event Exposure Data Types and Alignment with SA2 Requirements | Nokia, Huawei, vivo | agreed
| C4-253558 | Access token to support VFL | Huawei, Nokia | agreed
| C4-253559 | Support per-UE Signalling Analytics in Signalling-Measurement-Report Event | Nokia | agreed