## Tdoc cover sheet
3GPP TSG-CT WG3 Meeting #143 Sophia, France, 13 - 17 October, 2025 |  | C3-254340
Source: | Samsung Electronics
Title: | Work plan for the CT3 aspects of application enablement for satellite access Phase 3
Agenda item: | 19.49
Document for: | Information

## Contributions Plan
Contribution Plan |  | In Progress | To be started | Completed
Spec | Topic | SA6 agreed CR(s) | Responsible Company | Service operation Impacts? | API definition Impacts? | Open API Impacts? | Related LS or other WG tdoc(s) # | CT3 meeting #; tdoc(s) # | Comments | Open issues
29.558 | EDGEAPP APIs specification; Stage 3 | [7 empty] | Approved WID - CP-243071 (97% complete)
Eecs_EESRegistration
| Satellite edge computing | S6-243732 | Ericsson | Y | Y | Y |  |  | EES Profile update. Will be covered as part of next row
| Service provisioning enhancement considering EES onboard | S6-244742, S6-251413 | Huawei, Samsung, Nokia | Y | Y | Y |  | C3-246381, C3-251516, C3-253518 | EES Profile updated.
29.549 | Service Enabler Architecture Layer for Verticals; Stage 3
Configuration Management Service
| Satellite access with discontinuous coverage (New API - SS_SCAIInfoRetrieval API) | S6-245688, S6-251049, S6-251049, S6-252533 | CATT | Y | Y | Y |  |  | CR proposes two new procedures to SEAL Configuration Management: 1. CT1: satellite coverage availability information provisioning triggered from CMS to CMC. 2. CT3: satellite coverage availability information request triggered from consumer(CMC, VAL Server) to CMS.
| Clause 5.1 update | [6 empty] | C3-253516
| Service Operation(s) | [6 empty] | C3-253516
| API Data model definition | [6 empty] | C3-253516
| Open API file | [6 empty] | C3-253516
NRM Server
| Support the satellite S&F operation (new NRM event) | S6-245689, S6-244730 | CATT | Y | Y | Y |  | C3-251517 | New API SS_SatelliteS&FInfoEvent API exposed from NRM server to VAL Server. Extended as SEAL event under SS_Events APIs
| Correct the S&F events to align with SA2 exposure | S6-252466 | CATT |  | Y | Y |  | C3-253161 | Estimated DL delivery time and Feeder link availability
ADAE Server
| UE RAT connectivity analytics for non terrestrial access (New Analytics Service) | S6-245596 | Samsung | Y | Y | Y |  |  | New Analytics: UE RAT connectivity analytics
| SS_ADAE_UE_RAT_connectivity_analytics API | S6-245596 | Samsung | Y | Y | Y |  |  | New Analytics: UE RAT connectivity analytics
| Clause 5.1 update | [6 empty] | C3-251519
| Service Operation(s) | [6 empty] | C3-251519, C3-253517
| API Data model definition | [6 empty] | C3-250466, C3-251080, C3-252081, C3-252082, C3-253517, C3-253519
| Open API file | [6 empty] | C3-252038, C3-253517
A-ADRF Server
| SS_AADRF_UE RAT connectivity analytics API (New ADRF Service) | S6-245596 | Samsung | Y | Y | Y |  |  | New ADRF service: UE RAT connectivity information
| Clause 5.1 update | [6 empty] | C3-252510
| Service Operation(s) | [6 empty] | C3-252510
| API Data model definition | [6 empty] | C3-252406
| Open API file | [6 empty] | C3-252407
29.548 | SEAL Data Delivery Services; Stage 3
| SEALDD enabled S&F transmission (New API) | S6-244741, S6-251450, S6-252462 | Huawei, Samsung, CATT | Y | Y | Y |  | C3-250465 | SEALDD enabled data transmission for S&F Satellite operation Merged into SDD_Transmission API
Target Completion - TSG CT#109 September 2025)

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments