## RIL_Tables
RIL Id | WI | Class | Title | Tdoc | Delegate | Misc | File version | Status | Rapporteur Conclusions
N031 | AIML | 1 | Circular definition of applicable AI/ML configuration | N/A | Jerediah Fevold |  | vnnn | ToDo
E050 | NR_SL_relay_multihop-Core | 1 | Wrong/inaccurate definition for Last U2N Relay UE |  | Ericsson - Min |  | V018 | ToDo
E031 | MIMO | 1 | CJT definition is missing |  | Ericsson (Lian) |  | V006 | PropAgree
H455 | NR_SL_relay_multihop-Core | 1 | Indication in the measurement report whether the candidate Relay UE is on a single-hop or multi-hop target path, or to provide the hop count information to avoid inter gNB path switch failures. |  | Huawei(Jagdeep) |  | V12 | Agreed
S054 | AIML | 1 | Interaction with NR-U |  | Aby K Abraham |  | v026 | ToDo
V200 | NTN | 1 | Having a valid version of SIB2 when the CONNECTED UE is configured with location information reporting for assisted SMTC configuration | Yes, R2-250xxxx | vivo (Stephen) |  | v005 | Rejected
V500 | NES | 1 | OD-SIB1 related text for reception of SI change or PWS notification |  | vivo(Jianhui) |  | V015 | PropReject
V201 | NTN | 1 | PDCCH repetition impacts on SI acquisition | Yes, R2-250xxxxx | vivo (Stephen) |  | v005 | Rejected
X203 | NES | 1 | Using NUL/SUL for OD-SIB1 request | R2-25xxxxx | Xiaomi (Haitao) |  | V003 | PropReject
C002 | NTN | 1 | Missed geographical area coordinates in procedure of SIB7 reception | N | CATT (Da Wang) |  | v008 | Agreed
Z451 | NR_SL_relay_multihop-Core | 1 | Single hop and multi-hop type differentiation |  | ZTE (Weiqiang Du) |  | V009 | Agreed
C181 | NES | 1 | Cell selection case is missing in section 5.2.2.4.2x Actions upon reception of SIBxx |  | Rui(CATT) |  | V008 | PropReject
C003 | NTN | 1 | clarify how UE determines the service area if the Target Service Area in the USD or the ISA in SIBXX are not totally aligned | Yes, R2-250xxxxx | CATT (Da Wang) |  | v008 | ToDo
J055 | NR_SL_relay_multihop-Core | 1 | Wasteful behaviour of an intermediate relay UE |  | Tsuboi (Sharp) |  | v019 | Rejected
O500 | NR_SL_relay_multihop-Core | 1 | Last relay UE monitors PO based on sl-PagingInfo-RemoteUE or sl-PagingInfo-RemoteUE-List | R2-25xxxxx | OPPO (Bingxue Leng) |  | V004 | Agreed
H450 | NR_SL_relay_multihop-Core | 1 | The action of intermediate Relay UE when performing as a remote UE |  | Huawei (Jagdeep) |  | V12 | Agreed
E047 | SONMDT | 1 | Issues when failedPCellId is same with ltm-RecoveryCellId |  | Ali Parichehreh |  | V013 | Agreed
J056 | NR_SL_relay_multihop-Core | 1 | Unify |  | Tsuboi (Sharp) |  | v019 | Agreed
N086 | NTN | 1 | Missing smtc5list in measConfig association to CG check | No | Nokia (Jakob) |  | v022 | Agreed
O501 | NR_SL_relay_multihop-Core | 1 | Unnecessary differtiation of First U2N Relay and Intermediate U2N Relay |  | OPPO (Bingxue Leng) |  | V004 | Agreed
J050 | MOB | 1 | Clarify an RRCReconfiguration can be triggered by Conditional LTM |  | Takaki(Sharp) |  | V018 | Rejected
C150 | MOB | 1 | Upon inter-CU MCG LTM execution, SN key update is also needed for the case that SN terminated bearer configured with MCG RLC leg only. |  | Rui(CATT) |  | V005 | Agreed
C051 | SONMDT | 1 | MCG LTM |  | Tangxun |  | V002 | Agreed
H002 | AIML | 1 | Retaining logged measurements during LTM | R2-25xxxx | Dawid |  | vnnn | Rejected
Q510 | AIML | 1 | csi-LogMeasAvailable in the RRCReconfigurationComplete | N/A | Rajeev Kumar |  | V018 | Rejected
N076 | AIML | 1 | Entries related to measurements |  | Nokia (Sakira Hassan) |  | V052 | ToDo
C052 | SONMDT | 1 | Duplicate successHO-InfoAvailable indication |  | Tangxun |  | V002 | Agreed
H300 | SONMDT | 1 | SHR indicator for LTM |  | Jun Chen |  | V004 | Rejected
E015 | SONMDT | 1 | Misalignment on the naming of the newly introduced UE capabilities with TS 38.306 | R2-25xxxx | Ali Parichehreh |  | V004 | Agreed
O600 | MOB | 1 | Unncessary condition for including the selectedSK-Counter in RRCReconfigurationComplete |  | OPPO (Xue Lin) |  | V013 | Rejected
S024 | NTN | 1 | UE optionally reports N closest reference locations via the RRCReconfigurationComplete message. | Yes, R2-250xxxxx | Samsung (Shiyang) |  | v011 | Agreed
H252 | NTN | 1 | Closest RL reporting in RRCConfigurationComplete | R2-25xxxxx | Huawei (Lili) |  | V014 | Agreed
N077 | AIML | 1 | Clarification required for serving cell for applicability reporting during HO |  | Nokia (Gyorgy Wolfner) |  | V052 | ToDo
Z012 | AIML | 1 | Applicability reporting triggered by applicability status change |  | Fei Dong |  | V040 | ToDo
H013 | AIML | 1 | Corrections for using applicabilityConfigToAddModList and applicabilitySetConfigCSI-ToAddModList in section 5.7.4.3 |  | Huawei(Dawid) |  | V046 | ToDo
H014 | AIML | 2 | Enabling of Option A applicability reporting |  | Huawei(Seau Sian) |  | V046 | ToDo
A104 | AIML | 1 | Simplification of procedure text on applicability reporting in Section 5.3.5.3/5.3.13.4/5.7.4.3 |  | Peng Cheng (Apple) |  | V024 | ToDo
S049 | AIML | 1 | Applicability reporting needs to consider RRCResumeComplete |  | Aby K Abraham |  | v026 | Agreed
V100 | AIML | 1 | Missing applicability status | - | Boubacar |  | V009 | Rejected
Z001 | AIML | 1 | Preference suggestion to the functionality that is reported as inapplicable in RRCReconfiguration | R2-25xxxx | Fei |  | V015 | Rejected
Z151 | MOB | 1 | Wrong removal of report configuration associated with L3 based CLTM upon reconfiguration with sync |  | ZTE (Mengjie Zhang) |  | V009 | Agreed
S050 | AIML | 1 | UAI retransmission after HO/CHO/LTM cell switch |  | Aby K Abraham |  | v026 | ToDo
Z152 | MOB, Sidelink | 1 | The coexistsnce of (C)LTM and sidelink |  | ZTE (Mengjie Zhang) |  | V009 | Rejected
Z153 | MOB, QoE | 1 | The coexistsnce of (C)LTM and QoE |  | ZTE (Mengjie Zhang) |  | V009 | Rejected
Z154 | MOB, MBS | 1 | The coexistsnce of (C)LTM and MBS |  | ZTE (Mengjie Zhang) |  | V009 | Rejected
C151 | MOB | 1 | It is not clear on whether the UE should stop the LTM conditions evaluation based on L1 measurements and/or based on L3 measurements. |  | Rui(CATT) |  | V005 | Agreed
O502 | NR_SL_relay_multihop-Core | 1 | Clarification on the relationship between L2 U2N Relay UE and L2 Last U2N Relay UE |  | OPPO (Bingxue Leng) |  | V004 | Agreed
V000 | LPWUS | 1 | lpwus-OffsetPreferenceConfig should be captured as per cell group configuration |  | Vivo(Chenli) |  | V005 | Agreed
H250 | NTN | 1 | Descriptions of UAI | R2-25xxxxx | Huawei (Lili) |  | V006 | Agreed
V202 | NTN | 1 | Reference to 5.3.5.3 | N | vivo (Stephen) |  | v005 | Agreed
N081 | NTN | 1 | Considerations on no UE requirements for GNSS | Yes, R2-25xxxxx | Nokia (Jakob) |  | v016 | Rejected
C072 | AIML | 1 | “UE-side data collection” wording |  | Tangxun |  | V003 | Agreed
B200 | AIML | 1 | Missing of crossing reference to 5.7.4 |  | Congchi Zhang |  | V011 | Rejected
J051 | MOB | 1 | Wrong IE name |  | Takaki(Sharp) |  | V018 | Agreed
J011 | NR_SL_relay_multihop-Core | 1 | Add intermedia relay UE behavior for SRB1 in Remote UE Addition procedure |  | Sharp (LIU Lei) |  | V006 | Rejected
C152 | MOB | 1 | Ambiguity on whether the IE ltm-Config can be the one included in the RRCReconfiguration message contained in nr-SCG . |  | Rui(CATT) |  | V005 | Rejected
Z155 | MOB | 1 | The missing description for VarLTM-ServingCellNoSecurityChange |  | ZTE (Mengjie Zhang) |  | V009 | Agreed
Z156 | MOB | 1 | The handling order of the IEs in the received LTM-Config |  | ZTE (Mengjie Zhang) |  | V009 | Agreed
Z166 | MOB | 1 | Clarification on ltm-ServingCellExecutionCondition set to release |  | ZTE (Mengjie Zhang) |  | V015 | PropAgree
X150 | MOB | 1 | Avoid stop CLTM evaluation for new configured CLTM conditions. | R2-25xxxxx | Xiaomi (Yi Xiong) |  | V006 | Agreed
C153 | MOB | 1 | UE should stop the corresponding LTM conditions evaluation before release the ltm-ServingCellExecutionCondition. |  | Rui(CATT) |  | V005 | Agreed
X157 | MOB | 1 | Correction on LTM conditions modification based on ltm-ExecutionCondition in LTM-Candidate |  | Xiaomi (Yi Xiong) |  | V049 | Duplicate | I think is already solved if we agree on Z166, which addresses the same issue.
E061 | MOB | 2 | Support of LTM modification | R2-250xxxx | Ericsson (Tony) |  | V041 | ToDo | Let's discuss this issue via a tdoc.
X151 | MOB | 1 | Correction on conditional LTM cell switch execution for only one triggered LTM candidate configuration | R2-25xxxxx | Xiaomi (Yi Xiong) |  | V006 | Agreed
M200 | MOB | 1 | Ambiguity in handling of LTM UE variables in LTM cell switch |  | Pasi (MediaTek) |  | V008 | Agreed
Z157 | MOB | 1 | The release of the current SCG configuration in case of MCG LTM with SCG configuration |  | ZTE (Mengjie Zhang) |  | V009 | Agreed
J052 | MOB | 1 | Ambiguity on selecting a sk-Conter |  | Takaki(Sharp) |  | V018 | Rejected
C154 | MOB | 1 | Ambiguity on removing the the selected sk-Counter value from which entry in ltm-SK-Counters. |  | Rui(CATT) |  | V005 | Rejected
M201 | MOB | 1 | PDCP data recovery at the end of LTM cell switch |  | Pasi (MediaTek) |  | V008 | Rejected
C166 | MOB | 1 | The determination of the the selected cell for the LTM cell switch execution should be done in 5.3.5.18.8(LTM cell switch conditions evaluation based on L3 measurements) instead of in 5.3.5.18.6(LTM cell switch execution) |  | Rui(CATT) |  | V026 | PropReject | I honestly think that there is no issue about the timing. This is a UE internal process and I don't think current text causes any delay.
O602 | MOB | 1 | Compression continuation during inter-CU LTM |  | OPPO (Xue Lin) |  | V044 | PropReject | In LTM there is the reconfiguration with sync procedure, and we don’t use the full configuration flag, so I don’t see any issue with the current text. We can rely on network to set these flags properly
C167 | MOB | 1 | PDCP data recovery should not be performed for all the AM DRBs which is part of the current UE configuration |  | Rui(CATT) |  | V026 | PropAgree
C155 | MOB | 1 | Upon LTM execution, UE behaivor is missing on performing PDCP discard for SRBs according to the Rel-19 ID. |  | Rui(CATT) |  | V005 | Agreed
E055 | MOB | 1 | Using existing PDCP discard flag for SRBs |  | Tony (Ericsson) |  | V009 | ToDo
C156 | MOB | 1 | Duplicated check for the different R19 ID case |  | Rui(CATT) |  | V005 | Agreed
X152 | MOB | 1 | UE behaviours when ltm-NoSecurityChangeID = ltm-ServingCellNoSecurityChangeID is missing. | R2-25xxxxx | Xiaomi (Yi Xiong) |  | V006 | Agreed
X153 | MOB | 1 | Incorrect UE behaviours when the value of ltm-NoResetID is equal to the value of ltm-ServingCellNoResetID. | R2-25xxxxx | Xiaomi (Yi Xiong) |  | V006 | Agreed
X154 | MOB | 1 | Incorrect accordance section of the selected cell for CLTM |  | Xiaomi (Yi Xiong) |  | V006 | Agreed
E005 | MOB | 2 | Handling of radio bearers during LTM cell switch | R2-25xxxxx | Tony (Ericsson) |  | V004 | Agreed
X156 | MOB | 1 | Correction on the execution of SCG LTM |  | Xiaomi (Yi Xiong) |  | V049 | PropAgree | I agree with the change, but I guess that this change should start from Rel-18, right? Maybe something we need to check.
X155 | MOB | 1 | Perform the subsequent CLTM evaluation after LTM Cell switch triggered based on the indication from lower layers. | R2-25xxxxx | Xiaomi (Yi Xiong) |  | V006 | Rejected
Z167 | MOB | 1 | Clarification on stopping LTM cell switch conditions evaluation in LTM cell switch execution conditions modification procedure |  | ZTE (Mengjie Zhang) |  | V015 | PropAgree | Between the two TP I prefer the version from Huawei as is more aligned with what we have now. So my proposal is to go with that and my proposal to mark this PropAgree anyway
M205 | MOB | 1 | Condition related to UE variable VarLTM-ExecutionConditionList |  | Pasi (MediaTek) |  | V047 | PropAgree | Probably that text will me impacted by Z167 but I think is correct to use such terminology. So will use it if we have more occasions where we check if that variable is not empty.
J053 | MOB | 1 | Ambiguity on replaceing a sk-ConterList |  | Takaki(Sharp) |  | V018 | Rejected
Z158 | MOB | 1 | The wrong IE name |  | ZTE (Mengjie Zhang) |  | V009 | Agreed
Q511 | AIML | 1 | Release CSI-LoggedMeasurementConfig in RRC Re-establishment | N/A | Rajeev Kumar |  | V018 | Rejected
Z159 | MOB | 1 | Removing the wrong reference clause |  | ZTE (Mengjie Zhang) |  | V009 | Agreed
E051 | SONMDT | 1 | Remove editor’s note on logging of ltm-RecoveryCellId |  | Ali Parichehreh |  |  | Agreed
Q512 | AIML | 1 | Release CSI-LoggedMeasurementConfig following cell selection while T311 is running | N/A | Rajeev Kumar |  | V018 | Rejected
C073 | AIML | 1 | CSI logged measurement configuration |  | Tangxun |  | V003 | Agreed
S042 | AIML | 1 | Release of NSDC configuration upon transition to RRC_INACTIVE |  | Seung-Beom |  | v026 | ToDo
C074 | AIML | 1 | Duplicate release/discard UE behaviour |  | Tangxun |  | V003 | ToDo
J057 | NR_SL_relay_multihop-Core | 1 | L3 multi-hop relay behaviour is restricted. |  | Tsuboi (Sharp) |  | v019 | Agreed
H312 | SONMDT | 0 | Some editorial issues |  | Jun Chen |  | V007 | Agreed
Z301 | SONMDT | 1 | Alignment on terms of CHO with candidate SCG(s). | R2-25xxxx | QI Tao |  | V012 | Agreed
C053 | SONMDT | 1 | PSCell may not be available when RLF happens |  | Tangxun |  | V002 | Agreed
Z302 | SONMDT | 1 | Unnecessary reference | R2-25xxxx | QI Tao |  | V012 | Agreed
X550 | SONMDT | 1 | Incomplete procedure text |  | Xiaomi (Shuai) |  | V001 | Rejected
H301 | SONMDT | 1 | CHO trigger condition |  | Jun Chen |  | V004 | Rejected
N041, N042 | SONMDT | 1 | RLF-Report for conditional handover with time-based or location-based trigger condition |  | Nokia (Mani) |  | V005 | Rejected
J031 | SONMDT | 1 | Place distanceFromReference1 after cho-config |  | Chang Ningjuan |  | V008 | Agreed
Z303 | SONMDT | 1 | The timing to record the distance information and also the usage of puncturation marks (comma and semicolon) | R2-25xxxx | QI Tao |  | V012 | Agreed
C054 | SONMDT | 1 | Duplicate condition |  | Tangxun |  | V002 | Agreed
H313 | SONMDT | 0 | Missing a space in CHO with candidate SCG |  | Jun Chen |  | V007 | Agreed
J033 | SONMDT | 1 | Neighbour cell identity when measurement quantity is not available in RLF report |  | Chang Ningjuan |  | V008 | Agreed
C055 | SONMDT | 1 | Time based CHO is not relevant |  | Tangxun |  | V002 | Rejected
C056 | SONMDT | 1 | UE capability check is missing |  | Tangxun |  | V002 | Agreed
Z304 | SONMDT | 1 | All “cpc” should also include the case of “cpa” | R2-25xxxx | QI Tao |  | V012 | Agreed
J034 | SONMDT | 1 | Naming of timeBetweenLastFulfillmentAndEvent-r19 |  | Chang Ningjuan |  | V008 | Agreed
N064 | SONMDT | 1 | RLF, SHR logging when CHO only HO is performed | R2-250nnnn | Gyorgy Wolfner |  | V011 | Rejected
J030 | SONMDT | 1 | Condition for fulfilledConfigWhenChoOnly |  | Chang Ningjuan |  | V008 | Agreed
Z305 | SONMDT | 1 | Which condRRCReconfig should be more specific. | R2-25xxxx | QI Tao |  | V012 | ToDo
E016 | SONMDT | 1 | Conditions to log the L1 RSRP in RLF report |  | Ali Parichehreh |  | V004 | Agreed
E017 | SONMDT | 1 | Incorrect condition check to decide lastHO-Type |  | Ali Parichehreh |  | V004 | Agreed
Z003 | AIML | 1 | The UE behaviour for NW side data collection configuration when going to RRC-Idle. |  | Fei |  | V015 | Agreed
Z452 | NR_SL_relay_multihop-Core | 1 | RRC connection setup/resume initiation | R2-25xxxxx | ZTE (Weiqiang Du) |  | V009 | Agreed
E037 | LPWUS | 1 | Clarify when the UE is allowed to use LR-RSRP instead of RSRP | R2-25xxx | Ericsson (Martin) |  | V006 | Rejected
H056 | LPWUS | 1 | Missing “release lpwus-OffsetPreferenceConfig, if configured, and stop timer T346xx, if running;” from Section 5.3.7.3 | R2-25xxxxx | Rama Kumar Mopidevi (Huawei) |  | V010 | Agreed
H057 | LPWUS | 1 | Merge sentence “stop timer T346xx, if running” with “release lpwus-OffsetPreferenceConfig from the UE Inactive AS context, if stored” | R2-25xxxxx | Rama Kumar Mopidevi (Huawei) |  | V010 | Rejected
J001 | NES | 1 | Align smtc between MCG and SCG |  | Sharp (LIU Lei) |  | V006 | ToDo
C009 | NTN | 1 | clarify how UE determines the periodicity of smtc5list in MO | Yes, R2-250xxxxx | CATT (Da Wang) |  | v019 | Agreed
X200 | NES | 1 | SMTC handling for OD-SSB | R2-25xxxxx | Xiaomi (Li Zhao) |  | V003 | ToDo
L201 | NES | 1 | SMTC configuration for OD-SSB |  | LGE (Han Cha) |  | V016 | PropReject
A103 | NES | 1 | Simplification/polishment of SMTC handling for OD-SSB and SSB adaptation | Yes | Apple (Peng Cheng) |  | V030 | ToDo
N001 | NES | 1 | Smtcy and smtcx description sseems to differ unnecessarily much. |  | Jarkko Koskela(Nokia) |  | V009 | ToDo
L202 | NES | 1 | SMTC configuration for adapted SSB |  | LGE (Han Cha) |  | V016 | PropReject
X201 | NES | 1 | Serving cell MO handling for OD-SSB | R2-25xxxxx | Xiaomi (Li Zhao) |  | V003 | ToDo
S029 | NES | 2 | neighbor cell measurements | R2-25xxxxx | Anil Agiwal (Samsung) |  | V027 | PropReject
Z101 | NES | 1 | Clarification on the description of servingCellMO-OD |  | ZTE (Gao Yuan) |  | V028 | ToDo
H131 | NES | 1 | Serving cell measurements based on legacy servingCellMO/ new servingCellMO-OD | R2-25xxxxx | Huawei (Lili) |  | V035
Z102 | NES | 1 | Clarification on the description of rsType |  | ZTE (Gao Yuan) |  | V028 | ToDo
V101 | AIML | 1 | Change to “configuration” to “entry” |  | Boubacar |  | V009 | Agreed
V102 | AIML | 1 | Change “threshold” to “aboveThreshold” |  | Boubacar |  | V009 | Duplicate
V103 | AIML | 1 | Change “configuration” to “entry” |  | Boubacar |  | V009 | Agreed
H011 | AIML | 1 | Event A1 and event A2 description corrections |  | Huawei(Dawid) |  | V046 | ToDo
N032 | AIML | 1 | Incorrect mapping of thresh in Section 5.5.4.2 and 5.5.4.3, Event A1 and Event A2, respectively, to the threshold in csi-LoggedMeasurementEventTriggerConfig | N/A | Jerediah Fevold |  | vnnn | Rejected
V104 | AIML | 1 | Change “threshold ” to “belowThreshold” |  | Boubacar |  | V009 | Duplicate
H007 | AIML | 1 | Logged measurement configuration modification and release | R2-25xxxx | Dawid |  | vnnn | Rejected
Z004 | AIML | Class 1 | The timing point of logging the cell Id and configuration Id for the data collection | R2-25xxxx | Fei |  | V015 | Agreed
C075 | AIML | 1 | ARFCN and PCI |  | Tangxun |  | V003 | Agreed
H009 | AIML | 1 | Interactions with PHY for NW-side data collection | R2-25xxxx | Dawid |  | V017 | ToDo
H012 | AIML | 1 | Corrections for using csi-LoggedMeasurementConfigToAddModList in section 5.5a.3.2 |  | Huawei(Dawid) |  | V046 | ToDo
B201 | AIML | 1 | Terminlogy buffer vs. memory |  | Congchi Zhang |  | V011 | Agreed
Z005 | AIML | Class 1 | Start/stop performing L1 measurement in Logged NW side data collection | R2-25xxxx | Fei |  | V015 | ToDo
S043 | AIML | 1 | Correction on NSDC resource measurement and logging |  | Seung-Beom |  | v026 | Agreed
Z011 | AIML | 1 | The scenario where TimeGap indication presence |  | Fei |  | v027 | Rejected
L002 | AIML | 1 | Redundancy in Buffer Full Handling for CSI Logged Measurement |  | Soo Kim |  | V020 | ToDo
O500 | NR_SL_relay_multihop-Core | 1 | How to set indication in the measurement report to indicate the hop status of the candidate relay UE | R2-25xxxxx | OPPO (Bingxue Leng) |  | V044 | ToDo
X551 | SONMDT | 1 | Incomplete procedure text |  | Xiaomi (Shuai) |  | V001 | Rejected
E046 | SONMDT | 1 | Missing UE capability check |  | Ali Parichehreh |  | V013 | Agreed
H302 | SONMDT | 1 | Logged MDT for NTN |  | Jun Chen |  | V004 | Rejected
S019 | SONMDT | 1 | (Pre)Condition for logging NSAG information need to be updated. |  | Samsung (Aby) |  | V006 | Agreed
S020 | SONMDT | 1 | “highest priority” is not clear | R2-25xxxx | Samsung (Aby) |  | V006 | Rejected
X552 | SONMDT | 1 | Incomplete procedure text and field description |  | Xiaomi (Shuai) |  | V001 | Agreed
C057 | SONMDT | 1 | reselectedCellId doesn’t exist in any cell selection state | R2-25xxxx | Tangxun |  | V002 | Rejected
S021 | SONMDT | 1 | Logging of reselectid | R2-25xxxx | Samsung (Aby) |  | V006 | Rejected
Z306 | SONMDT | 0 | Extra space. | R2-25xxxx | QI Tao |  | V012 | Agreed
S018 | SONMDT | 1 | Logging PCell and PSCell in SCGFailureInformation |  | Samsung (Aby) |  | V006 | Agreed
C058 | SONMDT | 1 | SCG RLF | R2-25xxxx | Tangxun |  | V002 | Agreed
E048 | SONMDT | 1 | MRO for subsequenct CPAC |  | Ali Parichehreh |  | V013 | Agreed
C059 | SONMDT | 1 | CPC execution |  | Tangxun |  | V002 | Agreed
Z251 | NTN | 1 | Descriptions of UAI | No | ZTE (Zhihong) |  | v012 | Duplicate H250
X001 | AIML | 1 | Applicability report via UAI |  | Xing |  | V012 | Agreed
B202 | AIML | 1 | Trigger UAI upon applicability change since last report |  | Congchi Zhang |  | V011 | Rejected
Z014 | AIML | 1 | UAI initiation for applicability reporting |  | Fei Dong |  | V040 | ToDo
E039 | AIML | 1 | Update UAI procedural text for UE-side data collection in 5.7.4.2 to match corresponding capability |  | Ericsson (Andra) |  | V022 | ToDo
X002 | AIML | 1 | UAI trigger |  | Xing |  | V012 | Agreed
C005 | NTN | 1 | Clarify the meaning of “can” in the following agreement: - The UE reports an indication of the N closest reference locations via UE assistance information, e.g. bitmap or list of indices of the locations. - The UE can report the N closest reference locations via the RRCReconfigurationComplete message. | Yes, R2-250xxxxx | CATT (Da Wang) |  | v008 | Duplicate S024
Z252 | NTN | 1 | Triggering condition for reference location report in UAI | Yes, R2-250xxxxx | ZTE (Zhihong) |  | v012 | Duplicate S024
N082 | NTN | 1 | Considerations on no UE requirements for GNSS | Yes, R2-25xxxxx | Nokia (Jakob) |  | v016 | Rejected
S038 | XR | 1 | Checking T346o running status |  | Vinay (Samsung) |  | V07 | PropRej
N091 | XR | 1 | UAI for measurement gap cancellation preference | R2-25xxxxx | Chunli WU (Nokia) |  | V04 | ToDo
E009 | LPWUS | 1 | Empty UAI message for LP-WUS time offset (RRC-5, MAX-X3) |  | Ericsson (Martin) |  | V002 | Agreed
S048 | AIML | 1 | UAI initiation |  | Youn Heo |  | v026 | Agreed
Z017 | AIML | 1 | UAI initiation for UE side data collection |  | Fei Dong |  | v040 | ToDo
S025 | NTN | 1 | UE first time reports N closest reference locations using UAI. | Yes, R2-250xxxxx | Samsung (Shiyang) |  | v011 | Agreed
N034 | AIML | 2 | Incorrect field referenced in applicability reporting procedure | N/A | Jerediah Fevold |  | vnnn | Agreed
O300 | AIML | 1 | Incomplete applicability info may be transferred during HO | R2-25xxxx | OPPO(Jiangsheng Fan) |  | V23 | Rejected
C076 | AIML | 1 | Wrong field name |  | Tangxun |  | V003 | Duplicate
C077 | AIML | 1 | Undefined applicabilityReportConfigId |  | Tangxun |  | V003 | Agreed
Z002 | AIML | 1 | Preference suggestion to the functionality that is reported as inapplicable in UAI | R2-25xxxx | Fei |  | V015 | Rejected
S045 | AIML | 2 | Correction on dataCollectionSart | R2-25xxxx | Seung-Beom |  | v026 | Rejected
X003 | AIML | 1 | Remove the dataCollectionStart | R2-25xxx | Xing |  | V012 | Rejected
E040 | AIML | 2 | Ensure that UE does not request a candidate UE-side data collection configuration for which it already has a UE-side data collection configuration | R2-25xxxx | Ericsson (Andra) |  | V022 | Rejected
Z013 | AIML | 1 | Lower power state indication and full buffer indication |  | Fei Dong |  | V040 | ToDo
N084 | NTN | 1 | Determining the number of locations to report | No | Nokia (Jakob) |  | v016 | Rejected
N061 | SONMDT | 1 | timeSinceSHR missing in SHR for intra-NR mobility and timeSinceSPR not existing in SPR |  | Gyorgy Wolfner |  | V011 | Rejected
N033 | AIML | 2 | NW-side DC log request should not be datatype specific. | N/A | Jerediah Fevold |  | vnnn | ToDo
S044 | AIML | 1 | Correction on inclusion of NSDC data | R2-25xxxx | Seung-Beom |  | v026 | Rejected
J008 | AIML | 1 | Setting csi-LogMeasInfoList in UEInformationResponse | R2-25xxxx | Sharp (LIU Lei) |  | V009 | Rejected
J009 | AIML | 1 | Discard entries in csi-LogMeasInfoCellList after sending UEInformationResponse | R2-25xxxx | Sharp (LIU Lei) |  | V009 | Agreed
V105 | AIML | 1 | Logged measurement entries included in the csi-LogMeasInfoList |  | Boubacar |  | V009 | Rejected
E020 | SONMDT | 1 | SHR report to both HO and LTM |  | Ali Parichehreh |  | V004 | Agreed
E028 | SONMDT | 1 | Simplifying the if condition to check if the UE was configured with CHO with candidate SCG configuration |  | Ali Parichehreh |  | V004 | Agreed
S022 | SONMDT | 1 | Clarify as MCG LTM in SHR |  | Samsung (Aby) |  | V006 | Agreed
C060 | SONMDT | 1 | Not a R19 change | R2-25xxxx | Tangxun |  | V002 | Rejected
E019 | SONMDT | 1 | Logging L1 measurements for LTM candidate cells in RLF report |  | Ali Parichehreh |  | V009 | Agreed
J032 | SONMDT | 1 | L1 measurement result for neighbour cells in SHR |  | Chang Ningjuan |  | V008 | Rejected
N062 | SONMDT | 1 | Simplification of SHR determation section for CHO with candidate SCGs |  | Gyorgy Wolfner |  | V011 | Rejected
N063 | SONMDT | 1 | Simplification of SPR determation section for CHO with candidate SCGs |  | Gyorgy Wolfner |  | V011 | Rejected
N065 | SONMDT | 1 | SHR logging when CHO only HO is performed | R2-250nnnn | Gyorgy Wolfner |  | V011 | Rejected
Z453 | NR_SL_relay_multihop-Core | 1 | SUI initiation for MH |  | ZTE (Weiqiang Du) |  | V009 | Agreed
O503 | NR_SL_relay_multihop-Core | 1 | SUI initiation for discovery transmission resource requesting | R2-25xxxxx | OPPO (Bingxue Leng) |  | V004 | Agreed
X500 | SLRelay | 1 | U2N Relay UE needs clarification |  | Xiaomi (Shuai) |  | V005 | Duplicate with O503
Z454 | NR_SL_relay_multihop-Core | 1 | Source L2 ID report | R2-25xxxxx | ZTE (Weiqiang Du) |  | V009 | Agreed
Z456 | NR_SL_relay_multihop-Core | 1 | UE type in SUI message | R2-25xxxxx | ZTE (Weiqiang Du) |  | V009 | Rejected
W500 | NR_SL_relay_multihop-Core |  | SUI enhancement for Intermediate Relay UE | R2-xxxxxxx | NEC(Boyuan Zhang) |  | V13 | To Do
W501 | NR_SL_relay_multihop-Core |  | SUI enhancement for Intermediate Relay UE | R2-xxxxxxx | NEC(Boyuan Zhang) |  | V13 | ToDo
Z455 | NR_SL_relay_multihop-Core | 1 | Paging ID report | R2-25xxxxx | ZTE (Weiqiang Du) |  | V009 | Agreed
K001 | NR_SL_relay_multihop-Core | 1 | PC5 Relay RLC channel release by Intermediate U2N Relay UE |  | ASUSTeK (Richard Kuo) |  | V007 | Rejected
A500 | SLRelay | 1 | Clarificaiton of SIB, PosSIB, and Paging triggering conditions |  | Apple (Zhibin Wu) |  | V015 | Agreed
X501 | SLRelay | 1 | SI request determination |  | Xiaomi (Xing Yang) |  | V005 | Duplicate A500
J058 | NR_SL_relay_multihop-Core | 1 | Missing sl-PagingInfo-RemoteUE-List |  | Tsuboi (Sharp) |  | v019 | Agreed
X502 | SLRelay | 1 | Definition of Paging information is not clear |  | Xiaomi (Shuai) |  | V005 | Rejected
K003 | NR_SL_relay_multihop-Core | 1 | Release of sl-PagingInfo-RemoteUE-List |  | ASUSTeK (Richard Kuo) |  | V007 | Rejected
K004 | NR_SL_relay_multihop-Core | 1 | Behavior of Intermediate U2N Relay UE in response to reception of RemoteUEInformationSidelink |  | ASUSTeK (Richard Kuo) |  | V007 | Rejected
J059 | NR_SL_relay_multihop-Core | 1 | Missing sl-PagingInfo-RemoteUE-List |  | Tsuboi (Sharp) |  | v019 | Agreed
Z457 | NR_SL_relay_multihop-Core | 1 | Paging info list reception handling |  | ZTE (Weiqiang Du) |  | V009 | Agreed
J060 | NR_SL_relay_multihop-Core | 2 | The issue on signalling overhead for releasing paging information. |  | Tsuboi (Sharp) |  | v019 | Rejected
H451 | NR_SL_relay_multihop-Core | 1 | SIB/paging request information release at the relay UE when the connected child UE triggers the PC5 link release. |  | Huawei (Jagdeep) |  | V12 | Duplicate A500
O504 | NR_SL_relay_multihop-Core | 1 | For Intermediate relay UE, the Paging/SIB associated with the downstream remote UEs may comes from Parent instead of the network | R2-25xxxxx | OPPO (Bingxue Leng) |  | V004 | Agreed
O505 | NR_SL_relay_multihop-Core | 1 | Whether sl-PagingDelivery in multi-hop case needs to be a list for multipe child UEs | R2-25xxxxx | OPPO (Bingxue Leng) |  | V004 | Rejected
E029 | NR_SL_relay_multihop-Core | 1 | Unclear text on Reception of the UuMessageTransferSidelink by the L2 Intermediate U2N Relay UE |  | Ericsson - Min |  | V009 | Agreed
X503 | SLRelay | 1 | Figure needs to be revised |  | Xiaomi (Shuai) |  | V005 | Agreed
J061 | NR_SL_relay_multihop-Core | 1 | Avoid Using ‘Connected Child UE’ to Prevent Confusion |  | Tsuboi (Sharp) |  | V019 | Rejected
O506 | NR_SL_relay_multihop-Core | 1 | Notification trigger at the Intermediate Relay UE | R2-25xxxxx | OPPO (Bingxue Leng) |  | V004 | Rejected
B100 | NR_SL_relay_multihop-Core | 1 | One agreed case for intermediate relay in idle/inactive is missing | R2-25xxxxx | Lenovo (Lianhai Wu) |  | V011 | Agreed
B101 | NR_SL_relay_multihop-Core | 1 | Intermediate relay in connected state transmits notification message after receiving release message | R2-25xxxxx | Lenovo (Lianhai Wu) |  | V011 | Agreed
B102 | NR_SL_relay_multihop-Core | 1 | The intermediate relay UE is triggered to transmit notification messaage due to connection failure | R2-25xxxxx | Lenovo (Lianhai Wu) |  | V011 | Agreed
O507 | NR_SL_relay_multihop-Core | 1 | Missing Notification trigger at the intermediate relay UE | R2-25xxxxx | OPPO (Bingxue Leng) |  | V004 | Duplicate B100/101
X504 | SLRelay | 1 | Missed words |  | Xiaomi (Shuai) |  | V005 | Agreed
H454 | NR_SL_relay_multihop-Core | 1 | Whether the intermediate relay UE in RRC_IDLE/INACTIVE can omit sending the notification message should be limited to the case where the hop count does not exceed the maximum permited value. |  | Huawei(Jagdeep) |  | V12 | Rejected
K005 | NR_SL_relay_multihop-Core | 1 | Behavior of Intermediate U2N Relay UE in response to reception of NotificationMessageSidelink |  | ASUSTeK (Richard Kuo) |  | V007 | Rejected
O508 | NR_SL_relay_multihop-Core | 1 | Discovery transmission condition | R2-25xxxxx | OPPO (Bingxue Leng) |  | V004 | Agreed
Z459 | NR_SL_relay_multihop-Core | 1 | Prioritization between last relay UE and intermediate relay UE | R2-25xxxxx | ZTE (Weiqiang Du) |  | V009 | Rejected
H452 | NR_SL_relay_multihop-Core | 1 | The condition of discovery transmission |  | Huawei (Jagdeep) |  | V12 | Rejected
H457 | NR_SL_relay_multihop-Core | 1 | Stop condition of discovery transmission due to Overload |  | Huawei (Jagdeep) |  | V64 | ToDo
E044 | NR_SL_relay_multihop-Core | 1 | The capturing of the note is not aligned with RAN2 agreements |  | Ericsson - Min |  | V012 | Agreed
E046 | NR_SL_relay_multihop-Core | 1 | relayUE-RRCState is referred nowhere |  | Ericsson - Min |  | V012 | Agreed
E019 | SONMDT | 1 | Incomplete parameter |  | Ali Parichehreh |  | V004 | Agreed
O509 | NR_SL_relay_multihop-Core | 1 | No Discovery Solicitation Response message type |  | OPPO (Bingxue Leng) |  | V004 | Agreed
Z458 | NR_SL_relay_multihop-Core | 1 | Upper bound for intermediate relay UE |  | ZTE (Weiqiang Du) |  | V009 | Rejected
E011 | NTN | 1 | Establishment/Release of MRBs following the ISA |  | Ericsson (Ignacio) |  | v001 | ToDo
E014 | NTN | 1 | Clarificatory NOTE for the use of ISA in both SIB and USD to establish MRBs |  | Ericsson (Ignacio) |  | v001 | Agreed
Z253 | NTN | 2 | Add SIBxx as on demand SI in DedicatedSIBRequest | No | ZTE (Zhihong) |  | v012 | Agreed
X553 | SONMDT | 1 | Incomplete field description |  | Xiaomi (Shuai) |  | V001 | Agreed
E021 | SONMDT | 1 | Missing or wrong release version within AreaConfigurationNTN and MeasResult3NR |  | Ali Parichehreh |  | V004 | Agreed
X554 | SONMDT | 1 | Incomplete field description |  | Xiaomi (Shuai) |  | V001 | Rejected
N043 | SONMDT | 2 | Value range for distanceRadius-r19 in AreaConfigurationNTN-r19 |  | Nokia (Mani) |  | V005 | Agreed
H303 | SONMDT | 1 | NTN deployment |  | Jun Chen |  | V004 | Rejected
H304 | SONMDT | 1 | areaConfigurationNTN-List |  | Jun Chen |  | V004 | Agreed
C071 | AIML | 2 | Cond Sync |  | Tangxun |  | V003 | Agreed
O510 | NR_SL_relay_multihop-Core | 1 | Clarification on how to understand the Paging message included in dedicatedPagingDelivery | R2-25xxxxx | OPPO (Bingxue Leng) |  | V004 | Agreed
Z254 | NTN | 1 | Missing on demand SIBXX in dedicatedSystemInformationDelivery | No | ZTE (Zhihong) |  | v012 | Agreed
Z160 | MOB | 1 | Clarification on the sk-counter contained in the ltm-CandidateConfig for SCG LTM |  | ZTE (Mengjie Zhang) |  | V009 | Agreed
N024 | AIML | 1 | NW-side buffer is implied to be datatype specific but it is supposed to be general. | N/A | Jerediah Fevold |  | vnnn | ToDo
V208 | NTN | 2 | Confirm that bitmap is used for UE reference location report | Yes, R2-250xxxx | vivo (Stephen) |  | v007 | Agreed
Z006 | AIML | Class 1 | The field description of applicabilityReportList in RRCReconfigurationComplete |  | Fei |  | V015 | ToDo
S058 | TEI19 (NR_TN_NTN_redir) | 1 | SMTC handling for NR TN to NR NTN redirection | R2-2507289 | Jonas (Samsung) | Related to LTE RIL X500 | V001 | ToDo
Z161 | MOB | 1 | Clarification on the selectedSK-Counter for SCG LTM |  | ZTE (Mengjie Zhang) |  | V009 | Agreed
E010 | NTN | 2 | Add possibility for referenceLocationReport in the RRCResumeComplete message | R2-25xxxxx | Ericsson (Philipp) |  | v001 | ToDo
H305 | SONMDT | 1 | subsequent CPC |  | Jun Chen |  | V004 | Rejected
H050 | LPWUS | 1 | UAI for disabling LP-WUS | R2-25xxxxx | Kuang Yiru (Huawei) |  | V003 | ToDo
N071 | AIML | 1 | Field applicabilityReportList description missing |  | Sakira Hassan |  | V015 | Agreed
X251 | NTN | 2 | Providing the closest reference location in a list instead of bitmap | R2-25XXXX | Xiaomi (Xiaowei Jiang) |  | v010 | Duplicate V208
S045 | AIML | 2 | Correction on dataCollectionSart | R2-25xxxx | Seung-Beom |  | v026 | Rejected
O301 | AIML | 2 | Missing purpose for UE-side data collection request | R2-250x | OPPO(Jiangsheng Fan) |  | V23 | Rejected
A105 | AIML | 1 | Separate monitoring configuration for beam management and CSI prediction | R2-25xxxx | Peng Cheng (Apple) |  | V024 | Agreed
N114 | AIML | 2 | Remove dataCollectionStart and dataCollectionStopConfigurationList | R2-2507181 | Jerediah Fevold |  | v030 | Rejected
N115 | AIML | 2 | Remove a level of hierarchy from DataCollectionPreference-r19 | R2-2507181 | Jerediah Fevold |  | v030 | ToDo
O700 | LPWUS | 1 | The preference LP-WUS offset |  | Haocheng Wang (OPPO) |  | V007 | Agreed
C031 | LPWUS | 2 | Empty UAI report for LP-WUS time offset | R2-25xxxxx | Da Wang (CATT) |  | V014 | Duplicate
C028 | LPWUS | 1 | UAI reporting for UE’s preferred time offset for LP-WUS monitoring | No | Da Wang (CATT) |  | V012 | Agreed
W201 | LPWUS | 1 | UAI report for LP-WUS time offset | R2-25xxxxx | Rao Shi (NEC) |  | V015 | Rejected
O701 | LPWUS | 1 | Whether UE can send report an empty preference offset is still FFS. | R2-25xxxxx | Haocheng Wang (OPPO) |  | V007 | Rejected
N025 | AIML | 1 | NW-side buffer is implied to be datatype specific but it is supposed to be general. | N/A | Jerediah Fevold |  | vnnn | ToDo
Z007 | AIML | Class 1 | The field description of CSI-LogMeasReportReq | R2-25xxxx | Fei |  | V017 | ToDo
N026 | AIML | 2 | NW-side buffer is implied to be datatype specific but it is supposed to be general. | N/A | Jerediah Fevold |  | vnnn | ToDo
Z008 | AIML | Class 2 | Size optimization for measurement result list for logged data reporting |  | Fei |  | V017 | Agreed
S046 | AIML | 2 | Content of NSDC data |  | Seung-Beom |  | v026 | ToDo
S023 | SONMDT | 1 | Clarify ra-purpose for reconfigurationWithSync |  | Samsung (Aby) |  | V006 | Agreed
H306 | SONMDT | 1 | SDT failure cause |  | Jun Chen |  | V004 | Agreed
C061 | SONMDT | 1 | Wrong field description |  | Tangxun |  | V002 | Agreed
H307 | SONMDT | 1 | SDT UL data volume |  | Jun Chen |  | V004 | Agreed
H308 | SONMDT | 1 | Time since SDT execution |  | Jun Chen |  | V004 | Agreed
X555 | SONMDT | 1 | Incomplete field description |  | Xiaomi (Shuai) |  | V001 | Rejected
N044 | SONMDT | 1 | Definition of distanceFromReference1 in UEInformationResponse message |  | Nokia (Mani) |  | V005 | Agreed
C062 | SONMDT | 1 | Misalignment with procedural text |  | Tangxun |  | V002 | Agreed
C063 | SONMDT | 1 | Co-existence of LTM and DAPS is not supported |  | Tangxun |  | V002 | Agreed
E022 | SONMDT | 1 | Field description in RLF-Report and SuccessHO-Report |  | Ali Parichehreh |  | V004 | Agreed
H309 | SONMDT | 1 | pCellId |  | Jun Chen |  | V004 | Agreed
V106 | AIML | 1 | Better field description of cellid |  | Boubacar |  | V009 | Agreed
H251 | NTN | 1 | SMTC for serving cell | R2-25xxxxx | Huawei (Lili) |  | V006 | ToDo
Q200 | NTN | 1 | RefLocList-r19 in SIB2 | Yes | Qualcomm (Bharat) |  | v022 | Agreed
E013 | NTN | 2 | Maximum amount of reference locations for location-based SMTC selection | R2-25XXXX | Ericsson (Ignacio) |  | v001 | Agreed
X250 | NTN | 2 | Broadcast of distance threshold together with reference location for neighbor cells in SIB2 | R2-25XXXX | Xiaomi (Xiaowei Jiang) |  | v010 | Rejected
V209 | NTN | 2 | Radius is also needed for UE-based SMTC selection | Yes, Re-250xxxx | vivo (Stephen) |  | v013 | Duplicate X250
A200 | NTN | 1 | Reference location and SMTC5list | Yes | Apple (Yuqin) |  | v017 | ToDo
E035 | LPWUS | 2 | TimeToTrigger (TTT) for RRM relaxation entry | R2-25xxx | Ericsson (Martin) |  | V006 | Rejected
N083 | NTN | 1 | Reference location mapping to SMTC configuration IE | R2-25xxxxx | Nokia (Jakob) |  | v016 | Rejected
O702 | LPWUS | 1 | Align the name of low power wake-up receiver. |  | Haocheng Wang (OPPO) |  | V007 | Agreed
V203 | NTN | 1 | Refine the mapping between reference location and smtc4 and smtc5 | No | vivo (Stephen) |  | v007 | Rejected
E008 | LPWUS | 1 | Restrictions to configure s-SearchThresholdP5 and P6. |  | Ericsson (Martin) |  | V002 | ToDo
N085 | NTN | 1 | Selecting the number of SMTCs to consider | No | Nokia (Jakob) |  | v016 | ToDo
C006 | NTN | 1 | Clarify whether the R19 DL CE capable UEs perform measurement as configured in the SMTC4 | Yes, R2-250xxxxx | CATT (Da Wang) |  | v008 | Agreed
H255 | NTN | 1 | Total number of SMTCs | R2-25xxxxx | Huawei (Lili) |  | V045 | ToDo
C008 | NTN | 1 | Corrections on the smtc5list | Yes, R2-250xxxxx | CATT (Da Wang) |  | v019 | Agreed
H256 | NTN | 1 | Empty SSB-MTC5-r19 in smtc5list | R2-25xxxxx | Huawei (Lili) |  | V045 | ToDo
H257 | NTN | 1 | Total number of SMTC periodicities | R2-25xxxxx | Huawei (Lili) |  | V045 | ToDo
V204 | NTN | 2 | SMTC5 and the reference location list can be configured for the inter-frequency case | Yes, R2-250xxxx | vivo (Stephen) |  | v005 | Duplicate H250
H253 | NTN | 1 | Need code of warningAreaCoordinates-r19 | R2-25xxxxx | Huawei (Lili) |  | V014 | Rejected
O710 | NTN | 1 | Adding “warning area coordinates segment” to field description | R2-25xxxx | OPPO (Haocheng) |  | v015 | Agreed
V502 | NES | 1 | mandatory IEs in OD-SIB1-config |  | vivo (Jianhui) |  | V026 | Duplicate
A101 | NES | 1 | Type of carrierBandwidth-r19 |  | Apple (Peng Cheng) |  | V029 | PropAgree
H100 | NES | 2 | frequencyBandList-r19 field |  | Huawei (Marcin) |  | V013 | PropAgree
A102 | NES | 1 | Type of ss-PBCH-BlockPower-r19 |  | Apple (Peng Cheng) |  | V029 | PropAgree
H101 | NES | 2 | od-sib1-WindowDuration-r19 field |  | Huawei (Marcin) |  | V013 | PropAgree
Z103 | NES | 1 | Correction on the SIBxx |  | ZTE (Gao Yuan) |  | V028 | PropAgree
X202 | NES | 1 | Classify parameters of OD-SIB1 | R2-25xxxxx | Xiaomi (Li Zhao) |  | V003 | PropReject
X204 | NES | 2 | sib1-PDCCH-RestrictionToPRACH-r19 | R2-25xxxxx | Xiaomi (Haitao) |  | V014 | PropAgree
S031 | NES | 1 | prach-RootSequenceIndex-r19 |  | Anil Agiwal (Samsung) |  | V023 | PropAgree
H102 | NES | 2 | locationAndBandwidth-r19 field |  | Huawei (Marcin) |  | V013 | PropAgree
H103 | NES | 2 | absoluteFrequencyPointA-r19 field |  | Huawei (Marcin) |  | V013 | PropReject
S030 | NES | 1 | sib1-restrictedSetConfig-r19 |  | Anil Agiwal (Samsung) |  | V023 | PropAgree
J003 | NES | 1 | Field description on locationAndBandwidth |  | Sharp (LIU Lei) |  | V020 | PropAgree
J004 | NES | 1 | Field description on ul-FrequencyBandList |  | Sharp (LIU Lei) |  | V020 | PropAgree
Z255 | NTN | 2 | Signalling to indicate ISA the same as serving cell | R2-25xxxx | ZTE (Zhihong) |  | v012 | ToDo
S026 | NTN | 1 | Missing FD of radius-r19 in SIBXX |  | Samsung (Shiyang) |  | v011 | Agreed
S053 | AIML | 1 | Interaction with NTN |  | Aby K Abraham |  | v026 | ToDo
N027 | AIML | 1 | Fieldname mismatch | N/A | Jerediah Fevold |  | vnnn | Agreed
N111 | AIML | 2 | Excess hierarchy in Applicability Report | R2-2507181 | Jerediah Fevold |  | v030 | ToDo
Z015 | AIML | 1 | OPTIONAL presence of applicabilityInfoReportList in applicability report |  | Fei Dong |  | V040 | ToDo
E041 | AIML | 2 | Associated ID validity | R2-25xxxx | Ericsson (Jens) |  | V022 | Rejected
C100 | SBFD | 1 | Concern on ‘CFRA’ | R2-250xxxx | Jianxiang Li (CATT) |  | V005 | Agreed
Z401 | MIMO | 2 | The present condition for the pathlossOffsetPRACH-DCI-1-0 |  | ZTE (Wenting Li) |  | v008 | PropAgree
Z402 | MIMO | 2 | The present condition for the prachAssociationDCI-1-0 |  | ZTE (Wenting Li) |  | v008 | PropReject
Z352 | SBFD | 1 | Need code for sbfd-RSRP-ThresholdRO-Type |  | Yu Pan (ZTE) |  | V006 | Rejected
O000 | SBFD, MOB | 2 | Applicability of SBFD-RACH to LTM procedure |  | OPPO (Qianxi) |  | V003 | ToDo
L701 | SBFD | 1 | Whether to locate the rach-ConfigCommon and sbfd-RACH-DualConfig for the same feature combination in the same additionalRACH-Config. | R2-250xxxx | LGE (Hanseul Hong) |  | V008 | Agreed
C101 | SBFD | 1 | Reference |  | Jianxiang Li (CATT) |  | V005 | Agreed
Z351 | SBFD | 1 | SBFD RACH configuration type, option 1 |  | Yu Pan (ZTE) |  | V006 | Agreed
E001 | SBFD | 1 | Update FD for field sbfd-RACH-Config. |  | Ericsson (Min) |  | V009 | Agreed
L702 | SBFD | 1 | SBFD RO in the field description of sbfd-RACH-Config |  | LGE (Hanseul Hong) |  | V008 | Agreed
E002 | SBFD | 1 | Definition for the term “SBFD aware UE” is missing. |  | Ericsson (Min) |  | V009 | Agreed
C102 | SBFD | 1 | RACH occasion type |  | Jianxiang Li (CATT) |  | V005 | Agreed
C103 | SBFD | 1 | reference |  | Jianxiang Li (CATT) |  | V005 | Agreed
E004 | SBFD | 1 | Unclear FD for sbfd-AdditionalRACH-Config |  | Ericsson (Min) |  | V009 | Agreed
Z353 | SBFD | 1 | FD of sbfd-RACH-DualConfig-ValidRO-AcrossSymbolTypes |  | Yu Pan (ZTE) |  | V006 | Duplicate
E003 | SBFD | 1 | Term “RACH configuration option 2” is undefined |  | Ericsson (Min) |  | V009 | Agreed
H350 | SBFD | 1 | Revision of value range | - | Huawei-Tao Cai |  | V004 | Agreed
H403 | MIMO | 2 | Support of LTM cell switch |  | Huawei (David) |  | v007 | ToDo
H130 | NES | 1 | SSB adaptation for deactivated SCell | R2-25xxxxx | Huawei (Lili) |  | V034
O007 | NES | 2 | Optionality of fields for offset |  | OPPO (Qianxi) |  | V004 | PropReject
L203 | NES | 2 | Missing scenarios for OD-SSB transmission. |  | LGE (Han Cha) |  | V016 | PropAgree
S028 | NES | 2 | OD-SSB-r19 |  | Anil Agiwal (Samsung) |  | V023 | Duplicate
N002 | NES | 1 | Sfn offset and halfframeindex are now common for all od-ssb configs. This may be wrong |  | Jarkko Koskela(Nokia) |  | V009 | PropAgree
L204 | NES | 2 | Correction on maximum value range for adap-ssb-Offset-r19 |  | LGE (Han Cha) |  | V016 | PropAgree
N003 | NES | 1 | Haflframe index parameters for ssb adapatation has different values as for OD-SSB |  | Jarkko Koskela(Nokia) |  | V020 | PropAgree
V501 | NES | 1 | update field description for od-ssb-absoluteFrequency |  | vivo (Jianhui) |  | V015 | PropAgree
H129 | NES | 1 | Field description of od-ssb-absoluteFrequency-r19 | R2-25xxxxx | Huawei (Lili) |  | V034
C182 | NES | 1 | Ambiguity on SFN of which cell is referring to by the filed od-ssb-SFN-Offset |  | Rui(CATT) |  | V008 | PropAgree
L205 | NES | 1 | Correction on the field description of adap-ssb-Offset |  | LGE (Han Cha) |  | V016 | PropAgree
L206 | NES | 1 | Clarification on field description of adap-ssb-Periodicity-r19 |  | LGE (Han Cha) |  | V016 | PropAgree
H128 | NES | 1 | Conditional presence of od-ssb-absoluteFrequency-r19 | R2-25xxxxx | Huawei (Lili) |  | V034
C183 | NES | 1 | Incorrect description for the condition ODssbOnly |  | Rui(CATT) |  | V008 | PropReject
X556 | SONMDT | 2 | Missed cases when neigher of cho or cpc is fulfilled |  | Xiaomi (Shuai) |  | V001 | Rejected
H310 | SONMDT | 1 | fulfilledConfigWhenChoOnly | R2-25xxxx | Jun Chen |  | V004 | Agreed
H311 | SONMDT | 0 | a typo in atleast |  | Jun Chen |  | V004 | Agreed
Z309 | SONMDT | 1 | Definition of fulfilledConfigWhenChoOnly | R2-25xxxx | QI Tao |  | V012 | Agreed
Z310 | SONMDT | 1 | Definition of timeBetweenLastFulfillmentAndEvent | R2-25xxxx | QI Tao |  | V012 | Agreed
Z354 | SBFD | 1 | Description of CLI-RSSI-MeasResourceId |  | Yu Pan (ZTE) |  | V006 | Agreed
S001 | MIMO | 2 | Wrong place of cri-TypeI-SinglePanelRI-Restriction-r19 |  | Samsung (Shiyang) |  | V002 | PropAgree
S002 | MIMO | 2 | Wrong place of cri-TypeI-SinglePanelN1-N2-CBSR-r19 |  | Samsung (Shiyang) |  | V002 | PropAgree
Z405 | MIMO | 2 | Missed sub-elements for the ng-n1-n2-r19 |  | ZTE (Wenting Li) |  | v008 | PropReject
Z405 | MIMO | 2 | Missed sub-elements for the ng-n1-n2-r19 |  | ZTE (Wenting Li) |  | v008 | PropReject
H404 | MIMO | 2 | Parameter name, contents and description are inconsistent |  | Huawei (David) |  | V043 | ToDo
Z407 | MIMO | 2 | Optional Present of the numberOfPMI-SubbandsPerCQI-Subband-r19 |  | ZTE (Wenting Li) |  | v008 | PropAgree
S003 | MIMO | 2 | Wrong place of cri-TypeII-RI-Restriction-r19 |  | Samsung (Shiyang) |  | V002 | PropAgree
S004 | MIMO | 2 | Wrong place of cri-TypeII-N1-N2-CBSR-r19 |  | Samsung (Shiyang) |  | V002 | PropAgree
S005 | MIMO | 2 | Inconsistent value of paramCombination-r19 |  | Samsung (Shiyang) |  | V002 | PropReject
H405 | MIMO | 2 | CBSR List could be made more readable |  | Huawei (David) |  | V043 | ToDo
H406 | MIMO | 2 | X1-X2-CBSR List could be made more readable |  | Huawei (David) |  | V043 | ToDo
N051 | MIMO | 1 | Wrong reference in FD of codebookMode |  | Nokia (Andrew) |  | v004 | PropAgree
S006 | MIMO | 1 | Missing information in FD of cri-TypeI-SinglePanelN1-N2-CBSR |  | Samsung (Shiyang) |  | V002 | PropAgree
S007 | MIMO | 1 | Missing information in FD of cri-TypeI-SinglePanelRI-Restriction |  | Samsung (Shiyang) |  | V002 | PropAgree
S008 | MIMO | 1 | Missing information in FD of cri-TypeII-N1-N2-CBSR |  | Samsung (Shiyang) |  | V002 | PropAgree
S009 | MIMO | 1 | Missing information in FD of cri-TypeII-ri-Restriction |  | Samsung (Shiyang) |  | V002 | PropAgree
N052 | MIMO | 1 | Wrong reference in FD of n1-n2 |  | Nokia (Andrew) |  | v004 | PropAgree
Z404 | MIMO | 2 | Change the name of n1-n2-r19 to distinghish it from the legacy n1-n2 |  | ZTE (Wenting Li) |  | v008 | PropReject
N053 | MIMO | 1 | Wrong reference in FD of ng-n1-n2 |  | Nokia (Andrew) |  | v004 | PropAgree
N054 | MIMO | 1 | Wrong reference in FD of numberOfPMI-SubbandsPerCQI-Subband |  | Nokia (Andrew) |  | v004 | PropAgree
N055 | MIMO | 1 | Wrong reference in FD of ri-Restriction |  | Nokia (Andrew) |  | v004 | PropAgree
N056 | MIMO | 1 | Wrong reference in FD of typeI-SinglePanel-ri-Restriction |  | Nokia (Andrew) |  | v004 | PropAgree
N057 | MIMO | 1 | Wrong reference in FD of valueOfN |  | Nokia (Andrew) |  | v004 | PropAgree
H351 | SBFD | 1 | Revision of value range | - | Huawei-Tao Cai |  | V004 | Agreed
K101 | MIMO | 1 | Field description update for nrofHARQ-Processes regarding mode-B CG |  | ASUSTeK (Xinra) |  | V005 | PropAgree
S017 | MIMO | 1 | Update description of CSI-AperiodicTriggerStateList to make it applicable to UEI-CSI |  | Samsung (Shiyang) |  | V002 | PropAgree
Z414 | MIMO | 2 | Missed parameter for the CSI-CJTC triggerningScheme |  | ZTE (Wenting Li) |  | v008 | PropReject
H352 | SBFD | 1 | missing "optional" tag | - | Huawei-Tao Cai |  | V004 | Agreed
S012 | MIMO | 2 | Missing field for resourcesForChannelCJTC-r19 |  | Samsung (Shiyang) |  | V002 | PropReject
S010 | MIMO | 1 | Wording in FD of delayOffsetCompensation |  | Samsung (Shiyang) |  | V002 | PropAgree
S011 | MIMO | 1 | FD of mr-SelectedResources not correct |  | Samsung (Shiyang) |  | V002 | PropAgree
Z355 | SBFD | 1 | FD of resourceSetCLI |  | Yu Pan (ZTE) |  | V006 | Agreed
S052 | AIML | 2 | Qunatity configuration for Event triggered Logging of CSI measurements |  | Aby K Abraham |  | v026 | ToDo
B203 | AIML | 2 | Need code for loggingPeriodicity |  | Congchi Zhang |  | V011 | Agreed
N028 | AIML | 2 | Reuse of A1/A2 events for NW-side logging | R2-25xxxx | Jerediah Fevold |  | vnnn | Agreed
Z010 | AIML | 1 | UE measurement behavior when LoggingPeriodicity is configured |  | Fei |  | v027 | ToDo
Z009 | AIML | Class 1 | The data logging is missing in general description of CSI-MeasConfig |  | Fei |  | V017 | Agreed
H151 | MOB | 3 | Per cell configuration includes per CG items | R2-25xxxxx | Huawei (David) |  | V023 | Agreed
H400 | MIMO | 2 | In which serving cell to include UE-initiated CSI reports is unclear |  | Huawei (David) |  | v007 | ToDo
Z016 | AI/ML | 1 | The missing description about AI/ML functions in CSI-ReportConfig |  | Fei Dong |  | V040 | ToDo
N073 | AIML | 1 | Mismatch in ASN.1 and description of nrofReportedRS-v19xy |  | Sakira Hassan |  | V015 | Agreed
N074 | AIML | 1 | Need code to be updated for nrofReportedRs-vs1900 |  | Nokia (Sakira Hassan) |  | V052 | ToDo
N021 | AIML | 2 | Remove the CHOICE hierarchy from the configuration for CSI prediction and beam prediction | R2-25xxxx | Jerediah Fevold |  | vnnn | Rejected
H003 | AIML | 2 | Configuration for UE data collection | R2-25xxxx | Dawid |  | v017 | Rejected
H008 | AIML | 2 | Configuration restrictions in predictionConfiguration-r19 |  | Dawid |  | V017 | Agreed
S047 | AIML | 2 | Inference configuration | R2-25xxxx | Youn Heo |  | v026 | Rejected
N022 | AIML | 2 | Move csi-InferencePrediction into configurationForChannelPrediction-r19 | N/A | Jerediah Fevold |  | vnnn | Rejected
N023 | AIML | 2 | Make csi-InferencePrediction-r19 an OPTIONAL parameter with Need R | N/A | Jerediah Fevold |  | vnnn | Rejected
B207 | AIML | 1 | Incorrect IE type of component csi-InferencePrediction-r19 |  | Congchi Zhang |  | V037 | ToDo
N075 | AIML | 1 | Resources for channel prediction seems to be mandatory for BM prediction and UE-side data collection |  | Nokia (Sakira Hassan) |  | V052 | ToDo
C078 | AIML | 2 | Conditionally mandatory parameter |  | Tangxun |  | V003 | Rejected
Z411 | MIMO | 2 | Wrong structure for the reportQuantity-r19 |  | ZTE (Wenting Li) |  | v008 | PropReject
S013 | MIMO | 2 | linkedCJTC-Report-r19 can be merged to csi-ReportCJTC-r19 |  | Samsung (Shiyang) |  | V002 | PropAgree
Z412 | MIMO | 2 | Remove ED for the CSI-ReportCJTC |  | ZTE (Wenting Li) |  | v008 | PropAgree
N059 | MIMO | 2 | Optionality of a1-Parameters-v19xy |  | Nokia (Andrew) |  | v010
C250 | MIMO | 1 | Wrong place of field description of “When this field is set to event1, eventThreshold can only be configured with values from 14 to 113” |  | CATT (LeiWang) |  | V003 | PropAgree
E032 | MIMO | 1 | Aligment of CSI-ReportUE-IBR-r19 |  | Ericsson (Lian) |  | V006 | PropAgree
S014 | MIMO | 2 | Rename eventThreshold-r19 for UEIR event1 |  | Samsung (Shiyang) |  | V002 | PropAgree
K102 | MIMO | 1 | Wrong parameter name pusch-ResourceOfModeB |  | ASUSTeK (Xinra) |  | V005 | PropReject
K103 | MIMO | 2 | Redundant information in mode B CG configuration |  | ASUSTeK (Xinra) |  | V005 | ToDo
H402 | MIMO | 2 | PUCCH/PUSCH resources can only be configured in one BWP |  | Huawei (David) |  | v007 | PropReject
Z408 | MIMO | 2 | Redudant servCellIndex-r19 for the UEIBR mode B configuration |  | ZTE (Wenting Li) |  | v008 | ToDo
N058 | MIMO | 2 | minimumPucch-PuschOffset-r19 value definition inconsistency |  | Nokia (Andrew) |  | v004 | PropAgree
Z403 | MIMO | 2 | Change the reference chapter in the field description of the codebookMode in include R19 feature |  | ZTE (Wenting Li) |  | v008 | PropAgree
Z416 | MIMO | 2 | Delete the ED for the minimumPucch-PuschOffset-r19 |  | ZTE (Wenting Li) |  | v008 | PropAgree
C254 | MIMO | 2 | Re-structure of the conditionFulfillmentIndicator-r19 indication |  | CATT (LeiWang) |  | V003 | PropAgree
H401 | MIMO | 2 | CSI-ReportUE-IBR-r19 has no extension markers |  | Huawei (David) |  | v007 | PropAgree
L001 | AIML | 1 | Update sgcs-r19 to csi-pai-r19 |  | Soo Kim |  | V020 | Agreed
N072 | AIML | 1 | Description of Assoicated ID indication for Set A and Set B |  | Sakira Hassan |  | V015 | Agreed
Z413 | MIMO | 2 | Missed information in the FD of the linkedCJTC-Report |  | ZTE (Wenting Li) |  | v008 | PropAgree
H005 | AIML | 1 | L1 parameters descriptions |  | Dawid |  | vnnn | Agreed
B204 | AIML | 1 | Description related to none-BM-r19 and none-CSI-r19 |  | Congchi Zhang |  | V011 | Rejected
N060 | MIMO | 1 | Reference to wrong version of nrofReportedRS in FD of conditionFulfillmentIndicator |  | Nokia (Andrew) |  | v010
C251 | MIMO | 1 | Redundant field description in eventInstanceCount-r19 |  | CATT (LeiWang) |  | V003 | PropAgree
E033 | MIMO | 1 | Aligment of the term UE initiated CSI report in field description |  | Ericsson (Lian) |  | V006 | PropAgree
E062 | SBFD | 2 | Mandatory csi-RS-ResourceSetList in CSI-ResourceConfig | R2-25xxxxx | Hakan.l.palm@ericsson.com |  |  | ToDo
N029 | AIML | 1 | Variable name for maximum number of data collection candidate configs is inconsistent. | N/A | Jerediah Fevold |  | vnnn | Agreed
O004 | NES, SLRelay | 1 | Applicability of PO bundling to SL Relay | R2-25xxxxx | OPPO (Qianxi) |  | V002 | ToDo
O005 | NES, LPWUS | 1 | Applicability of PO bundling to LP-SS | R2-25xxxxx | OPPO (Qianxi) |  | V002 | Agred
S034 | NES | 2 | pagingAdaptNAndPagingFrameOffset-r19 |  | Anil Agiwal (Samsung) |  | V023 | PropReject
E034 | LPWUS | 2 | LP-WUS lastUsedCellOnly | R2-25xxx | Ericsson (Martin) |  | V006 | Rejected
H125 | NES | 1 | Optionality of R19 PEI configurations |  | Huawei (Lili) |  | V012 | PropReject
C026 | NES, LPWUS | 2 | Co-existence of LP-WUS in idle/inactive and paging adaptation | R2-25xxxxx | Da Wang (CATT) |  | V004 | Duplicate
S056 | LPWUS | 1 | Incorrect value range of lpss-BinarySeqIndex-r19 |  |  |  | vnnn | Rejected
H051 | LPWUS | 1 | Need code for “lpss-OverlaidSeqRoot-r19” parameter | R2-25xxxxx | Kuang Yiru (Huawei) |  | V003 | Agreed
H052 | LPWUS | 1 | Missing need code for “startSymbol2-r19” in “lpss-StartSymbol-r19” | R2-25xxxxx | Rama Kumar Mopidevi (Huawei) |  | V003 | Agreed
H053 | LPWUS | 1 | Impact on thresholds entry condition due to RAN4 definition on LR types | R2-25xxxxx | Rama Kumar Mopidevi (Huawei) |  | V003 | Rejected
E036 | LPWUS | 2 | Type 1 and 2 LR | R2-25xxx | Ericsson (Martin) | See also H53 and H54. | V006 | Rejected
H054 | LPWUS | 1 | Impact on thresholds exit condition due to RAN4 definition on LR types | R2-25xxxxx | Rama Kumar Mopidevi (Huawei) |  | V003 | Rejected
O601 | MOB | 1 | RRC and MAC misalignment issue |  | OPPO (Xue Lin) |  | V044 | PropAgree | Fine to align RRC to the name in MAC, but current name in MAC do not respect the ASN.1 name convention so they need to be changed anyway.
C157 | MOB | 1 | There is no need to mandatorily provide the 2TA configuration in the IE EarlyUL-SyncConfig if tag2 is present in the SpCellConfig in ltm-CandidateConfig |  | Rui(CATT) |  | V005 | ToDo
J002 | NES | 1 | Update field description of absoluteFrequencySSB |  | Sharp (LIU Lei) |  | V006 | ToDo
E023 | NES | 1 | It is unclear what is the Case1 with respect of the SSBless Scell. | yes | Helka-Liina Määttänen(ER) |  | V019 | ToDo
V503 | NES | 1 | Relation between OD-SSB case 1 & SSB-less SCell |  | vivo (Jianhui) |  | V032 | ToDo
O400 | XR | 1 | Restriction on additionalPriority-r19 and priorityAdjustmentThreshold-r19 |  | Zhe Fu (OPPO) |  | V06 | PropRej
H202 | GEN | 1 | Enhancing the readability of RRC procedure text | R2-250xxxx | Yinghao Guo (Huawei) |  | V09 | ToDo
S055 | XR | 1 | Reference to ‘same LCH configuration’ |  | Milos (Samsung) |  | V10 | PropAgree
E054 | MOB | 1 | Need code of ltm-ExecutionCondition in LTM-Candidate |  | Tony (Ericsson) |  | V009 | PropReject
C158 | MOB | 1 | Add the field description for ltm-CSI-ReportConfig-r19 under the LTM-Candidate |  | Rui(CATT) |  | V005 | Rejected
M202 | MOB | 1 | Need code for ltm-CSI-ReportConfig-r19 in LTM-Candidate IE |  | Pasi (MediaTek) |  | V008 | Agreed
B110 | MOB | 1 | CSI report configuration for early CSI acquisition after cell switch | R2-25xxxxx | Lenovo (Lianhai Wu) |  | V016 | Rejected
B111 | MOB | 1 | Maintenance of CSI resource in LTM-configu after cell switch | R2-25xxxxx | Lenovo (Lianhai Wu) |  | V016 | Rejected
H160 | MOB | 2 | It is unclear why there is a list of CSI-IM |  | Huawei (David) |  | V067 | PropReject | In the RAN1 parameter list I see that CSI-IM within LTM-CSI-ResourceConfig is just a single field, but within LTM-Candidate is actually a ToAddModList and ToReleaseList
C159 | MOB | 1 | Ambiguity of the ltm-ExecutionCondition field description on whether it is only used for MCG LTM |  | Rui(CATT) |  | V005 | Rejected
O001 | MOB, SLRelay | 1 | LTM, C-LTM applicability to intermediate Relay |  | OPPO (Qianxi) |  | V003 | Rejected
V400 | MOB | 1 | Introduce new attemptLTM-Switch-r19 to cover the case when a UE only support intra-CU LTM fast recovery but not inter-CU fast recovery |  | vivo(Jing Liang) |  | V007 | Rejeted
H150 | MOB | 3 | ltm-ServingCellExecutionCondition as SetupRelease Need M contradicts with procedure text | R2-250xxxx | Huawei (David) |  | V023 | Agreed
C160 | MOB | 1 | Ambiguity of the ltm-ServingCellExecutionCondition field description on whether it is only used for MCG LTM |  | Rui(CATT) |  | V005 | Rejected
M203 | MOB | 1 | Ambiguity of the Cond for attemptLTM-Switch |  | Pasi (MediaTek) |  | V008 | Agreed
N102 | MOB | 1 | LTM Config NR-DC Clarification | R2-250xxxx | Nokia(Srinivasan) |  | V017 | Agreed
B111 | MOB | 1 | LTM Config NR-DC Clarification | R2-25xxxxx | Nokia(Srinivasan) |  | V017 | Agreed
V401 | MOB | 2 | Missing RRC parameter used for LTM ‘CodebookConfig-LTM-r19’ and ‘cqi-Table’ for CSI acquisition |  | vivo(Jing Liang) |  | V007 | Agreed
H154 | MOB | 2 | It is unclear which fields are applicable to event triggered reports but not to execution conditions. |  | Huawei (David) |  | V018 | PropAgree
H153 | MOB | 2 | A field specific to eventLTM3 should be placed in eventLTM3 |  | Huawei (David) |  | V018 | PropAgree
H157 | MOB | 2 | The contents of LTM-CodebookConfig-r19 in R2-2507729 (CR endorsed at RAN2 131bis) is not an actual codebook config. |  | Huawei (David) |  | V021 | PropAgree | Ok to move the field inside LTM3 but maybe the need code should be Need N.
H158 | MOB | 2 | Sentence is difficult to read |  | Huawei (David) |  | V021 | PropAgree | This is correct, I read wrongly the RAN1 parameter list :)
H159 | MOB | 2 | Separating early CSI report config | R2-250xxxx | Huawei (David) |  | V067 | ToDo | I think it makes sense, but this RIL is also linked to the TEI which is still under discussion for the early CSI report for L3 handover. Therefore, I add the “TEI” tag in the WI tab of this RIL and I think we can discuss in main session how to unify.
H156 | MOB | 2 | ReportInterval-r1900 is not a new version of ReportInterval: it does not replace it anywhere and it does not match with the description of the ReportInterval IE. |  | Huawei (David) |  | V021 | PropAgree
H155 | MOB | 2 | value ssb-index-RSRP should be the default when reportQuantity is not signalled |  | Huawei (David) |  | V021 | ToDo | This comes from the RAN1 parameter list. Before changing this we should check with them if this change is okay
C162 | MOB | 1 | Issue on the name and place of the candidateSpecificOffsetS field description |  | Rui(CATT) |  | V005 | Agreed
C168 | MOB | 1 | CLTM case is missing in the filed description of ltm-ReportConfigType |  | Rui(CATT) |  | V026 | PropAgree
C161 | MOB | 1 | Ambiguity of the reportQuantity field description on the wording “CSI report” |  | Rui(CATT) |  | V005 | Rejected
Z162 | MOB | 1 | Clarification on the conditional presence of allowReportAnyBeam |  | ZTE (Mengjie Zhang) |  | V009 | Rejected
V402 | MOB | 2 | I think it makes sense, but this RIL is also linked to the TEI which is still under discussion for the early CSI report for L3 handover. Therefore, I add the “TEI” tag in the WI tab of this RIL and I think we can discuss in main session how to unify. |  | vivo(Jing Liang) |  | V007 | Agreed
C163 | MOB | 1 | Wrong fields in the LTM-CSI-IM-ResourceSet field descriptions |  | Rui(CATT) |  | V005 | Agreed
H200 | XR | 2 | Co-configuration of the fields dsr-ReporthingThresholdList and dsr-ReportNonDelayCriticalData |  | Yinghao Guo (Huawei) |  | V03 | PropAgree
V051 | XR | 1 | Restriction on ul-RateQueryConfigList-r19 |  | Vivo(Chenli) |  | V002 | PropRej
Z202 | XR | 1 | Field description of ul-RateQueryProhibitTimer |  | ZTE(Eswar) |  | V010 | Duplicate
S039 | XR | 1 | Correction on ul-RateQueryProhibitTimer |  | Vinay (Samsung) |  | V07 | PropAgree
C184 | NES | 1 | The needs of different ssb-ToMeasure configurations for OD-SSB |  | Rui(CATT) |  | V008 | PropReject
H126 | NES | 1 | Serving cell OD-SSB measurements for deactivated SCell | R2-25xxxxx | Huawei (Lili) |  | V012 | PropAgree
S027 | NTN | 1 | Incorrect FD of smtc5list in MO |  | Samsung (Shiyang) |  | v011 | Agreed
E025 | NES | 1 | It is unclear what is the Case1 with respect of the SSBless Scell. | yes | Helka-Liina Määttänen(ER) |  | V019 | ToDo
N045 | SONMDT | 1 | Definition of distanceFromReference2 in MeasResults IE |  | Nokia (Mani) |  | V005 | Agreed
Z415 | MIMO | 2 | The definition of additionalOneSlotOffset Dopp is missed |  | ZTE (Wenting Li) |  | v008 | PropReject
N121 | MIMO | 1 | Applicable codebooks for additionalOneSlotOffset |  | Nokia (Andrew) |  | v010
Z409 | MIMO | 2 | Change the ASN.1 coding for the additionalOneSlotOffsetDoppler-r19 |  | ZTE (Wenting Li) |  | v008 | PropReject
X205 | NES | 1 | How to configure od-ssb-PositionsInBurst | R2-25xxxxx | Xiaomi (Li Zhao) |  | V015 | PropAgree
S035 | NES | 2 | Paging search space for Adapative POs |  | Anil Agiwal (Samsung) |  | V023 | PropAgree
C185 | NES | 1 | The needs of the new field commonSearchSpaceListExt-r19 in PDCCH-ConfigCommon |  | Rui(CATT) |  | V008 | PropReject
Z256 | NTN | 2 | Missing linked SS in paging search space configuration | None | ZTE (Zhihong) |  | v012 | Rejected
Z203 | XR | 1 | Field description of remaingTimeThresholdRLC-Polling and remainingTimeThresholdRLC-ReTx |  | ZTE(Eswar) |  | V003 | PropAgree
V050 | XR | 1 | Coexistence of remaining time based RLC retransmission and polling | R2-25xxx | Vivo(Chenli) |  | V002 | ToDo
E007 | LPWUS | 2 | Move lpwus-Config-r19 in SpCellConfig |  | Ericsson (Martin) |  | V002 | Rejected
E043 | LPWUS | 2 | Exit condition for LP-WUS monitoring in connected mode | R2-25xxxxx | Ericsson (Martin) | See also H050 | V011 | ToDo
S057 | LPWUS | 2 |  |  |  |  | vnnn | Agreed
C027 | LPWUS | 2 | Support of Option 1-2 with dual DRX group | R2-25xxxxx | Da Wang (CATT) |  | V012 | Agreed
C030 | LPWUS | 1 | Configuration of Option 1-1 and Option 1-2 | No | Da Wang (CATT) |  | V012 | Rejected
H055 | LPWUS | 1 | Replace “option 1-1” and “option 1-2” terminology with description | R2-25xxxxx | Kuang Yiru (Huawei) |  | V003 | Rejected
O003 | SBFD, NES | 2 | Applicability of NES related RACH parameters |  | OPPO (Qianxi) |  | V003 | ToDo
H127 | NES | 1 | Which RA occasions to use when the configuration is absent in RACH-ConfigDedicated | R2-25xxxxx | Huawei (Lili) |  | V012 | ToDo
C104 | SBFD | 1 | Concern on ‘for CFRA’ | R2-250xxxx | Jianxiang Li (CATT) |  | V005 | Agreed
C079 | AIML | 1 | srb-Identity-v19xy |  | Tangxun |  | V003 | Agreed
L207 | NES | 1 | Optional configuration of msg1-FDM-r19 in RandomAccessAdaptConfig |  | LGE(Hanseul Hong) |  | V016 | PropReject
L208 | NES | 1 | Optional configuration of msg1-FrequencyStart-r19 in RandomAccessAdaptConfig |  | LGE (Hanseul Hong) |  | V016 | PropReject
L209 | NES | 1 | Optional configuration of prach-SubsetMask-Index-Adaptation-r19 in RandomAccessAdaptConfig |  | LGE (Hanseul Hong) |  | V016 | PropAgree
L210 | NES | 1 | Need code of ssb-perRACH-OccasionAndCB-PreamblesPerSSB in RandomAccessAdaptConfig |  | LGE (Hanseul Hong) |  | V016 | PropAgree
B111 | MOB | 1 | Reference configuration for Inter-SN SCG LTM | R2-25xxxxx | Nokia(Srinivasan) |  | V017 | Agreed
N101 | MOB | 1 | Reference configuration for Inter-SN SCG LTM |  | Nokia(Srinivasan) |  | V017 | Agreed
Z163 | MOB | 1 | Clarification on CondTriggerConfig field descriptions |  | ZTE (Mengjie Zhang) |  | V009 | Agreed
Z164 | MOB | 1 | Clarification on reportType |  | ZTE (Mengjie Zhang) |  | V009 | Agreed
C164 | MOB | 1 | Suffix “-r19” should be used instead of “” for the ReportInterval-v19xy |  | Rui(CATT) |  | V005 | Agreed
S051 | AIML | 1 | RLC-Config and MAC-LogicalChannelConfig has to be mandatory present while configuring SRBx |  | Aby K Abraham |  | v026 | Agreed
E012 | NTN | 2 | New RAN1 parameter on DL CE |  | Ericsson (Ignacio) |  | v001 | Agreed
Z356 | SBFD | 2 | MIMOParam-v19xy |  | Yu Pan (ZTE) |  | V006 | Agreed
L703 | SBFD | 1 | ToReleaseList for additionalUplinkPowerControl |  | LGE (Hanseul Hong) |  | V008 | Agreed
E024 | NES, GEN | 1 | It is unclear what is the Case1 with respect of the SSBless Scell. | yes | Helka-Liina Määttänen(ER) |  | V019 | ToDo
J005 | NES | 1 | Configuration limitation for servingCellMO-OD |  | Sharp (LIU Lei) |  | V020 | ToDo
O006 | NES | 2 | How to handle the SSB-less case | R2-25xxxxx | OPPO (Qianxi) |  | V004 | ToDo
C007 | NTN | 2 | The introduced SIBxx need to be added in the SI-SchedulingInfo | N | CATT (Da Wang) |  | v008 | Agreed
S015 | MIMO | 1 | FD of fourPortSRS-3Tx is in wrong place |  | Samsung (Shiyang) |  | V002 | PropAgree
Z410 | MIMO | 2 | Missed Reference for the FD of the srs-PortGrouping |  | ZTE (Wenting Li) |  | v008 | PropAgree
S016 | MIMO | 1 | startingBitOfFormat2-3-r19xy should be startingBitOfFormat2-3-r19 |  | Samsung (Shiyang) |  | V002 | PropAgree
H407 | MIMO | 2 | startingBitOfFormat2-3-r19 should be startingBitOfFormat2-3-v1900 with non-overlapping range |  | Huawei (David) |  | V034 | Todo
Z257 | NTN | 2 | Add conditional presence for offset and pci list in SSB-MTC5 | None | ZTE (Zhihong) |  | v012 | Rejected
N122 | MIMO | 2 | Conditional presence and field description of pathlossOffset |  | Nokia (Andrew) |  | v011
C252 | MIMO | 1 | Wrong field description of pathlossOffset-r19 in the IE TCI-State |  | CATT (LeiWang) |  | V003 | PropAgree
C253 | MIMO | 1 | Wrong field description of pathlossOffset-r19 in the IE TCI-UL-State-r17 |  | CATT (LeiWang) |  | V003 | PropAgree
C080 | AIML | 1 | TTT for stoping logging |  | Tangxun |  | V003 | Agreed
H453 | NR_SL_relay_multihop-Core | 1 | The timers T300/T301/T319 for multi-hop relay |  | Huawei (Jagdeep) |  | V12 | Agreed
O002 | UECap, for NR_ENDC_RF_Ph4 | 2 | Merging of 46-4, 46-5 | R2-25xxxxx | OPPO (Qianxi) |  | V002 | ToDo
E038 | LPWUS | 1 or 2 | Clarify the minimumTimeGap-r19 capability signalling | R2-25xxx | Ericsson (Martin) |  | V006 | Agreed
H201 | XR, LPWUS, AIML,NTN | 2 | OtherConfig for XR, LPWUS, AIML, NTN UAI report |  | Yinghao Guo (Huawei) |  | v05 | PropAgree
V205 | NTN | 2 | FFS whether also a distance threshold is indicated. | Yes, R2-250xxxx | vivo (Stephen) |  | v005 | Duplicate X250
E042 | AIML | 2 | Necessity of dedicated flag to configure applicability reporting via UAI | R2-25xxxx | Ericsson (Andra) |  | V022 | Rejected
C083 | AIML | 2 | AddModList for applicabilityConfigList-r19 | R2-250xxxx | Tangxun |  | V007 | Agreed
N112 | AIML | 2 | Excess hierarchy in configuration of inference-related parameters | R2-2507181 | Jerediah Fevold |  | v030 | ToDo
B205 | AIML | 2 | applicabilityConfigCellId is mandatory |  | Congchi Zhang |  | V011 | Agreed
C084 | AIML | 2 | AddModList for applicabilitySetConfigList-r19 | R2-250xxxx | Tangxun |  | V007 | Agreed
N030 | AIML | 2 | Applicability set config ID should not be optional in applicabilitySetConfig. | N/A | Jerediah Fevold |  | vnnn | Agreed
N035 | AIML | 1 | Applicability set is specific to two use cases but uses a generic name. | N/A | Jerediah Fevold |  | vnnn | Agreed
H010 | AIML | 1 | Report configuration type in ApplicabilitySetConfig-r19 | R2-25xxxx | Dawid |  | V017 | Rejected
H015 | AIML | 1 | Remove unnecessary configuration in Report configuration type in ApplicabilitySetConfig-r19 |  | Huawei(Seau Sian) |  | V046 | ToDo
E052 | AIML | 1 | Remove unnecessary reportQuantity values from otherConfig |  | Ericsson (Andra) |  | v006 | ToDo
N079 | AIML | 1 | UE side candidate data collection request |  | Nokia (Sakira Hassan) |  | V052 | ToDo
S041 | AIML | 2 | ToAddModList and To ReleaseList for candidate configuration | R2-25xxxx | Seung-Beom |  | v028 | Agreed
N113 | AIML | 2 | Excess hierarchy in Data Collection Candidate Config | R2-2507181 | Jerediah Fevold |  | v030 | ToDo
X004 | AIML | 1 | candidate data collection configuration | R2-25xxxx | Xing |  | V012 | Agreed
C081 | AIML | 1 | availability of logged radio measurements data |  | Tangxun |  | V006 | Agreed
C082 | AIML | 1 | availability of logged radio measurements data |  | Tangxun |  | V006 | Agreed
C029 | LPWUS | 1 | UAI configuration for UE’s preferred time offset for LP-WUS monitoring | No | Da Wang (CATT) |  | V012 | Agreed
H254 | NTN | 1 | Description of refLocList | R2-25xxxxx | Huawei (Lili) |  | V014 | Rejected
E049 | NR_SL_relay_multihop-Core | 1 | Wrong need code for sl-SRAP-ConfigRelay-ToAddModListsl-SRAP-ConfigRelay-ToReleaseList |  | Ericsson - Min |  | V017 | ToDo
H456 | NR_SL_relay_multihop-Core | 1 | The name of the sub IE sl-SRAP-ConfigRelay-r17 in SL-SRAP-Config-ToAddMod-r19 wrongly includes -r17 in its name |  | Huawei (Jagdeep) |  | V20 | Agreed
J012 | NR_SL_relay_multihop-Core | 1 | Remove First U2N Relay UE in field description for SL-RelayUE-ConfigMH |  | Sharp (LIU Lei) |  | V006 | Rejected
V206 | NTN | 1 | Need code for mbs-SessionAreaList-r19 should be Need S | Yes, R2-250xxxxx | vivo (Stephen) |  | v005 | Agreed
V207 | NTN | 1 | Capture the following agreement.RAN2 confirms that if no intended area ID is explicitly indicated in MCCH for an MBS broadcast service the UE is interested in, the UE considers the service is applicable for reception within the entire cell area, with legacy behavior applicable (FFS whether we capture this in the spec) | Yes, R2-250xxxxx | vivo (Stephen) |  | v003 | Duplicate V206
X505 | SLRelay | 1 | Wrong IE name |  | Xiaomi (Xing Yang) |  | V005 | Agreed
Z258 | NTN | 2 | Missing on demand SIBXX in SL-SIB-ReqInfo | No | ZTE (Zhihong) |  | v012 | Rejected
H006 | AIML | 2 | Missing imports |  |  |  | vnnn | Agreed
M204 | MOB | 1 | Ambiguity on UE variable VarLTM-ServingCellNoResetID for inter-CU LTM |  | Pasi (MediaTek) |  | V008 | Agreed
E045 | NR_SL_relay_multihop-Core | 1 | Missing description/definition for the IE/field.relayUE-RRCState-r19 |  | Ericsson - Min |  | V012 | Agreed
K002 | NR_SL_relay_multihop-Core | 1 | SIB/Paging information release due to SL RLF |  | ASUSTeK (Richard Kuo) |  | V007 | Agreed
N078 | AIML | 2 | Missing import of ApplicabilityReportList |  | Nokia (Sakira Hassan) |  | V052 | ToDo
B206 | AIML | 1 | Transfer of applicability information in handover command preparatoin |  | Congchi Zhang |  | V011 | Agreed
Z165 | MOB | 1 | No need to introduce ltm-Config-r19 in the CG-Config |  | ZTE (Mengjie Zhang) |  | V009 | ToDo | For this RIL we wait for RAN3 to implement the signalling and then we check.
C165 | MOB | 1 | ltm-ReferenceConfigurationMCG in CG-ConfigInfo should contain the LTM reference configuration to be used at the SCG, but not MCG |  | Rui(CATT) |  | V005 | Agreed
S037 | MOB | 1 | Maintaining the LTM-Config and reference configuration received in INM for Inter-SN LTM | R2-25xxxxx | Samsung(Aby) |  | V014 | Agreed
S036 | MOB | 1 | Upate L1-MeasConfigNRDC with CSI-RS measurement related information. | R2-25xxxxx | Samsung(Aby) |  | V014 | ToDo | This RIL is agreed but we are waiting for UE capabilities to be in the RRC spec.
E053 | NR_SL_relay_multihop-Core | 1 | The field sl-SRAP-ConfigRelay-ToReleaseList-r19 need to be removed |  | Ericsson - Min |  | V007 | ToDo
E058 | SBFD | 1 | Add field descr for startingPRB |  | Ericsson (Håkan) |  |  | ToDo
B002 | RedirToNTN | 1 | Incorrect and missing need code in the description of condition “SIB19” |  | Lenovo (Hyung-Nam) |  | V012 | Agree
B003 | SBFD | 1 | Incorrect constant in the sequence of srs-RSRP-MeasResourceSetToReleaseList-r19 |  | Lenovo (Hyung-Nam) |  | V012 | ToDo
C032 | LPWUS | 1 | Missing description of lpwus-OffsetPreferenceConfig for otherConfig | No | CATT (Da Wang) |  | V016 | PropAgree
C033 | LPWUS | 2 | Changing field timer2 as one optional field | R2-25xxxx | CATT (Da Wang) |  | V016 | PropAgree
OF001 | MIMO | 1 | Update the field description of tci-ServCellIndex under CSI-ReportUE-Initiated |  | Ofinno (Hsin-Hsi) |  | V017 | ToDo
S059 | SONMDT | 1 | Setting noSuitableCellFound for LTM failure |  | Samsung (Aby) |  | V019 | propAgree
S060 | SONMDT | 1 | Target cell need to be associated with ltm-Candidate |  | Samsung (Aby) |  | V020 | propAgree
E057 | LPWUS | 2 | Periodicity in lpwus-Mo1-2-r19 should be in msec instead of slots. |  | Ericsson (Martin) |  | V021 | PropReject
C255 | MIMO | 2 | Capture new RAN1 parameter for mode-A UEIBR |  | CATT (LeiWang) |  | V027 | ToDo
C256 | MIMO | 2 | Update the pusch-ResourceOfModeB-r19 to be a list according to RAN1 RRC parameter |  | CATT (LeiWang) |  | V027 | ToDo
C257 | MIMO | 2 | Update the pusch- PUCCHResource-r19 to be a list according to RAN1 RRC parameter |  | CATT (LeiWang) |  | V027 | ToDo
Z357 | SBFD | 1 | Add NW configuration restriction to the sbfd-RSRP-ThresholdMsg1-RepetitionNumX-r19 |  | Yu Pan(ZTE) |  | V028 | ToDo
N141 | MOB | 2 | CLTM execution conditions |  | Endrit Dosti (Nokia) |  | V029 | PropReject | I honestly think there is no necessity to have such flexibility. My guess is that most of the time you will stick with the execution conditions which you use.
B123 | MOB | 1 | Resume LTM execution condition evaluation after completing cell switch | R2-xxxxx | Lianhai(Lenovo) |  | V032 | PropReject | This was discussed in the last RAN2 meeting and the outcome was that network can triggered again at the UE to re-estart to evaluate the execution conditions.
S063 | NES | 1 | offsetToCarrier-r19 and carrierBandwidth-r19 configuration for OD-SIB1 | R2-xxxxx | Anil Agiwal(Samsung) |  | 35 | ToDo
F001 | NES | 1 | UE support of UL carrier for on-demand SIB1 request |  | Fujitsu (Katsunari Uemura) |  | 36 | ToDo
F002 | NES | 1 | UE support of UL carrier for on-demand SIB1 request |  | Fujitsu (Katsunari Uemura) |  | 36 | ToDo
K104 | MIMO | 2 |  |  | ASUSTeK (Xinra) |  | V038 | ToDo
K105 | MIMO | 1 | Unecessary flexibility on PUCCH Cell configuration for UEI beam reporting |  | ASUSTeK (Xinra) |  | V038 | ToDo
K106 | MIMO | 1 | Unclear Serving Cell association with pusch-ResourceOfModeB |  | ASUSTeK (Xinra) |  | V038 | ToDo
E059 | LPWUS | 1 | Clarification for UE supporting OFDM and OOK with different minimum time gaps |  | Ericsson (Martin) |  | V039 | ToDo
E060 | LPWUS | 1 | Clarification for the time offsets configured with lpwus-LoFrameOffsetList and the LO selected by the UE to monitor LP-WUS |  | Ericsson (Martin) |  | V039 | ToDo
Z104 | NES | 1 | Clarify the issue in section 5.5.2.10 |  | Jie Tan |  | V042
Z105 | NES | 1 | Alignment of IE names with 38.211 and 38.213 |  | Jie Tan |  | V042
Z106 | NES | 1 | Clarification on od-ssb-SFN-Offset |  | Jie Tan |  | V042
S061 | NES | 1 | Field description for halfFrameIndex in OD-SSB-Config IE |  | Samsung (Santanu) |  | V053 | ToDo
S062 | NES | 1 | Need codes for OD-SSB SFN-Offset and halfFrameIndex fields in OD-SSB-Config IE |  | Samsung (Santanu) |  | V053 | ToDo
H353 | SBFD | 1 | RAN1 spec reference correction | - | Huawei-Tao Cai |  | V050 | ToDo
H354 | SBFD | 0 | missing "-r19" suffix | - | Huawei-Tao Cai |  | V050 | ToDo
H355 | SBFD | 0 | missing "-r19" suffix | - | Huawei-Tao Cai |  | V050 | ToDo
A501 | SL Relay | 1 | How to use paging ID list in SUI procedure is missing | R2-25XXXXX | Zhibin Wu (Apple) |  | V052 | ToDo
A501 | SL Relay | 1 | Intermiedate relay UE report SUI | R2-25XXXXX | Zhibin Wu (Apple) |  | V052 | ToDo
S064 | AIML | 1 | Description of event A1 |  | Aby K Abraham |  | V058 | ToDo
S065 | AIML | 1 | Defenition of event A2 |  | Aby K Abraham |  | V058 | ToDo
S066 | AIML | 1 | Update of field description of dataCollectionRequest |  | Seung-Beom |  | V058 | ToDo
S067 | AIML | 1 | Description of UAI for applicability status change |  | Youn Heo |  | V058 | ToDo
S068 | AIML | 1 | Field description of mappingToResourcesForChannelPrediction |  | Youn Heo |  | V058 | ToDo
S069 | AIML | 1 | Field description of associatedIdForChannelMeasurement |  | Youn Heo |  | V058 | ToDo
OF002 | SBFD | 1 | Update the field description of p0AlphaSetforPUSCH-SBFD, p0AlphaSetforPUCCH-SBFD, p0AlphaSetforSRS-SBFD under Uplink-PowerControl |  | Ofinno (Jae-Nam) |  | V051 | ToDo
Y001 | NTN | 2 | UE behaviour upon smtc selection |  | Toyota (Kai-Erik Sunell) |  | V061
Y002 | NTN | 2 | Spare choice entries in ApplicabilityReport |  | Toyota (Kai-Erik Sunell) |  | V061
N142 | MOB | 1 | L3 Execution conditions for LTM | R2-25XXXXX | Srinivasan Selvaganapathy(Nokia) |  | V055 | PropReject | I guess there is no need for this clarifiation as the signalling already is clear