## Cover sheet
3GPP TSG-RAN5 Meeting #109 | [7 empty] | R5-256219
Dallas, United States, 17th Nov 2025 - 21st Nov 2025
Agenda Item: | 7.5.2
Source: | Samsung
Title: | WP UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2)
Work item code: | NR_HST_FR2_enh-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to ‘NR_HST_FR2_enh’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover Signalling, RF, Demod and RRM conformance test specifications for NR_HST_FR2_enh.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 36% | 0 | 6
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR2) |  | 36.2% | 0 | 6
FR2 |  | 36.2% | 0 | 6
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2 | 5% |  |  | 5%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx | 0% |  |  | 0%
FR2 RF Rx test cases | 38.521-2 Rx | 63.6% | 0 | 1 | 63.6% | 0 | 1
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533 | 33.3% | 0 | 5 | 33.3% | 0 | 5
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 10% |  |  | 10%
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
5 References
[1] RP-240371 | New WID on UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_HST_FR2_enh-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to ‘NR_HST_FR2_enh’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover Signalling, RF, Demod and RRM conformance test specifications for NR_HST_FR2_enh.
WP Resp: |  | Runsen Tang |  |  | runsen.tang@samsung.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR2
36.2%
15
8.4
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | Mutil clauses | Addition of new PC6 UE capability for Rel-18 HST FR2 test cases | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. | Samsung,Nokia, Apple, etc. | TBD | R5-245806 |  | 1 | 5% | 5% |  | 5%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-2 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 Tx | 6.2A.2.0.x | Maximum output power reduction for power class 6 | Introduce MPR requirement for PC6 |  | TBD |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.2A.3.0.3.x | A-MPR for CA_NS_202 for power class 6 | Introduce intra-band contiguous CA, A-MPR for CA_NS_202 |  | TBD |  |  | 0.1 | 0% | 0% |  | 0%
TBD |  | 38.521-2 Tx | 6.3A.1.0 | Minimum conformance requirements | Introduce minimum output power requirements for CA for PC 6. |  | TBD |  | 38.101-2 refer to PC5, but PC5 in 38.521-2 missed. | TBD
TBD |  | 38.521-2 Tx | 6.4A.2.2.0.x | Carrier leakage for power class 6 | Introduce the carrier leakage requirements for intra-band contiguous and non-contiguous carrier aggregation for PC6. |  | TBD |  | 38.101-2 refer to PC5, but PC5 in 38.521-2 missed. | TBD
TBD |  | 38.521-2 Tx | 6.4A.2.3.0.x | In-band emissions for power class 6 | Introduce the average of the in-band emission requirements for intra-band contiguous and non-contiguous carrier aggregation for PC6. |  | TBD |  | 38.101-2 refer to PC5, but PC5 in 38.521-2 missed. | TBD
TBD |  | 38.521-2 Tx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-2 Tx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  | R5-251553 fix HST FR2 flag R5-251554 fix HST FR2 flag | TBD
TBD | Y | 38.521-2 Tx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 Rx | 7.3K | Spherical coverage requirement for simultaneous reception from multiple directions | New sub-clause header |  | TBD |  |  | 0.1 | 100% | 100% |  | 100%
TBD | Y | 38.521-2 Rx | 7.3K.x | 2AoA spherical coverage for power class 6 | introduce 2AoA spherical coverage requirement for PC6 UE in new clause 7.3K | Apple | RAN5#107 (May-25) | R5-245461 |  | 1 | 60% | 60% |  | 60%
TBD |  | 38.521-2 Rx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-2 Rx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-2 Rx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-3 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
|  | 38.521-3 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-3 Tx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-3 Tx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-3 Tx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Rx
|  | 38.521-3 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-3 Rx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-3 Rx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-3 Rx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-4: Demod/CSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-4 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-4 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-4 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.522 | 4 | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. |  | TBD | R5-245916 |  | 0.1 |  |  |  | 10%
TBD |  | 38.522 | 4.1 | [10 empty] | 0%
TBD |  | 38.522 | 4.2 |  |  |  |  | R5-245916 | [5 empty] | 10%
[11 empty] | 0% | 0% |  | 0%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD | Y | 38.533 | 7.1.1.8 | Cell reselection to FR2 inter-frequency NR case for UE configured with highSpeedMeasFlagFR2-r17 | to verify the requirement for the inter frequency NR cell reselection requirements for UE that supports Idle mode inter-frequency measurement enhancement for HST in FR2 | Nokia | RAN5#107 (May-25) | R5-244549 | Test tolerance and measurement uncertainty analysis are missing | 1 | 90% | 90% |  | 90%
TBD | Y | 38.533 | 7.5.8.3.2 | NR PCell FR2 HST active TCI state switch for PC6 UE supporting [highSpeedTCISwitchEnhMAC-CE-FR2-r18] a known TCI state | to verify the active TCI state switch delay requirement defined in clause 8.10.3 applicable for FR2 power class 6 UE | Nokia | RAN5#107 (May-25) | R5-244550 | Test tolerance and measurement uncertainty analysis are missing | 1 | 90% | 90% |  | 90%
TBD | Y | 38.533 | 7.6.1.x | SA event triggered reporting test without gap under non-DRX for power class 6 UE supporting [measurementEnhancementCAInterFreqFR2-r18] | The purpose of this test is to verify that the UE makes correct reporting of an event. This test will partly verify the SA SCC intra-frequency NR cell measurement requirements for FR2 power class 6 UE which is configured with highSpeedMeasFlagFR2-r17 and supports [measurementEnhancementCAInterFreqFR2-r18] in clause 9.2.5. |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.533 | 7.6.2.x | SA event triggered reporting tests for FR2 without SSB time index detection when DRX is not used (PCell in FR2) for FR2 power class 6 UE configured with highSpeedMeasFlagFR2-r17 | The purpose of this test is to verify that the UE makes correct reporting of an event. This test will partly verify the SA inter-frequency NR cell search requirements for FR2 power class 6 UE which is configured with highSpeedMeasFlagFR2-r17 and supports [measurementEnhancementCAInterFreqFR2-r18] in clause 9.3.4 |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.533 | 7.6.3.x | SSB based L1-RSRP measurement when DRX is used for power class 6 UE supporting SimultaneousReceptionFR2HST-r18 | The purpose of this test is to verify that the power class 6 UE supporting SimultaneousReceptionFR2HST-r18 makes correct reporting of L1-RSRP measurement when highSpeedMeasFlagFR2-r17 is configured, and when highSpeedDeploymentTypeFR2-r17 is configured as bidirectional. This test will partly verify the L1-RSRP measurement requirements for power class 6 UE configured with highSpeedMeasFlagFR2-r17 for FR2 in clause 9.5.4.1 with the testing configurations for NR cells in Table A.7.6.3.X.1-1. | Samsung | RAN5#107 (May-25) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.533 | E.5 | Cell configuration mapping for SA FR2 test cases in Chapter 7 |  | Nokia,Samsung,etc. | RAN5#108 (Aug-25) | R5-244549 R5-244550 |  | 1 |  |  |  | 20%
TBD | Y | 38.533 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
Layer 2
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
RRC
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
NAS
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  | 0.1
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.