## Cover sheet
3GPP TSG-RAN5 Meeting #109 | [10 empty] | R5-256221
Dallas, United States, 17th Nov 2025 - 21st Nov 2025
Agenda Item: | 7.5.2
Source: | Samsung, Huawei, China Telecom
Title: | WP UE Conformance - NR MIMO Evolution for Downlink and Uplink
Work item code: | NR_MIMO_evo_DL_UL-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WI ‘NR_MIMO_evo_DL_UL’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover RF, Demod and RRM conformance test specifications for NR_MIMO_evo_DL_UL.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 75% (+14%) | 7 (+4) | 20
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 74.1% (+12.6%) | 6 (+4) | 17
FR1 |  | 78.9% (+11.1%) | 3 (+1) | 9
FR2 |  | 68.6% (+14.2%) | 3 (+3) | 8
NSA Option 3 (EN-DC) |  | 75.8% (+17.7%) | 1 | 7
FR1 |  | 92.3% (+0.4%) | 0 | 2
FR2 |  | 62.6% (+31.6%) | 1 | 5
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [6 empty] | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  |  | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases |  | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 70% (+25%) | [12 empty] | 70% (+25%)
Common ICS | 38.508-2 | 75% (+5%) | [5 empty] | 70% | [6 empty] | 90% (+20%)
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2 | 43.5% (+43.5%) | 0 | 4 |  |  |  | 43.2% (+43.2%) | 0 | 4 |  |  |  |  | 44.5% (+44.5%) | 0 | 4
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4 | 80.5% (+11%) | 2 | 6 | 75.9% (+13.5%) | 2 | 6 |  |  |  |  | 100%
RRM test cases | 38.533 | 97.5% (+5%) | 1 (+1) | 2 |  |  |  | 97.5% (+5%) | 1 (+1) | 2
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 60% (+20%) |  |  | 60% (+20%) |  |  | 60% (+20%) |  |  |  | 60% (+20%) |  |  | 60% (+20%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-250103 | Revised WID on UE Conformance – NR MIMO Evolution for Downlink and Uplink
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - NR MIMO Evolution for Downlink and Uplink | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_MIMO_evo_DL_UL-UEConTest
WP Scope: |  | <WP Scope description> | [13 empty] | vs Area
WP Resp: |  | Runsen Tang, Yaping Zhang, Jingzhou Wu |  |  | runsen.tang@samsung.com, zhangyaping13@huawei.com, wujingzhou@chinatelecom.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | NSA Option 3 (EN-DC)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 | FR2
[15 empty] | 78.9% (+11.1%) | 68.6% (+14.2%) | 92.3% (+0.4%) | 62.6% (+31.6%)
[15 empty] | 23 | 20 | 10 | 13
[15 empty] | 16.4 | 14.5 | 5.4 | 6.7
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.508-1 | 7.3.1 | <Title of new sub-clause header> | New sub-clause header | Huawei, Hisilicon | TBD | R5-254462 |  | 0.1 | 90% |  | 90% |  |  |  |  | 90%
|  | 38.508-1 | 5.4.2 | Radio resource control information elements for Demodulation Performance and CSI reporting tests | Codebook config adding | Ericsson, China Telecom | TBD | R5-256803 |  | 0.1 | 50% (+50%) |  | 50% (+50%) |  |  |  |  | 50%
TBD |  | 38.508-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.508-2 | A.4.3.2 | Physical Layer Baseline Implementation Capabilities | adding new Physical Layer Baseline Implementation Capabilities | China Telecom Nokia Huawei | TBD | R5-245808 R5-245809 R5-246941 R5-247711 R5-251908 R5-254463 R5-255651 |  | 1 | 80% (+10%) | 70% | 90% (+20%) |  |  | 70% |  | 90%
TS 38.509: Special test methods
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.509 | 5 | UE special conformance test functions operation | Support locking multiple TX beams from multiple panels simultaneously | Nokia, Apple, Keysight |  | R5-253401 |  | 1 | 80% | 80% |  |  |  | 80%
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 | 3.2 | Symbols | Add new symbols for StxMP related requirements. | Samsung | TBD |  |  | 0.1 | 0% | 0% | 0% |  |  | 0% |  | 0%
TBD |  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Add MU and TT for test cases | Multiple | TBD | R5-256836 |  | 0.1 | 30% (+30%) | 0% | 60% (+60%) |  |  | 0% |  | 60%
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 | 6.1 | General | add discription for simultaneous transmission to multiple directions | Ericsson | TBD | R5-256833 |  | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  |  | 100% |  | 100%
TBD |  | 38.521-2 | 6.2K | Transmitter power for simultaneous transmission to multiple directions | add sub-title | Ericsson | RAN5#107 (May-25) | R5-256916 |  | 0.1 | 100% (+100%) | 100% (+100%) | 100% (+100%) |  |  | 100% |  | 100%
TBD | Y | 38.521-2 | 6.2K.1 | UE maximum output power for simultaneous transmission to multiple directions | new test case for UE maximum output power for simultaneous transmission to multiple directions | Ericsson | RAN5#107 (May-25) | R5-256916 |  | 1 | 80% (+80%) | 80% (+80%) | 80% (+80%) |  |  | 80% |  | 80%
TBD | Y | 38.521-2 | 6.2K.2 | UE maximum output power reduction for simultaneous transmission to multiple directions | new test case for UE maximum output power reduction for simultaneous transmission to multiple directions | Ericsson, Apple | RAN5#107 (May-25) | R5-256834 R5-256835 |  | 1 | 90% (+90%) | 90% (+90%) | 90% (+90%) |  |  | 90% |  | 90%
TBD | Y | 38.521-2 | 6.2K.3 | UE maximum output power with additional requirements for simultaneous transmission to multiple directions | new test case for UE maximum output power with additional requirements for simultaneous transmission to multiple directions | Ericsson | RAN5#107 (May-25) |  |  | 1 | 0% | 0% | 0% |  |  | 0% |  | 0%
TBD | Y | 38.521-2 | 6.2K.4 | Configured transmitted power for simultaneous transmission to multiple directions | new test case for Configured transmitted power for simultaneous transmission to multiple directions | Ericsson | RAN5#107 (May-25) |  |  | 1 | 0% | 0% | 0% |  |  | 0% |  | 0%
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-2 Rx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-2 Rx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-2 Rx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-4: Demod/CSI reporting test cases
TBD |  | 38.521-4 | 5 | Demodulation performance requirements (Conducted requirements) | Clause header |  |  |  |  | 0
TBD |  | 38.521-4 | 5.1.1.3 | Applicability of requirements for optional UE features | Add the requirements applicability for enhanced DMRS | CTC | TBD | R5-250414 |  | 0.5 | 100% | 100% |  |  | 100%
TBD |  | 38.521-4 | 5.1.1.4 | Applicability of requirements for mandatory UE features with capability signalling | Add sub-test of enhanced DMRS | CTC | TBD | R5-250414 |  | 0.5 | 100% | 100% |  |  | 100%
TBD |  | 38.521-4 | 5.1.1.X | Applicability of requirements with enhanced DMRS | Add the applicability rule for enhanced DMRS | CTC | TBD |  |  | 1 | 0% | 0% |  |  | 0%
TBD |  | 38.521-4 | 5.2.2.1.1_4 | 2Rx FDD FR1 PDSCH mapping Type A performance | Add PDSCH Performance requirements of Rel-18 enhanced DMRS for FR1 2Rx | Huawei, CTC | RAN5#104 (Aug-24) | R5-244150 R5-250813 |  | 1 | 100% | 100% | 100% |  | 100% |  | 100%
TBD |  | 38.521-4 | 5.2.2.2.1_4 | 2Rx TDD FR1 PDSCH mapping Type A performance | Add PDSCH Performance requirements of Rel-18 enhanced DMRS for FR1 2Rx | Huawei | TBD | R5-246944 R5-250813 |  | 1 | 100% | 100% | 100% |  | 100% |  | 100%
TBD |  | 38.521-4 | 5.2.3.1.1_6 | 4Rx FDD FR1 PDSCH mapping Type A performance | Add PDSCH Performance requirements of Rel-18 enhanced DMRS for FR1 4Rx | Huawei | TBD | R5-246945 R5-250813 |  | 1 | 100% | 100% | 100% |  | 100% |  | 100%
TBD |  | 38.521-4 | 5.2.3.2.1_6 | 4Rx TDD FR1 PDSCH mapping Type A performance | Add PDSCH Performance requirements of Rel-18 enhanced DMRS for FR1 4Rx | CTC | TBD | R5-251910 |  | 1 | 100% | 100% |  |  | 100%
TBD |  | 38.521-4 | 6 | CSI reporting requirements (Conducted requirements) | Clause header |  |  | R5-256871 |  | 0
TBD |  | 38.521-4 | 6.1.1.3 | Applicability of requirements for optional UE features | Add the requirements applicability for Enhanced Type II Codebook | CTC | TBD | R5-250415 |  | 0.5 | 100% | 100% |  |  | 100%
TBD |  | 38.521-4 | 6.1.1.4 | Applicability of requirements for mandatory UE features with capability signalling | Add sub-tests of Enhanced Type II Codebook | CTC | TBD | R5-250415 R5-255971 |  | 0.5 | 100% | 100% |  |  | 100%
TBD |  | 38.521-4 | 6.3.2 | 2RX requirements | Sub-clause header |  |  |  |  | 0
TBD | Y | 38.521-4 | 6.3.2.1.8 | 2Rx FDD FR1 Multiple PMI with 16TX Enhanced Type II codebook for predicted PMI | Add PMI reporting requirements for Enhanced Type II Codebook (eType-II) based on doppler CSI | CTC | TBD | R5-256871 |  | 1 | 90% (+90%) | 90% (+90%) |  |  | 90%
TBD | Y | 38.521-4 | 6.3.2.1.9 | 2Rx FDD FR1 Multiple PMI with 8 ports Enhanced Type II Codebook for CJT | Add PMI reporting requirements for Enhanced Type II Codebook (eType-II) for multi-TRP CJT | Huawei | TBD | R5-247843 R5-250814 |  | 1 | 100% | 100% |  |  | 100%
TBD | Y | 38.521-4 | 6.3.2.2.9 | 2Rx TDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for predicted PMI | Add PMI reporting requirements for Enhanced Type II Codebook (eType-II) based on doppler CSI | Ericsson | TBD | R5-256873 |  | 1 | 90% (+90%) | 90% (+90%) |  |  | 90%
TBD |  | 38.521-4 | 6.3.3 | 4RX requirements | Sub-clause header |  |  |  |  | 0
TBD | Y | 38.521-4 | 6.3.3.1.8 | 4Rx FDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for predicted PMI | Add PMI reporting requirements for Enhanced Type II Codebook (eType-II) based on doppler CSI | Ericsson | TBD |  |  | 1 | 0% | 0% |  |  | 0%
TBD | Y | 38.521-4 | 6.3.3.1.9 | 4Rx FDD FR1 Multiple PMI with 8 ports Enhanced Type II Codebook for CJT | Add PMI reporting requirements for Enhanced Type II Codebook (eType-II) for multi-TRP CJT | Huawei | TBD | R5-247842 R5-250814 |  | 1 | 100% | 100% |  |  | 100%
TBD | Y | 38.521-4 | 6.3.3.2.8 | 4Rx TDD FR1 Multiple PMI with 16Tx Enhanced Type II codebook for predicted PMI | Add PMI reporting requirements for Enhanced Type II Codebook (eType-II) based on doppler CSI | Ericsson | TBD |  |  | 1 | 0% | 0% |  |  | 0%
TBD |  | 38.521-4 | Annex A | Measurement channels | Clause header |  |  |  |  | 0
TBD |  | 38.521-4 | A.3.2.1.1 | Reference measurement channels for SCS 15 kHz FR1 | Add PDSCH Reference Channel for enhanced DMRS for FR1 4Rx FDD | CTC | RAN5#104 (Aug-24) | R5-246006 |  | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
TBD |  | 38.521-4 | A.3.2.2.2 | Reference measurement channels for SCS 30 kHz FR1 | Add PDSCH Reference Channel for enhanced DMRS for FR1 4Rx TDD | CTC | RAN5#104 (Aug-24) | R5-246006 |  | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
TBD |  | 38.521-4 | Annex B | Propagation conditions | Clause header |  |  |  |  | 0
TBD |  | 38.521-4 | B.2.2 | Combinations of channel model parameters | Add Propagation channel for Enhanced Type II Codebook (eType-II) based on doppler CSI | CTC | RAN5#104 (Aug-24) | R5-246006 |  | 0.1 | 100% | 100% | 100% |  | 100% |  | 100%
TBD |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances for FR1 | Add MU and TT for Demod TCs | CTC | RAN5#104 (Aug-24) | R5-256871 |  | TBD | 60% (+60%) | 60% (+60%) | 60% (+60%) |  | 60% |  | 60%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.522 | multi clauses | addition of applicability for new test cases | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. | CTC Nokia Huawei Xiaomi Ericsson | TBD | R5-244142 R5-245918 R5-246946 R5-246982 R5-250815 R5-256923 R5-256922 R5-253590 R5-254464 R5-256925 |  | 0.1 | 60% (+20%) | 60% (+20%) | 60% (+20%) |  | 60% | 60% | 60% | 60%
TS 38.533: RRM test cases
|  | 38.533 | 3 | Definitions, symbols and abbreviations | TS 38.133 cl.3 |  | TBD |  |  | 1
|  | 38.533 | 4.4 | Timing | Sub-clause header |  |  |  |  | 0
|  | 38.533 | 4.4.1 | UE transimit timing | Sub-clause header |  |  |  |  | 0
| Y | 38.533 | 4.4.1.3 | EN-DC FR1 UE Transmit Timing Test for two TRPs | New test case for EN-DC FR1 UE transmit timing from two TRPS | Nokia | TBD | R5-244562 | Test requirements shall be updated Test tolerance and measurement uncertainty analysis are missing | 1 | 80% |  | 80% |  |  |  | 80%
|  | 38.533 | 4.7 | Measurement performance requirements | Sub-clause header |  |  |  |  | 0
|  | 38.533 | 4.7.X | TDCP amplitude measurement accuracy | New sub-clause header |  |  |  |  | 0
| Y | 38.533 | 4.7.X.1 | EN-DC FR1 TDCP amplitude measurement accuracy | Introduce new test case for EN-DC FR1 TDCP | Xiaomi | TBD | R5-250778 |  | 1 | 80% |  | 80% |  |  |  | 80%
|  | 38.533 | 5.4 | Timing | Sub-clause header |  |  |  |  | 0
|  | 38.533 | 5.4.1 | UE transimit timing | Sub-clause header |  |  |  |  | 0
| Y | 38.533 | 5.4.1.X | EN-DC FR2 UE Transmit Timing Test with 2-TA for FR2 UE supporting multiDCI-IntraCellMultiTRP-TwoTA-r18 | New test case for EN-DC FR2 UE transmit timing from two TRPS | Xiaomi | TBD | R5-251646 |  | 1 | 100% |  | 100% |  |  |  |  | 100%
|  | 38.533 | 6.4 | Timing | Sub-clause header |  |  |  |  | 0
|  | 38.533 | 6.4.1 | UE transimit timing | Sub-clause header |  |  |  |  | 0
| Y | 38.533 | 6.4.1.X | NR SA FR1 UE Transmit Timing Test for two TRPs | New test case for NR SA FR1 UE transmit timing from two TRPS | Nokia | TBD | R5-24XXXX |  | 1 | 80% | 80% |  |  | 80%
|  | 38.533 | 6.5 | Signaling characteristics | Sub-clause header |  |  |  |  | 0
|  | 38.533 | 6.5.13 | Active TCI state switch delay | New sub-clause header |  |  |  |  | 0
| Y | 38.533 | 6.5.13.1 | NR SA FR1 MAC-CE based joint TCI state switch for mDCI with two TA when RTD is larger than CP | Joint TCI state for mDCI based multi-TRP | Huawei | TBD | R5-252444 R5-254465 R5-254466 R5-256024 |  | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
|  | 38.533 | 6.7 | Measurement performance requirements | Sub-clause header |  |  |  |  | 0
|  | 38.533 | 6.7.X | TDCP amplitude measurement accuracy | New sub-clause header |  |  |  |  | 0
| Y | 38.533 | 6.7.X.1 | NR SA FR1 TDCP amplitude measurement accuracy | Introduce new test case for NR SA FR1 TDCP | Xiaomi | TBD | R5-250779 |  | 1 | 80% | 80% |  |  | 80%
|  | 38.533 | 7.4 | Timing | Sub-clause header |  |  |  |  | 0
|  | 38.533 | 7.4.1 | UE transimit timing | Sub-clause header |  |  |  |  | 0
| Y | 38.533 | 7.4.1.3 | NR SA FR2 UE Transmit Timing Test with 2-TA for UE supporting multiDCI-IntraCellMultiTRP-TwoTA-r18 | New test case for NR SA FR2 UE transmit timing from two TRPS | Nokia | RAN5#107 (May-25) | R5-246983 R5-252182 |  | 1 | 95% | 95% |  |  |  | 95%
|  | 38.533 | 7.5 | Signaling characteristics | Sub-clause header |  |  |  |  | 0
|  | 38.533 | 7.5.13 | Unified TCI state switch delay | Sub-clause header |  |  |  |  | 0
| Y | 38.533 | 7.5.13.4 | NR SA FR2 sDCI MAC-CE based joint TCI state switching | Joint TCI state for sDCI based multi-TRP | Huawei | TBD | R5-252445 R5-254465 R5-254466 R5-256025 |  | 1 | 100% (+10%) | 100% (+10%) |  |  |  | 100%
|  | 38.533 | 7.5.13.5 | MAC-CE based dual downlink TCI state switching delay for unified TCI for single-DCI mTRP | New sub-clause header |  |  |  |  | 0
| Y | 38.533 | 7.5.13.5.1 | NR SA FR2 PCell dual downlink TCI state switch in sDCI for known case | Separate DL TCI state for sDCI based multi-TRP | Huawei | TBD | R5-252446 R5-254465 R5-254466 R5-256025 |  | 1 | 100% (+10%) | 100% (+10%) |  |  |  | 100%
|  | 38.533 | 7.5.13.6 | MAC-CE based active uplink TCI state switch for single-DCI mTRP | New sub-clause header |  |  |  |  | 0
| Y | 38.533 | 7.5.13.6.1 | NR FR2 PCell uplink TCI state switch for two known TCI states | Separate UL TCI state for sDCI based multi-TRP | Nokia | RAN5#107 (May-25) | R5-245885 R5-247904 R5-256023 | Message contents are FFS Test tolerance analysis and measurement uncertainty are missing | 1 | 100% (+5%) | 100% (+5%) |  |  |  | 100%
|  | 38.533 | A.1.4A | CSI-RS for tracking | Add CSI-RS configurations for RRM test cases | Nokia |  | R5-245884 R5-254466 R5-254467 | [7 empty] | 100%
|  | 38.533 | A.3 | Reference SSB configuration | Add SSB configurations for RRM test cases |  | TBD |  |  | 1 | 100% | 100% |  |  |  | 100%
|  | 38.533 | A.9 | Angle of Arrival (AoA) for FR2 RRM test cases | Add AoA setup | Nokia | TBD | R5-245884 |  | 1 | 0% | 0% |  |  |  | 0%
|  | 38.533 | A.10A | Unified TCI State Configuration | Add DLorJoint TCI states and UL states | Nokia | TBD | R5-245884 R5-246985 R5-254466 R5-254467 |  | 1 | 100% | 100% |  |  |  | 100%
|  |  | E |  |  | Nokia, Huawei, CTC, Samsung | TBD | R5-244562
|  |  | F |  |  | Nokia | TBD | R5-246986
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.903 | 8 |  | Addition of Test Tolerance | Nokia Xiaomi Huawei Hisilicon |  | R5-247905 R5-247906 R5-251647 R5-256909 R5-256027 |  | 1 | 30% | 30% |  |  |  | 30%
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.905 | Multiple clauses | <Title of new sub-clause header> | Add applicable test points analysis for MIMO DL UL | Ericsson | TBD | R5-256816 |  | 0.1
TBD |  | 38.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
Layer 2
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
RRC
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
NAS
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  | 0.1
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.