## Cover sheet
3GPP TSG-RAN5 Meeting #109 | [10 empty] | R5-256223
Dallas, United States, 17th Nov 2025 - 21st Nov 2025
Agenda Item: | 7.5.2
Source: | Samsung
Title: | WP - UE Conformance - NR support for high speed train scenario in frequency range 2
Work item code: | NR_HST_FR2-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WI ‘NR_HST_FR2’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover RF, Demod and RRM conformance test specifications for NR_HST_FR2.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+28%) | 25 (+23) | 25
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 100% (+27.6%) | 25 (+23) | 25
FR2 |  | 100% (+27.6%) | 25 (+23) | 25
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases |  |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+50%) | [5 empty] | 100% (+50%)
Common ICS | 38.508-2 | 100% | [5 empty] | 100%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2 | 100% (+33.3%) | [5 empty] | 100% (+33.3%)
FR2 RF Tx test cases | 38.521-2 Tx | 100% (+44.8%) | 16 (+16) | 16 |  |  |  | 100% (+44.8%) | 16 (+16) | 16
FR2 RF Rx test cases | 38.521-2 Rx | 100% (+5%) | 2 (+2) | 2 |  |  |  | 100% (+5%) | 2 (+2) | 2
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4 | 100% (+4.2%) | 2 (+1) | 2 |  |  |  | 100% (+4.2%) | 2 (+1) | 2
RRM test cases | 38.533
Applicability RF. Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-251017 | Revised WID on UE Conformance - NR support for high speed train scenario in frequency range 2 (FR2)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP - UE Conformance - NR support for high speed train scenario in frequency range 2 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_HST_FR2-UEConTest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to WI ‘NR_HST_FR2’, by analysing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover RF, Demod and RRM conformance test specifications for NR_HST_FR2. | [12 empty] | vs Area
WP Resp: |  | Runsen Tang, Siddharth Das |  |  | runsen.tang@samsung.com, siddharth.1.das@nokia.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  |  | FR2
100% (+27.6%)
[14 empty] | 0 | 48 (-2)
[14 empty] | 0 | 36.2 (-2)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
LTE RF/RRM
LTE RAN and CN protocols
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.6.3 | Radio resource control information elements | adding release-17 PC6 HST FR2 radio resource control information element | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-233674 | R5-233674, add servingCellConfigCommonSIB, and HighSpeedConfigFR2. | 0.1 | 100% | 100% |  |  | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
3 |  | 38.508-2 | A.4 | High Speed Capabilities | adding release-17 PC6 HST FR2 capabilities | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-232238 R5-234336 R5-236211 | R5-232238 add PC6 band support, PC6, and oneshot UL timing capability. R5-234336: Add highSpeedMeasFlabFR2-r17 R5-236211, correction on wording. | 0.1 | 100% | 100% |  |  | 100%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
4 |  | 38.521-2 Annex | Annex F | PC6 FR2 MU - Annex F update in 38.521-2 | PC6 FR2 MU - Annex F update in 38.521-2 | Keysight Technologies | RAN5#104 (Aug-24) | R5-244176 R5-246238 R5-250205 R5-253802 | R5-244176, Updated MU and TT in annex F for the following test cases for PC6: -MOP-EIRP -MOP-TRP -REFESENS – EIS -Added applicable measurement grids in Annex M (leverage of PC1 grids with 6x6 array configuration). R5-246238, Updated MU and TT in annex F for PC6 for test cases 6.2.2, 6.3.1, 6.3.2, 6.5.2.1, 6.5.2.3, 7.5 and 7.6.2. R5-250205 Defined MU and TT in Annex F for OBW, EVM test and spurious tests for PC6 same as for PC5. R5-253802 Update MU and TT in annex F for Tx and REx 1AoA spherical. | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
4 |  | 38.521-2 | 6.2 | MU analysis associated to PC6 1AoA spherical tests | Table numbering of the minimum requirements updated. | Keysight | TBD | R5-253800 |  | 1 |  |  |  |  | 100%
4 |  | 38.521-2 Annex | Annex B | PC6 FR2 MU - Annex B update in 38.521-2 | PC6 FR2 MU - Annex B update in 38.521-2 | Keysight Technologies | RAN5#104 (Aug-24) | R5-246235 | R5-246235, Defined MTSU for PC6 for the following test cases: • MPR • Min Power • OFF power • SEM • ACLR • ACS Case 1 / IBB | 1 |  |  |  |  | 100%
4 |  | 38.521-2 Annex | Annex M | PC6 FR2 MU - Annex M update in 38.521-2 | PC6 FR2 MU - Annex M update in 38.521-2 | Keysight Technologies | RAN5#104 (Aug-24) | R5-244176 R5-253802 R5-251889 R5-253802 | R5-244176, Updated MU and TT in annex F for the following test cases for PC6: -MOP-EIRP -MOP-TRP -REFESENS – EIS -Added applicable measurement grids in Annex M (leverage of PC1 grids with 6x6 array configuration). R5-251889 Defined TRP Grids for Spurious Emissions for PC6 in annex M.4.5. R5-253802 Annex M updated leveraging the same measurement grid requirements for spherical coverage as for beam peak search. | 1 | 100% | 100% |  |  | 100%
TS 38.521-2: FR2 RF test cases - Tx
5 |  | 38.521-2 Tx | 6.1 | General | adding PC6 common uplink configuration | Samsung | RAN5#101 (Nov-23) | R5-246031 |  | 0.1 | 100% | 100% |  |  | 100%
6 |  | 38.521-2 Tx | 6.2.1.0 | General | adding Release-17 FR2 PC6 UE Type | Samsung | RAN5#101 (Nov-23) | R5-246031 |  | 0.1 | 100% | 100% |  |  | 100%
7 | Y | 38.521-2 Tx | 6.2.1.1 | UE maximum output power - EIRP and TRP | adding RF requirement for Release-17 FR2 PC6 UE | Keysight | RAN5#101 (Nov-23) | R5-245929 |  | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
8 | Y | 38.521-2 Tx | 6.2.1.1_1 | UE maximum output power - EIRP and TRP (Rel16 and forward) | adding RF requirement for Release-17 FR2 PC6 UE with beam correspondence side condition | Keysight | RAN5#101 (Nov-23) | R5-245929 | Covered by R5-245929 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
9 | Y | 38.521-2 Tx | 6.2.1.2 | UE maximum output power - Spherical coverage | adding UE spherical coverage for power class 6 | Keysight | RAN5#101 (Nov-23) | R5-245929 R5-253800 | Covered by R5-245929 R5-253800, Test procedure updated with TT and others. | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
10 | Y | 38.521-2 Tx | 6.2.1.2_1 | UE maximum output power - Spherical coverage (Rel16 and forward) | adding UE spherical coverage for power class 6 UE with beam correspondence side condition | Keysight, SGS Wireless | RAN5#101 (Nov-23) | R5-245929 R5-253800 R5-256102 | Covered by R5-245929 R5-253800, Test procedure updated with TT and others. | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
11 | Y | 38.521-2 Tx | 6.2.2 | UE maximum output power reduction | adding Release-17 FR2 PC6 UE MPR | Keysight | RAN5#101 (Nov-23) | R5-246236 | R5-246236, complete TT. | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
12 | Y | 38.521-2 Tx | 6.2.3 | UE maximum output power with additional requirements | adding Release-17 FR2 PC6 UE MPR for NS_202 and NS_203 | Samsung | RAN5#101 (Nov-23) | R5-225771 R5-231665 R5-256233 | R5-225771 add core for NS_202/203. R5-231665 add test config for NS202/203. | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
13 | Y | 38.521-2 Tx | 6.3.1 | Minimum output power | adding Release-17 FR2 PC6 Minimum output power | Samsung | RAN5#101 (Nov-23) | R5-225773 R5-231667 R5-246236 | R5-225773 add core for min out power. R5-231667 add test config for min outpower. R5-246236 clear TT | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
14 | Y | 38.521-2 Tx | 6.4.2.2 | Carrier leakage | adding Release-17 FR2 PC6 Carrier leakage | Samsung | RAN5#101 (Nov-23) | R5-225774 R5-231668 | R5-225774 add core for carrier leakage. R5-231668 test config/req for carrier leak. | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
15 | Y | 38.521-2 Tx | 6.4.2.3 | In-band emissions | adding Release-17 FR2 PC6 In-band emissions | Samsung | RAN5#101 (Nov-23) | R5-225775 R5-231669 R5-256229 | R5-225775 add core for IBE. R5-231669 test config/req for IBE. | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
16 | Y | 38.521-2 Tx | 6.2D.1.1 | UE maximum output power - EIRP and TRP for UL MIMO | adding Release-17 FR2 PC6 UE maximum output power for UL MIMO | Samsung | RAN5#101 (Nov-23) | R5-225772 R5-231666 R5-256231 | R5-225772 add core for MOP and spherical coverage of UL MIMO. R5-231666 add test config/req for MOP. | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
17 | Y | 38.521-2 Tx | 6.2D.1.2 | UE maximum output power - Spherical coverage for UL MIMO | adding Release-17 FR2 PC6 UE spherical coverage for UL MIMO | SGS Wireless, Samsung | RAN5#101 (Nov-23) | R5-232515 R5-256232 | R5-232515 add test config/req for spherical cov. | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
18 | Y | 38.521-2 Tx | 6.2D.2 | UE maximum output power reduction for UL MIMO | adding Release-17 FR2 PC6 UE maximum output power reduction for modulation / channel bandwidth for UL MIMO | Samsung | RAN5#101 (Nov-23) | R5-246026 R5-256226 | R5-246026 | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
19 | Y | 38.521-2 Tx | 6.2D.3 | UE maximum output power with additional requirements for UL MIMO | adding Release-17 FR2 PC6 UE maximum output power with additional requirements for UL MIMO | Samsung | RAN5#101 (Nov-23) | R5-256227 |  | 1 | 100% (+100%) | 100% (+100%) |  |  | 100%
20 | Y | 38.521-2 Tx | 6.3D.1 | Minimum output power for UL MIMO | adding Release-17 FR2 PC6 Minimum output power for UL MIMO | SGS Wireless, Samsung | RAN5#101 (Nov-23) | R5-232516 R5-256893 | R5-232516 add test config/req for MOP. | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
21 | Y | 38.521-2 Tx | 6.6 | Beam correspondence | adding Release-17 FR2 PC6 Beam correspondence | Samsung, SGS Wireless | RAN5#101 (Nov-23) | R5-243652 R5-255274 | R5-243652, Measurement Uncertainty and Test Tolerances are FFS. - OTA test procedure for UL MIMO is still under investigation - TP analysis is FFS. R5-255274 Add SSB-based and CSI-RS based enhanced beam correspondance requirements. | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
22 | Y | 38.521-2 Tx | Multi places | Multi sections | Checking all test cases and adding PC6 to configuration tables where 'inner full configuration' is used for testing | KeySight, Samsung | RAN5#101 (Nov-23) | R5-245730 R5-246030 R5-250203 R5-246236 R5-246237 R5-250204 | R5-245730 Adding PC6 in section 6.2.5, 6.3.3.2, 6.4.2.6, 6.5.2.1_1, 6.5.3.2, 6.5.3.2_1,6.5.3.3, 6.5.3.3_1 Adding missing PC6 in section 6.4D.2.2, 6.4D.2.3, 6.4.2.3 R5-246030 Adding absolute power tolerance power class 6 information Adding aggregate power tolerance power class 6 information R5-246236, Updated editor’s notes, requirements and TTs for PC6 in the folowwing Tx test cases: • MPR • Min Power • OFF power • SEM • ACLR R5-246237, Updated editor’s notes, requirements and TTs for PC6 in the folowwing Rx test cases: • ACS Case 1 • IBB R5-250203 Defined MU and TT for OBW, EVM test and TX spurious tests for PC6 same as for PC5. Tests definitions updated accordingly. R5-250204 Defined MU and TT for RX spurious tests for PC6 same as for PC5. Test defintion updated accordingly. | 1 | 100% (+70%) | 100% (+70%) |  |  | 100%
TBD | Y | 38.521-2 Tx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-2: FR2 RF test cases - Rx
23 | Y | 38.521-2 Rx | 7.3.2 | Reference sensitivity power level | adding Release-17 FR2 PC6 Reference sensitivity power level | SGS Wireless | RAN5#101 (Nov-23) | R5-234228 R5-244175 R5-253801 | R5-234228, add Refsens core and test. R5-244175, add TT. R5-253801, Test procedure updated with TT and others. | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
24 | Y | 38.521-2 Rx | 7.3.4 | EIS spherical coverage | adding Release-17 FR2 PC6 EIS spherical coverage | SGS Wireless | RAN5#101 (Nov-23) | R5-235667 R5-253801 | R5-235667 add EIS spherical coverage core and test. without TT. Measurement Uncertainties and Test Tolerances are FFS for power class 2, 4, 6 and 7. The test case is incomplete for band n259 and band n262.AV47 R5-253801, Test procedure updated with TT and others. | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
TBD |  | 38.521-2 Rx | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 38.521-2 Rx | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.521-4: Demod/CSI reporting test cases
25 | Y | 38.521-4 | 4.5.3.2 | Noc for NR operating bands in FR2 | add Noc power level for power class 6 UE | SGS Wireless | RAN5#101 (Nov-23) | R5-234230 |  | 1 | 100% | 100% |  |  | 100%
26 | Y | 38.521-4 | 7.2.2.2.4 | Minimum requirements for HST-DPS | add Minimum requirements for HST-DPS | Samsung | RAN5#101 (Nov-23) | R5-243881 | TT analysis and appcability are missing | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
27 |  | 38.521-4 | B.3.4 | FR2 HST-DPS Channel Profile | add new sub-title and introduction for the FR2 HST-DPS Channel Profile | Samsung | RAN5#101 (Nov-23) | R5-242668 |  | 0.2 | 100% | 100% |  |  | 100%
28 |  | 38.521-4 | B3.4.1 | Unidirectional Deployment Channel Profile | add Unidirectional Deployment Channel Profile for HST FR2 | Samsung | RAN5#101 (Nov-23) | R5-242668 |  | 0.1 | 100% | 100% |  |  | 100%
29 |  | 38.521-4 | B3.4.2 | Bidirectional Deployment Channel Profile | add Bidirectional Deployment Channel Profile for HST FR2 | Samsung | RAN5#101 (Nov-23) | R5-242668 |  | 0.1 | 100% | 100% |  |  | 100%
TBD | Y | 38.521-4 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
30 |  | 38.522 | 4 | Test case conditions and selection criteria | Adding Test case conditions and selection criteria | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-233506 R5-234335 R5-243717 | R5-233506, add common parts | 1 | 100% | 100% |  |  | 100%
31 |  | 38.522 | 4.1.2 | FR2 standalone conformance test cases | Adding applicability for test cases in 38.521-2 | Samsung, Huawei, SGS Wireless, Qualcomm | RAN5#101 (Nov-23) | R5-240508 R5-256225 | R5-240508, add applicability for 6.2.3, 6.2D.1.1, 6.3.1, 6.4.2.2, 6.4.2.3. R5-256225 add 6.2D.3 | 1 | 100% (+25%) | 100% (+25%) |  |  | 100%
32 |  | 38.522 | 4.1.4 | Performance conformance test cases | Adding applicability for test cases in 38.521-4 | SGS Wireless | RAN5#101 (Nov-23) | R5-243717 | R5-243717, add applicability for Demod 7.2.2.2.4_1 | 1 | 100% | 100% |  |  | 100%
33 |  | 38.522 | 4.2 | RRM conformance test cases | Adding applicability for test cases in 38.533 | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-233506 R5-234335 R5-236210 R5-237775 | R5-233506, add applicability of RRM TC 7.5.8.3.1 R5-234335, add applicability for 7.1.1.7 R5-237775, add 7.6.1.5, 7.6.3.5 | 1 | 100% | 100% |  |  | 100%
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. |  | TBD |  |  | 0.1
TS 38.533: RRM test cases
34 |  | 38.533 | 7.1.1.0.1 | Minimum conformance requirements for intra-frequency cell re-selection | update minimum conformance requirements for intra-frequency cell re-selection | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-234331 |  | 0.1 | 100% | 100% |  |  | 100%
35 | Y | 38.533 | 7.1.1.7 | Cell reselection to FR2 intra-frequency NR case for FR2 power class 6 UE configured with highSpeedMeasFlagFR2-r17 | This test is to verify the requirement for the intra frequency NR cell reselection requirements specified in clause 4.2.2.3 for FR2 power class 6 UE configured with highSpeedMeasFlagFR2-r17. | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-234332 R5-254361 | Test frequency f ≤ 40.8 GHz. UE PC6 This test case is incomplete for Test frequency f > 40.8 GHz Test tolerance and measurement uncertainty analysis are missing R5-254361 Test tolerance analysis has been completed | 1 | 100% | 100% |  |  | 100%
36 | Y | 38.533 | 7.4.1.1 | NR UE Transmit Timing Test for FR2 | The purpose of this test is to verify that the UE can follow frame timing change of the connected gNodeb and that the UE initial transmit timing accuracy, maximum amount of timing change in one adjustment, minimum and maximum adjustment rate are within the specified limits. | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-235708 R5-255544 | Test frequency f ≤ 40.8 GHz UE PC3 The test is incomplete for UE power classes other than PC3 and PC6 The test is incomplete for test frequencies > 40.8 GHz | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
37 |  | 38.533 | 7.5.8 | Active TCI state switch delay | add sub-title |  | RAN5#101 (Nov-23) |  |  |  | 100% | 100% |  |  | 100%
38 |  | 38.533 | 7.5.8.3 | MAC-CE based active TCI state switch for HST FR2 scenario | add sub-title |  | RAN5#101 (Nov-23) |  |  |  | 100% | 100% |  |  | 100%
39 | Y | 38.533 | 7.5.8.3.1 | NR PCell FR2 HST active TCI state switch for a known TCI state | The purpose of this test is to verify the active TCI state switch delay requirement for FR2 power class 6 UE. | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-233507 R5-235707 | R5-233507 add min conf req and TC, add cell mapping in Annex E.5 - Test tolerance and measurement uncertainty analysis are missing R5-235707 Correct wording. | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
40 | Y | 38.533 | 7.6.1.5 | NR SA event triggered reporting test without gap under non-DRX for UE configured with highSpeedMeasCA-Scell-r17 highSpeedMeasFlagFR2-r17 | The purpose of this test is to verify that the UE makes correct reporting of an event. This test will partly verify the TDD intra-frequency cell search requirements for FR2 power class 6 UE configured with highSpeedMeasFlagFR2-r17 | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-237959 | Test tolerance and measurement uncertainty analysis are missing | 1 | 100% (+10%) | 100% (+10%) |  |  | 100%
41 | Y | 38.533 | 7.6.3.5 | SSB based L1-RSRP measurement when DRX is used for power class 6 UE configured with highSpeedMeasFlagFR2-r17 | The purpose of this test is to verify that the power class 6 UE makes correct reporting of L1-RSRP measurement when highSpeedMeasFlagFR2-r17 is configured. This test will partly verify the L1-RSRP measurement requirements for power class 6 UE configured with highSpeedMeasFlagFR2-r17 | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-236209 R5-255547 | R5-236209, add 7.6.3.5, Test tolerance and measurement uncertainty analysis are missing | 1 | 100% (+20%) | 100% (+20%) |  |  | 100%
|  |  | Annex B | Conditions for RRM TC |  |  | RAN5#101 (Nov-23) | R5-255995 |  | 0.1 | 100% (+70%) | 100% (+70%) |  |  | 100%
|  |  | Annex E | Cell configuration mapping for SA FR2 test cases in Chapter 7 |  |  | RAN5#101 (Nov-23) | R5-235707 R5-240921, R5- 242612 | R5-240921 Cell Mapping correction for TC 6.6.1.8 in Annex E | 0.1 | 100% (+70%) | 100% (+70%) |  |  | 100%
|  |  | Annex F | RRM FR2 PC6 MU |  | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-251854 R5-254362 R5-255545 R5-255548 | R5-251854 The RRM FR2 MU tables in Annex F have been updated R5-254362 TT added to FR2 cell-reslection cases. | 0.1 | 100% (+40%) | 100% (+40%) |  |  | 100%
TBD | Y | 38.533 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
42 |  | 38.903 | Annex B/E | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | TT analysis for FR2 RF Test cases | SAMSUNG，KeySight, Nokia | RAN5#101 (Nov-23) | R5-233633 R5-244173 R5-250206 R5-253528 R5-253799 R5-256944 |  | 1 | 100% | 100% |  |  | 100%
43 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | TT analysis for RRM Test cases | Nokia, Nokia Shanghai Bell | RAN5#101 (Nov-23) | R5-255370 R5-255543 R5-255546 |  | 1 | 100% (+70%) | 100% (+70%) |  |  | 100%
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
TBD |  | 38.905 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.905 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.