## Slide 1
Vasil Aleksiev (SA1 Chair, Deutsche Telekom)
Alain Sultan (SA1 Support, MCC)
SA1 Status Report to
TSG SA#110
SP-251502
AI# 4.1
3GPP TSG SA Meeting #110
09 – 12 Dec 2025, Baltimore, USA

## Slide 2: Contents
1) General aspects (WG officials, WG meetings, statistics)
2) SA1 Work Report
  2.1) Rel-18 and before Maintenance
  2.2) Rel-19 Work and Maintenance
  2.3) Rel-20 5G-Ad Work and Maintenance
  2.4) Rel-20 6G Study
  2.5) Rel-21
3) SA1 Work Planning
4) External SDOs interaction (including IETF dependencies)
5) Collected Items requiring action from SA
6) Documents for Information and Approval

## Slide 3: 1) General Aspects – SA1 Officials
Qun Wei
SA1 Vice Chair (re-elected for second term)
weiqun5@chinaunicom.cn
Feifei Lou
SA1 Vice Chair
feifei.lou@nokia.com
Alain Sultan
Secretary
MCC
Alain.sultan@etsi.org
Vasil Aleksiev
SA1 Chair
Vasil.Aleksiev@magenta.at
  NEWLY ELECTED - Congratulations to Feifei and thank you Yusuke!!

## Slide 4: 1) General Aspects – SA1 meetings
SA1 meetings held since SA#109
  SA1#112 17 – 21 November 2025, Dallas, USA
Upcoming SA1 meetings (Q1 2026)
  SA1#112bis ad-hoc-e 12-16 January 2026 (initial proposal for a longer e-meeting is changed), online -> see slide 20
  SA1#113 9 – 13 February 2026, Goa, India

## Slide 5: - Document Handling / Meeting
1) General Aspects – SA1 statistics
 | Q2 24 | Q3 24 | Q4 24 | Q1 25 | Q2 25 | Q3 25 | Q4 25
Attended delegates | 277_F2F + 68_remote | 200_F2F + 74_remote | 359_F2F + 83_remote | 318_F2F + 85_remote | 338_F2F + 58_remote | 308_F2F + 138_remote | 345_F2F = 78_remote
Docs at meeting end | 425 | 551 | 871 | 806 | 972 | 949 | 522+rev
Docs at meeting start | 231 | 212 | 376 | 314 | 370 | 367 | 278
Incoming LS | 36 | 20 | 29 | 13 | 13 | 14 | 20
Outgoing LS | 2 | 4 | 6 | 0 | 3 | 1 | 5
Agreed CRs | 18 | 22 | 20 | 15 | 11 | 7 | 22
Agreed alignment CRs | 4 | 3 | 10 | 0 | 7 | 0 | 4
New Study Items | 0 | 1 | 0 | 0 | 0 | 0 | 1
New Work Items | 1 | 6 | 3 | 4 | 1 | 2 | 0
Revised WID/SID | 0 | 1 | 1 | 1 | 0 | 1 | 0
TR/TS for Information | 0 | 0 | 2 | 0 | 0 | 0 | 1
TR/TS for Approval | 0 | 0 | 0 | 1 | 1 | 0 | 0

## Slide 6: 1) General Aspects – Acknowledgements
The SA1 Chair wants to thank
  The two co-rapporteurs of TR 22.870 (FS_6G) for their tremendous work in producing several versions of the TR and proposing the consolidated PRs. These are:
    Jean Trakinat (T-Mobile USA) and
    Xiaonan Shi (China Mobile).
  Both vice chairs, for their continuous support and in particular for chairing parallel sessions
  Also Jesus Martin (Telefonica), Feifei Lou (Nokia), Erik Guttman (Samsung) for chairing parallel sessions
  And Alain Sultan (ETSI MCC) for his permanent work and support

## Slide 7: 1) General Aspects – SA1 statistics
Statistics at SA1#112 (17 – 21 November 2025, Dallas, USA)
  345 delegates ‘attended’ (checked-in) at SA1#112 78 registered for the on-line broadcast

## Slide 8: 2.1) Rel-18 and before Maintenance
Rel-16 |  | None
Rel-17 | TEI17, 5GSAT | TEI17: 1 CR’s to TS 22.261
Rel-18 | TEI17, 5GSAT | TEI17: 1 CR’s to TS 22.261
Rel-19 | TEI17, 5GSAT | TEI17: 1 CR’s to TS 22.261
Rel-20 | TEI17, 5GSAT | TEI17: 1 CR’s to TS 22.261
Correction on the end-to-end latency via satellite in clause 7.4.2

## Slide 9: 2.2) Rel-19 Work summary(1/2)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New %
960019 | Study on Energy Efficiency as service criteria | FS_EnergyServ | 09/09/2023 | 100% | SP-230235 | -
1000033 | Stage 1 of Energy Efficiency as Service Criteria | EnergyServ | 12/12/2023 | 100% | SP-230520 | -
950008 | Study on AI/ML Model Transfer Phase2 | FS_AIML_MT_Ph2 | 09/09/2023 | 100% | SP-220439 | -
1000030 | AI/ML Model Transfer Phase 2 | AIML_MT_Ph2 | 12/12/2023 | 100% | SP-230514 | -
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | 05/05/2023 | 100% | SP-220085 | -
1020030 | Stage 1 of Ambient power-enabled Internet of Things | AmbientIoT | 12/12/2023 | 100% | SP-231403 | -
960016 | Study on satellite access - Phase 3 | FS_5GSAT_Ph3 | 09/09/2023 | 100% | SP-220679 | -
1000024 | Stage 1 of Satellite access Phase 3 | 5GSAT_Ph3 | 12/12/2023 | 100% | SP-230516 | -
950005 | Study on Localized Mobile Metaverse Services | FS_Metaverse | 09/09/2023 | 100% | SP-220353 | -
1000028 | Stage 1 of Localized Mobile Metaverse Services | Metaverse | 12/12/2023 | 100% | SP-230509 | -
990052 | Supporting UE Mobility for XR Services | XRMobility | 11/05/2023 | 100% | SP-230233 | -
950006 | Study on Network Sharing Aspects | FS_NetShare | 09/09/2023 | 100% | SP-220087 | -
1000029 | (Stage 1 of) Indirect Network Sharing | NetShare | 12/12/2023 | 100% | SP-230511 | -
960015 | Study on roaming value added services | FS_RVAS | 12/12/2022 | 100% | SP-220442 | -
990051 | Roaming Value-Added Services | RVAS | 03/03/2023 | 100% | SP-230231 | -
1000027 | Non-Public Network (NPN) security considerations | SecNPN | 06/06/2023 | 100% | SP-230523 | -
1050114 | Monitoring of signalling traffic in 5G | MonSTra | 12/12/2024 | 100% | SP-240793 | -
1040082 | Stage 1 for MonSta | MonSTra | 06/06/2024 | 100% | SP-240793 | -
950003 | Study on Integrated Sensing and Communication | FS_Sensing | 09/09/2023 | 100% | SP-220717 | -
1000026 | Stage 1 of Integrated Sensing and Communication | Sensing | 12/12/2023 | 100% | SP-230750 | -
960017 | Study on (Stage 1 of) UAV Phase 3 | FS_UAV_Ph3 | 09/09/2023 | 100% | SP-220954 | -
1000032 | Stage 1 of Uncrewed Aerial System Phase 3 | UAS_Ph3 | 12/12/2023 | 100% | SP-230518 | -
960018 | Study on Upper layer traffic steering, switching and split over dual 3GPP access | FS_DualSteer | 09/09/2023 | 100% | SP-220445 | -

## Slide 10: 2.2) Rel-19 Work summary (2/2)
UID | Name | Acronym | Target | Old % | WID | New %
1020031 | Upper layer traffic steering and switching over dual 3GPP access | DualSteer | 12/12/2023 | 100% | SP-231412 | -
1010022 | Edge Computing Considering the Operational Needs of Service Hosting Environment | EdgeOpNeeds | 09/09/2023 | 100% | SP-231037 | -
950007 | Study on FRMCS Phase 5 | FS_FRMCS_Ph5 | 12/09/2023 | 100% | SP-241693 | -
1000031 | FRMCS Phase 5 | FRMCS_Ph5 | 12/12/2023 | 100% | SP-230512 | -
850044 | Study on Supporting of Railway Smart Station Services | FS_RAILSS | 08/09/2022 | 100% | SP-190838 | -
960020 | Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT | 12/12/2023 | 100% | SP-220447 | -
990053 | Study on Interconnect of SNPN | FS_ISN | 27/06/2024 | 100% | SP-230236 | -
1030041 | Interconnect of SNPN | ISN | 29/03/2024 | 100% | SP-240194 | -
990050 | Edge Computing for Industrial Scenarios | EDGINDUS | 03/03/2023 | 100% | SP-230229 | -
990049 | PS Data Off for IMS Data Channel Service | IMSDCDataOff | 03/03/2023 | 100% | SP-230227 | -
970044 | Multi-path relay | MultiRelay | 19/09/2022 | 100% | SP-220943 | -
1000025 | UE-to-UE multi-hop relay | UEMHopRelay | 06/06/2023 | 100% | SP-230521 | -
970043 | Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services | DTT4MBS | 19/09/2022 | 100% | SP-220941 | -
970042 | (stage 1 of) MPS for Messaging services | MPS4msg | 19/09/2022 | 100% | SP-220939 | -
1050104 | Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | 10/10/2025 | 100% | SP-220992 | -
970041 | Stage 2 of Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | 09/09/2022 | 100% | SP-220992 | -
980108 | Measurement Data Collection | MeasureData | 12/12/2022 | 100% | SP-221263 | -
1010025 | Local traffic routing for multi-access UE | LTR_MA | 09/09/2023 | 100% | SP-231035 | -
1090040 | Stage 1 for Lower Selection-priority for PLMN Selection | LoSePLMN-REQ | 09/09/2025 | 100% | SP-251194 | -

## Slide 11: 2.2) Rel-19 Maintenance
Rel-19 | TEI19 | TEI19: 1 CR to TS 22.268
Rel-20 | TEI19 | TEI19: 1 CR to TS 22.268
- Based on incoming LS from RAN2, SA1 decided to add clarification in TS 22.268 on PWS support in NB-IoT Terrestrial Network

## Slide 12: 2.3) Rel-20 5G-A Work summary
- Summary
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1030042 | Study on satellite access - Phase 4 | FS_5GSAT_Ph4 | 12/12/2024 | 100% | SP-241824 | - | 
1060071 | Stage 1 for Satellite access - Phase 4 | 5GSAT_Ph4-REQ | 06/06/2025 | 100% | SP-250386 | - | 
1050105 | Indirect Network Sharing on Satellite Access Network | INS_SAT | 09/09/2024 | 100% | SP-241393 | - | 
1060072 | MPS support in 3GPP system with satellite | MPS_Sat | 12/12/2024 | 100% | SP-241823 | - | 
1030044 | Study on Energy Efficiency as Service Criteria Phase 2 | FS_EnergyServ_Ph2 | 03/03/2025 | 100% | SP-240494 | - | 
1070051 | Stage 1 for Energy Efficiency as Service Criteria Phase 2 | EnergyServ_Ph2-REQ | 06/06/2025 | 100% | SP-250385 | - | 
1050106 | Stage 1 for Indirect Network Sharing Phase 2 | NetShare_Ph2-REQ | 09/09/2024 | 100% | SP-241147 | - | 
1030043 | Study on FRMCS Phase 6 | FS_FRMCS_Ph6 | 03/03/2025 | 100% | SP-241392 | - | 
1070054 | Stage 1 for FRMCS Phase 6 | FRMCS_Ph6-REQ | 09/09/2025 | 100% | SP-250277 | - | 
1070052 | Stage 1 of SMS to Emergency Centre | SMS2EC-REQ | 03/03/2025 | 100% | SP-250387 | - | 
1090039 | Stage 1 for Phase 2 of Mission Critical Discreet listening | MCDISC_Ph2-REQ | 09/09/2025 | 100% | SP-251267 | - | 
1060070 | Vehicle-Mounted Relays Phase3 | VMR_Ph3 | 12/12/2024 | 100% | SP-241821 | - | 
1050107 | Resident Phase 2 | Resident_Ph2 | 09/09/2024 | 100% | SP-241149 | - | 
1080047 | CPAS specific requirement | CPAS-REQ | 06/06/2025 | 100% | SP-250627 | - | 
1070053 | Stage 1 for Ambient listening enhancements including pause and resume in MCS | ALPR-REQ | 03/03/2025 | 100% | SP-250275 | - | 
1050108 | Combined QoS configuration and monitoring | CombQoS | 09/09/2024 | 100% | SP-241150 | - | 
1050109 | Legacy Residential Gateway Supporting 5G LAN-type Service | LegacyRG_5GLAN | 09/09/2024 | 100% | SP-241151 | - | 
1050111 | Exposure for Virtual Network information and capability | VNExposure | 09/09/2024 | 100% | SP-241153 | - | 

## Slide 13: 2.3) Rel-20 5G-A Maintenance
Rel-20 | 5GSAT_Ph4-REQ | 5GSAT_Ph4-REQ: 1 CR to TS 22.261
- Based on incoming LS from SA2, SA1 decided to clarify for IMS voice using GEO that support of DTMF is required, whilst support of more than one IMS voice call (per UE), simultaneously, is not required in this release

## Slide 14: 2.4) Rel-20 6G Work summary
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1050110 | Study on 6G Use Cases and Service Requirements | FS_6G_REQ | 03/03/2026 | 77% | SP-241391 | 80% | Sent for information to SA#110

## Slide 15: 2.4) Rel-20 6G Study (FS_6G_REQ)
- Key highlights
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1050110 | Study on 6G Use Cases and Service Requirements | FS_6G_REQ | 03/03/2026 | 77% | SP-241391 | 80% | Sent for information to SA#110
Progress since previous SA meeting:
  75 contributions (pCRs) have been approved as SA1#112
  Completed new use cases input to the TR
  18 editor’s notes still pending to be solved – some of them editorial ones
  Started discussions on 5 of 8 initial CPR clauses (computing, immersive and massive remain unopened)
Controversial or Open issues from this meeting
  user consent, computing CPR structure, definition of E2E joint latency, PR and KPI consolidation
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#112bis ad-hoc-e (01/26): Study 85%
  Clean up ENs & address FFS
  Controversial issues, e.g. user consent vs. subscriber permission, computing
  Consolidation of CPR sections System and Operation and AI
  KPIs consolidation
SA1#113 (02/26): Study 100%
  Complete Potential Requirements Consolidation
  Send to SA for Approval

## Slide 16: 2.5) Rel-21
- Key highlights
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
 | Study on Requirements Simplification | FS_SIMP | 12/12/2026 | 0% | SP-251509 | 0% | New SID
Progress since previous SA meeting:
  The SID was agreed. Focus on requirements in normative specifications, that do not have corresponding stage 2 and stage 3 specification. Study if to promote these requirements in the next release or decide to not pursue them further.
Controversial or Open issues from this meeting
  None
Impacts and dependencies on other WGs: none identified
Next steps
  SA1#113 (02/26): seek to agree the skeleton and scope, and consider an initial input. Time should be limited to one hour session time in the meeting
  SA1#114 (05/26): consider pCRs
  SA1#115 (08/26): last opportunity to consider pCRs. Begin to work on conclusions
  SA1#116 (11/26): conclude the study

## Slide 17: 3) SA1 Work Planning: General
The 6G study consolidation of potential service requirements and KPIs was on the agenda for the first time
Disagreement on usage of user consent, separate CPR clause on computing
Window for new use cases and new PRs closed
No progress on consolidation – therefore proposal for additional ad-hoc-e meeting with limited agenda (12-16 Jan 2026) : editors notes solving; consolidation of service requirements for System and Operation aspects, AI sections; KPIs consolidation; controversial issues (e.g. computing clause, user consent).

## Slide 18: 3) SA1 Work Planning: 6G Study
FS_6G_REQ SID: SP-241391 (Approved in SA#105, Sep 2024)
Latest TR: TR 22.870-v100
Consolidation of requirements started at Nov meeting.
Extra ad-hoc-e meeting with limited agenda needed (12-16 Jan 26) due to slow progress
SA1 6G study (FS_6G_REQ) is expected to be completed in SA#111, Mar 2026
#111
Mar.
#107
Mar.
#108
Jun.
#109
Sep.
#106
Dec.
#110
Dec.
TSGs
2025
SA1#110
May
SA1#111
Aug.
SA1#112
Nov
SA1#113
Feb
TR 22.870 finalization
#112
Jun.
#113
Sep.
#114
Dec.
2026
New use cases allowed
_____
New use cases allowed
FS_6G_REQ
Ad-hoc-e
needed
SA1#112bis
Jan
Resubmission of use cases allowed
- Consolidation starts

## Slide 19: 4) External SDOs interaction (including IETF dependencies)
None

## Slide 20: 5) Collected Items requiring action from SA
SA decision needed for additional ad-hoc-e meeting with limited agenda (12-16 Jan 2026) : Including but not limited to editors' notes solving; consolidation of service requirements and CPR structure, CPR clauses System and Operation aspects and AI; KPIs consolidation; user consent.
Rel-21 timeline needed for SA1 work planning. The SA1 chair proposed Rel-21 timeline to SA1 (end of Rel-21 in March 2027) but it is SA plenary decision.

## Slide 21: 6) Documents for Information and Approval
New SID/WID for Approval
TSG SA TDoc# | Type | Title | Acronym
SP-251509 | SID | New SID "Study on Requirements Simplification" | FS_SIMP

## Slide 22: 6) Documents for Information and Approval
TSs/TRs for Information
TSG SA TDoc# | Title | Release | TR/TS | WI Acronym
SP-251508 | Cover sheet for information and TR | 20 | TR 22.870 | FS_6G_REQ

## Slide 23: Thank You !