## Slide 1
Proposed Steps
after SA1#112
© 3GPP 2025
Vasil Aleksiev (SA1 Chair), Alain Sultan (MCC)
S1-254008 - 3GPP SA1#112, 17-21 November 2025, Dallas, USA

## Slide 2
Part 1: Rel-20 on FS_6G
© 3GPP 2025

## Slide 3
#111
Mar.
#107
Mar.
#108
Jun.
#109
Sep.
#106
Dec.
#110
Dec.
TSGs
2025
SA1#110
May
SA1#111
Aug.
SA1#112
Nov
NOW
SA1#113
Feb
TR 22.870 finalization
#112
Jun.
#113
Sep.
#114
Dec.
2026
No new use cases allowed
(only resubmission from previous meeting that were not agreed)
- Consolidation starts
New use cases allowed
Reminder on TR 22.870 (FS_6G_REQ) Milestones
_____
New use cases allowed
*
FS_6G_REQ
Target completion date: March 2026
Only one WG meeting left:
  SA1#113 (Feb 26): Finalization
* Online activities as needed
See next slide

## Slide 4: Discussion on next steps on FS_6G_REQ
Two time-consuming issues remain:
  Solving all Editor’s notes - some of which still require significant discussions
  Consolidating all proposed requirements and KPIs –starting SA1#112 (November) and to be completed at SA1#113. Extremely aggressive timeline.
This might require online activities to be handled between SA1#112 and SA1#113
In this case, two options are proposed:
  online ad-hoc meeting (SA1#112bis ad-hoc-e), or
  drafting calls

## Slide 5: Option 1: adhoc e-meeting
Option#1: SA1#112bis ad-hoc-e with decision power and limited agenda
  The meeting would run in a similar way to what used to be done during Covid: e-mail discussions in parallel to calls, etc.
  Limited agenda would contain only:
    Editor’s notes solving
    Consolidation of potential requirements
Proposed dates for option#1:
    5 calls spread between 13-20 Jan 2026, with deadline for submission 07 Jan 2026

## Slide 6: Option 2: series of calls
Option#2: series of drafting calls, without decision power
  The 3GPP portal would be used for contributions
Proposed dates for Option#2:
    13 Jan – address pending editor’s notes
    20 Jan –major discussions left on consolidation
    27 Jan – 6G WID discussion

## Slide 7: Way forward
In case of slow progress in SA1#112, choose between Option 1 OR Option 2

## Slide 8
Part 2: Rel-21
© 3GPP 2025

## Slide 9
Proposal for Rel-21 SA1 timeline
TSG#106
TSG#107
TSG#108
TSG#109
TSG#110
TSG#111
TSG#112
TSG#113
TSG#114
TSG#115
TSG#116
2025
2026
Mar.
Mar.
Mar.
Jun.
Jun.
Sep.
Sep.
Dec.
Dec.
Dec.
2027
SA1#110
SA1#115
SA1#112
SA1#113
SA1#114
SA1#109
SA1#116
Release 21
6G & 5GA
SA1#111
SA1#117
SA1#118
Jun.
FS_6G RAN WG
FS_6G RAN Plenary
FS_6G Stage 1
FS_6G Stage 2
or
FS_6G Stage 3
TBD
Reminder:
Release 20
FS_6G
* In case of remaining issues, an update to the 6G WID can be discussed in SA1#114.
**SA1#115bis- e-meeting potentially needed in Oct26, TBD in Aug26(SA1#115).
Agreement *
Presentation
SA1#108
6G Stage 1 80%
100%
**
Disclaimer: Rel21 final timeline decision will be taken at the SA plenary.

## Slide 10
Annex
© 3GPP 2025

## Slide 11: Annex
Next slide shows the SA1 organisation at an equivalent time for the transisiotn between 4G and 5G: number of meetings, time spent, etc.
This is provided as a reference

## Slide 12
SA1 Stats from Q4 2014 till Q1 2017
Chart: 
| Q4 2014 | Q1 2015 | Q2 2015 | Q3 2015 | Q4 2015 | Q1 2015
GCSE_LTE
UPCON
RSE
ACDC
MTC
NOVES
SSO
PWS
WebRTC
IOPS
SEES
eICBD
Chart: 
| Q4 2015 | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016 | Q1 2017
GCSE_LTE
UPCON
RSE
ACDC
MTC
NOVES
SSO
PWS
WebRTC
IOPS
SEES
eICBD
Includes
SMARTER ad-hoc
meeting
END OF FS_SMARTER
Part 2 06/2016
END OF SMARTER NORM. 06/2017
END OF FS_SMARTER
Part 1 (TR 22.891) 03/2016
“REAL” START OF FS_SMARTER
02/2016
Study => Rel-14 (read “FS_SMARTER”)
Normative => Rel-15
Includes 76#bis
meeting