## SA5#163
|  | Rel-20 |  |  | Meeting | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171)
|  |  |  | TU total (for planning purposes) | 177.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18 | 18 | 15 | 15.5
SA5 Open plenary+ LS
|  | Planned |  |  | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Actual |  |  |  | 1
Pre-Rel-19 maintenance
|  | Planned |  |  | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Actual |  |  |  | 1
Rel-19 maintenance
|  | Planned |  |  | 15.5 | 1 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 0.5 | 1
|  | Actual |  |  |  | 1
Rel-20 TEI
|  | Planned |  |  | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0
|  | Actual |  |  |  | 0
Buffer (Overflow, other)
|  | Planned |  |  | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Actual |  |  |  | 1
Rel-19
|  | Planned(from the original overall plan) |  |  | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Planned(sum of individual plans) |  |  |  | 8.25
|  | Actual |  |  |  | 9
Rel-20
|  | Planned(from the original overall plan) |  |  | 124 | 2 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 12
|  | Planned(5GA) |  |  | 67 | 1 | 14 | 14 | 10 | 9 | 7 | 6 | 4 | 2 | 0
|  | Planned(6G) |  |  | 57 | 1 | 0 | 0 | 4 | 5 | 7 | 8 | 10 | 10 | 12
|  | Planned(sum of individual plans) (5GA) |  |  | 62 | 3.6 | 8.1 | 9.85 | 8.9 | 8.15 | 7.7 | 7.4 | 5.2 | 2.9 | 0.2
|  | Actual (5GA) |  |  |  | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual (6G) |  |  |  | 3
Rel-21
|  | Planned |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
Actual
Overall total
|  | Planned(from sum of individual plans) |  |  | 116 | 20.1 | 12.6 | 14.35 | 13.4 | 12.65 | 12.2 | 11.9 | 9.2 | 5.9 | 3.7
|  | Actual |  |  |  | 18.7
|  | Rel-20 SID/WID detailed plan |  | TU estimates (from SID) | total TU planned by rapporteurs | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171)
5GA |  |  | total TU planned | 62
1 | IDM |  | Study TU's planned | 4 | 4 | 1 | 1 | 1 | 1
|  | Ruiyue Xu | Study TU's used |  |  | 1
|  | Mark Scott | Normative TU's planned | 4 | 4 |  |  |  |  | 1.5 | 1 | 1 | 0.5
Normative TU's used
2 | AIML |  | Study TU's planned | 4 | 4 | 0 | 1 | 1 | 1 | 1
|  | Hassan | Study TU's used |  | 0
|  | Jose | Normative TU's planned | 4 | 4 | [5 empty] | 1 | 1 | 1 | 1
|  |  | Normative TU's used |  | 0
3 | NDT |  | Study TU's planned | 2 | 2 |  | 0.5 | 1 | 0.5
|  | Xian Zhao | Study TU's used |  | 0
|  |  | Normative TU's planned | 2 | 2 |  |  |  |  | 1 | 0.5 | 0.5
|  |  | Normative TU's used |  | 0
4 | SBMA |  | Study TU's planned | 4 | 4 | 0 | 1 | 1 | 1 | 1
|  | Kai Zhang | Study TU's used |  | 0
|  | Balazs | Normative TU's planned | 4 | 4 | [5 empty] | 1 | 1 | 1 | 1
|  |  | Normative TU's used |  | 0
5 | EE |  | Study TU's planned | 2.5 | 2.5 | 0 | 0.5 | 1 | 1
|  | Srilakshmi | Study TU's used |  | 0
|  | Ashutosh Kaushik | Normative TU's planned | 2.5 | 2.5 |  |  |  |  | 0.3 | 0.7 | 0.8 | 0.7
|  |  | Normative TU's used |  | 0
6 | MDA |  | Study TU's planned | 2 | 2 | 0.5 | 0.5 | 0.5 | 0.5
|  | Brendan | Study TU's used |  | 0.3 | 0.3
|  | Gang Li | Normative TU's planned | 2 | 2 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5
|  |  | Normative TU's used |  | 0
7 | MADCOL |  | Study TU's planned | 2.75 | 2.75 | 0.7 | 0.7 | 0.65 | 0.7
|  | Sreekumar | Study TU's used |  | 0.2 | 0.2
|  | Robert Petersen | Normative TU's planned | 1.25 | 1.25 |  |  |  |  | 0.25 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  |  | Normative TU's used |  | 0
8 | Mexpo |  | Study TU's planned | 2.5 | 2.5 | 0 | 0.3 | 1 | 1.2
|  | Winnie | Study TU's used |  | 0
|  |  | Normative TU's planned | 1.5 | 1.5 |  |  |  |  | 0.2 | 0.3 | 0.4 | 0.4 | 0.2
|  |  | Normative TU's used |  | 0
9 | CCL |  | Study TU's planned | 2 | 2 | 0 | 0.2 | 0.9 | 0.9
|  | Deepanshu | Study TU's used |  | 0
|  | Stephen | Normative TU's planned | 2 | 2 |  |  |  |  | 0.3 | 0.5 | 0.5 | 0.5 | 0.2
|  |  | Normative TU's used |  | 0
10 | AdNRM |  | Study TU's planned | 0 | 0
|  | Sean Sun | Study TU's used |  | 0
|  | Xiaoli Shi | Normative TU's planned | 4 | 4 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.3
|  |  | Normative TU's used |  | 0.6 | 0.6
11 | PMTMQ |  | Study TU's planned | 0 | 0
|  | XiuMin Chen | Study TU's used |  | 0
|  | Qiang Zu | Normative TU's planned | 5 | 5 | 0.4 | 1 | 0.6 | 0.2 | 0.8 | 1 | 1 | 0 | 0 | 0
|  |  | Normative TU's used |  | 0.1 | 0.1
12 | NWDAFM |  | Study TU's planned | 0 | 0
|  | Song Zhao | Study TU's used |  | 0
|  |  | Normative TU's planned | 2 | 2 | 0.4 | 0.4 | 0.4 |  | 0.4 | 0.4
|  |  | Normative TU's used |  | 0.2 | 0.2
13 | XRMM |  | Study TU's planned | 0 | 0
|  | pengxiang Xie | Study TU's used |  | 0
|  |  | Normative TU's planned | 2 | 2 | 0.3 | 0.5 | 0.3 | 0.4 | 0.4 | 0.1
|  |  | Normative TU's used |  | 0.3 | 0.3
14 | UMMR |  | Study TU's planned | 3 |  |  | 0.25
|  | Veronica | Study TU's used
|  |  | Normative TU's planned | 2
Normative TU's used
6G |  |  | Study TU's planned | 62
|  |  | Study TU's planned (6G) |  |  | 1 | 0 | 0 | 4 | 5 | 7 | 8 | 10 | 10 | 12
|  |  | Study TU's used(6G) |  |  | 3
|  |  | TU consumed according to plan | TU planned | TU actual used
|  | Total for Rel-20 Studies |  | 87.75
|  | Total for Rel-20 Normative |  | 36.25
|  | Total for Rel-20 SID/WID |  | 124
|  | Breakout sessions bonus TU used | Total | TU estimates (from SID) |  | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171) | total BONUS TU
1 | IDM | Intent driven management enhancement
2 | AIML | AIML management enhancement
3 | NDT | NDT enhancement
4 | SBMA | SBMA enhancement
5 | EE | Energy efficiency enhancement
6 | MDA | MDA enhancement
7 | MADCOL | Data Management enhancement
8 | Mexpo | MExpo enhancement
9 | CCL | CCL enhancement
10 | AdNRM | AdNRM
11 | PMTMQ | PM/KPI/Trace/MDT/QoE/SON enhancement
12 | NWDAFM | NWDAFM
13 | XRMM | XR management
Other
|  | Rel-20 CH SID/WID detailed plan |  | TU estimates (from SID) |  | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171) | leftover
1 | CAPCH | Charging Aspects of CAPIF Phase 3 | Study TU's planned | 1
|  | João Rodrigues | Study TU's used
|  |  | Normative TU's planned | 1
Normative TU's used
2 | XRMCH | Charging aspects for XRM | Study TU's planned | 0
Study TU's used
|  |  | Normative TU's planned | 5
Normative TU's used
3 | 6GCH | Charging Aspects of 6G System | Study TU's planned | 28
Study TU's used
Normative TU's planned
Normative TU's used
4 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
5 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
6 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
7 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
8 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used

## SA5#164
|  | Rel-20 |  |  | Meeting | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171)
|  |  |  | TU total (for planning purposes) | 186.5 | 18.5 | 27.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18 | 18 | 15 | 15.5
SA5 Open plenary+ LS
|  | Planned |  |  | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Actual |  |  |  | 1 | 1
Pre-Rel-19 maintenance
|  | Planned |  |  | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Actual |  |  |  | 1 | 0.5
Rel-19 maintenance
|  | Planned |  |  | 15.5 | 1 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 0.5 | 1
|  | Actual |  |  |  | 1 | 3
Rel-20 TEI
|  | Planned |  |  | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0
|  | Actual |  |  |  | 0 | 0.3
Buffer (Overflow, other)
|  | Planned |  |  | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Actual |  |  |  | 1 | 4.5
Rel-19
|  | Planned(from the original overall plan) |  |  | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Planned(sum of individual plans) |  |  |  | 8.25 | 1
|  | Actual |  |  |  | 9 | 1
Rel-20
|  | Planned(from the original overall plan) |  |  | 124 | 2 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 12
|  | Planned(5GA) |  |  | 67 | 1 | 14 | 14 | 10 | 9 | 7 | 6 | 4 | 2 | 0
|  | Planned(6G) |  |  | 57 | 1 | 0 | 0 | 4 | 5 | 7 | 8 | 10 | 10 | 12
|  | Planned(sum of individual plans) (5GA) |  |  | 62 | 3.6 | 8.1 | 9.85 | 8.9 | 8.15 | 7.7 | 7.4 | 5.2 | 2.9 | 0.2
|  | Actual (5GA) |  |  |  | 2.7 | 7.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual (6G) |  |  |  | 3 | 1
Rel-21
|  | Planned |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
Actual
Overall total
|  | Planned(from sum of individual plans) |  |  | 116 | 20.1 | 12.6 | 14.35 | 13.4 | 12.65 | 12.2 | 11.9 | 9.2 | 5.9 | 3.7
|  | Actual |  |  |  | 18.7 | 18.5
|  | Rel-20 SID/WID detailed plan |  | TU estimates (from SID) | total TU planned by rapporteurs | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171)
5GA |  |  | total TU planned | 62
1 | IDM |  | Study TU's planned | 4 | 4 | 1 | 1 | 1 | 1
|  | Ruiyue Xu | Study TU's used |  |  | 1 | 1
|  | Mark Scott | Normative TU's planned | 4 | 4 |  |  |  |  | 1.5 | 1 | 1 | 0.5
Normative TU's used
2 | AIML |  | Study TU's planned | 4 | 4 | 0 | 1 | 1 | 1 | 1
|  | Hassan | Study TU's used |  | 1 |  | 1
|  | Jose | Normative TU's planned | 4 | 4 | [5 empty] | 1 | 1 | 1 | 1
|  |  | Normative TU's used |  | 0
3 | NDT |  | Study TU's planned | 2 | 2 |  | 0.5 | 1 | 0.5
|  | Xian Zhao | Study TU's used |  | 0.5 |  | 0.5
|  |  | Normative TU's planned | 2 | 2 |  |  |  |  | 1 | 0.5 | 0.5
|  |  | Normative TU's used |  | 0
4 | SBMA |  | Study TU's planned | 4 | 4 | 0 | 1 | 1 | 1 | 1
|  | Kai Zhang | Study TU's used |  | 1 |  | 1
|  | Balazs | Normative TU's planned | 4 | 4 | [5 empty] | 1 | 1 | 1 | 1
|  |  | Normative TU's used |  | 0
5 | EE |  | Study TU's planned | 2.5 | 2.5 | 0 | 0.5 | 1 | 1
|  | Srilakshmi | Study TU's used |  | 0.5 |  | 0.5
|  | Ashutosh Kaushik | Normative TU's planned | 2.5 | 2.5 |  |  |  |  | 0.3 | 0.7 | 0.8 | 0.7
|  |  | Normative TU's used |  | 0
6 | MDA |  | Study TU's planned | 2 | 2 | 0.5 | 0.5 | 0.5 | 0.5
|  | Brendan | Study TU's used |  | 0.8 | 0.3 | 0.5
|  | Gang Li | Normative TU's planned | 2 | 2 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5
|  |  | Normative TU's used |  | 0
7 | MADCOL |  | Study TU's planned | 2.75 | 2.75 | 0.7 | 0.7 | 0.65 | 0.7
|  | Sreekumar | Study TU's used |  | 0.7 | 0.2 | 0.5
|  | Robert Petersen | Normative TU's planned | 1.25 | 1.25 |  |  |  |  | 0.25 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  |  | Normative TU's used |  | 0
8 | Mexpo |  | Study TU's planned | 2.5 | 2.5 | 0 | 0.3 | 1 | 1.2
|  | Winnie | Study TU's used |  | 0.5 |  | 0.5
|  |  | Normative TU's planned | 1.5 | 1.5 |  |  |  |  | 0.2 | 0.3 | 0.4 | 0.4 | 0.2
|  |  | Normative TU's used |  | 0
9 | CCL |  | Study TU's planned | 2 | 2 | 0 | 0.2 | 0.9 | 0.9
|  | Deepanshu | Study TU's used |  | 0.2 |  | 0.2
|  | Stephen | Normative TU's planned | 2 | 2 |  |  |  |  | 0.3 | 0.5 | 0.5 | 0.5 | 0.2
|  |  | Normative TU's used |  | 0
10 | AdNRM |  | Study TU's planned | 0 | 0
|  | Sean Sun | Study TU's used |  | 0
|  | Xiaoli Shi | Normative TU's planned | 4 | 4 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.3
|  |  | Normative TU's used |  | 1.1 | 0.6 | 0.5
11 | PMTMQ |  | Study TU's planned | 0 | 0
|  | XiuMin Chen | Study TU's used |  | 0
|  | Qiang Zu | Normative TU's planned | 5 | 5 | 0.4 | 1 | 0.6 | 0.2 | 0.8 | 1 | 1 | 0 | 0 | 0
|  |  | Normative TU's used |  | 0.6 | 0.1 | 0.5
12 | NWDAFM |  | Study TU's planned | 0 | 0
|  | Song Zhao | Study TU's used |  | 0
|  |  | Normative TU's planned | 2 | 2 | 0.4 | 0.4 | 0.4 |  | 0.4 | 0.4
|  |  | Normative TU's used |  | 0.4 | 0.2 | 0.2
13 | XRMM |  | Study TU's planned | 0 | 0
|  | pengxiang Xie | Study TU's used |  | 0
|  |  | Normative TU's planned | 2 | 2 | 0.3 | 0.5 | 0.3 | 0.4 | 0.4 | 0.1
|  |  | Normative TU's used |  | 0.6 | 0.3 | 0.3
14 | UMMR |  | Study TU's planned | 3 |  |  | 0.25 | 0.5 | 0.5 | 0.5 | 0.75 | 0.5
|  | Veronica | Study TU's used |  |  |  | 0.25
|  |  | Normative TU's planned | 2
Normative TU's used
6G |  |  | Study TU's planned | 62
|  |  | Study TU's planned (6G) |  |  | 1 | 0 | 0 | 4 | 5 | 7 | 8 | 10 | 10 | 12
|  |  | Study TU's used(6G) |  |  | 3 | 1
|  |  | TU consumed according to plan | TU planned | TU actual used
|  | Total for Rel-20 Studies |  | 87.75
|  | Total for Rel-20 Normative |  | 36.25
|  | Total for Rel-20 SID/WID |  | 124
|  | Breakout sessions bonus TU used | Total | TU estimates (from SID) |  | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171) | total BONUS TU
1 | IDM | Intent driven management enhancement
2 | AIML | AIML management enhancement |  |  |  |  | 0.5
3 | NDT | NDT enhancement |  |  |  |  | 0.2
4 | SBMA | SBMA enhancement
5 | EE | Energy efficiency enhancement |  |  |  |  | 0.5
6 | MDA | MDA enhancement
7 | MADCOL | Data Management enhancement
8 | Mexpo | MExpo enhancement
9 | CCL | CCL enhancement
10 | AdNRM | AdNRM
11 | PMTMQ | PM/KPI/Trace/MDT/QoE/SON enhancement
12 | NWDAFM | NWDAFM
13 | XRMM | XR management
14 | UMMR
| Other | [5 empty] | 1.5
|  | Rel-20 CH SID/WID detailed plan |  | TU estimates (from SID) |  | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171) | leftover
1 | CAPCH | Charging Aspects of CAPIF Phase 3 | Study TU's planned | 1
|  | João Rodrigues | Study TU's used
|  |  | Normative TU's planned | 1
Normative TU's used
2 | XRMCH | Charging aspects for XRM | Study TU's planned | 0
Study TU's used
|  |  | Normative TU's planned | 5
Normative TU's used
3 | 6GCH | Charging Aspects of 6G System | Study TU's planned | 28
Study TU's used
Normative TU's planned
Normative TU's used
4 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
5 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
6 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
7 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
8 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used

## SA5#165
|  | Rel-20 |  |  | Meeting | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171)
|  |  |  | TU total (for planning purposes) | 192.5 | 18.5 | 27.5 | 24.5 | 18.5 | 18.5 | 18.5 | 18 | 18 | 15 | 15.5
SA5 Open plenary+ LS
|  | Planned |  |  | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Actual |  |  |  | 1 | 1 | 1
Pre-Rel-19 maintenance
|  | Planned |  |  | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  | Actual |  |  |  | 1 | 0.5 | 0.5
Rel-19 maintenance
|  | Planned |  |  | 15.5 | 1 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 0.5 | 1
|  | Actual |  |  |  | 1 | 3 | 2
Rel-20 TEI
|  | Planned |  |  | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0
|  | Actual |  |  |  | 0 | 0.3 | 0.3
Buffer (Overflow, other)
|  | Planned |  |  | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Actual |  |  |  | 1 | 4.5 | 3
Rel-19
|  | Planned(from the original overall plan) |  |  | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Planned(sum of individual plans) |  |  |  | 8.25 | 1 | 0
|  | Actual |  |  |  | 9 | 1 | 0
Rel-20
|  | Planned(from the original overall plan) |  |  | 124 | 2 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 12
|  | Planned(5GA) |  |  | 75 | 1 | 14 | 14 | 10 | 9 | 8 | 8 | 6 | 3 | 1
|  | Planned(6G) |  |  | 49 | 0 | 0 | 0 | 4 | 5 | 6 | 6 | 8 | 9 | 11
|  | Planned(sum of individual plans) (5GA) |  |  | 69.75 | 3.6 | 8.1 | 9.85 | 10.8 | 9.95 | 9.95 | 8.8 | 5.6 | 2.9 | 0.2
|  | Actual (5GA) |  |  |  | 2.7 | 7.2 | 8.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual (6G) |  |  |  | 3 | 1 | 2
Rel-21
|  | Planned |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
Actual
Overall total
|  | Planned(from sum of individual plans) |  |  | 123.75 | 20.1 | 12.6 | 14.35 | 15.3 | 14.45 | 14.45 | 13.3 | 9.6 | 5.9 | 3.7
|  | Actual |  |  |  | 18.7 | 18.5 | 17.15
|  | Rel-20 SID/WID detailed plan |  | TU estimates (from SID) | total TU planned by rapporteurs | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171)
5GA |  |  | total TU planned | 62
1 | IDM |  | Study TU's planned | 4 | 4 | 1 | 1 | 1 | 1
|  | Ruiyue Xu | Study TU's used |  |  | 1 | 1 | 1
|  | Mark Scott | Normative TU's planned | 4 | 4 |  |  |  |  | 1.5 | 1 | 1 | 0.5
Normative TU's used
2 | AIML |  | Study TU's planned | 4 | 4 | 0 | 1 | 1 | 1 | 1
|  | Hassan | Study TU's used |  | 2 |  | 1 | 1
|  | Jose | Normative TU's planned | 4 | 4 | [5 empty] | 1 | 1 | 1 | 1
|  |  | Normative TU's used |  | 0
3 | NDT |  | Study TU's planned | 2 | 2 |  | 0.5 | 1 | 0.5
|  | Xian Zhao | Study TU's used |  | 1.5 |  | 0.5 | 1
|  |  | Normative TU's planned | 2 | 2 |  |  |  |  | 1 | 0.5 | 0.5
|  |  | Normative TU's used |  | 0
4 | SBMA |  | Study TU's planned | 4 | 4 | 0 | 1 | 1 | 1 | 1
|  | Kai Zhang | Study TU's used |  | 2 |  | 1 | 1
|  | Balazs | Normative TU's planned | 4 | 4 | [5 empty] | 1 | 1 | 1 | 1
|  |  | Normative TU's used |  | 0
5 | EE |  | Study TU's planned | 2.5 | 2.5 | 0 | 0.5 | 1 | 1
|  | Srilakshmi | Study TU's used |  | 1.5 |  | 0.5 | 1
|  | Ashutosh Kaushik | Normative TU's planned | 2.5 | 2.5 |  |  |  |  | 0.3 | 0.7 | 0.8 | 0.7
|  |  | Normative TU's used |  | 0
7 | MDA |  | Study TU's planned | 2 | 2 | 0.5 | 0.5 | 0.5 | 0.5
|  | Brendan | Study TU's used |  | 1.1 | 0.3 | 0.5 | 0.3
|  | Gang Li | Normative TU's planned | 2 | 2 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5
|  |  | Normative TU's used |  | 0
8 | MADCOL |  | Study TU's planned | 2.75 | 2.75 | 0.7 | 0.7 | 0.65 | 0.7
|  | Sreekumar | Study TU's used |  | 1.35 | 0.2 | 0.5 | 0.65
|  | Robert Petersen | Normative TU's planned | 1.25 | 1.25 |  |  |  |  | 0.25 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  |  | Normative TU's used |  | 0
9 | Mexpo |  | Study TU's planned | 2.5 | 2.5 | 0 | 0.3 | 1 | 1.2
|  | Winnie | Study TU's used |  | 0.8 |  | 0.5 | 0.3
|  |  | Normative TU's planned | 1.5 | 1.5 |  |  |  |  | 0.2 | 0.3 | 0.4 | 0.4 | 0.2
|  |  | Normative TU's used |  | 0
10 | CCL |  | Study TU's planned | 2 | 2 | 0 | 0.2 | 0.9 | 0.9
|  | Deepanshu | Study TU's used |  | 0.9 |  | 0.2 | 0.7
|  | Stephen | Normative TU's planned | 2 | 2 |  |  |  |  | 0.3 | 0.5 | 0.5 | 0.5 | 0.2
|  |  | Normative TU's used |  | 0
11 | AdNRM |  | Study TU's planned | 0 | 0
|  | Sean Sun | Study TU's used |  | 0
|  | Xiaoli Shi | Normative TU's planned | 4 | 4 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.3
|  |  | Normative TU's used |  | 1.4 | 0.6 | 0.5 | 0.3
12 | PMTMQ |  | Study TU's planned | 0 | 0
|  | XiuMin Chen | Study TU's used |  | 0
|  | Qiang Zu | Normative TU's planned | 5 | 5 | 0.4 | 1 | 0.6 | 0.2 | 0.8 | 1 | 1 | 0 | 0 | 0
|  |  | Normative TU's used |  | 1.2 | 0.1 | 0.5 | 0.6
13 | NWDAFM |  | Study TU's planned | 0 | 0
|  | Song Zhao | Study TU's used |  | 0
|  |  | Normative TU's planned | 2 | 2 | 0.4 | 0.4 | 0.4 | 0.2 | 0.3 | 0.3
|  |  | Normative TU's used |  | 0.6 | 0.2 | 0.2 | 0.2
14 | XRMM |  | Study TU's planned | 0 | 0
|  | pengxiang Xie | Study TU's used |  | 0
|  |  | Normative TU's planned | 2 | 2 | 0.3 | 0.5 | 0.3 | 0.4 | 0.4 | 0.1
|  |  | Normative TU's used |  | 0.9 | 0.3 | 0.3 | 0.3
15 | UMMR |  | Study TU's planned | 3 | 3 |  | 0.25 | 0.5 | 0.5 | 0.5 | 0.75 | 0.5
|  | Veronica | Study TU's used |  | 0.45 |  | 0.25 | 0.2
|  |  | Normative TU's planned | 2
Normative TU's used
16 | LCMNFD |  | Study TU's planned | 0
Study TU's used
|  |  | Normative TU's planned | 4 | 4 |  |  |  | 0.9 | 0.9 | 0.9 | 0.9 | 0.4
Normative TU's used
17 | SECHAND |  | Study TU's planned | 0
Study TU's used
|  |  | Normative TU's planned | 1 | 1 |  |  |  | 0 | 0.4 | 0.3 | 0.3
Normative TU's used
18 | ISACM |  | Study TU's planned | 1.5 | 1.5 |  |  |  | 0.3 | 0.5 | 0.7
Study TU's used
|  |  | Normative TU's planned | 1.5 | 1.5 | [6 empty] | 0.4 | 0.4 | 0.4 | 0.3
Normative TU's used
6G |  |  | Study TU's planned | 49
6 | 6G OAM |  | Study TU's planned (6G) |  | 49 | 0 | 0 | 0 | 4 | 5 | 6 | 6 | 8 | 9 | 11
|  |  | Study TU's used(6G) |  | 6 | 3 | 1 | 2
|  |  | TU consumed according to plan | TU planned | TU actual used
|  | Total for Rel-20 Studies |  | 79.25
|  | Total for Rel-20 Normative |  | 44.75
|  | Total for Rel-20 SID/WID |  | 124
|  | Breakout sessions bonus TU used | Total | TU estimates (from SID) |  | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171) | total BONUS TU
1 | IDM | Intent driven management enhancement | [5 empty] | 0.3
2 | AIML | AIML management enhancement |  |  |  |  | 0.5
3 | NDT | NDT enhancement |  |  |  |  | 0.2
4 | SBMA | SBMA enhancement
5 | EE | Energy efficiency enhancement |  |  |  |  | 0.5 | 0.5
6 | 6G | 6G Management and orchestration | [5 empty] | 0.3
7 | MDA | MDA enhancement
8 | MADCOL | Data Management enhancement
9 | Mexpo | MExpo enhancement | [5 empty] | 0.5
10 | CCL | CCL enhancement
11 | AdNRM | AdNRM
12 | PMTMQ | PM/KPI/Trace/MDT/QoE/SON enhancement
13 | NWDAFM | NWDAFM
14 | XRMM | XR management
15 | UMMR
| Other | [5 empty] | 1.5 | 0.3
|  | Rel-20 CH SID/WID detailed plan |  | TU estimates (from SID) |  | Aug 2025 （SA5#162） | Oct 2025 （SA5#163） | Nov 2025 (SA5#164) | Feb 2026 (SA5#165) | Apr 2026 (SA5#166) | May 2026 (SA5#167) | Aug 2026 (SA5#168) | Oct 2026 (SA5#169) | Nov 2026 (SA5#170) | Feb 2027 (SA5#171) | leftover
1 | CAPCH | Charging Aspects of CAPIF Phase 3 | Study TU's planned | 1
|  | João Rodrigues | Study TU's used
|  |  | Normative TU's planned | 1
Normative TU's used
2 | XRMCH | Charging aspects for XRM | Study TU's planned | 0
Study TU's used
|  |  | Normative TU's planned | 5
Normative TU's used
3 | 6GCH | Charging Aspects of 6G System | Study TU's planned | 28
Study TU's used
Normative TU's planned
Normative TU's used
4 |  | Charging enhancements of next generation real time communication services phase 2 | Study TU's planned
Study TU's used
|  |  | Normative TU's planned | 4
Normative TU's used
5 |  | Study on 5GA Charging aspects of integrated sensing and communications | Study TU's planned | 8
Study TU's used
Normative TU's planned
Normative TU's used
6 |  | Study on Charging Aspects of satellite access phase 4 | Study TU's planned | 8
Study TU's used
Normative TU's planned
Normative TU's used
7 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used
8 |  |  | Study TU's planned
Study TU's used
Normative TU's planned
Normative TU's used