## Slide 1: Executive Report of SA5#162 SWG Charging Charging Management (CH)
Gerald Görmer, SA5 Charging SWG Chair, MATRIXX Software

## Slide 2: General information
SA5 SWG Charging leaders re-nominated:
  SWG Chair: Mr. Gerald Görmer MATRIXX Software (ETSI) CorpOPD: ATIS
  SWG Vice Chair: Ms.Chen Shan HuaWei Technologies Co., Ltd (CCSA) CorpOPD: CCSA
SA5 SWG CH work status:
  Rel-19 CH WIDs are all completed in time
  Rel-20 5GA is expected to include two more studies
  Rel-20 6G study expected to investigate on 6G requirements for Charging Prime features and Charging for Network services
SA5 SWG CH statistics:
  Registration at this meeting
  31 delegates face-to-face
  7 delegates online
  Participation to this meeting
  22 delegates attended
  Documents at this meeting
  85 total input and 55 output contributions
  3 contributions from the CH plenary
  2 LSin and no LSout
  1 new Rel-19 WID and 1 revised Rel-19 WID
  29 agreed CRs for Rel-19 WIDs, 1 pCR for Rel-20
  25 CRs for Maintenance

## Slide 3: Incoming LSs
Tdoc | Title | Source | Decision | Reply In
S5-253301 | Reply LS to C3-251642 = S5-252334 on Extending Charging Support in 5GC (S2-2506095; to CT3; cc: SA5, CT4; contact: Nokia) | SA2 | noted | 
S5-253309 | Reply LS to S5-252788 on UE type identification for UAS charging requirements (C4-253415; to: SA5; cc: CT3, CT1; contact: Qualcomm) | CT4 | noted | 

## Slide 4: Outgoing LSs
Tdoc | Title | To | Cc | Reply To

## Slide 5: Charging (CH) WIs/SIs

## Slide 6
New or Revised Charging SIDs/WIDs
Number | Title | Source
S5-253755 | New WID on Charging enhancement for disaster roaming | Ericsson
S5-253779 | Revised WID on Converged Charging aspects of CAPIF Phase 3 | Nokia

## Slide 7: SA5 progress – Summary
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
 | Rel-19 Work Items | ------ | ----- | ------ | ---- | ---- | 
1040012 | CHF Segmentation | CH_FSeg | 12/09/2025 | 90 % | SP-241001 | 100 % | completed
1040013 | Charging aspects of Ranging and Sidelink Positioning | Ranging_SL_CH | 03/03/2025 | 100 % | SP-241002 | 100 % | completed
1040018 | Charging aspects for energy efficiency of network slice | EnergySys_CH | 13/06/2025 | 100 % | SP-241003 | 100 % | completed
1040019 | Charging aspects for indirect network sharing | NetShare_CH | 12/12/2024 | 100 % | SP-241004 | 100 % | completed
1050030 | Charging for 5G ProSe Ph3 | 5G_ProSe_Ph3-CH | 12/09/2025 | 75 % | SP-241377 | 100 % | completed
1070014 | Charging aspects of satellite access Phase 3 | 5GSAT_Ph3-CH | 12/09/2025 | 90 % | SP-250365 | 100 % | completed
1070015 | Charging aspects of CAPIF | CH_CAPIF_EXT | 12/09/2025 | 70 % | SP-250366 | 100 % | completed
1070016 | Charging aspects of next generation real time communication services phase 2 | NG_RTC_Ph2-CH | 12/09/2025 | 70 % | SP-250513 | 100 % | completed
1070017 | Charging for Uncrewed Aerial Systems Phase 3 | UAS_Ph3-CH | 12/09/2025 | 45 % | SP-250512 | 100 % | completed
1070019 | Charging aspects of 5GC LoCation Services | CH_5G_eLCS_Ph3 | 12/09/2025 | 100 % | SP-250370 | 100 % | completed
1070018 | Charging for Ambient power-enabled Internet of Things | AmbientIoT-CH | 12/09/2025 | 100 % | SP-250369 | 100 % | completed
1070020 | Charging aspects for Multi-Operator Core Network (MOCN) Network Sharing | CH_MOCN_NetShare | 12/09/2025 | 75 % | SP-250819 | 100 % | completed
1080019 | Converged Charging aspects of CAPIF Phase 3 | CAPIF_Ph3_con-CH | 12/09/2025 | 0 % | SP-250509 | 100 % | revised & completed
10900xx | Charging enhancement for disaster roaming | MINT_Ph2-CH | 12/09/2025 | 0 % | S5-253755 | 100 % | For approval & completed
 | Rel-19 Studies | ------ | ----- | ------ | ----- | ---- | 
1040014 | SID on charging aspects of satellite access Phase 3 | FS_5GSAT_Ph3_CH | 1212/2024 | 100 % | SP-240980 | 100 % | completed
1040015 | SID on Charging Aspects of CAPIF | FS_CAPIF_CH | 12/12/2024 | 100 % | SP-240981 | 100 % | completed
1040016 | SID on Charging aspects of next generation real time communication services phase 2 | FS_NG_RTC_Ph2_CH | 12/12/2024 | 100 % | SP-240982 | 100 % | completed
1040017 | SID on Charging aspects of Uncrewed Aerial Vehicle | FS_UAS_CH | 12/12/2024 | 100 % | SP-240983 | 100 % | completed
 | Rel-20 Studies | ------ | ----- | ------ | ----- | ----- | 
1080014 | SID on Charging Aspects of CAPIF Phase 3 | FS_CAPIF_Ph3_CH | 12/06/2026 | 0 % | SP-250869 | 0 % | 
For more information, see the full Work Plan at: ftp://ftp.3gpp.org/information/WorkPlan

## Slide 8
Charging Exception requests
Number | Title
No exception needed
SA5 SWG Charging completed all approved Rel-19 work items in time
Thanks to all charging delegates for this great achievement!

## Slide 9: Rel-19 WID on CHF Segmentation
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040012 | CHF Segmentation | CHFSeg | 12/09/2025 | 90 % | SP-241001 | 100 % | completed
Progress since SA#108
1 CR agreed covering stage 2 aspects on TS 32.255:
  Clarify the CHF selection method
RAN impacts and dependencies:
  None identified
Next steps:
  Work item is completed

## Slide 10: Rel-19 WID on Charging Aspects for 5G ProSe Ph3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1050030 | Charging Aspects for 5G ProSe Ph3 | 5G_ProSe_Ph3-CH | 12/09/2025 | 75% | SP-241377 | 100% | completed
Progress since SA#108
  2 CRs agreed covering stage 2 aspects in TS 32.277:
    Add descriptions of multi-hop UE-to-UE relay communication via MANET networks
    Correction on the message flow for ProSe Layer-3 UE-to-UE relay communication
  2 CRs agreed covering stage 3 aspects:
    TS 32.291: Attributes for charging of layer 3 multi-hop ProSe UE-to-UE relay communication
    TS 32.298: CDR parameters for charging of layer 3 multi-hop ProSe UE-to-Network relay communication
RAN impacts and dependencies:
  None identified
Next steps:
  Work item is completed

## Slide 11: Rel-19 WID on charging aspects of satellite access Phase 3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070014 | Charging aspects of satellite access Phase 3 | 5GSAT_Ph3-CH | 12/09/2025 | 90 % | SP-250365 | 100% | completed
Progress since SA#108
  3 CRs agreed covering stage 2 and stage 3 aspects:
    32.260: Update message flow for UE-satellite-UE communication charging
    32.291: Update Data Type and Open API for UE-satellite-UE charging
    32.298: Add charging information for store and forward charging of UP CIoT
RAN impacts and dependencies:
  None identified
Next steps:
  Work item is completed

## Slide 12: Rel-19 WID on Charging aspects of CAPIF
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070015 | Charging aspects of CAPIF | CH_CAPIF_EXT | 12/09/2025 | 70 % | SP-250366 | 100% | completed
Progress since SA#108
2 CRs agreed covering stage 2 and stage 3 aspects:
  TS 32.254: CAPIF Charging Flow (ECUR)
  TS 32.298: CDR CAPIF Reference
RAN impacts and dependencies:
  None identified
Next steps:
  Work item is completed

## Slide 13: Rel-19 WID on Charging aspects of next generation real time communication services phase 2
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070016 | Charging aspects of next generation real time communication services phase 2 | NG_RTC_Ph2-CH | 12/09/2025 | 70 % | S5-250513 | 100% | completed
Progress since SA#108
2 CRs agreed covering stage 3 aspects in TS 32.291 and TS 32.298:
  Charging information for Avatar communication charging
RAN impacts and dependencies:
  None identified
Next steps:
  Work item is completed

## Slide 14: Rel-19 WID on Charging for Uncrewed Aerial Systems Phase 3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070017 | Charging for Uncrewed Aerial Systems Phase 3 | UAS_Ph3-CH | 12/09/2025 | 45 % | S5-250512 | 100% | completed
Progress since SA#108
  2 CRs agreed covering stage 2 aspects in TS 32.255 and TS 32.256:
  Add Service-level-AA for support of UAS charging
  2 CRs agreed covering stage 3 aspects in TS 32.291 and TS 32.298:
  Add Service-level-AA IE for UAS charging
RAN impacts and dependencies:
  None identified
Next steps:
  Work item is completed

## Slide 15: Rel-19 WID on Charging aspects for Multi-Operator Core Network (MOCN) Network Sharing
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070020 | WID on Charging aspects for Multi-Operator Core Network (MOCN) Network Sharing | CH_MOCN_NetShare | 12/09/2025 | 75 % | SP-250819 | 100% | completed
Progress since SA#108
3 CRs agreed covering stage 2 aspects:
  TS 32.240: Correction on the reference of network sharing charging
  TS 28.201: Add QoS level in Network Sharing Container Information, Addition of CDR information for MOCN
2 CRs agreed covering stage 3 aspects in TS 32.291 and TS 32.298:
  Addition of charging information for MOCN
RAN impacts and dependencies:
  Not known
Next steps:
  WID is completed

## Slide 16: Rel-19 WID on Converged Charging Aspects of CAPIF phase 3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1080019 | Converged Charging Aspects of CAPIF phase 3 | CAPIF_Ph3_con-CH | 12/09/2025 | 0 % | S5-253779 (SP-250509) | 100 % | Revised WID completed
Progress since SA#108
1 CR agreed covering stage 2 aspects to TS 32.254:
  • CAPIF Auditing and Provider Domain API Support (through NEF)
RAN impacts and dependencies:
  Not known
Next steps:
  WID is completed

## Slide 17: Rel-19 WID on Charging enhancement for disaster roaming
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
10900xx | Charging enhancement for disaster roaming | MINT_Ph2-CH | 12/09/2025 | 0 % | S5-253755 | 100 % | New WID for approval completied
Progress since SA#108
3 CRs agreed covering stage 2 aspects:
  TS 32.240: Addition of disaster roaming charging
  TS 32.255: Addition of disaster roaming indication charging
  TS 32.256: Addition of disaster roaming indication charging
  2 CRs agreed covering stage 2 and stage 3 aspects in TS 32.291 and TS 32.298:
  Addition of disaster roaming indication
RAN impacts and dependencies:
  Not known
Next steps:
  WID is completed

## Slide 18: Rel-20 Study on Charging Aspects of CAPIF phase 3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1080014 | SID on Charging Aspects of CAPIF phase 3 | FS_CAPIF_Ph3-CH | 12/06/2026 | 0 % | SP-250869 | 0 % | 
Progress since SA#108
  1 pCRs for TR 28.891 was approved covering
    Initial skeleton
RAN impacts and dependencies:
  Not known
Next steps:
  Start the SID

## Slide 19
Charging TSs & TRs to be sent to SA#109
Number | Title | For

## Slide 20: Charging contributions
Maintenance
TEI17
5GS_Ph1-SBI_CH
TEI18
TEI19
Release 19 Work
CHFseg
Ranging_SL_CH
5G_ProSe_Ph3-CH
5GSAT_Ph3-CH
CH_CAPIF_EXT
NG_RTC_Ph2-CH
UAS_Ph3-CH
AmbientIoT-CH
CH_MOCN_NetShare
CAPIF_Ph3_con-CH
DUMMY (MINT_Ph2-CH)

## Slide 21: Thank you!