3GPP TSG-SA6 Meeting #68	S6-253460

# Gothenburg, Sweden, 25th - 29th August 2025	                   (revision of S6-253356)

Source:	Airbus

Title:	Schedule for Rel-20 MCLOG_Ph2

Spec:	TR 23.700-39, all SA6 MC TSs

Agenda item:	9.2

Document for:	Information

Contact:	Jukka Vialen (jukka.vialen@airbus.com)

Abstract:

This living document provides the overall schedule and status for the Rel-20 Study on Logging and recording of mission critical services, Phase 2.

The schedule and target dates are for the SA6 work but status of related SIs/WIs in SA3, SA1 and CT1 is also included.

This document will be updated after every SA6 meeting until the “Logging and recording” work item is 100% ready.

The colour coding is: (Green: completed  /  Yellow: ongoing  / No highlight: not yet started)

NOTE: A high-level SA6 5GA workplan with milestones also for MCLOG_Ph2 is now in S6-253036. This document is still maintained to record the progress after each meeting in more detail and also monitor the related work in other WGs.

# Rel-20 overall time plan for MCLOG_Ph2

- Feb 17-21

  - SA6#65

    - For agreement: SID – S6-250500 - agreed

    - For discussion: TR template, initial analysis of TR 23.784 for MCLOG_Ph2 – noted

  - SA3#120: MC WID proposal from Motorola - S3-250348 – postponed

  - CT1#153: Discussion paper from Motorola – C1-250066 -   noted

  - SA1#109: nothing

- Mar 12-14 SA plenary#107:

  - SA6 SID for approval - SP-250185 - approved

- April 7-11 SA6#66 (SA3#121, CT1#154)

  - SA6#66

    - For discussion: (Final) analysis of TR 23.784 for MCLOG_Ph2 – S6-251029 - noted

    - TR skeleton + structure + Annex A agreed ==> TR 23.700-39-010

  - SA3#121: minor correction in S3-251792

  - CT1#154: nothing

- May 19-23 SA6#67 (SA3#122, SA1#110)

  - SA6#67:

    - Approved: 1 scenario, 5 KIs, 2 solutions

    - Updated SID (adding interconnection to the scope)

    - LS to SA1 on Discreet listening requirements

    - SI 10% ready.

  - SA3#122:

    - S3-252353 - New WID on mission critical security enhancements for release 20

    - S3-252348 – CRxxx TS 33.180 - Alignment of Logging Recording and Audit

  - CT1#156: nothing

  - SA1#110: nothing

- June 10-13 SA plenary#108

    - SA3 Rel-20 MC WID)

- Aug 25-29 SA6#68, SA3#123, SA1#111, CT1#157

  - SA6#68:

    - Approved: X scenarios, Y KIs, Z solutions

    - SI nn% ready.

  - CT1#157

    - Last meeting for Rel-19 stage3, confirmation that Recording is not in this release.

  - SA1, SA3 - nothing

- Sep 16-19 SA#109		(nothing for MCLOG_Ph2)

- Oct 13-17 SA6#69, SA3#124	- Scenarios, KIs, solutions, solution evaluations. Draft WID for SA6 review.

- Nov 17-21 SA6#70, SA3#125, SA1#112 – KI’s, solutions, solution evaluations, interim conclusions. WID agreement.	-

- Dec 9-12 SA plenary#109		- Approve WID.

- Feb 9-13 (2026) SA6#71	- Updated solutions, final conclusions. SI min 90% --> for approval. First normative CRs.

- Mar 9-13 (2026) SA plenary#110			- TR for approval.

- April 13-17 (2026) SA6#72		- Normative work.

- May 18-22 (2026) SA6#73		- Normative work.

- June XX-YY (2026) SA plenary#111	 - Target for normative work min 80%