**3GPP TSG- Meeting #**

**Wuhan, P.R.China, 13th – 17th October 2025 (revision of S6-253460)**

**Source: Airbus**

**Title: Schedule for Rel-20 MCLOG\_Ph2**

**Spec: TR 23.700-39, all SA6 MC TSs**

**Agenda item: 9.2**

**Document for: Information**

**Contact: Jukka Vialen (****jukka.vialen@airbus.com****)**

*Abstract:*

This living document provides the overall schedule and status for the Rel-20 Study on Logging and recording of mission critical services, Phase 2.

The schedule and target dates are for the SA6 work but status of related SIs/WIs in SA3, SA1 and CT1 is also included.

This document will be updated after every SA6 meeting until the “Logging and recording” work item is 100% ready.

The colour coding is: (Green: completed / Yellow: ongoing / No highlight: not yet started)

NOTE: A high-level SA6 5GA workplan with milestones also for MCLOG\_Ph2 is now in S6-253036. This document is still maintained to record the progress after each meeting in more detail and also to monitor the related work in other WGs.

# Rel-20 overall time plan for MCLOG\_Ph2

* **Feb 17-21**
	+ **SA6#65**
		- For agreement: SID – S6-250500 - **agreed**
		- For discussion: TR template, initial analysis of TR 23.784 for MCLOG\_Ph2 – **noted**
	+ **SA3#120:** MC WID proposal from Motorola - S3-250348 **– postponed**
	+ **CT1#153:** Discussion paper from Motorola – C1-250066 - **noted**
	+ **SA1#109:** nothing
* **Mar 12-14 SA plenary#107:**
	+ SA6 SID for approval - SP-250185 - **approved**
* **April 7-11 SA6#66 (SA3#121, CT1#154)**
	+ **SA6#66**
		- For discussion: (Final) analysis of TR 23.784 for MCLOG\_Ph2 – S6-251029 - noted
		- TR skeleton + structure + Annex A agreed ==> TR 23.700-39-010
	+ SA3#121: minor correction in S3-251792
	+ CT1#154: nothing
* **May 19-23 SA6#67 (SA3#122, SA1#110)**
	+ SA6#67:
		- Approved: 1 scenario, 5 KIs, 2 solutions
		- Updated SID (adding interconnection to the scope)
		- LS to SA1 on Discreet listening requirements
		- SI 10% ready.
	+ SA3#122:
		- S3-252353 - New WID on mission critical security enhancements for release 20
		- S3-252348 – CRxxx TS 33.180 - Alignment of Logging Recording and Audit
	+ CT1#156: nothing
	+ SA1#110: nothing
* **June 10-13 SA plenary#108**
	+ - SA3 Rel-20 MC WID)
* **Aug 25-29 SA6#68, SA3#123, SA1#111, CT1#157**
	+ SA6#68:
		- Approved: 5 scenarios, 4 KIs, 2 solutions
		- SI 20% ready.
	+ CT1#157
		- Last meeting for Rel-19 stage3, confirmation that Recording is not in this release.
	+ SA1, SA3 - nothing
* **Sep 16-19 SA#109** (nothing for MCLOG\_Ph2)
* **Oct 13-17 SA6#69, SA3#124** - Scenarios, KIs, solutions.
	+ SA6#69 :
		- Approved : x1 new scenarios, x2 updated scenarios, x3 new key issues, x4 updated key issues, x5 new solutions, x6 updated solutions
		- SI nn% ready.
	+ SA3#124 :
		- CRxxx
* **Nov 17-21 SA6#70, SA3#125, SA1#112** – KI’s, solutions, solution evaluations, interim conclusions. WID for agreement. -
* **Dec 9-12 SA plenary#109** - Approve WID.
* **Feb 9-13 (2026) SA6#71** - Updated solutions, final conclusions. SI min 90% --> for approval. First normative CRs.
* **Mar 9-13 (2026) SA plenary#110** - TR for approval.
* **April 13-17 (2026) SA6#72** - Normative work.
* **May 18-22 (2026) SA6#73** - Normative work.
* **June XX-YY (2026) SA plenary#111** - Target for normative work min 80%