## Tdoc cover sheet
3GPP TSG CT WG1 Meeting #157 Sophia Antipolis, France, 13-17 October 2025 |  | C1-256138
Source: | Huawei, HiSilicon
Title: | Work plan for the CT1 part of SEALDD_Ph2
Agenda item: | 19.33
Document for: | Discussion

## Contributions plan
Contribution Plan
Spec | Topic | Related stage 2 agreed CR # other WG tdoc(s) # | Responsible company | Related LS or other WG tdoc(s) # | CT1 meeting #; tdoc(s) # | Comments | Open issues
24.543 | Data delivery management SEAL service
| Policy triggered end-to-end redundant SEALDD transmissions | S6-233261 | Huawei |  | #151; C1-245448/Huawei, C1-245452/Huawei, C1-245874/Huawei, C1-245916 #152; C1-247071/Huawei
| Seamless SEALDD relocation enhancement | S6-240584 | Huawei |  | #151; C1-245870/Huawei
| SEALDD background data transfer | S6-240583 | Ericsson
| SEALDD enabled data transmission quality guarantee with BAT and periodicity adaptation; | S6-233288 | Ericsson |  | #151; C1-245872/Ericsson, C1-245873/Ericsson
| SEALDD enabled congestion control by L4S mechanism | S6-234092 | Huawei |  | #152; C1-246093/Huwaei, C1-247075/Huawei
| Enhancements to the SEALDD connection status procedure | S6-241446 | Ericsson |  | #151; C1-245878/Ericsson, C1-245879/Ericsson #154; C1-242383/Ericsson
| Correct BAT adaptation | S6-244137 | Ericsson |  | #152; C1-246988/Ericsson, C1-247075/Ericsson
| Correction on SEALDD data transmission connection establishment messsage | S6-244354 | Huawei |  | #152; C1-246995/Huawei, C1-246996/Huawei, C1-246997/Huawei, C1-247072/Huawei
| SEALDD enabled data transmission quality guarantee using a Non-3GPP RAT | S6-244356 | Ericsson |  | #152; C1-246991/Ericsson, C1-246992/Ericsson
| XR Application Client Capability Information Request Procedure | S6-244636 | Ericsson |  | #153; C1-250972/Ericsson, C1-250973/Ericsson | Applicable also to XRM_Ph2_App
| Correction on SEALDD URLLC transmission connection establishment request | S6-245633 | Huawei |  | #153; C1-250968/Huawei, C1-250969/Huawei, C1-250970/Huawei | Related to reply LS in C1-245880 from SA6
| Correction on Mode of reporting | S6-245683 | Ericsson |  | #153; C1-250974, C1-250975, C1-250976, C1-250977/Ericsson | Related to reply LS in C1-245880 from SA6
| Correction on mode of reporting | S6-250186 | Ericsson |  | #153; C1-250974, C1-250975, C1-250976, C1-250977/Ericsson | Related to reply LS in C1-245880 from SA6
| Corrections to non-3GPP access measurements | S6-250187 | Ericsson |  | #153; C1-250974, C1-250975, C1-250976, C1-250977/Ericsson #154; C1-242381/Ericsson | Related to reply LS in C1-245880 from SA6
| Clarification on SEALDD enabled XR data transmission service for XR application | S6-251365 | Huawei
| Corrections to message names | S6-252376 | Huawei, Ericsson |  | #155; C1-253947, C1-254032, C1-254034, C1-254035, C1-254039, C1-254047/Huawei, Ericsson | Related work already done at CT1#155
| Clarification on SEALDD client policy configuration | S6-252531 | Ericsson |  |  | Actually, related to XRM_Ph2_App rather than SEALDD_Ph2 as the initial CR on this was added by CR86v3 (S6-244738) under XRM_Ph2_App as well as related procedures (see CR128v1 in S6-250438)
| Clarification in SEALDD enabled bandwidth control procedure for XR application | S6-253244 | Ericsson |  |  | Actually, related to XRM_Ph2_App rather than SEALDD_Ph2 as the initial CR on this was added by a CR under XRM_Ph2_App. This CR impacts the EN in clause 7.2.2.1 of TS 24.543
| Correction to L4S Feedback capability | S6-253529 | Huawei |  |  | This CR impacts ENs in clauses 8.3 and A.2.4.12
| Add service overview on SEALDD enabled transmission for XR application | S6-253703 | Huawei |  |  | It is FFS if this impacts TS 24.543 in any particular way as already multi-modal transmission is part of the specification
24.548 | Network Resource Management SEAL service
Potential impact depending on progress in SA6

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
C1-245880 | LS reply on Questions on SEALDD Phase 2 work |  |  | A recommendation is provided for the unit of the “reporting interval” information. However, the unit for the “SEALDD client connection status reporting priority” is open. | Reply to C1-245880. As for answer to the CT1 Q3 (“reporting interval” information) and Q4 (“SEALDD client connection status reporting priority”), CT1 needs to define unit and valid range based on their understanding.

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
C1-245880 | LS on Questions on SEALDD Phase 2 work |  |  | CT1 asks questions about stage-2 requirements on SEALDD_Ph2 work.

## Editor's notes
Editor's notes
Spec | Topic | Related CT1 agreed CR # other WG tdoc(s) # | Responsible company | CT1 meeting #; tdoc(s) # | Comments | Open issues
24.543 | Data delivery management SEAL service
| Editor's note [WID: SEALDD_Ph2, CR#: 0052]: Specification of <xr-media-capability> and <xr-display-capability> elements is FFS. | C1-250972 | Ericsson |  | Clause 7.2.2.1. Actually, applicable also to XRM_Ph2_App (not SEALDD_Ph2 only). See CR which introduced the EN.
| Editor's note [WID: XRM_Ph2_App, CR#: 0094]: The definition of multimodalSealddFlowId is FFS. | C1-255574 | Huawei |  | Clause 7.2.24.2, clause 8.5. It also applies to SEALDD_Ph2.
| Editor's note [WID: XRM_Ph2_App, CR#: 0095]: The definition of multimodalSealddFlowId is FFS. | C1-255575 | Huawei |  | Clause A.4.4.2.2.6, A.A.4.5.2. It also applies to SEALDD_Ph2.
| Editor's note [WID: XRM_Ph2_App, CR#: 0095]: To align with stage 2 on changing XR to multi-modal is FFS. | C1-255575 | Ericsson |  | Clause 7.2.24.3, Clause 7.2.24.4, Clause A.4.4. It also applies to SEALDD_Ph2.
| Editor's note [WID: SEALDD_Ph2, CR#: 0085]: The data type L4sFeedbackCapability to support L4S mechanism will be checked to be aligned with the latest stage-2 requirements. | C1-255584 | Huawei |  | Clause 8.3, Clause A.2.4.12
| Editor's note [WID: XRM_Ph2_App, CR#: 0094]: The update of XML schema to support multimodalSealddFlowId is FFS. | C1-255574 | Huawei |  | Clause 8.4.2. It also applies to SEALDD_Ph2.
| Editor's note [WID: SEALDD_Ph2, CR#: 0053]: Specification of XrMediaCap and XrDisplayCap data types is FFS. | C1-250973 | Ericsson |  | Clause A.2.4.9. Actually, applicable also to XRM_Ph2_App (not SEALDD_Ph2 only). See CR which introduced the EN.
24.548 | Network Resource Management SEAL service
Potential impact depending on progress in SA6