## Cover
3GPP TSG CT WG1 Meeting #157 |  | C1-256242
Sophia-Antipolis, France 13-17 October 2025
Source: | CATT
Title: | eLSAPP CT1 Work plan
Document for: | Information
Agenda Item: | 19.32
Work Item / Release: | Rel-19

## Contributions plan
Contribution Plan
Spec | Topic | Related LS or other WG tdoc(s) # | CT1 meeting # | tdoc(s) # | Comments | Open issues
24.545
| Support for adaptive location configuration and reporting |  | CT1#151 | C1-245867
| Support geofencing based query |  | CT1#151 | C1-245950
| Exposure of value-added UE location information |  | CT1#151 | C1-245951
| LMS reuse the stored UE location information |  | CT1#152 | C1-246585
| Clarification on Location area monitoring information procedure |  | CT1#152 | C1-247054
| Update the procedures for reusing the stored UE location |  | CT1#153 | C1-251046
| Add the velocity in location reporting related procedures |  | CT1#153 | C1-251173
| Add failure case in the on-demand location reporting procedure |  | CT1#153 | C1-251191
| Reference to obsoleted IETF RFC4122 |  | CT1#154 | C1-252401
| Add the confirm location verification procedure |  | CT1#154 | C1-252404
| Uniform the IE description for the velocity |  | CT1#154 | C1-252456
| Add the confirm location service subscription procedure |  | CT1#154 | C1-252472
| Add the confirm location notification procedure |  | CT1#154 | C1-252479
| Optimize location services for multiple UEs sharing same location |  | CT1#154 | C1-252556
| Correction to wrong element name, data semantics, and table numbering |  | CT1#155 | C1-253147
| Introduction of new location positioning configuration procedure for HTTP |  | CT1#155 | C1-253965
| Introduction of new location positioning configuration procedure for CoAP |  | CT1#155 | C1-253966
| Introduction of new history location result report procedure for HTTP |  | CT1#155 | C1-253967
| Correction to velocity information |  | CT1#155 | C1-254015
| Introduction of new history location result report procedure for CoAP |  | CT1#155 | C1-254023
| Support for sidelink positioning management |  | CT1#155 | C1-254038
| Add the confirm location verification procedure |  | CT1#155 | C1-254045
| Add the short-Range based positioning information procedure |  | CT1#155 | C1-254046
| Introduce the HTTP procedure of LM Server identifying the UEs sharing the same location |  | CT1#156 | C1-255129
| Introduction of new location positioning subscription procedure for HTTP |  | CT1#156 | C1-255491
| Introduction of new location notification procedure for HTTP |  | CT1#156 | C1-255493
| Introduce the CoAP procedure of LM Server identifying the UEs sharing the same location |  | CT1#156 | C1-255494
| Resolution of editor's note on XML updates for the location positioning configuration procedure |  | CT1#156 | C1-255495
| Resolution of editor's note on XML updates for the history location result report procedure |  | CT1#156 | C1-255496
| Resolution of editor's note on CCDL document updates for the history location result report procedure |  | CT1#156 | C1-255497
| Resolution of editor's note on CCDL document updates for the location positioning configuration procedure |  | CT1#156 | C1-255498
| Coding of the short-Range based positioning information HTTP procedure |  | CT1#156 | C1-255499
| Add the short-Range based positioning information CoAP procedure |  | CT1#156 | C1-255500
| Coding of the sidelink positioning management procedure |  | CT1#156 | C1-255501
| Add the sidelink positioning management CoAP procedure |  | CT1#156 | C1-255502
| Resolve the EN related to confirm location notification procedure |  | CT1#156 | C1-255503
| Resolve the EN related to confirm location verification procedure |  | CT1#156 | C1-255504
| Resolve the EN related to failure case |  | CT1#156 | C1-255505
| Correction because of approved CRs in C1-254038 and C1-254046 |  | CT1#156 | C1-255506
| Resolve the EN related to location QoS |  | CT1#156 | C1-255507
| Introduction of new location positioning subscription procedure for CoAP |  | CT1#156 | C1-255571
24.546
| Introduction of new data type for location positioning configuration procedure for CoAP |  | CT1#155 | C1-253969
24.559
| Collision Detection Analytics |  | CT1#152 | C1-247177
| Location-related UE Group Analytics |  | CT1#152 | C1-247178

## Expected contributions
Expected Contributions for future meetings
Number | Topic | Related LS or other WG tdoc(s) # or TS # | CT1 Spec | CT1 meeting | Volunteered company/delegate | Contribution(s) | Note
Editor's note
1 | Editor's note (WIC: eLSAPP, CR 0171): SLM server HTTP procedure for the location positioning subscription procedure is FFS. |  | TS 24.545, clause 6.2.26.2 | CT1#157 | CATT |  | This EN is in the notification procedure.
2 | Editor's note (WIC: eLSAPP, CR 0170): Data structure updates for the location positioning subscription procedure are FFS. |  | TS 24.545, clause 7.3 | CT1#157
3 | Editor's note (WIC: eLSAPP, CR 0171): Data structure updates for the location positioning notification procedure are FFS |  | TS 24.545, clause 7.3 | CT1#157 | CATT
4 | Editor's note (WIC: eLSAPP, CR 0170): XML updates for the location positioning subscription procedure are FFS. |  | TS 24.545, clause 7.4.2 | CT1#157
5 | Editor's note (WIC: eLSAPP, CR 0171): XML updates for the location positioning notification procedure are FFS. |  | TS 24.545, clause 7.4.2 | CT1#157 | CATT
6 | Editor's note (WIC: eLSAPP, CR 0170): Data semantics updates for the location positioning subscription procedure are FFS. |  | TS 24.545, clause 7.5 | CT1#157
7 | Editor's note (WIC: eLSAPP, CR 0171): Data semantics updates for the location positioning notification procedure are FFS. |  | TS 24.545, clause 7.5 | CT1#157 | CATT
8 | Editor's note (WIC: eLSAPP, CR 0178): CCDL document updates for the sidelink positioning / ranging management procedure are FFS. |  | TS 24.545, clause B.3.1.5.2 | CT1#157 | CATT
9 | Editor's note (WIC: eLSAPP, CR 0171): Updates for the location positioning subscription procedure are FFS. |  | TS 24.545, clause B.4.1 | CT1#157

## Incoming LSs
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments