## Tdoc cover sheet
3GPP TSG CT WG1 Meeting #157 3GPP TSG CT WG3 Meeting #143 3GPP TSG CT WG4 Meeting #131 Sophia-Antipolis, France, 13th to 17th, October, 2025 |  | C1-256075 C3-254078 C4-254079
Source: | InterDigital
Title: | Work plan for UIA_ARC
Agenda item: | 19.28
Document for: | Information/Discussion

## CT1
Contribution Plan CT1
Meeting | Related stage 2 agreed CR # other WG tdoc(s) # | Title | SA2 TDoc source Companies | Impacted Stage-2 TS | Impacted stage-3 TS | Volunteered company | Comments
KI#4 Identifying non-3GPP Devices Connecting behind a UE or 5G-RG
SA2#108 Plenary cycle included SA2#168 and SA2#169
SA2#169 |  |  | SA2#166-Ad Hoc-e - Meeting
UIA_ARC was not on agenda for this meeting.
SA2#168 |  |  | SA2#166-Ad Hoc-e - Meeting
SA2#168 | S2-2502894 | Clarification on AF-5GC interaction for provisioning non-3GPP device identifiers | Apple, Charter Communications | 23.316 | N/A
SA2#168 | S2-2503000 | Adding a Reference to the Home Routed Roaming PDU Session Modification Procedure | InterDigital Inc., LG Electronics, Samsung, Nokia | 23.503 | N/A
SA2#168 | S2-2504028 | Update on Non-3GPP Device Identifier(s) Information provisioning and policy control | Xiaomi | 23.502 | N/A
SA2#168 | S2-2504029 | Updating the Nsmf_PDUSession_Update service description to account for non-3GPP device connection information | InterDigital Inc., LG Electronics, Samsung, Nokia | 23.502 | N/A
SA2#168 | S2-2504032 | Clarifying port ranges and removing EN | Ericsson | 23.501 | 24.501 |  | Encoding of the Connection information will be done by CT1. Note: Stage-2 TS was incorrect, changed to to TS 23.501 from TS 23.502
SA2#168 | S2-2504253 | Inclusion of several Non-3GPP Device Identifiers | Nokia, InterDigital Inc., LG Electronics, Samsung, ZTE, Xiaomi | 23.501 | 24.501 | InterDigital, | Multiple device identifier in single PDU Mod procedure + Rejection of whole procedure if any device identifier is not provisioned in the UDR.
SA2#168 | S2-2504259 | Clarification on the subscription to UDR | ZTE, Nokia, NEC, Xiaomi | 23.502 | N/A
SA2#168 | S2-2504260 | Clarification on PDU Session for non-3GPP device | LG Electronics | 23.501 | 24.501 | InterDigital, | Related to PDU Session selection for QoS differentiation
SA2#168 | S2-2504334 | Clarifications on SM signalling including non-3GPP device identifiers for QoS differentiation | Apple, Charter Communications, Nokia | 23.501 | 24.501 | InterDigital, | PDU modification reject scenario.
SA2#168 | S2-2504335 | Clarifications to Session Management aspects for handling Non-3GPP Device Identifiers | Samsung | 23.501 | 24.501 | InterDigital, | PDU modification reject scenario.
SA2#168 | S2-2504336 | QoS differention for multiple Non-3GPP devices | Ericsson, AT&T, Xiaomi, Nokia, CableLabs, ZTE | 23.502 | 24.501 |  | Multiple device identifier in single PDU Mod procedure + Rejection of whole procedure if any device identifier is not provisioned in the UDR.
SA2#168 | S2-2504477 | Clarificaiton on supporting multiple non-3GPP device identifiers | Huawei, HiSilicon, Samsung, Deutsche Telekom, Nokia, LGE, Charter Communications, ZTE | 23.503 | N/A
SA2#107 Plenary cycle included SA2#166-Ad Hoc-e and SA2#167
SA2#167 |  |  | SA2#166-Ad Hoc-e - Meeting
UIA_ARC was not on agenda for this meeting.
SA2#166-Ad Hoc-e - Meeting
SA2#166-AH | S2-2500215 | SM Policy Association Modification for Non-3GPP Device Identifiers | Nokia, InterDigital Inc. | 23.502 | N/A
SA2#166-AH | S2-2500349 | PCC enhancements for support of identified non-3GPP devices | China Mobile | 23.503 | 24.501
SA2#166-AH | S2-2500803 | Clarification on AF provisioning | ZTE | 23.501 | N/A
SA2#166-AH | S2-2500804 | Resolve the EN on the PDU session establishment and Reference correction | ZTE | 23.501 | N/A |  | Removal of EN, no potential impact
SA2#166-AH | S2-2501219 | Clarification to SMF and PCF behaviour during Session modification for handling device identifiers | Samsung | 23.502 | 24.501 |  | PDU Session Modification Reject scenario
SA2#166-AH | S2-2501220 | Clarification on AF provisioning of Non-3GPP device identifier information | Samsung | 23.502 | N/A
SA2#166-AH | S2-2501221 | Resolving EN related to PCF initiated Policy Updates | Nokia, InterDigital Inc., CableLabs, Charter Communications | 23.316 | N/A
SA2#166-AH | S2-2501222 | QoS differentiation of non-3GPP devices behind 5G-RG | CableLabs, Charter Communications, Nokia | 23.316 | N/A
SA2#166-AH | S2-2501223 | Definition of non-3GPP device connection information | Qualcomm Incorporated, InterDigital, ETRI | 23.501 | 24.501 |  | Clarified Non-3GPP Device Connection Information, to be defined in CT1.
SA2#166-AH | S2-2501224 | Removal of N3GPP device from UDR | Huawei, Hisilicon, China Telecom | 23.502 | N/A
SA2#166-AH | S2-2501225 | Clarification on session management enhancement | ZTE | 23.501 | 24.501 | ZTE | PDU Session Modification Reject scenario
SA2#166-AH | S2-2501226 | Clarification on UE triggering request for change of QoS | Apple | 23.501 | 24.501
SA2#166-AH | S2-2501227 | Further details for QoS information | Xiaomi | 23.501 | N/A
SA2#166-AH | S2-2501228 | Clarification on roaming support for Non-3GPP Device Identifier | LG Electronics | 23.501 | 24.501
SA2#166-AH | S2-2501229 | PCC enhancements for support of identified non-3GPP devices | Huawei, HiSilicon, China Telecom | 23.503 | N/A
SA2#166-AH | S2-2501230 | Corrections to PCR trigger and SM policy modification for Non-3GPP device identifier | Samsung | 23.503 | N/A
SA2#166-AH | S2-2501231 | Clarification on the AF provisioning procedure | ZTE | 23.502 | N/A
SA2#106 Plenary cycle included SA2#165 and SA2#166
SA2#166
SA2#166 | S2-2412558 | Identifying non-3GPP devices behind 5G-RG | CableLabs, Nokia, InterDigital, Charter Communications, Deutsche Telekom, Samsung | 23.316 | 24.501 |  | Revision of S2-2411020 from the SA2#165 meeting.
SA2#166 | S2-2412559 | Adding Device Identifier in PDU session related signalling | Lenovo, InterDigital, Qualcomm, NEC, Nokia, Huawei, Samsung, Oppo, Xiaomi, Charter Communications, Cablelabs | 23.502 | 24.501
SA2#166 | S2-2412779 | Update of services pertaining to defining Device Identifiers | Nokia, CableLabs, ZTE, Oppo, Xiaomi, Ericsson, NEC, Deutsche Telekom, Charter Communications, Samsung | 23.502 | N/A |  | Revision of S2-2411085 from the SA2#165 Meeting.
SA2#166 | S2-2412780 | PCC enhancements for support of identified non-3GPP devices | CATT, InterDigital Inc., NEC, Nokia, OPPO, ZTE, Deutsche Telekom, ETRI, Qualcomm, Samsung, Lenovo, Charter Communications | 23.503 | 24.501 |  | Revision of S2-2411083 from the SA2#165 Meeting. Reject handling of the PDU Session modification procedure.
SA2#165
SA2#165 | S2-2411020 | Identifying non-3GPP devices behind 5G-RG | CableLabs, Nokia, InterDigital, Charter Communications, Deutsche Telekom | 23.316 | N/A
SA2#165 | S2-2411026 | AF Provisioning of non-3GPP device identifer information to UDR | ZTE, Nokia, NEC, Deutsche Telekom, Samsung, Xiaomi, ETRI | 23.502 | N/A
SA2#165 | S2-2411079 | Definition of identifiers of N3GPP device behind UE/5G-RG | Huawei, HiSilicon, InterDigital Inc, Deutsche Telekom, Nokia | 23.501 | N/A
SA2#165 | S2-2411081 | UDR enhancement supporting Device Identifier of non-3GPP Devices connecting behind a UE/5G-RG | Xiaomi, NEC, Nokia, OPPO, InterDigital Inc. | 23.501 | N/A
SA2#165 | S2-2411083 | PCC enhancements for support of identified non-3GPP devices | CATT, InterDigital Inc., NEC, Nokia, OPPO, ZTE, Deutsche Telekom | 23.503 | N/A
SA2#165 | S2-2411085 | Update of services pertaining to defining Device Identifiers | Nokia, CableLabs, ZTE, Oppo, Xiaomi, Ericsson, NEC, Deutsche Telekom, Charter Communications, Samsung | 23.502 | N/A
SA2#165 | S2-2411260 | Ericsson, Deutsche Telekom | Ericsson, Deutsche Telekom | 23.503 | N/A
SA2#165 | S2-2411269 | Support of N3GPP device behind UE/5G-RGas concluded in TS 23.700-34 KI#4 | Huawei, HiSilicon, InterDigital Inc., Deutsche Telekom, NEC, Nokia, ZTE, Oppo, Lenovo | 23.501 | 24.501 | huawei | PDU Session Modification C1-246746 (Xiaomi) - Postponed. C1-246747 (Ericsson) - Postponed. General Section Update C1-246744 (Xiaomi) - Postponed C1-247150 (Huawei, HiSilicon) - Postponed

## CT3
Contribution Plan CT3
Meeting | Related stage 2 agreed CR # other WG tdoc(s) # | Title | SA2 TDoc source Companies | Impacted Stage-2 TS | Impacted stage-3 TS | Volunteered company | Comments
KI#4 Identifying non-3GPP Devices Connecting behind a UE or 5G-RG
SA2#108 Plenary cycle included SA2#168 and SA2#169
SA2#169 |  |  | SA2#166-Ad Hoc-e - Meeting
UIA_ARC was not on agenda for this meeting.
SA2#168 |  |  | SA2#166-Ad Hoc-e - Meeting
SA2#168 | S2-2502894 | Clarification on AF-5GC interaction for provisioning non-3GPP device identifiers | Apple, Charter Communications | 23.316 | N/A
SA2#168 | S2-2503000 | Adding a Reference to the Home Routed Roaming PDU Session Modification Procedure | InterDigital Inc., LG Electronics, Samsung, Nokia | 23.503 | N/A
SA2#168 | S2-2504028 | Update on Non-3GPP Device Identifier(s) Information provisioning and policy control | Xiaomi | 23.502 | N/A
SA2#168 | S2-2504029 | Updating the Nsmf_PDUSession_Update service description to account for non-3GPP device connection information | InterDigital Inc., LG Electronics, Samsung, Nokia | 23.502 | N/A
SA2#168 | S2-2504032 | Clarifying port ranges and removing EN | Ericsson | 23.502 | N/A
SA2#168 | S2-2504253 | Inclusion of several Non-3GPP Device Identifiers | Nokia, InterDigital Inc., LG Electronics, Samsung, ZTE, Xiaomi | 23.501 | N/A
SA2#168 | S2-2504259 | Clarification on the subscription to UDR | ZTE, Nokia, NEC, Xiaomi | 23.502 | 29.512
SA2#168 | S2-2504260 | Clarification on PDU Session for non-3GPP device | LG Electronics | 23.501 | N/A
SA2#168 | S2-2504334 | Clarifications on SM signalling including non-3GPP device identifiers for QoS differentiation | Apple, Charter Communications, Nokia | 23.501 | N/A
SA2#168 | S2-2504335 | Clarifications to Session Management aspects for handling Non-3GPP Device Identifiers | Samsung | 23.501 | N/A
SA2#168 | S2-2504336 | QoS differention for multiple Non-3GPP devices | Ericsson, AT&T, Xiaomi, Nokia, CableLabs, ZTE | 23.502 | N/A
SA2#168 | S2-2504477 | Clarificaiton on supporting multiple non-3GPP device identifiers | Huawei, HiSilicon, Samsung, Deutsche Telekom, Nokia, LGE, Charter Communications, ZTE | 23.503 | 29.512, 29.513 | Nokia
SA2#107 Plenary cycle included SA2#166-Ad Hoc-e and SA2#167
SA2#167
UIA_ARC was not on agenda for this meeting.
SA2#166-Ad Hoc-e - Meeting
SA2#166-AH | S2-2500215 | SM Policy Association Modification for Non-3GPP Device Identifiers | Nokia, InterDigital Inc. | 23.502 | 29.512, 29.513
SA2#166-AH | S2-2500349 | PCC enhancements for support of identified non-3GPP devices | China Mobile | 23.503 | N/A
SA2#166-AH | S2-2500803 | Clarification on AF provisioning | ZTE | 23.501 | 29.522
SA2#166-AH | S2-2500804 | Resolve the EN on the PDU session establishment and Reference correction | ZTE | 23.501 | N/A |  | Removal of EN, no potential impact
SA2#166-AH | S2-2501219 | Clarification to SMF and PCF behaviour during Session modification for handling device identifiers | Samsung | 23.502 |  |  | PDU Modification Reject scenario, Potential CT3 impact ?
SA2#166-AH | S2-2501220 | Clarification on AF provisioning of Non-3GPP device identifier information | Samsung | 23.502 | 29.522 |  | Editorial corrections and moving text, might have no impact
SA2#166-AH | S2-2501221 | Resolving EN related to PCF initiated Policy Updates | Nokia, InterDigital Inc., CableLabs, Charter Communications | 23.316 | 29.512, 29.513
SA2#166-AH | S2-2501222 | QoS differentiation of non-3GPP devices behind 5G-RG | CableLabs, Charter Communications, Nokia | 23.316 | N/A
SA2#166-AH | S2-2501223 | Definition of non-3GPP device connection information | Qualcomm Incorporated, InterDigital, ETRI | 23.501 | N/A
SA2#166-AH | S2-2501224 | Removal of N3GPP device from UDR | Huawei, Hisilicon, China Telecom | 23.502 | 29.512, 29.513, 29.522
SA2#166-AH | S2-2501225 | Clarification on session management enhancement | ZTE | 23.501 | N/A
SA2#166-AH | S2-2501226 | Clarification on UE triggering request for change of QoS | Apple | 23.501 | N/A
SA2#166-AH | S2-2501227 | Further details for QoS information | Xiaomi | 23.501 | N/A
SA2#166-AH | S2-2501228 | Clarification on roaming support for Non-3GPP Device Identifier | LG Electronics | 23.501 | N/A
SA2#166-AH | S2-2501229 | PCC enhancements for support of identified non-3GPP devices | Huawei, HiSilicon, China Telecom | 23.503 | 29.512, 29.513, 29.519
SA2#166-AH | S2-2501230 | Corrections to PCR trigger and SM policy modification for Non-3GPP device identifier | Samsung | 23.503 | 29.512, 29.513
SA2#166-AH | S2-2501231 | Clarification on the AF provisioning procedure | ZTE | 23.502 | 29.522
SA2#106 Plenary cycle included SA2#165 and SA2#166
SA2#166
SA2#166 | S2-2412558 | Identifying non-3GPP devices behind 5G-RG | CableLabs, Nokia, InterDigital, Charter Communications, Deutsche Telekom, Samsung | 23.316 | N/A |  | Revision of S2-2411020 from the SA2#165 meeting.
SA2#166 | S2-2412559 | Adding Device Identifier in PDU session related signalling | Lenovo, InterDigital, Qualcomm, NEC, Nokia, Huawei, Samsung, Oppo, Xiaomi, Charter Communications, Cablelabs | 23.502 | N/A
SA2#166 | S2-2412779 | Update of services pertaining to defining Device Identifiers | Nokia, CableLabs, ZTE, Oppo, Xiaomi, Ericsson, NEC, Deutsche Telekom, Charter Communications, Samsung | 23.502 | 29.512, 29.519, 29.522 |  | Revision of S2-2411085 from the SA2#165 Meeting.
SA2#166 | S2-2412780 | PCC enhancements for support of identified non-3GPP devices | CATT, InterDigital Inc., NEC, Nokia, OPPO, ZTE, Deutsche Telekom, ETRI, Qualcomm, Samsung, Lenovo, Charter Communications | 23.503 | 29.512, 29.513 |  | Revision of S2-2411083 from the SA2#165 Meeting.
SA2#165
SA2#165 | S2-2411020 | Identifying non-3GPP devices behind 5G-RG | CableLabs, Nokia, InterDigital, Charter Communications, Deutsche Telekom | 23.316 | N/A
SA2#165 | S2-2411026 | AF Provisioning of non-3GPP device identifer information to UDR | ZTE, Nokia, NEC, Deutsche Telekom, Samsung, Xiaomi, ETRI | 23.502 | 29.522 | Huawei, Nokia | C3-246492 (Huawei, Nokia, AT&T, Ericsson) - Agreed.
SA2#165 | S2-2411079 | Definition of identifiers of N3GPP device behind UE/5G-RG | Huawei, HiSilicon, InterDigital Inc, Deutsche Telekom, Nokia | 23.501 | N/A
SA2#165 | S2-2411081 | UDR enhancement supporting Device Identifier of non-3GPP Devices connecting behind a UE/5G-RG | Xiaomi, NEC, Nokia, OPPO, InterDigital Inc. | 23.501 | 29.519, 29.522 | Nokia | C3-246437 (Huawei, Nokia, Ericsson) - Agreed.
SA2#165 | S2-2411083 | PCC enhancements for support of identified non-3GPP devices | CATT, InterDigital Inc., NEC, Nokia, OPPO, ZTE, Deutsche Telekom | 23.503 | 29.512, 29.513 | Nokia | C3-246491 (Nokia) - Agreed
SA2#165 | S2-2411085 | Update of services pertaining to defining Device Identifiers | Nokia, CableLabs, ZTE, Oppo, Xiaomi, Ericsson, NEC, Deutsche Telekom, Charter Communications, Samsung | 23.502 | 29.512, 29.519, 29.522 | Huawei, Nokia | C3-246212 (Nokia) - Merged to C3-246492 C3-246213 (Nokia) - Merged to C3-246437
SA2#165 | S2-2411260 | Ericsson, Deutsche Telekom | Ericsson, Deutsche Telekom | 23.503 | 29.512, 29.513 | Huawei | C3-246491 (Nokia) - Agreed
SA2#165 | S2-2411269 | Support of N3GPP device behind UE/5G-RGas concluded in TS 23.700-34 KI#4 | Huawei, HiSilicon, InterDigital Inc., Deutsche Telekom, NEC, Nokia, ZTE, Oppo, Lenovo | 23.501 | N/A

## CT4
Contribution Plan CT4
Meeting | Related stage 2 agreed CR # other WG tdoc(s) # | Title | SA2 TDoc source Companies | Impacted Stage-2 TS | Impacted stage-3 TS | Volunteered company | Comments
KI#4 Identifying non-3GPP Devices Connecting behind a UE or 5G-RG
SA2#108 Plenary cycle included SA2#168 and SA2#169
SA2#169 |  |  | SA2#166-Ad Hoc-e - Meeting
UIA_ARC was not on agenda for this meeting.
SA2#168 |  |  | SA2#166-Ad Hoc-e - Meeting
SA2#168 | S2-2502894 | Clarification on AF-5GC interaction for provisioning non-3GPP device identifiers | Apple, Charter Communications | 23.316 | N/A
SA2#168 | S2-2503000 | Adding a Reference to the Home Routed Roaming PDU Session Modification Procedure | InterDigital Inc., LG Electronics, Samsung, Nokia | 23.503 | N/A
SA2#168 | S2-2504028 | Update on Non-3GPP Device Identifier(s) Information provisioning and policy control | Xiaomi | 23.502 | N/A
SA2#168 | S2-2504029 | Updating the Nsmf_PDUSession_Update service description to account for non-3GPP device connection information | InterDigital Inc., LG Electronics, Samsung, Nokia | 23.502 | 29.502
SA2#168 | S2-2504032 | Clarifying port ranges and removing EN | Ericsson | 23.502 | N/A
SA2#168 | S2-2504253 | Inclusion of several Non-3GPP Device Identifiers | Nokia, InterDigital Inc., LG Electronics, Samsung, ZTE, Xiaomi | 23.501 | N/A
SA2#168 | S2-2504259 | Clarification on the subscription to UDR | ZTE, Nokia, NEC, Xiaomi | 23.502 | N/A
SA2#168 | S2-2504260 | Clarification on PDU Session for non-3GPP device | LG Electronics | 23.501 | N/A
SA2#168 | S2-2504334 | Clarifications on SM signalling including non-3GPP device identifiers for QoS differentiation | Apple, Charter Communications, Nokia | 23.501 | N/A
SA2#168 | S2-2504335 | Clarifications to Session Management aspects for handling Non-3GPP Device Identifiers | Samsung | 23.501 | N/A
SA2#168 | S2-2504336 | QoS differention for multiple Non-3GPP devices | Ericsson, AT&T, Xiaomi, Nokia, CableLabs, ZTE | 23.502 | N/A
SA2#168 | S2-2504477 | Clarificaiton on supporting multiple non-3GPP device identifiers | Huawei, HiSilicon, Samsung, Deutsche Telekom, Nokia, LGE, Charter Communications, ZTE | 23.503 | N/A
SA2#107 Plenary cycle included SA2#166-Ad Hoc-e and SA2#167
SA2#167 |  |  | SA2#166-Ad Hoc-e - Meeting
UIA_ARC was not on agenda for this meeting.
SA2#166-Ad Hoc-e - Meeting
SA2#166-AH | S2-2500215 | SM Policy Association Modification for Non-3GPP Device Identifiers | Nokia, InterDigital Inc. | 23.502 | N/A
SA2#166-AH | S2-2500349 | PCC enhancements for support of identified non-3GPP devices | China Mobile | 23.503 | N/A
SA2#166-AH | S2-2500803 | Clarification on AF provisioning | ZTE | 23.501 | N/A
SA2#166-AH | S2-2500804 | Resolve the EN on the PDU session establishment and Reference correction | ZTE | 23.501 | N/A |  | Removal of EN, no potential impact
SA2#166-AH | S2-2501219 | Clarification to SMF and PCF behaviour during Session modification for handling device identifiers | Samsung | 23.502 | N/A
SA2#166-AH | S2-2501220 | Clarification on AF provisioning of Non-3GPP device identifier information | Samsung | 23.502 | N/A
SA2#166-AH | S2-2501221 | Resolving EN related to PCF initiated Policy Updates | Nokia, InterDigital Inc., CableLabs, Charter Communications | 23.316 | N/A
SA2#166-AH | S2-2501222 | QoS differentiation of non-3GPP devices behind 5G-RG | CableLabs, Charter Communications, Nokia | 23.316 | N/A
SA2#166-AH | S2-2501223 | Definition of non-3GPP device connection information | Qualcomm Incorporated, InterDigital, ETRI | 23.501 | N/A
SA2#166-AH | S2-2501224 | Removal of N3GPP device from UDR | Huawei, Hisilicon, China Telecom | 23.502 | N/A
SA2#166-AH | S2-2501225 | Clarification on session management enhancement | ZTE | 23.501 | N/A
SA2#166-AH | S2-2501226 | Clarification on UE triggering request for change of QoS | Apple | 23.501 | N/A
SA2#166-AH | S2-2501227 | Further details for QoS information | Xiaomi | 23.501 | N/A
SA2#166-AH | S2-2501228 | Clarification on roaming support for Non-3GPP Device Identifier | LG Electronics | 23.501 | N/A
SA2#166-AH | S2-2501229 | PCC enhancements for support of identified non-3GPP devices | Huawei, HiSilicon, China Telecom | 23.503 | N/A
SA2#166-AH | S2-2501230 | Corrections to PCR trigger and SM policy modification for Non-3GPP device identifier | Samsung | 23.503 | N/A
SA2#166-AH | S2-2501231 | Clarification on the AF provisioning procedure | ZTE | 23.502 | N/A
SA2#106 Plenary cycle included SA2#165 and SA2#166
SA2#166
SA2#166 | S2-2412558 | Identifying non-3GPP devices behind 5G-RG | CableLabs, Nokia, InterDigital, Charter Communications, Deutsche Telekom, Samsung | 23.316 | N/A |  | Revision of S2-2411020 from the SA2#165 meeting.
SA2#166 | S2-2412559 | Adding Device Identifier in PDU session related signalling | Lenovo, InterDigital, Qualcomm, NEC, Nokia, Huawei, Samsung, Oppo, Xiaomi, Charter Communications, Cablelabs | 23.502 | N/A
SA2#166 | S2-2412779 | Update of services pertaining to defining Device Identifiers | Nokia, CableLabs, ZTE, Oppo, Xiaomi, Ericsson, NEC, Deutsche Telekom, Charter Communications, Samsung | 23.502 | N/A |  | Revision of S2-2411085 from the SA2#165 Meeting.
SA2#166 | S2-2412780 | PCC enhancements for support of identified non-3GPP devices | CATT, InterDigital Inc., NEC, Nokia, OPPO, ZTE, Deutsche Telekom, ETRI, Qualcomm, Samsung, Lenovo, Charter Communications | 23.503 | N/A |  | Revision of S2-2411083 from the SA2#165 Meeting.
SA2#165
SA2#165 | S2-2411020 | Identifying non-3GPP devices behind 5G-RG | CableLabs, Nokia, InterDigital, Charter Communications, Deutsche Telekom | 23.316 | N/A
SA2#165 | S2-2411026 | AF Provisioning of non-3GPP device identifer information to UDR | ZTE, Nokia, NEC, Deutsche Telekom, Samsung, Xiaomi, ETRI | 23.502 | N/A
SA2#165 | S2-2411079 | Definition of identifiers of N3GPP device behind UE/5G-RG | Huawei, HiSilicon, InterDigital Inc, Deutsche Telekom, Nokia | 23.501 | 23.003 | Huawei | C4-250637 (Huawei, InterDigital) C4-245216 (Huawei) - Postponed.
SA2#165 | S2-2411081 | UDR enhancement supporting Device Identifier of non-3GPP Devices connecting behind a UE/5G-RG | Xiaomi, NEC, Nokia, OPPO, InterDigital Inc. | 23.501 | 29.504 | Huawei | C4-245289 (Nokia) Merged into C4-245539 C4-245539 (Huawei, Nokia) Agreed.
SA2#165 | S2-2411083 | PCC enhancements for support of identified non-3GPP devices | CATT, InterDigital Inc., NEC, Nokia, OPPO, ZTE, Deutsche Telekom | 23.503 | N/A
SA2#165 | S2-2411085 | Update of services pertaining to defining Device Identifiers | Nokia, CableLabs, ZTE, Oppo, Xiaomi, Ericsson, NEC, Deutsche Telekom, Charter Communications, Samsung | 23.502 | N/A
SA2#165 | S2-2411260 | Ericsson, Deutsche Telekom | Ericsson, Deutsche Telekom | 23.503 | N/A
SA2#165 | S2-2411269 | Support of N3GPP device behind UE/5G-RGas concluded in TS 23.700-34 KI#4 | Huawei, HiSilicon, InterDigital Inc., Deutsche Telekom, NEC, Nokia, ZTE, Oppo, Lenovo | 23.501 | N/A

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT meeting #; tdoc(s) # | Open issues | Comments
S2-2504337 | LS reply on support for multiple non-3GPP device identifiers | S2-2502806 / C1-250822 | C1-253031 |  | Reply back from the SA2

## Outcoming LSs
Outcoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
C1-250822 | LS on support for multiple non-3GPP device identifiers |  | CT1#153 Athens, Greece |  | LS Out sent to SA2 and copied to CT3.

## CT WG Progress
CT WGs Progress
Meeting | SA2 TDoc number | SA2 TDoc title / Title | SA2 TDoc source companies | Stage-2 Impacted TS | Stage-3 CT Impacted TS | Tageted meeting | Addressed in CT WGs? | Comments or related CT Tdocs
N/A | N/A | Resolving EN on VLAN tag id not allowed | Ericsson, Huawei, HiSilicon | 23.501 | 24.501 | CT1#156 Gothenburg, Sweden | CT1 | C1-255670 (Ericsson, Huawei, HiSilicon)
SA2#165 & SA2#168 | S2-2411269, S2-2504335 | Clarifications on non-3GPP device ID binding | Huawei, HiSilicon, InterDigital Inc., Deutsche Telekom, NEC, Nokia, ZTE, Oppo, Lenovo, Samsung, | 23.501 | 24.501 | CT1#156 Gothenburg, Sweden | CT1 | C1-255611 (Qualcomm Incorporated, InterDigital)
N/A | N/A | Connection information for QoS differentiation in PDU session modification procedure, coding | Huawei, HiSilicon, Ericsson, InterDigital, ZTE, Qualcomm Incorporated, Apple, Nokia | 23.501 | 24.501 | CT1#156 Gothenburg, Sweden | CT1 | C1-255610 (Huawei, HiSilicon, Ericsson, InterDigital, ZTE, Qualcomm Incorporated, Apple, Nokia)
N/A | N/A | Procedure update for QoS differentiation of non-3GPP device identifiers | Ericsson, Huawei, HiSilicon, ZTE, InterDigital Inc | 23.501 | 24.501 | CT1#156 Gothenburg, Sweden | CT1 | C1-255257 (Ericsson, Huawei, HiSilicon, ZTE, InterDigital Inc)
N/A | N/A | QoS differentiation for non-3GPP device identifiers clean up | Ericsson | - | 24.501 | CT1#156 Gothenburg, Sweden | CT1 | C1-255256 (Ericsson)
N/A | S2-2501223 | Updates to N3DCI | Qualcomm Incorporated, InterDigital, ETRI | 23.501 | 24.501 | CT1#156 Gothenburg, Sweden | CT1 | C1-255255 (Qualcomm)
N/A | N/A | Clarifying the usage of application identifiers for non-3gpp device info | Nokia, Huawei | - | 29.522 | CT3#142 Gothenburg, Sweden | CT3 | C3-253718 (Nokia, Huawei)
N/A | N/A | Correcting the Non 3gpp Device Address presence condition | Nokia, Huawei | 23.501, 23.503 | 29.512 | CT3#142 Gothenburg, Sweden | CT3 | C3-253522 (Nokia, Huawei)
N/A | S2-2504029 | Update of Nsmf_PDUSession_Update service to support Non-3GPP Device Connection Information | InterDigital Inc., LG Electronics, Samsung, Nokia | 23.502 | 29.502 | CT4#130 Gothenburg, Sweden | CT4 | C4-253388 (Nokia, InterDigital)
SA2#168 | S2-2504029 | Updating the Nsmf_PDUSession_Update service description to account for non-3GPP device connection information | InterDigital Inc., LG Electronics, Samsung, Nokia | 23.502 | 29.502 | CT4#129 Bratislava, Slovakia | CT4 | C4-252443 (Nokia, InterDigital)
N/A | N/A | Retrieving non-3gpp device information from the UDR | Nokia | 23.502 | 29.519 | CT3#141 Bratislava, Slovakia | CT3 | C3-252430 (Nokia)
N/A | N/A | Non-3gpp Device Information clarifications | Nokia | - | 29.522 | CT3#141 Bratislava, Slovakia | CT3 | C3-252383 (Nokia)
SA2#168 | S2-2504477 | Clarificaiton on supporting multiple non-3GPP device identifiers | Huawei, HiSilicon, Samsung, Deutsche Telekom, Nokia, LGE, Charter Communications, ZTE | 23.503 | 29.512 | CT3#141 Bratislava, Slovakia | CT3 | C3-252382 (Huawei, Nokia, Ericsson)
SA2#168 | S2-2504337 | LS reply on support for multiple non-3GPP device identifiers | Ericsson | 23.503 | 29.512 | CT3#141 Bratislava, Slovakia | CT3 | C3-252381 (Ericsson, Nokia, Huawei, AT&T)
SA2#168 | S2-2504253 | Inclusion of several Non-3GPP Device Identifiers | Nokia, InterDigital Inc., LG Electronics, Samsung, ZTE, Xiaomi | 23.501 | 24.501 | CT1#155 Bratislava, Slovakia | CT1 | C1-254127 (InterDigital)
SA2#168 | S2-2504253 | Inclusion of several Non-3GPP Device Identifiers | Nokia, InterDigital Inc., LG Electronics, Samsung, ZTE, Xiaomi | 23.501 | 24.501 | CT1#155 Bratislava, Slovakia | CT1 | C1-254126 (Huawei, HiSilicon, ZTE, InterDigital, Nokia)
SA2#168 | S2-2504260 | Clarification on PDU Session for non-3GPP device | LG Electronics | 23.501 | 24.501 | CT1#155 Bratislava, Slovakia | CT1 | C1-253745 (InterDigital)
SA2#168 | S2-2504334 | Clarifications on SM signalling including non-3GPP device identifiers for QoS differentiation | Apple, Charter Communications, Nokia | 23.501 | 24.501 | CT1#155 Bratislava, Slovakia | CT1 | C1-253730 (ZTE, InterDigital, Apple, Ericsson)
SA2#168 | S2-2504336 | Support of multiple Non-3GPP device identifiers for QoS differentiation | Ericsson, AT&T, Xiaomi, Nokia, CableLabs, ZTE | 23.502 | 24.501 | CT1#155 Bratislava, Slovakia | CT1 | C1-253654 (Huawei, HiSilicon, InterDigital, Apple, ZTE, Ericsson)
N/A | N/A | Handling of Non-3GPP device information in the PCF | N/A | 23.503 | 29.512 | CT3#140 Wuhan, China | CT3 | C3-251489 (Ericsson)
N/A | N/A | Support of Non-3GPP device information handling procedures | N/A | 23.503 | 29.513 | CT3#140 Wuhan, China | CT3 | C3-251490 (Ericsson)
N/A | N/A | Completion of non-3gpp device identifier information handling | N/A | 23.503 | 29.522 | CT3#140 Wuhan, China | CT3 | C3-251491 (Ericsson, Nokia)
N/A | N/A | Subscription to non-3gpp device information changes | N/A | 23.503 | 29.519 | CT3#140 Wuhan, China | CT3 | C3-251659 (Nokia, Ericsson, AT&T)
N/A | N/A | Support of QoS differentiation of traffic for N3GPP device behind UE or 5G-RG | N/A | 23.501 | 24.501 | CT1#153 Athens, Greece | CT1 | C1-251145 (Huawei, HiSilicon, Ericsson, Xiaomi, InterDigital, ZTE, Nokia)
N/A | N/A | Handling of Non-3GPP device provisioning | N/A | 23.501 | 29.512 | CT3#139 Athens, Greece | CT3 | C3-250722 (Ericsson, Huawei, Nokia, CEWiT)
SA2#166-AH | S2-2500215 / S2-2501229 | Support of the Non-3GPP Device Identifier Information notification | N/A | 23.502 23/503 | 29.519 | CT3#139 Athens, Greece | CT3 | C3-250606 (Huawei, Ericsson, Nokia)
N/A | N/A | Updates and corrections to the Non3gppDevice feature definition | N/A | 23.502 | 29.522 | CT3#139 Athens, Greece | CT3 | C3-250596 (Huawei, Nokia)
N/A | N/A | Presence condition alignment | N/A | - | 29.522 | CT3#139 Athens, Greece | CT3 | C3-250595 (Nokia, Huawei)
N/A | N/A | Non-3gpp device info trigger applicability | N/A | 23.503 | 29.512 | CT3#139 Athens, Greece | CT3 | C3-250503 (Nokia, Ericsson, Huawei)
N/A | N/A | Handling unavailable non-3gpp device identifier | N/A | 23.503 | 29.512 | CT3#139 Athens, Greece | CT3 | C3-250502 (Nokia, Huawei)
N/A | N/A | Restrictions of provisioning non-3gpp device information | N/A | 23.502 | 29.522 | CT3#139 Athens, Greece | CT3 | C3-250501 (Nokia)
N/A | N/A | Correction on the Non-3GPP device provisioning | N/A | 23.502 | 29.522 | CT3#139 Athens, Greece | CT3 | C3-250500 (Ericsson, Nokia, Huawei)
N/A | N/A | Non-3gpp device identifier information resource corrections | N/A | 23.502 | 29.519 | CT3#139 Athens, Greece | CT3 | C3-250499 (Nokia, Ericsson, Huawei)
N/A | N/A | Correction on the Non-3GPP device provisioning | N/A | 23.502 | 29.519 | CT3#139 Athens, Greece | CT3 | C3-250497 (Ericsson, Nokia, Huawei)
N/A | N/A | Non-3GPP Device Identifier | N/A | 23.501 | 23.003 | CT4#127, Athens, Greece | CT4 | C4-250637 (Huawei, InterDigital)
SA2#165 | S2-2411269 | Support of N3GPP device behind UE/5G-RGas concluded in TS 23.700-34 KI#4 | Huawei, HiSilicon, InterDigital Inc., Deutsche Telekom, NEC, Nokia, ZTE, Oppo, Lenovo | 23.501 | 24.501 | CT1#152 Orlando, USA | CT1 | PDU Session Modification C1-246746 (Xiaomi) - Postponed. C1-246747 (Ericsson) - Postponed. General Section Update C1-246744 (Xiaomi) - Postponed C1-247150 (Huawei, HiSilicon) - Postponed
SA2#165 | S2-2411079 | Definition of identifiers of N3GPP device behind UE/5G-RG | Huawei, HiSilicon, InterDigital Inc, Deutsche Telekom, Nokia | 23.501 | 23.003 | CT4#126 Orlando, USA | CT4 | C4-245216 (Huawei) - Postponed.
SA2#165 | S2-2411081 | UDR enhancement supporting Device Identifier of non-3GPP Devices connecting behind a UE/5G-RG | Xiaomi, NEC, Nokia, OPPO, InterDigital Inc. | 23.501 | 29.504 | CT4#126 Orlando, USA | CT4 | C4-245289 (Nokia) Merged into C4-245539 C4-245539 (Huawei, Nokia) Agreed.
SA2#165 | S2-2411026 | AF Provisioning of non-3GPP device identifer information to UDR | ZTE, Nokia, NEC, Deutsche Telekom, Samsung, Xiaomi, ETRI | 23.502 | 29.522 | CT3#138 Orlando, USA | CT3 | C3-246492 (Huawei, Nokia, AT&T, Ericsson) - Agreed.
SA2#165 | S2-2411081 | UDR enhancement supporting Device Identifier of non-3GPP Devices connecting behind a UE/5G-RG | Xiaomi, NEC, Nokia, OPPO, InterDigital Inc. | 23.501 | 29.519 | CT3#138 Orlando, USA | CT3 | C3-246437 (Huawei, Nokia, Ericsson) - Agreed.
SA2#165 | S2-2411083 | PCC enhancements for support of identified non-3GPP devices | CATT, InterDigital Inc., NEC, Nokia, OPPO, ZTE, Deutsche Telekom | 23.503 | 29.512 | CT3#138 Orlando, USA | CT3 | C3-246491 (Nokia) - Agreed
SA2#165 | S2-2411085 | Update of services pertaining to defining Device Identifiers | Nokia, CableLabs, ZTE, Oppo, Xiaomi, Ericsson, NEC, Deutsche Telekom, Charter Communications, Samsung | 23.502 | 29.512, 29.519, 29.522 | CT3#138 Orlando, USA | CT3 | C3-246212 (Nokia) - Merged to C3-246492 C3-246213 (Nokia) - Merged to C3-246437
SA2#165 | S2-2411260 | Ericsson, Deutsche Telekom | Ericsson, Deutsche Telekom | 23.503 | 29.512 | CT3#138 Orlando, USA | CT3 | C3-246491 (Nokia) - Agreed