3GPP TSG-S4 Meeting #132	S4-251101

Fukuoka City, Japan, May 19th - 23rd, 2025

Agenda item: 	14.7

Source: 	Qualcomm

Title: 	Time Plan for the AvCall-MED Work Item v0.2.1

Document for	Discussion and Agreement

# Introduction

The AvCall-MED work item has been agreed at the SA plenary #107 in document SP-250264.

The work item has the following objectives:

- For receiver-driven avatar animation and rendering:

  - Extend TS 26.264 for Avatar Communication by specifying format, protocols, and basic signaling of base avatars and animation streams in IMS-based AR calls,

  - In collaboration with SA2 and SA3, define an informative management interface in TS 26.264 for Base Avatar Repository (BAR) to enable management and access control to assets of base avatars.

- For sender-based avatar animation and rendering:

  - Leverage existing TS 26.264 capabilities for sender-based Avatar animation, potentially only resulting in guidelines,

  - Consider the need to introduce optional pose data exchange extensions when the receiver’s pose is used at the sender’s side for viewer-dependent rendering,

- For network-based avatar animation and rendering:

  - Extend TS 26.264 for Avatar Communication by specifying format, protocols, and basic signaling of base avatars and animation streams in IMS-based AR calls,

  - Add signaling and format negotiation to enable MF-based animation and rendering,

# Time Plan

The following time plan for the execution of the AvCall-MED work item objectives is proposed in the following table.

| Meeting | Work Item Objectives |
| --- | --- |
| SA4#131-bis-e (11 – 17 April 2025, Online) | - Agree structure of base CR. - Address sender-based and receiver-based avatar animation and rendering - Liaise with SA3 on security considerations for base avatar management. |
| Post SA4 #131-bis-e RTC AHG Calls - 30th April 2025, 15-17 CEST (Deadline 28th April) | - Address sender-based and receiver-based avatar animation and rendering - Discuss network-based avatar animation and rendering |
| SA4#132 (19 – 23 May 2025, Fukuoka City, Fukuoka, JP) | - Finalize sender-based, receiver-based, and network-based animation and rendering. - Document and profile format for the based avatar and animation streams. - Based on SA3’s response, define base avatar management. - Finalize and agree CR to TS 26.264. |
| Post #132 RTC AHG Call 25th June 2025, 15:00 –18:00 CEST (Deadline 23rd June 2025) | - Finalize call flows - Refine formats and profiles - Discuss signalling aspects - Discuss security aspects |
| SA4#133-e Meeting 21st – 25th July 2025 | - Finalize formats and profiles - Conclude signalling aspects - Progress security aspects - Finalize CR to TS26.264 |
| RTC F2F Ad-hoc 3rd-5th September 2025, Paris | - Handle any outstanding issues |
| SA#109 (16 – 19 September 2025, Beijing, CN) | - Approve CR to TS 26.264. |

# Proposal

It is proposed to agree on the time and work plan as described in Section 2.