## Slide 1: CT WG3 Status Report to TSG CT#110
Susana Fernández
Ericsson

## Slide 2: TSG CT WG3 Officials
Yue SUN
CT3 Vice Chair suny20@chinatelecom.cn
Apostolos Papageorgiou
CT3 Vice Chair
apostolos.papageorgiou@NOKIA.COM
Dongwook Kim
Secretary
MCC
Dongwook.Kim@etsi.org
Susana Fernández
CT3 Chair
susana.fernandez@ericsson.com

## Slide 3: Meeting Calendar
Since the last CT plenary
  CT3#143, (13th – 17th October, 2025) in Sophia-Antipolis, France
  CT3#144, (17th – 21st November, 2025) in Dallas , US
Upcoming Meetings
  CT3#145, (9th – 13th February, 2026) in Goa, India

## Slide 4: TSG WG CT3 Statistics
CT3#143:
Number of handled documents
  618 documents allocated
Agreed CRs
  Cat B/F : 39/125
Agreed pCRs
  59
Attendances
  112 registered/ 84 attendants
CT3#144:
Number of handled documents
  716 documents allocated
Agreed CRs
  Cat B/F : 58/149
Agreed pCRs
  70
Attendances
  237 registered/ 197 attendants

## Slide 5: New agreed Study/Work Items led by CT3
TDoc # | Title | Acronym | Source | Objectives | Release
N/A |  |  |  |  | 

## Slide 6: Revised agreed Study/Work Items led by CT3
TDoc # | Title | Acronym | Source | Objectives | Release
CP-253016 | Revised WID on CT Aspects of Phase 3 for UAS, UAV and UAM | UAS_Ph3 | LG Electronics | The objective of this work is to specify the CT aspects of phase 3 for UAS, UAV and UAM in CT WGs specifications based on stage 2 normative work. The WID is revised to complete the CT3 objectives and to update the list of TSs under CT3 responsibility. | Rel-19

## Slide 7: Rel-19 Work Plan – CT3 led (1/2)
UID | Name | Acronym | Release | Group | End | Status old | Status new | WID | Notes
1040009 | Rel-19 Enhancements of 3GPP Northbound and Application Layer interfaces and APIs | NBI19 | Rel-19 | C3 | 09/25 | 100% | 100% | CP-243079 | 
1040006 | CT aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA | TEI19_VLANSUB | Rel-19 | C3 | 06/25 | 100% | 100% | CP-250078 | 
1040007 | CT aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy | TEI19_IP_SP_EXP | Rel-19 | C3 | 06/25 | 100% | 100% | CP-243076 | 
1040008 | CT aspects for Enabling Edge Applications Phase 3 | EDGEAPP_Ph3 | Rel-19 | C3 | 09/25 | 100% | 100% | CP-241074 | 
1050014 | CT aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | Rel-19 | C3 | 09/25 | 85% | 100% | CP-251283 | 
1050012 | 5GS enhancement on QoS monitoring enhancement | TEI19_QME | Rel-19 | C3 | 06/25 | 100% | 100% | CP-243080 | 
1050015 | CT aspects of enhanced application layer support for location services | eLSAPP | Rel-19 | C3 | 09/25 | 100% | 100% | CP-242064 | 
1050011 | CT aspects on Spending Limits for UE Policies in Roaming scenario | TEI19_SLUPiR | Rel-19 | C3 | 09/25 | 100% | 100% | CP-242060 | 
1050010 | Rel-19 Enhancements of Network Automation Enablers | eNetAE19 | Rel-19 | C3 | 12/25 | 100% | 100% | CP-243078 | 
1050013 | CT Aspects of Phase 3 for UAS, UAV and UAM | UAS_Ph3 | Rel-19 | C3 | 09/25 | 100% | 100% | CP-253016 | 
1060027 | CT aspects of Extended Reality and Media service (XRM) Phase 2 | XRM_Ph2 | Rel-19 | C3 | 09/25 | 96% | 100% | CP-252058 | 
Legend Green row – Newly completed
Yellow row – small outstanding issues Red row – Exception sheet
black text - no change since the last plenary
blue text - Updated text since last plenary

## Slide 8: Rel-19 Work Plan – CT3 led (2/2)
UID | Name | Acronym | Release | Group | End | Status old | Status new | WID | Notes
1060023 | CT aspects for application enablement for satellite access Phase 3 | 5GSAT_Ph3_App | Rel-19 | C3 | 09/25 | 97% | 100% | CP-243071 | 
1060025 | Rel-19 Enhancements of UE Policy | UEP19 | Rel-19 | C3 | 09/25 | 100% | 100% | CP-243073 | 
1060024 | CT aspects of Application enablement for XRM Services Phase 2 | XRM_Ph2_App | Rel-19 | C3 | 09/25 | 99% | 100% | CP-243072 | 
1060026 | Common API Framework (CAPIF) Phase 3 | CAPIF_Ph3 | Rel-19 | C3 | 09/25 | 96% | 100% | CP-252059 | 
1050025 | CT aspects for application enablement for mobile metaverse services | Metaverse_App | Rel-19 | C3 | 09/25 | 80% | 100% | CP-251132 | 
1070002 | CT aspects of energy efficiency and energy saving | EnergySys | Rel-19 | C3 | 09/25 | 90% | 100% | CP-250247 | 
1070005 | Rel-19 Enhancements of SM Policy | SMPC19 | Rel-19 | C3 | 09/25 | 100% | 100% | CP-252060 | 
1070006 | CT Aspects for IP Domain usage | IPD | Rel-19 | C3 | 09/25 | 100% | 100% | CP-250248 | 
1070007 | UEId Service API support for MSISDN Verification operation | TEI19_MVOSNS | Rel-19 | C3 | 06/25 | 100% | 100% | CP-250077 | 
1070003 | CT aspects of Network Controlled Network Slice Selection | TEI19_SliceSel | Rel-19 | C3 | 06/25 | 100% | 100% | CP-251133 | 
1070004 | CT Aspects of Rel-19 Application Data Analytics Enablement Service | TEI19_ADAES | Rel-19 | C3 | 09/25 | 96% | 100% | CP-250074 | 
Legend Green row – Newly completed
Yellow row – small outstanding issues Red row – Exception sheet
black text - no change since the last plenary
blue text - Updated text since last plenary

## Slide 9: Rel-19 Work Plan – Non-CT3 led (1/2)
Legend Green row – Newly completed
Yellow row – small outstanding issues Red row – Exception sheet
black text - no change since the last plenary
blue text - Updated text since last plenary
UID | Name | Acronym | Release | Group | End | Status old | Status new | WID | Notes
1040001 | Service Based Interface Protocol Improvements Release 19 | SBIProtoc19 | Rel-19 | C4 | 09/25 | 100% | 100% | CP-241021 | 
1040041 | Protocol enhancements for Mission Critical Services | MCProtoc19 | Rel-19 | C1 | 09/25 | 100% | 100% | CP-241283 | 
1040039 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc19 | Rel-19 | C1 | 09/25 | 100% | 100% | CP-251219 | 
1040004 | CT Aspects on Minimize the Number of Policy Associations (TEI19_MINPA) | TEI19_MINPA | Rel-19 | C4 | 03/25 | 100% | 100% | CP-241024 | 
1040070 | CT Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3 | UASAPP_Ph3 | Rel-19 | C1 | 09/25 | 100% | 100% | CP-241150 | 
1050007 | MPS for Messaging and SMS services | MPS4msg | Rel-19 | C4 | 09/25 | 96% | 96% | CP-243047 | 
1050009 | Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | Rel-19 | C4 | 09/25 | 100% | 100% | CP242029 | 
1050024 | CT aspects of application enablement for AI/ML services | AIML_App | Rel-19 | C1 | 09/25 | 80% | 100% | CP-253123 | 
1050001 | CT aspects of UPF enhancement for Exposure And SBA Phase 2 | UPEAS_Ph2 | Rel-19 | C4 | 09/25 | 100% | 100% | CP-250018 | 
1050022 | Next Generation Real time Communication services Phase 2 | NG_RTC_Ph2 | Rel-19 | C1 | 09/25 | 97% | 100% | CP-243124 | 
1050006 | CT aspects of enhancement of support for Edge Computing in 5G Core network - Phase 3 | eEDGE_5GC_Ph3 | Rel-19 | C4 | 09/25 | 98% | 100% | CP-250016 | 
1050020 | CT aspects of Multi-Access (ATSSS_Ph4) | MASSS | Rel-19 | C1 | 09/25 | 100% | 100% | CP-251226 | 

## Slide 10: Rel-19 Work Plan – Non-CT3 led (2/2)
Legend Green row – Newly completed
Yellow row – small outstanding issues Red row – Exception sheet
black text - no change since the last plenary
blue text - Updated text since last plenary
UID | Name | Acronym | Release | Group | End | Status old | Status new | WID | Notes
1050019 | CT aspects of integration of satellite components in the 5G architecture Phase 3 | 5GSAT_Ph3_ARCH | Rel-19 | C1 | 09/25 | 100% | 100% | CP-250134 | 
1050023 | CT aspects of Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | Rel-19 | C1 | 09/25 | 100% | 100% | CP-243266 | 
1050017 | CT aspects of SEAL data delivery enabler for vertical applications Phase 2 | SEALDD_Ph2 | Rel-19 | C1 | 09/25 | 100% | 100% | CP-243261 | 
1050002 | CT aspects of Architecture support of roaming value-added services | TEI19_RVAS | Rel-19 | C4 | 06/25 | 100% | 100% | CP-242022 | 
106002 | CT aspects of 5G NR Femto | 5G_Femto | Rel-19 | C4 | 09/25 | 100% | 100% | CP-250020 | 
1060019 | CT aspects for enabling MSGin5G Service phase 3 | 5GMARCH_Ph3 | Rel-19 | C1 | 06/25 | 100% | 100% | CP-251225 | 
1050021 | CT aspects of ProSe support in NPN | TEI19_ProSe_NPN | Rel-19 | C1 | 09/25 | 100% | 100% | CP-251224 | 
1070008 | CT aspects for application enablement aspects for MMTel | MMTel_App | Rel-19 | C1 | 09/25 | 75% | 100% | CP-250249 | 
1050004 | CT Aspects of Indirect Network Sharing | TEI19_NetShare | Rel-19 | C4 | 09/25 | 100% | 100% | CP-250019 | 
1080001 | IMS Disaster Prevention and Restoration Enhancement | IMS_RES-CT | Rel-19 | C4 | 09/25 | 70% | 100% | CP-251016 | 
1080021 | CT aspects of Architecture support of Ambient power-enabled Internet of Things | AmbientIoT-CT | Rel-19 | C1 | 09/25 | 98% | 100% | CP-252196 | 
 | Protocol for AI Data Collection from UPF | PAIDC_UPF-UPF | Rel-19 | C4 | 09/25 | 100% | 100% | CP-252243 | 

## Slide 11: TS/TR sent to CT Plenary
TDoc # | Title | Acronym | Source | Objectives | Release
CP-253020 | Presentation of 3GPP TS 29.530 V1.2.0 to TSG for approval | AIML_CN | Huawei | The TS is sent for Approval | Rel-19
CP-253019 | Presentation of 3GPP TS 29.482 v1.3.0 to TSG for approval | AIML_App | Ericsson | This TS is sent for Approval | Rel-19
CP-253018 | Presentation of 3GPP TS 29.437 v1.3.0 to TSG for approval | Metaverse_App | Samsung | This TS is sent for Approval | Rel-19
CP-253021 | Presentation of 3GPP TS 29.566 v1.3.0 to TSG for approval | EnergySys | Samsung | The TS is sent for Approval | Rel-19
CP-253017 | Presentation of 3GPP TS 29.392 v1.0.0 to TSG for approval | MMTel_App | China Mobile | The TS is sent for Approval | Rel-19

## Slide 12: Exception sheet for work item
TDoc # | Title | Acronym | Source | Objectives | Release
N/A |  |  |  |  | 

## Slide 13: Release 20 Status (1/2)
Discussion Papers and/or SIDs for 6G have been submitted to CT3#143 & CT3#144 with proposals to initiate the study work in CT3. Main areas:
  AI/AI Agents protocols in 6G
  Network Capability Exposure in 6G
  Unified Event Exposure in the Core Network
  Interworking between 6G Network and Data Networks
A conference was organized on October-29 to find a way to progress to:
  Identify a candidate list of areas that require study in CT3.
  Get a rough estimation of the support of the companies for the identified areas.
  Get initial information of the interest of the companies in the rapporteurship of those areas.
  Get initial information of when the work can be started.

## Slide 14: Release 20 Status (2/2)
All SIDs/proposals have been postponed for future meetings
  Unified Event Exposure study, CT3 agreed that no work will be initiated in CT3 until some conclusion is reached in CT4.
  Different interpretations on stage 2 dependency and when the work can be started in CT3.
  Different interpretations on the need of cross-WG SIDs.
  Divergences in the scope/work tasks that need to be studied for the proposed SIDs.
Companies have been encouraged to initiate offline discussions to find convergent points and start progress.

## Slide 15: Release 19 Status
Release 19 is now declared completely frozen (including OpenAPI specifications).
Agreement or endorsement of new/revised Rel-19 WIDs:
  1 revised WID (i.e. UAS_Ph3 ) is agreed.
  3 revised WIDs (i.e. IMS_RES-CT, NG_RTC_Ph2, AIML_App) are endorsed.
5 new TS (not under change control) in CT3 are sent for Approval.
Several LSs from CT3#143 & CT3#144 meetings sent to SA2/SA6 for stage 2 clarifications.
Considering the freeze of the release in this Plenary cycle and a majority of companies supporting C3-255506, a Working Agreement is declared for agreeing on that CR.
Other controversial topics have been fortunately concluded:
  LMF-based AI/ML positioning indication for NWDAF under AIML_CN WI has been concluded without the need of the planned technical voting, after an extraordinary effort of finding an alternative solution.
  Solution for the handling of nonce counter and IANA registration for MRI packet transforms under XRM_Ph2 have been agreed.

## Slide 16: Pre-Release 19 Status
Number of pre-Release 19 contributions is being reduced significantly:
2 Cat-F CRs (TEI16, 5GC_Ph1-C; Vertical_LAN) agreed for Release 16.
2 Cat-F CRs (eNA_Ph2; en5GPccSer17) agreed for Release 17.
3 Cat-F CRs (eNA_Ph3; TEI18, en5GPccSer; XRM) agreed for Release 18.

## Slide 17: Backward Incompatible Changes
None

## Slide 18: For Information to CT
CT3 work focused on:
  Completion of work for Release 19, aligning with stage 2 and correcting identified issues.
  Agreement and endorsement of revised Release 19 Work Items.
  Initiating the discussions on the areas that can be studied in 6G for Release 20.
  Bringing corrections for previous releases.
Working Agreement declared for C3-255506.
Other controversial issues have been concluded in this Plenary cycle based on consensus.
Some corrections will still be needed for Release 19 based on the SA2/SA6 LS Replies.

## Slide 19
For Action to CT
Approval of the submitted CT3 ToR, as discussed in the CT Reflector.
Decision on how to proceed with MPS4msg WI, reported as 96% concluded in CT3.
Require stage 2 WGs to provide LS Replies to the open topics that require to be concluded in CT3.

## Slide 20: Acknowledgement
The CT3 Chair wants to thank
  Vice Chairs Apostolos and Yue for their support in the handling of CT3 meetings.
  MCC Dongwook for his excellent work to support CT3 before, during and after the CT3 meetings.
  ETSI & ATIS support for IT facilities.
  All CT3 delegates, and specially TS rapporteurs, for their hard work, professionalism and commitment for the success of the challenging meetings.
  CT WG Chairs, CT Chair and MCCs for helping with the good practices in the handling of meetings and coordination activities.

## Slide 21: Annex

## Slide 22: CRs for conditional approval (1/2)
TDoc # | Title | Spec | CR# | Dependency
C3-255073 | Update UE-Satellite-UE communication procedure | 29.214 | 1706 | TS 23.228 CR1680
C3-255318 | Enhancements on the QoS and policy assistance analytics | 29.520 | 1100 | TS 23.288 CR1491
C3-255372 | Update UE-Satellite-UE communication procedure | 29.514 | 0808 | TS 23.228 CR1680
C3-255398 | RAN-Controlled UL Bitrate Recommendation Indication | 29.514 | 0809 | TS 23.501 CR6194, TS 23.503 CR1531
C3-255401 | Corrections on the removable attribute | 29.514 | 0822 | TS 23.503 CR1531
C3-255403 | Multimodal handling update | 29.548 | 0066 | TS 23.433 CR0167
C3-255415 | MoQT Update | 29.561 | 0208 | TS 23.501 CR6408
C3-255417 | Support of RAN-controlled UL bitrate recommendation indication | 29.522 | 1754 | TS 23.503 CR1531
C3-255469 | Corrections on Historical data and analytics via notification procedure | 29.552 | 0177 | TS 23.288 CR1512
C3-255484 | Introduce DC-Info to indicate a DC operation request is initiated by the DC AS | 29.165 | 1045 | TS 24.186 CR0108
C3-255509 | Corrections on QoS and policy assistance analytics | 29.520 | 1136 | TS 23.288 CR1491
C3-255522 | Leave request on VFL services | 29.520 | 1126 | TS 23.288 CR1521, TS 23.288 CR1508
C3-255558 | Support of RAN-controlled UL bitrate recommendation indication | 29.512 | 1444 | TS 23.503 CR1531

## Slide 23: CRs for conditional approval (2/2)
TDoc # | Title | Spec | CR# | Dependency
C3-255581 | Clarify the behavior of the PCRF in the case of PGW failure | 29.214 | 1704 | TS 23.380 CR0133
C3-255582 | Clarify the behavior of the PCF in the case of SMF failure | 29.514 | 0806 | TS 23.380 CR0133
C3-255585 | IMS Event Exposure Notification corrections | 29.522 | 1737 | TS 23.228 CR2509, TS 23.208 CR2509
C3-255586 | Support of ADRF ID and storage handling information in Analytics subscription | 29.520 | 1134 | TS 23.288 CR1512
C3-255591 | RAN-Controlled UL Bitrate Recommendation Indication | 29.122 | 0983 | TS 23.501 CR6194, TS 23.503 CR1531
C3-255644 | No completion on requested time on VFL Training and Inference | 29.520 | 1125 | TS 23.288 CR1536, TS 23.288 CR1521
C3-255648 | Completion and corrections to Nnef_Inference | 29.591 | 0256 | TS 23.288 CR1426
C3-255649 | Completion and corrections to Nnef_VFLInference | 29.591 | 0257 | TS 23.288 CR1521
C3-255655 | Completion and corrections to VFLInference and VFLTraining APIs | 29.522 | 1748 | TS 23.288 CR1521

## Slide 24: Thank You!
Susana Fernández
Susana.fernandez@ericsson.com