## Tdoc cover sheet
3GPP TSG-CT WG3 Meeting #143 Sophia, France, 13 - 17 October, 2025 |  | C3-254185
Source: | Samsung Electronics
Title: | Work plan for CT3 aspects of Metaverse_APP
Agenda item: | 19.42
Document for: | Information

## Contributions plan
Contribution Plan |  | In Progress | To be started | Completed
Spec | Topic | SA6 agreed (p)CR(s) | Responsible Company | Service operation Impacts? | API definition Impacts? | Open API Impacts? | Related LS or other WG tdoc(s) # | CT3 meeting #; tdoc(s) # | Comments | Open issues
Approved WID - CP-251132 (80% complete)
29.437 (New TS) | Spatial map and spatial anchors APIs specification; Stage 3; (Rel-19) |  | Contributions based on TS 23.437 |  |  |  |  | C3-250652 - Skeleton, C3-250623 (v0.1.0), C3-251620 (v0.2.0), C3-252388 (v0.3.0), C3-252551 (v1.0.0 - Sent for Info), C3-253652 (V1..1.0)
| Introduction | [6 empty] | C3-250511 | Removed this clause. Not needed for this TS.
| Clause 1: Scope |  | Samsung | N | N | N |  | C3-250511 | Nothing pending as of now.
| Clause 2: References |  |  | N | N | N |  | C3-250511, C3-250512, C3-250649
| Clause 3: Definition of Terms, Symbols and Abbreviations |  | Samsung | N | N | N |  | C3-250511
| Clause 4: Overview |  | Samsung | N | N | N |  | C3-250512 | Nothing pending as of now.
| Clause 5.1: Introduction to services and API descriptions |  |  | N | N | N |  |  | Need to update will all the APIs agreed.
Spatial Anchors (SAn) services
| SS_SAnManagement |  | Samsung, Nokia | Y | Y | Y
| Service Description (Clause 5) | [6 empty] | C3-250650, C3-251515, C3-253420
| API definition (Clause 6) | [6 empty] | C3-250649, C30251507, C3-251513, C3-251514, C3-252408, C3-252409, C3-253420
| Open API (Annex A) | [6 empty] | C3-251507, C3-252408, C3-252409, C3-252410, C3-253420 | Needs to align with API definition with other data model updates.
| SS_SAnDiscovery |  | Samsung | Y | Y | Y
| Service Description (Clause 5) | [6 empty] | C3-251511
| API definition (Clause 6) | [6 empty] | C3-251510 | Editor’s note: The definition of anch-inf query parameter is FFS.
| Open API (Annex A) | [6 empty] | C3-252411, C3-253420 | Need to align Open API with data model updates.
| SS_SAnUsage (SS_SAnUsageReport API and SS_SAnUsageInfo APIs in stage-2 are merged into single API) |  | Samsung | Y | Y | Y
| Service Description (Clause 5) | [6 empty] | C3-253597
| API definition (Clause 6) | [6 empty] | C3-252412
Open API (Annex A)
Spatial Map (SM) services
| SS_SmManagement |  | Samsung | Y | Y | Y
| Service Description (Clause 5) | [6 empty] | C3-253598
| API definition (Clause 6) | [6 empty] | C3-252413, C3-253598 | Definition of "Pose" is FFS.
Open API (Annex A)
| SS_SmDiscovery |  | Samsung | Y | Y | Y
| Service Description (Clause 5) | [6 empty] | C3-253534
| API definition (Clause 6) | [6 empty] | C3-253594 | Definition of "Pose" is FFS.
Open API (Annex A)
| SS_SmLocalization |  | Samsung | Y | Y | Y
| Service Description (Clause 5) | [6 empty] | C3-253696 | Service procedure description is FFS, to be aligned based on data model (custom operation or GET method).
| API definition (Clause 6) | [6 empty] | C3-253596 | Data model FFS: Custom operation or GET method
Open API (Annex A)
| SS_SmDataSourceDiscovery |  | Samsung | Y | Y | Y |  |  | ONLY Request operation as per 23.437. Notify is under CT1 remitt.
| Service Description (Clause 5) | [6 empty] | C3-253413
| API definition (Clause 6) | [6 empty] | C3-253595 | Align area of interest in query parameter, based on S6-253081
Open API (Annex A)
| SS_SmSmasRegistration |  | Huawei,Samsung | Y | Y | Y
| Service Description (Clause 5) | [6 empty] | C3-253694
| API definition (Clause 6) | [6 empty] | C3-253533
| Open API (Annex A) | [6 empty] | C3-253695 | SpatialMapInfo, make the map Id ref to SmManagement yaml file.
Clause 7: Using Common API Framework
29.549 | Digital Asset APIs specification; Stage 3; (Rel-19) |  | Contributions based on TS 23.438 | [5 empty] | % Completion: 0
| SS_DAProfileManagement (Digital asset profile management) |  | Nokia | Y | Y | Y
| Service Description | [6 empty] | C3-253586
| API definition | [6 empty] | C3-253587
| Open API | [6 empty] | C3-253588
| SS_DADiscovery (Digital asset discovery) |  | Nokia | Y | Y | Y |  |  | DA Client and VAL server consumers
| Service Description | [6 empty] | C3-253589
| API definition | [6 empty] | C3-253590
| Open API | [6 empty] | C3-253591
| Digital asset media management |  | Nokia | Y | Y | Y
| Service Description | [6 empty] | C3-253592
| API definition | [6 empty] | C3-253599
| Open API | [6 empty] | C3-253593
29.549 | Impacts to SEAL serivces
| SEAL updates for metaverse services | S6-244664 | Samsung, Nokia |  |  |  |  | C3-245408, C3-250120, C3-250510, C3-253585
29.558 | Impacts to EDGEAPP serivces
| Support for metaverse services requiring multiple devices | S6-250419 | Samsung | N | Y | Y |  | C3-251509 | Updates to EAS profile and AC profile (in CT1 spec)
| Target Completion - TSG CT#110 December 2025) | [7 empty] | Exception Sheet : C3-253712, completion for Dec 2025 plenary

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments