## list of issues
TS 38.410 higher level open issues. Note: lower level open issues should be captured as editor's notes and FFSes in TS 38.410.
Issue # | Section(s) | Description of issue | Status | Comments
001 | General | Impact of NG-RAN architecture node definition on the figure 4.1 | Open | Update planned from rapporteur next meeting.
002 | General | Impact of access agnostic support | Open
003 | 5 | Finalizing list of functions e.g. Overload, Load Balancing | Open | List of functions with one sentence description per function.
004 | 6 | list of procedures to be completed. | Open | Update planned from rapporteur.
005 | 6 | Impact of the node definition on the name of the procedures | Open | Update planned from rapporteur to align with TS 38.413.
006 | 8 | Need to add TS 38.415 | Open | to be contributed at RAN3#97bis.