## Cover sheet
3GPP TSG-RAN5 Meeting #101 | [10 empty] | R5-236408
Chicago, USA, Nov 13th - Nov 17th, 2023
Agenda Item: | 7.5.2
Source: | Huawei, Hisilicon
Title: | WP of UE Conformance - Signal level Enhanced Network Selection
Work item code: | SENSE-UEContest
Release: | Rel-17
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WID on R18 Signal level Enhanced Network Selection. This work item will cover Protocol conformance test specifications.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% | 0 | 6
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE |  | 5% | 0 | 6
FDD |  | 5% | 0 | 6
TDD |  | 5% | 0 | 6
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD |  |  | TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1 | 0% | 0 | 6 | 0% | 0 | 6 | 0% | 0 | 6
Applicability Protocol test cases | 36.523-2 | 0% |  |  | 0% |  |  | 0%
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF. Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-232362 | New WID on UE Conformance - Signal level Enhanced Network Selection
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - Signal level Enhanced Network Selection | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | SENSE-UEContest
WP Scope: |  | The objective of this work item is to define the UE conformance requirements corresponding to WID on R18 Signal level Enhanced Network Selection. This work item will cover Protocol conformance test specifications. | [12 empty] | vs Area
WP Resp: |  | Ya Zhao |  |  | zhaoya@hisilicon.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD | TDD
[14 empty] | 5% | 5%
[14 empty] | 8 | 8
[14 empty] | 6.2 | 6.2
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.508 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 36.508 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
Idle Mode
TBD |  | 36.523-1 | 6.1.1 | PLMN selection | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 36.523-1 | 6.1.1.12 | eMTC / SENSE/ PLMN selection of RPLMN, HPLMN, UPLMN, OPLMN and Other PLMN / Automatic mode | TP1:[TS 23.122: 4.4.3.1] WITH: UE in Automatic network selection mode and RPLMN, HPLMN, UPLMN ,OPLMN cells available and signal level enhanced network selection is applicable. WHEN: UE is switched on. THEN: UE selects a cell of a PLMN, if received signal quality of this PLMN is equal to or greater than the ""Operator controlled signal threshold per access technology"" stored in the USIM. TP2:[TS 23.122: 4.4.3.3.1] WITH: UE camped on a VPLMN cell and cells of a higher priority PLMN available, received signal quality of the highest priority PLMN is lower than the "Operator controlled signal threshold per access technology" stored in the USIM and received signal quality of the second highest priority PLMN is equal to or greater than the "Operator controlled signal threshold per access technology"" stored in the USIM. WHEN: higher priority PLMN search timer T expires. THEN: UE selects and camps on a cell of the second highest priority PLMN. TP3:[TS 23.122: 4.4.3.1.1;4.4.3.1] WITH: UE in Automatic network selection mode and HPLMN, UPLMN, OPLMN and Other PLMN cells available but the received signal quality from none of the candidate PLMN(s) or PLMN/access technology combination(s) is equal to or greater than the "Operator controlled signal threshold per access technology" stored in the USIM . WHEN: UE returns to coverage. THEN: UE stops applying signal level enhanced network selection and selects a cell of the highest priority PLMN. |  | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 36.523-1 | 6.1.1.13 | eMTC / SENSE/ PLMN selection of RPLMN or (E)HPLMN; Automatic mode | TP1:[TS 23.122: 4.4.3.1] WITH: UE in Automatic network selection mode and signal level enhanced network selection is applicable and UE is fitted with a USIM containing the EHPLMN list and the USIM indicates RPLMN or (E)HPLMN should be selected and received signal quality of RPLMN is equal to or greater than the "Operator controlled signal threshold per access technology" and received signal quality of EHPLMN is lower than the "Operator controlled signal threshold per access technology". WHEN: UE is switched on. THEN: UE selects a cell of the RPLMN. TP2:[TS 23.122: 4.4.3.1] WITH: UE in Automatic network selection mode and signal level enhanced network selection is applicable and UE is fitted with a USIM containing the EHPLMN list and the USIM indicates RPLMN or (E)HPLMN should be selected and received signal quality of RPLMN and EHPLMN are equal to or greater than than the "Operator controlled signal threshold per access technology". WHEN: UE is switched on. THEN: UE selects a cell of the RPLMN or EHPLMN. TP3:[TS 23.122: 4.4.3.1] WITH: UE in Automatic network selection mode and signal level enhanced network selection is applicable and UE is fitted with a USIM not containing or containing empty EHPLMN list and the USIM indicates RPLMN or (E)HPLMN should be selected and received signal quality of RPLMN and VPLMN are equal to or greater than than the "Operator controlled signal threshold per access technology" and received signal quality of HPLMN is lower than the "Operator controlled signal threshold per access technology". WHEN: UE is switched on. THEN: UE selects a cell of the RPLMN. TP4:[TS 23.122: 4.4.3.1] WITH: UE in Automatic network selection mode and signal level enhanced network selection is applicable and UE is fitted with a USIM not containing or containing empty EHPLMN list and the USIM indicates RPLMN or (E)HPLMN should be selected and received signal quality of RPLMN, HPLMN and VPLMN are equal to or greater than the "Operator controlled signal threshold per access technology". WHEN: UE is switched on. THEN: UE selects a cell of the RPLMN or HPLMN. |  | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 36.523-1 | 6.1.1.14 | eMTC / SENSE/ Periodic attempts for signal level enhanced network selection; Automatic mode | TP1:[TS 23.122: 4.4.3.1] WITH: UE in Automatic network selection mode and RPLMN, HPLMN, UPLMN and OPLMN cells available and signal level enhanced network selection is applicable and the received signal quality of RPLMN is lower than the "Operator controlled signal threshold per access technology"" stored in the USIM and the received signal quality of HPLMN and OPLMN are equal to or greater than the ""Operator controlled signal threshold per access technology" stored in the USIM WHEN: UE is switched on. THEN: UE selects a cell of HPLMN. TP2:[TS 23.122: 4.4.3.5] WITH: UE in Automatic network selection mode and UE in RRC_IDLE and UE camped on a HPLMN cell. WHEN: The received signal quality of the HPLMN is lower than the "Operator controlled signal threshold per access technology" over an averaging window. THEN: UE shall periodically attempt to obtain service on an allowable PLMN/access technology combination for which the received signal quality of the candidate PLMN/access technology combination is equal to or greater than the "Operator controlled signal threshold per access technology" TP3:[TS 23.122: 4.4.3.5] WITH: UE in Automatic network selection mode and UE camps on a cell of RPLMN.. WHEN: The received signal quality of the registered PLMN and all other available and allowable PLMN/access technology combinations are lower than the "Operator controlled signal threshold per access technology" THEN: UE stops applying signal level enhanced network selection and selects a cell of the highest priority PLMN after higher priority PLMN search timer T expires." |  | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD |  | 36.523-1 | 22.2 | Idle mode operations | New sub-clause header
TBD | Y | 36.523-1 | 22.2.14 | NB-IoT / SENSE/ PLMN selection of RPLMN, HPLMN, UPLMN, OPLMN and Other PLMN / Automatic mode | same as 6.1.1.12 |  | RAN5#103 (May-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 36.523-1 | 22.2.15 | NB-IoT / SENSE/ PLMN selection of RPLMN or (E)HPLMN; Automatic mode | same as 6.1.1.13 |  | RAN5#103 (May-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 36.523-1 | 22.2.16 | NB-IoT / SENSE/ Periodic attempts for signal level enhanced network selection; Automatic mode | same as 6.1.1.14 |  | RAN5#103 (May-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 36.523-2: Applicability for Protocol test cases
TBD |  | 36.523-2 | 4.1 | Applicability for MBS test cases | Add test case applicability statements for the new test cases introduced in 36.523-1 |  | RAN5#103 (May-24) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
TBD |  | 36.523-2 | 4.2 | ICS for MBS test cases | Add test case applicability expressions for the new test cases introduced in 36.523-1 |  | RAN5#103 (May-24) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.