## Slide 1
Status Report RAN WG2 to TSG-RAN #76
3GPP TSG RAN#76 West Palm Beach, USA, 5th - 6th June 2017
RAN2 Chair: Richard Burbidge
RAN2 Vice Chair: Diana Pani
RAN2 Vice Chair: Hu Nan
RAN2 Secretary: Juha Korhonen

## Slide 2: UMTS items
UMTS DL interference mitigation WI
  Rel-15 WI is completed
  RAN2 agreed 25.300 and 25.331 CRs from Rel-14 as par of the Rel-15 WI
  RAN is requested to conclude whether the Rel-14 CRs can be agreed
ASN.1 review
  ASN.1 review completed and ASN.1 ready to be frozen

## Slide 3: LTE items (1)
New UE category combination to enable UE category 4 with UL 64 QAM
  Purpose to enable UL 64 QAM to be supported by a lower DL category than currently possible
  RAN2 technically endorsed 36.331 and 36.306 CRs from Rel-12 (provided to RAN in CR pack RP-171248)
  RAN asked to make decision on the need and the starting release of the CRs.
New UL category for 300Mbps with UL 64 QAM
  Proposed and postponed at RAN#75 to enable RAN2 review of CRs
  RAN2 technically endorsed 36.331 and 36.306 CRs from Rel-14 (provided to RAN in CR pack RP-171247)
  RAN asked to make final decision

## Slide 4: LTE items (2)
E-UTRAN sharing enhancement
  Enables PLMNs sharing a RAN to configure independent values of TAC and Cell-ID in broadcast system information
  RAN2 technically endorsed 36.300 and 36.331 CRs under TEI14 (provided to RAN in CR pack RP-171246)
  RAN2 also sent LS to SA2, RAN3 and RAN requesting that SA2/RAN3 provide feedback on the CRs
  RAN is requested to make final decision on the CRs considering any feedback received from SA2 or RAN3.

## Slide 5: LTE items (3)
Rel-14 NB-IoT
  Completed connected mode mobility enhancement for Control Plane CIoT optimization so WI now complete from RAN2 point of view
UDC SI
  UDC study item is complete in RAN2
  DEFLATE and APDC are identified as suitable candidates for a UL data compression, and RAN2 recommends one solution to be selected.
  TR 36.754 v 1.0.0 is provided to RAN for approval (in RP-171139)
feD2D SI
  feD2D study item is complete from RAN2 perspective
  Study concluded that bi-directional Layer 2 UE-NW relay is feasible from a RAN2 perspective
  TR 36.746 v 1.0.0 is provided to RAN for information (in RP-171312)
ASN.1 review
  ASN.1 review completed and ASN.1 ready to be frozen

## Slide 6: LTE - comments on time planning
At RAN2#97bis and RAN2#98 a combined total of 24 TUs were planned for corrections including the ASN.1 review
Rel-13 and Rel-14 NB-IoT/MTC corrections consumed significant part of this time - approx 17-18 TUs consumed over the 2 meetings
  Care needed to avoid a repeat situation with the Rel-15 NB-IoT and MTC work items.
V2X corrections and TEI14 also consumed significant time
Rel-15 FeD2D and sTTI both used more time than allocated - sTTI may need more than the 0.5 TU allocated in next quarter in order to complete the WI.

## Slide 7: LTE Capacity for Rel-15
Legacy, TEI15, Rel-15 open WIs, Spare capacity 1 figures are all taken from the RAN#75 approved time budget (RP-170882)
Reserved TUs corresponds to the time planned for the UDC WI, Aerials WI and FeD2D WI in the RAN#75 endorsed RP-170834
It remains critical to keep to LTE time budget during Rel-15. There is very limited flexibility during RAN2 meeting week
No time to add any new SI/WI

## Slide 8: NR items
Good progress at RAN2#97bis. At RAN2#98 good progress on user plane stage 3, but slower progress on some stage 2 and control plane topics.
  Companies/delegates are reminded to focus on meeting our deadlines, avoid adding more optimisations, be prepared to compromise to make progress...
NR UE categories for LTE-NR Dual Connectivity and NR Standalone
  RAN2 sent LS to RAN (RP-170901) raising questions on the need to define UE categories for LTE-NR Dual Connectivity and NR Standalone, the target peak rates for the categories and other associated capability parameters.
  Guidance is required to enable RAN2 to define capability coordination between LTE and NR.
  Feedback requested before October 2017
RAN2 NR ad hocs for Jan and July 2018
  These are currently TBC in the 3GPP calendar
  Chairman proposal is to confirm these 5 day NR ad hocs are required
  Coming just after the target completion of LTE-NR Dual Connectivity in Dec and the NR WI in June, a significant part of these ad hocs can be expected to be corrections and ASN.1 review.

## Slide 9: Rel-15 WI/SI status (RAN2 led)
SI/WI Name | Status | Target | Status report | WID
SI: feD2D_IoT_relay_wearable (Huawei) | 35%=> 80% | Sep. 17 | RP-171071 | RP-170295
SI: Study on uplink data compression in LTE (CATT) | 0%=> 100% | June 17 | RP-171107 | RP-170403
SI: Study on enhanced LTE Support for Aerial Vehicles (NTT DOCOMO) | 0%=> 15% | Dec.17 | RP-171053 | RP-170779
SI: Study on integrated access and backhaul for NR (QUALCOMM) | 0%=> 0% | June 18 | RP-171318 | RP-170831
WI: Signalling reduction to enable light connection for LTE (Huawei) | 79%=> 79% | Dec.17 | RP-171070 | RP-170788
WI: UE Positioning Accuracy Enhancements for LTE (Nokia) | 0%=> 10% | Dec.17 | RP-171008 | RP-170813
WI: DL interference mitigation for UMTS (Qualcomm) | 0%=> 100% | June 17 | RP-171134 | RP-170703
WI: : Further video enhancements for LTE (CMCC) | 0%=> 20% | Dec.17 | RP-170999 | RP-170781
WI: Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN (China Unicom) | 0%=> 25% | Dec.17 | RP-170954 | RP-170786
WI: Enhancing LTE CA Utilization (Nokia) | 0%=> 0% | Dec.17 | RP-171187 | RP-170805
WI: LTE connectivity to 5G-CN (Huawei) | 0%=> 5% | June 18 | RP-171072 | RP-170840

## Slide 10: Summary and concluding remarks
Very busy Q2 2017 and not expected to change for remainder of Rel-15.
No time to add new LTE SI/WIs
LTE and UMTS Rel-14 ASN.1 reviewed and ready to be frozen
Last meeting of UMTS inside RAN2.
  Special thanks to Xudong Yang for chairing this session and to all the UMTS delegates. Good luck in RAN6!
Special thanks to:
  Hu Nan, Diana Pani (RAN2 VCs)
  Johan Johansson (NB-IOT/MTC chair)
  Xudong Yang (UMTS chair)
  Yi Guo (Rel-15 positioning chair)
  Juha Korhonen (MCC support)
  Meeting hosts: North American Friends and Huawei