## Cover sheet
3GPP TSG-RAN WG5 meeting#75 | [6 empty] | R5-172400
Hangzhou, P. R. China, 15-19 May 2017
Agenda Item: | 7.4.2
Source: | Rapporteur (Bureau Veritas, Orange)
Title: | UE Conformance Test Aspects - LTE 2.6 GHz FDD SDL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for Region 1 (Band 69)
Work item code: | LTE_FDD_2600_CA_B3-UEConTest
Document for: Information
1. Introduction
At the RAN#75 meeting in Dubrovnik, Croatia, 6-9 March a Rel-14 RAN5 work item for LTE 2.6 GHz FDD SDL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for Region 1 (Band 69) (LTE_FDD_2600_CA_B3-UEConTest) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item for LTE 2.6 GHz FDD SDL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for Region 1 (Band 69). The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status; sheet CA_3A-69A (2DL/1UL) lists the planned LTE 2.6 GHz FDD SDL CA Band test scenarios and the detailed status.
2. Work item status
The completeness of the LTE 2.6 GHz FDD SDL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for Region 1 (Band 69) work item after RAN5#75 meeting is:
Test specification | Testing area |  | Completeness | 3 Month Target | 6 Month Target | Comments | History
TS 36.508 | Common test environments for User Equipment (UE); Conformance testing |  | 0% | 80% | 100% |  | RAN#76: 0% RAN#77: 80% RAN#78: 100%
TS 36.521-1 | Evolved Universal Terrestrial Radio Access (E-UTRA); User Equipment (UE) conformance specification; Radio transmission and reception; Part 1: Conformance testing |  | 30% | 80% | 100% |  | RAN#76: 30% RAN#77: 80% RAN#78: 100%
TS 36.521-2 | Evolved Universal Terrestrial Radio Access (E-UTRA); User Equipment (UE) conformance specification; Radio transmission and reception; Part 2: Implementation Conformance Statement (ICS) |  | 100% |  |  |  | RAN#76: 100%
TS 36.521-3 | Evolved Universal Terrestrial Radio Access (E-UTRA); User Equipment (UE) conformance specification; Radio transmission and reception; Part 3: Radio Resource Management (RRM) conformance testing |  | 100% |  |  |  | RAN#76: 100%
TS 36.523-2 | Evolved Universal Terrestrial Radio Access (E-UTRA) and Evolved Packet Core (EPC); User Equipment (UE) conformance specification; Part 2: Implementation Conformance Statement (ICS) |  | 100% |  |  |  | RAN#76: 100%
Estimation of WI overall completeness:
Overall completeness |  | 43.21%
Colour coding:
Not started
Ongoing
Ready
4 Test coverage analysis and assumptions
This work item proposes UE conformance testing for FDD SDL band 2570-2620 MHz for Region1. The Feature, Core and Performance Part Work Items were approved in RAN#72 (June 2016, RP-160867). TR 36.858 provides the technical report for the LTE 2.6 GHz FDD SDL band and TR 36.714 contains the CA related aspects of the WI. The band is to be used in CA (2DL /1UL) Band 3+ FDD SDL Band 2570-2620 MHz configuration in E-UTRA specified in TS 36.101. This work item will facilitate UE conformance testing of Rel-14 LTE for the Supplemental Downlink in E-UTRA (Band-69).
The relevant core requirements for the Rel-14 are specified in:
TS | Title
36.124 | E-UTRA; EMC requirements for mobile terminals and ancillary equipment
25.104 | Base Station (BS) radio transmission and reception (FDD)
25.141 | Base Station (BS) conformance testing (FDD)
36.104 | E-UTRA; BS Radio transmission and reception
36.113 | E-UTRA; BS and repeater EMC
36.141 | E-UTRA; BS conformance testing
37.104 | E-UTRA, UTRA and GSM/EDGE; Multi-Standard Radio (MSR) Base Station (BS) radio transmission and reception
37.113 | E-UTRA, UTRA and GSM/EDGE; Multi-Standard Radio (MSR) Base Station (BS) Electromagnetic Compatibility (EMC)
37.141 | E-UTRA, UTRA and GSM/EDGE; Multi-Standard Radio (MSR) Base Station (BS) conformance testing
36.101 | E-UTRA; UE Radio transmission and reception
25.133 | UTRAN: Requirements for support of radio resource management (FDD)
36.133 | E-UTRA; Requirements for support of RRM
5 References
[1] RP-161716 | New Work Item Proposal: LTE 2.6 GHz FDD SDL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for Region 1; Supporting companies: Bureau Veritas, Orange, Ericsson, Nokia, Keysight, Huawei, SGS Wireless

## CA_3A-69A (2DL-1UL)
UE Conformance Test Aspects - LTE 2.6 GHz FDD SDL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for Region 1 (Band 69)
| CA configuration |  |  | CA_3A-69A (2DL/1UL) | [14 empty] | Note! The columns T to W are used to calculate relative completeness vs areas and overall. Do not remove!
| Company |  |  | Bureau Veritas
| Contact |  |  | Amy Tao (Amy.Tao@tw.bureauveritas.com)
| Target completion |  |  | RAN5#77 (11-2017)
| Comments |  |  | -
Sub-WI scope
| New DL CA config(s) |  |  | DL-CA_3A-69A
| New DL Fallback CA config(s) |  |  | -
| New UL CA config(s) |  |  | -
Overall Sub-WI
| Overall completeness |  |  | 43.21% | [14 empty] | Overall sum of item weights |  |  | 28
| Common RF,RRM and Protocol |  |  | 0% | [14 empty] | Sum of item weights for common RF,RRM and protocol area |  |  | 2
| RF completeness |  |  | 30.5% | [14 empty] | Sum of item weights for the RF area |  |  | 20
| RRM completeness |  |  | 100% | [14 empty] | Sum of item weights for the RRM area |  |  | 5
| Protocol completeness |  |  | 100% | [14 empty] | Sum of item weights for the protocol area |  |  | 1
| Note! Do not insert any new rows above this row as the exact positioning of the information above is critical to generate the overall work plan. | [17 empty] | Note! The columns below are used to calculate relative completeness vs areas and overall. Don't remove!
WP Filter | Area | TS | TC / Clause Number | Description / Title | Impacted CA config(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | [7 empty] | Item Overall Completeness
RF, RRM and Protocol testing common area (TS 36.508)
Item Rel. Weight | Area | TS | TC / Clause Number | Description / Title | CA config | Test purpose / Task | Company | Target | TDOC(s) | Comments | Detailed Completion Status per area | [6 empty] | Item Overall Completeness | Item Accumulated Weight | Item Area Relative Completeness | Item Relative Completeness
[11 empty] | Test Freq. | Ref. System Config. | GenericTest proc. | Def. Mess. Cont. | Connection Diagrams | Other Areas
[11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | <- Compl.Weights
RF, RRM and Protocol testing common area
1 | Common | 36.508 | 4.3.1 | Test frequencies (including new band) | DL-CA_3A-69A | - Add test frequency of new band(s) in sub-clause 4.3.1.1 (FDD) or 4.3.1.2 (TDD). - Add test frequencies for the new CA configuration in sub-clause 4.3.1. - Check if reference system configurations in sub-clause 4.4 need to be updated. | Ericsson | RAN5#77 (11-2017) |  |  | 0% | 0% | [5 empty] | 0% | 2 | 0% | 0% | 1
1 | Common | 36.508 | 6.2.3.2 | Test frequencies for CA signalling test | DL-CA_3A-69A | Add test frequencies for the new CA configuration for CA signalling tests in sub-clause 6.2.3.2. | Ericsson | RAN5#77 (11-2017) |  |  | 0% | [6 empty] | 0% | 1 | 0% | 0% | 1
End list of common RF, RRM and Protocol items (insert any additional item rows above this row)
RF / Performance testing area (TS 36.521-1) and associated applicability defintions (TS 36.521-2)
Item Rel. Weight | Area | TS | TC / Clause Number | Description / Title | CA config | Test purpose / Task | Company | Target | TDOC(s) | Comments | Detailed Completion Status per area | [6 empty] | Item Overall Completeness | Item Accumulated Weight | Item Area Relative Completeness | Item Relative Completeness | Item Rel. Weight for calculation
[11 empty] | Min. Req. | Test proc. | Test Pts | Mess. Cont. | TT / TR 36.905 | ICS / TC appli. | Other Areas
[11 empty] | 1 | 5 | 5 | 2 | 2 | 2 | 2 | <- Compl.Weights
RF test cases (clauses 6 and 7)
1 | RF Tx | 36.521-1 | 6.2.5 | Configured UE transmitted Output Power | DL-CA_3A-69A | - Add delta TIB for the new CA configuration in sub-clause 6.2.5. | Bureau Veritas | RAN5#77 (11-2017) | R5-172376 |  | 100% | [6 empty] | 100% | 1 | 5% | 3.571% | 1
1 | RF Rx | 36.521-1 | 7.3A.3 | Reference sensitivity level for CA (inter-band DL CA without UL CA) | DL-CA_3A-69A | - Check if specific minimum requirements need to be updated in sub-clause 7.3A.0 and in 7.3.3 (for delta RIB of the new CA configuration). - Add test points if needed (Test Configuration Table). - Add test requirements. - Add test point analysis to TR 36.905. | Bureau Veritas | RAN5#77 (11-2017) | R5-169569 |  | 100% |  | 0% | 0% | 0% |  |  | 10% | 10 | 0.5% | 0.3571% | 1
1 | RF Rx | 36.521-1 | 7.4A.3 | Maximum input level for CA (inter-band DL CA without UL CA) | DL-CA_3A-69A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | Orange | RAN5#77 (11-2017) |  |  | 0% |  | 0% | 0% | 0% |  |  | 0% | 10 | 0% | 0% | 1
1 | RF Rx | 36.521-1 | 7.5A.3 | Adjacent Channel Selectivity (ACS) for CA (inter-band DL CA without UL CA) | DL-CA_3A-69A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | Orange | RAN5#77 (11-2017) |  |  | 0% |  | 0% | 0% | 0% |  |  | 0% | 10 | 0% | 0% | 1
1 | RF Rx | 36.521-1 | 7.6.1A.3 | In-band blocking for CA (inter-band DL CA without UL CA) | DL-CA_3A-69A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | Orange | RAN5#77 (11-2017) |  |  | 0% |  | 0% | 0% | 0% |  |  | 0% | 10 | 0% | 0% | 1
1 | RF Rx | 36.521-1 | 7.6.2A.3 | Out-of-band blocking for CA (inter-band DL CA without UL CA) | DL-CA_3A-69A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | Orange | RAN5#77 (11-2017) |  |  | 0% |  | 0% | 0% | 0% |  |  | 0% | 10 | 0% | 0% | 1
1 | RF Rx | 36.521-1 | 7.6.3A.3 | Narrow band blocking for CA (inter-band DL CA without UL CA) | DL-CA_3A-69A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | Orange | RAN5#77 (11-2017) |  |  | 0% |  | 0% | 0% | 0% |  |  | 0% | 10 | 0% | 0% | 1
1 | RF Rx | 36.521-1 | 7.7A.3 | Spurious response for CA (inter-band DL CA without UL CA) | DL-CA_3A-69A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | Orange | RAN5#77 (11-2017) |  |  | 0% |  | 0% | 0% | 0% |  |  | 0% | 10 | 0% | 0% | 1
1 | RF Rx | 36.521-1 | 7.8.1A.3 | Wideband intermodulation for CA (inter-band DL CA without UL CA) | DL-CA_3A-69A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | Orange | RAN5#77 (11-2017) |  |  | 0% |  | 0% | 0% | 0% |  |  | 0% | 10 | 0% | 0% | 1
1 | RF Rx | 36.521-1 | 7.9A | Spurious emissions for CA (only applicable for CA configs with SDL) | DL-CA_3A-69A | - Check if specific minimum requirements need to be updated. - Add test points if needed (Test Configuration Table). - Add test requirements. | Orange | RAN5#77 (11-2017) |  |  | 0% |  | 0% | 0% | 0% |  |  | 0% | 10 | 0% | 0% | 1
Perfomance test cases (clauses 8 and 9)
1 | Perf | 36.521-1 | 8.1.2 | Applicability of requirements | DL-CA_3A-69A | - Add new BW combinations in section 8.1.2 if needed - If this is the first CA configuration of this CA configuration types, add it in section 8.1.2 | Bureau Veritas | RAN5#77 (11-2017) | R5-17xxxx | [7 empty] | 100% | 100% | 2 | 5% | 3.571% | 1
1 | Perf | 36.521-1 | 8.2.1.1.1_A.1 | FDD PDSCH Single Antenna Port Performance for CA (2DL CA) | DL-CA_3A-69A | Add new BW combinations if needed | Bureau Veritas | RAN5#77 (11-2017) |  |  | 0% |  | 0% | 0% | 0% |  |  | 0% | 10 | 0% | 0% | 1
1 | Perf | 36.521-1 | 8.2.1.3.1_A.1 | FDD PDSCH Open Loop Spatial Multiplexing 2x2 for CA (2DL CA) | DL-CA_3A-69A | Add new BW combinations if needed | Bureau Veritas | RAN5#77 (11-2017) |  |  | 0% |  | 0% | 0% | 0% |  |  | 0% | 10 | 0% | 0% | 1
1 | Perf | 36.521-1 | 8.2.1.4.2_A.1 | FDD PDSCH Closed Loop Multi Layer Spatial Multiplexing 4x2 for CA (2DL CA) | DL-CA_3A-69A | Add new BW combinations if needed | Bureau Veritas | RAN5#77 (11-2017) |  |  | 0% |  | 0% | 0% | 0% |  |  | 0% | 10 | 0% | 0% | 1
1 | Perf | 36.521-1 | 8.7.1.1_A.1 | FDD Sustained data rate performance for CA (2DL CA) | DL-CA_3A-69A | Add new BW combinations if needed | Bureau Veritas | RAN5#77 (11-2017) |  |  | 0% |  | 0% | 0% | 0% |  |  | 0% | 10 | 0% | 0% | 1
1 | CSI reporting | 36.521-1 | 9.1 | Applicability of requirements | DL-CA_3A-69A | - Add new BW combinations in section 9.1.1 if needed. - If this is the first CA configuration of the new Rel-13 CA configuration types, add it in section 9.1.1. | Bureau Veritas | RAN5#77 (11-2017) |  | No changes required | [6 empty] | 100% | 100% | 2 | 5% | 3.571% | 1
1 | CSI reporting | 36.521-1 | 9.6.1.1_A.1 | FDD CQI Reporting under AWGN conditions – PUCCH 1-0 for CA (2DL CA) | DL-CA_3A-69A | Add new BW combinations if needed | Bureau Veritas | RAN5#77 (11-2017) |  | No changes required | 100% |  | 100% | 100% | 100% |  |  | 100% | 10 | 5% | 3.571% | 1
RF General (TS 36.521-1 clauses 3 to 5 and Annexes, TS 36.521-2 ICS)
1 | General RF | 36.521-1 | 5.2A | Operating bands for CA | Band 69, DL-CA_3A-69A | Add the operating band and channel assignments for the new CA configuration and new band to sub-clause 5.2A. | Bureau Veritas | RAN5#77 (11-2017) | R5-169572 R5-173216 | [7 empty] | 100% | 100% | 2 | 5% | 3.571% | 1
1 | General RF | 36.521-1 | Annex A | Measurement Channels Tx, Rx and Performance TCs | DL-CA_3A-69A | - Check if there is a need to update Measurement Channels in Annex A for the Tx and Rx TCs for the new CA configuration. - Check if there is a need to update Measurement Channels in Annex A for the Performance TCs for the new CA configuration. | Bureau Veritas | RAN5#77 (11-2017) | R5-172397 | [7 empty] | 0% | 0% | 2 | 0% | 0% | 1
1 | General RF | 36.521-1 | Annex F | Measurement uncertainties and Test Tolerances | DL-CA_3A-69A | Uncertainty of the test system and the allowed test tolerances is handled for each test case in the TS 36.521.1 section. | [12 empty] | 0 | 0% | 0% | 0
1 | ICS RF/RRM | 36.521-2 | Annex A | Implementation Conformance Statements for RF/RRM test cases | DL-CA_3A-69A | Update of CA Physical Layer Baseline Implementation Capabilities for new CA configuration in Annex A.4.6 | Bureau Veritas | RAN5#77 (11-2017) | R5-172697 | [6 empty] | 100% |  | 100% | 2 | 5% | 3.571% | 1
End list of RF Misc items (insert any additional RF Misc item rows above this row)
RRM testing area (TS 36.521-3 & TS 37.571-1) and associated applicability defintions (TS 36.521-2 and TS 37.571-3)
Item Rel. Weight | Area | TS | TC / Clause Number | Description / Title | CA config | Test purpose / Task | Company | Target | TDOC(s) | Comments | Detailed Completion Status per area | [6 empty] | Item Overall Completeness | Item Accumulated Weight | Item Area Relative Completeness | Item Overall Relative Completeness
[11 empty] | Min. Req. | Test proc. | Test Pts | Mess. Cont. | TT | ICS / TC appli. | Other Areas
[11 empty] | 1 | 5 | 5 | 2 | 2 | 2 | 2 | <- Compl.Weights
RRM test cases
1 | RRM | 36.521-3 | 8.16.x | Legacy TC(s) for CA 2CC DL for FDD and Measurement Procedures Performance (8.16.1, 8.16.3, 8.16.5, 8.16.7, 8.16.9, 8.16.11, 8.16.13, 8.16.15, 8.16.17, 8.16.17A ). | DL-CA_3A-69A | Typically no updates needed to legacy test cases for a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. | Bureau Veritas | RAN5#77 (11-2017) |  | no new band group is introduced |  |  |  |  | 100% |  | 100% | 100% | 4 | 20% | 3.571% | 1
1 | RRM | 36.521-3 | 9.1.x | Legacy TC(s) for CA 2CC DL for FDD and Measurement Performance (9.1.6, 9.1.12, 9.1.18, 9.1.20, 9.2.5, 9.2.11, 9.2.21, 9.2.23). | DL-CA_3A-69A | Typically no updates needed to legacy test cases for a new CA configuration. However, update of Test Tolerance analysis might be needed if the new CA band combinations introduces a new band group in clause 3.5.1. | Bureau Veritas | RAN5#77 (11-2017) |  | no new band group is introduced |  |  |  |  | 100% |  | 100% | 100% | 4 | 20% | 3.571% | 1
1 | Pos RRM | 37.571-1 | 10.x | Legacy TC(s) for OTDOA RSTD Positioning Performance requirements | DL-CA_3A-69A | Typically no updates needed to legacy test cases for a new CA configuration. | Bureau Veritas | RAN5#77 (11-2017) |  | the test cases are general and apply for all CA variants | [6 empty] | 100% | 100% | 2 | 20% | 3.571% | 1
RRM General
1 | General RRM | 36.521-3 | 3 | Groups of bands | DL-CA_3A-69A | Ensure that the operating bands of the CA configuration are covered in Clause 3.5.1 “Group of bands”. | Bureau Veritas | RAN5#77 (11-2017) | R5-171739 | [7 empty] | 100% | 100% | 2 | 20% | 3.571% | 1
1 | General RRM | 36.521-3 | Annex F | Uncertainty of the test system and test tollerances. | DL-CA_3A-69A | Uncertainty of the test system and the allowed test tolerances is handled for each test case in the TS 36.521-1 section of the work plan. | [12 empty] | 0 | 0% | 0% | 0
1 | General RRM | 36.521-3 | Annex I | RRM Requirements Exceptions | DL-CA_3A-69A | Check if the CA band combination is covered by the RRM condition in sub-clause I.4. |  | RAN5#77 (11-2017) |  | No changes required | [6 empty] | 100% | 100% | 2 | 20% | 3.571% | 1
End list of RF Misc ietms (insert any additional RRM Misc item rows above this row)
Protocol testing area (TS 36.523-1) and associated applicability defintions (TS 36.523-2)
Item Rel. Weight | Area | TS | TC / Clause Number | Description / Title | CA config | Test purpose / Task | Company | Target | TDOC(s) | Comments | Detailed Completion Status per area | [6 empty] | Item Overall Completeness |  | Item Area Relative Completeness | Item Relative Completeness
[11 empty] | TP & Conf. Req. | Test proc. | Mess . Cont. | ICS / TC appli. | Other Areas
[11 empty] | 2 | 5 | 2 | 1 | 1 | 1 | 1 | <- Compl.Weights
Protocol test cases
1 | Protocol | 36.523-1 |  | No new test cases needed. | [14 empty] | 0 | 0% | 0% | 0
End list of SIG test cases (insert any additional SIG test case rows above this row)
Protocol General
1 | ICS SIG | 36.523-2 | Annex A | Implementation Conformance Statements for Protocol test cases (new band added) | DL-CA_3A-69A | - Update of CA Physical Layer Baseline Implementation Capabilities for new CA configuration in Annex A.4.3.3. | Bureau Veritas, Ericsson | RAN5#77 (11-2017) | R5-172698 |  |  |  |  | 100% |  |  |  | 100% | 1 | 100% | 3.571% | 1
End list of SIG Misc items (insert any additional SIG Misc item rows above this row)
Note on A25: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on S27: Used to calculate work areas relative impact on the item's completeness. Default value is 1. For a more work intesive area set to value >1.
Note on A34: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on S36: Used to calculate work areas relative impact on the item's completeness. Default value is 1. For a more work intesive area set to value >1.
Note on A64: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on S66: Used to calculate work areas relative impact on the item's completeness. Default value is 1. For a more work intesive area set to value >1.
Note on A79: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on S81: Used to calculate work areas relative impact on the item's completeness. Default value is 1. For a more work intesive area set to value >1.