## Slide 1
3GPP submission towards IMT-2020
Version agreed at the drafting session
ITU-R Ad-Hoc Contact person

## Slide 2: Agenda items
Submission timeplan
Format of submission
Naming (not for discussion – already endorsed by RAN)
Distribution of this document

## Slide 3: Submission timeplan

## Slide 4: Submission timeplan
Submission Milestone Name | 3GPP Meeting | ITU-R Meeting | General Submission Content | Submission Templates (Release Basis) | Self- Evaluation (Release Basis)
Workshop | RAN # 77 Sept 2017 | WP 5D #28 Oct 2018 | Overview | - | -
Initial Templates Only | RAN # 78 Dec 2017 | WP 5D # 29 Feb 2018 | Description Templates | Description Templates 5.2.3 (R15) | -
Update & Self-Eval | RAN # 81 Sept 2018 | WP 5D # 31 Oct 2018 | Description Templates Compliance Templates Self-Evaluation | Description Templates 5.2.3 (R15) Compliance Templates 5.2.4 (R15) | Self-Evaluation (R15)
Final | RAN # 84 June 2019 | WP 5D # 32 July 2019 | Description Templates Compliance Templates Self-Evaluation | Description Templates 5.2.3 (R15+R16) Compliance Templates 5.2.4 (R15+R16) | Self-Evaluation (R15+R16)

## Slide 5: Submission timeplan
WF:
  Follow the timeplan as per slide 2 and slide 3
  February submission:
    High level description of NR and LTE (including NB-IoT and eMTC)
      All architectures are described, including dual connectivity between NR and LTE
    No self-evaluation required
    Target to provide description template
  Final submission based on Rel 15 and Rel 16 features and specifications

## Slide 6: Format of submission
WF:
  Submisison 1
    SRIT
      Component RIT: NR (TBD incl. NB-IoT, eMTC)
      Component RIT: EUTRA/LTE (incl. NB-IoT, eMTC)
      full 38 and 36 series (excluding operation in unlicensed spectrum, details TBD)
      Evaluation of each component RIT shall be performed, and IMT2020 compliance demonstrated, against all IMT2020 requirements and test environments
  Submission 2
    In addition to above, submit an NR RIT
    The plan is to leverage the NR RIT as in submission 1; exact proposal TBD by final submission

## Slide 7: Naming (already agreed)
Name of the 3GPP technology endorsed by RAN:
  Name : 5G
    Developed by 3GPP as 5G, Release 15 and beyond (5G)

## Slide 8: Distribution of this document
The agreed way forward to be submitted to RAN WGs
Submit the agreed to SA and PCG for their endorsement