3GPP TSG-RAN  #77	RP-171871

Sapporo, Japan, 11 - 14 September 2017

Agenda item:	9

Source:	Nokia, Nokia Shanghai Bell

Title:	Focusing the Relaease 15 NR Work

Document for:	Discussion and Decision

# 1	Introduction

This contribution gives an overview of the status of NR work in RAN and suggests possible solutions to maximise the chances of completing NSA and SA as originally scheduled.

# 2	NR Status

All relevant RAN working groups developing NR have an extremely high work load. Experience from the last WG meetings in Berlin show in many cases, very long days (7:30 till 23:00) and many submissions simply not considered due to time pressure. Considering that, since initial agreement of the NR work item, we have accelerated the schedule and at the same time increased the scope this should surprise no-one.

Observation 1: In our view if no significant action is taken at RAN #77 the current agreed timeline for NR cannot be met.

Although as stated all relevant working groups are extremely loaded it is worth looking at more detail where exactly the worst bottleneck’s are. In our view the status is as follows:

- RAN 1: Overloaded without focus on essential functionality the deadlines will not be met

- RAN 2 : User-Plane heavily loaded, Control-plane overloaded without focus on essential functionality the deadlines will not be met (more details are shown in Annex A)

- RAN 3: Heavily loaded, but not yet impossible.

- RAN 4: Heavily loaded

# 3	Proposed Way Forward

In general, we propose to follow a two-step approach to maximize NR progress:

- Firstly, where possible focus only on essential functionality of the NR work

- Secondly, investigate measures to increase the time available for NR at the up-coming meetings.

## 3.1	Reducing the scope of the NR work

Based on our initial analysis the key place to look for scope reduction is in RAN 1. Focusing on essential functionality in RAN1 has direct benefits in terms of reduction of work load on other working groups like RAN 2. In RAN 2 we see no clear path to significantly change the scope, as shown in the annex A analysis, the SA and NSA aspects are tightly intertwined in these features and cannot be separated.

Observation 2: Focusing RAN 1 NR on essential functionality presents the best possibility for competing the NR work on time.

Observation 3: NSA and SA are tightly coupled in RAN 2 (the user plane is common, subset of SA RRC is needed for NSA) and one option cannot ignore the other.

In addition to RAN 1 focusing on essential functionality our belief is that a reduction in the number of NR network architectures being considered in parallel would help to speed up the work we therefore propose to focus the discussions first on scenarios 2 and 3 and then expand to other once a stable baseline is agreed.

Observation 4: Reducing the number of NR network architectures to consider in the short term will speed up the work.

## 3.2	Increasing time for the NR work

We do not believe that simply further increasing the number or length of the WG meetings is a viable solution. There is a need to perform technical work, create new contributions and review proposals and if all time is taken with meetings and travel progress will be delayed not accelerated. In our view, we should rather look at possibilities to increase the number of time units available to NR in the existing meetings. Since many aspects are already running in parallel there appears limited scope to improve the time available for NR. One possibility, assuming we agree to concentrate on NR scenarios 2 and 3 would be to postpone eLTE discussion in RAN 2 until after the December deadline.

# 3	Conclusion

In order to maximise the chances of completing both NSA and SA on time, we suggest to:

1)	reduce the number of RAN1 features to an essential set. This will not only guarantee faster progress in RAN2 but also reduce the chances for "early UE handling" as seen in 3G. Note that the initial list of RRC parameters from RAN1 to RAN2 already contains ~3 times more parameters than in LTE Rel-8 [R2-1709847].

2)	progress both NSA and SA in parallel in RAN2: they are tightly coupled (the user plane is common, subset of SA RRC is needed for NSA) and one option cannot ignore the other.

3)	focus the discussions first on scenarios 2 and 3 and then expand to other once a stable baseline is agreed.

# Annex A

The following table summarizes the status of all aspects being discussed for the completion of NR (both SA and NSA) in 3GPP TSG RAN WG2. It is based on the Chairman's agenda.

| Feature | Status | Comments |
| --- | --- | --- |
| Stage 2 and common UP/CP aspects |  | UE capabilities, capability coordination, capability limitations, measurements and beam handling in general are lacking behind. |
| - Stage 2 TSs and running CR | good | Version 1.0.0 to be brought to plenary. |
| - Bearer type harmonisation | good | Security details just agreed, harmonisation in good shape. |
| - Bearer type change and L2 handling at mobility | good | Rel-15 focuses on solutions similar to LTE handover. |
| - Packet duplication | good | Most issues solved. |
| - NSA measurement coordination | late | Only few parameters for NR specific details of measurement object are agreed. Gaps and gap coordination discussed but not finalized. |
| - NSA procedures | late | Capability coordination progressed but final scheme not yet finalized. |
| - NSA operations |  |  |
| - - NSA Security | good | SA3 successfully involved. |
| - - NSA Single TX | late | 2TX UE is the agreed baseline. Large RAN2 impacts. |
| - - NSA SCG Failure | good | Stick to basic handling, no optimizations needed for the first release. |
| - UE capabilities |  |  |
| - - NR UE capabilities | late | Not defined yet, missing RAN1/4 input. Only needed at the end of release though. |
| - - UE categories | late | Unclear definition. Only needed at the end of release though. |
| - - UE capability coordination | late | Open issues in shared capabilities. Simple hard split can be considered first. |
| - - UE baseband capability sharing | late | Optimization – lot of discussion without clear convergence. |
| - - Temporary capability restriction | late | Optimisation, no conclusion. |
| - - 5G indicator | late | Optimization, no conclusion (pending progress in SA2, SA1, NGMN…) |
| - Mobility mechanisms - basic handover | good | Nearly finished. |
| - Mobility mechanisms - Other | late | Conditional HO is optimization and not critical to system operation. However, DC-based HO may be essential to ensure 0ms interruption is achieved within Rel-15. Work has not started at all. |
| - Mobility - RLM, RLF | good | Simple RLM/RLF handling only. Relation with beam failure/recovery still to be discussed. Should be on time. |
| - Mobility without RRC involvement | late | Not yet discussed in RAN2 (awaiting RAN1 input). |
| - Inter-RAT Mobility | good | Simple inter-RAT mobility is enough. |
| - Slicing | late | Forward compatibility needs to be ensured at least, for instance slice selection without prioritisation. |
| - QoS | good | Good coordination with SA2. Most Stage 2 issues solved. |
| - Positioning | good | Needed for emergency calls. RAN2 agreed to reuse LPP specification and transport LPP messages between 5GC and UE using NAS transport. RRC and NAS work needed in 5G. |
| - Supplementary uplink (SUL) | late | Not critical for first phase. |
| Stage 3 MAC |  | RAN1 optimisations with large impacts to MAC still need to be discussed (SPS, Grant Free, CORESET, BWP). |
| - TS | good | Good progress in general but some aspects are late. |
| - Architecture | late | Not clear yet how to model the time unit in MAC with multiple numerologies, bandwidth part, CORESET for PDCCH etc. |
| - PDU Format | good | Good progress. PDU format for UL/DL-SCH finalised. Format for RAR pending RAN1 feedback. |
| - Random Access | late | RACH parameter differentiation depending on service/event not essential and how it works not clear yet; and beam aspects not fully reflected in RACH procedure yet. |
| - SR | late | SR procedure still missing with open issues on how to handle SR restriction depending on the LCH that triggered the SR. Not essential to have the restriction if without LCP restriction. |
| - BSR | good | Input from RAN1 required to finalize buffer size tables. |
| - LCP | good | LCP restriction details to be finalised. Not essential to have LCP restriction in general, esp. not essential for single cell case as RAN1 will primarily work on single bandwidth part with single numerology for single cell. |
| - SPS/Grant Free | late | Multiple SPS not essential to support, introduce extra complexity on how to confirm activation/deactivation. |
| - HARQ | good | With the agreement of asynchronous adaptive HARQ for both UL and DL, baseline procedure available. |
| - DRX | late | Impact of bandwidth part and CORESET not clear yet, possible be kept transparent to MAC but to be discussed. |
| - Duplication | good | Duplication activation and deactivation MAC CE format settled. |
| - PHR | late | Pending RAN1 and RAN4 progress. |
| Stage 3 RLC |  | In good shape, no blocking points. |
| - TS | good | Still some open issues on how to handle pre-processing and avoid SN gap. |
| - Header Format | good | Data PDU format and Status Report PDU format finalised. |
| - UM Operation | good | Window with gap based timer agreed. |
| - Duplication | good | Agreement achieved on RLC failure handling for duplicated leg. |
| Stage 3 PDCP |  | In good shape, no blocking points. |
| - TS | good | Data volume calculation missing. |
| - PDU Format | good | PDU Formats finalised. |
| - Receive Operation | good | Basic receive operation ready, out-of-order delivery to higher layers almost ready. |
| - UL Data Split | good | Details of pre-processing limitations for threshold based UL data split missing. Data volume calculation missing. |
| Stage 3 SDAP |  | In good shape, no blocking points. |
| - TS | good |  |
| - Header Format | good | Header format agreed, to be confirmed by SA2. |
| Stage 3 RRC |  | Insufficient progress on many critical aspects for both SA and NSA. Large list of RAN1 parameters to handle (~150 vs. 50 for LTE Rel-8). |
| - TS | late | Decent progress for skeleton but missing lot of content. |
| - Specification Methodology | good | Good progress, done. |
| - Connection control procedures | late | Needed for any NR operation (including the NR leg of NSA - not all procedures though) |
| - - Message Harmonisation | late | Optimization. |
| - - Reconfiguration | late | Started. Critical message for EN-DC and most use cases. |
| - - NSA Aspects | late | Started and progressing. |
| - RRM Measurements | late | Going relatively slowly. |
| - - Cell Quality Derivation | good | After lengthy discussions - done. |
| - - Measurement report content | good | Almost done. |
| - - Measurement configuration | late | Missing many details. |
| - - Measurement events | late | Unknown status of Cx events. Ax events not discussed in detail. |
| - - Inter-RAT measurements | late | Not needed for NSA, but needed for SA. |
| - - Measurement gaps | late | No need for optimizations – stick LTE baseline. |
| - System Information | late | Overall there was good progress until RAN2 NR-adhoc#2 but after the NR-adhoc#2 progress is slow. Stage 3 details pending. |
| - - System information content/structure | late | MIB content is clear. SIB1 content is roughly known but still not finalized and other SIB contents are still not finalized. |
| - - Stored system information | late | This is mainly a UE optimization for battery saving by minimizing SI acquisitions but nevertheless needed in Rel-15. Few issues still remain open. |
| - - System information modification | late | Stage 3 details pending. One FFS issue still unresolved. |
| - - System information scheduling | late | Stage 3 details pending. |
| - - On demand system information | late | Optional feature and hence not critical. Stage 3 details pending. |
| - Inactive State | good | Inter-RAT mobility is not critical to have for inactive state to be operational. |
| - - RAN area configuration | good | RAN3 has managed to progress this well. |
| - - RAN area update procedure | good | RAN3 has managed to progress this well. |
| - - Paging in inactive | good | Should be similar to IDLE (but there are proposals to differentiate). |
| - - Inter-RAT mobility | good | Just falling back to IDLE is simplest → no need for anything extra. |
| - Access Control | late | Requires RAN2, CT1, SA1 work and coordination. It has dependency on NAS, service accessibility requirements and other RRC components (System Information, RRC Inactive). |
| - Inter-Node RRC messages | late | Almost nothing done yet, only agreed to use for inter-node coordination. |
| Stage 3 Idle Mode |  | Only high-level discussions so far, many topics not started yet. |
| - TS | late | Started but not much discussions yet. If we follow LTE, then most of the TS should be straightforward though. |
| - Selection/reselection rules | late | Not started. |
| - Cell quality derivation | late | Not started. |
| - Service based reselection | late | Very basic discussions so far |
| - Paging | late | Not started. |
| Stage 3 UE Capabilities |  | Further progress in all WGs needed first. |
| - TS | late | Only skeleton agreed, content input to be defined late in the release though. |

In general, the following can be observed:

-	user plane aspects are in good shape while control plane ones are lacking behind;

-	some RAN1 optimisations have large impacts to RAN2 and should be carefully considered;