## Slide 1: Wayforward on Rel-15 NR Study Items
3GPP TSG RAN #77
Sapporo, Japan
September 11-14, 2017
ZTE, Sanechips, Qualcomm, Thales, AT&T, Huawei
RP-172070

## Slide 2: Background
In RAN#75, the following NR Rel-15 SIs were approved
  Non-orthogonal multiple access (RP-170829), to start in RAN1 in Aug., 2017
  Unlicensed spectrum for NR (RP-170828), to start in RAN1 in Aug., 2017
  Non-terrestrial network (RP-170717), to start in RAN1 in Aug., 2017
  eV2X evaluation methodology (RP-170837), to start in RAN1 in Oct., 2017
  NR self-evaluation (RP-170832), to start in RAN in Sept., 2017
  Integrated access and backhaul (RP-170831), to start in RAN2 in Nov., 2017
In RAN#76, starting time in RAN WGs for the following NR SIs were postponed
  Non-orthogonal multiple access (RP-171499), to start in RAN1 in Oct. 2017
  Unlicensed spectrum (RP-171496), to start in RAN1 in Oct. 2017
  Non-terrestrial network (channel modeling) (RP-171488), to start in RAN1 in Oct. 2017 (Note that activity in RAN plenary started in June 2017)
It is a common understanding that RAN1 should focus on NR WI in Q4 of 2017 to ensure on-time completion of Rel-15 L1 design for eMBB

## Slide 3: Proposal
The following Rel-15 Study Items will start in RAN WGs in Q1 2018. TUs lost in Q4 2017 will be compensated in NR Ad-hoc meeting and regular meetings in Q1 and Q2 2018
  Non-orthogonal multiple access
  Unlicensed spectrum for NR
  Non-terrestrial network (channel modeling)
  eV2X evaluation methodology
  Integrated access and backhaul

## Slide 4: Detailed TU allocations in RAN1
SI | Oct | Nov | Jan (AH) | Feb | April | May
Non-orthogonal MA | 1 | 1 | 2 | 3 | 3 | 4
Unlicensed spectrum | 1 | 1 | 2 | 3 | 4 | 3
Non-terrestrial networks | 1 | 1 | 1 | 1  2 |  | 
eV2X evaluation method. | 1 | 1 | 1 | 1 |  | 
Integrated access & backhaul |  |  |  | 1 | 1 | 1
NR self evaluation | [1] | [1] |  | [1] | [1] | [1]
Note 1: red numbers are the modified and black numbers are the unchanged
Note 2: it has been agreed that Q4 TUs of NR self evaluation will be moved to RAN level

## Slide 5: Detailed TU allocations in RAN2
SI | Oct | Nov | Jan (AH) | Feb | April | May
Unlicensed spectrum |  |  |  | 1 | 1 | 1
Integrated access & backhaul |  | 1 | 1 | 1 | 1 | 1
NR self evaluation |  |  |  | [0.5] | [0.5] | [0.5]
Note: red numbers are the modified and black numbers are the unchanged

## Slide 6: Detailed TU allocations in RAN4
SI | Oct | Nov | Jan (AH) | Feb | April | May
Non-orthogonal MA |  |  |  | 0.5 | 0.5 | 
Unlicensed spectrum | 0.25 | 0.25 |  | 0.25 | 0.25 0.5 | 0.25 0.5
Note: red numbers are the modified and black numbers are the unchanged

## Slide 7: Thank you