## TU_overview_after_RAN_80_new
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation | [5 empty] | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | Final column of TU total. Insert new quarters before this column. Do not remove this column
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | target | sum TUs | comment | 81 Sept 18 | 94bis | 103bis | 101bis | 88bis | 88bis | 95 | 104 | 102 | 89 | 89 | 10 | 82 Dec 18 | 96 | 105 | 103 | 90 | 90 | 11 | 83 Mar 19 | 96bis | 105bis | 103bis | 90bis | 90bis | 97 | 106 | 104 | 91 | 91 | 12 | 84 Jun 19 | 98 | 107 | 105 | 92 | 92 | 13 | 85 Sept 19 | 98bis | 107bis | 105bis | 92bis | 92bis | 99 | 108 | 106 | 93 | 93 | 14 | 86 Dec 19 | 100 | 109 | 107 | 94 | 94 | 15 | 87 Mar.20 | 100bis | 109bis | 107bis | 94bis | 94bis | 101 | 110 | 108 | 95 | 95 | 16 | 88 Jun.20
R1 | NR | NR_newRAT-Core | WI | New Radio (NR) Access Technology | RP-181726 | NTT DOCOMO | Dec 18 | 84 | For RAN2 this row is the time allocation for late drop with NR Rel-15 maintenance time captured in the NR legacy row below. For other WGs this row is a combination of late drop and maintenance |  | 6 | 7 | 7 | 12 | 5 | 4 | 7 | 7 | 12 | 5 |  |  | 2 | 6 |  | 1 | 1 |  |  | 1 |  |  |  |  | 1
R4 | NR | NR_newRAT-Perf | WI | Perf. part: New Radio Access Technology | RP-181726 | NTT DOCOMO | Jun 18 | 34 | [5 empty] | 8 | 6 |  |  |  | 8 | 6 | [5 empty] | 2 | 2 | [5 empty] | 1 | 1
R1 | NR | FS_NR_NOMA | SI | Study on non-orthogonal multiple access for NR | RP-181403 | ZTE | Dec 18 | 5 |  |  | 2.5 |  |  |  |  | 2.5
R1 | NR | NR_NOMA | SI/WI | Study or work item (TBD) on non-orthogonal multiple access for NR |  | ZTE | Dec 19 | 14 | [14 empty] | 1 | [6 empty] | 1 | 1 |  |  |  | 1 | 1 | [5 empty] | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 | 1 | [9 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
R1 | NR | FS_NR_unlic | SI | Study on NR-based Access to Unlicensed Spectrum | RP-181339 | Qualcomm | Dec 18 | 7 |  |  | 2.5 | 1 |  |  |  | 2.5 | 1
R1 | NR | NR_unlic | WI | NR-based Access to Unlicensed Spectrum |  | Qualcomm | Dec 19 | 46.25 | [14 empty] | 3 | 1 | [5 empty] | 3 | 2 |  | 0.25 | 0.5 | 3 | 2 |  | 0.25 | 1 |  |  | 4 | 2 |  | 0.25 | 1.5 |  |  | 4 | 3 |  | 0.25 | 1.5 | 4 | 3 |  | 0.5 | 1 | [5 empty] | 0.25 | 1 | [5 empty] | 0.5 | 1.5 |  |  |  | 0.5 | 1.5
R1 | NR | FS_NR_V2X | SI | Study on NR Vehicle-to-Everything (V2X) | RP-182111 | LG Electronics | Mar 19 | 14.5 |  |  | 3 | 1 | 0.5 |  |  | 3 | 1 | 0.5 |  |  |  |  | 3 | 2 | 0.5
R1 | NR | NR_V2X | WI | NR Vehicle-to-Everything (V2X) |  | LG Electronics | Dec 19 | 44.5 | [21 empty] | 3 | 2 |  | 0.5 | 0.5 | 3 | 2 |  | 1 | 1 |  |  | 3 | 2 | 1 | 1 | 1.5 |  |  | 3 | 3 | 1 | 1 | 1.5 | 3 | 3 | 1 | 1 | 1.5 | [5 empty] | 0 | 1 | [5 empty] | 0 | 1.5 |  |  |  | 0 | 1.5
R1 | NR | NR_eMIMO-Core | WI | Core part: Enhancements on MIMO for NR | RP-182067 | Samsung | Dec 19 | 25.5 |  |  | 2 |  |  |  |  | 2 | [6 empty] | 2 | 0.5 | [5 empty] | 3 | 0.5 |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 | 0.5 |  |  | 1 | 3 | 1 |  |  | 1
R4 | NR | NR_eMIMO-Perf | WI | Perf. part: Enhancements on MIMO for NR | RP-182067 | Samsung | June 20 | 3 | [56 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
R1 | NR | SI_NR-PowerSaving | SI | Study on UE Power Saving in NR | RP-181463 | CATT | Jun 19 | 7 |  |  | 1 |  |  |  |  | 2 | [6 empty] | 1 | 1 | [6 empty] | 1 |  |  |  |  | 1
R1 | NR | NR-PowerSaving | WI | UE Power Saving in NR |  | CATT | Dec 19 | 29 | [21 empty] | 2 |  |  | 1 | 1 | 2 |  |  | 1 | 1 |  |  | 1 | 1 |  | 1 | 1.5 |  |  | 1 | 1 |  | 1 | 1.5 | 1 | 1 |  | 1 | 1.5 | [5 empty] | 1 | 1.5 | [5 empty] | 1 | 1.5 |  |  |  | 1 | 1.5
R1 | NR | FS_NR_POS | SI | Study on NR Positioning Support | RP-182155 | Intel | Mar 19 | 6 |  |  | 1 |  |  |  |  | 1 | 0.5 | [5 empty] | 2 | 0.5 | 1
R1 | NR | NR_POS | WI | NR Positioning Support |  | Intel | Dec 19 | 21 | [21 empty] | 2 | 1 |  |  |  | 2 | 1 | [5 empty] | 2 | 1 | 1 |  | 0.5 |  |  | 2 | 1 | 1 |  | 0.5 | 2 | 1 | 1 |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5
R1 | NR | FS_NR_L1enh_URLLC | SI | Study on physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-182089 | Huawei | Mar 19 | 5 |  |  | 1 |  |  |  |  | 2 | [6 empty] | 2
R1 | NR | FS_NR_L1enh_URLLC | WI | Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) |  | Huawei | Dec 19 | 22.25 | [21 empty] | 2 |  |  | 0.25 | 0.5 | 2 |  |  | 0.25 | 1 |  |  | 2 |  |  | 0.25 | 1.5 |  |  | 2 |  |  | 0.25 | 1.5 | 2 |  |  | 0.5 | 1 | [5 empty] | 0.25 | 1 | [5 empty] | 0.5 | 1.5 |  |  |  | 0.5 | 1.5
R1 | NR | FS_NR_RIM | SI | Study on remote interference management for NR | RP-181832 | CMCC | Dec 19 | 3 |  |  | 1 |  | 0.5 |  |  | 1 |  | 0.5
R1 | NR | NR_CLI_RIM-Core | WI | New WID on Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | RP-181652 | LG Electronics | Mar 19 | 3.75 | [14 empty] | 2 | [8 empty] | 1 |  | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25
R1 | NR | FS_IIIOT_CM | SI | SID on Channel Modeling for Indoor Industrial Scenarios | RP-182138 | Ericsson | Sept 19 | [22 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | [0.5]
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  | Dec 19 | 6 | [14 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
R2 | NR | FS_NR_IAB | SI | Study on Integrated Access and Backhaul for NR | RP-181349 | Qualcomm | Dec 18 | 8 |  |  | 1 | 2 | 1 |  |  | 1 | 2 | 1
0 | NR | NR_IAB | WI | Integrated Access and Backhaul for NR |  | Qualcomm | Dec 19 | 41 | [14 empty] | 1 | 2 | 1 |  | 1 |  |  | 1 | 3 | 1 | 0.5 | 1 | 1 | 3 | 1 | 1 | 1 |  |  | 1 | 3 | 1 | 1 | 1 |  |  | 1 | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | [6 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5
R2 | NR | FS_RACS_RAN | SI | Study on optimisations on UE radio capability signalling – NR/E-UTRA Aspects | RP-181459 | MediaTek | Mar 19 | 2.5 |  |  |  | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | 1
R2 | NR | RACS_RAN | WI | Optimisations on UE radio capability signalling – NR/E-UTRA Aspects |  | MediaTek | Dec 19 | 2.5 | [22 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5
R2 | NR | FS_NR_IIOT | SI | Study on NR Industrial IoT | RP-182090 | Nokia | Mar 19 | 7.5 |  |  |  | 0.5 | 1 |  |  |  | 1 | 2 | [5 empty] | 1 | 2
R2 | NR | NR_IIoT | WI | NR Industrial IoT |  | Nokia | Dec 19 | 30.25 | [22 empty] | 2 | 2 | 0 | 0 |  | 2 | 2 | 0 | 1 |  |  |  | 3 | 2 | 0.25 | 1 |  |  |  | 3 | 2 | 0.25 | 1 |  | 3 | 2 | 0.25 | 1 | [5 empty] | 0.25 | 0.5 | [5 empty] | 0.25 | 1 |  |  |  | 0 | 0.5
R2 | NR | NR_Mob_enh-Core | WI | Core part: NR mobility enhancements | RP-181433 | Intel | Dec 19 | 27 | [14 empty] | 1 | 1 |  |  | 1 |  |  | 1 | 2 |  |  | 1 | 1 | 2 | 1 |  | 1 |  |  | 1 | 2 | 1 |  | 1 |  |  | 1 | 2 | 1 |  | 1 | 1 | 2 | 1 |  | 1
R2 | NR | LTE_NR_DC_CA_enh-Core | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-182076 | Ericsson | Dec 19 | 32 | [14 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 |  |  | 1 | 2 |  | 1 | 1 |  |  | 1 | 2 |  | 1 | 1 | 1 | 2 |  | 1 | 1
RAN | NR, LTE | FS_5G_eval | SI | Study on Self Evaluation towards IMT-2020 Submission | RP-181318 | Huawei | Jun 18 | 0 |  |  |  | [0.5] |  |  |  |  | [0.5] | [6 empty] | [0.5] | [6 empty] | [0.5] |  |  |  |  | [0.5]
R3 | NR | LTE_NR_arch_evo-Core | WI | eNB(s) Architecture Evolution for E-UTRAN and NG-RAN | RP-181375 | China Unicom | Dec 19 | 6 |  |  |  |  | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
R3 | NR | FS_NR_NTN_solutions | SI | Study on solutions for NR to support Non Terrestrial Network (NTN) | RP-181598 | Thales | Dec 19 | 10.5 |  |  |  | 0.5 | 1 |  |  |  | 0.5 | 0.5 | [5 empty] | 0.5 | 1.5 |  |  |  |  | 1 | 0.5 |  |  |  | 1 | 0.5 | [5 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
R3 | NR, LTE | FS_LTE_NR_data_collect | SI | Study on RAN-centric Data Collection and Utilization for NR | RP-182105 | CMCC | Jun 19 | 7.5 |  |  |  |  | 0.5 | [10 empty] | 0.5 | 2 | [5 empty] | 0.5 | 2 |  |  |  | 0.5 | 1.5
R3 | NR | ??? | WI | RAN-centric Data Collection and Utilization for NR |  | CMCC | Dec 19 | 9 | [34 empty] | 1 | 2 | [5 empty] | 1 | 2 |  |  |  | 1 | 2
R4 | NR | FS_NR_test_methods | SI | Study on test methods for New Radio | RP-180546 | Intel | Dec 18 | 1 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_MIMO_OTA_TestMethod | SI | Study on radiated metrics and test methodology for the verification of multi-antenna reception performance of NR Ues | RP-181402 | CATR, OPPO, Samsung | Dec. 19 | 8 | [5 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 2
R4 | NR | NR_2RX_V-UE | SI | Evaluation for 2 RX exception in Rel-15 vehicle mounted UE | RP-181990 | SAMSUNG | Dec 18 | 1.5 | [5 empty] | 1 |  |  |  |  | 0.5
R4 | NR, LTE | LTE_B41_NR_n41_PCx | WI | New WID on 29dBm UE Power Class for B41 and n41 | RP-181655 | Sprint | Jun 19 | 1.75 | [5 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25 | [6 empty] | 0.25 | 0.25 |  |  |  | 0.25 | 0.25
R4 | NR | n65_NR_newRAT | WI | New WID on Band 65 for New Radio for Region 1 | RP-181844 | DISH Network | Dec 18 | 0.55 | [5 empty] | 0.25 |  |  |  |  | 0.25 |  |  | 0.05
R4 | NR | EN-DC Basket WIs-Core & Perf | WI | New WID on EN-DC for 2 bands DL with 2 bands UL (1 LTE band + 1 NR band) New WID on EN-DC for 3 bands DL with 2 bands UL (2 LTE bands + 1 NR band) New WID on EN-DC for 4 bands DL with 2 bands UL (3 LTE bands + 1 NR band) New WID on EN-DC for 5 bands DL with 2 bands UL (4 LTE bands + 1 NR band) New WID on EN-DC for 6 bands DL with 2 bands UL (5 LTE bands + 1 NR band) , New WID on EN-DC of LTE CA for up to 4 bands DL with 1 band UL + NR CA for 2 bands DL with 1 band UL New WID on SA NR Supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) New WID: Basket Rel-16 WID NR Intra-band CA New WID: Basket Rel-16 WID NR inter-band CA/DC for 2 DL bands with up to 2 UL bands | RP-181549 RP-181885 RP-181855 RP-181550 RP-181834 RP-180997 RP-181730 RP-181736 RP-181857 | NTT DOCOMO, etc | Dec 19 | 24 | [5 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3
|  |  |  | Last row in NR totals. Insert new NR items above this line. Do not remove |  |  |  | 0
|  |  |  | First row inLTE totals. Insert new LTE below this line. Do not remove |  |  |  | 0
R1 | LTE | LTE_eMTC5-Core | WI | Core part: Additional MTC enhancements for LTE | RP-181878 | Ericsson | Dec 19 | 48 |  |  | 2 | 2 |  |  |  | 3 | 2 | [5 empty] | 3 | 2 | 0.5 | 0.5 | 0.5 |  |  | 3 | 2 | 0.5 | 0.5 | 0.5 | 3 | 2 | 0.5 | 0.5 | 0.5 |  |  | 3 | 2 | 0.5 | 0.5 | 0.5 |  |  | 3 | 2 | 0.5 | 0.5 | 0.5 | 3 | 2 | 0.5 | 0.5 | 0.5
R4 | LTE | LTE_eMTC5-Perf | WI | Perf part: Additional MTC enhancements for LTE | RP-181878 | Ericsson | Jun. 20 | 4 | [48 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
R1 | LTE | NB_IOTenh3-Core | WI | Core part: Additional enhancements for NB-IoT | RP-181674 | Huawei | Dec 19 | 53.5 |  |  | 2 | 2 |  |  |  | 3 | 2 | [5 empty] | 3 | 2 | 0.5 | 0.5 | 0.5 |  |  | 3 | 2 | 0.5 | 0.5 | 0.5 | 4 | 2 | 0.5 | 0.5 | 0.5 |  |  | 4 | 2 | 1 | 0.5 | 0.5 |  |  | 4 | 2 | 1 | 0.5 | 0.5 | 4 | 2 | 1 | 0.5 | 0.5
R4 | LTE | NB_IOTenh3-Perf | WI | Perf part: Additional enhancements for NB-IoT | RP-181674 | Huawei | Jun. 20 | 4 | [48 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
R1 | LTE | FS_LTE_terr_bcast | SI | Study on LTE-based 5G terrestrial broadcast | RP-181706 | Qualcomm | Mar 19 | 3 |  |  | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | LTE | FS_LTE_terr_bcast | WI | LTE-based 5G Terrestrial Broadcast |  | Qualcomm | Dec 19 | 9 | [21 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  | 0.5 | 0 | 1 |  |  | 0.5 | 0.5 | [5 empty] | 0 | 0.5 | [5 empty] | 0 | 1 |  |  |  | 0 | 1
R1 | LTE | LTE_DL_MIMO_EE-Core | WI | Core part: DL MIMO efficiency enhancements for LTE | RP-181485 | Huawei | Dec 19 | 10.25 |  |  | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  | 0.25 |  | 1 |  |  | 0.5 |  |  |  | 1 |  |  | 0.5 |  |  |  | 1 | 0.5 |  |  |  | 1 | 0.5
R4 | LTE | LTE_DL-MIMO_EE-Perf | WI | Perf. part: DL MIMO efficiency enhancements for LTE | RP-181485 | Huawei | Dec 19 | 2 | [30 empty] | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5
R1 | LTE | LTE_sTTIandPT-Core | WI | Core part: Shortened TTI and processing time for LTE | RP-171468 | Ericsson | Sep.17 | 0
R4 | LTE | LTE_sTTIandPT-Perf | WI | Perf. part: Shortened TTI and processing time for LTE | RP-171468 | Ericsson | Sep 18 | 0
R1 | LTE | LTE_eMTC4-Core | WI | Core part: Even further enhanced MTC for LTC | RP-172811 | Ericsson | Dec 18 | 1 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | LTE | LTE_eMTC4-Perf | WI | Perf part: Even further enhanced MTC for LTC | RP-172811 | Ericsson | Dec. 18 | 2.75 | [5 empty] | 0.5 | 1 |  |  |  | 0.25 | 1
R1 | LTE | NB_IOTenh2-Core | WI | Core part: Further NB-IoT enhancements | RP-182114 | Huawei | Sep 18 | 0
R4 | LTE | NB_IOTenh2-Perf | WI | Perf part: Further NB-IoT enhancements | RP-171428 | Huawei | Dec.18 | 4 | [5 empty] | 1 | 1 |  |  |  | 1 | 1
R1 | LTE | LTE_unlic-Core | WI | Core part: Enhancements to LTE operation in unlicensed spectrum | RP-172841 | Nokia | Jun 2018 | 0
R4 | LTE | LTE_unlic-Perf | WI | Performance part: Enhancements to LTE operation in unlicensed spectrum | RP-170848 | Nokia | Dec 2018 | 3 | [5 empty] | 0.5 | 1 |  |  |  | 0.5 | 1
R1 | LTE | LTE_1024QAM_DL-Core | WI | Core part: High capacity stationary wireless link for LTE | RP-181670 | Huawei | June 18 | 0
R4 | LTE | LTE_1024QAM_DL-Perf | WI | Perf. part: High capacity stationary wireless link for LTE | RP-171738 | Huawei | Dec 18 | 1 | [6 empty] | 0.5 |  |  |  |  | 0.5
R1 | LTE | LTE_eV2X-Core | WI | Core part: Cellular V2X Phase 2 | RP-171740 | Huawei, CATT, LGE | June 18 | 0
R4 | LTE | LTE_eV2X-Perf | WI | Perf. part: Cellular V2X Phase 2 | RP-171740 | Huawei, CATT, LGE | Dec 18 | 3 | [6 empty] | 1.5 |  |  |  |  | 1.5
R1 | LTE | LTE_HRLLC-Core | WI | Core part: Highly Reliable Low Latency Communication for LTE | RP-172845 | Ericsson | Jun 2018 | 0
R4 | LTE | LTE_HRLLC-Perf | WI | Perf part: Highly Reliable Low Latency Communication for LTE | RP-171489 | Ericsson | Dec 2018 | 2 | [5 empty] | 0.5 | 1 |  |  |  | 0.5 | 1
R2 | LTE | LTE_5GCN_connect-Core | WI | LTE connectivity to NGC | RP-180064 | Huawei | Jun 18 | 0
R4 | LTE | LTE_5GCN_connect-Core | WI | LTE connectivity to NGC | RP-180064 | Huawei | Jun 18 | 1 | [6 empty] | 0.5 |  |  |  |  | 0.5
R2 | LTE | LTE_ViLTE_enh2-Core | WI | New WID on Further enhancements on Voice and Video for LTE | RP-177276 | CMCC | Dec 17 | 0
R2 | LTE | LCS_LTE_acc_enh-Core | WI | UE Positioning Accuracy Enhancements for LTE (Core Part) | RP-172313 | Nokia | 2018-06-01 | 0
R4 | LTE | LCS_LTE_acc_enh-Perf | WI | UE Positioning Accuracy Enhancements for LTE (Performance Part) | RP-172313 | Nokia | 2018-06-01 | 0
R2 | LTE | LTE_QMC_Streaming-Core | WI | Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN | RP-170956 | China Unicom | Dec 17 | 0
R2 | LTE | LTE_euCA-Core | WI | Core part: Enhancing CA Utilization | RP-180561 | Nokia | Sep 18 | 0 | `
R4 | LTE | LTE_euCA-Perf | WI | Perf. part: Enhancing CA Utilization | RP-180561 | Nokia | Dec 18 | 1.5 | [6 empty] | 0.5 |  |  |  |  | 1
R2 | LTE | LTE_UDC_Core | WI | UL data compression in LTE | RP-172365 | CATT | Mar 18 | 0
R2 | LTE | LTE_Aerial-Core | WI | WID on Enhanced LTE Support for Aerial Vehicles | RP-172826 | Ericsson | Jun-18 | 0
R2 | LTE | LTE_MDT_BT_WLAN-Core | WI | Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT) | RP-180306 | CMCC | Jun-18 | 0
R2 | LTE | LTE_INOBEAR-Core | WI | Increased number of E-UTRAN data bearers | RP-180569 | Samsung | June 18 | 0
R2 | LTE | LTE_feMob-Core | WI | Core Part: Even further Mobility enhancement in E-UTRAN | RP-181544 | China Telecom | Dec 19 | 13.5 |  |  |  | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | 1 | [5 empty] | 1 | 1 |  | 0.5 |  |  |  | 1 | 1 |  | 0.5 |  | 1 | 1 |  | 0.5
R4 | LTE | LTE_feMob-Perf | WI | Per Part: Even further Mobility enhancement in E-UTRAN | RP-181475 | China Telecom | Dec 19 | 1.5 | [37 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5
R4 | LTE | LTE_NWCRSIM | WI | Perf. Part: UE requirements for network-based CRS mitigation for LTE | RP-171408 | Ericsson | December 2018 | 2 | [6 empty] | 1 |  |  |  |  | 1
R4 | LTE | LTE_8Rx_AP_DL-Perf | WI | UE requirements for LTE DL 8Rx antenna ports | RP-172458 | Huawei | 2018-12-18 | 1 | [6 empty] | 0.5 |  |  |  |  | 0.5
R4 | LTE | LTE_CA_R15_>5DL1UL-Perf | WI | Perf. part: LTE Advanced inter-band CA Rel-15 for more than 5DL and 1UL | RP-180250 | Qualcomm Incorporated | Dec. 2018 | [7 empty] | 0.1 |  |  |  |  | 0.1 | [6 empty] | 0.1
R4 | LTE | LTE_high_speed_enh2-Core | WI | Core part: Further performance enhancement for LTE in high speed scenario | RP-181478 | NTT DOCOMO | Dec 19 | 2.5 | [18 empty] | 1 | [6 empty] | 0.5 |  | 0.25 |  |  | 0.5 |  |  |  | 0.25
R4 | LTE | LTE_high_speed_enh2-Perf | WI | Perf part: Further performance enhancement for LTE in high speed scenario | RP-181478 | NTT DOCOMO | Dec 19 | 7 | [18 empty] | 0.5 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1.5 | [6 empty] | 1.5 |  |  |  |  | 1.5
R4 | LTE | LTE CA basket WIs | WI | New WID: Basket WI for LTE Intra-band CA New WID on Rel16 LTE inter-band CA for 2 bands DL with 1 band UL New WID on Rel16 LTE inter-band CA for 2 bands DL with 1 band UL New WID: LTE Advanced inter-band CA Rel-16 for 3DL/1UL New WI: Rel16 LTE inter-band CA for 4 or 5 bands DL with 1 band UL New WID: LTE Advanced inter-band CA Rel-16 for 2DL/2UL New WID on Rel16 LTE inter-band CA for x bands DL with 2 bands UL with x=3, 4, 5 | RP-181548 RP-181930 RP-181851 RP-181887 RP-181853 RP-181733 RP-181824 RP-181825 | Ericsson, etc. | 2018-12-19 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
|  |  |  | Last row in LTE totals. Insert new LTE items above this line. Do not remove |  |  |  | 0
|  |  |  | First row in UMTS totals. Insert new UMTS items below this line. Do not remove. |  |  |  | 0
|  |  |  | Last row in UMTS totals. Insert new UMTS items above this line. Do not remove |  |  |  | 0
|  |  |  | First row in GERAN totals. Insert new GERAN items below this line. Do not remove |  |  |  | 0
R6 | GERAN | CIoT_EC_GSM_fenh-Core | WI | Further Enhanced Extended Coverage GSM for support of Cellular Internet of Things (EC-GSM-IoT) - Core aspects | RP-180541 | Nokia | Sep.18 | 0 | WI completed at RAN #81
R6 | GERAN | CIoT_EC_GSM_fenh-Perf | WI | Further Enhanced Extended Coverage GSM for support of Cellular Internet of Things (EC-GSM-IoT) - Perf aspects | RP-180541 | Nokia | Sep.18 | 0 | WI completed at RAN #81
|  |  |  | Last row in GERAN totals. Insert new GERAN items above this line. Do not remove |  |  |  | 0
| NR |  |  | allocated above | [6 empty] | 21 | 12.5 | 12 | 25.5 | 11 | 21 | 13.5 | 12 | 25 | 11 |  |  | 21 | 17.5 | 10.5 | 8.25 | 6 |  |  | 21.25 | 18 | 7.5 | 8.75 | 7 | 21.25 | 17.5 | 7.5 | 8.75 | 8.5 |  |  | 20 | 18.5 | 9 | 8.75 | 10.75 |  |  | 20 | 21 | 9 | 8.75 | 11.5 | 20 | 21.5 | 9 | 10.25 | 10.5 |  |  | 0 | 0 | 0 | 1.75 | 8 |  |  | 0 | 0 | 0 | 2.25 | 10 | 0 | 0 | 0 | 2 | 9.5
| NR |  |  | Legacy | [7 empty] | 12 |  |  |  |  | 12 | [6 empty] | 10 | [6 empty] | 9 |  |  |  |  | 8 | [6 empty] | 6 | [6 empty] | 4 |  |  |  |  | 4 | [6 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0
| NR |  |  | TEI and other not planned issues | [38 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 0 | [6 empty] | 0 |  |  |  |  | 0
| NR |  |  | Reserve
| NR |  |  | total used capacity | [6 empty] | 21 | 24.5 | 12 | 25.5 | 11 | 21 | 25.5 | 12 | 25 | 11 |  |  | 21 | 27.5 | 10.5 | 8.25 | 6 |  |  | 21.25 | 27 | 7.5 | 8.75 | 7 | 21.25 | 25.5 | 7.5 | 8.75 | 8.5 |  |  | 20 | 25.5 | 9 | 8.75 | 10.75 |  |  | 20 | 26 | 9 | 8.75 | 11.5 | 20 | 26.5 | 9 | 10.25 | 10.5 |  |  | #REF! | 0 | 0 | 1.75 | 8 |  |  | #REF! | 0 | 0 | 2.25 | 10 | #REF! | 0 | 0 | 2 | 9.5
| NR |  |  | available capacity | [6 empty] | 21 | 23 | 7 | 24 | 10 | 21 | 23 | 7 | 24 | 10 |  |  | 21 | 23 | 7 | 24 | 10 |  |  | 21 | 23 | 7 | 24 | 10 | 21 | 23 | 7 | 24 | 10 |  |  | 21 | 23 | 7 | 24 | 10 |  |  | 21 | 23 | 7 | 24 | 10 | 21 | 23 | 7 | 24 | 10 |  |  | 21 | 23 | 7 | 24 | 10 |  |  | 21 | 23 | 7 | 24 | 10 | 21 | 23 | 7 | 24 | 10
| NR |  |  | remaining/exceeded capacity | [6 empty] | 0 | -1.5 | -5 | -1.5 | -1 | 0 | -2.5 | -5 | -1 | -1 |  |  | 0 | -4.5 | -3.5 | 15.75 | 4 |  |  | -0.25 | -4 | -0.5 | 15.25 | 3 | -0.25 | -2.5 | -0.5 | 15.25 | 1.5 |  |  | 1 | -2.5 | -2 | 15.25 | -0.75 |  |  | 1 | -3 | -2 | 15.25 | -1.5 | 1 | -3.5 | -2 | 13.75 | -0.5 |  |  | #REF! | 23 | 7 | 22.25 | 2 |  |  | #REF! | 23 | 7 | 21.75 | 0 | #REF! | 23 | 7 | 22 | 0.5
| LTE |  |  | allocated above | [6 empty] | 6 | 5 | 0 | 3.5 | 8.6 | 8 | 5 | 0 | 3.25 | 9.1 |  |  | 8 | 5 | 1 | 2 | 2.6 |  |  | #REF! | 5 | 1 | 2.25 | 2.5 | 9 | 5.25 | 2 | 2.5 | 3 |  |  | 9 | 5.25 | 2.5 | 2.5 | 4 |  |  | 9 | 5.5 | 2.5 | 2.5 | 4 | 9 | 5.5 | 2.5 | 3.5 | 5.5 |  |  | 0 | 0 | 0 | 1 | 1.5 |  |  | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 1 | 2
| LTE |  |  | Legacy | [6 empty] | 4 | 8 | 3 | 1 | 1 | 2 | 8 | 3 | 1 | 1 |  |  | 1 | 6 | 3 |  |  |  |  | 1 | 5 | 3 |  |  |  | 5 | 3 | [5 empty] | 4 | 3 | [5 empty] | 4 | 3 |  |  |  | 4 | 3 | [5 empty] | 0 | 3 | [5 empty] | 0 | 3 |  |  |  | 0 | 3
| LTE |  |  | TEI and other not planned issues | [8 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  | 1 | 1 | [5 empty] | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 | 1 | [5 empty] | 0 | 1 | [5 empty] | 0 | 1 |  |  |  | 0 | 1
| LTE |  |  | Reserve | [8 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3
| LTE |  |  | total used capcaity | [6 empty] | 10 | 13 | 7 | 4.5 | 9.6 | 10 | 13 | 7 | 4.25 | 10.1 |  |  | 10 | 11 | 8 | 2 | 2.6 |  |  | #REF! | 10 | 8 | 2.25 | 2.5 | 10 | 11.25 | 9 | 2.5 | 3 |  |  | 10 | 10.25 | 9.5 | 2.5 | 4 |  |  | 10 | 10.5 | 9.5 | 2.5 | 4 | 10 | 10.5 | 9.5 | 3.5 | 5.5 |  |  | 0 | 0 | 7 | 1 | 1.5 |  |  | 0 | 0 | 7 | 1 | 2 | 0 | 0 | 7 | 1 | 2
| LTE |  |  | available capacity | [6 empty] | 10 | 15 | 12 | 6 | 5 | 10 | 15 | 12 | 6 | 5 |  |  | 10 | 15 | 12 | 6 | 5 |  |  | 10 | 15 | 12 | 6 | 5 | 10 | 15 | 12 | 6 | 5 |  |  | 10 | 15 | 12 | 6 | 5 |  |  | 10 | 15 | 12 | 6 | 5 | 10 | 15 | 12 | 6 | 5 |  |  | 10 | 15 | 12 | 6 | 5 |  |  | 10 | 15 | 12 | 6 | 5 | 10 | 15 | 12 | 6 | 5
| LTE |  |  | remaining/exceeded capacity | [6 empty] | 0 | 2 | 5 | 1.5 | -4.6 | 0 | 2 | 5 | 1.75 | -5.1 |  |  | 0 | 4 | 4 | 4 | 2.4 |  |  | #REF! | 5 | 4 | 3.75 | 2.5 | 0 | 3.75 | 3 | 3.5 | 2 |  |  | 0 | 4.75 | 2.5 | 3.5 | 1 |  |  | 0 | 4.5 | 2.5 | 3.5 | 1 | 0 | 4.5 | 2.5 | 2.5 | -0.5 |  |  | 10 | 15 | 5 | 5 | 3.5 |  |  | 10 | 15 | 5 | 5 | 3 | 10 | 15 | 5 | 5 | 3
| UTRA |  |  | allocated above | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UTRAN |  |  | Legacy | [16 empty] | 0.1
| UTRAN |  |  | TEI and other not planned issues | [16 empty] | 0.5
| UTRAN |  |  | Reserve | [16 empty] | 0.1
| UTRAN |  |  | total used capacity | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UTRAN |  |  | available capacity | [16 empty] | 0.7
| UTRAN |  |  | remaining/exceeded capacity | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GERAN |  |  | allocated above | [16 empty] | 0 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0
| GERAN |  |  | Legacy | [16 empty] | 0.2
| GERAN |  |  | TEI and other not planned issues | [16 empty] | 0.5
| GERAN |  |  | Reserve | [16 empty] | 0.1
| GERAN |  |  | total used capacity | [16 empty] | 0.8 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0
| GERAN |  |  | available capacity | [16 empty] | 0.8
| GERAN |  |  | remaining/exceeded capacity | [16 empty] | 0 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0 | [11 empty] | 0
R3 |  |  |  | RAN3 overall Status | [8 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0.5 | [6 empty] | 3.5 |  |  |  |  | 2.5 | [6 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 12 | [6 empty] | 12 |  |  |  |  | 12