## Slide 1
RAN4 Chairman: Xutao Zhou
RAN4 Vice Chairman: Xizeng Dai
RAN4 Vice Chairman: Hiromasa Umeda
RAN4 Secretary: Kyoungseok Oh
Status Report RAN WG4 to TSG-RAN #83
3GPP TSG RAN #83 RP-190011
Shenzhen, CN, 18 – 21 March, 2019

## Slide 2: Executive Summary – Rel-15 NR
Remaining core requirements maintenance are mainly for UE RF and RRM which still consume most of RAN4 meeting time
  System parameters and BS RF are quite stable
Performance work is in good shape but there are still a large amount of TBD in the specifications due to
  Lack of simulation results for Demod and CSI
  Large span of submitted results from companies for Demod and CSI
  Uncompleted RRM test cases in phase III and IV
  FFS for some test parameters
Late drop is progressing based on RAN approved schedule, i.e., targeting for core part completion @ June 2019, RAN #84
=> Exception sheet to be updated by capturing the latest progress in RAN #83. One quarter extension for remaining issues for core. Performance part including late drop can be maintained as Dec 2019 and performance part except late drop is expected to be completed by June 2019.

## Slide 3: Executive Summary – Rel-16 NR
Good progress in Rel-16 NR WI/SI for both spectrum and non-spectrum.
  First RAN4 meeting for NR-U, CLI/RIM, NR Mob Enh, High power UE for FDD band SI, 7-24GHz SI, NR V2X SI
  For other WG led Rel-16 items, If RAN4 impact is identified and no RAN4 TU for 2019 Q2/Q3 was requested before, early request for RAN4 TU are encouraged
  For spectrum related items including basket items, due to postpone of Rel-16 NR spec (as below bullets), only draft CRs were endorsed in Q1
Rel-16 NR specifications
  Based on RAN4 agreements in R4-1902215, RAN4 will introduce REL-16 38 series TSs in June 2019 according to the process described in R4-1900047
  A press release to be published on www.3gpp.org after RAN #83 describing which work on which bands and band combinations were completed up to Q1/2019 for REL-16

## Slide 4: Executive Summary – LTE
LTE maintenance up to Rel-15 and Rel-15 performance
  All remaining Rel-15 LTE WIs performance part are completed, i.e., sTTI, NB-IoTenh2, LTE-euCA and 8Rx
Rel-16 LTE
  Good progress in Rel-16 LTE items including spectrum and non-spectrum items

## Slide 5: Statistics
Meeting | Date | Location | Host | Delegates registered/attendees | Documents requested/uploaded
RAN4 #90 | 25th Feb – 1st Mar 2019 | Athens, GR | EF3 | 420/372 | 2712/2584
Chart: 
| AH 1801 | #86 | #86bis | #87 | AH 1807 | #88 | #88bis | #89 | #90
Delegates | 143 | 232 | 194 | 232 | 107 | 280 | 235 | 279 | 372
Chart: 
| AH 1801 | #86 | #86bis | #87 | AH 1807 | #88 | #88bis | #89 | #90
Contributions | 1256 | 2085 | 2341 | 2318 | 956 | 2185 | 2201 | 2292 | 2584

## Slide 6: Status of ongoing WI/SI
WI/SI to be completed – Rel-15 LTE WI perf part
  sTTI - Perf
  Further NB-IoT enhancements – Perf
  Enhancing LTE CA Utilization – Perf
  8Rx - Perf

## Slide 7: NR specifications
CR packs including the CR for Rel-15 NR specifications agreed by RAN4
  R4-1902690 CR to TS38.133 in CR pack RP-190403 will be revised by company CR (RP-190569) for correcting the section numbering
Big CRs approach will be continually used in Q2 2019
RP‑190399 | RAN4 CRs to NR Access Technology part 1
RP‑190400 | RAN4 CRs to NR Access Technology part 2
RP‑190401 | RAN4 CRs to NR Access Technology part 3
RP‑190402 | RAN4 CRs to NR Access Technology part 4
RP‑190403 | RAN4 CRs to NR Access Technology part 5

## Slide 8: Rel-15 NR – Tasked by RAN
Beam correspondence
  Based on RAN WF (RP-182879), RAN4 discussed the beam correspondence requirements and test procedure in Q1.
  Draft CR to 38.101-2 on core requirements (R4-1902590) and draft CR to TR 38.810 on test procedure (R4-1902683) were endorsed
  Based on approved WF (R4-1902684), RAN4 is going to further discuss the beam correspondence tolerance requirements in Q2 2019.
FR1 range extension
  As tasked by RAN #82, RAN4 agreed CRs to RAN4 NR spec for FR1 extension.
  In addition to the extension from 6GHz to 7.125GHz, lower bound of FR1 is agreed to be 410MHz to accommodate NR re-farming of the new LTE bands at 410 – 430 MHz.
  Detailed summary can be found in response LS to RAN in RP-190055.

## Slide 9: Rel-15 NR – Rel-15 Scope
In order to better clarify the Rel-15 NR scope, WF for UE RF, RRM and Demod/CSI were approved in RAN4 #90
  In general, for core requirements, no new items will be added besides the items listed in the exception sheet for Rel-15 NR
  For performance part, new requirements which was not discussed in previous RAN4 meetings, shall NOT be introduced in Rel-15.
  Detailed scope for Rel-15 can be found in WFs:
    UE RF (R4-1902216)
    RRM (R4-1902032)
    UE Demod/CSI (R4-1902403)
    BS Demod (agreed scope captured in chairman note as below)
      No new BS demodulation requirement, which was not discussed in the previous meetings, should be introduced in Rel-15.
      Whether to introduce the NR BS demodulation requirements for HST scenario will be discussed in RAN4#90bis.

## Slide 10: Rel-15 NR – Feature List
Updated UE feature list was also discussed in Q1. Latest updated UE feature list was approved in RAN4. The major updates are
  Maximum uplink duty cycle for FR2 PC3
  PA architecture for intra-band EN-DC and intra-band UL CA
Further discussion on UE power class capability is expected to be discussed in RAN #83

## Slide 11: Rel-15 NR – Late drop
RAN4 late drop discussion resumed in Q1.
Most of RF requirements for both NE-DC and NR-DC have been completed except
  Power control for NE-DC
Around 80% RRM core requirements for late drop were completed. The remaining issues:
  Gap sharing mechanism, which will impact CSSF for RRM measurement requirements
  Part of requirements of MTTD/MRTD, BWP switching interruption for NE-DC, and the requirements interruption and NR PSCell addition and release delay for NR-DC
RAN4 is planning to complete late drop core requirements and performance requirements according to shcedule approved by RAN in RP-182790, i.e.,
  RAN4
    Target for Rel-15 NR WI core part completion: RAN#84, June2019
    Target for Rel-15 NR WI performance part completion: RAN#86, Dec 2019

## Slide 12: Rel-15 NR – Other spec impact due to NR
UTRA FDD specifications
  RAN4 agreed the CR to UTRA FDD specification in Rel-15 due to introduction of NR in RAN4 #90
  If no strong need is identified, it is proposed to NOT continually maintain UTRA FDD specifications for new NR bands. Guideline on further maintenance of UTRA FDD specifications in Rel-16 for new NR bands is required from RAN #83.
LTE BS specification for AAS, eAAS and MSR maintenance/clean-up for NR introdcuation were discussed. Continue activities are expected in future RAN4 meetings

## Slide 13: Status of R15 NSA&SA RRM and demod after Q1 2019
The overall completion level:
  R15 NSA&SA RRM core: 94% completion
    Quite a number of open issues were identified after Q4 2018 and added in the exception, e.g., UE timing requirements due to beam switching (revisiting existing requirements), Scell activation with multiple TCI states.
  R15 NSA&SA RRM perf: 80% completion
    No final agreement on OTA-related test parameters/test method (AoA setup, Antenna gain, etc), which impacts all the FR2 related test cases
    8 more test cases were agreed to be introduced in Q2 2019
    Some test cases depend on the conclusions for core requirements
  R15 NSA&SA UE demod: 92% completion
  R15 BS demod: 80% completion
  NOTE：the detailed analysis and remaining issues are provided in the attached excel file)

## Slide 14: Rel-16 NR – WI (1/2)
NR-U
  First meeting in RAN4. Work plan was approved
  Response LS to RAN1 on wideband operation was approved
  For NR-U bands, band n46 is confirmed to be used to discuss the band specific requirements. FFS for whether to introduce sub-band for band n46 as LTE
  FFS for 6GHz band plan.
  Spectrum utilization for 20MHz BW with 15KHz SCS and 30KHz SCS was agreed
  Agreement for NR-U BS RF was made.
CLI/RIM
  First meeting in RAN4. Work plan was approved
  Co-existence scenario and simulation assumption for CLI were approved
  TR will be required for CLI/RIM WI in RAN #83
NR Mobility enhancement
  First meeting in RAN4
  Initial agreement on handover for simultaneous connectivity, make-before-break and RACH-less was made

## Slide 15: Rel-16 NR –WI (2/2)
Spectrum-related
  Spectrum-related WIs including basket WIs were going well in Q1.
  CR handling process for Rel-16 spectrum related WIs can be found in R4-1900047 for Q2.
  Completion timeline for some spectrum related items are postponed considering the agreements on Rel-16 NR specifications, e.g., Band n65
  Band n41 for LTE/NR spectrum sharing
    NBC issue was identified for introducing 100KHz raster. Further discussion in RAN4 is needed

## Slide 16: Rel-16 NR – SI (1/2)
Testability
  Further discussion/decision on the clarification on polarization setting for test system and DUT is needed in future meetings based on the agreement of no change on core and measurement grid
  Antenna gain difference assumption for deriving RRM test case side condition were continually discussed. Most of antenna gain difference assumption requires more discussions in future RAN4 meetings
  CR on test methods for Demod was agreed
MIMO OTA
  Most of agreements for MIMO OTA SI were captured in WF R4-1901383.
  Further study on the channel model for NR MIMO OTA is required.
  RAN4 also agreed to introduce NR ATF measurement in Rel-16.

## Slide 17: Rel-16 NR – SI (2/2)
High power UE for EN-DC with FDD band
  First meeting in RAN4. Work plan and TR skeleton were approved
  Most of agreements were captured in WF R4-1902452
Study on 7-24GHz
  First meeting in RAN4. Work plan was approved
  Draft skeleton was technically endorsed given TR was not requested in SID.
  TR will be requested in RAN #83
NR V2X
  Discussions were focusing on RF parameters, transient period and IBE model
  Response LS for transient period was approved

## Slide 18: Up to Rel-15 LTE
Multi-carrier operation for LAA
  RAN4 concluded multi-carrier operation in band 46.
  A set of CRs to RAN4 spec have been agreed in RAN4.
  LS with information of RAN4 decision and also action items for RAN2 (suggested changes for 36.300) was approved in RP-190043
TEI15 and Rel-15 perf part
  eMTC4 - Applicability for non-BL UEs in Rel-15 needs further discussions in RAN #83
  All the Rel-15 LTE items perf part have been completed

## Slide 19: Rel-16 LTE
eMTC5 and NB-IOTenh3
  Co-existence with NR for both eMTC and NB-IoT were discussed in Q1 in eMTC5 and NB-IOTenh3 WI respectively.
  Time plan for co-existence was concluded in RAN4, i.e.,
    Co-existing work for R15 start firstly
    Co-exsting work for R16 start secondly after RAN1 R16 co-existing enhance feature finalized
  How to proceed co-existing work for Rel-15 NR requires RAN guideline in RAN #83
Even furtehr mobility enhancement for LTE
  LS on interruption time during mobility was approved
High speed for LTE
  First meeting in RAN4. Work plan was approved
  Agreements are captured in the WF for RRM and UE/BS Demod for HST

## Slide 20: Rel-16 Basket WI Status
Rel-16 NR Basket WI Status Report
Above revised WIDs have been endorsed by RAN4
WI Title | Status Report | Revised WID
NR intra-band CA | RP-190155 | RP-190158
EN-DC for 2 bands DL with 2 bands UL (1 LTE band + 1 NR band) | RP-190313 | RP-190312
EN-DC for 3 bands DL with 2 bands UL (2 LTE bands + 1 NR band) | RP-190379 | RP-190379
EN-DC for 4 bands DL with 2 bands UL (3 LTE bands + 1 NR band) | RP-190156 | RP-190159
EN-DC for 5 bands DL with 2 bands UL (4 LTE bands + 1 NR band) | RP-190293 | RP-190294
EN-DC for 6 bands DL with 2 bands UL (5 LTE bands + 1 NR band) | RP-190223 | N/A
Inter-band CA/DC for 2 bands DL with up to 2 bands UL | RP-190493 | RP-190494
EN-DC of LTE inter-band CA for up to 4 bands DL with 1 band UL + NR inter-band CA for 1 band DL with 1 band UL | RP-190153 | RP-190151
SA SUL, NSA SUL, NSA SUL with ULSUP | RP-190380 | RP-190381

## Slide 21: Rel-16 Basket WI Status
Rel-16 LTE Basket WI Status Report
CR pack for LTE basket in RP-190409
Above revised WIDs have been endorsed by RAN4
WI Title | Status Report | Revised WID
LTE intra-band CA | RP-190154 | RP-190157
LTE inter-band CA for 2 bands DL with 1 band UL | RP-190499 | RP-190500
LTE inter-band CA for 3 bands DL with 1 band UL | RP-190374 | RP-190375
LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL | RP-190139 | RP-190138
LTE inter-band CA for 2 bands DL with 2 band UL | RP-190376 | RP-190377
LTE inter-band Carrier Aggregation for x bands DL with 2 bands UL | RP-190152 | RP-190150
Additional LTE bands for UE category M1 and/or NB1 | RP-190334 | RP-190332
Additional LTE bands for UE category M2 and/or NB2 | RP-190335 | RP-190333

## Slide 22: new WI/SI proposals
  Spectrum proposal for NR (13)
  WI: Introduction of n14 (Ericsson)
  WI: Introduction of n30 (Ericsson)
  WI: Introduction of n259 (Ericson)
  WI: NR inter-band CA/DC for 3 bands DL with x (x=1,2) bands UL (CATT)
  WI: Introduction of 1900MHz SUL band (Huawei)
  WI: Introduction of SUL band with same uplink frequency range of n5 (Huawei)
  WI: Addition of new wider BW in band n77 and n78 (Huawei )
  WI: Addition of new wider BW in band n38 (Huawei )
  WI: Add PC5 for FR2 (Huawei)
  WI: SUL usage for FR2 spectrum (Apple)
  WI: Generic requirements for NR FR1 UL intra-band continuous CA (China Telecom)
  WI: Intra-band non-contiguous CA RF requirements (Huawei)
  SI: Study on new NR bands 6.425GHz – 7.125GHz (Huawei)
  Non-spectrum proposal for NR (9)
  WI: NR requirement work continuation in Rel-16 (Nokia)
  WI: NR RRM requirements enhancement (ZTE)
  WI: NR measurement gap enhancement (Intel)
  WI: NR performance requirement enhancement (China Telecom)
  WI: NR DL 256QAM for FR2 (China Telecom)
  WI: NR support for high speed train scenario (CMCC)
  WI: CSI-RS based L3 measurement requirements (Huawei)
  WI: NR RRM requirement improvement (CATT)
  SI: Study on NR and NB-IoT/eMTC co-existence (Huawei)
Spectrum proposal for LTE (2)
  LTE-LAA based access in 6GHz spectrum (Ericsson)
  PC2 UE for LTE bands 31 and 72 (Nokia)
Multi-RAT (1)
  Introduction of GSM, UTRA, E-UTRAN and NR CS(s) to the MSR specifications (Ericsson)
  Rel-15 Leftover issues
  WI: NR requirement work continuation in Rel-16 (Nokia)
  WI: NR RRM requirements enhancement (ZTE)
  WI: NR performance requirement enhancement (CTC)
  WI: NR DL 256QAM for FR2 (China Telecom)
  WI: CSI-RS based L3 measurement requirements (Huawei)
  WI: NR RRM requirement improvement (CATT)
  New requirements
  WI: NR measurement gap enhancement (Intel)
  NR support for high speed train scenario (CMCC)
  SI: Study on NR and NB-IoT/eMTC co-existence (Huawei)
  Whether the proposals are spectrum related item shall be discussed first

## Slide 23: TU budget for NR and LTE
 | Q2 2019 |  |  |  | Q3 2019 |  | Q4 2019 |  |  |  | Q1 2020 |  | 2020 Q2 |  |  | 
 | RF | RD | RF | RD | RF | RD | RF | RD | RF | RD | RF | RD | RF | RD | RF | RD
NR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15 | 24 | 15
Rel-15 NR Core | 4 | 4->8* | 2 | 4->8* | 0->1* | 0->1* | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rel-15 NR Perf | 4 | 4 | 2 | 4 | 0->1* | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Rel-16 | 16.4 | 5.5 | 17.8 | 8 | 15 | 11 | 14.3 | 12.75 | 15 | 12.25 | 1.5 | 9 | 1.75 | 10.5 | 1.5 | 10
Available TU | -0.4 | -2.5 | 2.2 | -5 | 7 | 1 | 9.7 | 1.25 | 9 | 1.75 | 22.5 | 6 | 22.25 | 4.5 | 22.5 | 5
LTE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Total | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Approved items | 2.5 | 2.75 | 2.75 | 3.25 | 2.5 | 4 | 2.5 | 4 | 3.5 | 5.5 | 1 | 1.5 | 1 | 2 | 1 | 2
Available TUs | 0.75 | 0.5 | 0.5 | 0 | 0.5 | -1 | 0.5 | -1 | -0.5 | -2.5 | 2 | 1.5 | 2 | 1 | 2 | 1
Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Available TUs (LTE+NR) | 0.35 | -2 | 2.7 | -5 | 7.5 | 0 | 10.2 | 0.25 | 8.5 | -0.75 | 24.5 | 7.5 | 24.25 | 5.5 | 24.5 | 6
* Increased TU for Rel-15 RD comparing with RP-182904
  Rel-16 RF related items including spectrum related items can be started in Q2 2019
  Rel-16 RD (RRM and Demod/CSI) related items shall start no earlier than June 2019

## Slide 24: RAN WG4 Schedule in 2019
Meeting | Date | Location | Host
3GPPRAN4#90 | 25 Feb - 1 March 2019 | Athens | EF3
3GPPRAN4#90bis | 8 - 12 Apr 2019 | CN | CF3
3GPPRAN4#91 | 13 - 17 May 2019 | US | NF3
3GPP RAN4-AH-1906 (Cancelled) | 24 – 28 Jun 2019 | TBD | 
3GPPRAN4#92 | 26 – 30 Aug 2019 | Ljubijana | EF3
3GPPRAN4#92bis | 14 – 18 Oct 2019 | CN | CF3
3GPPRAN4#93 | 18 -22 Nov 2019 | Reno | NF3

## Slide 25: Thanks to
NR specifications rapporteturs and their companies for their extraordinary effort of coordinating the RAN4 discussions and also editing RAN4 NR specifications:
  Ville Vintola (Qualcomm): 38.101-1/2/3
  Johan Sköld (Ericsson): 38.104
  Yang Tang (Intel): 38.133
  Haijie Qiu (Samsung): 38.101-4
  Steven Chen (Huawei): 38.141-1/2
  Aijun Cao and Rui Zhou (ZTE): 38.113
  Christian Bergljung (Ericsson): 38.124
  Petri Vasenkari (Nokia): 38.307
Vice chairmen Xizeng Dai and Hiromasa Umeda for preparation and session chairing
Kyoungseok Oh for efficient secretary support
AH chairs and WI rapporteurs for coordinating the offline/ad-hoc discussions
Delegates for enthusiastic contributions
EF3 for meeting hosting