## TU_overview_after_RAN_83
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation | [5 empty] | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | Final column of TU total. Insert new quarters before this column. Do not remove this column
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | target | sum TUs | comment | 84 Jun 19 | 98 | 107 | 105 | 92 | 92 | 13 | 85 Sept 19 | 98bis | 107bis | 105bis | 92bis | 92bis | 99 | 108 | 106 | 93 | 93 | 14 | 86 Dec 19 | 100 | 109 | 107 | 94 | 94 | 15 | 87 Mar.20 | 100bis | 109bis | 107bis | 94bis | 94bis | 101 | 110 | 108 | 95 | 95 | 16 | 88 Jun.20 | 102 | 111 | 109 | 96 | 96 | 17 | 87 Sep.20
R1 | NR | NR_newRAT-Core | WI | New Radio (NR) Access Technology | RP-190213 | NTT DOCOMO | Dec 18 | 2 | [5 empty] | 1 | 1 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
R4 | NR | NR_newRAT-Perf | WI | Perf. part: New Radio Access Technology | RP-190213 | NTT DOCOMO | Jun 18 | 6 | [5 empty] | 1 | 3 | [5 empty] | 0 | 1 |  |  |  | 0 | 1
R1 | NR | NR_2step_RACH-Core | WI | Core part: 2-step RACH for NR | RP-190711 | ZTE | Mar 20 | 7 |  |  | 1 | 1 | [5 empty] | 1 | 1 |  |  |  | 1 | 1 | [6 empty] | 1
R4 | NR | NR_2step_RACH-Perf | WI | Perf part: 2-step RACH for NR | RP-190711 | ZTE | Sep 20 | 4 | [25 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | NR | NR_unlic-Core | WI | Core part: NR-based Access to Unlicensed Spectrum | RP-191575 | Qualcomm | Mar 20 | 35.5 |  |  | 4 | 2 |  | 2 | 1.5 |  |  | 4 | 3 |  | 2 | 2 | 4 | 3 |  | 2 | 2 |  |  |  | 3 |  | 0 | 1
R4 | NR | NR_unlic-Perf | WI | Perf part: NR-based Access to Unlicensed Spectrum | RP-191575 | Qualcomm | Sep 20 | 3 | [32 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | NR, LTE | 5G_V2X_NRSL-Core | WI | Core part: 5G V2X with NR sidelink | RP-190984 | LG Electronics | Mar 20 | 33 |  |  | 3 | 2 | 0.5 | 1 | 1 |  |  | 3 | 3 | 1 | 1 | 1.5 | 3 | 3 | 1 | 1 | 1.5 |  |  |  | 3 | 1 | 1 | 1.5
R4 | NR | 5G_V2X_NRSL-Perf | WI | Perf part: 5G V2X with NR sidelink | RP-190984 | LG Electronics | Sep 20 | 4.5 | [32 empty] | 1.5 |  |  |  |  | 1.5 | [6 empty] | 1.5
R1 | NR | NR_eMIMO-Core | WI | Core part: Enhancements on MIMO for NR | RP-182863 | Samsung | Mar 20 | 12.5 |  |  | 3 | 0.5 | [5 empty] | 3 | 0.5 |  |  | 0.5 | 3 | 0.5 |  |  | 0.5 |  |  |  | 1
R4 | NR | NR_eMIMO-Perf | WI | Perf. part: Enhancements on MIMO for NR | RP-182863 | Samsung | June 20 | 3 | [25 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
R1 | NR | NR_UE_pow_sav-Core | WI | Core part: UE Power Saving in NR | RP-191607 | CATT | Mar 20 | 12 |  |  | 1 | 1 |  | 0.5 |  |  |  | 1 | 1 |  | 0.5 | 1 | 1 | 1 |  | 0.5 | 1 |  |  |  | 1 |  | 0.5 | 1
R4 | NR | NR_PoserSaving-Perf | WI | Perf part: UE power saving in NR performance | RP-191607 | CATT | Sep 20 | 1.5 | [32 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R1 | NR | NR_POS-Core | WI | Core part: NR Positioning Support | RP-191156 | Intel | Mar 20 | 15.5 |  |  | 2 | 1 | 0.5 |  | 0.5 |  |  | 2 | 1 | 0.5 |  | 1 | 2 | 1 | 0.5 |  | 1 |  |  |  | 1 | 1 |  | 0.5
R4 | NR | NR_POS-Perf | WI | Perf part：NR Positioning Support | RP-191156 | Intel | Sep 20 | 3.5 | [25 empty] | 0.5 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R1 | NR | NR_L1enh_URLLC-Core | WI | Core part: Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-191584 | Huawei | Mar 20 | 9 |  |  | 2 | 0.5 |  | 0.1 | 0.25 |  |  | 2 |  |  | 0.1 | 0.25 | 2 | 0.5 |  | 0.1 |  |  |  |  | 1 |  | 0.1 | 0.1
R4 | NR | NR_L1enh_URLLC-Perf | WI | Perf Part: Physical layer enhancements for NR ultra-reliable and low latency case (URLLC) | RP-191584 | Huawei | Sep 20 | 6.25 | [6 empty] | 0.25 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 1.5 |  |  |  |  | 1.5 | [6 empty] | 1.5
R1 | NR | NR_CLI_RIM-Core | WI | Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | RP-191546 | LG Electronics | Dec 19 | 1.75 |  |  |  | 0.5 |  |  | 0.25 |  |  |  | 0.5 |  |  | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_CLI_RIM-Perf | WI | Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | RP-191546 | LG Electronics | Dec 19 | 0.75 | [25 empty] | 0.25 | [6 empty] | 0.25 |  |  |  |  | 0.25
R1 | NR | FS_IIIOT_CM | SI | SID on Channel Modeling for Indoor Industrial Scenarios | RP-182862 | Ericsson | Sept 19 |  |  |  | 0.5
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  | Dec 19 | 3 |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1
R2 | NR | NR_IAB-Core | WI | Core part: Integrated Access and Backhaul for NR | RP-191558 | Qualcomm | Mar 20 | 32.5 |  |  | 1 | 3 | 1 | 2 | 1 |  |  | 1 | 3 | 2 | 2 | 1.5 | 1 | 3 | 2 | 2 | 1.5 |  |  |  | 3 | 1 |  | 1.5
R4 | NR | NR_IAB-Perf | WI | Perf part: Integrated Access and Backhaul for NR | RP-191558 | Qualcomm | Dec 20 | 4.5 | [32 empty] | 1.5 |  |  |  |  | 1.5 | [6 empty] | 1.5
R2 | NR | RACS_RAN | WI | Optimisations on UE radio capability signalling – NR/E-UTRA Aspects | RP-191088 | MediaTek | Mar 20 | 3 |  |  |  | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | 1
R2 | NR | NR_IIoT | WI | NR Industrial IoT | RP-191561 | Nokia | Mar 20 | 16 |  |  |  | 2 | 1 | [5 empty] | 3 | 1 |  |  |  | 3 | 1 | [5 empty] | 3 | 2
R2 | NR | NR_Mob_enh-Core | WI | Core part: NR mobility enhancements | RP-190489 | Intel | Mar 20 | 19 |  |  | 1 | 2 | 1 |  | 1 |  |  | 1 | 2 | 0.5 |  | 1 | 1 | 2 | 0.5 |  | 1 |  |  |  | 2 | 1 |  | 1 |  |  |  |  | 1
R4 | NR | NR_Mob_enh-Perf | WI | Perf part: NR mobility enhancements | RP-190489 | Intel | Mar 20 | 0.75 | [32 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25
R2 | NR | LTE_NR_DC_CA_enh-Core | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-191600 | Ericsson | Mar 20 | 18.5 |  |  | 1 | 2 |  | 0.5 | 1 |  |  | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 |  |  |  | 2
R2 | NR | SRVCC_NR_to_UMTS-Core | WI | Core part: Single Radio Voice Call Continuity from 5G to 3G | RP-190713 | China Unicom | Mar 20 | 4.75 |  |  |  | 0.5 | 0.5 |  | 0.25 | 0.25 |  |  | 0.5 | 0.5 |  | 0.25 |  | 0.5 | 0.5 |  | 0.25 | 0.25 |  |  | 0.5
R4 | NR | SRVCC_NR_to_UMTS-Perf | WI | Perf part: Single Radio Voice Call Continuity from 5G to 3G | RP-190713 | China Unicom | Jun 20 | 0.75 | [25 empty] | 0.25 | [6 empty] | 0.25 |  |  |  |  | 0.25
R2 | NR, LTE |  |  | Reserved for SA2/3 with with no RAN WI/SI (as agreed in RP-182974) |  |  |  | 2 |  |  |  | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
RAN | NR, LTE | FS_5G_eval | SI | Study on Self Evaluation towards IMT-2020 Submission | RP-181318 | Huawei | Jun 18 | 0
R3 | NR | LTE_NR_arch_evo-Core | WI | eNB(s) Architecture Evolution for E-UTRAN and NG-RAN | RP-181375 | China Unicom | Dec 19 | 3 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1
R3 | NR | FS_NR_NTN_solutions | SI | Study on solutions for NR to support Non Terrestrial Network (NTN) | RP-190710 | Thales | Dec 19 | 5 |  |  | 1 | 0.5 | [5 empty] | 1 | 0.5 |  |  |  | 1 | 0.5 | [6 empty] | 0.5
R3 | NR | NR_SON_MDT | WI | SON/MDT Support for NR | RP-191594 | CMCC | Mar 20 | 9.5 |  |  |  | 1 | 1.5 | [5 empty] | 1 | 1.5 |  |  |  | 1 | 1 | [5 empty] | 1 | 1 |  | 0.5
R3 | NR | RANImp_5WWC | WI | NG Interface Usage for WWC (Wireless Wireline Convergence) | RP-190999 | Huawei | Dec 19 | 1.5 |  |  |  |  | 0.5 | [11 empty] | 0.5 | [6 empty] | 0.5
R3 | NR | FS_NR_NPN | WI | Private Network Support for NG-RAN | RP-191563 | China Telecom | Mar 20 | 6 |  |  |  | 0.5 | 1 | [5 empty] | 0.5 | 1 |  |  |  | 0.5 | 1 | [5 empty] | 0.5 | 1
R3 | NR | FS_NR_LOCAL_POS | SI | Study on Local NR Positioning in NG-RAN | RP-191460 | CMCC | Dec 19 | 1.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5
R3 | NR | FS_eDisaggregated_gNB | SI | Study on Enhancement for Disaggregated gNB Architecture | RP-191481 | CATT | Dec 19 | 1.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_MIMO_OTA_TestMethod | SI | Study on radiated metrics and test methodology for the verification of multi-antenna reception performance of NR Ues | RP-181402 | CATR, OPPO, Samsung | Dec. 19 | 4 | [5 empty] | 1 | [6 empty] | 1 |  |  |  |  | 2
R4 | NR | NR_RF_FR1_Req_Enh-Core | WI | Core part: RF requirement for FR1 | RP-191114 | Huawei | Mar. 20 | 16 | [5 empty] | 4 | [6 empty] | 4 |  |  |  |  | 4 | [6 empty] | 4
R4 | NR | NR_RF_FR1_Req_Enh-Perf | WI | Perf part: RF requirement for FR1 | RP-191114 | Huawei | Sep. 20 | 0.75 | [31 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25
R4 | NR | NR_RF_FR2_Req_Enh-Core | WI | Core part: NR RF Requirement Enhancements for FR2 | RP-191290 | Nokia | March 2020 | 16 | [5 empty] | 4 | [6 empty] | 4 |  |  |  |  | 4 | [6 empty] | 4
R4 | NR | NR_RF_FR2_Req_Enh-Perf | WI | Perf part: NR RF Requirement Enhancements for FR2 | RP-191290 | Nokia | March 2020 | 0.75 | [31 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25
R4 | NR | NR_DL256QAM_FR2-Core | WI | Core part: Add support of NR DL 256QAM for FR2 | RP-190925 | China Telecom | Mar. 2020 | 2 | [5 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R4 | NR | NR_DL256QAM_FR2-Perf | WI | Perf. Part: Add support of NR DL 256QAM for FR2 | RP-190925 | China Telecom | Sept. 2020 | 1.5 | [31 empty] | 0.25 | 0.25 |  |  |  | 0.25 | 0.25 | [5 empty] | 0.25 | 0.25
R4 | NR,LTE, UTRA, E-UTRA, GSM | MSR_GSM_UTRA_LTE_NR | WI | New WID on introduction of GSM, UTRA, E-UTRA and NR capability set(s) (CS(s)) to the multi-standard radio (MSR) specifications | RP-190642 | Ericsson | Sep 2019 | 0.25 | [5 empty] | 0.25
R4 | NR | NR_RRM_Enh_Core | WI | WI on NR RRM enhancement in R16 | RP-191601 | Intel, ZTE | Mar 20 | 5.75 | [6 empty] | 0.25 | [6 empty] | 2 |  |  |  |  | 2 | [6 empty] | 1.5
R4 | NR | NR_RRM_Enh_Perf | WI | WI on NR RRM enhancement in R16 | RP-191601 | Intel, ZTE | Sep 20 | 4.5 | [32 empty] | 1.5 |  |  |  |  | 1.5 | [6 empty] | 1.5
R4 | NR | NR_CSIRS_L3meas | WI | Core part: CSI-RS based L3 measurement requirements for NR | RP-191580 | CATT | Mar 20 | 2.75 | [6 empty] | 0.25 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 0.5
R4 | NR | NR_CSIRS_L3meas | WI | Perf. part: CSI-RS based L3 measurement requirements for NR | RP-191580 | CATT | Sep 20 | 2 | [25 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R4 | NR | NR_HST | WI | Core part: NR support for high speed train scenario | RP-191512 | CMCC | Mar 20 | 3.25 | [6 empty] | 0.25 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
R4 | NR | NR_HST | WI | Perf part: NR support for high speed train scenario | RP-191512 | CMCC | Sep 20 | 7 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1
R4 | NR | NR_enh-Perf | WI | NR performance requirement enhancement | RP-191587 | China Telecom | June. 20 | 4 | [6 empty] | 1 | [6 empty] | 0.75 |  |  |  |  | 0.75 | [6 empty] | 0.75 | [6 empty] | 0.75 |  |  |  |  | 0.75
R4 | NR, LTE | LTE_B41_NR_n41_PCx | WI | New WID on 29dBm UE Power Class for B41 and n41 | RP-190502 | Sprint | Dec 19 | 0.75 | [5 empty] | 0.25 | [6 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_wide_chs_n7 | WI | New WID on adding wider channel bandwidths in Band n7 | RP-182827 | BT | Sep 19 | 0.2 | [5 empty] | 0.2
R4 | NR | FS_7to24GHz_NR | SI | Study on 7 - 24 GHz Frequency Range | RP-190373 | Huawei | Dec 19 | 4.5 | [5 empty] | 2 | [6 empty] | 1.5 |  |  |  |  | 1
R4 | NR | ENDC_UE_PC2_TDD_TDD-Core | WI | Core part: Power class 2 UE for EN-DC (1 LTE TDD band + 1 NR TDD band) | RP-190315 | CMCC | Dec 19 | 3 | [5 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1
R4 | NR | ENDC_UE_PC2_TDD_TDD-Perf | WI | Perf part: Power class 2 UE for EN-DC (1 LTE TDD band + 1 NR TDD band) | RP-190315 | CMCC | Dec 19 | 0
R4 | NR | FS_ENDC_UE_PC2_FDD_TDD | SI | Study on high power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | RP-191439 | China Unicom | Sep 19 | 1 | [5 empty] | 1
R4 | NR | NR_Band_n259_R16 | WI | New WID: introduction of Band n259 | RP-191416 | Ericsson | Dec. 19 | 1.6 | [5 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5 | 0.1
R4 | NR | NR_SUL_UL_n5 | WI | Core part: Introduction of NR SUL (supplemental uplink) band with same uplink frequency range of NR band n5 | RP-191116 | Huawei | Sep.19 | 0.2 | [5 empty] | 0.2
R4 | NR | NR_n38_BW | WI | Core part: addition of wider channel bandwidth in NR band n38 | RP-191472 | Huawei | Dec.19 | 0.75 | [5 empty] | 0.25 | [6 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_n1_BW-Core | WI | Core part: Adding 30 MHz channel bandwidth to NR band n1 | RP-191595 | Ericsson | Mar 20 | 0.8 | [5 empty] | 0.25 | [6 empty] | 0.25 |  |  |  |  | 0.15 | [6 empty] | 0.15
R4 | NR | NR_n1_BW-Perf | WI | Perf part: Adding 30 MHz channel bandwidth to NR band n1 | RP-191595 | Ericsson | Mar 20 | 0.2 | [17 empty] | 0.1 | [6 empty] | 0.1
R4 | NR | NR_band_n29 | WI | Introduction of NR supplementary DL band n29 | RP-191474 | DISH | Sep 19 | 0.5 | [5 empty] | 0.5
R4 | NR |  | WI | Addition of wider channel bandwidth in Band n77 and n78 | RP-191606 | Huawei | Dec 19 | 0.75 | [5 empty] | 0.25 | [6 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR |  | WI | NR FDD bands with variable duplex | RP-191567 | Huawei | Dec 19 | 1.5 | [5 empty] | 0.5 | [6 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | EN-DC Basket WIs-Core & Perf | WI | New WID on EN-DC for 2 bands DL with 2 bands UL (1 LTE band + 1 NR band) New WID on EN-DC for 3 bands DL with 2 bands UL (2 LTE bands + 1 NR band) New WID on EN-DC for 4 bands DL with 2 bands UL (3 LTE bands + 1 NR band) New WID on EN-DC for 5 bands DL with 2 bands UL (4 LTE bands + 1 NR band) New WID on EN-DC for 6 bands DL with 2 bands UL (5 LTE bands + 1 NR band) , New WID on EN-DC of LTE CA for up to 4 bands DL with 1 band UL + NR CA for 2 bands DL with 1 band UL New WID on SA NR Supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) New WID: Basket Rel-16 WID NR Intra-band CA New WID: Basket Rel-16 WID NR inter-band CA/DC for 2 DL bands with up to 2 UL bands New WID: Rel-16 NR Inter-band Carrier Aggregation for 3 bands DL with 1 band bands UL New WID: Rel-16 NR Inter-band Carrier Aggregation/Dual connectivity for 3 bands DL with 2 band bands UL Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL Dual Connectivity (EN-DC) with 3 bands DL (max.2 NR) and 3 bands UL (max. 2 NR) RF requirements for EN-DC with 3 uplink CC with 2 different bands | RP-191194 RP-191566 RP-191153 RP-191568 RP-191124 RP-191195 RP-191205 RP-191565 RP-190949 RP-191126 RP-191196 RP-191598 RP-191604 | NTT DOCOMO, etc | Dec 19 | 12 | [5 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3
|  |  |  | Last row in NR totals. Insert new NR items above this line. Do not remove |  |  |  | 0
|  |  |  | First row in LTE totals. Insert new LTE items below this line. Do not remove |  |  |  | 0
R1 | LTE | LTE_eMTC5-Core | WI | Core part: Additional MTC enhancements for LTE | RP-191356 | Ericsson | Mar 20 | 25 |  |  | 3 | 2.5 | 0.5 | 0.5 | 0.5 |  |  | 3 | 2.5 | 0.5 | 0.5 | 0.5 | 3 | 2.5 | 0.5 | 0.5 | 0.5 |  |  |  | 2.5 | 0.5 | 0.5 | 0.5
R4 | LTE | LTE_eMTC5-Perf | WI | Perf part: Additional MTC enhancements for LTE | RP-191356 | Ericsson | Sep. 20 | 5 | [17 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5
R1 | LTE | NB_IOTenh3-Core | WI | Core part: Additional enhancements for NB-IoT | RP-191576 | Huawei | Mar 20 | 28 |  |  | 4 | 2.5 | 0.5 | 0.5 | 0.5 |  |  | 4 | 2.5 | 0.5 | 0.5 | 0.5 | 4 | 2.5 | 0.5 | 0.5 | 0.5 |  |  |  | 2.5 | 0.5 | 0.5 | 0.5
R4 | LTE | NB_IOTenh3-Perf | WI | Perf part: Additional enhancements for NB-IoT | RP-191576 | Huawei | Sep. 20 | 5 | [17 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5
R1 | LTE | LTE_terr_bcast-Core | WI | Core part: LTE-based 5G Terrestrial Broadcast | RP-190732 | Qualcomm | Mar 20 | 8 |  |  | 1 | [6 empty] | 1 |  |  | 0.5 | 0.5 | 1 |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5 | 0 | [6 empty] | 0 | 1 |  |  |  | 0 | 1
R4 | LTE | LTE_Terr_bcast-Perf | WI | Performance part: LTE-based 5G terrestrial broadcast | RP-190732 | Qualcomm | Jun 20 | [26 empty] | 0.5 | [6 empty] | 1 |  |  |  |  | 1
R1 | LTE | LTE_DL_MIMO_EE-Core | WI | Core part: DL MIMO efficiency enhancements for LTE | RP-182901 | Huawei | Mar 20 | 4 |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1 | 0.5 | [6 empty] | 0.5
R4 | LTE | LTE_DL-MIMO_EE-Perf | WI | Perf. part: DL MIMO efficiency enhancements for LTE | RP-182901 | Huawei | Mar 20 | 0.75 | [32 empty] | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25
R2 | LTE | LTE_feMob-Core | WI | Core Part: Even further Mobility enhancement in E-UTRAN | RP-181544 | China Telecom | Dec 19 | 9 |  |  |  | 1 | 1 |  | 0.5 |  |  |  | 1 | 0.5 |  | 0.5 |  | 1 | 0.5 |  | 0.5 |  |  |  | 1 | 1 |  | 0.5
R4 | LTE | LTE_feMob-Perf | WI | Per Part: Even further Mobility enhancement in E-UTRAN | RP-181475 | China Telecom | Dec 19 | 1.5 | [32 empty] | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R4 | LTE | LTE_high_speed_enh2-Core | WI | Core part: Further performance enhancement for LTE in high speed scenario | RP-181478 | NTT DOCOMO | Sep 19 | 1 |  |  |  | 0.25 |  |  | 0.5 |  |  |  | 0.25
R4 | LTE | LTE_high_speed_enh2-Perf | WI | Perf part: Further performance enhancement for LTE in high speed scenario | RP-181478 | NTT DOCOMO | Dec 19 | 4 | [6 empty] | 1 | [6 empty] | 1.5 |  |  |  |  | 1.5
R4 | LTE | LTE_PC2_B31_B72 |  | Power Class 2 UE for LTE bands 31 and 72 | RP-190665 | Nokia | Sep 19 | 0.25 | [5 empty] | 0.25
R4 | LTE | LTE CA basket WIs | WI | New WID: Basket WI for LTE Intra-band CA New WID on Rel16 LTE inter-band CA for 2 bands DL with 1 band UL New WID on Rel16 LTE inter-band CA for 2 bands DL with 1 band UL New WID: LTE Advanced inter-band CA Rel-16 for 3DL/1UL New WI: Rel16 LTE inter-band CA for 4 or 5 bands DL with 1 band UL New WID: LTE Advanced inter-band CA Rel-16 for 2DL/2UL New WID on Rel16 LTE inter-band CA for x bands DL with 2 bands UL with x=3, 4, 5 | RP-191193 RP-191085 RP-191120 RP-190906 RP-191122 RP-190946 RP-181824 RP-181825 | Ericsson, etc. | 2019-03-20 | 4 | [5 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
|  |  |  | Last row in LTE totals. Insert new LTE items above this line. Do not remove |  |  |  | 0
|  |  |  | First row in UMTS totals. Insert new UMTS items below this line. Do not remove. |  |  |  | 0
|  |  |  | Last row in UMTS totals. Insert new UMTS items above this line. Do not remove |  |  |  | 0
|  |  |  | First row in GERAN totals. Insert new GERAN items below this line. Do not remove |  |  |  | 0
|  |  |  | Last row in GERAN totals. Insert new GERAN items above this line. Do not remove |  |  |  | 0
| NR |  |  | allocated above | [6 empty] | 20.5 | 21 | 9.5 | 27.75 | 13.75 |  |  | 20 | 23.5 | 11 | 23.6 | 17.5 | 20 | 23.5 | 11 | 24.1 | 17.35 |  |  | 0 | 24.5 | 9.5 | 13.35 | 15.1 |  |  | 0 | 0 | 1 | 0.75 | 13.75 | 0 | 0 | 0 | 0.75 | 13.75 |  |  | 0 | 0 | 0 | 1.75 | 10.5
| NR |  |  | Legacy | [7 empty] | 6 | [6 empty] | 4 |  |  |  |  | 4 | [6 empty] | 4 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| NR |  |  | TEI and other not planned issues | [7 empty] | 1 | [6 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 0 |  |  |  |  | 0 | [6 empty] | 0
| NR |  |  | Reserve | [6 empty] | 0.5 | [6 empty] | 1 |  |  |  |  | 1
| NR |  |  | total used capacity | [6 empty] | 21 | 28 | 9.5 | 27.75 | 13.75 |  |  | 21 | 28.5 | 11 | 23.6 | 17.5 | 21 | 28.5 | 11 | 24.1 | 17.35 |  |  | #REF! | 29.5 | 9.5 | 13.35 | 15.1 |  |  | #REF! | 0 | 1 | 0.75 | 13.75 | #REF! | 0 | 0 | 0.75 | 13.75 |  |  | #REF! | 0 | 0 | 1.75 | 10.5
| NR |  |  | available capacity | [6 empty] | 21 | 23 | 7 | 24 | 15 |  |  | 21 | 23 | 7 | 24 | 15 | 21 | 23 | 7 | 24 | 15 |  |  |  | 23 | 7 | 24 | 15 |  |  |  | 23 | 7 | 24 | 15 |  | 23 | 7 | 24 | 15 |  |  |  | 23 | 7 | 24 | 15
| NR |  |  | remaining/exceeded capacity | [6 empty] | 0 | -5 | -2.5 | -3.75 | 1.25 |  |  | 0 | -5.5 | -4 | 0.4 | -2.5 | 0 | -5.5 | -4 | -0.1 | -2.35 |  |  | #REF! | -6.5 | -2.5 | 10.65 | -0.1 |  |  | #REF! | 23 | 6 | 23.25 | 1.25 | #REF! | 23 | 7 | 23.25 | 1.25 |  |  | #REF! | 23 | 7 | 22.25 | 4.5
| LTE |  |  | allocated above | [6 empty] | 9 | 6.25 | 2 | 2.25 | 3 |  |  | 9 | 6.25 | 1.5 | 2.5 | 3.5 | 9 | 6.5 | 1.5 | 3.5 | 4.5 |  |  | 0 | 7 | 2.5 | 3 | 3 |  |  | 0 | 0 | 0 | 1 | 3.75 | 0 | 0 | 0 | 1 | 3.75 |  |  | 0 | 0 | 0 | 1 | 1.75
| LTE |  |  | Legacy | [7 empty] | 4 | 3 | [5 empty] | 4 | 3 |  |  |  | 4 | 3 | [5 empty] | 3 | 3 | [5 empty] | 0 | 3 |  |  |  | 0 | 3 | [5 empty] | 0 | 3
| LTE |  |  | TEI and other not planned issues | [7 empty] | 0.5 | 1 | [5 empty] | 0.5 | 1 |  |  |  | 1 | 1 | [5 empty] | 1 | 1 | [5 empty] | 0 | 1 |  |  |  | 0 | 1 | [5 empty] | 0 | 1
| LTE |  |  | Reserve | [8 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 |  |  |  |  | 3 | [6 empty] | 3
| LTE |  |  | total used capcaity | [6 empty] | 10 | 10.75 | 9 | 2.25 | 3 |  |  | 10 | 10.75 | 8.5 | 2.5 | 3.5 | 10 | 11.5 | 8.5 | 3.5 | 4.5 |  |  | 0 | 11 | 9.5 | 3 | 3 |  |  | 0 | 0 | 7 | 1 | 3.75 | 0 | 0 | 7 | 1 | 3.75 |  |  | 0 | 0 | 7 | 1 | 1.75
| LTE |  |  | available capacity | [6 empty] | 10 | 15 | 12 | 3 | 3 |  |  | 10 | 15 | 12 | 3 | 3 | 10 | 15 | 12 | 3 | 3 |  |  | 0 | 15 | 12 | 3 | 3 | 0 |  | 0 | 15 | 12 | 3 | 3 | 0 | 15 | 12 | 3 | 3 | 0 |  | 0 | 15 | 12 | 3 | 3 | 0
| LTE |  |  | remaining/exceeded capacity | [6 empty] | 0 | 4.25 | 3 | 0.75 | 0 |  |  | 0 | 4.25 | 3.5 | 0.5 | -0.5 | 0 | 3.5 | 3.5 | -0.5 | -1.5 |  |  | 0 | 4 | 2.5 | 0 | 0 |  |  | 0 | 15 | 5 | 2 | -0.75 | 0 | 15 | 5 | 2 | -0.75 |  |  | 0 | 15 | 5 | 2 | 1.25
| UTRA |  |  | allocated above | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
| UTRAN |  |  | Legacy | [11 empty] | 0.1 | [11 empty] | 0.1
| UTRAN |  |  | TEI and other not planned issues | [11 empty] | 0.25 | [11 empty] | 0.25 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0
| UTRAN |  |  | Reserve | [11 empty] | 0.1 | [11 empty] | 0.1
| UTRAN |  |  | total used capacity | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| UTRAN |  |  | available capacity | [11 empty] | 0.7 | [11 empty] | 0.7 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0
| UTRAN |  |  | remaining/exceeded capacity | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
| GERAN |  |  | allocated above | [11 empty] | 0 | [11 empty] | 0
| GERAN |  |  | Legacy | [11 empty] | 0.2 | [11 empty] | 0.2
| GERAN |  |  | TEI and other not planned issues | [11 empty] | 0.5 | [11 empty] | 0.5 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0
| GERAN |  |  | Reserve | [11 empty] | 0.1 | [11 empty] | 0.1
| GERAN |  |  | total used capacity | [11 empty] | 0.8 | [11 empty] | 0.8 | [6 empty] | 0 | [11 empty] | 0 | [6 empty] | 0
| GERAN |  |  | available capacity | [11 empty] | 0.8 | [11 empty] | 0.8
| GERAN |  |  | remaining/exceeded capacity | [11 empty] | 0 | [11 empty] | 0
R3 |  |  |  | RAN3 overall Status | [8 empty] | 0.5 | [6 empty] | -0.5 |  |  |  |  | -0.5 | [6 empty] | 0 | [6 empty] | 11 |  |  |  |  | 12 | [6 empty] | 12