## Cover
3GPP TSG RAN Meeting #88e |  | RP-201230
Electronic Meeting, June 29 - July 3, 2020
Agenda Item: | 9.3.22
Source: | CATT
Title: | Overview on remaining work for RRM requirements for CSI-RS based L3 measurement
Document for: | Discussion
Discussion
In this excel sheet, we gave an overview and on the work progress open issues for R16 WI RRM requirements for CSI-RS based L3 measurement. Recommandation on prioritization for Rel-16 completion is also presented in the sheet. It is proposed to prioritize the remaining work based on the analysis and recommandations in this paper. Exception sheet shall only capture the prioritized work for Rel-16 completion so that the discussion in Q3 can be more focused and efficient.

## Analysis and recommandations
WI | Issue | Sub-issue | Completed or not? | Critical for R16 completion? | Recommendation for not completed topics | Note
RRM requirements for CSI-RS based L3 measurement | 1、Definition of intra/inter frequency measurement | 1-1 Whether to include following factors into definition 1. center frequency 2. SCS 3. CP type 4. active BWP | Yes | Yes | N/A
| 2、CSI-RS configuration | 2-1 Whether to define different sets of requirements | Yes | Yes | N/A
|  | 2-2 CSI-RS configuration applicability | No | No | Further enhancement in R17
| 3、Measurement capability | 3-1 Applicable scenario | Yes | Yes | N/A
|  | 3-2 Whether multiple MOs can be counted as one frequency layer | No | Yes | Prioritized for Q3 discussion.
|  | 3-3 Number of frequency layers to be monitored | No | Yes | Prioritized for Q3 discussion.
|  | 3-4 Number of cells to be monitored | Yes | Yes | N/A
|  | 3-5 Number of CSI-RS beams/resources to be monitored | No | Yes | Prioritized for Q3 discussion.
| 4、Measurement requirements for CSI-RS intra/inter-frequency measurements | 4-1 Whether dedicated searcher(s) is assumed for CSI-RS measurement | No | Yes | Prioritized for Q3 discussion.
|  | 4-2 Whether and how to introduce time-domain restriction（CMTC） | No | No | Further enhancement in R17 | Some basic solution or side condition is needed if it is postponed to Rel-17.
|  | 4-3 How to define CSSF | No | Yes | Prioritized for Q3 discussion.
|  | 4-4 New UE capability on the simultaneous reception of CSI-RS of neighbour cell and SSB of serving cell | No | No | Prioritized for Q3? | It seems majority view is supportive for this one.
|  | 4-5 New UE capability for minimum separation between two slots with CSI-RS resources | No | No | Further enhancement in R17 | Discussion is still not started in Rel-16.
|  | 4-6 Scheduling and measurement restriction | No | No | Prioritized for Q3 discussion.
|  | 4-7 Scaling factor for RX beam sweeping | No | Yes | Prioritized for Q3 discussion.
|  | 4-9 Cell identification and measurement period | No | Yes | Prioritized for Q3 discussion.
|  | 4-10 The tuning time of inter-frequency GAP of CSI-RS measurement | No | Yes | Prioritized for Q3 discussion.
| 5、Others | 5-1 Synchronization assumption for CSI-RS measurement | No | Yes | Prioritized for Q3 discussion.