## Slide 1: Release, Meeting and TU planning
Source: TSG RAN Chairman, RAN1 Chairman, RAN2 Chairman, RAN3 Chairman, RAN4 Chairman, RAN5 Chairman
RP-201965

## Slide 2: Outline
Proposed meeting timeplan until June 2021
Release 17 timeline considerations
TU handling until June 2021

## Slide 3: Proposed RAN meeting plan
INACTIVE
RAN1
RAN2
RAN3
RAN4
Q
U
I
E
T
P
E
R
I
O
D
WG
WG
TSG
I
N
A
C
T
I
V
E
P
E
R
I
O
D
October
December
November
January
February
March
TSG
WG
WG
TSG
WG
WG
T
S
G
#
9
1
RAN1 (4+4+5)
T
S
G
#
9
0
RAN5
RAN4
RAN3
RAN2
Confirmed as E-meetings by default
12-16
19-23
26-30
2-6
9-13
16-20
23-27
30-4
7-11
18-22
25-29
1-5
8-12
15-19
22-26
1-5
8-12
15-19
22-26
RAN5
RAN1 (2+5)
RAN4
RAN3
RAN2
April
June
May
29-2
5-9
12-16
19-23
26-30
3-7
10-14
17-21
24-28
31-4
7-11
14-18
5-9
T
S
G
#
9
2
RAN1 (2+5)
RAN5
RAN4 (2+5)
RAN3
RAN2 (5+2)
RAN1 (5+2)
RAN1 (2+5)
I
N
A
C
T
I
V
E
P
E
R
I
O
D
I
N
A
C
T
I
V
E
P
E
R
I
O
D
RAN2 (2+5)
INACTIVE
RAN1
RAN2
RAN3
RAN4
Q
U
I
E
T
P
E
R
I
O
D
RAN4 (5+2)
INACTIVE
RAN1
RAN2
RAN3
RAN4
Q
U
I
E
T
P
E
R
I
O
D

## Slide 4: Key elements of the proposed plan (1/2)
Quarters with multiple WG meetings may have staggered handling of items
  Details to be further considered, and will be presented at subsequent RAN plenary meetings
Inactive periods are installed between meetings to allow proper internal preparation and observe key regional holidays
  No email discussions are allowed on any WG reflector during these periods unless explicitly agreed during a previous meeting. No GTW sessions are allowed, not even informal ones.
  23-29/Nov (Thanksgiving)
  21/Dec – 3/January (Christmas+New Year)
  8-21/Feb (Lunar New Year)
  29/March – 5/April (Easter)
  26/April-9/May

## Slide 5: Key elements of the proposed plan (2/2)
Tightening of scope is needed across all items at December plenary to ensure timely progress
  Potential follow-on Work Items of Study Items will need a very well defined tight scope!
TSG#91 may have 2 days set aside exclusively for conducting election rounds on Thursday and Friday before the normal meeting week

## Slide 6: Release 17 timeline
Expect Electronic era to last throughout 2021 – this is what we should plan for
The leadership is committed to facilitate delivering Rel-17 with minimal additional delay (6 months) even with a fully Electronic 2021
  Detailed analysis still needed to understand if this is feasible  Overall timeline decision to be taken only in December
Firmly commit to a new timeline (in December), and endorse a detailed planning (meetings and TUs) to achieve it
2021
Q2
Q3
Q4
Q1
2022
Q1
Rel-17 RAN1 freeze
Rel-17 stage-3 freeze
Rel-17 ASN.1 freeze
Rel-17 RAN4
performance completion
Current Release 17 timeline as per RAN#87E decision
2021
Q4
Q1
Q2
Q3
2022
Q3
Rel-17 RAN1 freeze
Rel-17 stage-3 freeze
Rel-17 ASN.1 freeze
Rel-17 RAN4
performance completion
Potential new timeline to be committed to latest in Dec

## Slide 7: RAN1 TU Management for 4Q’20 & 1Q/2Q’21
Assumptions: all RAN1 meetings in the next 3 quarters are e-meetings
Due to the natural difference between a physical meeting and an e-Meeting, the absolute values of the TUs herein should not be interpreted the same as in a physical meeting in terms of RAN1 capacity
  Note that different e-meetings may have different durations
The TU #s herein are primarily for gauging the ratio of email threads and GTW session times for different topics
Total TUs:
  27 + 4 (reserved for maintenance)=31
  For RAN1#103-e, a total of 40 TUs is assumed
    The 4 Rel-17 SIs are allocated with 4 TUs each, targeting for completion by Dec’2020
    Meeting planning: staggering for different items
      Rel-17 4 SIs: all the 3 weeks
      Maintenance: primarily first 2 weeks
      Other Rel-17 items: primarily last 2 weeks

## Slide 8: RAN2 TUs
- R2 Early SIs end after 21Q1.
- For Quarters with 2 meetings
the meetings will be 70% of
an ordinary meeting (5+2)
- Proposal to make the difference
visible at RP, i.e. Nominal
R2 capacity for such meetings
28 TUs instead of 40 TUs.
- Q4: Assume that 50% is used
for maintenance
Approximately for R2
1 TU = 1.5h online + CB time
1 TU = 1-3 AT-email disc.
1 TU = 1-3 input tdocs.
 | 20Q3 | 20Q4 | 21Q1 | 21Q2 | 
Rel 17 | 111 | 112 | 113 | 113B | 114
NR Sidelink relay SI + WI | 2 | 1.5 | 1.5 | 1.5 | 1
[R1] NR positioning enhancements SI + WI | 1 | 1 | 1 | 2 | 2
[R1] Reduced Capability SI = WI | 2 | 1 | 1 | 0.5 | 1
RAN slicing SI + WI | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
NR Multicast | 2 | 2 | 2 | 1.5 | 1.5
[R1] NR Non-Terrestrial Networks (NTN) | 2 | 2 | 2 | 1.5 | 1.5
UE Power Saving | 1 | 1 | 1 | 0 | 1
MR DC/CA enhancements | 1 | 1 | 1 | 1 | 0
Small Data enhancements | 1 | 1.5 | 1.5 | 1 | 0.5
NR IIoT/URLLC | 1 | 1 | 1 | 0 | 1
[R1] NB-IoT / eMTC enhancements | 1 | 1 | 1 | 1 | 1
[R3] SON/MDT | 1 | 1 | 1 | 1 | 0.5
NR IAB enhancements |  | 1 | 1 | 1 | 1
Multi SIM |  | 1 | 1 | 1 | 0.5
Non-Public Networks (NPN) |  | 0.5 | 1 | 1 | 1
[R1] IoT NTN SI |  | 1 | 1 | 0.5 | 0.5
[R1] NR Sidelink enhancements |  | 1.5 | 2 | 1 | 1
[R1] NR MIMO fe |  |  |  |  | 
[R3] NR QoE SI and WI |  |  | 0.5 | 0.5 | 0.5
[R1] NR up to 71GHz |  |  |  |  | 
[R1] Misc R1 items, Cov Enh, DSS sched enh etc |  |  |  |  | 
R17 Other | 1.5 | 0.5 | 2 | 0.5 | 1
TEI17 |  |  |  |  | 
R17 Total | 17 | 20 | 23 | 17 | 17
Rel 16 Total | 18 | 15 | 14 | 9 | 9
NR Rel 15 Total | 3 | 3 | 2 | 1 | 1
EUTRA R15 and earlier Total | 2 | 2 | 1 | 1 | 1
RAN2 Total (40) | 40 | 40 | 40 | 28 | 28

## Slide 9: RAN3 TU Management Until Q2/21
Assumption: all RAN3 meetings in the next 3 quarters are e-meetings
Plan assumes 12 “f2f TUs” per meeting
1 f2f TU ↔ ~7 e-mail discussions + ~40 min. online time
Actual allocation of e-mail discussions and online sessions in an e-meeting continues to be up to the Chairman’s discretion
2 meetings/quarter are assumed in Q4/21 in order to keep the Rel-17 deadline
Study item * RAN3-led

## Slide 10: RAN4 TU projection for R17
  Once R16 perf part work is done, the following is planned for RAN4:
Topics | RF | RD | Notes
RAN4 R15/R16 maintenance | 2 | 2 | 
RAN1/2/3 led R17 WIs | 8 | 10 | Assuming 18 TUs are required and roughly 40% for RF, 60% for RD. Precise TU budget remains to be clearly defined and justified
RAN4 R17 basket and other spectrum WIs | 6 |  | 4 for basket WIs and 2 for other spectrum WIs
Remaining TUs for RAN4 R17 non-spectrum WIs | 8.5 | 8.5 | Assuming a total of 45 TUs, and 24.5 TUs for RF and 20.5 TUs for RD

## Slide 11: Proposal
It is proposed to endorse the RAN meeting plan presented in slides 3,4,5.
It is proposed to endorse the TU planning shown in 7,8, 9, 10
For Release 17 timeline it is proposed to take an initial assumption of an additional 6 month delay, and task the RAN leadership to present to RAN#90-E a detailed plan and analysis for achieving this timeline. Formal decision on the new Release 17 timeline would then be made at TSG#90-E

## Slide 12: Thank you!

## Slide 13: Appendix: RAN2 TUs entire R17
- At end of the release, there
will be additional R1 and R4
induced work, and TEI17.
Suggest to end some smaller
items early, as shown.
 | 20Q3 | 20Q4 | 21Q1 | 21Q2 |  | 21Q3 | 21Q4 |  | 22Q1 | 
Rel 17 | 111 | 112 | 113 | 113B | 114 | 115 | 115B | 116 | 116B | 117
NR Sidelink relay SI + WI | 2 | 1.5 | 1.5 | 1.5 | 1 | 2 | 1 | 1 | 1.5 | 1.5
[R1] NR positioning enhancements SI + WI | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1
[R1] Reduced Capability SI = WI | 2 | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5
RAN slicing SI + WI | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 |  | 
NR Multicast | 2 | 2 | 2 | 1.5 | 1.5 | 2 | 2 | 1 | 1 | 1
[R1] NR Non-Terrestrial Networks (NTN) | 2 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1 | 1.5 | 1 | 1.5
UE Power Saving | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0.5 | 0.5
MR DC/CA enhancements | 1 | 1 | 1 | 1 | 0 | 1 | 0.5 | 1 | 1 | 1
Small Data enhancements | 1 | 1.5 | 1.5 | 1 | 0.5 | 1.5 | 0 | 1.5 | 1 | 1
NR IIoT/URLLC | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0.5 | 1
[R1] NB-IoT / eMTC enhancements | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
[R3] SON/MDT | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 0.5
NR IAB enhancements |  | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
Multi SIM |  | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 |  | 
Non-Public Networks (NPN) |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 |  | 
[R1] IoT NTN SI |  | 1 | 1 | 0.5 | 0.5 | 1 |  |  |  | 
[R1] NR Sidelink enhancements |  | 1.5 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1.5
[R1] NR MIMO fe |  |  |  |  |  |  | 0.5 | 0.5 | 0.5 | 1
[R3] NR QoE SI and WI |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 |  | 
[R1] NR up to 71GHz |  |  |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5
[R1] Misc R1 items, Cov Enh, DSS sched enh etc |  |  |  |  |  | 1 | 1 | 1 | 1 | 1
R17 Other | 1.5 | 0.5 | 2 | 0.5 | 1 | 2.5 | 1.5 | 1 | 3.5 | 1.5
TEI17 |  |  |  |  |  | 1 | 1 | 2 | 2 | 2
R17 Total | 17 | 20 | 23 | 17 | 17 | 26 | 18 | 19 | 19 | 19
Rel 16 Total | 18 | 15 | 14 | 9 | 9 | 11 | 7 | 6 | 6 | 6
NR Rel 15 Total | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2
EUTRA R15 and earlier Total | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
RAN2 Total (40) | 40 | 40 | 40 | 28 | 28 | 40 | 28 | 28 | 28 | 28