3GPP TSG RAN meeting #90e										      RP-202685

Electronic Meeting, December 07-11, 2020

## Status Report to TSG

Agenda item: 9.8.7 UE power saving enhancements for NR [RAN2 WI: NR_UE_pow_sav_enh]

| WI / SI Name | UE power saving enhancements for NR |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: - | Core part: Yes | Performance part: No |  | Testing part: - |
| Acronym | NR_UE_pow_sav_enh |  |  |  |  |
| Unique ID | 860047 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-200938 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: - | Core part: 09/2021 | Performance part: 03/2022 | Testing part: - |  |
| Overall Completion level | Study Item: - | Core part: Overall: 20% RAN1: 25% RAN2: 20% RAN4: 15% | Performance Part: Overall: 0% RAN1: 0% RAN2: 0% RAN4: 0% | Testing part: - |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | RAN2 |
| --- | --- | --- |
| Rapporteur | Name | Weide Wu |
|  | Company | MediaTek Inc. |
|  | Email | weide.wu@mediatek.com |

## 1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | No |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

Additional explanations/motivations for the time budget changes in the attached Excel table: N/A

## 2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

NOTE: Agreements and Open issues impacted cross-TSG aspects shall be explicitly highlighted

## 2.1	RAN1

#### 2.1.1	Agreements

Relating to scope item 1) – a): - Specify enhancements for idle/inactive-mode UE power saving, considering system performance aspects [RAN2, RAN1] - Study and specify paging enhancement(s) to reduce unnecessary UE paging receptions, subject to no impact to legacy UEs [RAN2, RAN1] - NOTE: RAN1 to check and update, if needed, evaluation methodology in RAN1 #102-e meeting The following agreements are achieved:

RAN1 #103-e meeting Agreements: Observation: For NR idle/inactive-mode UEs with 10% group paging rate, paging early indication without UE sub-grouping can achieve the following power saving gains w.r.t. Rel-16: - [0%] - [22.8%] where the baseline assumes 1 SS burst for synchronization before PO reception - Note: [0%] means UE can apply the baseline behavior if the time offset between the utilized SS burst and PO is small. - [5.0%] - [32.0%] where the baseline assumes 2 SS bursts for synchronization before PO reception - [10.2%] - [67.7%] where the baseline assumes 3 SS bursts for synchronization before PO reception The power saving gains will become lower for higher group paging rate. The power saving gains are dependent on the assumptions about placement of PEI and PO relative to SSB. The power saving gains may vary with different paging early indication design. Agreements: Observation: For NR idle/inactive-mode UEs, UE sub-grouping indication within a PO can provide the following power saving gains w.r.t. Rel-16: - If the original group paging rate is 10%: - [0.3%] - [1.1%] where the baseline assumes 1 SS burst for synchronization before PO reception - [0.4%] - [0.8%] where the baseline assumes 2 SS bursts for synchronization before PO reception - [0.3%] - [1.0%] where the baseline assumes 3 SS bursts for synchronization before PO reception - Some sources also evaluated performance if the original group paging rate is in the range between 20% and 80% and showed following results: - [0.7%] - [7.6%] where the baseline assumes 1 SS burst for synchronization before PO reception - [0.8%] - [3.0%] where the baseline assumes 2 SS bursts for synchronization before PO reception - [0.5%] - [4.7%] where the baseline assumes 3 SS bursts for synchronization before PO reception The number of UE sub-groups evaluated ranges from 2 to 16. Some companies show concern on assuming group paging rate larger than 60%. Note: It is FFS in RAN1 another group paging rate > 10% for the evaluation of Rel-17 paging enhancement. Agreements: Observation: For NR idle/inactive-mode UEs, UE sub-grouping indication carried in paging early indication can provide the following power saving gains w.r.t Rel-16: - If the original group paging rate is 10%: - [10.6%] –[19.1%] where the baseline assumes 1 SS burst for synchronization before PO reception - [16.0%] –[36.0%] where the baseline assumes 2 SS bursts for synchronization before PO reception - [14.3%] –[46.0%] where the baseline assumes 3 SS bursts for synchronization before PO reception - Some sources also evaluated performance if the original group paging rate is in the range between 20% and 60% and showed following results: - [8.0%] –[19.1%] where the baseline assumes 1 SS burst for synchronization before PO reception - [18.1%] –[34.0%] where the baseline assumes 2 SS bursts for synchronization before PO reception - [20.6%] –[42.0%] where the baseline assumes 3 SS bursts for synchronization before PO reception The additional power saving gains w.r.t. paging early indication without UE sub-grouping are given as follows: - If the original group paging rate is 10%: - [0.6%] –[2.7%] where the baseline assumes 1 SS burst for synchronization before PO reception - [0.6%] –[4.0%] where the baseline assumes 2 SS bursts for synchronization before PO reception - [0.6%] –[4.7%] where the baseline assumes 3 SS bursts for synchronization before PO reception - Some sources also evaluated performance if the original group paging rate is in the range between 20% and 60% and showed following results: - [1.3%] –[8.0%] where the baseline assumes 1 SS burst for synchronization before PO reception - [2.1%] –[13.0%] where the baseline assumes 2 SS bursts for synchronization before PO reception - [3.3%] –[16.1%] where the baseline assumes 3 SS bursts for synchronization before PO reception The number of UE sub-groups evaluated ranges from 2 to 16. The power saving gains are dependent on the assumptions about placement of PEI and PO relative to SSB. Note: It is FFS in RAN1 another group paging rate > 10% for the evaluation of Rel-17 paging enhancement. Note: Not all sources providing results for paging early indication without UE sub-grouping also provide results for paging early indication with UE sub-grouping. Agreements: Observation: For NR idle/inactive-mode UEs with 10% group paging rate, cross-slot scheduling with K0 = 1, which can be supported by Rel-15/Rel-16 for Type 2 CSS, can provide the following power saving gains w.r.t. same-slot scheduling (K0 = 0): - [<1%] –[2.5%] where the baseline assumes 1 SS burst for synchronization before PO reception - [<1%] -[1.6%] where the baseline assumes 2 SS bursts for synchronization before PO reception - [<1%] -[1.44%] where the baseline assumes 3 SS bursts for synchronization before PO reception One source shows that cross-slot scheduling with K0 = 32, which cannot be supported by Rel-15/Rel-16 for Type 2 CSS, can provide the following power saving gains w.r.t. same-slot scheduling (K0 = 0): - [0%] where the baseline assumes 1 SS burst for synchronization before PO reception - [6.3%] where the baseline assumes 3 SS bursts for synchronization before PO reception The power saving gain will become lower with higher group paging rate. Agreements: For NR idle/inactive-mode paging enhancement, paging early indication before paging occasion is supported from RAN1 perspective - FFS: Physical layer design based on DCI, SSS or TRS/CSI-RS - Send LS to inform RAN2 and kindly ask RAN2 to inform RAN1 if there is anything that RAN1 should take into consideration in the physical layer design for this feature, including any other progress RAN2 has made in this WI which may has RAN1 impact Draft LS in R1-2009754 is approved. Final LS in R1-2009801.

RAN1 #102-e meeting Agreements: For study of Rel-17 paging enhancement, the following are assumed as a baseline for FR1 and FR2: - Reference configuration for FR1/FR2 as specified in Section 8.1.1/8.1.2 of TR 38.840 - Note: the setting for some PDSCH parameters may not be applicable for RedCap UEs - Baseline paging cycle length: [1.28] second - SS burst related assumptions: - 20 ms periodicity - 2 ms duration for serving cell RRM measurement, which can overlap with the one for synchronization before PO - FFS time/frequency tracking - Measurement related assumptions: - 20 ms SMTC periodicity - 2 ms SMTC window for intra-frequency RRM measurement, assuming synchronized deployment - [5 ms SMTC window and 6 ms measurement gap for inter-frequency RRM measurement] - Note: RAN4 requirement assumes one frequency layer per measurement gap, and 0.5 ms is assumed for switch in/out a frequency layer - Note: the inclusion of potential TRS/CSI-RS occasions can be considered Agreements: The following power consumption model for FR1 is utilized for the evaluations of Rel-17 UE power saving enhancements in idle/inactive mode - FFS: FR2 power consumption model for idle/inactive mode operations Power State; Relative Power (FR1 reference from TR 8438.840); Relative Power (Idle/inactive-mode operation with reception bandwidth 20 MHz). Deep Sleep (PDS); 1; 1. Light Sleep (PLS); 20; 20. Micro sleep (PMS); 45; 45. PDCCH-only (PPDCCH); 100; 50Note. PDCCH + PDSCH (PPDCCH+PDSCH); 300; 120. PDSCH-only (PPDSCH); 280; 112. SSB/CSI-RS proc. (PSSB); 100 (synchronization or serving cell measurement); 50. Intra-frequency RRM measurement (Pintra);  150 (synchronous case, N=8, measurement only; Pintra, meas-only)  200 (combined search and measurement; Pintra, search+meas);  [60] (synchronous case, N=8, measurement only; Pintra, meas-only)  [80] (combined search and measurement; Pintra, search+meas). Inter-frequency RRM measurement (Pinter); · 150 (measurement only per freq. layer; Pinter, meas-only) · 150 (neighbor cell search power per freq. layer; Pinter, search-only) · Micro sleep power assumed for switch in/out a freq. layer; · [60] (measurement only per freq. layer; Pinter, meas-only) · [150] (neighbor cell search power per freq. layer; Pinter, search-only) · Micro sleep power assumed for switch in/out a freq. layer. Note: Power scaling to 20MHz reception bandwidth follows the rule in Section 8.1.3 of TR 38.840, i.e., max{reference power * 0.4, 50}.. Agreements: Group paging rate of 10% is assumed for the evaluation of Rel-17 paging enhancement - FFS: Another group paging rate > 10% - Note: If UE sub-grouping is applied, the sub-group paging rate can be reduced w.r.t. the total sub-group number for a PO Agreements: For the study on paging enhancements to reduce unnecessary paging reception, the following metrics are considered: - UE power saving gain (relative to a given feature or overall) - Impact to UE paging detection probability - FFS: Link level simulation assumptions - System impact, including - Additional resource overhead and its implications - Impact to Rel-15/Rel-16 idle/inactive-mode UEs and connected-mode UEs - Impact to other legacy functionalities, including SI change and ETWS indication - [Note: NW energy consumption evaluation is not precluded] Agreements: For the study of paging enhancement, 1, 2, or 3 SS burst processing is assumed before PO - Note: in choosing one or more values (1, 2, or 3) for the evaluations, companies to provide justification Agreements Send a LS with for evaluation methodology updates related to paging enhancement(s) to RAN2 - Draft LS in R1-2007355, which is endorsed, with final LS in R1-2007356 -> (typo fix) R1-2007425 Agreements: For the study on paging enhancements, the following LLS assumptions are considered. - For investigating the residual frequency error after one or multiple SS burst processing, at least -6 dB SNR should be considered Parameters; Values; Note. Carrier Frequency; 4GHz (FR1). Transmission BW; 20MHz (FR1). Antenna Configuration; 1/2TX and 2/4 RX; Companies to report. Channels; TDL-C or CDL-C 300 ns delay spread 100 Hz Doppler shift. Frequency error; Uniform distribution in the range [-X, +X]ppm Companies to report the utilized X value(s) with justification; Modelled at the input of the considered paging channel/early indication design(s). Paging PDCCH configuration; AL8, 41 info + 24 CRC bits, REG bundle size 6; Companies to report additional setting(s), e.g., CORESET duration, etc.. Paging PDSCH configuration; Mapping type A, MCS 0, 48 PRB, TB scaling 1, DMRS type 1 with 2 additional DMRS; Companies to report additional setting(s), e.g., other TB scaling factor, other DMRS type(s), etc.. Paging early indication design(s); Companies to report. Agreements: For potential paging enhancements, RAN1 to study the following candidate schemes: - Paging early indication before a target PO to indicate UE whether to monitor PDCCH scrambled with P-RNTI at the PO. Potential candidate indication methods include - DCI-based indication, e.g., based on - Extending existing DCI format 1_0 or 2_6 - New DCI format - RS-based or sequence-based indication, e.g., based on TRS/CSI-RS or SSS - Sub-grouping for paging, based on - Legacy paging DCI - Paging early indication - Additional reception occasions in time/frequency domain - Multiple P-RNTIs - Cross-slot scheduling for paging PDSCH - Other proposal is not precluded

Relating to scope item 1) – b): - Specify enhancements for idle/inactive-mode UE power saving, considering system performance aspects [RAN2, RAN1] - Specify means to provide potential TRS/CSI-RS occasion(s) available in connected mode to idle/inactive-mode UEs, minimizing system overhead impact [RAN1] - NOTE: Always-on TRS/CSI-RS transmission by gNodeB is not required The following agreements are achieved:

RAN1 #103-e Meeting Agreements: - Functionality of RRM measurement for neighbour cell is not supported for TRS/CSI-RS for idle/inactive UE(s). Agreements: - SIB signalling provides the configuration of TRS/CSI-RS occasion(s) for idle/inactive UE(s). - Up to RAN2 to decide which SIB is to be used. - Whether or not to additionally support other high-layer signalling methods (e.g., dedicated RRC, RRC release message, etc.) is up to RAN2 Send an LS to RAN2 informing the above agreements, and - To further add that RAN1 is working on the detailed physical layer design Draft LS is endorsed, with final LS in R1-2009791. R1-2009848 Agreements: - Aperiodic TRS and semi-persistent/aperiodic CSI-RS are not used as TRS/CSI-RS occasion(s) for idle/inactive UEs. Agreements: - Target sending an LS to RAN2 and RAN4 to ask whether it is feasible to allow a UE to use the potential TRS/CSI-RS occasion to enhance the SSB based IDLE/Inactive mode evaluations of the serving cell. (to also include agreements from last meeting) * Further discussion whether any additional information needs to be included in the LS or not, including potential re-wording of the leading sentence Agreements: - Discuss further based on the following alternatives and down-select at RAN1#104-e: - Alt 1: The availability of TRS/CSI-RS at the configured occasion(s) is NOT informed to the UE. - Alt 2: The availability of TRS/CSI-RS at the configured occasion(s) is informed to the UE. - Alt 3. The conditional availability of TRS/CSI-RS at the configured occasion(s) is informed to the UE. - The condition can be, e.g., existence of paging. - Alt 4. Combination of the above alternatives. - FFS for details - FFS for UE behavior when the availability is not informed. - Other techniques are not precluded. - Companies encourage to provide sufficient information for the proposal, e.g., - how to achieve power saving gain - how to minimize impact on NW how to minimize extra UE implementation complexity - feasibility check on sharing the TRS/CSI-RS between connected UEs and idle/inactive UEs - Proposals should be consistent with the WID objective. Conclusion: - TRS/CSI-RS based PEI is discussed in AI 8.7.1.1. - PEI functionality is not further discussed under AI 8.7.1.2. - Note: This does not prevent to potentially use PEI to carry the indication for TRS/CSI-RS presence.

RAN1 #102-e Meeting Agreements: - New types/patterns of TRS/CSI-RS are not introduced specifically for idle/inactive mode UE. Agreements: The TRS/CSI-RS occasion(s) that may be for connected mode UEs can be shared to idle/inactive mode UEs. - Note: It is understood that gNB can potentially share the occasions to idle/inactive (which would just mean it up to NW whether to share or not share). - Note: It is understood that TRS/CSI-RS in the TRS/CSI-RS occasion(s) may or may not be transmitted. - Note: Always-on TRS/CSI-RS transmission by gNodeB is not required - At least TRS/CSI-RS occasion(s) corresponding to periodic TRS is supported - FFS for other RS types - FFS: Whether UE blind detection is required or not. Agreements: Idle/inactive UE may use the TRS/CSI-RS occasion(s) that are shared to it for functionalities such as: - AGC, time/frequency tracking - FFS: RRM measurement for serving cell, RRM measurement for neighbor cell, paging reception indication Observation: It is up to gNB implementation whether or not to transmit a TRS/CSI-RS to idle/inactive UEs even when the TRS/CSI-RS is not needed by connected UEs (e.g., when there is a connected mode UE in a cell but the UE is no longer using the TRS/CSI-RS, or when there is no longer connected mode UE in a cell, etc.) Agreements: The configuration of TRS/CSI-RS occasion(s) for idle/inactive mode UE(s) is provided by higher layer signalling - FFS higher layer signalling candidates (e.g., SIB, dedicated RRC, RRC release message, etc.) - FFS for other signalling candidates (e.g., pre-configuration, etc.) - FFS for detailed configuration parameters (e.g., whether and how to reduce the signalling overhead for configuration, etc.) Agreements: Further study whether and how to inform the availability of TRS/CSI-RS to idle/inactive mode UE (implicitly or explicitly). - Note: Availability corresponds to the information for whether TRS/CSI-RS is actually transmitted or not.

Relating to scope item 2) – a): - Study and specify, if agreed, enhancements on power saving techniques for connected-mode UE, subject to minimized system performance impact [RAN1, RAN4] - Study and specify, if agreed, extension(s) to Rel-16 DCI-based power saving adaptation during DRX Active Time for an active BWP, including PDCCH monitoring reduction when C-DRX is configured [RAN1] - NOTE: Rel-15 and Rel-16 available power saving solutions should be supported by the UE and included in the evaluation. RAN1 will ask the confirmation from RAN2 that Rel-15 and Rel-16 available power saving solutions are properly utilized. The following agreements are achieved:

RAN1 #103-e Meeting Agreements: Observation: - Each of the following schemes is individually shown to be beneficial for UE power saving compared to the baseline. - Dynamically switching search space set - Dynamically skipping PDCCH monitoring for a certain duration or until next DRX ON - At least the following Rel-15 and/or Rel-16 power saving solutions have been utilized for baseline, - For eMBB traffic, - DRX setting(including using short DRX or long DRX with a short IAT or long IAT), Wake-up signal, Cross-slot scheduling, CA/Scell dormancy, MAC-CE skipping, BWP switching - For VoIP traffic, - DRX setting(only long DRX cycle with a short IAT), Wake-up signal, Cross-slot scheduling, MAC-CE skipping - For IM traffic, - DRX setting(long DRX cycle [with a short IAT]), Wake-up signal - For intensive eMBB traffic, - DRX setting(including using short DRX or long DRX with a short IAT), Wake-up signal, Cross-slot scheduling, [CA/Scell dormancy], MAC-CE skipping, BWP switching - Note: intensive eMBB traffic is optional and companies may use FTP model 3 with different packet size and mean data arrival time, e.g., 15ms, 30ms, 50ms or 100ms. - Note 1: For Search space switching, switching from 1slot monitoring to 2, 4, 8, 10, 16 or 32 slot with 30kHz SCS (FR1) and 120kHz (FR2) is utilized. - Note 2: For PDCCH skipping , skipping 2ms, 4ms, 5ms, 8ms, 15ms, 16ms, 32ms, 64ms or to next DRX cycle is utilized - Note 3: the baseline assumed may vary across companies Agreements: - Specify at least one of the following options for Rel-17 dynamic PDCCH adaptation in time-domain for active time, - Option 1: Search space set group switching,e.g., potential adjustments/enhancements forincluding explicit and implicit search spaceset group switching specified in R16 for NR-U - Option 2: PDCCH skipping for a certain duration / DRX cycle - FFS: which option(s)(e.g. taking into account additional gain of option 1 over option 2, or vice-versa) - Candidate DCI formats for dynamic PDCCH adaptation include DCI formats 1_1(including scheduling and non-scheduling DCI), 0_1, 1_2, 0_2, 2_0, 2_6. - Note: - Companies are encouraged to provide analysis on specification impact, power saving benefit and system impact (e.g., packet latency, system overhead) - FFS: other schemes are not precluded for further study

RAN1 #102-e Meeting Agreements: - Reusing power model in TR38.840 for evaluation of DCI-based power saving adaptation schemes. - Note: company reporting additional power model for missing state or update is not precluded. Agreements: - Company should report assumptions used for periodic measurement activities for the Rel-17 DCI-based power saving adaptation evaluation. - The periodic activities defined in TR38.840 can be reused. - Measurement for RLM/BFD every C-DRX cycle can be optionally modelled Agreements: - The performance metrics described in TR38.840 section 8.2 is reused for power saving evaluation of Rel-17 DCI-based power saving adaptation during ActiveTime. - The following Rel-15 / 16 features is recommended of the power consumption as reference for baseline. Company can report the feature(s) being used in the baseline. - DRX - C-DRX cycle 40msec for VoIP - 10ms IAT, 8ms On-duration - Assume max two packets bundled - C-DRX cycle 160msec for FTP - Alt 1: 20 msec IAT, 8ms On-duration - Alt 2: short DRX - 20 ms [or 40ms as optional] IAT, 8ms On-duration - 20 ms for short DRX cycle, 4 cycles - Note: 100 msec IAT, 8ms On-duration can also be used with sufficient justifications that available Rel-15/16 Techniques being used to reduce UE power saving - DCP for DRX adaptation, - DCP offset to DRX ON = 2 ms, other values are not precluded - Cross-slot scheduling adaptation - Minimum K0 can be adapted from 0 to 1 for FR1, 0 to [4] for FR2 - BWP switching, including - MIMO layer adaptation, - Max # of MIMO layer can be adapted from 4 layer to 2 layer for FR1, 2 layer to 1 layer for FR2 - PDCCH monitoring period adaptation - PDCCH monitoring period can be adapted from per slot monitoring to X slot monitoring - X = [2] for FR1 and [8] for FR2 - Bandwidth adaptation - Bandwidth can be adapted from 100MHz to 20MHz for FR1,FFS for FR2 - Note: - BWP transition time type 2 is assumed, BWP transition duration is - 5 slot @ 30kHz SCS for FR1, - 18 slot@120kHz SCS for FR2 - the slot-average power level for BWP transition duration is according to TR38.840 - BWP transition time type 1 can be optional modelled - BWP switching is Y (ms) after last packet/data burst. - Y = [8], other values are not precluded - Whether BWP switching is modeled depends on the assumed UE capability and evaluated schemes. - Scell dormancy assumption for CA capable UEs - FR1 & FR2: SCell dormancy with [160 ms] periodic CSI measurement and reporting - Other settings - CA assumption if configured for CA capable UEs - For FR1, FFS - For FR2, 4*100MHz can be considered. - Assumptions for scheduler - For FR1, no restriction on the beam assumptions being used in each slot - For FR2, up to each company, e.g., gNB equally schedule the slots for UEs targeting to different beams. - Note: the assumptions does not necessary mean to restrict or precluded any implementation. Other assumptions are not precluded and can be reported by companies. - Company to report the used assumption for the interruption and also power savings impact due to presence/absence of interruptions . Agreements: Legacy traffic models in TR38.840 can be considered for Rel-17 DCI-based power saving adaptation evaluation, other traffic models can be optionally modelled and company report which traffic model(s) is used. Update on 8/28: Draft LS is approved (with generic RAN2 action), with final LS in R1-2007419.

#### 2.1.2	Remaining open issues

RAN1 agrees to specify the enhancements for idle/inactive-mode power saving, relating to scope item 1)-a), and for connected-mode power saving, relating to scope item 2)-a). It remains for RAN1 to decide the physical layer details. In particular, the following are the remaining open issues:

- For scope item 1) - a):

  - Specify physical layer design based on DCI, SSS or TRS/CSI-RS for paging early indication before paging occasion

  - Discuss the feasibility and limitation of incorporating other paging enhancement scheme(s), including UE sub-grouping and/or cross-slot scheduling

- For scope item 1) - b):

  - Discuss and decide whether and how gNodeB to indicate the availability of TRS/CSI-RS at the configured occasion(s) for idle/inactive-mode UEs

  - Specify details for the configuration of TRS/CSI-RS for idle/inactive mode UEs

- For scope item 2) - a):

  - Specify at least one of Option 1 and Option 2. Note that other schemes are not excluded.

## 2.2	RAN2

#### 2.2.1	Agreements

Relating to scope item 1) - a) - Specify enhancements for idle/inactive-mode UE power saving, considering system performance aspects [RAN2, RAN1] - Study and specify paging enhancement(s) to reduce unnecessary UE paging receptions, subject to no impact to legacy UEs [RAN2, RAN1] - NOTE: RAN1 to check and update, if needed, evaluation methodology in RAN1 #102-e meeting The following agreements are achieved:

- RAN2 #112-e Meeting Confirm that UE grouping is considered a candidate of paging enhancement for UE power saving RAN2 have discussed and considered “paging indication for UE subgroups using paging DCI”, “paging early indication or wake-up signal (WUS) for UE subgroups”, “cross-slot scheduling of paging for UE subgroups”. RAN2 understands that RAN1 have started to evaluate performance and complexity. RAN2 assumes that RAN1 continues with this evaluation, in order that decisions can be made regarding the paging indication/scheduling solution. As R2 is the leading group for this WI objective it is expected that final decisions are made by R2. Will send an LS to R1 (action to be discussed offline). The solution of PRNTI based group discrimination is deprioritized from RAN2 perspective The solution of “paging for UE subgroups using different time/frequency resources” is de-prioritized from RAN2 perspective. [AT112-e][047][ePowSav] LS on Paging enhancement (Mediatek) Scope: LS covering decisions and clarifying work split to the extent possible. Intended outcome: Approved LS to R1 (R2-2010884) Deadline: EOM [Post112-e][0xx][Pow17] Paging subgroup determination () Scope: For how to determine which paging subgroup a UE belongs to, several methods have been proposed, applying hash based on UE-ID similar to today, take into account paging probability, power consumption sensitivity etc. Objective to pave the way for agreements next meeting. Quantitative analysis argumentation is allowed (this is RAN2 scope). Intended outcome: Report Deadline: Long

- RAN2 #111-e Meeting For PowSav solutions for Idle/Inactive (for smart phones) that can easily also be applied to redcap, R2 assume they may be applied. Details FFS and to be discuss case by case when the maturity is high (might in the end just be a question of UE caps). Dual DRX not in the scope of current WID. [Post111-e][xxx][ePowSav] UE grouping (Mediatek) Scope: UE grouping, put solutions on the table, describe intentions / how they work (high level), and their potential to save power. Possibly take into account R1 evalaution methodology (if they have agreements on the evaluation parameters). Intended outcome: Report Deadline: Long

#### 2.2.2	Remaining open issues

For scope item 1) – a), RAN2 will continue to study and specify, if agreed, UE grouping for paging enhancement, including paging subgroup determination.

For scope item 1) – b), as requested in RAN1 LS, R1-2009848, RAN2 will discuss and decide whether or not to additionally support other high-layer signalling methods (e.g., dedicated RRC, RRC release message, etc.) in order to provide the configuration of TRS/CSI-RS occasion(s) for idle/inactive UE(s).

## 2.3	RAN3

#### 2.3.1	Agreements: N/A (RAN3 is not involved in the WI)

#### 2.3.2	Remaining Open issues: N/A

## 2.4	RAN4

#### 2.4.1	Agreements

Relating to scope item 2) - b) - Study and specify, if agreed, enhancements on power saving techniques for connected-mode UE, subject to minimized system performance impact [RAN1, RAN4] - Study the feasibility and performance impact of relaxing UE measurements for RLM and/or BFD, particularly for low mobility UE with short DRX periodicity/cycle, and specify, if agreed, relaxation in the corresponding requirements [RAN4] - NOTE: Supplementary RAN2 work, if needed, can be triggered by RAN4 LS The following agreements are achieved:

RAN4 #97-e Meeting Approved: WF on NR UE Power Saving Enhancements (R4-2017269) Issue 2-1-1: Evaluation assumption for SLS on mobility impact - Evaluation assumptions are in section 2 of R4-2017306 - Note: Further updates in future meetings are not precluded. Issue 2-1-2: Evaluation assumption for power consumption - Power consumption model in 38.840 is used as the starting point of evaluation assumption. Other options are not precluded, e.g., - LS R1-2007419 - VoIP traffic model as in TR 38.840 - Evaluation assumptions in section 3 of R4-2017306 - Note: Further updates in future meetings are not precluded. Issue 2-1-3: From configuration perspective, factors to be studied and evaluated for RLM/BFD relaxation - At least the following factors are prioritized for RLM/BM relaxation study, - DRX cycle (option 1) for both 20ms and 40ms cycle length - The following factors can also be considered for evaluation. Companies are encouraged to evaluate the following factors and clarify the corresponding assumption. - Option 2: RS configurations, - 2a: RLM/BFD-RS types - 2b: Periodicity of SSB or CSI-RS resource - 2c: BW of RLM/BFD-RS types - 2d: the relation to RSs for RRM - 2e: relation to RS for other L1 measurement - 2f: WUS is applied or not - Option 3: N factor (# of RX beams for FR2) - Option 4: P (scale factor with consideration of overlap with measurement gap and/or SMTC window) Issue 2-2-2: Evaluation metrics, system impact aspects - Study the system impact of relaxed RLM/BFD measurements, taking in to account the following evaluation metrics: - increased latency in RLF triggering (for RLM) - increased latency in beam failure detection and the initiation of beam recovery procedure (for BFD) - Delta SINR as one of the performance statistic to evaluate the RLM/BFD performance impact - RAN4 to discuss the impact of RLM/BM relaxation on PDCCH monitoring. Issue 2-3-1: Scheme of RLM/BFD measurements relaxation - At least extending evaluation period of RLM/BFD measurement (Option 1) to be considered as the scheme of RLM/BFD measurements relaxation. FFS schemes as follows - Option 1a: RAN4 to further discuss use of a scaling factor for defining the relaxed RLM/BM evaluation period and indication intervals. - Option 2: Reducing the number of candidate beams when UE fulfilled relaxed criteria can be a feasible way to reduce power consuming. - Option 3: Reducing the number reducing the sample number. Issue 2-3-2: Criteria which the UE is allowed to relax the RLM/BM requirements - RAN4 to further study the criteria which the UE is allowed to relax the RLM/BM requirements, according to UE mobility and/or serving cell’s quality. - Note: The options discussed in RAN4 97e meeting are listed below for information. - Option 1: UE mobility - 1a: Low mobility criteria, e.g. R16 RRM relaxation criterion can be used as a starting point. - 1b: other solutions. - Option 2: Serving cell’s quality (e.g. RSRP, SINR) - 2a: at-cell-center criteria, e.g. R16 RRM relaxation criterion can be used as a starting point. - 2b: the measured SINR is above one additional threshold (e.g. SINR > 2dB). - 2c: other solutions. Issue 2-3-3: Network or UE to determine if the criteria for relaxation is fulfilled The following options are FFS - Option 1: Low mobility scenario under which the UE is allowed to relax the RLM/BM requirements is determined by the network. - Option 2: Low mobility scenario under which the UE is allowed to relax the RLM/BM requirements is determined by the UE. - Option 3: Low mobility scenario under which the UE is allowed to relax the RLM/BM requirements is determined by both the network and UE. Issue 2-4-1: Reverting to the normal RLM operation The following options are FFS - Option 1: The UE while performing relaxed RLM upon detecting certain number of out-of-sync indications or upon triggering T310 reverts to the normal RLM operation (i.e. without relaxation). - Other options are not precluded Issue 2-4-2: Reverting to the normal BM operation The following options are FFS - Option 1: The UE while performing relaxed BFD upon beam failure detection reverts to the normal BFD operation (i.e. without relaxation). - Other options are not precluded Issue 2-4-3: Relaxation of BM when not all serving cells in intra-band CA/DC meets relaxation criteria - RAN4 to further discuss the relaxation of BFD when not all serving cells in intra-band CA/DC meets relaxation criteria. - The following options are FFS - Option 1A: relax on all serving cells when the relaxed criteria is fulfilled in one serving cell. - Option 1B: relax only on serving cells where the relaxed criteria is fulfilled. - Option 1C: Other solutions Approved: Evaluation assumptions for R17 RLM/BFD relaxation (R4-2017306) System level simulation assumptions for mobility impact analysis from RLM/BFD relaxation The intention of this evaluation is to justify the mobility impact of RLM/BFD relaxation under different scenarios. For FR1 and FR2, the evaluation assumption is provided in Table I. Table I Evaluation assumptions for mobility impact of RLM/BFD relaxation in FR1 and FR2 Parameters; Dense urban (UMi) in FR1; Dense urban (UMi) in FR2. UE speed; 3km/h; 30km/h. Relaxation factor (X); 2, [3], 4, [8] Note: For DRX cycle <=320 ms, “1.5” factor is considered in the R15/R16 baseline.; 2, [3], 4, [8] Note: For DRX cycle <=320 ms, “1.5” factor is considered in the R15/R16 baseline.. DRX cycle length; 20ms, 40ms. Layout; Single layer: Macro layer: Hex. Grid. Moving across Boarder; Option 1: Wrap around as defined in 36.839 [1] Option 2: Bouncing back as defined in 36.839 [1]. Inter-BS distance; 200m; 200m. Carrier frequency and SCS; 4GHz and 30kHz SCS for SSB; 30GHz and 120kHz SCS for SSB. Simulation bandwidth; 20MHz (for CORESET0 BW); 80MHz (for CORESET0 BW). N factor (# of RX beams for FR2); N.A.; 8 for SSB, 1 for CSI-RS. SSB multiplex with Data; No. LoS probability; According to Table 7.4.2-1 in TR 38.901 [2]. Pathloss and shadow fading std.; Refer to UMi model in TR38.901 [2]. Shadow fading correlation distance; 10 for LOS and 13 for NLOS. BS Tx power (PA power); 44dBm; 40dBm. UE receiver noise figure; 9dB; 13dB. UE distribution; 100% outdoor. BS antenna height; 10m. UE antenna height; 1.5m. BS antenna element gain + connector loss; Follow 38.802 [3] Table A.2.1-4. UE antenna model; Follow 38.802 [3] Table A.2.1-4; Follow 38.802 [3] Table A.2.1-4 (M,N,P,Mg,Ng) = Option 1: (1,2,2,1,2) Option 2: (2,2,2,1,2) Θmg,ng=90°; Ω0,1=Ω0,0+180°; (dg,H, dg,V)=(0,0) Note: only one of panels should be selected. UE beam sweeping; No; Yes. # of beams: N = 8. BS antenna down-tilt; 15 degree. BS array configuration; (M,N,P,Mg,Ng) = Option 1: (8,8,2,1,1) Option 2: (2,4,2,1,1) (dH,dV) = Option 1: (0.5, 0.8)λ Option 2: (0.5, 0.9)λ +45°, -45° polarization; (M,N,P,Mg,Ng) = Option 1: (4,8,2,1,1) Option 2: (4,8,2,2,2) (dH,dV) = (0.5, 0.5)λ, (dg,H,dg,V) = (4.0, 2.0)λ +45°, -45° polarization. BS beam set; For direction of analog beam steering (in LCS): Azimuth angle φi = [-45, -15, 15, 45] degree Zenith angle θj = [90,115] degree Note: Other options are not precluded.; For direction of analog beam steering (in LCS): Azimuth angle φi = [-60, -42.86, -25.71, -8.57, 8.57, 25.71, 42.86, 60] degree Zenith angle θj = [90, 100, 110, 120] degree Note: Other options are not precluded.. The UE performs signal and interference measurements based on RLM-RS (i.e. SSB or CSI-RS) to derive a downlink link quality metric, and SINR is considered here for simplicity. The performance metric of this evaluation can be - increased latency in RLF triggering (for RLM) - increased latency in beam failure detection and the initiation of beam recovery procedure (for BFD) - the CDF curves of Delta SINR comparison between R15 an R17. - Delta SINR = (estimated SINR_R17– estimated SINR_R15) [dB]. As one reference, the definition of Delta SINR in R15 is - Delta SINR = (estimated SINR – ideal SINR) [dB]. Evaluation assumptions for power saving benefits from RLM/BFD relaxation This evaluation is going to provide power consumption comparison between relaxed RLM/BFD and R15/R16 baseline. The evaluation is based on power model in annex of TR 38.840 [4] and some further evaluation assumptions are provided in Table II as follows. Table II Evaluation assumptions for power saving gain of RLM/BFD relaxation Parameters; FR1; FR2. longDRXCycle; 40ms for VoIP traffic models; 160ms for FTP Model 3 Note: Other options are not precluded; 40ms for VoIP traffic models; 160ms for FTP Model 3 Note: Other options are not precluded. OnDurationTimer; 4ms for VoIP traffic models; 8ms for FTP Model 3 Note: Other options are not precluded; 4ms for VoIP traffic models; 8ms for FTP Model 3 Note: Other options are not precluded. Drx_InactiveTimer; 4ms for VoIP traffic models; 20ms for FTP Model 3 Note: Other options are not precluded; 4ms for VoIP traffic models; 20ms for FTP Model 3 Note: Other options are not precluded. Slot length; 0.5ms; 0.125ms. Relaxation factor (X); 2, [3], 4, [8] Note: For DRX cycle <=320 ms, “1.5” factor is considered in the R15/R16 baseline.; 2, [3], 4, [8] Note: For DRX cycle <=320 ms, “1.5” factor is considered in the R15/R16 baseline.. PDCCH-WUS configuration; Option 1: Yes WUS offset: 4 slot No wake-up if WUS is missed Option 2: No; Option 1: Yes WUS offset: 4 slot No wake-up if WUS is missed Option 2: No. Traffic Model; Option 1: FTP Model 3 0.1Mbytes packet size 200ms mean inter-arrival time (Note: Other options are not precluded) Option 2: VoIP traffic models in TR 38.840; Option 1: FTP Model 3 0.1Mbytes packet size 200ms mean inter-arrival time (Note: Other options are not precluded) Option 2: VoIP traffic models in TR 38.840. RLM-RS periodicity; SSB: 20 ms CSI-RS: TBD; SSB: 20 ms CSI-RS: TBD. RRM-RS periodicity; SSB(SMTC periodicity): 20ms Note: Other options are not precluded.; SSB(SMTC periodicity): 20ms Note: Other options are not precluded.. UL transmission; Interested companies are encouraged to consider this and claim the detailed assumptions when delivering results.. BW of RLM/BFD-RSs; Interested companies are encouraged to consider this and claim the detailed assumptions when delivering results.. RS for L1 measurements; Interested companies are encouraged to consider this and claim the detailed assumptions when delivering results.. Approved: Work Plan of R17 UE Power Saving Enhancements WI (R4-2017270)

#### 2.4.2	Remaining open issues

With the above, the following are remaining open issues for RLM/BFD relaxation in RAN4:

- Scheme of RLM/BFD measurements relaxation

- Criteria which the UE is allowed to relax the RLM/BM requirements

- Network or UE to determine if the criteria for relaxation is fulfilled

- Reverting to the normal RLM operation

- Reverting to the normal BM operation

- Relaxation of BM when not all serving cells in intra-band CA/DC meets relaxation criteria

## 2.5	RAN5

#### 2.5.1	Agreements: N/A (RAN5 is not involved in the WI)

#### 2.5.2	Remaining Open issues: N/A

#### 2.5.3	Remaining Open issues with cross-WG dependencies: N/A

## 2.6	RAN6

#### 2.6.1	Agreements: N/A (RAN6 is not involved in the WI)

#### 2.6.2	Remaining Open issues: N/A

## 3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

## 3.1	SAx/CTs

#### 3.1.1	Agreements with cross-TSG impacts: N/A

#### 3.1.2	Remaining Open issues with cross-TSG impacts: N/A

## 4.	References

RAN1 Contributions

RAN1 #103-e Meeting - Potential paging enhancements: R1-2007600 Paging enhancement(s) for UE power saving in IDLE/inactive mode Huawei, HiSilicon R1-2007673 Paging enhancements for idle/inactive mode UE power saving vivo R1-2007867 Paging enhancement for UE power saving CATT R1-2007890 Potential paging enhancements TCL Communication Ltd. R1-2007898 Paging enhancement for power saving Beijing Xiaomi Software Tech R1-2007971 Discussion on power saving enhancements for paging ZTE R1-2008021 Discussion on paging enhancement CMCC R1-2008053 Discussion on potential paging enhancements LG Electronics R1-2008103 Discussion on potential paging enhancements Spreadtrum Communications R1-2008175 Discussion on paging enhancements Samsung R1-2008265 Further discussion on Paging enhancements for power saving OPPO R1-2008287 Potential paging enhancements for idle/inactive-mode UE power saving Panasonic R1-2008368 Paging enhancement for idle/inactive mode UE Sony R1-2008474 Paging enhancements for idle/inactive-mode UE power saving Apple R1-2008689 Paging enhancements for UE power saving InterDigital, Inc. R1-2008933 On paging enhancements for UE power saving Nokia, Nokia Shanghai Bell R1-2008964 Paging enhancements for idle/inactive-mode UE power saving MediaTek Inc R1-2008992 On paging enhancements for UE power saving Intel Corporation R1-2009105 Paging enhancement for UE power saving Lenovo, Motorola Mobility R1-2009187 Discussion on paging enhancements NTT DOCOMO, INC. R1-2009200 Discussion on potential paging enhancements for UE power savings Ericsson R1-2009266 Paging enhancements and evaluation methodology Qualcomm Incorporated - TRS/CSI-RS occasion(s) for idle/inactive UEs R1-2007601 Assistance RS occasions for IDLE/inactive mode Huawei, HiSilicon R1-2007674 TRS/CSI-RS occasion(s) for idle/inactive UEs vivo R1-2007868 Configuration of TRS/CSI-RS for paging enhancement CATT R1-2007891 TRS/CSI-RS occasion(s) for idle/inactive UEs TCL Communication Ltd. R1-2007899 TRS CSI-RS occasion(s) for idle inactive UEs Beijing Xiaomi Software Tech R1-2007972 Reference signal for RRC idle and inactive UEs ZTE R1-2008022 Discussion on TRS/CSI-RS occasion(s) for idle/inactive-mode UEs CMCC R1-2008054 Discussion on TRS/CSI-RS occasion(s) for idle/inactive UEs LG Electronics R1-2008176 Discussion on TRS/CSI-RS occasion(s) for idle/inactive Ues Samsung R1-2008177 Discussion on DCI-based power saving techniques Samsung R1-2008266 Further discussion on RS occasion for idle/inactive UEs OPPO R1-2008288 Potential enhancements for TRS/CSI-RS occasion(s) for idle/inactive Ues Panasonic R1-2008369 Considerations on TRS/CSI-RS occasion(s) for idle/inactive mode UE Sony R1-2008475 Indication of TRS/CSI-RS for idle/inactive-mode UE power saving Apple R1-2008690 Discussion on TRS/CSI-RS occasion(s) for idle/inactive UEs InterDigital, Inc. R1-2008934 On RS information to IDLE/Inactive mode Ues Nokia, Nokia Shanghai Bell R1-2008965 On TRS/CSI-RS occasion(s) for idle/inactive mode UE power saving MediaTek Inc. R1-2008993 Discussion on TRS/CSI-RS reception during idle/inactive mode Intel Corporation R1-2009106 Provision of TRS/CSI-RS for idle/inactive UEs Lenovo, Motorola Mobility R1-2009151 Consideration on TRS/CSI-RS occasion(s) for idle/inactive UEs Spreadtrum R1-2009188 Discussion on TRS/CSI-RS occasion for idle/inactive UEs NTT DOCOMO, INC. R1-2009201 Provisioning of potential TRS/CSI-RS occasion(s) for Idle/Inactive UEs Ericsson R1-2009267 TRS CSI-RS for idle and inactive UE power saving Qualcomm Incorporated - Potential extension(s) to Rel-16 DCI-based power saving adaptation during DRX Active Time R1-2007602 Extension(s) to Rel-16 DCI-based power saving adaptation for an active BWP Huawei, HiSilicon R1-2007676 Discussion on DCI-based power saving adaptation in connected mode vivo R1-2007701 Extension to Rel-16 DCI-based power sabing adaptation during DRX Active Time GDCNI R1-2007870 PDCCH monitoring adaptation CATT R1-2007974 Extension to Rel-16 DCI-based power saving adaptation during DRX Active Time ZTE R1-2008023 Discussion on PDCCH monitoring reduction during DRX active time CMCC R1-2008055 Discussion on DCI-based power saving adaptation during DRX ActiveTime LG Electronics R1-2008267 Discussion on DCI-based power saving adaptation OPPO R1-2008289 Potential extension(s) to Rel-16 DCI-based power saving adaptation during DRX ActiveTime Panasonic R1-2008476 Enhanced DCI-based power saving adapation Apple R1-2008691 PDCCH-based power saving signal design considerations InterDigital, Inc. R1-2008711 DCI-based Power Saving Enhancements Fraunhofer HHI, Fraunhofer IIS R1-2008714 Power saving adaptation during Active Time ASUSTeK R1-2008935 UE power saving enhancements for Active Time Nokia, Nokia Shanghai Bell R1-2008966 Discussion on DCI-based power saving adaptation during DRX active time MediaTek Inc. R1-2008994 On PDCCH monitoring reduction techniques during active time Intel Corporation R1-2009056 Discussion on extension(s) to Rel-16 DCI-based power saving adaptation Asia Pacific Telecom co. Ltd R1-2009107 Enhanced DCI based power saving adaptation Lenovo, Motorola Mobility R1-2009150 Discussion on power saving techniques for connected-mode UE Spreadtrum R1-2009189 Discussion on extension to DCI-based power saving adaptation NTT DOCOMO, INC. R1-2009203 Discussion on potential enhancements for power savings during active time Ericsson R1-2009268 DCI-based power saving adaptation during DRX ActiveTime Qualcomm Incorporated R1-2009299 On power saving adaptation during the DRX active time Sony - Others R1-2007675 Discussion on paging grouping vivo R1-2007869 Link level performance of IDLE UE for UE power saving CATT R1-2007973 Additional simulation results of UE power consumption in RRC idle and inactive state ZTE R1-2008335 Analysis on power consumption for IDLE mode UE Huawei, HiSilicon R1-2009202 High-level UE energy consumption profiling Ericsson R1-2009300 On network power consumption model Nokia, Nokia Shanghai Bell R1-2007677 Discussion on RAN2 and RAN4 related power saving relaxation vivo R1-2007871 Feature interaction between Secondary DRX group and DCP/SCell dormancy CATT R1-2007975 Further discussion on potential power saving schemes for RRC connected UEs ZTE R1-2008268 Discussion on RLM relaxation OPPO R1-2008330 Other considerations on power saving in Rel-17 Huawei, HiSilicon R1-2008477 Power saving evaluation for RLM/BFD relaxation Apple R1-2009204 Evaluation of additional UE power saving schemes Ericsson

RAN1 #102-e Meeting - Potential paging enhancements: R1-2005388 Discussion on paging enhancements for idle/inactive mode UE power saving vivo R1-2005615 Evaluation methodology and paging enhancement for idle/inactive mode UE power saving MediaTek Inc. R1-2005262 Paging enhancement(s) for UE power saving in IDLE/inactive mode Huawei, HiSilicon R1-2005520 Discussion on power saving enhancements for paging ZTE R1-2005582 Considerations on paging enhancements Sony R1-2005719 Paging enhancement for UE power saving CATT R1-2005738 Paging enhancement for power saving Beijing Xiaomi Software Tech R1-2005773 Potential paging enhancements TCL Communication Ltd. R1-2005884 On paging enhancements for UE power saving Intel Corporation R1-2005935 Power efficient paging Lenovo, Motorola Mobility R1-2006041 Paging enhancements for power saving OPPO R1-2006157 On potential paging enhancements Samsung R1-2006221 Discussion on paging enhancement CMCC R1-2006291 Discussion on potential paging enhancements Spreadtrum Communications R1-2006311 Discussion on potential paging enhancements LG Electronics R1-2006385 Potential paging enhancements for idle/inactive-mode UE power saving Panasonic R1-2006527 Potential paging enhancements for idle/inactive-mode UE power saving Apple R1-2006544 Paging enhancements for UE power saving InterDigital, Inc. R1-2006665 Discussion on potential paging enhancements for UE power savings Ericsson R1-2006736 Discussion on paging enhancements NTT DOCOMO, INC. R1-2006815 Paging enhancements and evaluation methodology Qualcomm Incorporated R1-2006896 On paging enhancements for UE power saving Nokia, Nokia Shanghai Bell - TRS/CSI-RS occasion(s) for idle/inactive UEs R1-2006158 On TRS/CSI-RS occasion(s) for idle/inactive UEs Samsung R1-2006386 Potential enhancements for TRS/CSI-RS occasion(s) for idle/inactive UEs Panasonic R1-2005263 Assistance RS occasions for IDLE/inactive mode Huawei, HiSilicon R1-2005389 Discussion on TRS/CSI-RS occasion(s) for idle/inactive UEs vivo R1-2005521 Reference signal for RRC idle and inactive UEs ZTE R1-2005583 On the usage of TRS/CSI-RS for the UE in Idle Mode Sony R1-2005616 On TRS/CSI-RS occasion(s) for idle/inactive mode UE power saving MediaTek Inc. R1-2005720 Configuration of TRS/CSI-RS for paging enhancement CATT R1-2005739 Discussion on TRS CSI-RS occasions for idle/inactive UEs Beijing Xiaomi Software Tech R1-2005885 Discussion on TRS/CSI-RS reception during idle/inactive mode Intel Corporation R1-2006042 RS occasion for idle/inactive UEs OPPO R1-2006222 Discussion on potential TRS CSI-RS occasion(s) for idle/inactive UEs CMCC R1-2006269 Consideration on TRS/CSI-RS occasion(s) for idle/inactive UEs Spreadtrum Communications R1-2006312 Discussion on TRS/CSI-RS occasion(s) for idle/inactive UEs LG Electronics R1-2006528 Indication of TRS/CSI-RS for idle/inactive-mode UE power saving Apple R1-2006666 Provisioning of potential TRS/CSI-RS occasion(s) for Idle/Inactive UEs Ericsson R1-2006737 Discussion on TRS/CSI-RS occasion for idle/inactive UEs NTT DOCOMO, INC. R1-2006816 TRS/CSI-RS for idle/inactive UE power saving Qualcomm Incorporated R1-2006897 On RS information to IDLE/Inactive mode UEs Nokia, Nokia Shanghai Bell - Potential extension(s) to Rel-16 DCI-based power saving adaptation during DRX Active Time R1-2006738 Discussion on extension to DCI-based power saving adaptation NTT DOCOMO, INC. R1-2005264 Extension(s) to Rel-16 DCI-based power saving adaptation for an active BWP Huawei, HiSilicon R1-2005391 Discussion on DCI-based power saving adaptation vivo R1-2005523 Extension to Rel-16 DCI-based power saving adaptation during DRX Active Time ZTE R1-2005617 Evaluation methodology and enhancement for connected mode UE power saving MediaTek R1-2005721 PDCCH monitoring adaptation CATT R1-2005886 On PDCCH monitoring reduction techniques during active time Intel Corporation R1-2005936 Potential enhancement to DCI based power saving adaptation Lenovo, Motorola Mobility R1-2006043 DCI-based adaptation for PDCCH OPPO R1-2006159 On enhancements of power saving techniques during DRX active time Samsung R1-2006223 Discussion on PDCCH monitoring reduction during DRX active time CMCC R1-2006271 Discussion on power saving techniques for connected-mode UE Spreadtrum Communications R1-2006313 Discussion on DCI-based power saving adaptation during DRX Active Time LG Electronics R1-2006387 Potential extension(s) to Rel-16 DCI-based power saving adaptation during DRX Active Time Panasonic R1-2006529 PDCCH based power saving enhancements for connected-mode UEs Apple R1-2006548 PDCCH-based power saving signal design considerations InterDigital, Inc. R1-2006668 Discussion on potential enhancements for power savings during active time Ericsson R1-2006755 Power saving adaptation during Active Time ASUSTEK COMPUTER (SHANGHAI) R1-2006817 DCI-based power saving adaptation during DRX Active Time Qualcomm Incorporated R1-2006898 UE power saving enhancements for Active Time Nokia, Nokia Shanghai Bell R1-2006946 Power saving enhancements for connected mode UEs Sony - Others R1-2005392 Discussion on RLM/BFD relaxation vivo R1-2005524 Further discussion on potential power saving schemes for RRC connected UEs ZTE R1-2006044 Discussion on RLM Relaxation OPPO R1-2006404 Other considerations on power saving in Rel-17 Huawei, HiSilicon R1-2006669 Evaluation of UE power saving schemes Ericsson

RAN2 Contributions

RAN2 #112-e Meeting ### Organizational, Scope and Requirements: R2-2008716 LS on evaluation methodology for connected mode UE power saving enhancements (R1-2007419; contact: vivo, MediaTek) RAN1 LS in Rel-17 NR_UE_pow_sav_enh To:RAN2 Cc:RAN4. R2-2008719 LS on evaluation methodology for UE power saving enhancements (R1-2007425; contact: MediaTek) RAN1 LS in Rel-17 NR_UE_pow_sav_enh-Core To:RAN2 Cc:RAN4 ### Idle/inactive-mode UE power saving: - General R2-2009784 Report of [Post111-e][907][ePowSav] UE grouping (Mediatek) MediaTek Inc. R2-2008952 Discussion on paging enhancement Xiaomi Communications discussion R2-2009785 Paging Enhancements for UE Power Saving in NR MediaTek Inc. R2-2010244 Paging enhancements for idle/inactive-mode UE Huawei, HiSilicon, British Telecom R2-2009955 Paging enhancement to reduce unnecessary UE paging receptions Ericsson R2-2010079 Paging Enhancements for UE Power Savings Convida Wireless R2-2009878 Consideration on Idle/inactive-mode UE power saving Lenovo, Motorola Mobility - Group determination R2-2009274 Paging enhancement using UE subgrouping Intel Corporation R2-2009092 Paging Enhancements to Reduce False Alarms Samsung Electronics Co., Ltd R2-2010397 UE Power profile based UE subgrouping CMCC R2-2010629 Further consideration on the UE grouping methods ZTE corporation, Sanechips - Paging / Group indication R2-2008892 Power saving enhancements for paging reception Qualcomm Incorporated R2-2009083 Paging enhancement in idle inactive mode for power saving vivo R2-2009442 Paging enhancement for power saving LG Electronics Inc. R2-2009351 General requirements for potential paging enhancement Nokia, Nokia Shanghai Bell R2-2009503 NR UE Power Save Wakeup and Paging Reception Apple R2-2009893 Discussion on reduction of unnecessary UE paging receptions Sony R2-2009642 Discussion on the UE grouping method ITRI R2-2009464 Discussion on UE group based paging OPPO discussion - Other R2-2009502 NR UE Power Save False Paging Mitigation Apple R2-2009504 NR UE Power Save UE Paging Grouping Apple - TRS CSI-RS for Idle Inactive R2-2010245 On potential TRS/CSI-RS for idle/inactive-mode UE Huawei, HiSilicon R2-2009956 Exposure of connected mode TRS occasions to Idle and Inactive mode Ericsson R2-2008946 Discussion on TRS CSI-RS for RRC-IDLE and RRC-INACTIVE State UE Xiaomi R2-2009918 Potential TRS/CSI-RS occasion(s) Nokia, Nokia Shanghai Bell R2-2009465 Potential RAN2 impacts for TRS/CSI-RS configuration OPPO

RAN2 #111-e Meeting ### Organizational, Scope and Requirements: R2-2007189 RAN2 Work Plan for UE Power Saving Enhancements WI MediaTek Inc. R2-2007440 Discussion on RAN2 scope for UE Power Saving Huawei, HiSilicon R2-2006730 Views on Rel-17 NR UE power saving Xiaomi Communications R2-2006789 Discussion on use cases of UE power saving enhancements OPPO R2-2007326 Discussion on RAN2 scope in Power saving LG Electronics. R2-2007436 Initial consideration on RAN2’s work on UE power saving CMCC ### Idle/inactive-mode UE power saving: - General R2-2007190 Paging Enhancements for UE Power Saving in NR MediaTek Inc. R2-2006775 Power Consumption by RRC IDLE_INACTIVE UE Samsung Electronics Co., Ltd R2-2006790 Paging enhancement for power saving OPPO R2-2006608 Power saving enhancements for paging reception Qualcomm Inc R2-2006729 Discussion on UE Power saving for RRC-IDLE and RRC-INACTIVE State Xiaomi Communications R2-2007182 Discussion on reduction unnecessary UE paging receptions Sony R2-2007115 False Paging Mitigation Apple R2-2006690 Paging enhancement in idle inactive mode for power saving vivo R2-2006654 UE power saving for paging procedures ETRI R2-2006689 Coordination between RAN1 and RAN2 for paging enhancement vivo R2-2006720 Paging enhancements to reduce UE power consumption Intel Corporation R2-2006774 Paging Enhancements to Reduce Unnecessary Paging receptions Samsung Electronics Co., Ltd R2-2006874 Solutions to reduce unnecessary paging reception ZTE corporation, Sanechips R2-2006990 Considerations on paging enhancements for Power saving CATT R2-2007116 Wakeup and Paging Reception Apple R2-2007249 Discussion on the UE grouping based solution for idle/inactive-mode UE power saving ITRI R2-2007260 Paging enhancement to reduce unnecessary UE paging receptions Ericsson R2-2007437 Paging enhancement for idle inactive-mode UE power saving CMCC R2-2007441 Discussion on paging enhancements Huawei, HiSilicon R2-2007468 Consideration on Idle/inactive-mode UE power saving Lenovo, Motorola Mobility R2-2007563 IDLE / INACTIVE mode UE power saving Nokia, Nokia Shanghai Bell R2-2007990 Paging enhancement for power saving LG Electronics Inc. - TRS / CSI-RS R2-2007261 Exposure of connected mode TRS occasions to Idle and Inactive mode Ericsson R2-2007562 Potential TRS/CSI-RS occasion(s) Nokia, Nokia Shanghai Bell

RAN4 Contributions

RAN4 #97-e Meeting - General and work plan [NR_UE_pow_sav_enh]: R4-2014366 Work plan of Rel-17 Power Saving Enhancements MediaTek inc. R4-2014367 Evaluation on Rel-17 RLM/BFD measurement relaxation MediaTek inc. R4-2014534 Evaluation assumptions for R17 RLM/BFD relaxation vivo, MediaTek R4-2014219 Discussion on feasibility and performance impact of RLM/BFD relaxation Apple R4-2014428 Discussion on RLM relaxition for NR power saving CATT R4-2014535 Discussion and initial results for R17 RLM/BFD relaxation vivo R4-2014654 Discussion on RRM measurement relaxation in connected mode for NR power saving enhancement Xiaomi R4-2014797 Discussion on RLM BFD measurement relaxation OPPO R4-2015199 Discussion about evaluation methodology for relaxation of RLM/BFD measurements Nokia Solutions & Networks R4-2015485 Preliminary discussion on RLM/BFD relaxation in power saving enhancements Huawei, HiSilicon R4-2016150 Discussions on UE power saving for RLM and BM Ericsson