## Cover sheet
3GPP TSG-RAN WG5 Meeting #90-e | [8 empty] | R5-211163
Electronic Meeting, 22nd February - 5th March 2021
Agenda Item: | 7.4.2
Source: | Ericsson
Title: | Work plan: UE Conformance Test Aspects – Even further enhanced MTC for LTE
Work item code: | LTE_eMTC4-UEConTest
Release: | Rel-15
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#86 meeting in December 2019 the Rel-15 RAN5 work item for UE Conformance Test Aspects – Even further enhanced MTC for LTE was approved [1]. The present document provides the work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 54% | 10 | 24
Completion Compensation |  | 0.2233%
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE |  | 54.1% (-0.2%) | 10 | 24
|  | 54.1% (-0.2%) | 10 | 24
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 95% (+55%) |  |  | 95% (+55%)
UE specific test functions | 36.509 | 0% |  |  | 0%
LTE RF/RRM
RF common parts | 36.521-1 | 65% |  |  | 65%
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx | 50% (-6.2%) |  |  | 50% (-6.2%)
RF Demod test cases | 36.521-1 Demod | 91.7% | 4 | 4 | 91.7% | 4 | 4
Applicability RF, Demod/QSI and RRM test cases | 36.521-2 | 100% |  |  | 100%
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1 | 75% | 6 | 8 | 75% | 6 | 8
Applicability Protocol test cases | 36.523-2 | 23.6% (+0%) |  |  | 23.6%
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4
RRM test cases | 38.533
Applicability RF, Demod/QSI and RRM test cases | 38.522
Test Tolerances analysis RRM and RF Rx test cases | 38.903
Test Point analysis receiver and transmitter test cases | 38.905
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1 | 0% | 0 | 12 | 0% | 0 | 12
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3 | 0% |  |  | 0%
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
5 References
[1] RP-192894 | New WID on: New WID on UE Conformance Test Aspects - Even further enhanced MTC for LTE (eMTC4, Rel-15); Supporting companies: AT&T, Bureau Veritas, Ericsson, KDDI, NTT DOCOMO, INC., Orange
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Even further enhanced MTC for LTE (eMTC4, Rel-15) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_eMTC4-UEConTest
WP Scope: |  | Even further enhanced MTC for LTE (eMTC4, Rel-15)
WP Resp: |  | Calle Hagenfeldt, Ericsson |  |  | calle.hagenfeldt@ericsson.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE
54.1% (-0.2%)
74 (+14)
69 (+14)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
LTE - RAN and CN
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 | 4.3 | Test environment eMTC4 | Check if changes are needed for test environment for eMTC4 in clauses 4.3.2 to 4.3.6. |  | RAN5#90-e (Feb-21) |  | No updates neeed | 1 | 100% (+100%) | 100% (+100%) |  | 100%
2 |  | 36.508 | 4.4.3, 4.5, 4.6, 4.8, 5.2, 5.2A, 5.3, 7.2, 7.2A, 7.3 | Test environment eMTC4 | Check if changes needed for generic procedures and default messages for protocol and RF/RRM testing |  | RAN5#90-e (Feb-21) | R5-204966 R5-204499 R5-206392 R5-211450 |  | 1 | 90% (+10%) | 90% (+10%) |  | 90%
TS 36.509: UE specific testing functions
3 |  | 36.509 |  | UE test functions | Check if the UE test functions needs to be updated. |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
LTE RF/RRM
TS 36.521-1: RF test cases - Common parts (general clauses, Annexes)
4 |  | 36.521-1 | Annex A |  | Add new RMCs | Ericsson | RAN5#90-e (Feb-21) | R5-201950 |  | 1 | 50% | 50% |  | 50%
54 |  | 36.521-1 | Annex F |  | Update Test Requirements (Transmitter tests) | Ericsson | RAN5#90-e (Feb-21) | R5-204001 |  | 1 | 80% | 80% |  | 80%
TS 36.521-1: RF test cases - Tx
42 |  | 36.521-1 Tx | 6.2.2EA | Maximum Output Power for UE category M1 | Update test case for PC6 | Ericsson | RAN5#89-e (Nov-20) | R5-204972 |  | 1 | 100% | 100% |  | 100%
47 |  | 36.521-1 Tx | 6.2.2EC | Maximum Output Power for UE category M2 | Update test case for PC6 | Ericsson | RAN5#89-e (Nov-20) | R5-205538 |  | 1 | 100% | 100% |  | 100%
5 |  | 36.521-1 Tx | 6.2.3EA | Maximum Power Reduction (MPR) for UE category M1 | Update test case for PC6 | Ericsson | RAN5#89-e (Nov-20) | R5-204973 | No MPR for subPRB allocation | 1 | 100% | 100% |  | 100%
6 |  | 36.521-1 Tx | 6.2.3EC | Maximum Power Reduction (MPR) for UE category M2 | Update test case for PC6 and add subPRB MPR tables | Ericsson | RAN5#89-e (Nov-20) | R5-205539 R5-210549 |  | 1 | 100% | 100% |  | 100%
7 |  | 36.521-1 Tx | 6.2.4E | UE maximum output power with additional requirements for category M1 and M2 UE | Update test case with subPRB allocation |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
62 |  | 36.521-1 Tx | 6.2.4EA | Additional Maximum Power Reduction (A-MPR) for UE category M1 | Update test case with subPRB allocation |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
43 |  | 36.521-1 Tx | 6.2.5EA | Configured UE transmitted Power for UE category M1 | Update test case for PC6 | Ericsson | RAN5#89-e (Nov-20) | R5-204007 |  | 1 | 100% | 100% |  | 100%
48 |  | 36.521-1 Tx | 6.2.5EC | Configured UE transmitted Power for UE category M2 | Update test case for PC6 | Ericsson | RAN5#89-e (Nov-20) | R5-205542 |  | 1 | 100% | 100% |  | 100%
44 |  | 36.521-1 Tx | 6.3.5EA.1 | Power Control Absolute power tolerance for UE category M1 | Update test case for PC6 | Ericsson | RAN5#89-e (Nov-20) | R5-204005 |  | 1 | 100% | 100% |  | 100%
45 |  | 36.521-1 Tx | 6.3.5EA.2 | Power Control Relative power tolerance for UE category M1 | Update test case for PC6 | Ericsson | RAN5#89-e (Nov-20) | R5-204017 |  | 1 | 100% | 100% |  | 100%
49 |  | 36.521-1 Tx | 6.5.2.1EA.1 | Error Vector Magnitude (EVM) for UE category M1 | Update test case for PC6 | Ericsson | RAN5#90-e (Feb-21) |  | No updates needed? | 1 | 0% | 0% |  | 0%
63 |  | 36.521-1 Tx | 6.5.2.1EA.2 | PUSCH-EVM with exclusion period for UE category M1 | Add subPrb allocation | Ericsson | RAN5#90-e (Feb-21) | R5-210552 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
50 |  | 36.521-1 Tx | 6.5.2.1EC.1 | Error Vector Magnitude (EVM) for UE categoy M2 | Update test case for PC6 | Ericsson | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
64 |  | 36.521-1 Tx | 6.5.2.1EC.2 | PUSCH-EVM with exclusion period for UE category M2 | Add subPrb allocation | Ericsson | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
65 |  | 36.521-1 Tx | 6.5.2.2EA | Carrier leakage for UE category M1 | Add subPrb allocation | Ericsson | RAN5#90-e (Feb-21) | R5-210553 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
66 |  | 36.521-1 Tx | 6.5.2.2EC | Carrier leakage for UE category M2 | Add subPrb allocation | Ericsson | RAN5#90-e (Feb-21) | R5-210553 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
8 |  | 36.521-1 Tx | 6.5.2.3EA | In-band emissions for non allocated RB for UE category M1 | Update test case with subPRB allocation | Ericsson | RAN5#89-e (Nov-20) | R5-204971 |  | 1 | 100% | 100% |  | 100%
9 |  | 36.521-1 Tx | 6.5.2.3EC | In-band emissions for non allocated RB for UE category M2 | Update test case with subPRB allocation | Ericsson | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
67 |  | 36.521-1 Tx | 6.6.2.1EA | Spectrum Emission Mask for UE category M1 | Align RB allocation with ACLR/MPR test cases |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
51 |  | 36.521-1 Tx | 6.6.2.1EC | Spectrum Emission Mask for UE category M2 | Update test case for PC6 (test config. table) Align test points with MPR test case for subPRB allocation | Ericsson | RAN5#90-e (Feb-21) | R5-210558 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
68 |  | 36.521-1 Tx | 6.6.2.2EA | Additional Spectrum Emission Mask for UE category M1 | Align RB allocation with A-MPR test case |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
52 |  | 36.521-1 Tx | 6.6.2.2EC | Additional Spectrum Emission Mask for UE category M2 | Update test case for PC6 (test config. table) | Ericsson | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
69 |  | 36.521-1 Tx | 6.6.2.3EA | Adjacent Channel Leakage power Ratio for UE category M1 | Align RB alllocation with MPR test case | Ericsson | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
53 |  | 36.521-1 Tx | 6.6.2.3EC | Adjacent Channel Leakage power Ratio for UE category M2 | Update test case for PC6 (test config. table) Align test points with MPR test case for subPRB allocation | Ericsson | RAN5#90-e (Feb-21) | R5-210559 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
70 |  | 36.521-1 Tx | 6.6.3EA.1 | Transmitter Spurious emissions for UE category M1 | Add subPrb allocation | Ericsson | RAN5#90-e (Feb-21) | R5-210560 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
71 |  | 36.521-1 Tx | 6.6.3EA.2 | Spurious emission band UE co-existence for UE category M1 | Add subPrb allocation | Ericsson | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
72 |  | 36.521-1 Tx | 6.6.3EA.3 | Additional spurious emissions for UE category M1 | Align RB allocation with A-MPR test case |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
73 |  | 36.521-1 Tx | 6.6.3EA.1 | Transmitter Spurious emissions for UE category M2 | Add subPrb allocation |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
74 |  | 36.521-1 Tx | 6.6.3EA.2 | Spurious emission band UE co-existence for UE category M2 | Add subPrb allocation |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
75 |  | 36.521-1 Tx | 6.6.3EA.3 | Additional spurious emissions for UE category M2 | Align RB allocation with A-MPR test case |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
TS 36.521-1: Demod/QSI reporting test cases
10 |  | 36.521-1 Demod | 8.11.1.1.3.1 | FDD and half-duplex FDD PDSCH Transmit Diversity 2x1 for UE category M1 | Add new subtest with CRS muting, 64QAM and 200Hz doppler spread | Ericsson | RAN5#89-e (Nov-20) | R5-202324 R5-203776 R5-203779 |  | 1 | 100% | 100% |  | 100%
11 |  | 36.521-1 Demod | 8.11.1.1.3.2_1 | FDD and half-duplex FDD PDSCH Transmit Diversity 2x1 for UE category M2 (CEmodeB) | Add new subtest with CRS muting | Ericsson | RAN5#89-e (Nov-20) | R5-205543 |  | 1 | 100% | 100% |  | 100%
46 |  | 36.521-1 Demod | 8.11.1.2.3.1 | TDD PDSCH Transmit Diversity for UE category M1 | Add new subtest with CRS muting, 64QAM and 200Hz doppler spread | Ericsson | RAN5#89-e (Nov-20) | R5-203776 R5-203782 R5-210550 |  | 1 | 100% | 100% |  | 100%
12 |  | 36.521-1 Demod | 8.11.1.2.3.1_1 | TDD PDSCH Transmit Diversity for UE category M1 (CEModeB) | Add new subtest with CRS muting | Ericsson | RAN5#89-e (Nov-20) | R5-205545 |  | 1 | 100% | 100% |  | 100%
13 |  | 36.521-1 Demod | 8.11.1.2.3.2_1 | TDD PDSCH 2 Tx Antenna Port supporting wideband transmission for UE category M2 (CEModeB) | Add new subtest with CRS muting | Ericsson | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
14 |  | 36.521-1 Demod | 9.1.1.5 |  | Update applicability in this clause | Ericsson | RAN5#89-e (Nov-20) | R5-203775 |  | 1 | 100% | 100% |  | 100%
15 |  | 36.521-1 Demod | 9.8.3 | CQI reporting definition for UE supporting 64QAM under AWGN | New clause | Ericsson | RAN5#89-e (Nov-20) | R5-204967 |  | 1 | 100% | 100% |  | 100%
16 | Y | 36.521-1 Demod | 9.8.3.1 | FDD and half duplex FDD CQI reporting under AWGN conditions for UE supporting coverage enhancement and 64QAM |  | Ericsson | RAN5#89-e (Nov-20) | R5-204967 |  | 1 | 100% | 100% |  | 100%
17 | Y | 36.521-1 Demod | 9.8.3.2 | TDD CQI reporting under AWGN conditions for UE supporting coverage enhancement and 64QAM |  | Ericsson | RAN5#89-e (Nov-20) | R5-204968 |  | 1 | 100% | 100% |  | 100%
18 |  | 36.521-1 Demod | 9.8.4 | CQI reporting definition for UE supporting alternative table under AWGN | New clause | Ericsson | RAN5#89-e (Nov-20) | R5-204969 |  | 1 | 100% | 100% |  | 100%
19 | Y | 36.521-1 Demod | 9.8.4.1 | FDD and half duplex FDD CQI reporting under AWGN conditions for UE supporting coverage enhancement and alternative table |  | Ericsson | RAN5#89-e (Nov-20) | R5-204969 |  | 1 | 100% | 100% |  | 100%
20 | Y | 36.521-1 Demod | 9.8.4.2 | TDD and half duplex FDD CQI reporting under AWGN conditions for UE supporting coverage enhancement and alternative table |  | Ericsson | RAN5#89-e (Nov-20) | R5-204970 R5-211803 |  | 1 | 100% | 100% |  | 100%
TS 36.521-2: Applicability for RF, Demod/QSI reporting and RRM test cases
55 |  | 36.521-2 |  |  | Add new ICS and test case applicability statements for the new test cases introduced for 36.521-1. | Ericsson | RAN5#89-e (Nov-20) | R5-203773 |  | 0.1 | 100% | 100% |  | 100%
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
Idle Mode
21 | Y | 36.523-1 | 8.1.1.8 | RRC / Paging / DRX Operation / Enhanced Coverage / WUS |  | Tech Mahindra | RAN5#89-e (Nov-20) | R5-204500 |  | 1 | 100% | 100% |  | 100%
22 | Y | 36.523-1 | 8.1.1.9 | RRC / Paging / eDRX Operation / Enhanced Coverage / WUS |  | Tech Mahindra | RAN5#89-e (Nov-20) | R5-204501 |  | 1 | 100% | 100% |  | 100%
MAC
23 | Y | 36.523-1 | 7.1.4.14a | Correct HARQ process handling / feedback for UL data |  | Ericsson | RAN5#89-e (Nov-20) | R5-206058 |  | 1 | 100% | 100% |  | 100%
24 | Y | 36.523-1 | 7.1.3.23 | Enhanced Coverage / DL Fexible starting PRB |  | Ericsson | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
25 | Y | 36.523-1 | 7.1.4.42 | Enhanced Coverage / UL Fexible starting PRB |  | Ericsson | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
RRC
26 | Y | 36.523-1 | 23.1.3 | CIoT / Control Plane / EDT |  | Ericsson | RAN5#89-e (Nov-20) | R5-203058 |  | 1 | 100% | 100% |  | 100%
27 | Y | 36.523-1 | 23.2.4 | CIoT / User Plane / EDT |  | Ericsson | RAN5#89-e (Nov-20) | R5-204503 |  | 1 | 100% | 100% |  | 100%
NAS
28 | Y | 36.523-1 | 9.2.1.1.27b | Attach / EAB / CE-level based access barring |  | Tech Mahindra | RAN5#89-e (Nov-20) | R5-204502 |  | 1 | 100% | 100% |  | 100%
TS 36.523-2: Applicability for Protocol test cases
29 |  | 36.523-2 |  | Legacy test cases | Check if Implementation Conformance Statements needs to be updated. |  | RAN5#90-e (Feb-21) | R5-204504 R5-211451 |  | 1 | 0% | 0% |  | 0%
57 |  | 36.523-2 |  | Applcibility idle mode test cases | Add ICS and test case applicability statements for the new idle mode test cases introduced in 36.523-1 | Ericsson | RAN5#89-e (Nov-20) | R5-204504 |  | 0.1 | 100% | 100% |  | 100%
58 |  | 36.523-2 |  | Applicability MAC test cases | Add ICS and test case applicability statements for the new MAC test cases introduced in 36.523-1 | Ericsson | RAN5#90-e (Feb-21) | R5-206393 |  | 0.1 | 30% | 30% |  | 30%
59 |  | 36.523-2 |  | Applcibility RRC test cases | Add ICS and test case applicability statements for the new RRC test cases introduced in 36.523-1 | Ericsson | RAN5#89-e (Nov-20) | R5-203059 R5-204506 |  | 0.1 | 100% | 100% |  | 100%
60 |  | 36.523-2 |  | Applcibility NAS test cases | Add ICS and test case applicability statements for the new RRC test cases introduced in 36.523-1 | Tech Mahindra | RAN5#89-e (Nov-20) | R5-204505 |  | 0.1 | 100% | 100% |  | 100%
UE Positioning
TS 37.571-1: UE Positioning -Performance
9 - E-UTRA OTDOA measurement requirements
9.3 RSTD Intra-Frequency Measurements for UE Category M1/M2
30 | Y | 37.571-1 | 9.3.13 | E-UTRAN FDD intra-frequency RSTD measurement period test case in CE Mode A with longer PRS occasions |  |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
31 | Y | 37.571-1 | 9.3.14 | E-UTRAN HD-FDD intra-frequency RSTD measurement period test case in CE Mode A with longer PRS occasions |  |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
32 | Y | 37.571-1 | 9.3.15 | E-UTRAN TDD intra-frequency RSTD measurement period test case in CE Mode A with longer PRS occasions |  |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
33 | Y | 37.571-1 | 9.3.16 | E-UTRAN FDD intra-frequency RSTD measurement period test case in CE Mode B with longer PRS occasions |  |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
34 | Y | 37.571-1 | 9.3.17 | E-UTRAN HD-FDD intra-frequency RSTD measurement period test case in CE Mode B with longer PRS occasions |  |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
35 | Y | 37.571-1 | 9.3.18 | E-UTRAN TDD intra-frequency RSTD measurement period test case in CE Mode B with longer PRS occasions |  |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
9.4 RSTD Inter-Frequency Measurements for UE Category M1/M2
36 | Y | 37.571-1 | 9.4.13 | E-UTRAN FDD inter-frequency RSTD measurement period test case in CE Mode A with longer PRS occasions |  |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
37 | Y | 37.571-1 | 9.4.14 | E-UTRAN HD-FDD inter-frequency RSTD measurement period test case in CE Mode A with longer PRS occasions |  |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
38 | Y | 37.571-1 | 9.4.15 | E-UTRAN TDD inter-frequency RSTD measurement period test case in CE Mode A with longer PRS occasions |  |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
39 | Y | 37.571-1 | 9.4.16 | E-UTRAN FDD inter-frequency RSTD measurement period test case in CE Mode B with longer PRS occasions |  |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
40 | Y | 37.571-1 | 9.4.17 | E-UTRAN HD-FDD inter-frequency RSTD measurement period test case in CE Mode B with longer PRS occasions |  |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
41 | Y | 37.571-1 | 9.4.18 | E-UTRAN TDD inter-frequency RSTD measurement period test case in CE Mode B with longer PRS occasions |  |  | RAN5#90-e (Feb-21) |  |  | 1 | 0% | 0% |  | 0%
TS 37.571-3: Applicability and ICS UE Positioning test cases
61 |  | 37.571-3 | <Clause> | Applicability for new positioning test cases | Add test case applicability statements for the new test cases introduced in 37.571-1 . |  | RAN5#90-e (Feb-21) |  |  | 0.5 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.