## Cover sheet
3GPP TSG-RAN WG5 Meeting #90-e | [10 empty] | R5-211198
Electronic Meeting, 22nd February - 5th March 2021
Agenda Item: | 7.4.2
Source: | China Unicom
Title: | WP UE Conformance Test Aspects - High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band)
Work item code: | ENDC_UE_PC2_FDD_TDD
Release: | Rel-16
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance test cases and associated test environment, test applicability, test point analysis on High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band). The scope of this WI is all the Ran4 completed PC2 1 LTE FDD +1 NRTDD EN-DC configurations as following：DC_3A_n78A, DC_3A_n41A. More PC2 EN-DC configurations may be introduced in this Work Item after other basket WIs of ENDC_UE_PC2_FDD_TDD in RAN4 is completed. At the RAN#89-emeeting in Sep 2020, Rel-16 RAN5 work item for UE Conformance Test Aspects - High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) [1] was approved. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 78% (+3%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
NSA Option 3 (EN-DC) |  | 78.1% (+2.9%)
FR1 |  | 78.1% (+2.9%)
FR2
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | NSA Option 3 (EN-DC)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 0% |  |  | 0%
Common ICS | 38.508-2 | 100% |  |  | 100%
NR RF/RRM
FR1 and FR2 Interworking operation with other radios RF test cases - Common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx | 100% (+5%) |  |  | 100% (+5%)
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx | 100% (+5%) |  |  | 100% (+5%)
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 0% |  |  | 0%
5 References
[1] RP-201776 | New WID on UE Conformance Test Aspects – High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band)；China Unicom
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | ENDC_UE_PC2_FDD_TDD
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [12 empty] | vs Area
WP Resp: |  | Yu Shi, China Unicom |  |  | shiyu19@chinaunicom.cn | [5 empty] | WP item completion |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | NSA Option 3 (EN-DC) |  | FR1 | FR2 | FR1 + FR2
78.1% (+2.9%)
[14 empty] | 9 | 0 | 0
[14 empty] | 6.5 | 0 | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS - RAN and CN
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4,6 | Common test environment | Definition of common test environment for FDD-TDD PC2 EN-DC UE | China Unicom | RAN5#90-e (Feb-21) |  |  | 0.5 | 0% | 0% |  | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.508-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Introduction of RF Baseline Implementation Capabilities for FDD-TDD PC2 EN-DC UE | China Unicom, CMCC | RAN5#90-e (Feb-21) | R5-205640, R5-206771 |  | 1 | 100% | 100% |  | 100%
NR RF/RRM
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-3 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Tx
|  | 38.521-3 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
3 |  | 38.521-3 Tx | 6.2B.1.3 | UE Maximum Output Power for Inter-Band EN-DC within FR1 | Introduction of UE Maximum Output Power for Inter-Band EN-DC PC2 configuration DC_3-n78 | Huawei | RAN5#90-e (Feb-21) | R5-206773 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100%
4 |  | 38.521-3 Tx | 6.2B.1.3 | UE Maximum Output Power for Inter-Band EN-DC within FR1 | Introduction of UE Maximum Output Power for Inter-Band EN-DC PC2 configuration for DC_3-n41 | CMCC | RAN5#90-e (Feb-21) | R5-206772 |  | 1 | 100% | 100% |  | 100%
TS 38.521-3: FR1 and FR2 Interworking operation with other radios RF test cases - Rx
|  | 38.521-3 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5 |  | 38.521-3 Rx | 7.3B.2.3 | Reference sensitivity for Inter-band EN-DC within FR1 | Introduction of Reference sensitivity for Inter-Band EN-DC PC2 configuration DC_3-n78 | China Unicom | RAN5#90-e (Feb-21) | R5-206919 |  | 1 | 100% (+10%) | 100% (+10%) |  | 100%
6 |  | 38.521-3 Rx | 7.3B.2.3 | Reference sensitivity for Inter-band EN-DC within FR1 | Introduction of Reference sensitivity for Inter-Band EN-DC PC2 configuration DC_3-n41 | CMCC | RAN5#90-e (Feb-21) | R5-206918 |  | 1 | 100% | 100% |  | 100%
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
7 |  | 38.522 | 4 | Test case conditions and selection criteria | Introduction of Test case conditions and selection criteria for Inter-Band EN-DC within FR1 for FDD-TDD PC2 EN-DC UE | China Unicom | RAN5#91-e (May-21) |  |  | 0.3 | 0% | 0% |  | 0%
8 |  | 38.522 | 4.1.3 | NR interworking between NR FR1 and NR FR2 and between NR and LTE conformance test cases | Introduction of Test case applicability for Inter-Band EN-DC within FR1 for FDD-TDD PC2 EN-DC UE | China Unicom | RAN5#91-e (May-21) |  |  | 0.3 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
9 |  | 38.905 | 4.3 | Test point analysis for NR CA and EN-DC | Introduction of Test point analysis for FDD-TDD PC2 EN-DC UE |  | RAN5#91-e (May-21) |  |  | 0.4 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.