3GPP TSG RAN WG1 Meeting #102-e	R1-2006447

E-meeting, August 17-28, 2020

Agenda Item:	8.9

Source:	Huawei, Ericsson

Title:	Work plan of Rel-17 enhancements for NB-IoT and LTE-MTC

Document for:	Discussion and Decision

Introduction

The Rel-17 additional enhancements for NB-IoT and LTE-MTC WI was approved at RAN#86 and updated at RAN#88e, with RAN1 completion due by June 2021 (RAN#91) and overall core part completion due by September 2021 (RAN#92)[1]. Totally 7 TUs in RAN1, 7 TUs in RAN2 and 3.5 TUs in RAN3 are allocated for this WI [2]. The number of TUs in RAN4 is to be allocated.

This contribution presents the rapporteurs’ workplan for the WI. It does not affect or limit the scope of the approved WID or the exchange of information the working groups can undertake. Note that there may be changes in the proposed workplan due to schedule updates in the responsible working groups.

WID objectives

It is the Work Item objective to specify the following improvements for NB-IoT and LTE-MTC [1]:

- Specify 16-QAM for unicast in UL and DL, including necessary changes to DL power allocation for NPDSCH and DL TBS. This is to be specified without a new NB-IoT UE category. For DL, increase in maximum TBS of e.g. 2x the Rel-16 maximum, and soft buffer size will be specified by modifying at least existing Category NB2. For UL, the maximum TBS is not increased. [NB-IoT] [RAN1, RAN4]

  - Extend the NB-IoT channel quality reporting based on the framework of Rel-14—16, to support 16-QAM in DL. [NB-IoT] [RAN2, RAN1, RAN4]

- Support additional PDSCH scheduling delay for introduction of 14-HARQ processes in DL, for HD-FDD Cat M1 UEs. [LTE-MTC] [RAN1]

- Specify signaling for neighbor cell measurements and corresponding measurement triggering before RLF, to reduce the time taken to RRC reestablishment to another cell, without defining specific gaps. [NB-IoT] [RAN2, RAN4].

- Introduce support for NB-IoT carrier selection based on the coverage level, and associated carrier specific configuration (e.g. maximum repetitions UL/DL, DRX configurations, etc.). [NB-IoT] [RAN2, RAN3]

- For UEs supporting PUSCH sub-PRB resource allocation, study and if found feasible, specify support power reduction for PRACH, PUCCH, and full-PRB PUSCH, with a maximum reduction of e.g. 3 dB below sub-PRB PUSCH power. [LTE-MTC] [RAN4]

- Add a Rel-17 optional UE capability to support a maximum DL TBS of 1736 bits for HD-FDD Cat. M1 UEs in CE mode A only. [LTE-MTC] [RAN1, RAN2]

  - Determine soft buffer size [RAN1]

  - Capability signaling without introducing a new UE category [RAN2]

  - There shall be no changes to: DCI formats, TBS tables, CQI tables

  - This objective begins work from RAN#90, i.e. December 2020

Work plan

August 2020

RAN1#102e:

- Discussion on TBS/MCS to support 16-QAM for NB-IoT, agree on list of different proposals, FFS points and agree on the evaluation assumptions.

- Discussion on power allocation for NPDSCH, and agree on list of options on power allocation and value ranges if any.

- Discussion on additional PDSCH scheduling delay to support 14-HARQ processes in DL, and agree on the list of options.

- Note: The steps indicated here are as originally planned for RAN1#100 and RAN1#100bis.

RAN2#111-e:

- Discussions on signaling for neighbor cell measurements and corresponding measurement triggering before RLF.

- Discussions on support for NB-IoT carrier selection based on the coverage level, and associated carrier specific configuration.

- Kick-off for the document to capture the RAN2 agreements from the meetings which is to be endorsed in an e-mail discussion following the meeting.

October – November 2020

RAN1#103e:

- Continue the discussion on TBS/MCS design to support 16-QAM for NB-IoT.

- Continue discussion on power allocation for NPDSCH, and conclude on the change to power allocation and value ranges if any.

- Continue discussion on additional PDSCH scheduling delay to support 14-HARQ processes in DL, and conclude on the solution.

- Liaise with other working groups on the agreements achieved if necessary.

RAN2#112-e:

- Continue discussions on signaling for neighbor cell measurements and corresponding measurement triggering before RLF, down-select solutions if needed.

- Continue discussions on support for NB-IoT carrier selection based on the coverage level, and associated carrier specific configuration, down-select solutions if needed

[January 2021, possible ad-hoc]

- [If an ad-hoc including this WI is arranged, the workplan will be updated accordingly based on the progress].

February – March 2021

RAN1#104:

- Conclude on the design of MCS/TBS table to support 16-QAM for NB-IoT.

- Discussion on channel quality report to support 16QAM, and agree on list of options for channel quality reporting for 16QAM.

- Discussion on maximum DL TBS of 1736 bits for HD-FDD Cat. M1 UEs in CE mode A, and agree on list of options or FFS points.

RAN2#113:

- Progress technical details of signaling for neighbor cell measurements and corresponding measurement triggering before RLF. Liaise with other working groups as necessary.

- Progress technical details of support for NB-IoT carrier selection based on the coverage level, and associated carrier specific configuration. Liaise with other working groups as necessary

- Discussion on RAN2 aspects of support of 16QAM.

- Discussion on RAN2 aspects of additional PDSCH scheduling delay to support 14-HARQ processes in DL.

RAN3#111:

- Discussion on the scenarios and issues to support for NB-IoT carrier selection based on the coverage level, and associated carrier specific configuration, take RAN2 progress into account.

- Identify other RAN3 impacts of other topics, if any.

April 2021

RAN1#104bis:

- Conclude on the design of channel quality report for 16QAM.

- Conclude on the design of maximum DL TBS of 1736 bits for HD-FDD Cat. M1 UEs in CE mode A.

- First version of RAN1 parameters list, and liaise with other working groups on the parameter list and agreements achieved if necessary.

RAN2#113bis:

- Agree on technical details of signaling for neighbor cell measurements and corresponding measurement triggering before RLF.

- Agree on technical details of support for NB-IoT carrier selection based on the coverage level, and associated carrier specific configuration.

- Progress technical details of RAN2 aspects of support of 16QAM.

- Progress technical details of RAN2 aspects of additional PDSCH scheduling delay to support 14-HARQ processes in DL.

- Discussion on RAN2 aspects of DL TBS of 1736 bits for HD-FDD Cat. M1 UEs in CE mode A (e.g. L2 buffer size).

- Kick-off running CRs to capture the RAN2 agreements in the related specifications which are to be endorsed in an e-mail discussion following the meeting.

RAN3#111bis:

- Discussion on potential solutions and RAN3 impacts to support for NB-IoT carrier selection, take RAN2 progress into account.

- Discussion on other RAN3 impacts of other topics, if any.

- Start baseline CRs to capture the RAN3 impacts.

May 2021

RAN1#105:

- Discuss and conclude on the soft buffer size of Cat. NB2 to support 16QAM.

- Discuss and conclude on the soft buffer size of HD-FDD Cat. M1 in CE mode A to support a maximum DL TBS of 1736 bits.

- Update of the RAN1 parameter list, and liaise with other working groups on the parameter list and agreements achieved if necessary.

- The remaining issues of the WI.

RAN2#114:

- Finalize technical details of signaling for neighbor cell measurements and corresponding measurement triggering before RLF.

- Finalize technical details of support for NB-IoT carrier selection based on the coverage level, and associated carrier specific configuration.

- Agree on technical details of RAN2 aspects of support of 16QAM, taking into account any input from RAN1.

- Agree on technical details of RAN2 aspects of additional PDSCH scheduling delay to support 14-HARQ processes in DL, taking into account any input from RAN1.

- Agree on technical details of RAN2 aspects of DL TBS of 1736 bits for HD-FDD Cat. M1 UEs in CE mode A (e.g. L2 buffer size).

- Discussion on optional/mandatory requirements and need for capability reporting.

- Update running CRs with the agreements from the meeting, including RAN1 parameters list if available, in an e-mail discussion following meeting.

RAN3#112:

- Finalize the discussion on RAN3 impacts of the NB-IoT carrier selection and other topics (if any).

- Update baseline CRs according to the discussion.

August 2021

RAN2#115:

- Finalize any RAN2 remaining issues.

- Discuss and finalize RAN2 aspects resulting from latest RAN1, RAN3 & RAN4 agreements.

- Finalize discussion on optional/mandatory requirements and need for capability reporting.

- Finalize the CRs based on the agreements from the meetings for RAN plenary submission.

RAN3#113:

- Finalize the baseline CRs, complete the work in RAN3.

- References

RP-201306, “WID revision: Additional enhancements for NB-IoT and LTE-MTC”, Huawei, HiSilicon, RAN#88e, Electronic Meeting, June 29-July 3, 2020.

RP-193267, “Status of time budgets for RAN1/2/3/4/6 ongoing and new WIs/SIs after RAN #86”, RAN1/RAN2/RAN3/RAN4/RAN6 chairmen, RAN#86, Sitges, Spain, Dec. 9-12, 2019.