3GPP TSG-RAN WG2 Meeting #116 electronic                                              R2-2109939

Online, November 1 – 12, 2021                                               	     Revision of R2-2107169

Agenda item: 		8.4.1

Source: 		Qualcomm Incorporated, Samsung (WI Rapporteurs)

Title: 	Workplan for Rel-17 IAB

Document for:	Information

# 1	Introduction

At RAN#86, the Work Item on Enhancements for Integrated Access and Backhaul was agreed (NR_IAB_enh) [1]. As WI Rapporteur, in this contribution, we recommend a work plan for RAN1, RAN2, RAN3 and RAN4. The workplan captures interdependences among tasks and timeline for RAN1/2/3/4.

The WID [1] introduced the following objectives in the core part:

Duplexing enhancements [RAN1-led, RAN2, RAN3, RAN4]: - Specification of enhancements to the resource multiplexing between child and parent links of an IAB node, including: - Support of simultaneous operation (transmission and/or reception) of IAB-node’s child and parent links (i.e., MT Tx/DU Tx, MT Tx/DU Rx, MT Rx/DU Tx, MT Rx/DU Rx). - Support for dual-connectivity scenarios defined by RAN2/RAN3 in the context of topology redundancy for improved robustness and load balancing. - Specification of IAB-node timing mode(s), extensions for DL/UL power control, and CLI and interference measurements of BH links, as needed, to support simultaneous operation (transmission and/or reception) by IAB-node’s child and parent links. Topology adaptation enhancements [RAN3-led, RAN2]: - Specification of procedures for inter-donor IAB-node migration to enhance robustness and load-balancing, including enhancements to reduce signalling load. - Specification of enhancements to reduce service interruption due to IAB-node migration and BH RLF recovery. - Specification of enhancements to topological redundancy, including support of CP/UP separation. Topology, routing and transport enhancements [RAN2-led, RAN3]: - Specifications of enhancements to improve topology-wide fairness, multi-hop latency and congestion mitigation RF and RRM requirements [RAN4-led]: - Definition of IAB node RF requirements if needed for any Rel-17 extensions. - Definition of RRM core requirements if needed for any Rel-17 extensions.

The WID [1] introduced the following objectives in the performance part:

- Specification of RRM performance requirements for Rel-17 enhancements. - Specification of demodulation performance requirements for Rel-17 enhancements. - Specification of conformance testing requirements for Rel-17 enhancements [RAN4]

# 2	Workplan

## 2.1	Prioritization of efforts

This section captures the interdependences among the various tasks defined in the WID [1].

RAN1-led efforts:

The WID defines two main objectives related to physical layer enhancements, which are led by RAN1. These objectives are expected to cause impact on RAN2/3 on later stage of the WI, mostly related to L3 configuration. The RAN2/3-related efforts will be explicitly captured under the RAN2/3-led objectives as time moves on.

RAN2-led and RAN3-led efforts:

The WID defines one RAN-2-led objective as well as three RAN3-led objectives.

Based on experience made during Rel-16 IAB WI, it can be expected that most of these objectives have strong interdependences between these WGs. This interdependence can be handled via parallel discussions as well as liaisons exchanged between both WGs. Some initial effort may be necessary by RAN3, e.g., to define new procedures such as for inter-donor topology adaptation, before associated RAN2 work can start.

RAN4-led efforts (core part):

The WID defines the two objectives in the core part led by RAN4. The RAN-4 effort depends on prior work by the other RAN WGs, mostly RAN1.

RAN4-led efforts (performance part):

The WID defines the three objectives in the performance part led by RAN4.

## 2.2	Timeline

Table 1 summarizes a timeline for RAN1/2/3/4.

The timeline and the TU allocation are based on the latest SR agreed in RAN#92. The RAN1 schedule has been moved back by 6 months and the RAN2/3 schedules have been moved back by 3 months due to delays of Rel-16. The RAN4 core part schedule has been moved back by 9 months due to RAN4’s delay with completion of Rel-16 IAB efforts and TU limitation. The RAN4 performance part schedule has been moved back to 2022Q3.  Some changes to this timeline may occur, e.g., due to replacement of in-lieu meeting with e-meetings.

Since the WI primarily defines enhancements to Rel-16 IAB functionality, the various objectives can be mostly addressed in parallel. Further, since the WID objectives are rather general, the first meeting in each WG should emphasize on scoping the effort.

Table 1: Timeline for RAN1, 2, 3, 4 efforts

| TSG/WG | Meeting Number | Date | TU | Task |
| --- | --- | --- | --- | --- |
| RAN1 | #107e | Nov 11-19, 2021 | 1 | Finalize efforts based on agreements on agenda item 8.10.1 and on agenda item 8.10.2 from RAN1 #106bis-e: Resource multiplexing for duplexing enhancements, including: - Further details on IAB-DU FDM resource configuration. - Details on indication of applicability of non-TDM multiplexing modes. - Further details on DCI format 2_5 extension for FDM resource configuration. - Further details on SDM beam restriction/recommendation. - Further details on guard symbols for transition between MT and DU as a function of timing cases and associated multiplexing modes. - If and which rules need to be defined for an IAB-node to be allowed to operate in non-TDM mode. - Details on signaling of enhanced multiplexing capabilities. Other enhancements to support simultaneous operation (transmission and/or reception) by IAB-node’s child and parent links, including: - Further details on timing : - If and how OTA synchronization needs to be updated for an IAB-node operating in Case 6 timing. - Range for Case 7 timing offset. - If and how OTA synchronization needs to be updated for an IAB-node while parent node operates in Case 7 timing. - Further details on power control enhancements: - Details on configuration conditions associated with desired DL Tx power adjustment indication, desired UL Tx PSD range indication, DL Tx power adjustment indication. Signals/channels applicability rules for DL Tx power adjustment. |
| RAN2 | #116e | Nov 1-12, 2021 | 1 | AI: 8.4.2 Fairness/latency/congestion: - Discuss LCG range extension: BSR format, other st3 details. - Final discussion if UL hop-by-hop flow control is in or out. AI: 8.4.3 Inter-donor BAP routing (and inter-donor-DU rerouting): - Discuss outcome of email discussion on inter-topology routing and inter-donor-DU rerouting. Converge on a common solution for both topics. Local rerouting based on congestion: - Discuss and converge on: - Available buffer size threshold configuration Type-2/3 RLF indication: - Discuss and converge on: - Terminology of type-2/3/4 RLF indication for Rel-17 specifications. - How behavior of node receiving type-2/3 indication be captured on St2. - If type-2 indication carry additional information and/or be propagated. - If type-2 indication be transmitted after RLF has been detected on only one leg for a dual-connected node. - Transmission of type-3 indication in case type-2 indication was not transmitted beforehand. - Configuration of local rerouting after reception of type-2 indication. - Trigger of CHO based on type-2 indication. CP-UP separation: - Discuss and converge on: - For use of split-SRB for scenario 2: Enhancements necessary to ensure that F1-C traffic is only carried over the SCG link. - Support of SRB3 for scenario 2. |
| RAN3 | #114e | Nov 1-12, 2021 | 2 | AI 13.2.1 Inter-donor migration: Procedure details (1) Identify gaps of St2 procedure for Partial Migration, including: For access traffic to boundary node: - IP address assignment/addition/replacement - QoS info transfer for UE traffic, including message type - Routing configuration on target path - Admission control on intermediate nodes and donor-DU on target path - DL mapping configuration on target-donor-DU - UL mapping configuration and default mapping on boundary node - Migration of TNL-, F1-C and F1-U to target path (incl. IPv6 FL/DSCP update, etc.) For descendent node traffic - IP address allocation procedure in this AI. For the baseline, we assume that IP addresses need to be updated. We can further that descendent-node migration is done after boundary node migration. (2) Equivalent St2 procedure for RLF recovery via RRC Reestablishment (3) Equivalent St2 procedure for inter-donor redundancy (4) St2 for revocation of partial migration. (5) DU migration: Discuss outcome of LSs from RAN1, 2, 4. R3#114 should agree on how to proceed with this topic. AI 13.2.2 Reduction of service interruption (1) RRC Reconfiguration delivery via source path: - Final discussion with consecutive decision on Solution 1 vs. Solution 2, so that R3#114 can aim for selection of one of these solutions and proceed with specification. (2) Discussion on avoidance of reconfiguration of the descendant nodes (e.g., the reconfiguration of IP addresses). In absence of a baseline for inter-donor migration, this discussion can address intra-donor migration. AI 13.2.3 Topological redundancy (1) Inter-topology transport for descendent-node traffic (partial migration and redundancy): - Discuss granularity of QoS-info transfer for UE traffic of descendent nodes. - Discuss Xn information exchange and configurations needed for UL mapping update at descendent nodes as well as BAP header mapping, BH RLC CH mapping, and routing at the boundary node for inter-topology traffic, etc. For BAP-related issues, the discussions should consider the RAN2 agreements from last meeting. (2) CP-UP separation: - Remaining issues. AI 13.3.1 Congestion Mitigation Update BL CR. AI 13.3.2 Multi-hop performance For inter-Donor-DU re-routing, Option 4 (i.e., IP-based tunneling between IAB-donor-DUs): - Static vs. dynamic tunnel establishment. What specification is needed (if any). - Do we need to provide source IP address to target donor DU. - Consider RAN2’s LS to RAN3 to perform header rewriting for inter-donor-DU rerouting. Any impact for RAN3? AI 13.4 Duplexing Enhancements Discuss outcome and LSs from RAN1#106e and RAN1#106bis-e meeting. |
| RAN4RF | #101e | Nov 1-12, 2021 | 0.5 | Simultaneous operation of IAB node’s child and parent links - Further study on intra-node interference considering MT/DU simultaneous transmission operation with unbalanced transmitting power with/without same antenna panel between DU and MT - Discussion on specification impact(if any) based on above study Timing related enhancement - RAN4 requirement on Timing error between intra-node IAB-DU and IAB-MT transmission with timing case#6. - Study on Timing error between parent IAB-DU and child node IAB-DU transmission Others Discussion on other aspect is not precluded depending on other working group update |
| RAN4RD | #101e | Nov 1-12, 2021 | 1 | Continue efforts on RRM impact on below aspects based on RAN1/2 update - simultaneous operation and interference management - if additional RRM update needed for timing case# 6 - Other discussion triggered by other WGs input |
| RAN | #94e | Dec 12-16, 2021 |  |  |
| RAN2 | #116e-bis | Jan 17-25, 2022 | 1 | Continue efforts |
| RAN3 | #114e-bis | Jan 17-26, 2022 | 1 | Continue efforts |
| RAN4RF | #101e-bis | Jan 17-25, 2022 | 1 | Core part: Continue efforts |
| RAN4RD | #101e-bis | Jan 17-25, 2022 | 0.5 | Core part: Continue efforts |
| RAN2 | #117e | Feb 21-March 3, 2022 | 1 | Finalize efforts |
| RAN3 | #115e | Feb 21-March 3, 2022 | 2 | Finalize efforts |
| RAN4RF | #102e | Feb 21-March 3, 2022 | 1 0.5 | Core part: Finalize efforts Perf part: initial discussion |
| RAN4RD | #102e | Feb 21-March 3, 2022 | 0.5 0.25 | Core part: Finalize efforts Perf part: initial discussion |
| RAN | #95 | March 2022 |  | Rel-17 functional freeze |
| RAN4RF | #102bis | Apr 4-8, 2022 | 0.5 | Perf part: continue discussion |
| RAN4RD | #102bis | Apr 4-8, 2022 | 0.5 | Perf part: continue discussion |
| RAN4RF | #103 | May 16-20, 2022 | 0.5 | Perf part: continue discussion |
| RAN4RD | #103 | May 16-20, 2022 | 0.5 | Perf part: continue discussion |
| RAN | #96 | June 2022 |  | Rel-17 ASN.1 freeze |
| RAN4RF | #103 | Aug, 2022 | 0.5 | Perf part: Finalize efforts |
| RAN4RD | #103 | Apr, 2022 | 0.5 | Perf part: Finalize efforts |

# References

- RP-211548: Revised WID for NR_IAB_enh; TSG RAN Meeting #92, Electronic Meeting, June 14 –18, 2020