3GPP TSG-RAN WG2 Meeting #99bis	R2-1711582

Prague, Czech Republic, 9 - 13 October 2017

Agenda item:	9.8.1

Source:	Nokia, Nokia Shanghai Bell

Title:	Updated work plan for UE Positioning Accuracy Enhancements for LTE work item

WID/SID:	LCS_LTE_acc_enh-Core - Release 15

Document for:	Discussion and Decision

# 1	Introduction

This paper provides an updated work plan for the Release 15 work item “UE Positioning Accuracy Enhancements for LTE”. Updates include status after August RAN2#99 and plans for October RAN1/2/3/4 meetings.

# 2	Background

A Release 15 work item “UE Positioning Accuracy Enhancements for LTE” [2] was approved in RAN#75. In RAN#76 this work item was updated [3] where the UE-based OTDOA objective was down prioritized as a second priority objective. Also, the completion date for the work item was updated from Dec 2017 to June 2018. The following are the objectives of this work item:

- GNSS positioning enhancements: - Specify the signalling and procedure to support RTK GNSS positioning over LPP and LPPa, taking into account both UE and network complexity. [RAN2, RAN3, RAN1] - Specify support for IMU positioning: - Specify the signalling and procedure to support IMU positioning over LPP and hybrid positioning including IMU related estimates. [RAN2, RAN1] - As second priority, specify the signalling and procedure to support UE-based OTDOA positioning [RAN2] - Broadcasting of assistance data [RAN2, RAN3, SA3, SA2] - Specify a new SIB to support signalling of positioning assistance information for A-GNSS, RTK and UE-based OTDOA assistance information. - Specify optional encryption procedure for broadcast assistance data, including mechanism for delivery of UE-specific encryption keys.

# 3	Discussion

## 3.1	Work plan and task break down per RAN WG

Following table details the work plan in terms of tasks for different RAN WG. It also shows the time line and planned allocation of time units for each meeting.

| TSG/WG | Meeting Number | Date | TU | Task |
| --- | --- | --- | --- | --- |
| RAN2 | 98 | MAY 2017 | 1 | Agreements: - Correction data (for RTK GNSS) is provided by ESMLC. RAN2 will not discuss how ESMLC gets this data in 3GPP - LS sent to SA3 on the provision of an encryption solution for broadcast positioning information - Support both UE based and UE assisted modes for RTK GNSS. How to support them is FFS |
| RAN | 76 | JUN 2017 | - | Agreements: - WID updated in RP-171508 - UE based OTDOA is down prioritized as a 2nd priority objective |
| RAN1 | 90 | AUG 2017 | 0.5 | Agreements: - Agreed definition of GNSS carrier phase measurement a.k.a. Accumulated Delta Range (ADR) and a corresponding CR to 36.214 |
| RAN2 | 99 | AUG 2017 | 1 | Agreements: - Use the RTCM Standard 10403.3 OSR message types and data fields to support network RTK - VRS (virtual reference station method) should be considered as a viable network RTK technique implemented using SIB broadcast - Support at least the following RTCM message types: - Observation message types using MSM definitions (1071 - 1127) - Station Coordinates messages (1006) - Receiver and Antenna Descriptors (1033) - GLONASS code-bias information (1230) - MAC Network RTK messages (1014, 1017, 1030, 1039, 1031) - FKP Network RTK messages (1034, 1035) - Agreed to discuss support for additional RTK GNSS methods - Agreed on some UE measurement enhancements for RTK GNSS to be captured in TS 36.355 We also discussed options for signalling of RTK GNSS assistance data but no consensus could be reached. Also, IMU positioning use cases were discussed but decided to continue discussion in next meeting. |
| RAN | 77 | SEP 2017 | - | - WI progress/status discussed and noted. |
| RAN1 | 90bis | OCT 2017 | 0.5 | - Wait for RAN2 progress on IMU positioning and address any RAN1 issues raised by RAN2. May be this time unit can be used in a future RAN1 meeting based on request from RAN2 |
| RAN2 | 99bis | OCT 2017 | 1 | NOTE: it is critical to resolve the transparent signalling vs ASN.1 encoding of RTCM message and send LS to RAN3 so they can proceed with their work. Also, it is critical to resolve the need for any L1 measurement for IMU positioning so RAN1 can utilize the TU they have remaining for this WID - Discuss whether RTCM (or other SDO defined/proprietary) messages is signalled transparently in the SIB and LPP/LPPa messages - Send LS to RAN3 providing them with RAN2 progress and identifying areas where RAN3 can work independently and where RAN3 must wait for further RAN2 progress - Discuss broadcast assistance data support and encrypted broadcast assistance data (and send reply LS to SA3) - Discuss whether we need to request RAN1 help for any L1 measurements for IMU positioning - Discuss support for SSR messages (standardized or proprietary) and PPP, PPP-RTK positioning |
| RAN3 | 97bis | OCT 2017 | 0.5 | - Begin discussion on GNSS enhancement and broadcast assistance data objectives of the work item |
| RAN4 | 84bis | OCT 2017 | 0.5 | - Investigate what core requirements work need to be done for RTK GNSS |
| RAN2 | 100 | NOV 2017 | 1 | - Start creating running stage 2 (36.305) and stage 3 (36.355) CRs for RTK GNSS, IMU, and stage 3 (36.331) for broadcast assistance data |
| RAN3 | 98 | NOV 2017 | 0.5 | - Discuss LPPa impacts for RTK GNSS and broadcast of assistance data |
| RAN4 | 85 | NOV 2017 | 0.5 | - Continue discussions on core requirements for RTK GNSS positioning |
| RAN | 78 | DEC 2017 | - | - Discuss WI progress/status and any required updates to WID - Update time unit budget and request additional TU for RAN3 for 1H18 |
| RAN1 | 92 | FEB 2018 | - | - Wait for RAN2 progress on IMU positioning and address any RAN1 issues raised by RAN2 |
| RAN2 | 101 | FEB 2018 | 1 | - Continue working on stage 2 (36.305) and stage 3 (36.355) CRs for RTK GNSS, IMU, and stage 3 (36.331) for broadcast assistance data - Finalize stage 2 decisions for IMU positioning |
| RAN3 | 99 | FEB 2018 | - | - Start creating running stage 3 (36.455) CR for RTK GNSS and broadcast assistance data |
| RAN4 | 86 | FEB 2018 | 0.5 | - Continue discussions on core and performance requirements for RTK GNSS positioning |
| RAN | 79 | MAR 2018 |  | - Discuss WI progress/status and any required updates to WID |
| RAN1 | 92bis | APR 2018 | - |  |
| RAN2 | 101bis | APR 2018 | 1 | - Finalize running CR on 36.305, 36.355, 36.331 and agree in-principle - Discuss and decide UE-based OTDOA positioning support |
| RAN3 | 99bis | APR 2018 | - | - Continue working on running stage 3 (36.455) CR for RTK GNSS and broadcast assistance data |
| RAN4 | 86bis | APR 2018 | 0.5 | - Continue discussions on core and performance requirements for RTK GNSS positioning |
| RAN1 | 93 | MAY 2018 | - |  |
| RAN2 | 102 | MAY 2018 | 1 | - Agree CRs to 36.305, 36.355, 36.331 |
| RAN3 | 100 | MAY 2018 | - | - Finalize and agree on 36.455 CR |
| RAN4 | 87 | MAY 2018 | 0.5 | - Finalize discussions on core and performance requirements for RTK GNSS positioning |
| RAN | 80 | JUN 2018 |  | - Approve CRs to RAN1/RAN2/RAN3/RAN4 core specifications |

# 4	Conclusion

This paper provided an updated work plan for completion of the work item.

# References

- 3GPP TS 21.801 Drafting Rules

- RP-170813 UE Positioning Accuracy Enhancements for LTE – 3GPP Work Item Description

- RP-171508 UE Positioning Accuracy Enhancements for LTE – 3GPP Work Item Description