## Sheet1
CB No. | Can be closed? | Flag with company name | Comments
XX | Null | Compnay name1, Company name2,... | Company name1: It is not acceptable due to... Company name2: The flag reason is ...
CB: # SONMDT1_SON | Still open | Nokia | CR in 3981 needs online checking
CB: # SONMDT2_MDT | Still open | ZTE | On line discussion about Excess Packet delay
CB: # SONMDT3_NRU | Null
CB: # SONMDT4_ASN | Yes
CB: # IAB_01_VariousStage2 | Yes
CB: # IAB_02_CR38.401 | Null
CB: # IAB_03_CR38.423 | Null
CB: # IAB_04_CR38.473 | Null
CB: # MRDC1_SCG | Yes
CB: # MRDC2_CPAC | Yes
CB: # MRDC3_ASN | Yes
CB: # QoE1_Stage2 | Yes
CB: # QoE2_Stage3 | Null
CB: # QoE3_ASN | Null
CB: # Positioning_01_MultiMeas | Null
CB: # Positioning_02_PPW_Procedures | Null
CB: # Positioning_03_St3_Corrections | Null
CB: # Positioning_04_RRC_INACTIVEandLS | Null
CB: # Positioning_05_ASN1_CRs | Yes
CB: # MBS1_General_Architecture | Yes |  | E///: Flag, due to a couple of not agreeable conclusions
CB: # MBS2_Service_Continuity | Yes | Lenovo | Lenovo: Flag, the CRs are not agreeable due to the CRs are changed a lot…
CB: # MBS3_Stage3Corr | Yes |  | E:/// Flag, due to a couple of not agreeable conclusions
CB: # MBS4_ASN | Yes
CB: # NTN1_NRNTN | Null
CB: # NTN2_IoToverNTN | Yes
CB: # NTN3_ASN | Yes
CB: # SR1_Corrections | Null
CB: # SR2_ASN | Yes
CB: # SDT1_Common | Yes
CB: # SDT2_CGbased | Null
CB: # SDT3_RACHbased | Yes
CB: # NRIIOT1_Corrections | Yes
CB: # EPSUPIP_Corrections | Yes
CB: # UEPowSav_Corrections | Null
CB: # MUSIM_Corrections | Yes
CB: # RedCap_Corrections | Yes
CB: # 1_DirectDataFwd_DCtoSA | Null
CB: # 2_DynamicACL | Yes
CB: # 3_NASPDU_Delivery | Yes
CB: # 4_PRACH | Yes | Nokia | Nokia: Introduction of new attribute is redundant with existing attribute, so needs online discussion.
CB: # 5_ProtocolSupport | Still open | Ericsson | E///: fear this needs online time
CB: # 6_RapporteurUpdates | Yes
CB: # 7_UserConsent | Still open | Ericsson | There is a need to discuss what is the remit of the LS to SA3. Right now there is no grounds for agreements
CB: # 8_MDTReportAmount | Still open | Ericsson | There is no consensus on agreed to extensions of the report amount for M4, M5, M7
CB: # 9_Flexible_gNBID | Still open | Ericsson | Revise R3-224010 to remove from the cover page what seems to be an extract from stage 2. We will tackle stage 2 at the next meeting as per agreements. I have uploaded a draft version in the “Final” folder. I propose to technically endorse the revision of R3-224010, as the agreement in our WF package was conditional to “Assuming positive feedback from RAN2, agree RAN3 CRs by end of meeting”. RAN2 has not agree to their CR yet, so the best we can do in RAN3 is to technically endorse the CR and to hope for “positive feedback from RAN2” We need to send an LS to SA2 including the revision of R3-224010, as per our way forward agreement stating “Assuming positive feedback from RAN2, agree RAN3 CRs by end of meeting”
CB: # 10_IABCorr | Yes
CB: # 11_PositionCorr | Null
CB: # 50_RACHNSA | Null
CB: # 51_DiscardTimer | Yes | Ericsson | Discuss briefly the way forward for keeping alignment between RAN2 and RAN3 regarding PDCP and SDAP config
CB: # 52_EHC | Yes
CB: # 53_V2XCorrec | Null
CB: # 54_SIB15 | Yes
CB: # 55_PriorityCall | Null
CB: # Slice1_Group_Priority | Still open | CMCC（moderator） | There is still an open issue to discuss online about whether Xn signalling is needed
CB: # Slice2_Others | Yes
CB: # 56_GapConfig | Still open | Huawei (moderator) | Huawei: Online discussion is need to final check the proposal in the SOD
CB: # 57_PDCPCount | Still open | NEC (moderator) | online to have final check of the moderator proposals.
CB: # 58_NPNOnlyCell | Yes
CB: # 59_TraceActivation | Yes
CB: # 60_F1UDelay | Null