## list of issues
TS 38.413 higher level open issues. Note: lower level open issues (e.g. stage 3 details) are captured as editor's notes and FFSes in TS 38.413.
Issue # | Section(s) | Description of issue | Status | Comments
001 | General | Impact of NG-RAN architecture description on NGAP | Closed | Resolved by R3-172863
002 | 9.1.x.y | Message structure should maximise the chances that NGAP can be reused for other Access Networks without delaying 3GPP RAN work (see LS to SA2 in R3-171401) | Open
003 | 8.9 | Procedures to support PWS are FFS | Open
004 | 8.1 | In order to support IMS multimedia services, including emergency calls, according to SA2 requirements, it may be necessary to introduce additional procedures for UE radio capability handling | Open
005 | General | The grouping of SM-related IEs using an NGAP SM container transparent to the AMF is subject to confirmation. | Closed | Use of containers for SM-related IEs (named "XX Transfer IE") has been confirmed. The related Editor's Notes are being deleted as the "XX Transfer IEs" are introduced.
006 | General | Impact on NGAP of a node supporting both E-UTRA and NR, if agreed | Open