3GPP TSG-RAN WG4 Meeting #100-e		R4-2113312
Electronic Meeting, 16th Aug. – 27th Aug., 2021

Agenda item:	9.1.2.1

Source:	CAICT, OPPO

Title:	Time plan for FR1 lab alignment and requirement development

Document for:	Approval

1	Introduction

The FR1 framework on performance requirement [1] is agreed in the last meeting of RAN4 #99-e [2]. According to the updated work plan of NR MIMO OTA Work Item, the lab alignment activity will be launched from RAN4 #100-e. In order to make laboratory volunteers and related participants have a whole picture of the lab alignment and performance requirement development activities, this paper presents the time plan and corresponding actions for developing FR1 MIMO OTA performance requirement.

2	Discussion

Regarding the performance part of the WI should be finished by September of 2022, the following time plan is specified based on the MIMO OTA WI work plan and the agreed set of activities on lab alignment and requirement development as below.

| Lab alignment & requirement development activities | Action required | Action deadline |
| --- | --- | --- |
| Lab volunteer application | Lab volunteer submits application to Rapporteur | 2021/10/15 |
| PAD list frozen | RAN4 decides PAD list from PAD candidates | 2021/11/12 |
| Channel model validation | Lab volunteer submits channel model validation results to RAN4 for review | 2022/1/14 |
| Performance alignment start | PADs arrive at lab volunteers | 2022/1/14 Note: Performance alignment can start before the date once the lab volunteer is approved |
| Performance alignment finish | Lab volunteers should finish the PADs measurement in 7 days and send the measurement results to Rapporteur | 2022/3/31 |
| Performance alignment result review | RAN4 review the performance alignment results | RAN4 #102-bis-e |
| FR1 MIMO OTA measurement data collection | Aligned labs share results into data pool | RAN4 #103-e |

Lab volunteers should note the deadline on lab volunteer application and channel model validation results submission, which relates to lab qualification and the following performance alignment arrangement.

Performance alignment device (PAD) providers should guarantee the PADs arrive at the lab volunteers as the PAD distribution arrangement before the corresponding deadline.

After lab alignment activity, the aligned labs can collect measurement results of commercial devices on the selected bands.

Proposal: Adopt the above time plan and corresponding actions for FR1 MIMO OTA lab alignment and performance requirement development, and update the progress in the following RAN4 meetings.

3	Conclusion

Proposal: Adopt the above time plan and corresponding actions for FR1 MIMO OTA lab alignment and performance requirement development, and update the progress in the following RAN4 meetings.

References

- R4-2108617 Framework on FR1 MIMO OTA requirements development

- R4-2108613 WF on NR MIMO OTA-v4