## NR BS RF work plan
| Requirement | Range-(Conducted or OTA, non-AAS or AAS type) in TR38.803 | RAN4#82bis April 2017 | RAN4#83 May 2017 | RAN4-NR#2 June 2017 | RAN4#84 August 2017 | RAN4-NR#3 September 2017 | RAN4#84bis October 2017 | RAN4#85 November 2017
General | General | 1-C-N | - Conclude the priority of conducted and OTA for below 6GHz.
|  | 1-C-A |  | The priority should be Concluded in April for the discussion after April.
1-O
2
| BS class | 1-C-N/1-C-A | - Discuss the necessity of home BS. (Definitions of WA, MR and LA BS are already agreed in SI for both BS with/without connector) | Continue | - Decide the necessity of NR home BS.
1-O
2
TX | BS output power | 1-C-N | - Discuss the metric and unit of output power limit for each BS class. | Continue | - Decide the metric and unit of output power limit for each BS class.
|  | 1-C-A |  | Continue
|  | 1-O | - Discuss the metric and unit of output power limit for each BS class. - Decide the necessity of TRP accuracy requirement. - Decide the method to derive TRP accuracy value if needed. | - Discuss the metric and unit of output power limit for each BS class. - Decide the method to derive TRP accuracy value if needed. - Provide proposed TRP accuracy value if needed. | - Decide the metric and unit of output power limit for each BS class. - Provide proposed TRP accuracy value if needed, and decide. | - Decide TRP accuracy value if needed.
|  | 2 | - Discuss the metric and unit of output power limit for each BS class. - Decide the necessity of TRP accuracy requirement. - Decide the method to derive TRP accuracy value if any. - Provide proposed EIRP accuracy value (for each three factor). | - Discuss the metric and unit of output power limit for each BS class. - Provide proposed EIRP accuracy value (for each three factor) (for each frequency range if needed). - Provide proposed TRP accuracy value (for each frequency range if needed). | - Fix the metric and unit of output power limit for each BS class. - Provide proposed EIRP accuracy value (for each three factor) (for each frequency range if needed). - Provide proposed TRP accuracy value (for each frequency range if needed). | - Provide proposed EIRP accuracy value (for each three factor) (for each frequency range if needed). - Provide proposed TRP accuracy value (for each frequency range if needed). | - Decide proposed EIRP accuracy value (for each three factor) (for each frequency range if needed). - Decide proposed TRP accuracy value (for each frequency range if needed).
| Output power dynamics | 1-C-N | - Discuss if the same dynamic range with LTE can be reused. | Continue | - Decide if the same dynamic range with LTE can be reused. If not discuss the required values. | - Discuss the required values. | - Fix the required values.
1-C-A
1-O
|  | 2 | - Discuss the necessity of dynamic range requirement. | Continue | - Decide the necessity of dynamic range requirement. If needed discuss the required values. | - Discuss the required values. | - Fix the required values.
| Transmit ON/OFF power | 1-C-N/1-C-A |  |  | RAN1 design fix?
1-O
2
Transmitted signal quality
| Frequency error | 1-C-N/1-C-A | - Discuss if it is possible to reuse the same frequency error (±0.05, 0.1, 0.25ppm) accuracy. | - Conclude if it is possible to reuse the same frequency error (±0.05, 0.1, 0.25ppm) accuracy. | Continue | - Decide frequency error accuracy. | - Draft spec. | - Finalize spec.
|  | 1-O | - Discuss if it is possible to reuse the same frequency error (±0.05, 0.1, 0.25ppm) accuracy. - Direction of measurement (if eAAS outcome can be reused or not). | - Decide if it is possible to reuse the same frequency error (±0.05, 0.1, 0.25ppm) accuracy. | Continue | - Decide frequency error accuracy. | - Draft spec. | - Finalize spec.
|  | 2 | - Discuss the needed parameters to decide frequency error accuracy. - Frequency error accuracy value. - Direction of measurement (if eAAS outcome can be reused or not). | - Discuss the frequency error accuracy for each frequency range if needed. - Decide direction of measurement. | Continue | - Decide frequency error accuracy. | - Draft spec. | - Finalize spec.
| EVM | 1-C-N/1-C-A | - Discuss the same EVM value with LTE can be reused or not. - If not, provide required and feasible EVM value for average over all PRBs and edge PRBs. - For mixed numerology, how to achieve a requirement that is implementation agnostic | Continue | Continue | Continue | - Fix EVM values for each modulation scheme. | - Draft spec. | - Finalize spec.
|  | 1-O | - Discuss the same EVM value with LTE can be reused or not. - If not, provide required and feasible EVM value for average over all PRBs and edge PRBs. - For mixed numerology, how to achieve a requirement that is implementation agnostic | Continue | Continue | Continue | - Fix EVM values for each modulation scheme. | - Draft spec. | - Finalize spec.
|  | 2 | - Discuss the same EVM value with LTE can be reused or not. - If not, provide required and feasible EVM value for average over all PRBs and edge PRBs. | Continue | Continue | Continue | - Fix EVM values for each modulation scheme. | - Draft spec. | - Finalize spec.
| TAE | 1-C-N/1-C-A | - Discuss if the same TAE value can be reused. | Continue | Continue | - Fix TAE values for each case. | - Draft spec. | - Finalize spec.
|  | 1-O | - Quantitative evaluation to confirm whether TAE is needed or not. - If TAE is needed, the same TAE can be reused. | Continue | Continue | Continue | - Conclude the necessity of TAE requirement. - If needed | - Draft spec. | - Finalize spec.
|  | 2 | - Quantitative evaluation to confirm whether TAE is needed or not. - If TAE is needed, the same TAE can be reused. | Continue | Continue | Continue | - Conclude the necessity of TAE requirement. | - Draft spec. | - Finalize spec.
| DL RS power | 1-C-N | - Discuss whether this requirement is really needed or can be excluded. - Accuracy value if requirement needed. If the same RS power accuracy can be reused. | Continue | Continue | Continue | - Conclude the necessity of DL RS power accuracy requirement. | - Draft spec. | - Finalize spec.
|  | 1-C-A | - Discuss whether this requirement is really needed or can be excluded. - Accuracy value if requirement needed. If the same RS power accuracy can be reused. | Continue | Continue | Continue | - Conclude the necessity of DL RS power accuracy requirement. | - Draft spec. | - Finalize spec.
|  | 1-O | - Discuss whether this requirement is really needed or can be excluded. - Accuracy value if requirement needed. If the same RS power accuracy can be reused. | Continue | Continue | Continue | - Conclude the necessity of DL RS power accuracy requirement. | - Draft spec. | - Finalize spec.
|  | 2 | - Discuss whether this requirement is really needed or can be excluded. - Accuracy value if requirement needed. If the same RS power accuracy can be reused. | Continue | Continue | Continue | - Conclude the necessity of DL RS power accuracy requirement. | - Draft spec. | - Finalize spec.
Unwanted emissions
| Occupied bandwidth | 1-C-N/1-C-A | - Discuss the same principle with existing (99% power should be within CBW) can be reused or not. | Continue | - Conclude the principle. | - Draft spec. | - Finalize spec.
|  | 1-O | - Direction of measurement (if eAAS outcome can be reused or not). - Discuss the same principle with existing (99% power should be within CBW) can be reused or not. | Continue | - Conclude the principle. - Conclude the direction. | - Draft spec. | - Finalize spec.
|  | 2 | - Direction of measurement (if eAAS outcome can be reused or not). - Discuss the same principle with existing (99% power should be within CBW) can be reused or not. | Continue | - Conclude the principle. - Conclude the direction. | - Draft spec. | - Finalize spec.
| ACLR | 1-C-N | - If it is possible to reuse the same ACLR value (45dBc). - Confirm necessity of co-ex simulation => simulation assumptions if needed. | -Conduct co-ex study if concluded the same ACLR value (45dBc) is not reusable. | Fix ACLR value | Need to be fixed no later than June for UE MPR evaluation. Not only UE side but also BS side simultaneously.
|  | 1-C-A |  |  |  | Need to be fixed no later than June for UE MPR evaluation. Not only UE side but also BS side simultaneously.
|  | 1-O |  |  |  | Need to be fixed no later than June for UE MPR evaluation. Not only UE side but also BS side simultaneously.
|  | 2 | - Confirm necessity of co-ex simulation. Or can reuse WP5D results. | -Conduct co-ex study if needed | Fix ACLR value | Need to be fixed no later than June for UE MPR evaluation. Not only UE side but also BS side simultaneously.
| Mask | 1-C-N | - SEM or UEM principle. - Boundary between OOB and spurious domain. | Continue | Continue | Continue | - Conclude the limit and boundary. | - Draft spec. | - Finalize spec.
|  | 1-C-A | - SEM or UEM principle. - Boundary between OOB and spurious domain. | Continue | Continue | Continue | - Conclude the limit and boundary. | - Draft spec. | - Finalize spec.
|  | 1-O | - SEM or UEM principle. - Boundary between OOB and spurious domain. - AAS emission scaling. | Continue | Continue | Continue | - Conclude the limit and boundary. | - Draft spec. | - Finalize spec.
|  | 2 | - SEM or UEM principle. - Boundary between OOB and spurious domain. - Limit value based on the FCC limit. | Continue | Continue | Continue | - Conclude the limit and boundary. | - Draft spec. | - Finalize spec.
| TX spurious emissions | 1-C-N | - Confirm required limits for cat.A and cat.B are the same as ITU-R recommendation. - Confirm if there is any open issue. | - Draft spec. | - Finalize spec.
|  | 1-C-A | - Confirm required limits for cat.A and cat.B are the same as ITU-R recommendation. - Confirm if there is any open issue. | - Draft spec. | - Finalize spec.
|  | 1-O | - Confirm required limits for cat.A and cat.B are the same as ITU-R recommendation. - Confirm if there is any open issue. | - Draft spec. | - Finalize spec.
|  | 2 | - Provide evaluation result of testability of 2nd harmonic spurious level. | Continue | Continue | Continue | - Conclude upper frequency limit for above 13GHz as a core spec. | - Draft spec. | - Finalize spec.
| TX IM | 1-C-N | - Discuss whether the same requirement with LTE can be reused or not. | - Discuss interference signal modeling. | Continue | Continue | - Conclude interference signal modeling. | - Draft spec. | - Finalize spec.
|  | 1-C-A | - Discuss whether the same requirement with AAS can be reused or not. | - Discuss interference (intra-array and inter-system) signal modeling. | Continue | Continue | - Conclude interference (intra-array and inter-system) signal modeling. | - Draft spec. | - Finalize spec.
|  | 1-O | - (If there is agreement in eAAS) Discuss whether the same requirement with eAAS can be reused or not. | - Discuss interference (intra-array and inter-system) signal modeling. | Continue | Continue | - Conclude interference (intra-array and inter-system) signal modeling. | - Draft spec. | - Finalize spec.
|  | 2 | - Discuss whether this requirement is needed or can be excluded. - Discuss interference signal modelling (frequency offset, signal level, signal bandwidth) | - Discuss whether this requirement is needed or can be excluded. - Discuss interference signal modelling (frequency offset, signal level, signal bandwidth) | Continue | Continue | - Conclude interference (intra-array and inter-system) signal modeling if needed. | - Draft spec. | - Finalize spec.
| In-band emission | 1-C-N | It was agreed not introducing in-band emission requirement in first phase spec
|  | 1-C-A | It was agreed not introducing in-band emission requirement in first phase spec
|  | 1-O | It was agreed not introducing in-band emission requirement in first phase spec
|  | 2 | It was agreed not introducing in-band emission requirement in first phase spec
RX | REFSENS | 1-C-N/1-C-A | - Discuss NF value for each BS class. | - Discuss NF value for each BS class. - Discuss the simulation assumption for SNR evaluation other than RAN1 design related. | - Fix NF value for each BS class. - Fix the simulation assumption for SNR evaluation other than RAN1 design related. | - Evaluate required SNR with the simulation assumption with temporary RAN1 design related parameters. - Fix the simulation assumption for SNR evaluation other than RAN1 design related. | - Evaluate required SNR | - Fix required SNR - Fix REFSENS | Shoud be fixed before Nov. for other RX requirements.
|  | 1-O | - Discuss how to derive EIS or TRS value. - Discuss if the same concept with AAS (vender declares the direction range to meet the requirement) can be reused or different concept | - Discuss how to derive EIS or TRS value. - Discuss if the same concept with AAS (vender declares the direction range to meet the requirement) can be reused or different concept | - Discuss how to derive EIS or TRS value. - Discuss OTA sensitivity concept | - Decide how to derive EIS or TRS value. - Decide OTA sensitivity concept. | (The same SNR and NF are used as 1-C-N/1-C-A.) | - Fix TRP or TRS values. | Shoud be fixed before Nov. for other RX requirements.
|  | 2 | - Discuss NF value for each BS class for each frequency range. - Discuss how to decide EIS or TRS value. - Discuss if the same concept with AAS (vender declares the direction range to meet the requirement) can be reused or different concept | - Discuss NF value for each BS class for each frequency range. - Discuss the simulation assumption for SNR evaluation other than RAN1 design related. - Discuss how to derive EIS or TRS value. - Discuss if the same concept with AAS (vender declares the direction range to meet the requirement) can be reused or different concept | - Fix NF value for each BS class for each frequency range. - Fix the simulation assumption for SNR evaluation other than RAN1 design related. - Discuss how to derive EIS or TRS value. - Discuss OTA sensitivity concept | - Evaluate required SNR with the simulation assumption with temporary RAN1 design related parameters. - Fix the simulation assumption for SNR evaluation other than RAN1 design related. - Decide how to derive EIS or TRS value. - Decide OTA sensitivity concept. | - Evaluate required SNR | - Fix required SNR - Fix TRP or TRS values. | Shoud be fixed before Nov. for other RX requirements.
| Dynamic range | 1-C-N/1-C-A
1-O
2
| In-channel selectivity | 1-C-N/1-C-A
1-O
2
| ACS and narrow-band blocking | 1-C-N/1-C-A | - If it is possible to reuse the same ACS value. - Confirm necessity of co-ex simulation => simulation assumptions if needed. | -Conduct co-ex study if concluded the same ACS value is not reusable. | Fix ACS value | Need to be fixed no later than June for UE MPR evaluation. Not only UE side but also BS side simultaneously.
|  | 1-O |  |  | Fix ACS value | Need to be fixed no later than June for UE MPR evaluation. Not only UE side but also BS side simultaneously.
|  | 2 | - Confirm necessity of co-ex simulation. Or can reuse WP5D results. | -Conduct co-ex study if needed | Fix ACS value | Need to be fixed no later than June for UE MPR evaluation. Not only UE side but also BS side simultaneously.
| Blocking | 1-C-N/1-C-A
1-O
2
| RX spurious emissions | 1-C-N | - Discuss if it is possible to reuse the same spurious limits. | Continue | - Draft spec. | - Finalize spec.
|  | 1-C-A | - Discuss if it is possible to reuse the same spurious limits. | Continue | - Draft spec. | - Finalize spec.
|  | 1-O | - Discuss applicability of RX spurious emission other than TDD TX OFF priod. | - Decide applicability of RX spurious emission on each case. - if needed TRP is feasible or not. | - If needed, discuss required value, upper/lower frequency limit, resolution bandwidth. | Continue | - Draft spec. | - Finalize spec.
|  | 2 | - Discuss applicability of RX spurious emission other than TDD TX OFF priod. | - Decide applicability of RX spurious emission on each case. - if needed TRP is feasible or not. | - If needed, discuss required value, upper/lower frequency limit, resolution bandwidth. | Continue | - Draft spec. | - Finalize spec.
| RX IM | 1-C-N/1-C-A
1-O
2
Other | [New] Beam related NR specific | 1-C-N/1-C-A | No need
|  | 1-O | - Discuss necessity, testability etc. on each proposed reuqirement. | - Down select candidate requirement. | - Decide new requirement to be introduced if any. | - If any, discuss the how to define the requirement(s). | - Discuss the structure of requirement. - Discuss reqired values/levels. | - Fix the structure of requirement. - Discuss reqired values/levels. - Draft spec without values. | - Fix reqired values/levels. - Finalize spec with final values.
|  | 2 | - Discuss necessity, testability etc. on each proposed reuqirement. | - Down select candidate requirement. | - Decide new requirement to be introduced if any. | - If any, discuss the how to define the requirement(s). | - Discuss the structure of requirement. - Discuss reqired values/levels. | - Fix the structure of requirement. - Discuss reqired values/levels. - Draft spec without values. | - Fix reqired values/levels. - Finalize spec with final values.