## NR UE RF work plan
[7 empty] | [Milestone#1] Fix all parameters for MPR evaluation |  | [Milestone#2] Fix MPR values & Conditions A MPR evaluation |  | Agree all CRs
Requirement |  | Range 1: Conductive for below 6GHz Range 2: OTA for above 24GHz | Outcome in SI | Topic to be addressed in WI | RAN4#82bis April 2017 | RAN4#83 May 2017 | RAN4 NR#2 June 2017 | RAN4#84 August 2017 | RAN4 NR#3 September 2017 | RAN4#84bis October 2017 | RAN4#85 November 2017
General | Subcarrier spacing |  | 15kHz, 30kHz, 60kHz are feasible for sub 6GHz 60kHz, 120kHz, 240kHz are potential candidates. 480kHz is FFS. | - Subcarrier spacing to be supported for NR bands | -Fix which subcarrier spacing(s) to be supported in each frequency range | Needs to be determined for co-ex study (if any) no later than May. |  | Needs to be determined for MPR simulation no later than August.
| CBW |  | Range for further study is 100MHz ~ 200MHz for sub 6GHz Range for further study is 100MHz ~ 1GHz for above 6GHz | - Maximum CBW and subsets of CBW to be supported for NR bands - Whether RF requirements are scalable or not - How to handle wider channel | -Fix max CBW and subsets -Investigate feasibility of flexble bandwidth from spec, testability and implementation point of view | Needs to be determined for co-ex study (if any) no later than May. -If flexble bandwidth is introduced, discussion will continue. | -Fix flexible bandwidth specs if any | Needs to be determined for MPR simulation no later than August.
| FFT size |  | 4096 FFT size is feasible as the maximum FFT size. | FFT size 8192 is FFS. | -Confirm feasibility of 8192 FFT size | Needs to be determined for co-ex study (if any) no later than May. |  | Needs to be determined for MPR simulation no later than August.
| Transmission bandwidth configuration adaptation |  | Initial analysis on transition time (RF aspects) [R4 1702029] | - How to specify transmission bandwidth configuration adaptation | -Discuss how to specify transmission bandwidth configuration adaptation | continue | continue | continue | continue | - Draft spec | - Finalize spec
| Spectrum Utilization |  | Above 90% is feasible | Spectrum Utilization value | -Determine spectrum utilizaiton value | Needs to be determined for co-ex study (if any) no later than May. |  | Needs to be determined for MPR simulation no later than August.
| Channel spacing |  | - FFS | - Channel spacing for NR | Need subcarrir spacing first | - Discuss Channel spacing based on selected subcarrier spacing | -Fix Channel spacing
| Channel raster |  | - FFS | - Channel raster for NR, possibility of sparse synchronization channel raster | Discuss channel raster based on RAN1 agreement if possible | continue | continue | continue | Fix channel raster
| Frequency channel number |  | - FFS | - Frequency channel number for NR | -Discuss how to define channel number | continue | continue | continue | - Draft spec | - Finalize spec
| TX RX frequency separation |  | - FFS | - TX RX frequency separation for NR | ・Discuss necessity of flexible separation considering LO returning for FDD band | continue | -Fix if LO returning is assumed or not | Needs to be determined for MPR simulation no later than August.
Tx | Tx maximum output power | 1 | - At least conductive test is needed. | - Conducted value - Conducted tolerance - Power sharing mechanism with LTE in NSA if specified | -Discuss conductive value and tolerance -Discuss how to treat power sharing based on LS reply from RAN1 | -Fix conductive value (for co-ex if any) continue |  | Needs to be determined for MPR simulation no later than August.
|  | 2 | - At least EIRP is used as a metric - Develop requirements for one power class as priority After requirements are understood for one PC, then, other PCs will be added. - Develop different spatial coverage requirement. Smartphone (i.e. Full sphere) is the baseline of UE types in Rel 15 - For CDF method, RAN4 method for describing spherical coverage of RF parameters is CDF where each point represents equal surface area in sphere surrounding the UE. To study the advantage of this CDF method. The other method(s) are not precluded. | - EIRP value - EIRP tolerance - How to categorise the UE type with different spatial coverage - Necessity of TRP considering regulation and/or 3GPP point of view - How to specify different power classes depending on “TRP or EIRP” and band dependency - Necessity of power sharing mechanism with LTE in NSA | -CDF details Percentile EIRP value Test points Other (e.g., side conditions) -Confirm necessity of TRP and the value -Determine how to define power class based on either EIRP or TRP | -Fix EIRP value -Fix TRP value if any (for co-ex if any) continue |  | Needs to be determined for MPR simulation no later than August.
| MPR | 1 | - At least conductive test is needed. | - MPR values for both contiguous and non contiguous resource allocation (MOP and emission requirements need to be defined first) - Granularity of MPR spec table |  |  |  | -Conduct MPR simulation for both contiguous and non-contiguous allocations | -Fix MPR valuesfor both contiguous and non-contiguous allocations | Needs to be determined for A MPR simulation, no later than October.
|  | 2 | - At least EIRP is used as a metric | - Same as range 1 - Necessity of TRP | -Confirm necessity of TRP |  |  | -Conduct MPR simulation for both contiguous and non-contiguous allocations | -Fix MPR values for both contiguous and non-contiguous allocations | Needs to be determined for A MPR simulation, no later than October.
| A-MPR | 1 | - At least conductive test is needed. | - Whether the same values as LTE are reused or not (MPR requirement is needed first) | [5 empty] | -Conduct A-MPR simulation | -Fix A-MPR values
|  | 2 | - At least EIRP is used as a metric | - Same as range 1 - Necessity of TRP | -Confirm necessity of TRP |  |  |  |  | -Conduct A-MPR simulation | -Fix A-MPR values
| PCMAX | 1 | - At least conductive test is needed. | - Calculation mechanism (e.g. reference SF) - PCMAX tolerance |  | If power control mechanism is clarified by RAN1, discussion can start. | -Start discussion of Power control mechanism based on RAN1 agreement | continue | continue | - Draft spec | - Finalize spec
|  | 2 | - At least EIRP is used as a metric | - Same as range 1 - Necessity of TRP | -Confirm necessity of TRP | If power control mechanism is clarified by RAN1, discussion can start. | -Start discussion of Power control mechanism based on RAN1 agreement | continue | continue | - Draft spec | - Finalize spec
| Minimum output power | 1 | - At least conductive test is needed. - To specify 40dBm in sub 6GHz | - No open issue
|  | 2 | - At least EIRP is used as a metric | - Whether the same limit ( 40 dBm) can be reused in mmWave considering NF, MCL and degradation level of noise floor and system perspective. - Necessity of TRP - How to categorise the UE type with different spatial coverage | -Discuss whether the same limit ( 40 dBm) can be reused in mmWave considering NF, MCL and degradation level of noise floor and system perspective. If not, alternative is provided. -Confirm necessity of TRP | continue | continue | continue | - Draft spec | - Finalize spec
| Tx OFF power | 1 | - At least conductive test is needed. - To specify 50dBm/MHz in sub 6GHz | - No open issue
|  | 2 | - TRP is used as a metric | - Whether 50dBm should be used in mmWave considering; NF of NR UE MCL between the aggressive and victim UE Degradation level of noise floor due to interference from aggressive NR UE transmit OFF power | - Discuss whether 50dBm should be used in mmWave considering; NF of NR UE MCL between the aggressive and victim UE Degradation level of noise floor due to interference from aggressive NR UE transmit OFF power | continue | continue | - Draft spec | - Finalize spec
| ON/OFF mask | 1 | - At least conductive test is needed. | - ON/OFF mask value - Whether shorter transient period (20 us) can be reused in sub 6GHz according to possible sub carrier spacing | - Discuss whether shorter transient period (20 us) can be reused in sub 6GHz according to possible sub carrier spacing | Reply LS with feasible transient period to RAN1 | - Draft spec | - Finalize spec
|  | 2 | - At least Beam peak is used as a metric | - Same as range 1 - Necessity of TRP - Achievable transient period in mmWave (e.g., 28 GHz) devices assuming dynamic range of 63dB which is starting point | -Confirm necessity of TRP - Discuss achievable transient period in mmWave (e.g., 28 GHz) devices assuming dynamic range of 63dB which is starting point | Reply LS with feasible transient period to RAN1 | continue | continue | - Draft spec | - Finalize spec
| Power control | 1 | - At least conductive test is needed. | - Power control requirements based on RAN1 agreement |  |  | -Start discussion of Power control mechanism based on RAN1 agreement | continue | continue | - Draft spec | - Finalize spec
|  | 2 | - At least Beam peak is used as a metric | - Same as range 1 - Necessity of TRP | -Confirm necessity of TRP |  | -Start discussion of Power control mechanism based on RAN1 agreement | continue | continue | - Draft spec | - Finalize spec
| Frequency error | 1 | - At least conductive test is needed. - To specify 0.1ppm in sub 6GHz | - No open issue
|  | 2 | - Beam peak is used as a metric | - Frequency error value - Whether the same frequency error (0.1 ppm) can be reused in mmWave considering settling time, etc. | - Discuss whether the same frequency error (0.1 ppm) can be reused in mmWave considering settling time, etc. | continue | continue | - Draft spec | - Finalize spec
| EVM | 1 | - At least conductive test is needed. - Develop first requirements for the baseline CP OFDM assuming suitable spectral confinement methods - Similar Transmitter impairments to LTE will be used as baseline for sub 6 and mmWave studies (IQ Image, Carrier leakage, CIM3, Phasenoise) | - EVM value for both average EVM measured over all the allocated PRBs and a few edge PRBs - How to limit sub carrier spacing for the Rel 15 WID - EVM equalizer spectrum flatness value | - Discuss the same EVM value as that ofLTE can be reused or not. - If not, provide required and feasible EVM value for average over all PRBs and edge PRBs. | continue | -Fix EVM values for each modulation scheme | Needs to be determined for MPR simulation no later than August.
|  | 2 | - Beam peak is used as a metric - Same as range 1 | - Same as range 1 | - Discuss the same EVM value as that ofLTE can be reused or not. - If not, provide required and feasible EVM value for average over all PRBs and edge PRBs. | continue | -Fix EVM values for each modulation scheme | Needs to be determined for MPR simulation no later than August.
| Carrier leakage | 1 | - At least conductive test is needed. - Develop first requirements for the baseline CP OFDM assuming suitable spectral confinement methods - Similar Transmitter impairments to LTE will be used as baseline for sub 6 and mmWave studies (IQ Image, Carrier leakage, CIM3, Phasenoise) | - Carrier leakage value - TRx impairment impact to multiple numerology case - How to limit sub carrier spacing for the Rel 15 WID | -Discuss required carrier leakage value -Indentify TRx impairment impact to multiple numerology case | continue | -Fix Carrier leakage value | Needs to be determined for MPR simulation no later than August.
|  | 2 | - Beam peak is used as a metric - Same as range 1 | - Same as range 1 | -Discuss required carrier leakage value -Indentify TRx impairment impact to multiple numerology case | continue | -Fix Carrier leakage value | Needs to be determined for MPR simulation no later than August.
| In band emissions | 1 | - At least conductive test is needed. - Develop first requirements for the baseline CP OFDM assuming suitable spectral confinement methods - Similar Transmitter impairments to LTE will be used as baseline for sub 6 and mmWave studies (IQ Image, Carrier leakage, CIM3, Phasenoise) | - In band emission values - TRx impairment impact to multiple numerology case - How to limit sub carrier spacing for the Rel 15 WID | -Discuss required in-band emissions value -Indentify TRx impairment impact to multiple numerology case | continue | -Fix in-band emissions value | Needs to be determined for MPR simulation, no later than August.
|  | 2 | - Beam peak is used as a metric - Same as range 1 | - Same as range 1 | -Discuss required in-band emissions value -Indentify TRx impairment impact to multiple numerology case | continue | -Fix in-band emissions value | Needs to be determined for MPR simulation, no later than August.
| Occupied BW | 1 | - At least conductive test is needed. | - Occupied BW value | - Discuss the same principle with existing (99% power should be within CBW) can be reused or not. | -Fix occupied bandwidth depending on CBW
|  | 2 | - TRP is used as a metric | - Same as range 1 - Necessity of EIRP | -Confirm necessity of EIRP | continue | -Determine the metric
| SEM | 1 | - At least conductive test is needed. - Assume different numerologies and RB allocations - NR UE shall meet the same SEM limit as that of LTE up to 20 MHz CBW. How to treat larger bandwidth than 20 MHz of NR is FFS. | - SEM value | -Discuss how to treat SEM limit for larger bandwidth than 20 MHz based on CBW discussion | continue | -Fix SEM value | Needs to be determined for MPR simulation no later than August.
|  | 2 | - TRP is used as a metric - Same as range 1 | - Same as range 1 - Whether there is any justification not to follow the ITU response | -Discuss whether there is any justification not to follow the ITU response. -if yes, alternative way is provided | continue | -Fix SEM value | Needs to be determined for MPR simulation no later than August.
| ACLR | 1 | - At least conductive test is needed. - NR ACLR requirements for UTRA and E UTRA are to be specified | - ACLR value for UTRA, E UTRA and NR | -Confirm necessity of co ex > simulation assumptions if any | -Conduct co ex study if any | -Conduct co ex study if any and Fix ACLR value | Needs to be determined for MPR simulation no later than August.
|  | 2 | - TRP is used as a metric - NR ACLR requirements for UTRA and E UTRA are not to be specified | - Same as range 1 | -Confirm necessity of co ex > simulation assumptions if any | -Conduct co ex study if any | -Conduct co ex study if any and Fix ACLR value | Needs to be determined for MPR simulation no later than August.
| General spurious | 1 | - At least conductive test is needed. - NR UE shall meet the same spurious limit as that of LTE. How to treat FOOB of larger bandwidth than 20 MHz of NR is FFS. | - General spurious value - Actual required level in mmWave should also be investigated from system point of view (sub 6GHz > mmWave) | -Discuss general spurious value and actual required level in mmWave -Discuss how to treat F_OOB for larger bandwidth than 20 MHz based on CBW discussion | continue | -Fix general spurious value | Needs to be determined for MPR simulation no later than August.
|  | 2 | - TRP is used as a metric - For above 13 GHz transmission, upper frequency limits should be specified as 2nd harmonics of the upper edge of the UL operating band including the full harmonic spectrum. | - Same as range 1 - Whether there is any justification not to follow the ITU response - Feasibility of post PA filtering taking harmonics and other spurious levels into account - Actual required level in mmWave should also be investigated from system point of view (mmWave > mmWave) - OOB boundary | -Discuss whether there is any justification not to follow the ITU response. -if yes, alternative way is provided | continue | -Fix general spurious value | Needs to be determined for MPR simulation no later than August.
| Additional spurious | 1 | - At least conductive test is needed. - The same limits are reused in legacy victim bands in sub 6GHz | - How to treat NS applicable bands | -Investigate required additional requirements | continue | continue | continue | -Identify required additional requirements | Needs to be determined for A MPR simulation no later than October.
|  | 2 | - TRP is used as a metric | - Same as range 1 - Additional limit on top of the ITU response | -Investigate required additional requirements | continue | continue | continue | -Identify required additional requirements | Needs to be determined for A MPR simulation no later than October.
| UE to UE coexistence | 1 | - At least conductive test is needed. - The same limits are reused in legacy victim bands in sub 6GHz | - Actual required level in mmWave should also be investigated from system point of view (sub 6GHz > mmWave) | -Investigate actual required protection level in mmWave from system point of view | continue | continue | continue | - Draft spec | - Finalize spec
|  | 2 | - TRP is used as a metric - 50dBm/MHz (mmWave > sub 6GHz) | - Actual required level in mmWave should also be investigated from system point of view. (mmWave > mmWave) | -Investigate actual required protection level in mmWave from system point of view | continue | continue | continue | - Draft spec | - Finalize spec
| Tx intermodulation | 1 | - At least conductive test is needed. | - Tx intermodulation value | - Discuss the same EVM value as that ofLTE can be reused or not. - If not, provide required and feasible EVM value for average over all PRBs and edge PRBs. | continue | - Draft spec | - Finalize spec
|  | 2 | - TRP is used as a metric with the blocker from the same direction of transmitted signal. | - Same as range 1 considering probability of being same direction when deciding blocker level | -Discuss required Tx intermodulation level | continue | continue | continue | - Draft spec | - Finalize spec
| [New] Beam correspondence | 1 | - At least conductive test is needed. | -
|  | 2 | - UE capability is introduced (RAN1 agreement) | - How to define Beam correspondence requirement | -Discuss how to define beam correspondence requirement | continue | continue | continue | continue | - Draft spec | - Finalize spec
Rx | REFSENS | 1 | At least conductive test is needed. | - REFSENS value - MSD impact in NSA of sub 6GHz and mmWave for both 1UL and 2UL. | -Study MSD impact and delta values in NSA of sub 6GHz and mmWave for both 1UL and 2UL. | continue | -Conduct SNR simulation based on FRC based on RAN1 agreement | - Identify required SNR at BB, NF, other essential factors to derive REFSENS values | ・Fix REFSENS | -Discuss UL configuration for FDD | -Fix UL configuration for FDD if any
|  | 2 | - At least EIS is used as a metric - Develop different spatial coverage requirement. Smartphone (i.e. Full sphere) is the baseline of UE types in Rel 15. - For CDF method, RAN4 method for describing spherical coverage of RF parameters is CDF where each point represents equal surface area in sphere surrounding the UE. The other method(s) are not precluded. | - Same as range 1 - How to categorise the UE type with different spatial coverage - Necessity of TRS | -CDF details Percentile EIRP value Test points Other (e.g., side conditions) -Confirm necessity of TRS -Study MSD impact and delta values in NSA of sub 6GHz and mmWave for 1UL | continue | -Conduct SNR simulation based on FRC based on RAN1 agreement | - Identify required SNR at BB, NF, other essential factors to derive REFSENS values | ・Fix REFSENS | -Discuss UL configuration for FDD if any | -Fix UL configuration for FDD if any
| Maximum input level | 1 | - At least conductive test is needed. | - Maximum input level value and the test modulation order |  |  | If maximum modulation is clarified by RAN1, discussion can start. | Discuss maximum input level with maximum modulation based on RAN1 agreement | Continue | Continue | Fix Maximum input level
|  | 2 | - At least beam peak is used as a metric | - Same as range 1 |  |  | If maximum modulation is clarified by RAN1, discussion can start. | Discuss maximum input level with maximum modulation based on RAN1 agreement | Continue | Continue | Fix Maximum input level
| ACS | 1 | - At least conductive test is needed. | - ACS value | -Confirm necessity of co ex > simulation assumptions if any | -Conduct co ex study if any | -Conduct co ex study if any and Fix ACS value | To be fixed with ACLR in co ex study if any
|  | 2 | - Beam peak is used as a metric (to be further investigated) i.e. the blocker from the same direction of wanted signal. | - Same as range 1 considering probability of being same direction when deciding blocker level - Necessity of TRS | -Confirm necessity of co ex > simulation assumptions if any -Confirm necessity of TRS | -Conduct co ex study if any | -Conduct co ex study if any and Fix ACS value | To be fixed with ACLR in co ex study if any
| In band blocking | 1 | - At least conductive test is needed. | - In band blocking value | -Confirm if the same blocker level can be used | Continue | Continue | - Draft spec | - Finalize spec
|  | 2 | - Beam peak is used as a metric (to be further investigated) i.e. the blocker from the same direction of wanted signal. | - Same as range 1 considering probability of being same direction when deciding blocker level - Necessity of TRS | -Discuss in-band blocker level -Confirm necessity of TRS | Continue | Continue | Continue | Continue | - Draft spec | - Finalize spec
| Out of band blocking | 1 | - At least conductive test is needed. | - Out of band blocking value | -Confirm if the same blocker level can be used | Continue | Continue | - Draft spec | - Finalize spec
|  | 2 | - Beam peak is used as a metric (to be further investigated) where OOB blocker is <±FFS% away from the center frequency of the wanted signal | - Blocker frequency offset value - Same as range 1 considering receiver tolerance and possibility of blocker in mmWave. - Necessity of TRS | -Confirm necessity of TRS -Investigate expected blocker level in each region/country -Discuss how to treat blocker frequency offset value | Continue | Continue | Continue | Continue | - Draft spec | - Finalize spec
| Narrow band blocking | 1 | - At least conductive test is needed. | - Narrow band blocking value considering applicable bands | -Confirm if the same blocker level can be used | Continue | Continue | - Draft spec | - Finalize spec
|  | 2 | - Same as range 1 | - Necessity of this requirement - Same as range 1 | -Confirm necessity of this requirement | If the need is identified, discussion will continue
| Spurious response | 1 | - At least conductive test is needed. | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking
|  | 2 | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking | - See Out of band blocking
| Rx intermodulation | 1 | - At least conductive test is needed. | - Rx intermodulation value | - Discuss if it is possible to reuse the same spurious limits as LTE. | Continue | - Draft spec | - Finalize spec
|  | 2 | - Beam peak is used as a metric i.e. the both blockers from the same direction of wanted signal. | - Same as range 1 considering probability of being same direction when deciding blocker level | -Investigate possible blocker level | Continue | Continue | Continue | Continue | - Draft spec | - Finalize spec
| Rx spurious emission | 1 | - At least conductive test is needed. | - Rx spurious emission value | -Confirm if the same blocker level can be used | - Draft spec | - Finalize spec
|  | 2 | - TRP is used as a metric - For above 13 GHz transmission, upper frequency limits should be specified as 2nd harmonics of the upper edge of the DL operating band including the full harmonic spectrum. | - Same as range 1 | -Discuss general spurious value and actual required level in mmWave | continue | -Fix general spurious value and actual required level in mmWave
| Receiver image | 1 | - At least conductive test is needed. | - Receiver image value | -Investigate required receiver image value | Continue | Continue | - Draft spec | - Finalize spec
|  | 2 | - | - Same as range 1 - Receiver image metric | -Discuss the metric -Investigate required value | Continue | Continue | - Draft spec | - Finalize spec
| [New] In channel selectivity | 1 | - At least conductive test is needed. - Definition in mixed numerology case should follow the same format as uplink, taking the possible power imbalance level between numerologies into consideration | - In channel selectivity value for different numerologies (15 and 60 kHz SCS) | -Investigate required and feasible in-channel selectivity value | Continue | Continue | Continue | Continue | - Draft spec | - Finalize spec
|  | 2 | - Same as range 1 - Beam peak is used as a metric i.e. the blocker from the same direction of wanted signal. | - Same as range 1 | -Investigate required and feasible in-channel selectivity value | Continue | Continue | Continue | Continue | - Draft spec | - Finalize spec