## Slide 1
3GPP TSG RAN5 Meeting #75 R5-172956
Hangzhou, China, 15-19 May 2017
Discussion of time plan for RAN5 5G-NR WI
CMCC

## Slide 2: Observation: RAN agreed L1 and L2-user-plane for 5G NR SA will complete together with NSA option 3 in Dec 2017, SA and NSA option 3 can start at the same time in RAN5.
By December 2017: complete Stage 3 for Non-Standalone 5G-NR eMBB (incl. low latency support) with Option 3
  Ensure commonality with Standalone eMBB (incl. low latency support), as well as forward compatibility
    Complete stage-3 of all L1 and L2-User-Plane for both Non-Standalone and Standalone by December 2017
    L1 and L2-User-Plane for both Non-Standalone and Standalone is different for some aspects
  Prioritization of NR band definition (and related band combinations with LTE) will be discussed separately
RAN agreement from RP-170741:

## Slide 3: RAN agreed time plan for core groups
2016 | 2017 |  |  |  | 2018 |  |  | 
Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
NSA = Non StandAlone = EPC core (“Option 3”) & LTE anchor
SA = StandAlone
5G study
5G NR Work Item
5G NR NSA Completion
Stage 3 completion for Non-Standalone 5G-NR
RAN #74
RAN #75
RAN #78
RAN #80 (Rel-15 completion)
Further evolution
5G NR SA Completion
Stage 3 completion for Standalone 5G-NR
NSA Option 3 family ASN.1
Rel-15 ASN.1 for SA & NSA
Observation 1:
5G NR NSA option 3 and SA (option 2) are under working parallel in core groups and option 3 may complete earlier.
Observation 2:
According to the present clear industry requirements, option 3 and option 2 have higher priority comparing to other options.
Proposal:
RAN5 starts working on Option 3 and Option 2 simultaneously, the completion date of options depends on the progress of the core groups.

## Slide 4
#75
RAN5
#76
#77
#78
#79
#80
#81
#1 AH
#2 AH
#3 AH
May-17
Aug
Nov
Feb-18
April
May
July
Aug
Oct
Nov
RAN
#76
#78
#79
#80
#81
Jun-17
Dec
Mar-18
June
Sep
Dec
#82
NSA option 3 core part & SA L1/2 complete
Initial Pseudo CRs
Option 3 & 2
Complete SA and NSA common TCs and Option 3 specific TCs.
Option 5/7
performance Start
core part complete
Option 4 & Performance
SA and other options core complete
ASN.1 freeze for option 3
ASN.1 freeze for SA
RAN5 WI approval
RAN5 WI Complete
V15.0.0 of TSs/TRs
V15.4.0 of TSs/TRs
Initial RAN5 5G-NR WI time plan for discussion
Mar-19
#83
Jun-19
#84
#82
#4 AH
Jan-19
Feb
#83
#5 AH
April
May-19
RAN4 Performance Complete
Performance complete
core part start
WP
2017
2018
2019
WI common
Skeleton of WP and TSs/TRs
Initial WP
V1.0.0 of TSs/TRs
V2.0.0 of TSs/TRs
WI complete
Option 2 Core part complete