3GPP TSG-RAN WG5 Meeting #76	R5-174443

Berlin, Germany, 21st – 25th August 2017

Agenda Item:	7.4.2

Source: 	Rapporteur (ZTE)

Title: 	WP - UE Conformance Test Aspects – LTE UE TRP and TRS and UTRA Hand Phantom

Work item code:	LTE_UTRA_TRP_TRS-UEConTest

Document for:	Information

__________________________________________________________________________

# 1	Introduction

At the RAN#63 meeting in Fukuoka, Japan, 3 - 6 March 2014 a RAN5 work item for UE Conformance Test Aspects – LTE UE TRP and TRS and UTRA Hand Phantom (Unique ID# 630011) was approved [1].

The purpose of present document is to provide a work plan for the RAN5 work item for LTE UE TRP and TRS and UTRA Hand Phantom (LTE_UTRA_TRP_TRS-UEConTest). The work plan is updated after each RAN5 meeting to provide the current status of the work item.

Based on the revised WID in [2] GSM have been removed from the work plan. The release has been changed to Rel-13 based on the revised WID in [2]. The RAN5 work item has been revised in [3].

Section 2 gives an overview of the work item status. Section 3 lists the planned test cases and the detailed status. Section 4 summarises the test coverage analysis and the agreed assumptions used as base for the work plan.

# 2	Work item status

The current completeness of the LTE_UTRA_TRP_TRS-UEConTest work item is:

| specification | Testing area | Current Completeness | 3 month target | 6 month target | Comments | History |
| --- | --- | --- | --- | --- | --- | --- |
| TS 37.544 | User Equipment (UE) and Mobile Station (MS) Over The Air (OTA) performance; Conformance testing | 78% |  |  |  |  |

Estimation of WI overall completeness:

| Overall completeness | 78% |  |
| --- | --- | --- |

Colour coding:

|  | Not started |
| --- | --- |
|  | Ongoing |
|  | Ready |

# 3	Test Case List in Work Plan

## 3.1	Changes to TS 37.544

| No | Area | TS | Clause | Release | TC Title | Test purpose / Description | Company | Target | Status | TDOC | Comments |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 37.544 – RF |  |  |  |  |  |  |  |  |  |  |  |
|  | Scope | 37.544 | 1 | Rel-13 | Scope | Scope of Specification | ZTE | RAN5#71 | 100% | R5-144867 R5-150198 |  |  |
|  | References | 37.544 | 2 | Rel-13 | References | References of Specification | ZTE | RAN5#71 | 100% | R5-144868 R5-150199 |  |  |
|  | Definitions, Symbols, and Abbreviations | 37.544 | 3 | Rel-13 | Definitions, Symbols, and Abbreviations | Definitions, Symbols, and Abbreviations | ZTE | RAN5#71 | 100% | R5-144869 R5-145474 R5-150200 R5-150201 R5-151216 |  |  |
|  | General | 37.544 | 4 | Rel-13 | General | General | ZTE | RAN5#71 | 100% | R5-150202 R5-155509 |  |  |
|  |  | 37.544 | 4.1 | Rel-13 | Terminal classes |  | ZTE | RAN5#71 | 100% | R5-155379 |  |  |
|  |  | 37.544 | 4.2 | Rel-13 | UTRA chip rates |  | ZTE | RAN5#71 | 100% | R5-155379 |  |  |
|  |  | 37.544 | 4.3 | Rel-13 | DUT positioning |  | Intel Corp. | RAN5#71 | 100% | R5-144882 R5-151217 R5-151219 R5-151220 R5-151221 R5-151222 |  |  |
|  |  | 37.544 | 4.4 | Rel-13 | Sampling grid |  | Intel Corp. | RAN5#71 | 100% | R5-144883 |  |  |
|  |  | 37.544 | 4.5 | Rel-13 | Number of independent samples (for reverberation chamber procedure) |  | ZTE, Sporton | RAN5#71 | 100% | R5-155549 |  |  |
|  | Measurement Frequencies | 37.544 | 5 | Rel-13 | General |  | Sporton | RAN5#71 | 100% | R5-150203 R5-155509 |  |  |
|  |  | 37.544 | 5.1 | Rel-13 | UTRA FDD Frequency Bands |  | Sporton | RAN5#71 | 100% | R5-144888 |  |  |
|  |  | 37.544 | 5.2 | Rel-13 | UTRA TDD Frequency Bands |  | Sporton | RAN5#71 | 100% | R5-144889 |  |  |
|  |  | 37.544 | 5.3 | Rel-13 | E-UTRA FDD Frequency Bands |  | Intel Corp. | RAN5#71 | 90% | R5-144884 R5-155509 R5-171914 |  | Some frequency bands TBD |
|  |  | 37.544 | 5.4 | Rel-13 | E-UTRA TDD Frequency Bands |  | Intel Corp. | RAN5#71 | 90% | R5-144888 R5-150451 R5-155509 R5-171914 |  | Some frequency bands TBD |
|  | Transmitter Total Radiated Power | 37.544 | 6 | Rel-13 | Transmitter Performance |  | Sporton | RAN5#71 | 100% | R5-150204 |  |  |
|  |  | 37.544 | 6.1 | Rel-13 | Performance for handheld UE |  | Sporton | RAN5#71 | 100% | R5-145863 |  |  |
|  |  | 37.544 | 6.1.1 | Rel-13 | Total Radiated Power (TRP) for UTRA FDD using Head Phantom |  | Sporton | RAN5#71 | 100% | R5-145863 R5-155676 R5-155549 R5-155509 R5-171303 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 6.1.2 | Rel-13 | Total Radiated Power (TRP) for UTRA LCR TDD using Head Phantom |  | ZTE | RAN5#71 | 100% | R5-153120 R5-155676 R5-155549 R5-155509 R5-171303 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 6.1.3 | Rel-13 | Total Radiated Power (TRP) for UTRA FDD using Head and Hand Phantom |  | Intel Corp. | RAN5#71 | 100% | R5-145417 R5-155676 R5-155549 R5-155509 R1-166094 R5-171303 R1-173368 |  |  |
|  |  | 37.544 | 6.1.4 | Rel-13 | Total Radiated Power (TRP) for UTRA LCR TDD using Head and Hand Phantom |  | Intel Corp. | RAN5#71 | 100% | R5-145418 R5-155676 R5-155549 R5-155509 R5-171303 R1-173368 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 6.1.5 | Rel-13 | Total Radiated Power (TRP) for E-UTRA FDD using Head and Hand Phantom |  | Intel Corp. | RAN5#71 | 75% | R5-150433 R5-155676 R5-155549 R5-155509 |  | Missing some requirements and TT |
|  |  | 37.544 | 6.1.6 | Rel-13 | Total Radiated Power (TRP) for E-UTRA TDD using Head and Hand Phantom |  | Intel Corp. | RAN5#71 | 75% | R5-150434 R5-155676 R5-155549 R5-155509 |  | Missing some requirements and TT |
|  |  | 37.544 | 6.1.7 | Rel-13 | Total Radiated Power (TRP) for UTRA FDD using Browsing Mode |  | ZTE | RAN5#71 | 100% | R5-151531 R5-153121 R5-155676 R5-155549 R5-155509 R5-171303 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 6.1.8 | Rel-13 | Total Radiated Power (TRP) for UTRA LCR TDD using Browsing Mode |  | ZTE | RAN5#71 | 100% | R5-151531 R5-153122 R5-155676 R5-155549 R5-155509 R5-171303 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 6.1.9 | Rel-13 | Total Radiated Power (TRP) for E-UTRA FDD using Browsing Mode |  | ZTE | RAN5#71 | 75% | R5-153123 R5-155676 R5-155549 R5-155509 |  | Missing some requirements and TT |
|  |  | 37.544 | 6.1.10 | Rel-13 | Total Radiated Power (TRP) for E-UTRA TDD using Browsing Mode |  | ZTE | RAN5#71 | 75% | R5-153124 R5-155676 R5-155549 R5-155509 |  | Missing some requirements and TT |
|  |  | 37.544 | 6.2 | Rel-13 | Performance for LME |  | ZTE | RAN5#71 | 100% | R5-153125 |  |  |
|  |  | 37.544 | 6.2.1 | Rel-13 | Total Radiated Power (TRP) for UTRA FDD using LME |  | ZTE | RAN5#71 | 100% | R5-153125 R5-155676 R5-155549 R5-155509 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 6.2.2 | Rel-13 | Total Radiated Power (TRP) for UTRA LCR TDD using LME |  | ZTE | RAN5#71 | 100% | R5-153126 R5-155676 R5-155549 R5-155509 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 6.2.3 | Rel-13 | Total Radiated Power (TRP) for E-UTRA FDD using LME |  | ZTE | RAN5#71 | 75% | R5-153127 R5-155676 R5-155549 R5-155509 |  | Missing some requirements and TT |
|  |  | 37.544 | 6.2.4 | Rel-13 | Total Radiated Power (TRP) for E-UTRA TDD using LME |  | ZTE | RAN5#71 | 75% | R5-153128 R5-155676 R5-155549 R5-155509 |  | Missing some requirements and TT |
|  |  | 37.544 | 6.3 | Rel-13 | Performance for LEE |  | Intel Corp. | RAN5#71 | 100% | R5-151530 R5-155506 |  |  |
|  |  | 37.544 | 6.3.1 | Rel-13 | Total Radiated Power (TRP) for UTRA FDD using LEE |  | Intel Corp. | RAN5#71 | 100% | R5-145420 R5-155506 R5-155676 R5-155549 R5-155509 R1-166093 R5-171303 |  |  |
|  |  | 37.544 | 6.3.2 | Rel-13 | Total Radiated Power (TRP) for UTRA LCR TDD using LEE |  | Intel Corp. | RAN5#71 | 100% | R5-145421 R5-155506 R5-155676 R5-155549 R5-155509 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 6.3.3 | Rel-13 | Total Radiated Power (TRP) for E-UTRA FDD using LEE |  | Intel Corp. | RAN5#71 | 100% | R5-150435 R5-155506 R5-155676 R5-155549 R5-155509 R5-173368 |  | Missing some requirements and TT |
|  |  | 37.544 | 6.3.4 | Rel-13 | Total Radiated Power (TRP) for E-UTRA TDD using LEE |  | Intel Corp. | RAN5#71 | 100% | R5-150436 R5-155506 R5-155676 R5-155549 R5-155509 R5-173368 |  | Missing some requirements and TT |
|  | Receiver Total Radiated Sensitivity | 37.544 | 7 | Rel-13 | Receiver Performance |  | Sporton | RAN5#71 | 100% | R5-150205 |  |  |
|  |  | 37.544 | 7.1 | Rel-13 | Performance for handheld UE |  | Sporton | RAN5#71 | 100% | R5-153085 |  |  |
|  |  | 37.544 | 7.1.1 | Rel-13 | Total Radiated Sensitivity (TRS) for UTRA FDD using Head Phantom |  | Sporton | RAN5#71 | 100% | R5-153085 R5-155676 R5-155549 R5-155509 R5-171303 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 7.1.2 | Rel-13 | Total Radiated Sensitivity (TRS) for UTRA LCR TDD using Head Phantom |  | Sporton | RAN5#71 | 100% | R5-153086 R5-155676 R5-155549 R5-155509 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 7.1.3 | Rel-13 | Total Radiated Sensitivity (TRS) for UTRA FDD using Head and Hand Phantom |  | Intel Corp. | RAN5#71 | 100% | R5-150439 R5-153271 R5-155676 R5-155549 R5-155509 R1-166094 R5-171303 R5-173368 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 7.1.4 | Rel-13 | Total Radiated Sensitivity (TRS) for UTRA LCR TDD using Head and Hand Phantom |  | Intel Corp. | RAN5#71 | 100% | R5-150442 R5-153271 R5-155676 R5-155549 R5-155509 R5-171303 R5-173368 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 7.1.5 | Rel-13 | Total Radiated Sensitivity (TRS) for E-UTRA FDD Head and Hand Phantom |  | Intel Corp. | RAN5#71 | 75% | R5-150445 R5-155676 R5-155549 R5-155509 |  | Missing some requirements and TT |
|  |  | 37.544 | 7.1.6 | Rel-13 | Total Radiated Sensitivity (TRS) for E-UTRA TDD using Head and Hand Phantom |  | Intel Corp. | RAN5#71 | 75% | R5-150446 R5-155676 R5-155549 R5-155509 |  | Missing some requirements and TT |
|  |  | 37.544 | 7.1.7 | Rel-13 | Total Radiated Sensitivity (TRS) for UTRA FDD using Browsing Mode |  | Intel Corp | RAN5#71 | 100% | R5-153267 R5-155676 R5-155549 R5-155509 R5-171303 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 7.1.8 | Rel-13 | Total Radiated Sensitivity (TRS) for UTRA LCR TDD using Browsing Mode |  | Intel Corp | RAN5#71 | 100% | R5-153268 R5-155676 R5-155549 R5-155509 R5-171303 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 7.1.9 | Rel-13 | Total Radiated Sensitivity (TRS) for E-UTRA FDD using Browsing Mode |  | Intel Corp | RAN5#71 | 75% | R5-153269 R5-155676 R5-155549 R5-155509 |  | Missing some requirements and TT |
|  |  | 37.544 | 7.1.10 | Rel-13 | Total Radiated Sensitivity (TRS) for E-UTRA TDD using Browsing Mode |  | Intel Corp | RAN5#71 | 75% | R5-153270 R5-155676 R5-155549 R5-155509 |  | Missing some requirements and TT |
|  |  | 37.544 | 7.2 | Rel-13 | Performance for LME |  | Sporton | RAN5#71 | 100% | R5-153087 |  |  |
|  |  | 37.544 | 7.2.1 | Rel-13 | Total Radiated Sensitivity (TRS) for UTRA FDD using LME |  | Sporton | RAN5#71 | 100% | R5-153087 R5-155676 R5-155549 R5-155509 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 7.2.2 | Rel-13 | Total Radiated Sensitivity (TRS) for UTRA LCR TDD using LME |  | Sporton | RAN5#71 | 100% | R5-153088 R5-155676 R5-155549 R5-155509 |  | Aligned with RAN4 requirements |
|  |  | 37.544 | 7.2.3 | Rel-13 | Total Radiated Sensitivity (TRS) for E-UTRA FDD using LME |  | Sporton | RAN5#71 | 75% | R5-153089 R5-155676 R5-155549 R5-155509 |  | Missing some requirements and TT |
|  |  | 37.544 | 7.2.4 | Rel-13 | Total Radiated Sensitivity (TRS) for E-UTRA TDD using LME |  | Sporton | RAN5#71 | 75% | R5-153090 R5-155676 R5-155549 R5-155509 |  | Missing some requirements and TT |
|  |  | 37.544 | 7.3 | Rel-13 | Performance for LEE |  | Intel Corp. | RAN5#71 | 100% | R5-151530 R5-155508 |  |  |
|  |  | 37.544 | 7.3.1 | Rel-13 | Total Radiated Sensitivity (TRS) for UTRA FDD using LEE |  | Intel Corp. | RAN5#71 | 100% | R5-150447 R5-155508 R5-155676 R5-155549 R5-155509 R5-166093 |  | R5-155676 R5-155549 R5-155509 Aligned with RAN4 requirements |
|  |  | 37.544 | 7.3.2 | Rel-13 | Total Radiated Sensitivity (TRS) for UTRA LCR TDD using LEE |  | Intel Corp. | RAN5#71 | 100% | R5-150448 R5-155508 R5-155676 R5-155549 R5-155509 |  | R5-155676 R5-155549 R5-155509 Aligned with RAN4 requirements |
|  |  | 37.544 | 7.3.3 | Rel-13 | Total Radiated Sensitivity (TRS) for E-UTRA FDD using LEE |  | Intel Corp. | RAN5#71 | 100% | R5-150449 R5-155508 R5-155676 R5-155549 R5-155509 R5-173368 |  | R5-155676 R5-155549 R5-155509 |
|  |  | 37.544 | 7.3.4 | Rel-13 | Total Radiated Sensitivity (TRS) for E-UTRA TDD using LEE |  | Intel Corp. | RAN5#71 | 100% | R5-150450 R5-155508 R5-155676 R5-155549 R5-155509 R5-173368 |  | R5-155676 R5-155549 R5-155509 |
|  | Annex A & Test System Characterization and Environmental requirements | 37.544 | A | Rel-13 | Annex A |  | ZTE | RAN5#71 | 100% | R5-144882 R5-145860 R5-145881 R5-150206 R5-151218 R5-151220 |  |  |
|  | Calibration | 37.544 | B | Rel-13 | Annex B |  | ZTE | RAN5#71 | 100% | R5-145875 R5-150207 |  |  |
|  | Measurement Test Report | 37.544 | C | Rel-13 | Annex C |  | ZTE | RAN5#71 | 100% | R5-151224 R5-155380 |  |  |
|  | Maximum Uncertainty of Test System and Test Tolerances | 37.544 | D | Rel-13 | Annex D |  | ZTE | RAN5#71 | 75% | R5-151908 R5-151909 |  |  |
|  | Estimation of Measurement Uncertainty | 37.544 | E | Rel-13 | Annex E |  | ZTE | RAN5#71 | 100% | R5-151227 R5-155380 |  |  |
|  | Suggested Recipes of Liquid to be used inside SAM Phantom | 37.544 | F | Rel-13 | Annex F |  | ZTE | RAN5#71 | 100% | R5-151223 |  |  |
|  | Anechoic Chamber Specifications and Validation Method | 37.544 | G | Rel-13 | Annex G |  | Intel Corp. | RAN5#71 | 100% | R5-151228 R5-151528 |  |  |
|  | Reverberation chamber Specifications and Validation Method | 37.544 | H | Rel-13 | Annex H |  | Sporton | RAN5#71 | 100% | R5-151229 R5-155549 |  |  |
|  | Recommended performance for Handheld UE | 37.544 | I | Rel-13 | Annex I |  | Sporton | RAN5#71 | 75% | R5-153091 |  |  |
|  | Recommended performance for LME | 37.544 | J | Rel-13 | Annex J |  | Sporton | RAN5#71 | 75% | R5-153092 |  |  |
|  | Recommended performance for LEE | 37.544 | K | Rel-13 | Annex K |  | Intel Corp | RAN5#71 | 75% | R5-151907 R5-153093 R5-155506 R5-155508 |  |  |

# 4	Test coverage analysis and assumptions

Impacted core specifications relevant for RAN5 test specifications for UE Conformance Test Aspects for LTE UE TRP and TRS and UTRA Hand Phantom are:

| TS/TR | Title |
| --- | --- |
| TS 37.144 | Technical Specification Group Radio Access Network; User Equipment (UE) and Mobile Station (MS) over the air performance requirements |
| TR 37.902 | Technical Specification Group Radio Access Network; Measurements of User Equipment (UE) radio performances for LTE/UMTS terminals; Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) test methodology |

Following assumptions have been made as base for this work plan:

- RF testing

  - Core requirements of 37.144 will be covered by RF test cases in new specification.

# 5	References

[1]	RP-140090	New work item proposal: UE Conformance Test Aspects - LTE UE TRP and TRS and UTRA Hand Phantom (Source: ZTE)

[2]	RP-141966	Revised WID: LTE UE TRP and TRS and UTRA Hand Phantom related UE TRP and TRS Requirements, Nokia Corporation

[3]	RP-150070	Revised WID: UE Conformance Test Aspects - LTE UE TRP and TRS and UTRA Hand Phantom (Source: ZTE)