## Sheet1
RAN5 5GS AP list
AP-5G# | WG | Area | Description | AP Owner(s) | Comments | Status | Start date | Target / End date
1 | RF+SIG | RAN1 | DCI formats and information about transport block size to be used for NR is missing in RAN1 specifictions. This is basic information critical to be available in the RAN1 NR TSs after RAN1#91 (Nov-17) to progress of RAN5 work. Check with RAN1 when this information will be available. If needed, RAN5 chair to inform RAN1 chair before RAN1#91 (Nov-17) about the RAN5 needs. | Ericsson (Leif Mattisson), RAN5 chair (Jacob John) |  | Not started | 2017-11-02 | Before RAN5#77
2 | RF+SIG | RAN1, RAN2 | L1\L2 layer parameters still not defined, this will impact overall SIG progress. Check with RAN1 & RAN2 when this will be included in RAN1 and RAN2 draft TSs. If needed, RAN5 chair to inform RAN1 and RAN2 chair before RAN1#91 and RAN2#100 (Nov-17) about the RAN5 needs. | Ericsson (Leif Mattisson), RAN5 chair (Jacob John) |  | Not started | 2017-11-02 | Before RAN5#77
3 | RF | RAN4 | To progress RAN5 RF for Option 3 at the RAN5 ad-hoc#1 (16-19 Jan 2018) it is necessary to clarify which specs (TS38.101-1/2/3) are capturing the requirements for NSA and it is critical that TSs or the associated TRs will become available after the RAN4#85 meeting in Reno. RAN4 needs to be informed about this before RAN4#85. If needed, RAN5 chair to inform RAN4 chair before RAN4#85 (Nov-17) about the RAN5 needs. | CMCC (Jinqiang Xing), Qualcomm (Pradeep Gowda), RAN5 chair (Jacob John) |  | Not started | 2017-11-02 | Before RAN5#77
4 | SIG | RAN2 | Which encryption and integrity protection algorithms will be used for NR? Need to check with RAN2 when this will be decided. | Qualcomm (Yogesh Tugnawat) |  | Not started | 2017-11-02 | RAN5#77
5 | SIG | RAN2 | Is support of NR-PDCP on MCG split bearer mandatory or optional? If optional this will result in NR-PDCP test cases will be optional for NSA option 3. Need to be confirmed with RAN2. | Qualcomm (Yogesh Tugnawat) |  | Not started | 2017-11-02 | RAN5#77
6 | SIG | RAN2 | Uplink Switching for Split Bearer options - Is it controlled by NW? | Qualcomm (Yogesh Tugnawat) |  | Not started | 2017-11-02 | RAN5#77
7 | SIG | UE test functions | Update the Discussion paper for checking UE's IP stack, add some examples. | Qualcomm (Yogesh Tugnawat) |  | Not started | 2017-11-02 | RAN5#77
8 | RF+SIG | UE test functions | Rapporteurs need to collect requirements (and possible operation) for loopback modes based on their test case requirement and inform TS 38.509 rapporteur (Stoyan Baev, Samsung) | WP sub-area rapporteurs |  | Not started | 2017-11-02 | Option 3: RAN5#77
9 | SIG | EN-DC | RAN5 assumption is that all options for EN-DC needs to be considered (3, 3a, 3x). Further confirmation needed? | Qualcomm (Yogesh Tugnawat) |  | Ongoing | 2017-11-02 | RAN5#77
10 | SIG | EN-DC | Discuss complexities due to testing of several bearer options for EN-DC. | Qualcomm (Yogesh Tugnawat) |  | Not started | 2017-11-02 | RAN5#77
11 | SIG | UE test functions | UE beamlock function, will it be needed for signaling? RAN5 need to evaluate. | Ericsson (Leif Mattisson), SS vendors |  | Not started | 2017-11-02 | RAN5#78
12 | SIG | SIG OTA | Evaluate means for performing protocol testing for UEs only supporting NR mmWave bands. Must OTA chambers as used for RF/RRM for NR mmWave frequencies be used?; or can "simpler" means be used considering that protocol testing is functional? Discussions from OTA discussions in the RF group to be included in RF/SIG joint session. | Qualcomm (Pradeep Gowda), SS vendors |  | Not started | 2017-11-02 | RAN5#77
13 | RF | RF OTA | Ensure reliability of the LTE OTA link: 1. Define appropriate DL power, TM mode, MCS 2. No DL or UL grants after 5G-NR connection setup. Do we require active 5G-NR signaling over LTE link which would need LTE DL/UL Traffic? 3. Impact to OTA chamber dimensions due to OTA LTE 4. Impact of multipath due to reflections for OTA LTE | Qualcomm (Vijay Balasubramanian), SS vendors |  | Not started | 2017-11-02 | RAN5#77
14 | RF | RAN4 | UE beam lock function (UBF) for RF/RRM mmwOTA tests. Way fwd to be finalized by Ran5, but need RAN4 input on the requirements that will need UBF, to help RAN5 define the UBF aspects. LS input from RAN4 on the need for UBF to RAN5#77. RAN5 need to request further details from RAN4 in the response LS to RAN4 to be able to define the details in 38.509. | Qualcomm (Pradeep Gowda) |  | Not started | 2017-11-02 | RAN5#78