## R5#78 post meeting planning
Task ID | Task Description | Priority | Compl. Target yyyy-mm-dd | 5GArea | Specification | External Dependency | Owner (Company) | Supervisor | Completion status | Comments
78#G01 | Notify on RAN5 5G NR reflector about the baseline of RAN2 and RAN4 TSs to be used as base for RAN5 5GS Ad-hoc#2 text proposals. The baseline may be RAN2/RAN4 Athens meeting agreed CRs, post meeting draft specs, or RAN plenary approved specs. | High | 2018-03-19 | NSA Op3 Ph1 | See Comments |  | Ericsson, Qualcomm | Leif Mattisson, Ericsson | Open | Impact on 38.508 and 38.523-1
78#G02 | Draft all EN-DC RRC and NAS protocol details necessary for generic procedures RRC_IDLE and RRC_CONNECTED and ASN.1 messages with default IE values according to 36.331 and 38.331 v15.1.0 | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.508-1 | The RAN5 progress for this task will depend on the RAN2 progress of TS 36.331 v15.1.0, TS 38.331 v15.1.0 | Ericsson | Bo Jönsson, Ericsson | Open | Note! This task is limited to the generic procedures for RRC_IDLE and RRC_CONNECTED state.
78#G03 | Draft common procedures for TS 38.508-1 clause 4.8, not covered by generic procedures for RRC_IDL and RRC_Connected generic procedures in clause 4.5, but needed for a set of test cases. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.508-1 |  | Test Case authors | Bo Jönsson, Ericsson | Open | Note! First step could be to include the details in the test cases followed by creating the common procedure in clause 4.8 as second step.
78#G04 | Get companies assigned to not yet assigned 38.501-1 areas | High | 2018-03-12 | NSA Op3 Ph1 | TS 38.508-1 | Companies not coming forward to get test cases assigned | Ericsson | Bo Jönsson, Ericsson | Open
78#G05 | Draft Radio conditions (cl 4.3.1), Physical channel allocations (cl 4.3.3), Signal levels (cl 4.3.4), Reference system configurations (cl 4.4) and Connection Diagrams (Annex A) for EN-DC (this also includes possible specific RF and signalling specific information in chapter 5 for RF and in chapter 6 for signalling) | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.508-1 | RAN4 progress of version v15.1.0 for TS 38.101-1, TS 38.101-2, TS 38.101-3. | Pending assignments | Bo Jönsson, Ericsson | Open | The RAN5 progress for this task will depend on; companies coming forward to get areas assigned
78#R01 | Kick off email discussion about the WP of working on MU and TT, and how to accommodate the MU and TT work in TS 36.903. | High | 2018-03-23 | NSA Op3 Ph1 | TR 38.903 |  | Rohde & Schwarz, Keysight, Anritsu | Chunying Gu, Huawei | Open
78#R02 | Update the draft TS 36.903 skeleton according to the output of email discussion. | High | 2018-04-04 | NSA Op3 Ph1 | TR 38.903 |  | Huawei | Chunying Gu, Huawei | Open
78#R03 | Focusing on TCs 6.2.1 (UE maximum output power) and 7.3 (REFSENS). Provide inputs. | High | 2018-04-04 | NSA Op3 Ph1 | TR 38.903 |  | Rohde & Schwarz, Keysight, Anritsu | Chunying Gu, Huawei | Open
78#R04 | FR1: Draft Discussion paper with a text proposal to TR 38.905 on how to document the RX and TX test point selections for FR1. | High | 2018-04-04 | NSA Op3 Ph1 | TR 38.905 | N/A | Ericsson | Mats Johansson, Ericsson | Open
78#R05 | FR1: Draft General clauses 2 to 4 and Annexes for FR1 to enable approval of TS 38.521-1 as v15.0.0 at RAN#80 in June-18. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-1 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-1 v15.1.0 | Bureau Veritas + TBD (for Annexes) | Geng Su, CATR | Open
78#R06 | Get companies assigned to draft the Annexes A-C in TS 38.521-1 | High | 2018-03-12 | NSA Op3 Ph1 | TS 38.521-1 | Companies not coming forward to get test cases assigned | Geng Su, CATR | Dan Song, China Mobile | Open
78#R07 | FR1: Draft Operating bands, bandwidth and channel arrangements for NR FR1 and NR-CA FR1 (chapter 5) that will be referenced by NSA Option 3 phase 1 EN-DC test cases in TS 38.521-3. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-1 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-1 v15.1.0 | China Unicom | Geng Su, CATR | Open
78#R08 | FR1: Complete the minimum requirements and test requirement in Tx test cases (chapter 6) for FR1 that will be referenced by NSA Option 3 phase 1 EN-DC Tx test cases in TS 38.521-3. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-1 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-1 v15.1.0 | Huawei, CATR, Ericsson, KTL, MTCC, Rohde & Schwarz, Keysight, Qualcomm + TBD for not yet assigned TCs | Geng Su, CATR | Open
78#R09 | Get companies assigned to draft the remaining Tx FR1 test cases for NR and NR-CA planed to be included in TS 38.521-1 | High | 2018-03-12 | NSA Op3 Ph1 | TS 38.521-1 | Companies not coming forward to get test cases assigned | Geng Su, CATR | Dan Song, China Mobile | Open
78#R10 | FR1: Complete the minimum requirements and test requirement in Rx test cases (chapter 7) for FR1 that will be referenced by NSA Option 3 phase 1 EN-DC test cases in TS 38.521-3. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-1 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-1 v15.1.0 | China Unicom, Qualcomm, CATR, Keysight + TBD for not yet assigned TCs | Geng Su, CATR | Open
78#R11 | Get companies assigned to draft the remaining Rx FR1 test cases for NR and NR-CA planed to be included in TS 38.521-1 | High | 2018-03-12 | NSA Op3 Ph1 | TS 38.521-1 |  | Geng Su, CATR | Dan Song, China Mobile | Open
78#R12 | FR2: Draft General clauses 2 to 3 and Annexes for FR2 to enable approval of TS 38.521-2 as v15.0.0 at RAN#80 in June-18. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-2 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-2 v15.1.0 | CATR | Yufeng Zhang, CATR | Open
78#R13 | Get companies assigned to draft the General clauses 4 in TS 38.521-2 | High | 2018-03-12 | NSA Op3 Ph1 | TS 38.521-2 |  | Yufeng Zhang, CATR | Dan Song, China Mobile | Open
78#R14 | FR2: Draft Annexes A to C for FR2 to enable approval of TS 38.521-2 as v15.0.0 at RAN#80 in June-18. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-2 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-2 v15.1.0 | Bureau Veritas | Yufeng Zhang, CATR | Open
78#R15 | FR2: Draft Operating bands, bandwidth and channel arrangements for NR FR2 and NR-CA FR2 (chapter 5) that will be referenced by NSA Option 3 phase 1 EN-DC test cases in TS 38.521-3. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-2 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-2 v15.1.0 | CATR | Yufeng Zhang, CATR | Open | This chapter 5
78#R16 | FR2: Draft Minimum requirements and test requirement in Tx test cases (chapter 6) for FR2 that will be referenced by NSA Option 3 phase 1 EN-DC test cases in TS 38.521-3. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-2 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-2 v15.1.0 | Ericsson,CATR, Huawei, KTL, MTCC, Rohde & Schwarz, Keysight, Anritsu + TBD for not yet assigned TCs | Yufeng Zhang, CATR | Open
78#R17 | Get companies assigned to draft the remaining Option 3 phase 1 Tx test cases NR and NR-CA planed to be included in TS 38.521-2 | High | 2018-03-12 | NSA Op3 Ph1 | TS 38.521-2 | Companies not coming forward to get test cases assigned | Yufeng Zhang, CATR | Dan Song, China Mobile | Open
78#R18 | FR2: Draft Minimum requirements and test requirement in Rx test cases (chapter 7) for FR2 that will be referenced by NSA Option 3 phase 1 EN-DC test cases in TS 38.521-3. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-2 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-2 v15.1.0 | Qualcomm, CATR, Keysight, Anritsu + TBD for not yet assigned TCs | Yufeng Zhang, CATR | Open | 2018-04-04
78#R19 | Get companies assigned to draft the remaining Option 3 phase 1 Rx test cases NR and NR-CA planed to be included in TS 38.521-2 | High | 2018-03-12 | NSA Op3 Ph1 | TS 38.521-2 | Companies not coming forward to get test cases assigned | Yufeng Zhang, CATR | Dan Song, China Mobile | Open
78#R20 | LTE+FRx: Update General clauses 2 to 4 and Annexes for EN-DC to enable to approval TS 38.521-3 as v15.0.0 at RAN#80 in June-18. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-3 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-3 v15.1.0 | Qualcomm | Mayur Vora, Qualcomm | Open
78#R21 | Get companies assigned to draft the Annexes in TS 38.521-3 | High | 2018-03-12 | NSA Op3 Ph1 | TS 38.521-3 | Companies not coming forward to get test cases assigned | Mayur Vora, Qualcomm | Dan Song, China Mobile | Open
78#R22 | LTE+FRx: Update Operating bands, bandwidth and channel arrangements for EN-DC (chapter 5). | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-3 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-3 v15.1.0 | Qualcomm, Bureau Veritas | Mayur Vora, Qualcomm | Open
78#R23 | LTE+FR1: Update of phase 1 Tx test cases (chapter 6) for EN-DC | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-3 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-3 v15.1.0 | Qualcomm, Ericsson,CATR, Keysight + TBD for not yet assigned TCs | Mayur Vora, Qualcomm | Open
78#R24 | LTE+FR2: Update of phase 1 Tx test cases (chapter 6) for EN-DC | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-3 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-3 v15.1.0 | Qualcomm, Ericsson,CATR, Keysight + TBD for not yet assigned TCs | Mayur Vora, Qualcomm | Open
78#R25 | Get companies assigned to draft the remaining Option 3 phase 1 Tx test cases for EN_DC planed to be included in TS 38.521-2 | High | 2018-03-12 | NSA Op3 Ph1 | TS 38.521-3 | Companies not coming forward to get test cases assigned | Mayur Vora, Qualcomm | Dan Song, China Mobile | Open
78#R26 | LTE+FR1: Update of phase 1 Rx test cases (chapter 7) for EN-DC | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-3 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-3 v15.1.0 | Qualcomm + TBD for not yet assigned TCs | Mayur Vora, Qualcomm | Open
78#R27 | LTE+FR2: Update of phase 1 Rx test cases (chapter 7) for EN-DC | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.521-3 | The RAN5 progress for this task will depend on the RAN4 progress of TS 38.101-3 v15.1.0 | Qualcomm + TBD for not yet assigned TCs | Mayur Vora, Qualcomm | Open
78#R28 | Get companies assigned to draft the remaining Option 3 phase 1 Rx test cases for EN_DC planed to be included in TS 38.521-2 | High | 2018-03-12 | NSA Op3 Ph1 | TS 38.521-3 | Companies not coming forward to get test cases assigned | Mayur Vora, Qualcomm | Dan Song, China Mobile | Open
78#R29 | Formulate the test procedure for UE best beam selection during initial call setup | High | 2018-04-04 | See Comments | TS 38.521-4 |  | Qualcomm, Keysight, Rohde & Schwarz, Anritsu | Vijay Balasubramanian, Qualcomm | Open | stage1 of WF on mmWave demod testing
78#R30 | Formulate the test function for RSRP per branch UE reporting | High | 2018-04-04 | See Comments | TS 38.521-4 | LS from RAN4 on RSRP per branch | Qualcomm, Keysight, Rohde & Schwarz, Anritsu | Vijay Balasubramanian, Qualcomm | Open | part of stage2 of WF on mmWave demod testing
78#R31 | Report on RAN4 progress in RRM Testability and core requirement definition | Mid | 2018-04-04 | See Comments | TS 38.533 |  | R&S | Adrian Cardalda-Garcia, Rohde & Schwarz | Open | 5G area not yet defined
78#R32 | Analyse the LTE Legacy RRM scenarios and how could they be translated into NR scenarios; Provide overview. | Mid | 2018-04-04 | NSA Op3 Ph2 | TS 38.533 |  | R&S | Adrian Cardalda-Garcia, Rohde & Schwarz | Open
78#S01 | Progress discussion on OTA Chamber requirements for signalling purposes. Consideration of near field as well as far field measurements. | High | 2018-04-04 | NSA Op3 Ph1 | See Comments |  | Mohit Kanchan, Keysight Yogesh Tugnawat, Qualcomm | Leif Mattisson, Ericsson | Open | Impact testability for FR2 bands.
78#S02 | Arrange conference call for OTA SIG topic. The invitation to be sent out on the 5G_NR reflector | High | 2018-03-19 | NSA Op3 Ph1 | See Comments |  | Ericsson | Leif Mattisson, Ericsson | Open | Impact testability for FR2 bands.
78#S03 | Provide answers to the question in R5-181283 in regard to Numerology: Which numerology(ies) / sub-carrier spacing will RAN5 use for SIG TCs? Any default numerology in 38.508-1? | High | 2018-03-18 | NSA Op3 Ph1 | TS 38.508-1 |  | Leif Mattisson, Ericsson | Bo Jönsson, Ericsson | Open | Test model needed
78#S04 | Provide answers to the question in R5-181283 in regard to Bandwidth Parts (BWPs): How many BWPs will be used for SIG TCs? Default BWP(s)? Size of each BWP? Same or different numerology for each BWP? | High | 2018-03-18 | NSA Op3 Ph1 | TS 38.508-1 |  | Leif Mattisson, Ericsson | Bo Jönsson, Ericsson | Open | Test model needed
78#S05 | Define PICS to enable definition of TC applicability | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.508-2 | Availability of RAN2 ASN.1 and UE Capability spec 38.306 | Motorola Mobility | Abdul Rasheed Mohammed, Motorola Mobility | Open
78#S06 | Update of EN-DC related corrections for Loopback Modes | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.509 |  | Leif Mattisson, Ericsson | Stoyan Baev, Samsung | Open
78#S07 | Investigate and implement potential test case optimizations in Work Plan | High | 2018-03-12 | NSA Op3 Ph1 | TS 38.523-1 |  | Ericsson | Calle Hagenfeldt, Ericsson | Open
78#S08 | Complete the EPC protocol test cases for NSA option 3 | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.523-1 |  | Ericsson | Calle Hagenfeldt, Ericsson | Open
78#S09 | Update Signalling RRC WP to latest RAN2 specs - 36.331 and 38.331 | High | 2018-03-18 | NSA Op3 Ph1 | TS 38.523-1 |  | yogesh tugnawat, Qualcomm | Leif Mattisson, Ericsson | Open
78#S10 | Get companies assigned to draft the remaining Option 3 phase 1 Test cases for RRC WP | High | 2018-03-18 | NSA Op3 Ph1 | TS 38.523-1 |  | yogesh tugnawat, Qualcomm | Leif Mattisson, Ericsson | Open
78#S11 | Update all already drafted RRC TCs to reflect the latest RAN2 changes and resolve open issues. Wherever possible do not wait for RAN2 spec update - used agreed at the RAN2 Athens meeting CR. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.523-1 |  | TC Owners | Yogesh Tugnawat, Qualcomm | Open
78#S12 | Draft at least 30% of the remaining new RRC TCs. Wherever possible do not wait for RAN2 spec update - used agreed at the RAN2 Athens meeting CR. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.523-1 |  | TC Owners | Yogesh Tugnawat, Qualcomm | Open | The list with new TCs to be drafted shall be provided latest by 16.03.2018
78#S13 | Update work plan to align with the latest RAN2 changes which are quite drastic, find coverage gaps | High | 2018-03-26 | NSA Op3 Ph1 | TS 38.523-1 | Availability of RAN2 draft specs | Motorola Mobility | Abdul Rasheed Mohammed, Motorola Mobility | Open
78#S14 | Get companies assigned to not yet assigned 21 out of 64 test cases | High | 2018-03-12 | NSA Op3 Ph1 | TS 38.523-1 | Companies not coming forward to get test cases assigned | Motorola Mobility | Abdul Rasheed Mohammed, Motorola Mobility | Open
78#S15 | Resolve specific message content, Test procedure issues of 26 available test cases and move the status from 40% to 75% | Mid | 2018-04-04 | NSA Op3 Ph1 | TS 38.523-1 | Availability of RAN2 ASN.1 progress of default message contents | Motorola Mobility, Qualcomm, KeySight, Anritsu | Abdul Rasheed Mohammed, Motorola Mobility | Open
78#S16 | Come up with prose for DCH assignment test cases as it will in turn be used in every test case by MCC 160 | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.523-1 | Any RAN1 dependencies | Motorola Mobility | Abdul Rasheed Mohammed, Motorola Mobility | Open
78#S17 | Draft at least 50% of the remaining new L2 TCs. Wherever possible do not wait for RAN2 spec update - used agreed at the RAN2 Athens meeting CR. | High | 2018-04-04 | NSA Op3 Ph1 | TS 38.523-1 |  | TC Owners | Abdul Rasheed Mohammed, Motorola Mobility | Open | The list with new TCs to be drafted shall be provided latest by 16.03.2018
78#S18 | TF160 to provide outcome of study into implementation options of RAN5 decision on R5-181169. Determine impact to Prose CR, so this can be addressed in Adhoc meeting. | High | 2018-03-24 | NSA Op3 Ph1 | TS 38.523-1 |  | Olivier Genoud, MCC TF160 | Yogesh Tugnawat, Qualcomm | Open
78#S19 | Bring in applicability spec with previous TC added as per RAN5#78 | Mid | 2018-04-04 | NSA Op3 Ph1 | TS 38.523-2 |  | Ankit Banaudha, Qualcomm | Yogesh Tugnawat, Qualcomm | Open
78#S20 | Come up with basic selection expressions needed for Layer 2 test cases | Mid | 2018-04-04 | NSA Op3 Ph1 | TS 38.523-2 | Availability of RAN2 ASN.1 and UE Capability spec 38.306 | Motorola Mobility | Abdul Rasheed Mohammed, Motorola Mobility | Open
Note on A1: The left most 2 char = the RAN5 meeting number at which the plan was endorsed. Examples: 78#G01 (G for General) 78#R01 (R for RF subWG) 78#S01 (S for SIG subWG) A2#R01 (A for AdHoc)
Note on G1: Describe if the completion of the task depends on work outside of RAN5, e.g. RAN4, CT1, GCF, etc. Indicate WHEN the work in the external group is expected to be completed.

## Settings
Priority | 5GArea | Specification | Supervisor | CompletionStatus
High | NSA Op3 Ph1 | TS 38.508-1 | Abdul Rasheed Mohammed, Motorola Mobility | Open
Mid | NSA Op3 Ph2 | TS 38.508-2 | Adrian Cardalda-Garcia, Rohde & Schwarz | In-Progress
Low | NSA Op7 Ph1 | TS 38.509 | Bo Jönsson, Ericsson | Completed
| SA Op2 Ph1 | TS 38.521-1 | Calle Hagenfeldt, Ericsson | Closed - see comments
| SA Op5 Ph1 | TS 38.521-2 | Chunying Gu, Huawei
| See Comments | TS 38.521-3 | Dan Song, China Mobile
|  | TS 38.521-4 | Geng Su, CATR
|  | TS 38.522 | Holger Jauch, Rohde & Schwarz
|  | TS 38.533 | Leif Mattisson, Ericsson
|  | TR 38.903 | Mats Johansson, Ericsson
|  | TR 38.905 | Mayur Vora, Qualcomm
|  | TS 38.523-1 | Olivier Genoud, MCC TF160
|  | TS 38.523-2 | Stoyan Baev, Samsung
|  | TS 38.523-3 | Vijay Balasubramanian, Qualcomm
|  | TS 36.508 | Xiaozhong Chen, CATT
|  | TS 36.509 | Yogesh Tugnawat, Qualcomm
|  | TS 36.523-1 | Yufeng Zhang, CATR
|  | TS 36.523-2 | See Comments
TS 36.523-3
TS 34.229-1
TS 34.229-2
TS 34.229-3
TS 37.571-1
TS 37.571-2
TS 37.571-3
TS 37.571-4
TS 37.571-5
See Comments

## Guide how to fill
Column | How to Fill Guide
Task ID | Do not write anything here. I'll assign those when I have all tasks put together.
Task Description | Describe the tasks in words which would allow us to be able to verify if what was written as a task was achieved at the target date specified.
Priority | Chose one of the Priorities provided by a drop-down menu when you click on the cell in that column. You should base your choice on the possible impact the task may have on other tasks, or, on the overall completion of the RAN5 5G work in accordance with what RAN5 has agreed. Please avoid putting in personal preferences.
Compl. Target yyyy-mm-dd | Set an exact date for target completion of the task. The Idea is that for example a task may need to be ready 2 week before the meeting in order to allow people to take it into account and produce contributions for the meeting, still on time.
5GArea | Chose one of the 5GArea provided by a drop-down menu when you click on the cell in that column. These are the same as those used in the WP.
If for whatever reason you cannot chose one then select the "See Comments" and provide the clarification in the column "Comments".
Specification | Chose one of the Specification provided by a drop-down menu when you click on the cell in that column.
If for whatever reason you cannot chose one then select the "See Comments" and provide the clarification in the column "Comments".
External Dependency | Describe any dependency the task completion may have on work done e.g. in RAN4, RAN2, CT1, GCF, etc. Indicate the type of work expected, and, when the work in the external group is expected to be done
Owner (Company) | Specify the Company (or Companies) which are expected to do the job the task describes
Supervisor | Chose one of the Supervisors provided by a drop-down menu when you click on the cell in that column. This is one of you the (sub)Rapporteurs.
If for whatever reason you cannot chose one then select the "See Comments" and provide the clarification in the column "Comments".
Completion status | Chose one of the Completion status provided by a drop-down menu when you click on the cell in that column. At this moment of time, all of them will be Open - from the next meeting we will use also when appropriate the other from the list.
Comments | Add anything you think my facilitate the understanding of the task. Especially add clarification if you have chose in one of the drop-down lists the entry "See Comments"