## Sheet1
RAN5 5GS AP list
AP-5G# | WG | Area | Description | AP Owner(s) | Comments | Status | Start date | Target / End date
1 | RF+SIG | RAN1 | DCI formats and information about transport block size to be used for NR is missing in RAN1 specifications. This is basic information critical to be available in the RAN1 NR TSs after RAN1#91 (Nov-17) to progress of RAN5 work. Check with RAN1 when this information will be available. If needed, RAN5 chair to inform RAN1 chair before RAN1#91 (Nov-17) about the RAN5 needs. | Ericsson (Leif Mattisson), RAN5 chair (Jacob John) | RAN1 chair feedback: DCI format and TBS formula are progressing and aim is to have then ready by Dec 2017 (subject to further corrections) | Closed | 2017-11-02 | 2017-11-15
2 | RF+SIG | RAN1, RAN2 | L1\L2 layer parameters still not defined, this will impact overall SIG progress. Check with RAN1 & RAN2 when this will be included in RAN1 and RAN2 draft TSs. If needed, RAN5 chair to inform RAN1 and RAN2 chair before RAN1#91 and RAN2#100 (Nov-17) about the RAN5 needs. | Ericsson (Leif Mattisson), RAN5 chair (Jacob John) | RAN1/RAN2 chairs feedback: L1 and L2 parameters (and complete RRC for LTE/NR dual connectivity) should be available in RAN1 and RAN2 specifications by Dec 2017. Corrections are expected at the ASN.1 freeze in March 2018. | Closed | 2017-11-02 | 2017-11-15
3 | RF | RAN4 | To progress RAN5 RF for Option 3 at the RAN5 ad-hoc#1 (16-19 Jan 2018) it is necessary to clarify which specs (TS38.101-1/2/3) are capturing the requirements for NSA and it is critical that TSs or the associated TRs will become available after the RAN4#85 meeting in Reno. RAN4 needs to be informed about this before RAN4#85. If needed, RAN5 chair to inform RAN4 chair before RAN4#85 (Nov-17) about the RAN5 needs. | CMCC (Jinqiang Xing), Qualcomm (Pradeep Gowda), RAN5 chair (Jacob John) | RAN4 chair feedback: For the Jan ad-hoc RAN5 could start the work for NR FR1 (Below 6GHz) which is highly possible to be completed in RAN4 by Nov meeting. For FR2, some inter-WG working between RAN4 and RAN5 are needed to finalize the remaining core requirements for FR2 in Q1 2018. | Closed | 2017-11-02 | 2017-11-15
4 | SIG | RAN2 | Which encryption and integrity protection algorithms will be used for NR? Need to check with RAN2 when this will be decided. | Qualcomm (Yogesh Tugnawat) | RAN2 agreed that a PDCP associated with KeNB can be configured with one of the LTE algorithms only and a PDCP associated with S-KgNB can be configured with one of the NR algorithms only, regardless of PDCP version. | Closed | 2017-11-02 | 2017-11-11
5 | SIG | RAN2 | Is support of NR-PDCP on MCG split bearer mandatory or optional? If optional this will result in NR-PDCP test cases will be optional for NSA option 3. Need to be confirmed with RAN2. | Qualcomm (Yogesh Tugnawat) | Support of NR PDCP for split bearer is mandatory requirement as split bearer is always configured with NR PDCP. | Closed | 2017-11-02 | 2017-11-11
6 | SIG | RAN2 | Uplink Switching for Split Bearer options - Is it controlled by NW? | Qualcomm (Yogesh Tugnawat) | RAN2 U-plane session made an agreement how to configure the UL switching. Agreed that signaling allows RAN to configure either UL aggregation or UL switching. But the spec update part is to be discussed in the C-plane session (i.e. the final conclusion hasn’t yet been made). | Ongoing | 2017-11-02 | RAN5#78
7 | SIG | UE test functions | Update the Discussion paper for checking UE's IP stack, add some examples. | Qualcomm (Yogesh Tugnawat) | Qualcomm’s discussion paper in R5-176379 was noted. RAN5 doesn't see this as a priority at this time for 5GS. May need industry feedback before pursuing further on this. | Closed | 2017-11-02 | 2017-12-01
8 | RF+SIG | UE test functions | Rapporteurs need to collect requirements (and possible operation) for loopback modes based on their test case requirement and inform TS 38.509 rapporteur (Stoyan Baev, Samsung) | WP sub-area rapporteurs | Current identified test functions are at RAN5#77: 1. UE beamlock function (ref R5-176996). 2. UE test loop mode A and B in 36.509 are transperant for radio access and can be used for NR (R5-176414). | Ongoing | 2017-11-02 | RAN5#78
9 | SIG | EN-DC | RAN5 assumption is that all options for EN-DC needs to be considered (3, 3a, 3x). Further confirmation needed? | Qualcomm (Yogesh Tugnawat) | Yes, all options are still valid. | Ongoing | 2017-11-02 | RAN5#78
10 | SIG | EN-DC | Discuss complexities due to testing of several bearer options for EN-DC. | Qualcomm (Yogesh Tugnawat) | Qualcomm’s discussion paper in R5-176382 and Ericsson discussion paper R5-176234 proposed using generic procedures (to be defined in 38.508) to reduce the number of test cases, as way forward. | Closed | 2017-11-02 | 2017-12-01
11 | SIG | UE test functions | UE beamlock function, will it be needed for signaling? RAN5 need to evaluate. | Keysight (Mohit. Kanchan), Ericsson (Leif Mattisson) | RAN#77 (Nov-17): There was a discussion paper in R5-176996 at RAN5#77 introducing the UE beamlock function in 38.509. The scope of this function is agreed to be for RF test cases now. The paper discussed the scope of the UE beamlock function for Signaling test cases as well. As per the discussions UE Beamlock function for signaling test cases can be perceived to provide reliable test environment. However it would require further investigation to ascertain the benefits and if it is found feasible then the scope needs to be finalized as it may not be applicable for all kind of signaling scenarios. As per the agreement the decision to make UE beamlock function applicable for Signaling test cases does not need to be made now. Pre-RAN5#78 (Feb-18): The applicability of UE beamlock function would depend upon the OTA test setup requirements that gets agreed upon for Signaling test cases. The OTA test setup requirements are under discussion, UBF applicability decision postponed till OTA test setup requirements are finalized. | Ongoing | 2017-11-02 | RAN5#78
12 | SIG | SIG OTA | Evaluate means for performing protocol testing for UEs only supporting NR mmWave bands. Must OTA chambers as used for RF/RRM for NR mmWave frequencies be used?; or can "simpler" means be used considering that protocol testing is functional? Discussions from OTA discussions in the RF group to be included in RF/SIG joint session. | Anritsu (Kalahasti, Narendra), Qualcomm (Pradeep Gowda) | Discussion at RAN5#77 concluded with initial understanding on This was discussed as part of R5-176915 at RAN5#77. The purpose of this paper is to determine the key aspects that need to be considered for OTA chamber in case of signalling test cases. It has discussed three key aspects far-field measurements, positioning sytem and N sets of cross-polarised antennas transmitting the signals from the emulated gNB sources to the DUT. RAN5 has reached to an basic assumption regarding the baseline for OTA chamber in case of signalling testcases that it does not need to consider far-field measurements and positioning system. It is further need to investigated regarding maximum number of inter-bands mmWave Cells/maximum different beams per cell required for NR signalling testcases. | Ongoing | 2017-11-02 | RAN5#78
13 | RF | RF OTA | Ensure reliability of the LTE OTA link: 1. Define appropriate DL power, TM mode, MCS 2. No DL or UL grants after 5G-NR connection setup. Do we require active 5G-NR signaling over LTE link which would need LTE DL/UL Traffic? 3. Impact to OTA chamber dimensions due to OTA LTE 4. Impact of multipath due to reflections for OTA LTE | Qualcomm (Vijay Balasubramanian), SS vendors | Qualcomm submitted a discussion paper at RAN5#77 in R5-176599 on the considerations of having LTE anchor as OTA for mmWave testing. Following is the summary along with proposals endorsed. Details are captured in the final tdoc (R5-177455) LTE OTA anchor can successfully co-exist with mmW link for NSA test environment, provided the Tx/Rx for LTE link are within defined dynamic range and is maintained without degrading mmW performance. Interested companies are requested to bring supporting documents on the feasibility of implementing these DL and UL power configuration. Proposal 1: Use proposed Tx/Rx power range as baseline assumption to maintain a robust LTE link, irrespective of OTA degradations. Proposal 2: Disable LTE-DL/UL allocation for RF test cases after establishing the mmW link, to avoid LTE-Tx/Rx interference on mmW. Disable LTE-DL/UL allocation for RRM test cases is FFS Baseline assumption as part of prop1 is 10MHz LTE channel BW, DL RSRP of -85 dBm, 10 dBm Tx Power, 0 RB DL/UL allocation after LTE and 5G connection setup, use of circular polarized or dual polarized link antenna. | Ongoing | 2017-11-02 | RAN5#78
14 | RF | RAN4 | UE beam lock function (UBF) for RF/RRM mmwOTA tests. Way fwd to be finalized by Ran5, but need RAN4 input on the requirements that will need UBF, to help RAN5 define the UBF aspects. LS input from RAN4 on the need for UBF to RAN5#77. RAN5 need to request further details from RAN4 in the response LS to RAN4 to be able to define the details in 38.509. | Keysight (Emilio Ruiz), Qualcomm (Pradeep Gowda) | Discussion paper R5-176996 (remove proposals not endorsed by RF session) and proposals are endorsed . Proposals are implemented in R5-176997, UBF function definition is added in 38.509 and specific messages are created. Definition of message type and message content is FFS and UBF messages definition over LTE link in NSA mode is FFS as well*. *) A text proposal to TS 38.509 will be submitted by Ericsson for RAN5#78 to resolve how Test Control message is to be handled depending of 5GS connectivity option. | Ongoing | 2017-11-02 | RAN5#78
15 | RF+SIG | Inter-RAT GSM/UTRA | Ensure that relevant sub-are WPs takes GSM/UTRA interoperability into account (Ref: RAN LS in RP-172823) w.r.t.: For E-UTRA deployments with 5GC (i.e. deployment Options 5 and 7), Access-Stratum interworking between GSM/UMTS and E-UTRA continues to be possible without changes to GSM/UMTS/E-UTRAN specifications, enabling: - Idle mode cell reselection - Connected mode measurements to support redirection at RRC connection release, CS call release, TBF release once in idle mode For EN-DC (i.e. deployment Option 3), legacy EPS/E-UTRA interworking with GSM/UMTS shall be fully supported. This includes e.g. handover perspective impacting PDCP, RRC and multi-layer test cases. Impacted WPs: - Protocol Idle Mode - Protocol L2 - Protocol RRC - RRM | RRC/idle mode: Yogesh Tugnawat, Qualcomm Protocol L2: Mohammead, Abdul Rasheed RRM: Adrian Cardalda-Garcia , Rohde & Schwarz | Pre-RAN5#78 (Feb-18): - RRC/idle mode & Protocol L2: The assumption is that the RRM test cases will provide the necessary test coverage. - RRM: RAN4 has discussed the issue and the assumption is that the same inter-RAT requirements applicable to LTE, will also apply for Option 3. RAN4 will make the necessary changes in spec (with respect to number of carriers to monitor, etc) to reflect this. From RAN5 side, we can expect the same legacy inter-RAT test cases (re-selection, handover, re-direction, event triggered measurements) to be required also for Option 3. When RAN4 discussion have been concluded the necessary test cases will be include the RRM Work Plan. | Not started | 2018-01-12 | RAN5#78
16 | RF+SIG | L1/L2 parameters | Investigate how to achieve necessary test coverage of NR L1/L2 parameters (LTE was ~140, NR is ~470) considering NR RF, RRM and protocol test cases. | Leif Mattisson, Ericsson |  | Not started | 2018-01-12 | RAN5#79